## vpis
Doc. No. | Rev. | Title | Requisition No. | Vendor Name | Plan Received Date | Vendor Upload Date | Vendor Issued Date | Issued By Vendor | Vendor Delay | PIDEC Comment Date(EDMS3) | PIDEC No Comment Date(EDMS3) | PIDEC No Comment Date | PIDEC Minor Comment Date | PIDEC Major Comment Date | PIDEC Information Comment Date | PIDEC Reject Comment Date | PIDEC RE Email Date | PIDEC RTS Email Date | Replied By PIDEC | Originator Delay | viewed By | Viewd Date | Employer External Comment Date | Employer External Approval Date
VD-9001-213B-CAL-001 | 0 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-01-10 | 2013-10-20 15:43 |  | No | 283 | 2013-11-19 10:24 | [8 empty] | No | 0
VD-9001-213B-CAL-002 | 0 | Roof Structure Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-05-10 | 2013-10-20 15:43 |  | No | 163 | 2013-11-20 15:57 | [8 empty] | No | 0
VD-9001-213B-CAL-003 | 0 | Roof Structure Lifting Calculation for Erection. For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-01 | 2014-05-10 12:21 |  | No | 9 | 2014-05-17 09:56 | [8 empty] | No | 0
VD-9001-213B-CAL-004 | 0 | Nozzle Load Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-10-11 | 2014-09-23 14:07 |  | No | 347 | 2014-10-11 15:18 | [8 empty] | No | 0
VD-9001-213B-CAL-005 | 0 | Pipe Support Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-15 | 2014-09-24 15:44 |  | No | 313 | 2014-10-11 14:47 | [8 empty] | No | 0
VD-9001-213B-MTO-006 | 0 | MTO for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-01-11 |  |  | No | 2716 | [9 empty] | No | 0
VD-9001-213B-PCJ-007 | 0 | Roof structure Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-01 | 2016-09-10 07:51 |  | No | 863 | 2016-09-25 09:44 | [7 empty] | 2016-09-25 18:56 | Yes | 0
VD-9001-213B-ITP-008 | 0 | Inspection & Test Plan for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2013-12-11 08:22 |  | No | -21 | 2013-12-17 14:34 | [8 empty] | No | 0
VD-9001-213B-QCP-009 | 0 | Quality Control Plan for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 |  |  | No | 2361 | [9 empty] | No | 0
VD-9001-213B-WPS-010 | 0 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-04-20 12:21 |  | No | 109 | 2014-05-25 17:10 | [8 empty] | No | 0
VD-9001-213B-PQR-011 | 0 | PQR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-04-20 12:23 |  | No | 109 | 2014-06-22 12:15 | [8 empty] | No | 0
VD-9001-213B-PCJ-012 | 0 | Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-04-17 09:36 |  | No | 106 | 2014-10-06 10:28 | [8 empty] | No | 0
VD-9001-213AB-PCJ-013 | 0 | Hydro Test and Air Test Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-02-17 11:08 |  | No | 47 | 2014-04-19 15:57 | [8 empty] | No | 0
VD-9001-213B-PCJ-014 | 0 | NDT Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-02-23 12:53 |  | No | 53 | 2014-04-13 09:20 | [8 empty] | No | 0
VD-9001-213B-WMP-015 | 0 | Welding Maps for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-07-06 07:57 |  | No | 186 | 2014-07-23 10:53 | [8 empty] | No | 0
VD-9001-213B-PCJ-016 | 0 | Painting & Pickling and Passivation procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-04-06 13:05 |  | No | 95 | 2014-04-12 18:00 | [8 empty] | No | 0
VD-9001-213B-LST-017 | 0 | SPLIR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 |  |  | No | 2361 | [9 empty] | No | 0
VD-9001-213B-DWG-018 | 0 | General Assembly for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-15 | 2014-06-19 09:00 |  | No | 155 | 2014-07-10 12:43 | [8 empty] | No | 0
VD-9001-213B-DWG-019 | 0 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-15 | 2014-01-22 15:11 |  | No | 68 | 2014-01-28 16:37 | [8 empty] | No | 0
VD-9001-213B-DWG-020 | 0 | Bottom Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-10-25 | 2013-11-19 13:53 |  | No | 25 | 2013-12-08 10:39 | [8 empty] | No | 0
VD-9001-213B-DWG-021 | 0 | Fixed Roof Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-20 | 2014-04-20 06:57 |  | No | 151 | 2014-06-14 17:02 | [8 empty] | No | 0
VD-9001-213B-DWG-022 | 0 | Fixed Roof Orientation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-20 | 2014-04-20 06:58 |  | No | 151 | 2014-06-12 10:55 | [8 empty] | No | 0
VD-9001-213B-DWG-023 | 0 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-10-15 | 2013-10-20 15:43 |  | No | 5 | 2013-11-25 11:26 | [8 empty] | No | 0
VD-9001-213B-DWG-024 | 0 | Spiral Stairway For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-03 | 2014-06-19 09:02 |  | No | 167 | 2014-07-08 10:14 | [8 empty] | No | 0
VD-9001-213B-DWG-025 | 0 | Walkway With Handrail for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-03 | 2014-08-20 08:27 | 2014-08-20 09:49 | Yes | 229 |  | 2014-09-06 16:47 | [6 empty] | 2014-09-06 16:48 | Yes | 3
VD-9001-213B-DWG-026 | 0 | Wind Girder for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-10-11 | 2014-06-08 06:44 |  | No | 240 | 2014-06-22 15:34 | [8 empty] | No | 0
VD-9001-213B-DWG-027 | 0 | Shell Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-30 | 2014-01-04 16:43 |  | No | 35 | 2014-05-18 12:19 | [8 empty] | No | 0
VD-9001-213B-DWG-028 | 0 | Roof Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-30 | 2014-02-10 16:43 |  | No | 72 | 2014-04-26 12:40 | [8 empty] | No | 0
VD-9001-213B-DWG-029 | 0 | Shell Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-30 | 2014-02-18 08:14 |  | No | 80 | 2014-03-16 15:17 | [8 empty] | No | 0
VD-9001-213B-DWG-030 | 0 | Roof Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-11-30 | 2014-02-15 17:05 |  | No | 77 | 2014-03-16 15:15 | [8 empty] | No | 0
VD-9001-213B-DWG-031 | 0 | Drain Sump for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2013-12-04 14:04 |  | No | -28 | 2013-12-16 09:30 | [8 empty] | No | 0
VD-9001-213B-DWG-032 | 0 | Anchor Chair for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-12 | 2014-02-26 15:56 |  | No | 76 | 2014-03-15 14:17 | [8 empty] | No | 0
VD-9001-213B-DWG-033 | 0 | Earth Lug for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-02-23 09:57 |  | No | 53 | 2014-03-15 14:27 | [8 empty] | No | 0
VD-9001-213B-DWG-034 | 0 | Name Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-01 | 2014-04-16 16:32 |  | No | 105 | 2014-05-07 14:25 | [8 empty] | No | 0
VD-9001-213B-DWG-035 | 0 | Pipe Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-15 | 2015-08-25 18:20 |  | No | 556 | 2015-09-06 10:40 | [8 empty] | No | 0
VD-9001-213B-DWG-036 | 0 | Instrument Cable Tray Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-15 | 2014-08-25 09:17 |  | No | 191 | 2014-09-07 14:51 | [8 empty] | No | 0
VD-9001-213B-DWG-037 | 0 | Gauge Hatch for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-15 | 2014-04-17 09:00 |  | No | 61 | 2014-05-12 16:24 | [8 empty] | No | 0
VD-9001-213A-CAL-001 | 0 | Mechanical Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-09-22 | 2013-10-20 15:55 |  | No | 28 | 2013-11-16 10:15 | [8 empty] | No | 0
VD-9001-213A-CAL-002 | 0 | Roof Structure Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-09-30 | 2013-10-20 15:55 |  | No | 20 | 2013-11-19 16:16 | [8 empty] | No | 0
VD-9001-213A-CAL-003 | 0 | Roof Structure Lifting Calculation for Erection. for Tk-2201 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-03-12 13:24 | 2014-03-12 14:13 | Yes | 4685 |  | 2014-03-18 19:28 | [6 empty] | 2014-03-18 19:29 | Yes | -8
VD-9001-213A-CAL-004 | 0 | Nozzle Load Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-10-25 10:18 |  | No | 1108 | 2014-11-15 09:31 | [8 empty] | No | 0
VD-9001-213A-CAL-005 | 0 | Pipe Support Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-09-24 15:39 |  | No | 313 | 2014-12-03 11:18 | [8 empty] | No | 0
VD-9001-213A-MTO-006 | 0 | MTO for Tk-2201 | PV-213A | MachineSazi Pars | 2011-01-13 | 2016-02-21 12:04 | 2016-02-21 12:05 | Yes | 1865 |  | 2016-02-25 09:44 | [6 empty] | 2016-02-25 20:00 | Yes | -10
VD-9001-213A-PCJ-007 | 0 | Roof Structure Erection Procedure for Tk-2201 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-09-14 14:48 |  | No | 4871 | 2014-09-24 08:46 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 0 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2013-09-22 | 2013-10-20 15:55 |  | No | 28 | 2013-11-19 10:40 | [8 empty] | No | 0
VD-9001-213A-CAL-009 | 0 | Roof Structure Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2010-03-13 | 2013-10-20 15:55 |  | No | 1317 | 2013-11-20 10:52 | [8 empty] | No | 0
VD-9001-213A-CAL-010 | 0 | Roof Structure Lifting Calculation for Erection. for Tk-6401 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-03-12 13:27 | 2014-03-12 14:14 | Yes | 4685 |  | 2014-03-18 19:29 | [6 empty] | 2014-03-18 19:30 | Yes | -8
VD-9001-213A-CAL-011 | 0 | Nozzle Load Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-09-23 13:52 |  | No | 1076 | 2014-11-15 09:14 | [8 empty] | No | 0
VD-9001-213A-CAL-012 | 0 | Pipe Support Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-09-24 15:41 |  | No | 313 | 2014-12-03 11:18 | [8 empty] | No | 0
VD-9001-213A-MTO-013 | 0 | MTO for Tk-6401 | PV-213A | MachineSazi Pars | 2011-01-13 | 2016-02-21 12:04 | 2016-02-21 12:05 | Yes | 1865 |  | 2016-02-25 09:47 | [6 empty] | 2016-02-25 20:00 | Yes | -10
VD-9001-213A-PCJ-014 | 0 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-08-26 08:21 |  | No | 4852 | 2014-09-22 16:24 | [8 empty] | No | 0
VD-9001-213A-CAL-015 | 0 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2010-12-13 | 2013-10-20 15:55 |  | No | 1042 | 2013-12-17 17:03 | [8 empty] | No | 0
VD-9001-213A-CAL-016 | 0 | Roof Structure Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2010-05-13 | 2013-10-20 15:55 |  | No | 1256 | 2013-11-20 15:47 | [8 empty] | No | 0
VD-9001-213A-CAL-017 | 0 | Roof Structure Lifting Calculation for Erection. For Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-03-12 13:29 | 2014-03-12 14:15 | Yes | 4685 |  | 2014-03-18 19:29 | [6 empty] | 2014-03-18 19:30 | Yes | -8
VD-9001-213A-CAL-018 | 0 | Nozzle Load Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-09-23 13:55 |  | No | 1076 | 2014-11-15 09:15 | [8 empty] | No | 0
VD-9001-213A-CAL-019 | 0 | Pipe Support Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-09-28 11:08 |  | No | 317 | 2014-12-03 12:16 | [8 empty] | No | 0
VD-9001-213A-MTO-20 | 0 | MTO for Tk-7101A/B | PV-213A | MachineSazi Pars | 2011-01-13 | 2016-02-21 12:06 |  | No | 1865 | 2016-02-25 10:03 | [7 empty] | 2016-02-25 20:00 | Yes | 0
VD-9001-213A-PCJ-021 | 0 | Roof structure Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-08-26 08:28 |  | No | 4852 | 2014-09-22 16:28 | [8 empty] | No | 0
VD-9001-213A-CAL-022 | 0 | Mechanical Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2013-09-22 | 2013-10-20 15:55 |  | No | 28 | 2013-11-19 09:59 | [8 empty] | No | 0
VD-9001-213A-CAL-023 | 0 | Roof Structure Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2010-05-13 | 2013-10-20 15:55 |  | No | 1256 | 2013-11-20 11:01 | [8 empty] | No | 0
VD-9001-213A-CAL-024 | 0 | Roof Structure Lifting Calculation for Erection. for Tk-7201 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-04-07 06:57 |  | No | 4711 |  | 2014-04-29 15:38 | [7 empty] | No | 0
VD-9001-213A-CAL-025 | 0 | Nozzle Load Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-07-20 11:19 |  | No | 1011 | 2014-09-06 09:52 | [8 empty] | No | 0
VD-9001-213A-CAL-026 | 0 | Pipe Support Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-09-28 11:09 |  | No | 317 | 2014-12-03 12:17 | [8 empty] | No | 0
VD-9001-213A-MTO-027 | 0 | MTO for Tk-7201 | PV-213A | MachineSazi Pars | 2011-01-13 | 2016-02-21 12:05 |  | No | 1865 | 2016-02-25 09:55 | [7 empty] | 2016-02-25 20:00 | Yes | 0
VD-9001-213A-PCJ-028 | 0 | Roof structure Erection Procedure for Tk-7201 | PV-213A | MachineSazi Pars | 2001-05-14 | 2014-09-14 14:53 |  | No | 4871 | 2014-09-24 08:47 | [8 empty] | No | 0
VD-9001-213A-ITP-029 | 0 | Inspection & Test Plan for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2013-12-11 08:20 |  | No | 4714 | 2013-12-17 10:32 | [8 empty] | No | 0 | 1204-Owner-v | 2020-01-01 12:56
VD-9001-213A-WPS-031 | 0 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-06 13:54 |  | No | 4830 | 2014-05-03 16:55 | [8 empty] | No | 0
VD-9001-213A-PQR-032 | 0 | PQR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-06 13:56 |  | No | 4830 | 2014-05-07 09:45 | [8 empty] | No | 0
VD-9001-213A-PCJ-033 | 0 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-12-20 15:54 |  | No | 5088 | 2015-01-26 17:51 | [8 empty] | No | 0
VD-9001-213A-PCJ-034 | 0 | Erection Procedure forTk-2201 & Tk-6401 & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-17 09:40 |  | No | 4841 | 2014-10-08 12:33 | [8 empty] | No | 0
VD-9001-213A-PCJ-035 | 0 | Hydro Test and Air test procedurefor Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-17 11:10 |  | No | 4782 | 2014-10-08 12:28 | [8 empty] | No | 0
VD-9001-213A-PCJ-036 | 0 | NDT Procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-23 13:19 |  | No | 4788 | 2014-04-09 16:20 | [8 empty] | No | 0
VD-9001-213A-WMP-037 | 0 | Welding Maps for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-07-06 07:55 |  | No | 4921 | 2014-08-18 15:49 | [8 empty] | No | 0
VD-9001-213A-PCJ-038 | 0 | Painting procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-25 10:01 |  | No | 4790 | 2014-04-09 16:28 | [8 empty] | No | 0
VD-9001-213A-LST-039 | 0 | SPLIR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2016-02-22 10:14 |  | No | 5517 | 2016-03-10 10:07 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-213A-MTO-040 | 0 | MTO for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2011-01-13 | 2016-02-21 12:06 |  | No | 1865 | 2016-02-25 10:08 | [7 empty] | 2016-02-25 20:00 | Yes | 0
VD-9001-213A-DWG-041 | 0 | General Assembly for Tk-2201 | PV-213A | MachineSazi Pars | 2014-01-15 | 2014-06-19 08:44 |  | No | 155 | 2014-09-07 16:02 | [8 empty] | No | 0
VD-9001-213A-DWG-042 | 0 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-01-22 15:03 |  | No | 68 | 2014-02-19 10:21 | [8 empty] | No | 0
VD-9001-213A-DWG-043 | 0 | Bottom Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2013-10-25 | 2013-12-30 17:00 |  | No | 66 | 2014-01-20 11:48 | [8 empty] | No | 0
VD-9001-213A-DWG-044 | 0 | Fix Roof Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-04 14:21 |  | No | 76 | 2014-02-26 09:48 | [8 empty] | No | 0
VD-9001-213A-DWG-045 | 0 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-08 17:07 |  | No | 80 | 2014-04-05 14:01 | [8 empty] | No | 0
VD-9001-213A-DWG-046 | 0 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2013-09-30 | 2013-10-20 15:55 |  | No | 20 | 2013-11-25 11:14 | [8 empty] | No | 0
VD-9001-213A-DWG-047 | 0 | Spiral Stairway for Tk-2201 | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-02-25 08:09 |  | No | 4060 | 2014-05-24 15:20 | [8 empty] | No | 0
VD-9001-213A-DWG-049 | 0 | Shell Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-01-04 16:45 |  | No | 35 | 2014-05-05 12:18 | [8 empty] | No | 0
VD-9001-213A-DWG-050 | 0 | Roof Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-10 16:35 |  | No | 72 | 2014-05-06 12:46 | [8 empty] | No | 0
VD-9001-213A-DWG-051 | 0 | Shell Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-18 08:16 |  | No | 80 | 2014-02-20 12:55 | [8 empty] | No | 0
VD-9001-213A-DWG-052 | 0 | Roof Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-15 17:07 |  | No | 77 | 2014-02-22 14:56 | [8 empty] | No | 0
VD-9001-213A-DWG-053 | 0 | Drain Sump for Tk-2201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2013-12-04 14:06 |  | No | 4707 | 2013-12-16 09:25 | [8 empty] | No | 0
VD-9001-213A-DWG-054 | 0 | Anchor Chair for Tk-2201 | PV-213A | MachineSazi Pars | 2012-12-13 | 2014-02-26 15:57 |  | No | 440 | 2014-03-18 19:20 | [8 empty] | No | 0
VD-9001-213A-DWG-055 | 0 | Earth Lug for Tk-2201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-23 09:59 |  | No | 4788 | 2014-03-19 17:05 | [8 empty] | No | 0
VD-9001-213A-DWG-056 | 0 | Name Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-16 16:36 |  | No | 4840 | 2014-05-07 09:28 | [8 empty] | No | 0
VD-9001-213A-DWG-057 | 0 | Pipe Support for Tk-2201 | PV-213A | MachineSazi Pars | 2014-02-15 | 2015-08-25 18:14 |  | No | 556 | 2015-09-05 14:25 | [8 empty] | No | 0
VD-9001-213A-DWG-058 | 0 | Instrument Cable Tray Support for Tk-2201 | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-08-25 09:24 |  | No | 191 | 2014-09-30 10:22 | [8 empty] | No | 0
VD-9001-213A-DWG-060 | 0 | General Assembly for Tk-6401 | PV-213A | MachineSazi Pars | 2014-01-15 | 2014-06-19 08:50 |  | No | 155 | 2014-09-07 16:03 | [8 empty] | No | 0
VD-9001-213A-DWG-061 | 0 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-01-22 15:05 |  | No | 68 | 2014-02-19 10:22 | [8 empty] | No | 0
VD-9001-213A-DWG-062 | 0 | Bottom Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2013-10-25 | 2013-11-19 13:55 |  | No | 25 | 2013-12-08 10:37 | [8 empty] | No | 0
VD-9001-213A-DWG-063 | 0 | Fixed Roof Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-04 14:25 |  | No | 76 | 2014-02-26 09:49 | [8 empty] | No | 0
VD-9001-213A-DWG-064 | 0 | Fixed Roof Orientation for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-08 07:50 |  | No | 80 | 2014-04-05 14:02 | [8 empty] | No | 0
VD-9001-213A-DWG-065 | 0 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2012-10-13 | 2013-10-20 15:55 |  | No | 372 | 2013-11-25 11:20 | [8 empty] | No | 0
VD-9001-213A-DWG-066 | 0 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-07-01 14:22 |  | No | 4186 | 2014-07-26 09:57 | [8 empty] | No | 0
VD-9001-213A-DWG-067 | 0 | Walkway With Handrail for Tk-6401 | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-11-11 08:22 |  | No | 4319 | 2015-01-03 10:42 | [8 empty] | No | 0
VD-9001-213A-DWG-068 | 0 | Wind Girder for Tk-6401 | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-04-29 16:13 |  | No | 929 | 2014-05-19 12:29 | [8 empty] | No | 0
VD-9001-213A-DWG-069 | 0 | Shell Nozzles for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-01-04 16:47 |  | No | 35 | 2014-05-05 12:19 | [8 empty] | No | 0
VD-9001-213A-DWG-070 | 0 | Roof Nozzles for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-10 16:37 |  | No | 72 | 2014-05-06 12:47 | [8 empty] | No | 0
VD-9001-213A-DWG-071 | 0 | Shell Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-18 08:18 |  | No | 80 | 2014-02-20 12:56 | [8 empty] | No | 0
VD-9001-213A-DWG-072 | 0 | Roof Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-15 17:10 |  | No | 77 | 2014-02-22 14:57 | [8 empty] | No | 0
VD-9001-213A-DWG-073 | 0 | Drain Sump for Tk-6401 | PV-213A | MachineSazi Pars | 2001-01-14 | 2013-12-04 14:07 |  | No | 4707 | 2013-12-16 09:26 | [8 empty] | No | 0
VD-9001-213A-DWG-074 | 0 | Anchor Chair for Tk-6401 | PV-213A | MachineSazi Pars | 2012-12-13 | 2014-02-26 15:59 |  | No | 440 | 2014-03-18 19:21 | [8 empty] | No | 0
VD-9001-213A-DWG-075 | 0 | Earth Lug for Tk-6401 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-23 10:00 |  | No | 4788 | 2014-03-19 17:06 | [8 empty] | No | 0
VD-9001-213A-DWG-076 | 0 | Name Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-16 16:41 |  | No | 4840 | 2014-05-07 09:29 | [8 empty] | No | 0
VD-9001-213A-DWG-077 | 0 | Pipe Support for Tk-6401 | PV-213A | MachineSazi Pars | 2014-02-15 | 2015-08-30 08:38 |  | No | 561 | 2015-09-05 14:33 | [8 empty] | No | 0
VD-9001-213A-DWG-078 | 0 | Instrument Cable Tray Support for Tk-6401 | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-08-25 09:26 |  | No | 191 | 2014-09-30 10:23 | [8 empty] | No | 0
VD-9001-213A-DWG-079 | 0 | Gauge Hatch for Tk-6401 | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-04-17 09:04 |  | No | 61 | 2014-05-19 11:15 | [8 empty] | No | 0
VD-9001-213A-DWG-080 | 0 | General Assembly for Tk-7101A | PV-213A | MachineSazi Pars | 2014-01-15 | 2014-06-19 08:53 |  | No | 155 | 2014-09-07 16:03 | [8 empty] | No | 0
VD-9001-213A-DWG-081 | 0 | General Assembly for Tk-7101B | PV-213A | MachineSazi Pars | 2014-01-15 | 2014-06-19 08:54 |  | No | 155 | 2014-09-07 16:04 | [8 empty] | No | 0
VD-9001-213A-DWG-082 | 0 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-01-29 07:58 |  | No | 75 | 2014-02-19 10:24 | [8 empty] | No | 0
VD-9001-213A-DWG-083 | 0 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-01-29 07:59 |  | No | 75 | 2014-02-19 10:26 | [8 empty] | No | 0
VD-9001-213A-DWG-084 | 0 | Bottom Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2013-10-25 | 2013-11-19 13:56 |  | No | 25 | 2013-12-08 10:36 | [8 empty] | No | 0
VD-9001-213A-DWG-085 | 0 | Bottom Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2013-10-25 | 2013-11-19 13:57 |  | No | 25 | 2013-12-08 10:37 | [8 empty] | No | 0
VD-9001-213A-DWG-086 | 0 | Fixed Roof Plate for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-04 14:28 |  | No | 76 | 2014-02-26 09:49 | [8 empty] | No | 0
VD-9001-213A-DWG-087 | 0 | Fixed Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-08 07:52 |  | No | 80 | 2014-04-05 14:03 | [8 empty] | No | 0
VD-9001-213A-DWG-088 | 0 | Fixed Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-08 07:54 |  | No | 80 | 2014-04-05 14:04 | [8 empty] | No | 0
VD-9001-213A-DWG-089 | 0 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-25 08:09 |  | No | 308 | 2015-01-13 09:53 | [8 empty] | No | 0
VD-9001-213A-DWG-090 | 0 | Deck Plate for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-25 08:10 |  | No | 308 | 2015-01-13 09:54 | [8 empty] | No | 0
VD-9001-213A-DWG-091 | 0 | Floating Roof Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-25 12:53 |  | No | 308 | 2015-02-04 18:04 | [8 empty] | No | 0
VD-9001-213A-DWG-092 | 0 | Floating Roof Earthing for Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-12-22 11:03 |  | No | 5090 | 2015-02-23 16:32 | [8 empty] | No | 0
VD-9001-213A-DWG-093 | 0 | Deck Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-05-04 11:55 |  | No | 73 | 2014-05-04 15:00 | [8 empty] | No | 0
VD-9001-213A-DWG-094 | 0 | Pontoon Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-05-04 11:57 |  | No | 73 | 2014-05-04 15:01 | [8 empty] | No | 0
VD-9001-213A-DWG-095 | 0 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-24 11:47 |  | No | 307 | 2015-04-25 09:58 | [8 empty] | No | 0
VD-9001-213A-DWG-096 | 0 | Auto Breather Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2015-03-03 11:10 |  | No | 376 | 2015-03-07 09:07 | [8 empty] | No | 0
VD-9001-213A-DWG-097 | 0 | LHD Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2015-03-18 11:59 |  | No | 391 | 2015-04-14 11:57 | [8 empty] | No | 0
VD-9001-213A-DWG-098 | 0 | Rim Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2015-03-03 11:10 |  | No | 376 | 2015-03-07 09:08 | [8 empty] | No | 0
VD-9001-213A-DWG-099 | 0 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-25 08:11 |  | No | 308 | 2015-01-13 09:54 | [8 empty] | No | 0
VD-9001-213A-DWG-100 | 0 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-12-25 08:12 |  | No | 308 | 2015-01-13 09:54 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 0 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2012-10-13 | 2013-10-20 15:55 |  | No | 372 | 2013-11-25 11:07 | [8 empty] | No | 0
VD-9001-213A-DWG-102 | 0 | Spiral Stairway for Tk-7101A | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-06-07 10:42 |  | No | 4162 | 2014-07-26 09:50 | [8 empty] | No | 0
VD-9001-213A-DWG-103 | 0 | Spiral Stairway for Tk-7101B | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-06-07 10:43 |  | No | 4162 | 2014-07-26 09:51 | [8 empty] | No | 0
VD-9001-213A-DWG-104 | 0 | Walkway With Handrail for Tk-7101A | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-09-14 15:05 |  | No | 4261 | 2014-11-12 09:15 | [8 empty] | No | 0
VD-9001-213A-DWG-105 | 0 | Walkway With Handrail for Tk-7101B | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-09-14 15:06 |  | No | 4261 | 2014-11-12 09:15 | [8 empty] | No | 0
VD-9001-213A-DWG-106 | 0 | Wind Girder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-08-03 07:59 |  | No | 1025 | 2014-10-16 11:58 | [8 empty] | No | 0
VD-9001-213A-DWG-107 | 0 | Shell Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-01-04 16:49 |  | No | 35 | 2014-05-05 12:20 | [8 empty] | No | 0
VD-9001-213A-DWG-108 | 0 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-10 16:38 |  | No | 72 | 2014-05-06 12:48 | [8 empty] | No | 0
VD-9001-213A-DWG-109 | 0 | Shell Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-18 08:20 |  | No | 80 | 2014-02-20 12:56 | [8 empty] | No | 0
VD-9001-213A-DWG-110 | 0 | Roof Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-15 17:11 |  | No | 77 | 2014-02-22 14:58 | [8 empty] | No | 0
VD-9001-213A-DWG-111 | 0 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-01-14 | 2013-12-04 14:08 |  | No | 4707 | 2013-12-16 09:27 | [8 empty] | No | 0
VD-9001-213A-DWG-112 | 0 | Anchor Chair for Tk-7101A/B | PV-213A | MachineSazi Pars | 2012-12-13 | 2014-02-26 16:02 |  | No | 440 | 2014-03-18 19:22 | [8 empty] | No | 0
VD-9001-213A-DWG-113 | 0 | Earth Lug for Tk-7101A/B | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-23 10:02 |  | No | 4788 | 2014-03-19 17:06 | [8 empty] | No | 0
VD-9001-213A-DWG-114 | 0 | Name Plate for Tk-7101A | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-16 16:45 |  | No | 4840 | 2014-05-07 09:30 | [8 empty] | No | 0
VD-9001-213A-DWG-115 | 0 | Name Plate for Tk-7101B | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-16 16:46 |  | No | 4840 | 2014-05-07 09:30 | [8 empty] | No | 0
VD-9001-213A-DWG-116 | 0 | Pipe Support for Tk-7101A | PV-213A | MachineSazi Pars | 2014-02-15 | 2015-08-25 18:15 |  | No | 556 | 2015-09-05 14:26 | [8 empty] | No | 0
VD-9001-213A-DWG-117 | 0 | Pipe Support for Tk-7101B | PV-213A | MachineSazi Pars | 2014-02-15 | 2015-08-25 18:15 |  | No | 556 | 2015-09-05 14:28 | [8 empty] | No | 0
VD-9001-213A-DWG-118 | 0 | Instrument Cable Tray Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-08-25 09:52 |  | No | 191 | 2014-09-30 10:23 | [8 empty] | No | 0
VD-9001-213A-DWG-119 | 0 | Water Cooling System for Tk-7101A | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-02 08:49 |  | No | 194 | 2014-11-08 16:08 | [8 empty] | No | 0
VD-9001-213A-DWG-120 | 0 | Water Cooling System for Tk-7101B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-02 08:50 |  | No | 194 | 2014-11-08 16:09 | [8 empty] | No | 0
VD-9001-213A-DWG-121 | 0 | Foam Protection System for Tk-7101A | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-10 12:13 |  | No | 202 | 2014-11-09 11:46 | [8 empty] | No | 0
VD-9001-213A-DWG-122 | 0 | Foam Protection System for Tk-7101B | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-10 12:17 |  | No | 202 | 2014-11-09 11:47 | [8 empty] | No | 0
VD-9001-213A-DWG-123 | 0 | Foam Dam for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-02-20 | 2015-03-03 17:17 |  | No | 376 | 2015-04-14 11:53 | [8 empty] | No | 0
VD-9001-213A-DWG-124 | 0 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2014-01-15 | 2014-06-19 08:56 |  | No | 155 | 2014-09-07 16:04 | [8 empty] | No | 0
VD-9001-213A-DWG-125 | 0 | Shell Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-15 | 2014-01-25 15:05 |  | No | 71 | 2014-02-19 10:23 | [8 empty] | No | 0
VD-9001-213A-DWG-126 | 0 | Bottom Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2013-10-25 | 2013-11-19 13:59 |  | No | 25 | 2013-12-08 10:38 | [8 empty] | No | 0
VD-9001-213A-DWG-127 | 0 | Fixed Roof Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-04 14:31 |  | No | 76 | 2014-02-26 09:50 | [8 empty] | No | 0
VD-9001-213A-DWG-128 | 0 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-20 | 2014-02-08 07:55 |  | No | 80 | 2014-04-05 14:04 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 0 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2012-10-13 | 2013-10-20 15:55 |  | No | 372 | 2013-11-25 10:03 | [8 empty] | No | 0
VD-9001-213A-DWG-130 | 0 | Spiral Stairway for Tk-7201 | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-06-07 10:46 |  | No | 4162 | 2014-07-26 09:52 | [8 empty] | No | 0
VD-9001-213A-DWG-131 | 0 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2003-01-14 | 2014-12-03 15:36 |  | No | 4341 | 2015-01-31 11:10 | [8 empty] | No | 0
VD-9001-213A-DWG-132 | 0 | Wind Girder for Tk-7201 | PV-213A | MachineSazi Pars | 2011-10-13 | 2014-04-29 16:15 |  | No | 929 | 2014-05-19 12:30 | [8 empty] | No | 0
VD-9001-213A-DWG-133 | 0 | Shell Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-01-04 16:50 |  | No | 35 | 2014-05-05 12:20 | [8 empty] | No | 0
VD-9001-213A-DWG-134 | 0 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-10 16:40 |  | No | 72 | 2014-05-06 12:48 | [8 empty] | No | 0
VD-9001-213A-DWG-135 | 0 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-18 08:21 |  | No | 80 | 2014-02-20 12:56 | [8 empty] | No | 0
VD-9001-213A-DWG-136 | 0 | Roof Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2014-02-15 17:13 |  | No | 77 | 2014-02-22 14:59 | [8 empty] | No | 0
VD-9001-213A-DWG-137 | 0 | Drain Sump for Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2013-12-04 14:09 |  | No | 4707 | 2013-12-16 09:28 | [8 empty] | No | 0
VD-9001-213A-DWG-138 | 0 | Anchor Chair for Tk-7201 | PV-213A | MachineSazi Pars | 2012-12-13 | 2014-02-26 16:04 |  | No | 440 | 2014-03-18 19:22 | [8 empty] | No | 0
VD-9001-213A-DWG-139 | 0 | Earth Lug for Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-02-23 10:03 |  | No | 4788 | 2014-03-19 17:07 | [8 empty] | No | 0
VD-9001-213A-DWG-140 | 0 | Name Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2001-01-14 | 2014-04-16 16:50 |  | No | 4840 | 2014-05-07 09:31 | [8 empty] | No | 0
VD-9001-213A-DWG-141 | 0 | Pipe Support for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-15 | 2015-08-30 08:38 |  | No | 561 | 2015-09-05 14:34 | [8 empty] | No | 0
VD-9001-213A-DWG-142 | 0 | Instrument Cable Tray Support for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-08-25 09:27 |  | No | 191 | 2014-09-30 10:24 | [8 empty] | No | 0
VD-9001-213A-DWG-143 | 0 | Gauge Hatch for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-15 | 2014-04-17 09:06 |  | No | 61 | 2014-05-19 11:15 | [8 empty] | No | 0
VD-9001-213A-DWG-144 | 0 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-02 08:52 |  | No | 194 | 2014-11-08 16:09 | [8 empty] | No | 0
VD-9001-213A-DWG-145 | 0 | Foam Protection System for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-20 | 2014-09-10 12:20 |  | No | 202 | 2014-11-09 11:50 | [8 empty] | No | 0
VD-9001-213A-CAL-001 | 1 | Mechanical Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-11-30 | 2013-12-14 16:39 |  | No | 14 | 2013-12-22 10:14 | [8 empty] | No | 0
VD-9001-213A-CAL-022 | 1 | Mechanical Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-03 | 2013-12-28 17:46 |  | No | 25 | 2014-01-20 11:05 | [8 empty] | No | 0
VD-9001-213B-CAL-001 | 1 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-03 | 2013-12-30 16:55 |  | No | 27 | 2014-01-20 15:46 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 1 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2013-12-03 | 2013-12-28 17:43 |  | No | 25 | 2014-01-20 11:04 | [8 empty] | No | 0
VD-9001-213A-CAL-002 | 1 | Roof Structure Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2013-12-03 | 2014-02-08 17:05 | 2014-02-08 17:34 | Yes | 67 |  | 2016-04-05 11:57 | [6 empty] | 2016-04-05 20:00 | Yes | 773
VD-9001-213A-CAL-009 | 1 | Roof Structure Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2013-12-04 | 2013-12-19 15:58 |  | No | 15 | 2014-01-14 10:53 | [8 empty] | No | 0
VD-9001-213A-CAL-023 | 1 | Roof Structure Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-04 | 2013-12-30 05:33 |  | No | 26 | 2014-01-14 11:03 | [8 empty] | No | 0
VD-9001-213A-CAL-016 | 1 | Roof Structure Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-12-04 | 2013-12-29 19:01 |  | No | 25 | 2014-01-14 11:02 | [8 empty] | No | 0
VD-9001-213B-CAL-002 | 1 | Roof Structure Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-04 | 2014-01-11 10:56 |  | No | 38 | 2014-01-22 09:59 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 1 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-09 | 2013-12-30 05:36 |  | No | 21 | 2014-01-14 11:04 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 1 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-12-09 | 2013-12-30 05:34 |  | No | 21 | 2014-01-14 11:04 | [8 empty] | No | 0
VD-9001-213A-DWG-046 | 1 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2013-12-09 | 2014-02-08 17:09 |  | No | 61 | 2014-02-26 09:51 | [8 empty] | No | 0
VD-9001-213A-DWG-065 | 1 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2013-12-09 | 2013-12-19 16:02 |  | No | 10 | 2014-01-14 10:54 | [8 empty] | No | 0
VD-9001-213B-DWG-023 | 1 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-09 | 2014-01-11 10:57 |  | No | 33 | 2014-01-22 10:00 | [8 empty] | No | 0
VD-9001-213A-DWG-084 | 1 | Bottom Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2013-12-22 | 2013-12-21 15:11 |  | No | -1 | 2014-01-15 11:28 | [8 empty] | No | 0
VD-9001-213A-DWG-085 | 1 | Bottom Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2013-12-22 | 2013-12-21 15:13 |  | No | -1 | 2014-01-15 11:29 | [8 empty] | No | 0
VD-9001-213A-DWG-062 | 1 | Bottom Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2013-12-22 | 2013-12-21 15:09 |  | No | -1 | 2014-01-15 11:27 | [8 empty] | No | 0
VD-9001-213A-DWG-126 | 1 | Bottom Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-22 | 2013-12-21 15:15 |  | No | -1 | 2014-01-15 11:29 | [8 empty] | No | 0
VD-9001-213B-DWG-020 | 1 | Bottom Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-22 | 2013-12-21 15:07 |  | No | -1 | 2014-01-15 11:30 | [8 empty] | No | 0
VD-9001-213A-DWG-053 | 1 | Drain Sump for Tk-2201 | PV-213A | MachineSazi Pars | 2013-12-30 | 2013-12-24 21:17 |  | No | -6 | 2014-01-16 12:17 | [8 empty] | No | 0
VD-9001-213A-DWG-073 | 1 | Drain Sump for Tk-6401 | PV-213A | MachineSazi Pars | 2013-12-30 | 2013-12-24 21:19 |  | No | -6 | 2014-01-16 12:17 | [8 empty] | No | 0
VD-9001-213A-DWG-111 | 1 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-12-30 | 2013-12-24 21:20 |  | No | -6 | 2014-01-16 12:18 | [8 empty] | No | 0
VD-9001-213A-DWG-137 | 1 | Drain Sump for Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-30 | 2013-12-24 21:21 |  | No | -6 | 2014-01-16 12:19 | [8 empty] | No | 0
VD-9001-213B-DWG-031 | 1 | Drain Sump for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-30 | 2013-12-24 21:13 |  | No | -6 | 2014-01-16 12:19 | [8 empty] | No | 0
VD-9001-213A-ITP-029 | 1 | Inspection & Test Plan for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2013-12-31 | 2013-12-22 10:43 | 2013-12-22 15:36 | Yes | -9 |  | 2014-01-15 11:19 | [6 empty] | 2014-01-15 11:20 | Yes | 10 | 1204-Owner-v | 2020-01-01 12:56
VD-9001-213B-ITP-008 | 1 | Inspection & Test Plan for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2013-12-31 | 2013-12-22 10:41 | 2013-12-22 15:37 | Yes | -9 |  | 2014-01-15 11:21 | [6 empty] | 2014-01-15 11:22 | Yes | 10
VD-9001-213A-CAL-015 | 1 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2013-12-31 | 2014-01-27 16:30 |  | No | 27 | 2014-04-26 15:58 | [8 empty] | No | 0
VD-9001-213A-CAL-001 | 2 | Mechanical Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-01-05 | 2013-12-24 21:16 |  | No | -12 | 2014-01-08 10:16 | [8 empty] | No | 0
VD-9001-213A-CAL-001 | 3 | Mechanical Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-01-22 | 2014-01-13 16:28 | 2014-01-14 09:47 | Yes | -8 |  | 2014-01-18 09:25 | [6 empty] | 2014-01-18 09:26 | Yes | -9
VD-9001-213A-CAL-009 | 2 | Roof Structure Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-01-27 16:24 | 2014-01-27 17:09 | Yes | -1 |  | 2014-02-18 09:21 | [6 empty] | 2014-02-18 09:22 | Yes | 8
VD-9001-213A-DWG-065 | 2 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-01-27 16:35 |  | No | -1 | 2014-02-18 09:30 | [8 empty] | No | 0
VD-9001-213A-CAL-016 | 2 | Roof Structure Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-02-02 11:50 | 2014-02-02 14:17 | Yes | 5 |  | 2014-02-18 09:31 | [6 empty] | 2014-02-18 09:32 | Yes | 2
VD-9001-213A-CAL-023 | 2 | Roof Structure Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-02-02 11:55 | 2014-02-02 14:17 | Yes | 5 |  | 2014-02-18 09:32 | [6 empty] | 2014-02-18 09:33 | Yes | 2
VD-9001-213A-DWG-101 | 2 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-02-02 11:57 |  | No | 5 | 2014-02-18 09:34 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 2 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2014-01-28 | 2014-02-02 11:59 |  | No | 5 | 2014-02-18 09:34 | [8 empty] | No | 0
VD-9001-213A-DWG-062 | 2 | Bottom Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-01-29 | 2014-01-22 14:42 | 2014-01-22 14:55 | Yes | -7 |  | 2014-01-28 16:31 | [6 empty] | 2014-01-28 16:32 | Yes | -8
VD-9001-213A-DWG-084 | 2 | Bottom Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-01-29 | 2014-01-22 14:44 |  | No | -7 | 2014-01-28 16:32 | [8 empty] | No | 0
VD-9001-213A-DWG-085 | 2 | Bottom Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-01-29 | 2014-01-22 14:45 |  | No | -7 | 2014-01-28 16:33 | [8 empty] | No | 0
VD-9001-213A-DWG-126 | 2 | Bottom Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-01-29 | 2014-01-22 14:47 |  | No | -7 |  | 2014-01-28 16:34 | [7 empty] | No | 0
VD-9001-213B-DWG-020 | 2 | Bottom Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-29 | 2014-01-22 15:07 | 2014-01-22 15:10 | Yes | -7 |  | 2014-01-28 16:36 | [6 empty] | 2014-01-28 16:37 | Yes | -8
VD-9001-213A-DWG-053 | 2 | Drain Sump for Tk-2201 | PV-213A | MachineSazi Pars | 2014-01-30 | 2014-01-22 14:55 |  | No | -8 | 2014-02-18 09:36 | [8 empty] | No | 0
VD-9001-213A-DWG-073 | 2 | Drain Sump for Tk-6401 | PV-213A | MachineSazi Pars | 2014-01-30 | 2014-01-22 14:58 |  | No | -8 | 2014-02-18 09:36 | [8 empty] | No | 0
VD-9001-213A-DWG-111 | 2 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-01-30 | 2014-01-22 15:00 |  | No | -8 | 2014-02-18 09:37 | [8 empty] | No | 0
VD-9001-213A-DWG-137 | 2 | Drain Sump for Tk-7201 | PV-213A | MachineSazi Pars | 2014-01-30 | 2014-01-22 15:01 |  | No | -8 |  | 2014-02-18 09:39 | [7 empty] | No | 0
VD-9001-213B-DWG-031 | 2 | Drain Sump for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-01-30 | 2014-01-22 15:09 |  | No | -8 | 2014-02-24 11:04 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 2 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-02-03 | 2014-01-26 13:28 |  | No | -8 | 2014-02-02 09:19 | [8 empty] | No | 0
VD-9001-213A-CAL-022 | 2 | Mechanical Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-02-03 | 2014-01-27 16:34 |  | No | -7 | 2014-03-01 15:33 | [8 empty] | No | 0
VD-9001-213A-DWG-043 | 1 | Bottom Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-02-03 | 2014-01-22 14:40 |  | No | -12 | 2014-01-28 16:30 | [8 empty] | No | 0
VD-9001-213B-CAL-001 | 2 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-03 | 2014-02-03 10:46 |  | No | 0 | 2014-03-10 09:37 | 2014-02-18 09:18 | [7 empty] | No | 0
VD-9001-213B-CAL-002 | 2 | Roof Structure Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-05 | 2014-02-04 14:10 | 2014-02-04 15:49 | Yes | -1 |  | 2014-02-18 10:42 | [6 empty] | 2014-02-18 10:43 | Yes | 0
VD-9001-213B-DWG-023 | 2 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-05 | 2014-02-04 14:15 |  | No | -1 | 2014-02-18 09:19 | [8 empty] | No | 0
VD-9001-213A-DWG-043 | 2 | Bottom Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-02-11 | 2014-02-02 12:33 |  | No | -9 |  | 2014-02-09 17:12 | [7 empty] | No | 0
VD-9001-213A-DWG-084 | 3 | Bottom Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-02-11 | 2014-02-02 13:14 | 2014-02-02 14:21 | Yes | -9 |  | 2014-02-09 17:13 | [6 empty] | 2014-02-09 17:14 | Yes | -7
VD-9001-213A-DWG-085 | 3 | Bottom Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-02-11 | 2014-02-02 13:16 | 2014-02-02 14:22 | Yes | -9 |  | 2014-02-09 17:13 | [6 empty] | 2014-02-09 17:14 | Yes | -7
VD-9001-213B-DWG-019 | 1 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-02-11 | 2014-02-04 14:12 |  | No | -7 | 2014-04-05 12:21 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 3 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-02-16 | 2014-02-10 06:54 |  | No | -6 | 2014-03-01 11:57 | [8 empty] | No | 0
VD-9001-213B-DWG-023 | 3 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-04 | 2014-03-08 16:35 |  | No | 4 | 2014-03-12 14:04 | [8 empty] | No | 0
VD-9001-213A-DWG-065 | 3 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-03-08 16:37 |  | No | 4 | 2014-03-09 17:32 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 3 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-03-08 16:39 |  | No | 4 | 2014-03-09 17:32 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 3 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-03-08 16:42 |  | No | 4 | 2014-03-09 17:32 | [8 empty] | No | 0
VD-9001-213A-DWG-053 | 3 | Drain Sump for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-02-23 12:55 |  | No | -9 |  | 2014-02-26 09:45 | [7 empty] | No | 0
VD-9001-213A-DWG-073 | 3 | Drain Sump for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-02-23 12:56 |  | No | -9 | 2014-02-26 09:47 | [8 empty] | No | 0
VD-9001-213A-DWG-111 | 3 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-04 | 2014-02-23 13:17 |  | No | -9 | 2014-03-16 13:22 | [8 empty] | No | 0
VD-9001-213A-DWG-042 | 1 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-05 | 2014-03-16 17:52 |  | No | 11 | 2014-04-09 16:05 | [8 empty] | No | 0
VD-9001-213A-DWG-061 | 1 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-05 | 2014-03-16 17:54 |  | No | 11 | 2014-04-09 16:06 | [8 empty] | No | 0
VD-9001-213A-DWG-125 | 1 | Shell Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-05 | 2014-03-16 17:58 |  | No | 11 | 2014-05-03 16:48 | [8 empty] | No | 0
VD-9001-213A-DWG-082 | 1 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-03-05 | 2014-03-16 17:55 |  | No | 11 | 2014-04-09 16:07 | [8 empty] | No | 0
VD-9001-213A-DWG-083 | 1 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-03-05 | 2014-03-16 17:57 |  | No | 11 | 2014-04-09 16:07 | [8 empty] | No | 0
VD-9001-213A-DWG-051 | 1 | Shell Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-06 | 2014-03-05 11:29 |  | No | -1 | 2014-03-15 09:03 | [8 empty] | No | 0
VD-9001-213A-DWG-071 | 1 | Shell Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-06 | 2014-03-05 11:31 |  | No | -1 | 2014-03-15 09:04 | [8 empty] | No | 0
VD-9001-213A-DWG-109 | 1 | Shell Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-06 | 2014-03-05 11:32 |  | No | -1 | 2014-03-15 09:05 | [8 empty] | No | 0
VD-9001-213A-DWG-135 | 1 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-06 | 2014-03-05 11:36 |  | No | -1 | 2014-03-15 09:06 | [8 empty] | No | 0
VD-9001-213A-DWG-052 | 1 | Roof Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-08 | 2014-02-25 08:11 |  | No | -11 | 2014-02-26 09:41 | [8 empty] | No | 0
VD-9001-213A-DWG-072 | 1 | Roof Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-08 | 2014-02-25 08:12 |  | No | -11 |  | 2014-02-26 09:43 | [7 empty] | No | 0
VD-9001-213A-DWG-110 | 1 | Roof Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-08 | 2014-02-25 08:15 |  | No | -11 |  | 2014-02-26 09:43 | [7 empty] | No | 0
VD-9001-213A-DWG-136 | 1 | Roof Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-08 | 2014-02-25 08:17 |  | No | -11 |  | 2014-02-26 09:44 | [7 empty] | No | 0
VD-9001-213B-DWG-031 | 3 | Drain Sump for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-10 | 2014-02-26 15:55 |  | No | -12 |  | 2014-03-09 17:07 | [7 empty] | No | 0
VD-9001-213A-DWG-052 | 2 | Roof Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-03-15 12:10 | 2014-03-15 14:08 | Yes | 3 |  | 2014-03-18 19:36 | [6 empty] | 2014-03-18 19:37 | Yes | -11
VD-9001-213A-DWG-073 | 4 | Drain Sump for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-03-03 08:14 | 2014-03-03 09:32 | Yes | -9 |  | 2014-03-15 08:45 | [6 empty] | 2014-03-15 08:46 | Yes | -2
VD-9001-213A-DWG-044 | 1 | Fix Roof Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-04-28 13:13 |  | No | 47 | 2014-05-24 15:25 | [8 empty] | No | 0
VD-9001-213A-DWG-063 | 1 | Fixed Roof Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-03-15 12:12 | 2014-03-15 14:10 | Yes | 3 |  | 2014-03-19 17:29 | [6 empty] | 2014-03-19 17:30 | Yes | -10 | 1204-Owner-v | 2020-06-07 10:02
VD-9001-213A-DWG-086 | 1 | Fixed Roof Plate for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-03-15 12:14 |  | No | 3 |  | 2014-03-19 17:30 | [7 empty] | No | 0
VD-9001-213A-DWG-127 | 1 | Fixed Roof Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-03-15 12:16 | 2014-03-15 14:14 | Yes | 3 |  | 2014-03-19 17:30 | [6 empty] | 2014-03-19 17:31 | Yes | -10
VD-9001-213A-DWG-046 | 2 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-12 | 2014-04-16 12:29 |  | No | 35 | 2014-05-19 11:22 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 4 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-15 | 2014-03-04 07:50 |  | No | -11 | 2014-03-15 08:53 | [8 empty] | No | 0
VD-9001-213A-CAL-022 | 3 | Mechanical Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-15 | 2014-03-04 07:54 |  | No | -11 | 2014-04-14 12:46 | [8 empty] | No | 0
VD-9001-253(A)-DSH-001 | 0 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-02-15 | 2014-03-05 10:05 |  | No | 18 | 2014-04-13 17:18 | [8 empty] | No | 0
VD-9001-253(A)-DWG-002 | 0 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2003-11-14 | 2014-06-30 12:35 |  | No | 3881 | 2014-07-09 10:46 | [8 empty] | No | 0
VD-9001-253(A)-DWG-003 | 0 | TUBE BUNDLE for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2003-04-14 | 2014-06-23 16:35 |  | No | 4088 | 2014-07-01 16:49 | [8 empty] | No | 0 | 1204-Owner-v | 2019-06-22 16:50
VD-9001-253(A)-DWG-004 | 0 | BUNDLE FRAME for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-04-15 | 2014-12-04 11:19 |  | No | 233 | 2014-12-15 17:08 | [8 empty] | No | 0
VD-9001-253(A)-DWG-005 | 0 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2006-07-14 | 2015-09-05 14:55 |  | No | 3340 | 2015-10-28 14:44 | [8 empty] | No | 0
VD-9001-253(A)-DWG-006 | 0 | PLENUM for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-10-21 08:57 |  | No | 174 | 2014-12-15 16:56 | [8 empty] | No | 0
VD-9001-253(A)-DWG-007 | 0 | FAN RING for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-08-20 10:31 |  | No | 112 | 2014-08-24 16:57 | [8 empty] | No | 0
VD-9001-253(A)-DWG-008 | 0 | MOTOR SUPPORT for 2001 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2016-01-16 15:41 |  | No | 3442 |  | 2016-01-17 16:11 | [6 empty] | 2016-01-17 20:03 | Yes | 0 | 1204-Owner-v | 2018-05-16 10:02
VD-9001-253(A)-DWG-009 | 0 | FAN GUARD & PULLEY GUARD for 2001 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2014-09-03 08:06 |  | No | 2942 | 2014-09-14 11:53 | [8 empty] | No | 0
VD-9001-253(A)-DWG-010 | 0 | LADDER for 2001 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2015-08-19 11:05 |  | No | 2866 | 2015-08-31 12:12 | [8 empty] | No | 0
VD-9001-253(A)-DWG-011 | 0 | HEADER WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2016-04-02 12:27 |  | No | 3093 | 2016-04-24 11:25 | [7 empty] | 2016-04-24 19:59 | Yes | 0
VD-9001-253(A)-DWG-012 | 0 | NAME PLATE for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-04-19 | 2014-11-18 14:38 |  | No | 213 | 2014-12-15 17:04 | [8 empty] | No | 0
VD-9001-253(A)-DSH-013 | 0 | PULLEY DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-09-02 16:46 |  | No | 168 | 2014-09-09 12:24 | [8 empty] | No | 0
VD-9001-253(A)-DWG-014 | 0 | ROTATING PART DETAIL for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-10-21 11:50 |  | No | 217 |  | 2014-12-15 16:55 | [7 empty] | No | 0
VD-9001-253(A)-DWG-015 | 0 | GRATING DETAIL for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-03-13 | 2016-07-18 10:42 |  | No | 858 | 2016-09-25 15:30 | [7 empty] | 2016-09-25 18:56 | Yes | 0
VD-9001-253(A)-DSH-016 | 0 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2015-05-31 08:36 |  | No | 4034 | 2015-06-18 11:35 | [8 empty] | No | 0
VD-9001-253(A)-DSH-017 | 0 | MOTOR GENERAL ARRANGEMENT DWG. For 2001 | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2016-06-20 08:39 |  | No | 4420 | 2016-06-29 15:30 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-DWG-018 | 0 | MOTOR WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2006-07-14 | 2016-04-02 12:25 |  | No | 3550 | 2016-04-24 16:49 | [7 empty] | 2016-04-24 19:59 | Yes | 0
VD-9001-253(A)-CAL-019 | 0 | BUNDLE CALCULATION (INCLUDING FEA) for 2001 | HM-253A | FATEH SANAT KIMIA | 2003-04-14 | 2014-06-23 16:49 |  | No | 4088 | 2014-07-01 16:48 | [8 empty] | No | 0
VD-9001-253(A)-CAL-020 | 0 | STRUCTURE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2005-03-14 | 2015-01-05 09:21 |  | No | 3584 | 2015-02-03 09:32 | [8 empty] | No | 0
VD-9001-253(A)-CAL-021 | 0 | BASE PLATE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2005-03-14 | 2014-12-31 16:30 |  | No | 3579 | 2015-01-18 10:28 | [8 empty] | No | 0
VD-9001-253(A)-RPT-022 | 0 | FOUNDATION LOADING for 2001 | HM-253A | FATEH SANAT KIMIA | 2005-03-14 | 2014-09-27 12:20 |  | No | 3484 |  | 2014-10-04 16:25 | [7 empty] | No | 0
VD-9001-253(A)-DWG-023 | 0 | ASSEMBLY MARKING FOR STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2016-12-25 10:17 |  | No | 2994 | 2016-12-25 14:24 | [7 empty] | 2016-12-25 19:59 | Yes | 0
VD-9001-253(A)-DWG-024 | 0 | ASSEMBLY MARKING FOR MOTOR WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2017-03-13 12:12 | 2017-03-13 12:13 | Yes | 3072 |  | 2017-03-14 17:02 | [6 empty] | 2017-03-14 20:00 | Yes | -13 | 1204-Owner-v | 2018-03-12 14:04
VD-9001-253(A)-DWG-025 | 0 | ASSEMBLY MARKING FOR HEADER WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2016-12-25 10:08 | 2016-12-25 10:09 | Yes | 2994 |  | 2016-12-25 14:43 | [6 empty] | 2016-12-25 19:59 | Yes | -14 | 1204-Owner-v | 2018-05-16 09:57
VD-9001-253(A)-DSH-026 | 0 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2015-03-08 09:50 |  | No | 3889 | 2015-04-11 16:58 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-027 | 0 | FERRITE CONTENT PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2015-05-13 14:43 |  | No | 3955 | 2015-05-18 09:50 | [8 empty] | No | 0
VD-9001-253(A)-DWG-028 | 0 | MOTOR WALKWAY GRATING DETAIL AE-2001 | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2016-07-27 14:40 |  | No | 4396 | 2016-09-25 14:58 | [7 empty] | 2016-09-25 18:56 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:42
VD-9001-253(A)-***-029 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-030 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-DSH-031 | 0 | THERMAL & MECHANICAL DATA SHEET for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-02-15 | 2014-03-05 10:05 |  | No | 18 | 2014-04-13 17:19 | [8 empty] | No | 0
VD-9001-253(A)-DWG-032 | 0 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-02-28 | 2014-06-22 08:43 |  | No | 114 | 2014-07-07 17:01 | [8 empty] | No | 0
VD-9001-253(A)-DWG-033 | 0 | TUBE BUNDLE for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-02-19 | 2014-06-14 16:05 |  | No | 115 | 2014-06-30 11:53 | [8 empty] | No | 0
VD-9001-253(A)-DWG-034 | 0 | BUNDLE FRAME for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2004-11-14 | 2014-12-04 11:23 |  | No | 3672 | 2014-12-22 17:32 | [8 empty] | No | 0
VD-9001-253(A)-DWG-035 | 0 | STEEL STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2005-12-14 | 2015-07-22 15:19 |  | No | 3507 | 2015-08-19 10:53 | [8 empty] | No | 0
VD-9001-253(A)-DWG-036 | 0 | PLENUM for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-10-29 14:33 |  | No | 182 | 2014-12-22 17:28 | [8 empty] | No | 0
VD-9001-253(A)-DWG-037 | 0 | FAN RING for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-08-20 10:32 |  | No | 112 | 2014-08-24 16:57 | [8 empty] | No | 0
VD-9001-253(A)-DWG-038 | 0 | MOTOR SUPPORT for 3001 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2016-01-16 15:48 |  | No | 3442 |  | 2016-01-17 16:07 | [6 empty] | 2016-01-17 20:03 | Yes | 0 | 1204-Owner-v | 2018-05-16 10:02
VD-9001-253(A)-DWG-039 | 0 | FAN GUARD & PULLEY GUARD for 3001 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2014-09-03 08:07 |  | No | 2942 | 2014-09-14 11:53 | [8 empty] | No | 0
VD-9001-253(A)-DWG-040 | 0 | LADDER for 3001 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2015-08-19 11:05 |  | No | 2866 | 2015-08-31 12:13 | [8 empty] | No | 0
VD-9001-253(A)-DWG-041 | 0 | HEADER WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2015-08-05 10:57 |  | No | 2852 | 2015-08-18 10:10 | [8 empty] | No | 0
VD-9001-253(A)-DWG-042 | 0 | NAME PLATE for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-04-19 | 2014-11-18 14:42 |  | No | 213 | 2014-12-22 17:21 | [8 empty] | No | 0
VD-9001-253(A)-DSH-043 | 0 | PULLEY DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-09-02 16:47 |  | No | 168 | 2014-09-09 12:25 | [8 empty] | No | 0
VD-9001-253(A)-DWG-044 | 0 | ROTATING PART DETAIL for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-10-21 11:52 |  | No | 217 |  | 2014-12-22 17:17 | [7 empty] | No | 0
VD-9001-253(A)-DWG-045 | 0 | GRATING DETAIL for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-08-13 | 2015-10-18 16:10 | 2015-10-18 18:00 | Yes | 431 |  | 2015-10-25 11:26 | [6 empty] | 2015-10-25 11:27 | Yes | -7 | 1204-Owner-v | 2018-08-14 17:40
VD-9001-253(A)-DSH-046 | 0 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2015-05-31 08:38 |  | No | 4034 | 2015-06-18 11:35 | [8 empty] | No | 0
VD-9001-253(A)-DSH-047 | 0 | MOTOR GENERAL ARRANGEMENT DWG. For 3001 | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2016-06-20 08:39 |  | No | 4420 | 2016-06-29 15:25 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-DWG-048 | 0 | MOTOR WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2006-07-14 | 2015-08-05 10:57 |  | No | 3309 | 2015-08-18 10:11 | [8 empty] | No | 0
VD-9001-253(A)-CAL-049 | 0 | BUNDLE CALCULATION (INCLUDING FEA) for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-02-19 | 2014-06-14 16:15 |  | No | 115 | 2014-06-30 11:54 | [8 empty] | No | 0
VD-9001-253(A)-CAL-050 | 0 | STRUCTURE CALCULATION for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-03-19 | 2015-05-13 14:45 |  | No | 420 | 2015-05-24 15:41 | [8 empty] | No | 0
VD-9001-253(A)-CAL-051 | 0 | BASE PLATE CALCULATION for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-03-19 | 2015-05-13 14:47 |  | No | 420 |  | 2015-05-24 15:42 | [7 empty] | No | 0
VD-9001-253(A)-RPT-052 | 0 | FOUNDATION LOADING for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-03-19 | 2014-10-15 16:45 | 2014-10-16 11:51 | Yes | 211 |  | 2015-01-26 17:19 | [6 empty] | 2015-01-26 17:20 | Yes | 89
VD-9001-253(A)-DWG-053 | 0 | ASSEMBLY MARKING FOR STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2017-01-24 16:31 |  | No | 3024 | 2017-01-30 12:50 | [7 empty] | 2017-01-30 19:59 | Yes | 0
VD-9001-253(A)-DWG-054 | 0 | ASSEMBLY MARKING FOR MOTOR WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2017-02-25 10:39 | 2017-02-25 10:40 | Yes | 3056 |  | 2017-04-10 10:34 | [6 empty] | 2017-04-10 20:59 | Yes | 30 | 1204-Owner-v | 2018-03-12 14:33
VD-9001-253(A)-DWG-055 | 0 | ASSEMBLY MARKING FOR HEADER WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2017-02-01 08:44 |  | No | 3032 | 2017-02-04 15:42 | [7 empty] | 2017-02-04 19:59 | Yes | 0 | 1204-Owner-v | 2018-05-16 14:18
VD-9001-253(A)-DSH-056 | 0 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2015-03-08 09:52 |  | No | 3889 | 2015-04-11 16:59 | [8 empty] | No | 0
VD-9001-253(A)-DWG-057 | 0 | MOTOR WALKWAY GRATING DETAIL FOR AE-3001 | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2016-08-15 10:09 |  | No | 4415 | 2016-09-25 15:49 | [7 empty] | 2016-09-25 18:56 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:45
VD-9001-253(A)-***-058 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-059 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-060 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-DSH-061 | 0 | THERMAL & MECHANICAL DATA SHEET for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-02-15 | 2014-03-05 10:06 |  | No | 18 | 2014-04-13 17:19 | [8 empty] | No | 0
VD-9001-253(A)-DWG-062 | 0 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2003-07-14 | 2014-06-17 12:18 |  | No | 3991 | 2014-07-06 10:05 | [8 empty] | No | 0
VD-9001-253(A)-DWG-063 | 0 | TUBE BUNDLE for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-02-26 | 2014-06-11 16:53 |  | No | 105 | 2014-06-30 11:44 | [8 empty] | No | 0
VD-9001-253(A)-DWG-064 | 0 | BUNDLE FRAME for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2004-12-14 | 2014-12-04 11:27 |  | No | 3642 | 2014-12-17 16:44 | [8 empty] | No | 0
VD-9001-253(A)-DWG-065 | 0 | STEEL STRUCTURE for 3002 | HM-253A | FATEH SANAT KIMIA | 2006-07-14 | 2015-07-13 10:53 |  | No | 3286 | 2015-08-15 11:19 | [8 empty] | No | 0
VD-9001-253(A)-DWG-066 | 0 | PLENUM for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-10-04 15:42 |  | No | 157 |  | 2014-10-08 16:43 | [7 empty] | No | 0
VD-9001-253(A)-DWG-067 | 0 | FAN RING for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-30 | 2014-08-20 10:33 |  | No | 112 | 2014-08-24 16:58 | [8 empty] | No | 0
VD-9001-253(A)-DWG-068 | 0 | MOTOR SUPPORT for 3002 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2016-01-16 15:56 |  | No | 3442 |  | 2016-01-17 16:00 | [6 empty] | 2016-01-17 20:03 | Yes | 0 | 1204-Owner-v | 2018-05-16 10:03
VD-9001-253(A)-DWG-069 | 0 | FAN GUARD & PULLEY GUARD for 3002 | HM-253A | FATEH SANAT KIMIA | 2006-08-14 | 2014-09-06 09:43 |  | No | 2945 | 2014-09-14 11:52 | [8 empty] | No | 0
VD-9001-253(A)-DWG-070 | 0 | LADDER for 3002 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2015-08-19 11:06 |  | No | 2866 | 2015-08-31 12:13 | [8 empty] | No | 0
VD-9001-253(A)-DWG-071 | 0 | HEADER WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2007-10-14 | 2015-08-02 10:22 |  | No | 2849 | 2015-08-15 11:26 | [8 empty] | No | 0
VD-9001-253(A)-DWG-072 | 0 | NAME PLATE for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-19 | 2014-11-18 14:43 |  | No | 213 | 2014-12-17 16:41 | [8 empty] | No | 0
VD-9001-253(A)-DSH-073 | 0 | PULLEY DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-09-02 16:54 |  | No | 168 | 2014-09-09 12:25 | [8 empty] | No | 0
VD-9001-253(A)-DWG-074 | 0 | ROTATING PART DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-03-18 | 2014-10-21 11:56 |  | No | 217 |  | 2014-12-17 16:36 | [7 empty] | No | 0
VD-9001-253(A)-DWG-075 | 0 | GRATING DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-08-13 | 2015-10-18 16:27 |  | No | 431 |  | 2015-10-25 11:26 | [7 empty] | No | 0
VD-9001-253(A)-DSH-076 | 0 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2015-05-31 08:36 |  | No | 4034 | 2015-06-18 11:36 | [8 empty] | No | 0
VD-9001-253(A)-DSH-077 | 0 | MOTOR GENERAL ARRANGEMENT DWG. For 3002 | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2016-06-20 08:40 |  | No | 4359 | 2016-06-29 15:33 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-DWG-078 | 0 | MOTOR WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2006-07-14 | 2015-07-28 15:57 |  | No | 3301 | 2015-08-05 18:05 | [8 empty] | No | 0
VD-9001-253(A)-CAL-079 | 0 | BUNDLE CALCULATION (INCLUDING FEA) for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-02-26 | 2014-06-11 16:57 |  | No | 105 | 2014-06-30 11:45 | [8 empty] | No | 0
VD-9001-253(A)-CAL-080 | 0 | STRUCTURE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-26 | 2014-11-01 15:39 |  | No | 189 | 2015-02-03 09:21 | [8 empty] | No | 0
VD-9001-253(A)-CAL-081 | 0 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-26 | 2014-11-01 15:48 |  | No | 189 | 2014-12-15 17:12 | [8 empty] | No | 0
VD-9001-253(A)-RPT-082 | 0 | FOUNDATION LOADING for 3002 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2014-09-03 08:12 |  | No | 2150 | 2014-09-09 12:26 | [8 empty] | No | 0
VD-9001-253(A)-DWG-083 | 0 | ASSEMBLY MARKING FOR STRUCTURE for 3002 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2016-05-28 11:12 |  | No | 2783 |  | 2016-05-29 15:36 | [6 empty] | 2016-05-29 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:46
VD-9001-253(A)-DWG-084 | 0 | ASSEMBLY MARKING FOR MOTOR WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2017-03-13 17:03 | 2017-03-13 17:04 | Yes | 3072 |  | 2017-03-14 17:04 | [6 empty] | 2017-03-14 20:00 | Yes | -13 | 1204-Owner-v | 2018-01-03 16:02
VD-9001-253(A)-DWG-085 | 0 | ASSEMBLY MARKING FOR HEADER WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2008-10-14 | 2016-06-11 16:06 | 2016-06-11 16:07 | Yes | 2797 |  | 2016-07-03 09:39 | [6 empty] | 2016-07-03 19:58 | Yes | 8 | 1204-Owner-v | 2018-05-16 14:20
VD-9001-253(A)-DSH-086 | 0 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2015-03-08 09:52 |  | No | 3889 | 2015-04-11 16:59 | [8 empty] | No | 0
VD-9001-253(A)-DWG-087 | 0 | MOTOR WALKWAY GRATING DETAIL AE-3002 | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2016-06-19 16:40 |  | No | 4358 | 2016-06-21 10:58 | [7 empty] | 2016-06-21 19:57 | Yes | 0
VD-9001-253(A)-***-088 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-089 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-090 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-PCJ-091 | 0 | EXPANDING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2003-08-14 | 2014-09-27 12:27 |  | No | 4062 | 2014-10-11 08:48 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-092 | 0 | ERECTION PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-09-16 | 2017-01-14 11:07 | 2017-01-14 11:08 | Yes | 851 |  | 2017-01-15 14:25 | [6 empty] | 2017-01-15 20:00 | Yes | -13 | 1204-Owner-v | 2019-01-31 11:34
VD-9001-253(A)-LST-093 | 0 | SPARE PART LIST | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2015-07-06 12:33 |  | No | 4070 | 2015-07-22 10:24 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-094 | 0 | PACKING AND SHIPPING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-08-23 | 2015-11-23 09:16 | 2015-11-23 10:14 | Yes | 457 |  | 2016-02-03 09:55 | [6 empty] | 2016-02-03 20:02 | Yes | 58 | 1204-Owner-v | 2018-10-01 15:46
VD-9001-253(A)-DIS-097 | 0 | VENDOR DOCUMENT INDEX AND SCHEDULE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2017-08-10 12:41 |  | No | 4775 |  | 2017-09-02 11:05 | [6 empty] | 2017-09-02 19:57 | Yes | 0
VD-9001-253(A)-PCJ-098 | 0 | WELDING DOCUMENT FOR HEADER BOX | HM-253A | FATEH SANAT KIMIA | 2014-04-14 | 2015-01-25 16:47 |  | No | 286 | 2015-02-14 09:01 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-099 | 0 | WELDING DOCUMENT FOR STRUCTURE | HM-253A | FATEH SANAT KIMIA | 2004-10-14 | 2015-04-18 12:12 |  | No | 3838 | 2015-04-27 17:46 | [8 empty] | No | 0
VD-9001-253(A)-ITP-100 | 0 | INSPECTION TEST PLAN | HM-253A | FATEH SANAT KIMIA | 2014-02-26 | 2014-03-05 10:02 |  | No | 7 | 2014-04-07 16:52 | [8 empty] | No | 0 | 1204-Owner-v | 2020-01-01 10:15
VD-9001-253(A)-PCJ-101 | 0 | NDT PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-02-26 | 2014-03-05 10:01 | 2014-03-05 10:54 | Yes | 7 |  | 2014-04-07 16:54 | [6 empty] | 2014-04-07 16:55 | Yes | 19
VD-9001-253(A)-PCJ-102 | 0 | PWHT and HARDNESS TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-03-16 | 2015-01-17 15:38 | 2015-01-17 16:18 | Yes | 307 |  | 2015-02-14 08:49 | [6 empty] | 2015-02-14 08:50 | Yes | 14 | 1204-Owner-v | 2019-07-06 13:04
VD-9001-253(A)-PCJ-103 | 0 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-03-16 | 2015-01-17 15:49 |  | No | 307 | 2015-02-14 08:50 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-104 | 0 | PAINTING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2004-10-14 | 2015-06-02 14:37 |  | No | 3883 | 2015-06-09 09:43 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-105 | 0 | WELDER QUALIFICATION RECORDS | HM-253A | FATEH SANAT KIMIA | 2014-04-14 | 2015-04-18 12:41 | 2015-04-18 14:07 | Yes | 369 |  | 2015-04-27 17:44 | [6 empty] | 2015-04-27 17:45 | Yes | -5
VD-9001-253(A)-PCJ-106 | 0 | INSPECTION TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-02-26 | 2014-03-05 10:03 | 2014-03-05 11:03 | Yes | 7 |  | 2014-04-07 16:53 | [6 empty] | 2014-04-07 16:54 | Yes | 19 | 1204-Owner-v | 2019-07-06 13:00
VD-9001-253(A)-PCJ-107 | 0 | PICKLING AND PASSIVATION | HM-253A | FATEH SANAT KIMIA | 2014-02-28 | 2014-03-05 09:58 | 2014-03-05 10:51 | Yes | 5 |  | 2014-04-07 16:54 | [6 empty] | 2014-04-07 16:55 | Yes | 19 | 1204-Owner-v | 2019-07-06 14:20
VD-9001-253(A)-PCJ-108 | 0 | COMMISSIONING, OPERATION AND MAINTENANCE PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-08-23 | 2016-03-06 11:03 | 2016-03-06 11:04 | Yes | 561 |  | 2016-04-05 14:32 | [6 empty] | 2016-04-05 20:00 | Yes | 16 | 1204-Owner-v | 2018-04-21 10:58
VD-9001-253(A)-LST-109 | 0 | LIST OF ALL ELECTRICAL CONSUMERS | HM-253A | FATEH SANAT KIMIA | 2004-05-14 | 2016-06-15 14:44 | 2016-06-15 14:45 | Yes | 4415 |  | 2016-06-29 15:22 | [6 empty] | 2016-06-29 19:58 | Yes | 0 | 1204-Owner-v | 2019-05-12 10:34
VD-9001-253(A)-CAL-110 | 0 | THERMAL CALCULATION BOOK | HM-253A | FATEH SANAT KIMIA | 2014-04-14 | 2016-06-16 12:04 | 2016-06-16 12:05 | Yes | 794 |  | 2016-09-11 14:50 | [6 empty] | 2016-09-11 19:56 | Yes | 73 | 1204-Owner-v | 2019-06-23 10:54
VD-9001-253(A)-PCJ-111 | 0 | PMI PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-04-14 | 2015-01-17 15:54 | 2015-01-17 16:19 | Yes | 278 |  | 2015-02-14 08:51 | [6 empty] | 2015-02-14 08:52 | Yes | 14
VD-9001-253(A)-PCJ-112 | 0 | REPAIR PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-04-14 | 2016-02-18 09:33 |  | No | 675 | 2016-03-02 15:53 | [7 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-253(A)-RPT-113 | 0 | HSE PLAN | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2017-10-19 15:56 |  | No | 4845 | 2017-10-22 10:31 | [7 empty] | 2017-10-22 19:59 | Yes | 0
VD-9001-253(A)-RPT-114 | 0 | HSE INSTRUCTION | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2018-01-17 10:24 |  | No | 4935 | 2018-01-20 09:30 | [7 empty] | 2018-01-20 19:59 | Yes | 0
VD-9001-253(A)-MDB-115 | 0 | FINAL DATA BOOK INDEX | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2017-08-26 15:40 |  | No | 4791 | 2017-09-24 16:27 | [7 empty] | 2017-09-24 18:58 | Yes | 0
VD-9001-253(A)-LST-117 | 0 | SUB-VENDOR LIST | HM-253A | FATEH SANAT KIMIA | 2004-07-14 | 2015-05-23 11:58 | 2015-05-23 14:09 | Yes | 3965 | 2016-05-24 15:28 | 2018-01-06 15:57 | [6 empty] | 2018-01-06 20:00 | Yes | 353 | 1204-Owner-v | 2018-10-01 15:45
VD-9001-253(A)-***-118 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-119 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-253(A)-***-120 | 0 | RESERVE | HM-253A | FATEH SANAT KIMIA | 2004-07-14 |  |  | No | 5819 | [9 empty] | No | 0
VD-9001-213A-DWG-065 | 4 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-23 | 2014-03-19 16:27 |  | No | -4 | 2014-04-28 16:32 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 4 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-23 | 2014-03-19 16:30 |  | No | -4 | 2014-04-28 16:39 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 4 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-23 | 2014-04-07 17:13 |  | No | 15 | 2014-04-29 15:47 | [8 empty] | No | 0
VD-9001-213B-CAL-001 | 3 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-24 | 2014-03-19 09:01 |  | No | -5 | 2014-04-12 17:13 | [8 empty] | No | 0
VD-9001-213B-DWG-023 | 4 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-26 | 2014-03-19 13:40 |  | No | -7 | 2014-06-02 11:32 | [8 empty] | No | 0
VD-9001-213A-CAL-008 | 5 | Mechanical Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-29 | 2014-03-18 15:55 | 2014-03-18 16:14 | Yes | -11 |  | 2014-03-19 11:06 | [6 empty] | 2014-03-19 11:07 | Yes | -13
VD-9001-213A-DWG-051 | 2 | Shell Manhole for Tk-2201 | PV-213A | MachineSazi Pars | 2014-03-29 | 2014-03-18 15:58 | 2014-03-18 16:10 | Yes | -11 |  | 2014-03-19 11:05 | [6 empty] | 2014-03-19 11:06 | Yes | -13
VD-9001-213A-DWG-071 | 2 | Shell Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-03-29 | 2014-03-18 15:59 |  | No | -11 | 2014-03-19 11:02 | [8 empty] | No | 0
VD-9001-213A-DWG-109 | 2 | Shell Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-29 | 2014-03-18 16:01 |  | No | -11 | 2014-03-19 11:03 | [8 empty] | No | 0
VD-9001-213A-DWG-135 | 2 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-03-29 | 2014-03-18 16:02 |  | No | -11 | 2014-03-19 11:03 | [8 empty] | No | 0
VD-9001-213B-DWG-032 | 1 | Anchor Chair for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-29 | 2014-03-19 09:04 |  | No | -10 | 2014-04-12 17:11 | [8 empty] | No | 0
VD-9001-213B-DWG-033 | 1 | Earth Lug for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-29 | 2014-03-19 09:05 | 2014-03-19 11:28 | Yes | -10 |  | 2014-04-05 12:13 | [6 empty] | 2014-04-05 12:14 | Yes | 3
VD-9001-213A-DWG-111 | 4 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-03-30 | 2014-03-18 15:56 |  | No | -12 |  | 2014-03-19 11:05 | [7 empty] | No | 0
VD-9001-213B-DWG-030 | 1 | Roof Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-30 | 2014-03-19 09:03 |  | No | -11 | 2014-04-26 12:45 | [8 empty] | No | 0
VD-9001-213B-DWG-029 | 1 | Shell Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-03-30 | 2014-03-19 09:02 |  | No | -11 | 2014-04-20 18:09 | [8 empty] | No | 0
VD-9001-213A-DWG-054 | 1 | Anchor Chair for Tk-2201 | PV-213A | MachineSazi Pars | 2014-04-01 | 2014-04-16 16:35 |  | No | 15 | 2014-04-26 08:46 | [8 empty] | No | 0
VD-9001-213A-DWG-074 | 1 | Anchor Chair for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-01 | 2014-04-16 16:39 |  | No | 15 | 2014-04-26 08:47 | [8 empty] | No | 0
VD-9001-213A-DWG-112 | 1 | Anchor Chair for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-04-01 | 2014-04-16 16:43 |  | No | 15 | 2014-04-26 08:48 | [8 empty] | No | 0
VD-9001-213A-DWG-138 | 1 | Anchor Chair for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-01 | 2014-04-16 16:49 |  | No | 15 | 2014-04-26 08:49 | [8 empty] | No | 0
VD-9001-213A-DWG-071 | 3 | Shell Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-08 16:07 |  | No | 6 | 2014-05-03 17:05 | [8 empty] | No | 0
VD-9001-213A-DWG-109 | 3 | Shell Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-08 16:09 |  | No | 6 | 2014-05-03 17:05 | [8 empty] | No | 0
VD-9001-213A-DWG-135 | 3 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-08 16:10 |  | No | 6 | 2014-05-03 17:06 | [8 empty] | No | 0
VD-9001-213A-DWG-055 | 1 | Earth Lug for Tk-2201 | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-05 11:47 |  | No | 3 | 2014-04-09 10:03 | [8 empty] | No | 0
VD-9001-213A-DWG-075 | 1 | Earth Lug for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-05 11:49 |  | No | 3 | 2014-04-09 10:03 | [8 empty] | No | 0
VD-9001-213A-DWG-113 | 1 | Earth Lug for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-05 11:51 |  | No | 3 | 2014-04-09 10:04 | [8 empty] | No | 0
VD-9001-213A-DWG-139 | 1 | Earth Lug for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-02 | 2014-04-05 11:52 |  | No | 3 | 2014-04-09 10:04 | [8 empty] | No | 0
VD-9001-213B-DWG-019 | 2 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-19 | 2014-04-23 15:58 |  | No | 4 | 2014-05-18 10:40 | [8 empty] | No | 0
VD-9001-213A-DWG-045 | 1 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-04-19 | 2014-04-08 16:02 |  | No | -11 | 2014-04-29 15:51 | [8 empty] | No | 0
VD-9001-213A-DWG-064 | 1 | Fixed Roof Orientation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-19 | 2014-04-08 16:03 |  | No | -11 | 2014-04-29 15:52 | [8 empty] | No | 0
VD-9001-213A-DWG-087 | 1 | Fixed Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2014-04-19 | 2015-09-07 13:19 |  | No | 506 | 2015-09-19 08:58 | [8 empty] | No | 0
VD-9001-213A-DWG-088 | 1 | Fixed Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2014-04-19 | 2015-09-07 13:19 |  | No | 506 | 2015-09-19 08:59 | [8 empty] | No | 0
VD-9001-213A-DWG-128 | 1 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-19 | 2014-04-08 16:05 |  | No | -11 | 2014-09-07 17:15 | [8 empty] | No | 0
VD-9001-253(A)-ITP-100 | 1 | INSPECTION TEST PLAN | HM-253A | FATEH SANAT KIMIA | 2014-04-21 | 2015-04-08 09:08 |  | No | 352 | 2015-04-29 17:02 | [8 empty] | No | 0 | 1204-Owner-v | 2020-01-01 10:15
VD-9001-213A-DWG-055 | 2 | Earth Lug for Tk-2201 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-09 16:15 | 2014-04-09 16:36 | Yes | -14 |  | 2014-04-09 17:57 | [6 empty] | 2014-04-09 17:58 | Yes | -14
VD-9001-213A-DWG-075 | 2 | Earth Lug for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-09 16:16 | 2014-04-09 16:37 | Yes | -14 |  | 2014-04-09 17:58 | [6 empty] | 2014-04-09 17:59 | Yes | -14 | 1204-Owner-v | 2019-12-30 09:17
VD-9001-213A-DWG-113 | 2 | Earth Lug for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-09 16:18 | 2014-04-09 16:38 | Yes | -14 |  | 2014-04-09 17:58 | [6 empty] | 2014-04-09 17:59 | Yes | -14
VD-9001-213A-DWG-139 | 2 | Earth Lug for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-09 16:19 | 2014-04-09 16:38 | Yes | -14 |  | 2014-04-09 17:58 | [6 empty] | 2014-04-09 17:59 | Yes | -14
VD-9001-213A-DWG-042 | 2 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-14 07:01 |  | No | -9 | 2014-04-27 10:47 | [8 empty] | No | 0
VD-9001-213A-DWG-061 | 2 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-14 07:03 |  | No | -9 | 2014-04-27 10:48 | [8 empty] | No | 0
VD-9001-213A-DWG-082 | 2 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-14 07:05 |  | No | -9 | 2014-04-27 10:48 | [8 empty] | No | 0
VD-9001-213A-DWG-083 | 2 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-14 07:06 |  | No | -9 | 2014-04-27 10:49 | [8 empty] | No | 0
VD-9001-213A-PCJ-036 | 1 | NDT Procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-04-23 08:41 | 2014-04-23 09:53 | Yes | 0 |  | 2014-06-03 10:04 | [6 empty] | 2014-06-03 10:05 | Yes | 27
VD-9001-213A-PCJ-038 | 1 | Painting procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-23 | 2014-05-01 07:40 |  | No | 8 | 2014-08-05 17:34 | [8 empty] | No | 0
VD-9001-206A-FAS-001 | 0 | Time scheduele | PV-206A | TASHA | 2004-06-14 |  |  | No | 5849 | [9 empty] | No | 0
VD-9001-206A-MPR-001 | 0 | MONTHLY PROGRESS REPORT | PV-206A | TASHA | 2014-04-25 |  |  | No | 2247 | [9 empty] | No | 0
VD-9001-206A-ITP-001 | 0 | INSPECTION AND TEST PLAN | PV-206A | TASHA | 2004-08-14 | 2014-04-13 12:36 |  | No | 3529 | 2014-04-21 17:23 | [8 empty] | No | 0 | 1204-Owner-v | 2020-01-01 12:53
VD-9001-206A-PCJ-001 | 0 | MAGNETIC TEST PROCEDURE (MT) | PV-206A | TASHA | 2014-05-25 | 2014-05-11 15:29 | 2014-05-11 16:22 | Yes | -14 |  | 2014-07-28 16:16 | [6 empty] | 2014-07-28 16:17 | Yes | 64
VD-9001-206A-PCJ-002 | 0 | VISUAL INSPECTION PROCEDURE (VT) | PV-206A | TASHA | 2014-05-25 | 2014-05-11 15:36 | 2014-05-11 16:23 | Yes | -14 |  | 2014-07-28 16:17 | [6 empty] | 2014-07-28 16:18 | Yes | 1
VD-9001-206A-PCJ-003 | 0 | RADIOGRPHY TEST PROCEDURE (RT) | PV-206A | TASHA | 2014-05-25 | 2014-05-11 15:40 | 2014-05-11 16:24 | Yes | -14 |  | 2014-07-28 16:17 | [6 empty] | 2014-07-28 16:18 | Yes | 1
VD-9001-206A-PCJ-004 | 0 | LIQUID PENETRANT TEST PROCEDURE (PT) | PV-206A | TASHA | 2014-05-25 | 2014-05-11 15:42 | 2014-05-11 16:25 | Yes | -14 |  | 2014-07-28 16:18 | [6 empty] | 2014-07-28 16:19 | Yes | 1
VD-9001-206A-PCJ-005 | 0 | ULTRASONIC TEST PROCEDURE (UT) | PV-206A | TASHA | 2014-05-25 | 2014-05-11 15:43 | 2014-05-11 16:25 | Yes | -14 |  | 2014-07-28 16:18 | [6 empty] | 2014-07-28 16:19 | Yes | 64
VD-9001-206A-PCJ-006 | 0 | NDT Personal QUALIFICATION | PV-206A | TASHA | 2006-02-14 | 2014-12-11 13:18 | 2014-12-14 10:26 | Yes | 3225 |  | 2014-12-27 15:12 | [6 empty] | 2014-12-27 15:13 | Yes | 2
VD-9001-206A-WBK-001 | 0 | WELDING BOOK (WPS & PQR) | PV-206A | TASHA | 2005-08-14 | 2014-04-21 09:24 |  | No | 3172 | 2014-07-09 10:58 | [8 empty] | No | 0
VD-9001-206A-WMP-001 | 0 | WELDING MAP & NDT TABLE | PV-206A | TASHA | 2014-05-25 | 2014-04-26 08:39 |  | No | -29 | 2014-07-09 11:04 | [8 empty] | No | 0
VD-9001-206A-PCJ-007 | 0 | REPAIR PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-07-01 11:44 |  | No | 3059 | 2014-07-26 15:53 | [8 empty] | No | 0
VD-9001-206A-PCJ-008 | 0 | POST WELD HEAT TREATMENT PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-05-26 16:16 |  | No | 3023 | 2014-06-29 16:52 | [8 empty] | No | 0
VD-9001-206A-PCJ-009 | 0 | HARDNESS TEST PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-05-26 16:18 |  | No | 3023 | 2014-06-29 16:53 | [8 empty] | No | 0
VD-9001-206A-PCJ-010 | 0 | PENUMATIC TEST PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-07-01 11:48 |  | No | 3059 | 2014-07-26 15:53 | [8 empty] | No | 0
VD-9001-206A-PCJ-011 | 0 | HYDRO TEST PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-07-01 11:50 |  | No | 3059 | 2014-07-26 15:54 | [8 empty] | No | 0
VD-9001-206A-PCJ-012 | 0 | BLASTING & PAINTING PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-07-01 11:52 |  | No | 3059 | 2014-07-26 15:54 | [8 empty] | No | 0
VD-9001-206A-PCJ-013 | 0 | PACKING ,MARKING,LOADING&SHIPPING PROCEDURE | PV-206A | TASHA | 2006-02-14 | 2014-07-01 11:54 | 2014-07-01 14:52 | Yes | 3059 |  | 2014-11-23 14:43 | [6 empty] | 2014-11-23 14:44 | Yes | 131
VD-9001-206A-PCJ-014 | 0 | Erection procedure | PV-206A | TASHA | 2006-02-14 | 2015-02-16 09:15 |  | No | 3289 | 2015-04-05 15:18 | [8 empty] | No | 0
VD-9001-206A-SPL-001 | 0 | SPARE PART LIST FOR COMMISIONING & START UP | PV-206A | TASHA | 2006-02-14 | 2015-02-18 17:20 |  | No | 3291 | 2015-06-17 10:47 | [8 empty] | No | 0
VD-9001-206A-SPL-002 | 0 | SPARE PART LIST FOR TWO YEARS OPERATION | PV-206A | TASHA | 2006-02-14 | 2015-02-18 17:20 |  | No | 3291 | 2015-08-01 11:05 | [8 empty] | No | 0
VD-9001-206A-INX-001 | 0 | FINAL DATA BOOK INDEX | PV-206A | TASHA | 2006-02-14 | 2015-02-18 17:18 | 2015-02-18 17:51 | Yes | 3291 |  | 2015-04-06 15:52 | [6 empty] | 2015-04-06 15:53 | Yes | 33
VD-9001-206A-CAL-001 | 0 | MECHANICAL CALCULATION BOOK ( T-3001 ) | PV-206A | TASHA | 2004-06-14 | 2014-04-13 12:06 |  | No | 3590 | 2014-05-12 11:42 | [8 empty] | No | 0
VD-9001-206A-CAL-002 | 0 | EXTERNAL ATTACHMENT & LIFTING LUG CALCULATION ( T-3001 ) | PV-206A | TASHA | 2014-05-15 | 2014-06-21 15:05 |  | No | 37 | 2014-07-29 11:07 | [8 empty] | No | 0
VD-9001-206A-DWG-001 | 0 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2004-06-14 | 2014-04-13 12:09 |  | No | 3590 | 2014-06-10 15:07 | [8 empty] | No | 0
VD-9001-206A-DWG-002 | 0 | BODY & SUPPORT DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2004-06-14 | 2014-04-13 12:16 |  | No | 3590 | 2014-05-12 11:44 | [8 empty] | No | 0
VD-9001-206A-DWG-003 | 0 | NOZZLE DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2005-04-14 | 2014-06-21 15:12 |  | No | 3355 | 2014-08-18 10:14 | [8 empty] | No | 0
VD-9001-206A-DWG-004 | 0 | INTERNAL ATTACHMENT DRAWING ( T-3001 ) | PV-206A | TASHA | 2005-04-14 | 2015-02-17 10:01 |  | No | 3596 | 2015-04-19 10:39 | [8 empty] | No | 0
VD-9001-206A-DWG-005 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-05-15 | 2014-10-07 13:37 |  | No | 145 | 2014-10-29 10:07 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-22 09:53
VD-9001-206A-DWG-006 | 0 | INSULATION SUPPORT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-05-15 | 2014-09-09 18:03 |  | No | 117 | 2014-11-02 10:42 | [8 empty] | No | 0
VD-9001-206A-DWG-007 | 0 | TOP DAVIT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-05-15 | 2014-09-03 20:21 |  | No | 111 | [9 empty] | No | 0
VD-9001-206A-DWG-008 | 0 | PIPE CLIP DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-05-15 | 2014-09-03 20:22 |  | No | 111 | 2014-09-27 16:26 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-22 10:22
VD-9001-206A-DWG-009 | 0 | NAME PLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2005-04-14 | 2014-09-03 20:22 |  | No | 3429 | 2014-10-11 15:55 | [8 empty] | No | 0
VD-9001-206A-DWG-010 | 0 | TEMPLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-04-17 | 2014-04-26 08:36 |  | No | 9 | 2014-06-21 10:21 | [8 empty] | No | 0
VD-9001-206A-CAL-003 | 0 | MECHANICAL CALCULATION BOOK ( T-3002 ) | PV-206A | TASHA | 2004-09-14 | 2014-04-15 08:40 |  | No | 3500 | 2014-05-12 11:52 | [8 empty] | No | 0
VD-9001-206A-CAL-004 | 0 | EXTERNAL ATTACHMENT & LIFTING LUG CALCULATION ( T-3002 ) | PV-206A | TASHA | 2014-05-22 | 2014-07-06 17:52 | 2014-07-07 12:07 | Yes | 46 |  | 2014-07-29 11:21 | [6 empty] | 2014-07-29 11:22 | Yes | 9
VD-9001-206A-DWG-011 | 0 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2004-09-14 | 2014-04-15 09:42 |  | No | 3500 | 2014-06-11 08:53 | [8 empty] | No | 0
VD-9001-206A-DWG-012 | 0 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2004-09-14 | 2014-04-15 09:44 |  | No | 3500 | 2014-06-15 09:56 | [8 empty] | No | 0
VD-9001-206A-DWG-013 | 0 | NOZZLE DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2005-07-14 | 2014-07-01 12:01 |  | No | 3274 | 2014-08-18 10:24 | [8 empty] | No | 0
VD-9001-206A-DWG-014 | 0 | INTERNAL ATTACHMENT DRAWING ( T-3002 ) | PV-206A | TASHA | 2005-07-14 | 2015-03-28 11:22 |  | No | 3544 | 2015-04-19 10:51 | [8 empty] | No | 0
VD-9001-206A-DWG-015 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-05-22 | 2015-01-29 10:35 |  | No | 252 | 2015-02-17 17:49 | [8 empty] | No | 0
VD-9001-206A-DWG-016 | 0 | INSULATION SUPPORT DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-05-22 | 2014-12-04 13:08 |  | No | 196 | 2015-02-17 11:21 | [8 empty] | No | 0
VD-9001-206A-DWG-017 | 0 | TOP DAVIT DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-05-22 | 2014-09-24 10:34 |  | No | 125 | 2014-11-25 17:45 | [8 empty] | No | 0
VD-9001-206A-DWG-018 | 0 | PIPE CLIP DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-05-22 | 2014-11-30 16:48 |  | No | 192 | 2014-12-27 11:52 | [8 empty] | No | 0
VD-9001-206A-DWG-019 | 0 | NAME PLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2005-07-14 | 2014-09-24 10:35 |  | No | 3359 | 2015-04-06 16:10 | 2014-11-25 17:46 | [7 empty] | No | 0
VD-9001-206A-DWG-020 | 0 | TEMPLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-04-17 | 2014-04-26 08:37 |  | No | 9 | 2014-06-21 10:22 | [8 empty] | No | 0
VD-9001-206A-CAL-005 | 0 | MECHANICAL CALCULATION BOOK ( T-3003 ) | PV-206A | TASHA | 2014-04-13 | 2014-04-21 09:20 |  | No | 8 | 2014-05-12 11:55 | [8 empty] | No | 0
VD-9001-206A-CAL-006 | 0 | EXTERNAL ATTACHMENT & LIFTING LUG CALCULATION ( T-3003 ) | PV-206A | TASHA | 2014-05-29 | 2014-07-13 12:07 | 2014-07-13 14:38 | Yes | 45 |  | 2014-11-02 11:21 | [6 empty] | 2014-11-02 11:22 | Yes | 98
VD-9001-206A-DWG-021 | 0 | GENERAL ARRANGMENT ( T-3003 ) | PV-206A | TASHA | 2014-04-13 | 2014-04-21 09:16 |  | No | 8 | 2014-06-10 18:03 | [8 empty] | No | 0
VD-9001-206A-DWG-022 | 0 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-04-13 | 2014-04-21 09:18 |  | No | 8 | 2014-06-15 10:02 | [8 empty] | No | 0
VD-9001-206A-DWG-023 | 0 | NOZZLE DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2005-11-14 | 2014-07-13 12:19 |  | No | 3163 | 2014-08-18 10:30 | [8 empty] | No | 0
VD-9001-206A-DWG-024 | 0 | INTERNAL ATTACHMENT DRAWING ( T-3003 ) | PV-206A | TASHA | 2005-11-14 | 2015-05-10 09:15 |  | No | 3464 | 2015-05-25 17:18 | [8 empty] | No | 0
VD-9001-206A-DWG-025 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-05-29 | 2014-12-20 17:17 |  | No | 205 | 2015-01-17 10:30 | [8 empty] | No | 0
VD-9001-206A-DWG-026 | 0 | INSULATION SUPPORT DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-05-29 | 2014-12-04 13:11 |  | No | 189 | 2015-02-17 11:22 | [8 empty] | No | 0
VD-9001-206A-DWG-027 | 0 | TOP DAVIT DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-05-29 | 2014-09-24 11:41 |  | No | 118 | 2014-11-25 17:53 | [8 empty] | No | 0
VD-9001-206A-DWG-028 | 0 | PIPE CLIP DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-05-29 | 2014-11-30 16:50 |  | No | 185 | 2014-12-09 09:47 | [8 empty] | No | 0
VD-9001-206A-DWG-029 | 0 | NAME PLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2005-11-14 | 2014-09-24 10:44 |  | No | 3236 | 2015-04-06 16:11 | 2014-11-25 17:54 | [7 empty] | No | 0
VD-9001-206A-DWG-030 | 0 | TEMPLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-04-17 | 2014-04-26 08:38 |  | No | 9 | 2014-06-21 10:23 | [8 empty] | No | 0
VD-9001-213B-DWG-032 | 2 | Anchor Chair for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-26 | 2014-04-23 16:00 |  | No | -3 | 2014-05-03 16:34 | [8 empty] | No | 0
VD-9001-213B-CAL-001 | 4 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-26 | 2014-05-11 07:06 |  | No | 15 | 2014-05-17 17:17 | [8 empty] | No | 0
VD-9001-213B-PCJ-016 | 1 | Painting & Pickling and Passivation procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-26 | 2014-06-08 06:43 |  | No | 43 | 2014-06-25 14:36 | [8 empty] | No | 0
VD-9001-213B-PCJ-014 | 1 | NDT Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-27 | 2014-04-23 08:39 |  | No | -4 | 2014-05-26 09:34 | [8 empty] | No | 0
VD-9001-213A-DWG-126 | 3 | Bottom Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-13 | 2014-04-14 13:05 | 2014-04-14 14:24 | Yes | 1 |  | 2014-04-14 15:25 | [6 empty] | 2014-04-14 15:26 | Yes | -14
VD-9001-253(A)-DSH-001 | 1 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-04-27 | 2014-05-20 12:12 |  | No | 23 | 2014-05-21 15:02 | [8 empty] | No | 0
VD-9001-253(A)-DSH-031 | 1 | THERMAL & MECHANICAL DATA SHEET for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-04-27 | 2014-05-20 12:30 |  | No | 23 | 2014-05-21 15:03 | [8 empty] | No | 0
VD-9001-253(A)-DSH-061 | 1 | THERMAL & MECHANICAL DATA SHEET for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-04-27 | 2014-05-20 12:36 |  | No | 23 | 2014-05-21 15:03 | [8 empty] | No | 0
VD-9001-213A-CAL-022 | 4 | Mechanical Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-04-28 | 2014-04-19 13:47 | 2014-04-19 14:06 | Yes | -9 |  | 2014-05-07 09:38 | [6 empty] | 2014-05-07 09:39 | Yes | 4
VD-9001-213AB-PCJ-013 | 1 | Hydro Test and Air Test Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-03 | 2014-04-27 07:18 |  | No | -6 | 2014-05-26 15:01 | [8 empty] | No | 0
VD-9001-213B-DWG-029 | 2 | Shell Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-04 | 2014-04-27 07:19 |  | No | -7 | 2014-05-03 16:29 | [8 empty] | No | 0
VD-9001-206A-ITP-001 | 1 | INSPECTION AND TEST PLAN | PV-206A | TASHA | 2014-05-05 | 2014-05-11 15:44 |  | No | 6 |  | 2014-07-28 16:15 | [7 empty] | No | 0 | 1204-Owner-v | 2020-01-01 12:53
VD-9001-213B-DWG-031 | 4 | Drain Sump for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-04-23 | 2014-04-23 14:57 | 2014-04-23 15:16 | Yes | 0 |  | 2014-04-26 12:33 | [6 empty] | 2014-04-26 12:34 | Yes | -11
VD-9001-213A-DWG-054 | 2 | Anchor Chair for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-10 | 2014-04-27 07:08 |  | No | -13 |  | 2014-04-27 11:26 | [7 empty] | No | 0
VD-9001-213A-DWG-074 | 2 | Anchor Chair for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-10 | 2014-04-27 07:11 | 2014-04-27 09:47 | Yes | -13 |  | 2014-04-27 11:27 | [6 empty] | 2014-04-27 11:28 | Yes | -14
VD-9001-213A-DWG-112 | 2 | Anchor Chair for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-10 | 2014-04-27 07:14 |  | No | -13 |  | 2014-04-27 11:28 | [7 empty] | No | 0
VD-9001-213A-DWG-138 | 2 | Anchor Chair for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-10 | 2014-04-27 07:15 | 2014-04-27 09:49 | Yes | -13 |  | 2014-04-27 11:28 | [6 empty] | 2014-04-27 11:29 | Yes | -14
VD-9001-213B-DWG-028 | 1 | Roof Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-10 | 2014-04-27 15:46 |  | No | -13 |  | 2014-05-03 16:39 | [7 empty] | No | 0
VD-9001-213B-DWG-030 | 2 | Roof Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-10 | 2014-04-27 15:48 | 2014-04-27 16:29 | Yes | -13 |  | 2014-05-03 16:44 | [6 empty] | 2014-05-03 16:45 | Yes | -8
VD-9001-213A-CAL-015 | 2 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-10 | 2014-05-24 11:55 |  | No | 14 | 2014-06-28 16:55 | [8 empty] | No | 0
VD-9001-213A-DWG-042 | 3 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-04-28 11:41 |  | No | -13 |  | 2014-04-29 11:58 | [7 empty] | No | 0
VD-9001-213A-DWG-061 | 3 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-04-28 11:43 |  | No | -13 |  | 2014-04-29 11:58 | [7 empty] | No | 0
VD-9001-213A-DWG-082 | 3 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-04-28 11:45 |  | No | -13 |  | 2014-04-29 11:59 | [7 empty] | No | 0
VD-9001-213A-DWG-083 | 3 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-04-28 11:46 |  | No | -13 |  | 2014-04-29 11:59 | [7 empty] | No | 0
VD-9001-213A-DWG-065 | 5 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-12 | 2014-07-23 10:28 |  | No | 72 | 2014-08-05 17:45 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 5 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-12 | 2014-07-28 12:01 |  | No | 77 | 2014-08-16 09:39 | [8 empty] | No | 0
VD-9001-213A-DWG-129 | 5 | Roof Structure for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-13 | 2015-08-15 12:52 | 2015-08-15 14:26 | Yes | 459 |  | 2015-09-05 14:21 | [6 empty] | 2015-09-05 14:22 | Yes | 7
VD-9001-213A-DWG-045 | 2 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-13 | 2014-04-30 11:24 |  | No | -13 | 2014-05-24 15:32 | [8 empty] | No | 0
VD-9001-213A-DWG-064 | 2 | Fixed Roof Orientation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-13 | 2014-04-30 11:26 |  | No | -13 | 2014-05-03 17:10 | [8 empty] | No | 0
VD-9001-213A-DWG-086 | 2 | Fixed Roof Plate for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-01 | 2014-05-03 06:46 | 2014-05-03 11:40 | Yes | 2 |  | 2014-05-03 17:17 | [6 empty] | 2014-05-03 17:18 | Yes | -14
VD-9001-213A-DWG-112 | 3 | Anchor Chair for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-01 | 2014-05-03 06:48 | 2014-05-03 11:41 | Yes | 2 |  | 2014-05-03 17:18 | [6 empty] | 2014-05-03 17:19 | Yes | -14
VD-9001-213B-DWG-029 | 3 | Shell Manhole for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-17 | 2014-05-07 14:16 | 2014-05-07 15:12 | Yes | -10 |  | 2014-05-12 09:38 | [6 empty] | 2014-05-12 09:39 | Yes | -9
VD-9001-213B-DWG-032 | 3 | Anchor Chair for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-17 | 2014-05-07 14:18 | 2014-05-07 15:14 | Yes | -10 |  | 2014-06-10 14:16 | [6 empty] | 2014-06-10 14:17 | Yes | 20
VD-9001-213A-DWG-125 | 2 | Shell Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-05-07 12:30 |  | No | -10 |  | 2014-05-18 16:13 | [7 empty] | No | 0
VD-9001-213A-WPS-031 | 1 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-06-10 07:25 |  | No | 24 | 2014-06-29 14:55 | [8 empty] | No | 0
VD-9001-213A-DWG-071 | 4 | Shell Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-05-07 12:25 | 2014-05-07 12:52 | Yes | -10 | 2014-05-18 16:32 | [7 empty] | 2014-05-18 16:33 | Yes | -3
VD-9001-213A-DWG-109 | 4 | Shell Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-05-07 12:28 | 2014-05-07 12:53 | Yes | -10 | 2014-05-18 16:33 | [7 empty] | 2014-05-18 16:34 | Yes | -3
VD-9001-213A-DWG-135 | 4 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-05-07 12:34 |  | No | -10 |  | 2014-05-18 16:13 | [7 empty] | No | 0
VD-9001-213A-DWG-064 | 3 | Fixed Roof Orientation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-17 | 2014-05-07 12:23 |  | No | -10 | 2014-07-08 15:20 | [8 empty] | No | 0
VD-9001-213A-DWG-093 | 1 | Deck Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-18 | 2014-12-22 09:42 |  | No | 218 | 2015-02-23 16:24 | [8 empty] | No | 0
VD-9001-213A-DWG-094 | 1 | Pontoon Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-18 | 2014-12-24 11:45 |  | No | 220 | 2015-02-23 16:37 | [8 empty] | No | 0
VD-9001-213A-DWG-049 | 1 | Shell Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-19 | 2014-05-14 07:45 |  | No | -5 |  | 2014-06-25 17:43 | [7 empty] | No | 0
VD-9001-213A-DWG-069 | 1 | Shell Nozzles for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-19 | 2014-05-14 07:50 | 2014-05-14 10:04 | Yes | -5 |  | 2014-06-25 17:45 | [6 empty] | 2014-06-25 17:46 | Yes | 28
VD-9001-213A-DWG-107 | 1 | Shell Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-19 | 2014-05-14 07:55 |  | No | -5 | 2014-06-25 17:46 | [8 empty] | No | 0
VD-9001-213A-DWG-133 | 1 | Shell Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-19 | 2014-05-14 08:01 |  | No | -5 |  | 2014-06-25 17:47 | [7 empty] | No | 0
VD-9001-213A-DWG-050 | 1 | Roof Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-20 | 2014-05-14 07:47 | 2014-05-14 10:03 | Yes | -6 |  | 2014-06-25 17:44 | [6 empty] | 2014-06-25 17:45 | Yes | 28
VD-9001-213A-DWG-070 | 1 | Roof Nozzles for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-20 | 2014-05-14 07:52 | 2014-05-14 10:04 | Yes | -6 |  | 2014-06-25 17:45 | [6 empty] | 2014-06-25 17:46 | Yes | 28
VD-9001-213A-DWG-108 | 1 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-20 | 2014-05-14 07:58 |  | No | -6 | 2014-06-25 17:47 | [8 empty] | No | 0
VD-9001-213A-DWG-134 | 1 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-20 | 2014-05-14 08:03 |  | No | -6 | 2014-06-25 17:48 | [8 empty] | No | 0
VD-9001-213A-DWG-056 | 1 | Name Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-05-11 07:19 |  | No | -10 | 2014-05-18 15:59 | [8 empty] | No | 0
VD-9001-213A-DWG-076 | 1 | Name Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-05-11 07:21 |  | No | -10 | 2014-05-18 16:00 | [8 empty] | No | 0
VD-9001-213A-DWG-114 | 1 | Name Plate for Tk-7101A | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-05-11 07:24 |  | No | -10 | 2014-05-18 16:04 | [8 empty] | No | 0
VD-9001-213A-DWG-115 | 1 | Name Plate for Tk-7101B | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-05-11 07:26 |  | No | -10 | 2014-05-18 16:05 | [8 empty] | No | 0
VD-9001-213A-DWG-140 | 1 | Name Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-05-11 07:29 |  | No | -10 | 2014-05-18 16:05 | [8 empty] | No | 0
VD-9001-213A-PQR-032 | 1 | PQR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-21 | 2014-06-10 07:20 |  | No | 20 | 2014-06-29 14:56 | [8 empty] | No | 0
VD-9001-213B-DWG-034 | 1 | Name Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-21 | 2014-05-11 07:09 |  | No | -10 | 2014-05-25 17:17 | [8 empty] | No | 0
VD-9001-213B-DWG-028 | 2 | Roof Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-07 | 2014-05-11 07:07 |  | No | 4 | 2014-05-11 12:03 | [8 empty] | No | 0
VD-9001-213A-DWG-136 | 2 | Roof Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-05-11 09:38 | 2014-05-11 09:54 | Yes | 0 |  | 2014-05-18 15:47 | [6 empty] | 2014-05-18 15:48 | Yes | -7
VD-9001-213A-DWG-110 | 2 | Roof Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-05-11 09:36 | 2014-05-11 09:54 | Yes | 0 |  | 2014-05-18 15:47 | [6 empty] | 2014-05-18 15:48 | Yes | -7
VD-9001-213A-DWG-072 | 2 | Roof Manhole for Tk-6401 | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-05-11 09:33 | 2014-05-11 09:52 | Yes | 0 |  | 2014-05-18 15:46 | [6 empty] | 2014-05-18 15:47 | Yes | -7
VD-9001-213A-DWG-082 | 4 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-05-18 11:40 |  | No | 7 |  | 2014-05-18 15:38 | [7 empty] | No | 0
VD-9001-213A-DWG-083 | 4 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-05-11 | 2014-05-18 11:43 |  | No | 7 |  | 2014-05-18 15:39 | [7 empty] | No | 0
VD-9001-213B-DWG-028 | 3 | Roof Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-25 | 2014-06-08 06:45 | 2014-06-08 09:15 | Yes | 14 |  | 2014-06-09 10:35 | [6 empty] | 2014-06-09 10:36 | Yes | -13
VD-9001-206A-CAL-001 | 1 | MECHANICAL CALCULATION BOOK ( T-3001 ) | PV-206A | TASHA | 2014-05-26 | 2014-06-21 15:03 |  | No | 26 | 2014-07-29 11:05 | [8 empty] | No | 0
VD-9001-206A-DWG-002 | 1 | BODY & SUPPORT DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-05-26 | 2014-06-21 15:09 |  | No | 26 | 2014-07-29 11:08 | [8 empty] | No | 0
VD-9001-206A-CAL-003 | 1 | MECHANICAL CALCULATION BOOK ( T-3002 ) | PV-206A | TASHA | 2014-05-26 | 2014-07-01 11:57 |  | No | 36 | 2014-10-29 14:36 | [8 empty] | No | 0
VD-9001-206A-CAL-005 | 1 | MECHANICAL CALCULATION BOOK ( T-3003 ) | PV-206A | TASHA | 2014-05-26 | 2014-07-13 12:06 |  | No | 48 | 2014-08-04 16:14 | [8 empty] | No | 0
VD-9001-213B-DWG-037 | 1 | Gauge Hatch for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-26 | 2014-05-14 16:08 |  | No | -12 | 2014-06-11 12:30 | [8 empty] | No | 0
VD-9001-213B-CAL-003 | 1 | Roof Structure Lifting Calculation for Erection. For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-31 | 2016-05-23 07:14 |  | No | 723 |  | 2016-06-13 12:37 | [6 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-213B-CAL-001 | 5 | Mechanical Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-05-31 | 2014-05-19 14:08 | 2014-05-19 14:22 | Yes | -12 |  | 2014-05-21 11:48 | [6 empty] | 2014-05-21 11:49 | Yes | -12
VD-9001-213B-DWG-019 | 3 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-02 | 2014-05-22 08:44 |  | No | -11 | 2014-06-08 15:54 | [8 empty] | No | 0
VD-9001-213B-DWG-027 | 1 | Shell Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-02 | 2014-05-22 08:46 |  | No | -11 | 2014-06-08 15:55 | [8 empty] | No | 0
VD-9001-213A-DWG-056 | 2 | Name Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-19 17:14 |  | No | -14 |  | 2014-05-21 15:23 | [7 empty] | No | 0
VD-9001-213A-DWG-076 | 2 | Name Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-19 17:16 |  | No | -14 |  | 2014-05-21 15:24 | [7 empty] | No | 0
VD-9001-213A-DWG-114 | 2 | Name Plate for Tk-7101A | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-19 17:19 |  | No | -14 |  | 2014-05-21 15:24 | [7 empty] | No | 0
VD-9001-213A-DWG-115 | 2 | Name Plate for Tk-7101B | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-19 17:21 |  | No | -14 |  | 2014-05-21 15:24 | [7 empty] | No | 0
VD-9001-213A-DWG-140 | 2 | Name Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-19 17:22 |  | No | -14 |  | 2014-05-21 15:25 | [7 empty] | No | 0
VD-9001-213A-DWG-079 | 1 | Gauge Hatch for Tk-6401 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-06-19 08:51 |  | No | 17 | 2014-06-29 10:59 | [8 empty] | No | 0
VD-9001-213A-DWG-143 | 1 | Gauge Hatch for Tk-7201 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-06-19 08:58 |  | No | 17 | 2014-06-29 10:59 | [8 empty] | No | 0
VD-9001-213A-DWG-046 | 3 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-07-22 07:44 |  | No | 50 | 2014-08-05 17:40 | [8 empty] | No | 0
VD-9001-213A-DWG-068 | 1 | Wind Girder for Tk-6401 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-25 06:53 | 2014-05-25 10:10 | Yes | -8 |  | 2014-06-25 17:24 | [6 empty] | 2014-06-25 17:25 | Yes | 17
VD-9001-213A-DWG-132 | 1 | Wind Girder for Tk-7201 | PV-213A | MachineSazi Pars | 2014-06-02 | 2014-05-25 06:54 | 2014-05-25 10:14 | Yes | -8 |  | 2014-06-25 17:25 | [6 empty] | 2014-06-25 17:26 | Yes | 17
VD-9001-253(A)-DSH-001 | 2 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-06-05 | 2014-05-21 15:51 |  | No | -15 | 2014-06-03 10:35 | [8 empty] | No | 0
VD-9001-253(A)-DSH-031 | 2 | THERMAL & MECHANICAL DATA SHEET for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-06-05 | 2014-05-21 16:12 | 2014-05-21 16:41 | Yes | -15 |  | 2014-06-03 10:36 | [6 empty] | 2014-06-03 10:37 | Yes | -1 | 1204-Owner-v | 2018-05-08 09:12
VD-9001-253(A)-DSH-061 | 2 | THERMAL & MECHANICAL DATA SHEET for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-06-05 | 2014-05-21 16:26 | 2014-05-21 16:42 | Yes | -15 |  | 2014-06-03 10:37 | [6 empty] | 2014-06-03 10:38 | Yes | -1 | 1204-Owner-v | 2018-05-08 09:15
VD-9001-213A-DWG-047 | 1 | Spiral Stairway for Tk-2201 | PV-213A | MachineSazi Pars | 2014-06-08 | 2014-06-10 10:44 |  | No | 2 | 2014-09-23 12:12 | [8 empty] | No | 0
VD-9001-213A-DWG-044 | 2 | Fix Roof Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2014-06-08 | 2014-05-28 17:12 |  | No | -11 | 2014-06-25 17:32 | [8 empty] | No | 0
VD-9001-213A-DWG-045 | 3 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-06-08 | 2014-05-28 17:10 |  | No | -11 |  | 2014-06-25 17:33 | [7 empty] | No | 0
VD-9001-213B-WPS-010 | 1 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-09 | 2014-06-10 07:00 |  | No | 1 | 2014-06-22 12:11 | [8 empty] | No | 0
VD-9001-213B-DWG-034 | 2 | Name Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-09 | 2014-06-07 10:39 |  | No | -2 |  | 2014-06-09 10:11 | [7 empty] | No | 0
VD-9001-213B-PCJ-014 | 2 | NDT Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-10 | 2014-05-28 08:04 | 2014-05-28 10:31 | Yes | -13 |  | 2014-06-09 10:05 | [6 empty] | 2014-06-09 10:06 | Yes | -2
VD-9001-213AB-PCJ-013 | 2 | Hydro Test and Air Test Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-10 | 2014-06-08 10:31 |  | No | -2 | 2014-06-18 11:01 | [8 empty] | No | 0
VD-9001-213B-DWG-023 | 5 | Roof Structure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-16 |  |  | No | 2195 | [9 empty] | No | 0
VD-9001-253(A)-DSH-001 | 3 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-06-17 | 2014-06-08 09:54 |  | No | -9 |  | 2014-06-10 14:09 | [7 empty] | No | 0
VD-9001-213B-DWG-019 | 4 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-22 | 2014-06-12 09:20 |  | No | -10 |  | 2014-06-14 12:30 | [7 empty] | No | 0
VD-9001-213B-DWG-027 | 2 | Shell Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-22 | 2014-06-12 09:22 |  | No | -10 |  | 2014-06-14 12:34 | [7 empty] | No | 0
VD-9001-206A-DWG-001 | 1 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2014-06-24 | 2014-06-21 15:07 |  | No | -3 | 2014-08-18 10:12 | [8 empty] | No | 0
VD-9001-206A-DWG-021 | 1 | GENERAL ARRANGMENT ( T-3003 ) | PV-206A | TASHA | 2014-06-24 | 2014-07-13 12:10 |  | No | 19 | 2014-08-18 10:30 | [8 empty] | No | 0
VD-9001-206A-DWG-011 | 1 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2014-06-25 | 2014-07-01 11:59 |  | No | 6 | 2014-08-18 10:23 | [8 empty] | No | 0
VD-9001-213B-DWG-037 | 2 | Gauge Hatch for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-25 | 2014-06-18 10:21 |  | No | -7 |  | 2014-06-22 12:20 | [7 empty] | No | 0
VD-9001-213B-DWG-022 | 1 | Fixed Roof Orientation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-26 | 2014-06-23 07:35 |  | No | -3 | 2014-07-01 09:35 | [8 empty] | No | 0
VD-9001-213B-DWG-021 | 1 | Fixed Roof Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-06-28 | 2014-06-23 07:33 | 2014-06-23 09:38 | Yes | -5 |  | 2014-07-01 09:34 | [6 empty] | 2014-07-01 09:35 | Yes | -6
VD-9001-206A-DWG-012 | 1 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-06-29 | 2014-07-06 17:54 |  | No | 7 | 2014-08-05 11:34 | [8 empty] | No | 0
VD-9001-206A-DWG-022 | 1 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-06-29 | 2014-07-13 12:13 |  | No | 14 | 2014-07-26 17:59 | [8 empty] | No | 0
VD-9001-213AB-PCJ-013 | 3 | Hydro Test and Air Test Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-02 | 2014-06-29 12:48 | 2014-06-29 12:58 | Yes | -3 |  | 2014-07-01 09:43 | [6 empty] | 2014-07-01 09:44 | Yes | -12
VD-9001-206A-DWG-010 | 1 | TEMPLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-07-05 | 2014-06-21 15:13 |  | No | -14 | 2014-08-18 10:15 | [8 empty] | No | 0
VD-9001-206A-DWG-020 | 1 | TEMPLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-07-05 | 2014-07-01 12:03 | 2014-07-01 14:57 | Yes | -4 |  | 2014-08-06 17:01 | [6 empty] | 2014-08-06 17:02 | Yes | 22
VD-9001-206A-DWG-030 | 1 | TEMPLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-07-05 | 2014-07-13 12:21 | 2014-07-13 14:43 | Yes | 8 |  | 2014-08-06 17:11 | [6 empty] | 2014-08-06 17:12 | Yes | 10
VD-9001-213B-WPS-010 | 2 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-06 | 2014-07-05 13:36 |  | No | -1 | 2014-07-10 10:33 | [8 empty] | No | 0
VD-9001-213B-PQR-011 | 1 | PQR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-06 | 2014-07-05 13:40 |  | No | -1 | 2014-07-10 10:34 | [8 empty] | No | 0
VD-9001-213B-DWG-026 | 1 | Wind Girder for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-06 | 2014-06-29 12:51 |  | No | -7 |  | 2014-07-01 09:44 | [7 empty] | No | 0
VD-9001-213B-PCJ-016 | 2 | Painting & Pickling and Passivation procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-09 | 2014-06-29 12:49 |  | No | -10 |  | 2014-07-05 09:34 | [7 empty] | No | 0
VD-9001-213A-DWG-044 | 3 | Fix Roof Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2014-07-09 | 2014-07-09 09:10 |  | No | 0 |  | 2014-07-26 10:01 | [7 empty] | No | 0
VD-9001-213A-DWG-107 | 2 | Shell Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-07-09 | 2014-06-29 13:45 |  | No | -10 | 2014-07-08 15:25 | [8 empty] | No | 0
VD-9001-213A-DWG-108 | 2 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-07-09 | 2015-07-25 16:16 |  | No | 381 | 2015-11-07 15:33 | [8 empty] | No | 0
VD-9001-213A-DWG-134 | 2 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2014-07-09 | 2015-06-21 15:48 |  | No | 347 | 2015-09-08 10:16 | [8 empty] | No | 0
VD-9001-213A-CAL-015 | 3 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-07-12 | 2014-07-05 14:35 |  | No | -7 | 2014-07-28 12:47 | [8 empty] | No | 0
VD-9001-213A-DWG-079 | 2 | Gauge Hatch for Tk-6401 | PV-213A | MachineSazi Pars | 2014-07-13 | 2014-07-02 14:12 |  | No | -11 | 2014-07-08 15:31 | [8 empty] | No | 0
VD-9001-213A-DWG-143 | 2 | Gauge Hatch for Tk-7201 | PV-213A | MachineSazi Pars | 2014-07-13 | 2014-07-02 14:13 |  | No | -11 | 2014-07-08 15:32 | [8 empty] | No | 0
VD-9001-213A-WPS-031 | 2 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-07-13 | 2014-08-12 07:43 |  | No | 30 | 2014-08-24 09:20 | [8 empty] | No | 0
VD-9001-213A-PQR-032 | 2 | PQR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-07-13 | 2014-08-12 07:45 |  | No | 30 | 2014-08-24 09:21 | [8 empty] | No | 0
VD-9001-206A-PCJ-008 | 1 | POST WELD HEAT TREATMENT PROCEDURE | PV-206A | TASHA | 2014-07-13 | 2014-07-01 11:46 | 2014-07-01 14:59 | Yes | -12 |  | 2014-09-27 16:17 | [6 empty] | 2014-09-27 16:18 | Yes | 74
VD-9001-206A-PCJ-009 | 1 | HARDNESS TEST PROCEDURE | PV-206A | TASHA | 2014-07-13 | 2014-07-01 11:47 | 2014-07-01 15:00 | Yes | -12 |  | 2014-09-27 16:18 | [6 empty] | 2014-09-27 16:19 | Yes | 74
VD-9001-253(A)-DWG-063 | 1 | TUBE BUNDLE for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-07-14 | 2014-08-06 08:49 | 2014-08-06 09:57 | Yes | 23 |  | 2014-08-16 16:39 | [6 empty] | 2014-08-16 16:40 | Yes | -4 | 1204-Owner-v | 2018-01-28 15:30
VD-9001-253(A)-CAL-079 | 1 | BUNDLE CALCULATION (INCLUDING FEA) for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-07-14 | 2014-08-06 08:48 | 2014-08-06 09:55 | Yes | 23 |  | 2014-08-09 15:19 | [6 empty] | 2014-08-09 15:20 | Yes | -11
VD-9001-253(A)-DWG-033 | 1 | TUBE BUNDLE for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-07-14 | 2014-07-23 12:42 | 2014-07-23 14:50 | Yes | 9 |  | 2014-10-07 10:44 | [6 empty] | 2014-10-07 10:45 | Yes | 62 | 1204-Owner-v | 2018-01-29 14:22
VD-9001-253(A)-CAL-049 | 1 | BUNDLE CALCULATION (INCLUDING FEA) for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-07-14 | 2014-07-23 12:45 |  | No | 9 | 2014-08-02 09:28 | [8 empty] | No | 0
VD-9001-213B-DWG-022 | 2 | Fixed Roof Orientation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-14 | 2014-07-15 07:18 | 2014-07-15 09:38 | Yes | 1 |  | 2014-07-28 17:24 | [6 empty] | 2014-07-28 17:25 | Yes | -1
VD-9001-253(A)-CAL-019 | 1 | BUNDLE CALCULATION (INCLUDING FEA) for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-08-14 | 2014-08-20 10:15 | 2014-08-20 11:41 | Yes | 6 |  | 2014-09-09 11:19 | [6 empty] | 2014-09-09 11:20 | Yes | 6 | 1204-Owner-v | 2018-05-14 12:17
VD-9001-253(A)-DWG-003 | 1 | TUBE BUNDLE for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-08-14 | 2014-08-20 10:29 |  | No | 6 | 2014-09-09 11:21 | [8 empty] | No | 0 | 1204-Owner-v | 2019-06-19 15:58
VD-9001-253(A)-DWG-062 | 1 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-07-20 | 2014-07-15 16:32 |  | No | -5 | 2014-08-19 11:33 | [8 empty] | No | 0
VD-9001-253(A)-DWG-032 | 1 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-07-21 | 2014-07-15 16:30 |  | No | -6 | 2014-10-07 10:38 | [8 empty] | No | 0
VD-9001-213B-DWG-024 | 1 | Spiral Stairway For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-22 | 2014-08-20 08:26 |  | No | 29 | 2014-09-02 16:46 | [8 empty] | No | 0
VD-9001-213A-DWG-064 | 4 | Fixed Roof Orientation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-07-22 | 2014-07-15 07:29 | 2014-07-15 09:40 | Yes | -7 |  | 2014-09-07 16:54 | [6 empty] | 2014-09-07 16:55 | Yes | 40
VD-9001-213A-DWG-107 | 3 | Shell Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-07-22 | 2014-07-15 07:28 | 2014-07-15 09:41 | Yes | -7 |  | 2014-07-26 10:13 | [6 empty] | 2014-07-26 10:14 | Yes | -3
VD-9001-213A-DWG-079 | 3 | Gauge Hatch for Tk-6401 | PV-213A | MachineSazi Pars | 2014-07-22 | 2014-07-12 12:52 |  | No | -10 |  | 2014-07-26 10:07 | [7 empty] | No | 0
VD-9001-213A-DWG-143 | 3 | Gauge Hatch for Tk-7201 | PV-213A | MachineSazi Pars | 2014-07-22 | 2014-07-12 12:54 |  | No | -10 |  | 2014-07-26 10:07 | [7 empty] | No | 0
VD-9001-253(A)-DWG-002 | 1 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-07-23 | 2014-07-21 10:48 |  | No | -2 | 2014-07-28 16:27 | [8 empty] | No | 0
VD-9001-206A-WBK-001 | 1 | WELDING BOOK (WPS & PQR) | PV-206A | TASHA | 2014-07-23 | 2014-07-13 12:25 |  | No | -10 | 2014-09-09 11:57 | [8 empty] | No | 0
VD-9001-206A-WMP-001 | 1 | WELDING MAP & NDT TABLE | PV-206A | TASHA | 2014-07-23 | 2014-07-13 12:42 |  | No | -10 | 2014-07-26 15:52 | [8 empty] | No | 0
VD-9001-213B-WPS-010 | 3 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-24 | 2014-07-12 11:44 |  | No | -12 | 2014-07-23 15:42 | [8 empty] | No | 0
VD-9001-213B-PQR-011 | 2 | PQR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-24 | 2014-07-12 11:43 |  | No | -12 | 2014-07-26 09:40 | [8 empty] | No | 0
VD-9001-213B-DWG-018 | 1 | General Assembly for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-07-24 | 2014-07-15 07:17 |  | No | -9 | 2014-07-29 10:50 | [8 empty] | No | 0
VD-9001-213B-WMP-015 | 1 | Welding Maps for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-08-06 | 2014-07-23 13:55 |  | No | -14 | 2014-09-16 09:33 | [8 empty] | No | 0
VD-9001-213B-WPS-010 | 4 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-08-06 | 2014-08-06 10:30 |  | No | 0 | 2014-09-09 12:15 | [8 empty] | No | 0
VD-9001-213B-PQR-011 | 3 | PQR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-08-09 | 2014-08-06 10:32 |  | No | -3 | 2014-09-09 12:16 | [8 empty] | No | 0
VD-9001-213A-DWG-102 | 1 | Spiral Stairway for Tk-7101A | PV-213A | MachineSazi Pars | 2014-08-09 | 2014-09-14 14:59 |  | No | 36 | 2014-11-12 09:12 | [8 empty] | No | 0
VD-9001-213A-DWG-103 | 1 | Spiral Stairway for Tk-7101B | PV-213A | MachineSazi Pars | 2014-08-09 | 2014-09-14 15:02 |  | No | 36 | 2014-11-12 09:14 | [8 empty] | No | 0
VD-9001-213A-DWG-130 | 1 | Spiral Stairway for Tk-7201 | PV-213A | MachineSazi Pars | 2014-08-09 | 2014-12-03 15:33 |  | No | 116 | 2015-01-31 11:10 | [8 empty] | No | 0
VD-9001-213A-DWG-066 | 1 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2014-08-09 | 2014-11-11 08:19 |  | No | 94 | 2015-01-03 10:41 | [8 empty] | No | 0
VD-9001-206A-WMP-001 | 2 | WELDING MAP & NDT TABLE | PV-206A | TASHA | 2014-08-09 | 2014-08-06 15:09 |  | No | -3 |  | 2014-08-19 11:44 | [7 empty] | No | 0
VD-9001-206A-PCJ-007 | 1 | REPAIR PROCEDURE | PV-206A | TASHA | 2014-08-09 | 2014-08-06 15:08 | 2014-08-06 17:33 | Yes | -3 |  | 2014-08-19 11:45 | [6 empty] | 2014-08-19 11:46 | Yes | -1
VD-9001-206A-PCJ-010 | 1 | PENUMATIC TEST PROCEDURE | PV-206A | TASHA | 2014-08-09 | 2014-08-06 15:08 |  | No | -3 | 2014-08-19 11:46 | [8 empty] | No | 0
VD-9001-206A-PCJ-011 | 1 | HYDRO TEST PROCEDURE | PV-206A | TASHA | 2014-08-09 | 2014-09-06 12:27 | 2014-09-06 14:22 | Yes | 28 |  | 2014-10-11 15:59 | [6 empty] | 2014-10-11 16:00 | Yes | 21
VD-9001-206A-PCJ-012 | 1 | BLASTING & PAINTING PROCEDURE | PV-206A | TASHA | 2014-08-09 | 2014-09-02 08:06 |  | No | 24 | 2014-09-24 17:49 | [8 empty] | No | 0
VD-9001-206A-DWG-022 | 2 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-08-09 | 2014-09-24 10:41 |  | No | 46 |  | 2014-11-25 10:07 | [7 empty] | No | 0
VD-9001-213A-CAL-015 | 4 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-08-11 | 2014-08-10 10:21 |  | No | -1 | 2014-10-08 15:02 | [8 empty] | No | 0
VD-9001-253(A)-DWG-002 | 2 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-08-11 | 2014-08-02 15:29 |  | No | -9 | 2014-09-09 12:43 | [8 empty] | No | 0
VD-9001-213B-DWG-018 | 2 | General Assembly for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-08-12 | 2014-08-04 11:37 |  | No | -8 |  | 2014-08-18 11:33 | [7 empty] | No | 0
VD-9001-206A-CAL-001 | 2 | MECHANICAL CALCULATION BOOK ( T-3001 ) | PV-206A | TASHA | 2014-08-12 | 2014-08-27 15:03 | 2014-08-27 15:53 | Yes | 15 |  | 2014-10-29 14:41 | [6 empty] | 2014-10-29 14:42 | Yes | 49
VD-9001-206A-CAL-002 | 1 | EXTERNAL ATTACHMENT & LIFTING LUG CALCULATION ( T-3001 ) | PV-206A | TASHA | 2014-08-12 | 2014-08-27 15:04 | 2014-08-27 15:54 | Yes | 15 |  | 2014-10-11 16:04 | [6 empty] | 2014-10-11 16:05 | Yes | 31 | 1204-Owner-v | 2019-07-22 10:19
VD-9001-206A-DWG-002 | 2 | BODY & SUPPORT DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-08-12 | 2014-08-27 15:07 | 2014-08-27 15:57 | Yes | 15 |  | 2014-10-11 16:11 | [6 empty] | 2014-10-11 16:12 | Yes | 31
VD-9001-253(A)-CAL-049 | 2 | BUNDLE CALCULATION (INCLUDING FEA) for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-08-16 | 2016-01-30 16:50 | 2016-01-30 16:45 | Yes | 532 |  | 2016-02-01 11:19 | [6 empty] | 2016-02-01 20:02 | Yes | -12 | 1204-Owner-v | 2018-08-08 10:46
VD-9001-205A-DWG-001 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-14 11:51 |  | No | 114 | 2015-08-26 10:28 | [8 empty] | No | 0
VD-9001-205A-DWG-002 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-14 11:52 |  | No | 114 | 2015-10-03 16:31 | [8 empty] | No | 0
VD-9001-205A-DWG-003 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-12-14 11:54 |  | No | 219 | 2015-10-03 16:32 | [8 empty] | No | 0
VD-9001-205A-CAL-004 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-01-13 15:25 |  | No | -1005 | 2015-08-26 10:33 | [8 empty] | No | 0
VD-9001-205A-CAL-005 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-11-09 17:33 |  | No | -705 | 2015-12-01 16:41 | [8 empty] | No | 0
VD-9001-205A-DWG-006 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-29 | 2014-12-29 11:57 |  | No | 122 | 2015-10-03 16:42 | [8 empty] | No | 0
VD-9001-205A-DWG-007 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-29 | 2015-01-04 16:17 |  | No | 128 | 2015-07-27 17:27 | [8 empty] | No | 0
VD-9001-205A-DWG-008 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-09 | 2015-01-04 16:19 |  | No | 26 | 2015-10-03 16:46 | [8 empty] | No | 0
VD-9001-205A-CAL-009 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-09 | 2015-12-16 16:49 | 2015-12-16 17:43 | Yes | 372 |  | 2015-12-24 13:00 | [6 empty] | 2015-12-24 20:03 | Yes | -6
VD-9001-205A-CAL-010 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-11-09 17:32 |  | No | -705 | 2015-12-01 16:45 | [8 empty] | No | 0
VD-9001-205A-DWG-011 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-08-20 15:52 |  | No | -2 | 2014-10-11 16:17 | [8 empty] | No | 0
VD-9001-205A-DWG-012 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-08-20 15:52 |  | No | -2 | 2014-10-18 16:04 | [8 empty] | No | 0
VD-9001-205A-DWG-013 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-09-06 14:26 |  | No | 120 | 2014-10-18 16:09 | [8 empty] | No | 0
VD-9001-205A-CAL-014 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-08-23 12:31 |  | No | -1148 | 2014-08-24 11:28 | [8 empty] | No | 0
VD-9001-205A-CAL-015 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-08-23 12:31 |  | No | -1148 | 2014-08-24 11:29 | [8 empty] | No | 0
VD-9001-205A-DWG-016 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-08-26 09:19 |  | No | 109 | 2014-10-11 16:23 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-08-26 09:20 |  | No | 109 | 2014-10-18 16:14 | [8 empty] | No | 0
VD-9001-205A-DWG-018 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-19 | 2015-01-05 10:20 |  | No | 108 | 2015-02-28 17:17 | [8 empty] | No | 0
VD-9001-205A-CAL-019 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-08-23 17:10 |  | No | -1148 | 2014-08-24 11:29 | [8 empty] | No | 0
VD-9001-205A-CAL-020 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-08-23 17:10 |  | No | -1148 | 2014-08-24 11:31 | [8 empty] | No | 0
VD-9001-205A-DWG-021 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-08-31 15:30 |  | No | 114 | 2014-10-11 16:27 | [8 empty] | No | 0
VD-9001-205A-DWG-022 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-08-31 15:31 |  | No | 114 | 2014-10-18 16:18 | [8 empty] | No | 0
VD-9001-205A-DWG-023 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-19 | 2015-01-05 13:17 |  | No | 108 | 2015-02-28 17:22 | [8 empty] | No | 0
VD-9001-205A-CAL-024 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-09-10 14:09 |  | No | -1130 | 2014-10-11 10:49 | [8 empty] | No | 0
VD-9001-205A-CAL-025 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-09-10 14:10 |  | No | -1130 | 2014-10-11 10:50 | [8 empty] | No | 0
VD-9001-205A-DWG-026 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-29 | 2014-12-14 13:57 |  | No | 107 | 2015-10-03 16:37 | [8 empty] | No | 0
VD-9001-205A-DWG-027 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-29 | 2014-12-14 13:58 |  | No | 107 | 2015-10-03 16:37 | [8 empty] | No | 0
VD-9001-205A-DWG-028 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-09 | 2014-12-14 14:09 |  | No | 5 | 2015-10-03 16:37 | [8 empty] | No | 0
VD-9001-205A-CAL-029 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-12-16 16:50 | 2015-12-16 17:43 | Yes | -668 |  | 2015-12-24 13:03 | [6 empty] | 2015-12-24 20:03 | Yes | -6
VD-9001-205A-CAL-030 | 0 | HYDRAULIC CALCULATION FOR INTERNALS OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-11-09 17:32 |  | No | -705 | 2015-12-01 16:47 | [8 empty] | No | 0
VD-9001-205A-DWG-031 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-09 10:59 |  | No | 109 | 2015-08-26 10:10 | [8 empty] | No | 0
VD-9001-205A-DWG-032 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-28 14:58 |  | No | 128 | 2015-04-11 17:44 | [8 empty] | No | 0
VD-9001-205A-DWG-033 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-12-28 14:59 |  | No | 233 | 2015-04-11 17:44 | [8 empty] | No | 0
VD-9001-205A-CAL-034 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-12-29 10:32 | 2014-12-30 12:03 | Yes | -1019 |  | 2015-01-28 18:00 | [6 empty] | 2015-01-28 18:01 | Yes | 16
VD-9001-205A-DWG-035 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2015-08-23 14:07 |  | No | 471 | 2015-09-13 17:04 | [8 empty] | No | 0
VD-9001-205A-DWG-036 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2015-08-23 14:08 |  | No | 471 | 2015-09-13 17:05 | [8 empty] | No | 0
VD-9001-205A-DWG-037 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-19 | 2015-08-23 14:08 |  | No | 338 | 2015-09-13 17:05 | [8 empty] | No | 0
VD-9001-205A-CAL-038 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2016-02-17 09:01 | 2016-02-17 09:02 | Yes | -605 |  | 2016-02-22 15:34 | [6 empty] | 2016-02-22 20:00 | Yes | -9
VD-9001-205A-DWG-039 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-08-17 16:35 |  | No | -5 | 2014-11-23 14:52 | [8 empty] | No | 0
VD-9001-205A-DWG-040 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-08-17 16:39 |  | No | -5 | 2014-11-23 14:54 | [8 empty] | No | 0
VD-9001-205A-DWG-041 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-08-17 16:41 |  | No | 100 | 2014-11-23 14:55 | [8 empty] | No | 0
VD-9001-205A-CAL-042 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-12-29 10:24 | 2014-12-30 12:33 | Yes | -1019 |  | 2015-01-28 18:02 | [6 empty] | 2015-01-28 18:03 | Yes | 16
VD-9001-205A-DWG-043 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-10 12:40 |  | No | 110 | 2015-10-03 16:15 | [8 empty] | No | 0
VD-9001-205A-DWG-044 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-29 16:34 |  | No | 129 | 2015-04-11 17:36 | [8 empty] | No | 0
VD-9001-205A-DWG-045 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-12-29 16:35 |  | No | 234 | 2015-04-11 17:37 | [8 empty] | No | 0
VD-9001-205A-CAL-046 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-12-20 16:23 | 2014-12-22 16:50 | Yes | -1027 |  | 2015-01-28 15:45 | [6 empty] | 2015-01-28 15:46 | Yes | 25
VD-9001-205A-DWG-047 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-10 12:37 |  | No | 110 | 2015-08-26 10:15 | [8 empty] | No | 0
VD-9001-205A-DWG-048 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-22 | 2014-12-28 14:09 |  | No | 128 |  | 2015-04-11 17:48 | [7 empty] | No | 0
VD-9001-205A-DWG-049 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2014-12-28 14:10 | 2014-12-28 15:48 | Yes | 233 |  | 2015-04-11 17:48 | [6 empty] | 2015-04-11 17:49 | Yes | 90
VD-9001-205A-CAL-050 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2014-12-27 13:34 | 2014-12-28 15:49 | Yes | -1021 |  | 2015-01-28 17:54 | [6 empty] | 2015-01-28 17:55 | Yes | 18
VD-9001-205A-DWG-051 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2016-02-20 14:40 |  | No | 652 | 2016-03-01 09:40 | [7 empty] | 2016-03-01 20:00 | Yes | 0
VD-9001-205A-DWG-052 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-05-09 | 2016-02-20 14:40 |  | No | 652 |  | 2016-03-01 09:36 | [6 empty] | 2016-03-01 20:00 | Yes | 0
VD-9001-205A-DWG-053 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-19 | 2016-02-20 14:40 |  | No | 519 | 2016-03-02 09:04 | [7 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-205A-CAL-054 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2016-04-04 15:43 | 2016-04-04 15:44 | Yes | -558 |  | 2016-04-13 10:03 | [6 empty] | 2016-04-13 19:59 | Yes | -5
VD-9001-205A-LST-055 | 0 | SPARE PART LIST FOR COMMISSIONING & START-UP | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-11-12 12:33 |  | No | -702 | 2015-12-24 12:42 | [7 empty] | 2015-12-24 20:03 | Yes | 0
VD-9001-205A-LST-056 | 0 | SPARE PART LIST FOR 2 YEARS OPERATION | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-11-12 12:34 |  | No | -702 | 2015-12-24 12:42 | [7 empty] | 2015-12-24 20:03 | Yes | 0
VD-9001-205A-QCP-057 | 0 | INSPECTION AND TEST PALN & PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-01-06 10:33 |  | No | -1012 | 2015-02-04 11:37 | [8 empty] | No | 0
VD-9001-205A-WPS-058 | 0 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-01-07 10:56 |  | No | -1011 | 2015-02-04 11:42 | [8 empty] | No | 0
VD-9001-205A-WPQ-059 | 0 | WELDERS PERFORMANCE QUALIFICATION (WPQ) | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-09-15 14:49 |  | No | -760 | 2015-10-13 10:25 | [8 empty] | No | 0
VD-9001-205A-PCJ-060 | 0 | PICKLING & PASSIVATION PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-09-15 14:48 |  | No | -760 | 2015-10-13 10:25 | [8 empty] | No | 0
VD-9001-205A-PCJ-061 | 0 | PACKING PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-06-10 15:33 |  | No | -857 | 2015-06-21 12:05 | [8 empty] | No | 0
VD-9001-205A-PCJ-062 | 0 | INSTALLATION PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-09-19 15:20 |  | No | -756 | 2015-11-04 15:06 | [8 empty] | No | 0
VD-9001-205A-DIS-063 | 0 | VENDOR PRINT INDEX & SCHEDULE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 |  |  | No | 979 | [9 empty] | No | 0
VD-9001-205A-SCH-064 | 0 | DELIVERY SCHEDULE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-05-09 15:35 | 2015-05-09 16:04 | Yes | -889 |  | 2015-05-28 12:41 | [6 empty] | 2015-05-28 12:42 | Yes | 5
VD-9001-205A-INX-065 | 0 | FINAL BOOK INDEX | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-10-14 | 2015-12-14 10:36 | 2015-12-14 11:08 | Yes | -670 |  | 2015-12-24 12:57 | [6 empty] | 2015-12-24 20:03 | Yes | -4
VD-9001-206A-CAL-005 | 2 | MECHANICAL CALCULATION BOOK ( T-3003 ) | PV-206A | TASHA | 2014-08-18 | 2014-09-24 10:37 |  | No | 37 |  | 2014-11-25 10:03 | [7 empty] | No | 0
VD-9001-206A-DWG-012 | 2 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-08-19 | 2014-09-24 10:30 |  | No | 36 |  | 2014-10-29 10:13 | [7 empty] | No | 0
VD-9001-213A-PCJ-038 | 2 | Painting procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-08-19 | 2014-08-14 09:21 |  | No | -5 |  | 2014-08-16 08:47 | [7 empty] | No | 0
VD-9001-213A-DWG-046 | 4 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2014-08-19 | 2014-08-14 10:08 |  | No | -5 |  | 2014-08-24 10:09 | [7 empty] | No | 0
VD-9001-213A-DWG-065 | 6 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-08-19 | 2014-08-16 13:03 |  | No | -3 |  | 2014-08-24 10:14 | [7 empty] | No | 0
VD-9001-213A-DWG-101 | 6 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-08-30 | 2014-08-17 13:21 |  | No | -13 |  | 2014-08-24 10:16 | [7 empty] | No | 0
VD-9001-206A-DWG-001 | 2 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2014-09-01 | 2014-09-06 12:25 |  | No | 5 | 2014-10-08 17:41 | [8 empty] | No | 0
VD-9001-206A-DWG-003 | 1 | NOZZLE DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-09-01 | 2014-08-27 15:08 |  | No | -5 | 2014-09-24 17:55 | [8 empty] | No | 0
VD-9001-206A-DWG-010 | 2 | TEMPLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-09-01 | 2014-10-27 10:39 | 2014-10-27 11:50 | Yes | 56 |  | 2014-11-12 17:02 | [6 empty] | 2014-11-12 17:03 | Yes | 2 | 1204-Owner-v | 2017-12-31 16:31
VD-9001-206A-DWG-011 | 2 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2014-09-01 | 2014-09-24 10:29 |  | No | 23 | 2014-11-30 16:21 | [8 empty] | No | 0
VD-9001-206A-DWG-013 | 1 | NOZZLE DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-09-01 | 2014-09-21 16:42 |  | No | 20 | 2014-10-29 10:02 | [8 empty] | No | 0
VD-9001-206A-DWG-021 | 2 | GENERAL ARRANGMENT ( T-3003 ) | PV-206A | TASHA | 2014-09-01 | 2014-09-24 10:39 |  | No | 23 | 2014-11-25 10:06 | [8 empty] | No | 0
VD-9001-206A-DWG-023 | 1 | NOZZLE DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-09-01 | 2014-09-29 14:39 |  | No | 28 | 2014-12-27 12:08 | [8 empty] | No | 0
VD-9001-213A-WMP-037 | 1 | Welding Maps for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-01 | 2014-08-20 11:44 |  | No | -12 | 2014-10-16 10:21 | [8 empty] | No | 0
VD-9001-253(A)-DWG-062 | 2 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-09-02 | 2014-09-03 08:14 |  | No | 1 | 2014-09-24 15:45 | [8 empty] | No | 0
VD-9001-206A-PCJ-010 | 2 | PENUMATIC TEST PROCEDURE | PV-206A | TASHA | 2014-09-02 | 2014-09-02 08:05 | 2014-09-02 10:06 | Yes | 0 |  | 2014-09-24 17:48 | [6 empty] | 2014-09-24 17:49 | Yes | 8
VD-9001-213A-WPS-031 | 3 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-07 | 2014-08-25 09:20 |  | No | -13 |  | 2014-09-22 16:13 | [7 empty] | No | 0
VD-9001-213A-PQR-032 | 3 | PQR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-07 | 2014-08-25 09:22 | 2014-08-25 09:59 | Yes | -13 |  | 2014-09-22 16:13 | [6 empty] | 2014-09-22 16:14 | Yes | 14
VD-9001-205A-CAL-014 | 1 | MECHANICAL CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-07 | 2014-09-02 16:08 |  | No | -5 | 2014-10-11 10:37 | [8 empty] | No | 0
VD-9001-205A-CAL-015 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-07 | 2014-09-02 15:47 |  | No | -5 | 2014-10-11 10:38 | [8 empty] | No | 0
VD-9001-205A-CAL-019 | 1 | MECHANICAL CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-07 | 2014-09-02 16:32 |  | No | -5 | 2014-10-11 10:45 | [8 empty] | No | 0
VD-9001-205A-CAL-020 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-09-07 | 2014-09-02 16:34 |  | No | -5 | 2014-10-11 10:45 | [8 empty] | No | 0
VD-9001-253(A)-DWG-007 | 1 | FAN RING for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-09-07 | 2015-01-20 14:14 | 2015-01-20 16:16 | Yes | 135 |  | 2015-01-26 17:24 | [6 empty] | 2015-01-26 17:25 | Yes | -8 | 1204-Owner-v | 2019-06-09 11:59
VD-9001-253(A)-DWG-037 | 1 | FAN RING for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-09-07 | 2015-01-20 14:16 | 2015-01-20 16:17 | Yes | 135 |  | 2015-01-26 17:25 | [6 empty] | 2015-01-26 17:26 | Yes | -8
VD-9001-253(A)-DWG-067 | 1 | FAN RING for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-09-07 | 2015-01-20 14:17 | 2015-01-20 16:17 | Yes | 135 |  | 2015-01-26 17:25 | [6 empty] | 2015-01-26 17:26 | Yes | -8 | 1204-Owner-v | 2018-01-28 15:27
VD-9001-213B-DWG-024 | 2 | Spiral Stairway For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-09-16 | 2014-10-11 16:06 | 2014-10-11 16:42 | Yes | 25 |  | 2014-11-02 15:11 | [6 empty] | 2014-11-02 15:12 | Yes | 8
VD-9001-213A-CAL-025 | 1 | Nozzle Load Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-20 | 2014-09-23 14:00 |  | No | 3 | 2014-11-15 09:15 | [8 empty] | No | 0
VD-9001-206A-DWG-007 | 1 | TOP DAVIT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-09-06 | 2014-11-12 15:50 |  | No | 67 | 2014-12-08 16:45 | [8 empty] | No | 0
VD-9001-213B-DWG-036 | 1 | Instrument Cable Tray Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-09-21 | 2014-09-10 11:48 |  | No | -11 | 2014-09-30 15:56 | [8 empty] | No | 0
VD-9001-213A-DWG-041 | 1 | General Assembly for Tk-2201 | PV-213A | MachineSazi Pars | 2014-09-21 | 2014-09-14 14:56 |  | No | -7 | 2014-11-10 12:13 | [8 empty] | No | 0
VD-9001-213A-DWG-060 | 1 | General Assembly for Tk-6401 | PV-213A | MachineSazi Pars | 2014-09-21 | 2015-01-15 13:01 |  | No | 116 | 2015-04-04 10:57 | [8 empty] | No | 0
VD-9001-213A-DWG-080 | 1 | General Assembly for Tk-7101A | PV-213A | MachineSazi Pars | 2014-09-21 | 2015-10-11 07:17 |  | No | 385 | 2015-11-11 10:27 | [8 empty] | No | 0
VD-9001-213A-DWG-081 | 1 | General Assembly for Tk-7101B | PV-213A | MachineSazi Pars | 2014-09-21 | 2015-10-11 07:18 |  | No | 385 | 2015-11-11 10:28 | [8 empty] | No | 0
VD-9001-213A-DWG-124 | 1 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-21 | 2015-01-15 13:04 |  | No | 116 | 2015-04-04 10:58 | [8 empty] | No | 0
VD-9001-213A-DWG-128 | 2 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-21 | 2014-12-25 08:35 |  | No | 95 |  | 2015-02-23 16:42 | [7 empty] | No | 0
VD-9001-213A-DWG-046 | 5 | Roof Structure for Tk-2201 | PV-213A | MachineSazi Pars | 2014-09-08 09:24 | 2015-03-18 17:07 | 2015-03-18 17:21 | Yes | 191 |  | 2015-04-14 12:01 | [6 empty] | 2015-04-14 12:02 | Yes | 13
VD-9001-253(A)-DWG-003 | 2 | TUBE BUNDLE for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2014-09-16 09:51 | 2014-09-16 10:53 | Yes | -7 |  | 2014-10-07 10:35 | [6 empty] | 2014-10-07 10:36 | Yes | 7 | 1204-Owner-v | 2019-06-19 15:56
VD-9001-206A-WBK-001 | 2 | WELDING BOOK (WPS & PQR) | PV-206A | TASHA | 2014-09-23 | 2014-10-02 15:30 |  | No | 9 |  | 2014-10-08 17:35 | [7 empty] | No | 0
VD-9001-213B-WPS-010 | 5 | WPS for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-09-23 |  |  | No | 2096 | [9 empty] | No | 0
VD-9001-213B-PQR-011 | 4 | PQR for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-09-23 |  |  | No | 2096 | [9 empty] | No | 0
VD-9001-253(A)-DSH-013 | 1 | PULLEY DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2016-06-16 11:44 |  | No | 632 |  | 2016-06-29 16:17 | [6 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-DSH-043 | 1 | PULLEY DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2016-06-16 11:45 |  | No | 632 |  | 2016-06-29 16:16 | [6 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-DSH-073 | 1 | PULLEY DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2016-06-16 11:45 |  | No | 632 |  | 2016-06-29 16:10 | [6 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-253(A)-RPT-082 | 1 | FOUNDATION LOADING for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2014-09-15 17:06 | 2014-09-16 08:45 | Yes | -7 |  | 2014-09-27 16:35 | [6 empty] | 2014-09-27 16:36 | Yes | -2
VD-9001-253(A)-DWG-002 | 3 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-09-23 | 2014-09-27 14:19 |  | No | 4 | 2014-10-11 16:31 | [8 empty] | No | 0
VD-9001-253(A)-DWG-069 | 1 | FAN GUARD & PULLEY GUARD for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-09-28 | 2014-09-16 09:58 | 2014-09-16 10:56 | Yes | -12 |  | 2014-09-24 15:52 | [6 empty] | 2014-09-24 15:53 | Yes | -6 | 1204-Owner-v | 2018-01-28 15:29
VD-9001-253(A)-DWG-009 | 1 | FAN GUARD & PULLEY GUARD for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-09-28 | 2014-09-16 09:54 | 2014-09-16 10:54 | Yes | -12 |  | 2014-09-24 15:51 | [6 empty] | 2014-09-24 15:52 | Yes | -6 | 1204-Owner-v | 2019-01-31 11:23
VD-9001-253(A)-DWG-039 | 1 | FAN GUARD & PULLEY GUARD for 3001 | HM-253A | FATEH SANAT KIMIA | 2014-09-28 | 2014-09-16 09:56 | 2014-09-16 10:56 | Yes | -12 |  | 2014-09-24 15:51 | [6 empty] | 2014-09-24 15:52 | Yes | -6 | 1204-Owner-v | 2019-01-31 11:25
VD-9001-213B-WMP-015 | 2 | Welding Maps for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-09-30 | 2014-09-24 06:55 |  | No | -6 | 2014-10-11 10:26 | [8 empty] | No | 0
VD-9001-213A-PCJ-014 | 1 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2014-10-06 | 2014-11-25 10:42 |  | No | 50 | 2015-01-03 11:41 | [8 empty] | No | 0
VD-9001-213A-PCJ-021 | 1 | Roof structure Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-10-06 | 2016-01-10 15:47 | 2016-01-10 15:48 | Yes | 461 |  | 2016-01-25 17:58 | [6 empty] | 2016-01-25 20:02 | Yes | 1
VD-9001-213A-DWG-047 | 2 | Spiral Stairway for Tk-2201 | PV-213A | MachineSazi Pars | 2014-10-07 | 2014-11-09 07:31 |  | No | 33 |  | 2014-12-14 11:26 | [7 empty] | No | 0
VD-9001-213A-PCJ-007 | 1 | Roof Structure Erection Procedure for Tk-2201 | PV-213A | MachineSazi Pars | 2014-10-08 | 2015-09-02 10:47 | 2015-09-02 11:00 | Yes | 329 |  | 2015-09-19 08:53 | [6 empty] | 2015-09-19 08:54 | Yes | 3
VD-9001-213A-DWG-042 | 4 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-09-24 | 2014-09-25 08:03 |  | No | 1 |  | 2014-09-30 10:33 | [7 empty] | No | 0
VD-9001-213A-DWG-061 | 4 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-09-24 | 2014-09-25 08:05 |  | No | 1 |  | 2014-09-30 10:33 | [7 empty] | No | 0
VD-9001-213A-DWG-082 | 5 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-09-24 | 2014-09-25 08:07 |  | No | 1 |  | 2014-09-30 10:34 | [7 empty] | No | 0
VD-9001-213A-DWG-083 | 5 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-09-24 | 2014-09-25 08:10 |  | No | 1 |  | 2014-09-30 10:34 | [7 empty] | No | 0
VD-9001-213A-DWG-125 | 3 | Shell Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-09-24 | 2014-09-25 08:11 |  | No | 1 |  | 2014-09-30 10:35 | [7 empty] | No | 0
VD-9001-253(A)-DWG-062 | 3 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-10-08 | 2015-05-10 10:09 |  | No | 214 | 2015-06-06 17:00 | [8 empty] | No | 0
VD-9001-206A-PCJ-012 | 2 | BLASTING & PAINTING PROCEDURE | PV-206A | TASHA | 2014-10-08 | 2014-10-01 15:41 | 2014-10-01 15:56 | Yes | -7 |  | 2014-10-08 17:50 | [6 empty] | 2014-10-08 17:51 | Yes | -7
VD-9001-206A-DWG-003 | 2 | NOZZLE DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-10-08 | 2015-01-10 18:41 |  | No | 94 | 2015-01-28 18:14 | [8 empty] | No | 0
VD-9001-206A-DWG-008 | 1 | PIPE CLIP DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-10-11 | 2014-09-27 16:49 | 2014-09-27 17:08 | Yes | -14 |  | 2014-10-08 17:46 | [6 empty] | 2014-10-08 17:47 | Yes | -3 | 1204-Owner-v | 2019-07-22 10:21
VD-9001-213A-DWG-058 | 1 | Instrument Cable Tray Support for Tk-2201 | PV-213A | MachineSazi Pars | 2014-10-14 | 2014-10-06 08:32 |  | No | -8 |  | 2014-10-16 12:14 | [7 empty] | No | 0
VD-9001-213A-DWG-078 | 1 | Instrument Cable Tray Support for Tk-6401 | PV-213A | MachineSazi Pars | 2014-10-14 | 2014-10-06 08:37 | 2014-10-06 09:14 | Yes | -8 |  | 2014-10-16 12:15 | [6 empty] | 2014-10-16 12:16 | Yes | -4
VD-9001-213A-DWG-118 | 1 | Instrument Cable Tray Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-10-14 | 2014-10-06 08:39 | 2014-10-06 09:15 | Yes | -8 |  | 2014-10-16 12:15 | [6 empty] | 2014-10-16 12:16 | Yes | -4
VD-9001-213A-DWG-142 | 1 | Instrument Cable Tray Support for Tk-7201 | PV-213A | MachineSazi Pars | 2014-10-14 | 2014-10-06 08:40 | 2014-10-06 09:16 | Yes | -8 |  | 2014-10-16 12:16 | [6 empty] | 2014-10-16 12:17 | Yes | -4
VD-9001-213B-DWG-036 | 2 | Instrument Cable Tray Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-10-14 | 2014-10-06 14:48 | 2014-10-06 15:32 | Yes | -8 |  | 2014-10-08 11:27 | [6 empty] | 2014-10-08 11:28 | Yes | -12
VD-9001-213B-PCJ-012 | 1 | Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-10-20 | 2014-12-07 06:58 |  | No | 48 | 2015-01-27 14:52 | [8 empty] | No | 0
VD-9001-253(A)-RPT-022 | 1 | FOUNDATION LOADING for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-10-06 | 2014-10-06 15:56 |  | No | 0 |  | 2014-10-18 10:32 | [7 empty] | No | 0
VD-9001-253(A)-DWG-032 | 2 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2014-10-21 | 2014-10-15 16:37 |  | No | -6 | 2015-01-26 15:29 | [8 empty] | No | 0
VD-9001-213A-PCJ-035 | 1 | Hydro Test and Air test procedurefor Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-10-22 | 2014-10-27 07:11 |  | No | 5 | 2015-02-07 09:52 | [8 empty] | No | 0
VD-9001-213A-PCJ-034 | 1 | Erection Procedure forTk-2201 & Tk-6401 & Tk-7201 | PV-213A | MachineSazi Pars | 2014-10-22 | 2014-12-20 15:56 |  | No | 59 | 2014-12-30 18:25 | [8 empty] | No | 0
VD-9001-206A-ITP-001 | 2 | INSPECTION AND TEST PLAN | PV-206A | TASHA | 2014-10-08 | 2014-10-09 11:37 | 2014-10-09 12:20 | Yes | 1 |  | 2014-10-29 10:28 | [6 empty] | 2014-10-29 10:29 | Yes | 6 | 1204-Owner-v | 2020-01-01 12:53
VD-9001-213A-CAL-015 | 5 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-10-22 | 2014-11-01 15:53 |  | No | 10 | 2014-11-25 10:26 | [8 empty] | No | 0
VD-9001-206A-DWG-001 | 3 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2014-10-22 |  |  | No | 2067 | 2014-10-29 09:54 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-091 | 1 | EXPANDING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2014-10-25 | 2014-11-25 09:32 | 2014-11-25 15:24 | Yes | 31 |  | 2014-12-27 15:25 | [6 empty] | 2014-12-27 15:26 | Yes | 18 | 1204-Owner-v | 2018-07-12 11:22
VD-9001-213B-WMP-015 | 3 | Welding Maps for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-10-25 | 2014-10-25 07:20 |  | No | 0 |  | 2014-10-27 15:42 | [7 empty] | No | 0
VD-9001-205A-CAL-014 | 2 | MECHANICAL CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-10-25 13:23 | 2014-10-25 15:59 | Yes | 0 |  | 2014-11-12 10:51 | [6 empty] | 2014-11-12 10:52 | Yes | 4
VD-9001-205A-CAL-015 | 2 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-12-20 08:58 | 2014-12-20 10:03 | Yes | 56 |  | 2014-12-27 10:07 | [6 empty] | 2014-12-27 10:08 | Yes | -7
VD-9001-205A-CAL-019 | 2 | MECHANICAL CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-10-28 11:24 | 2014-10-28 14:22 | Yes | 3 |  | 2014-11-12 10:52 | [6 empty] | 2014-11-12 10:53 | Yes | 1
VD-9001-205A-CAL-020 | 2 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2015-02-01 12:42 |  | No | 99 | 2015-03-09 16:10 | [8 empty] | No | 0
VD-9001-205A-CAL-024 | 1 | MECHANICAL CALCULATION FOR INTERNALS OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2015-01-11 12:32 |  | No | 78 |  | 2015-01-28 15:50 | [7 empty] | No | 0
VD-9001-205A-CAL-025 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2015-02-02 12:36 | 2015-02-03 09:10 | Yes | 101 |  | 2015-03-09 16:15 | [6 empty] | 2015-03-09 16:16 | Yes | 21
VD-9001-213B-CAL-005 | 1 | Pipe Support Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-10-25 | 2015-01-17 13:22 |  | No | 84 | 2015-02-26 12:12 | [8 empty] | No | 0
VD-9001-213B-CAL-004 | 1 | Nozzle Load Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-10-25 | 2014-11-26 12:57 |  | No | 32 | 2014-12-17 15:07 | [8 empty] | No | 0
VD-9001-206A-DWG-009 | 1 | NAME PLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-10-25 | 2014-10-27 10:32 |  | No | 2 |  | 2014-11-30 17:22 | [7 empty] | No | 0
VD-9001-205A-DWG-011 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-10-21 15:03 |  | No | -4 | 2014-11-02 16:27 | [8 empty] | No | 0
VD-9001-205A-DWG-016 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-10-28 11:29 |  | No | 3 | 2014-11-25 17:05 | [8 empty] | No | 0
VD-9001-205A-DWG-021 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-10-25 | 2014-10-30 11:54 |  | No | 5 | 2014-11-25 17:10 | [8 empty] | No | 0
VD-9001-253(A)-DWG-002 | 4 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-10-25 | 2015-04-25 16:38 |  | No | 182 | 2015-05-17 15:08 | [8 empty] | No | 0
VD-9001-213A-WMP-037 | 2 | Welding Maps for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-10-30 | 2014-10-25 07:25 |  | No | -5 |  | 2014-12-03 11:27 | [7 empty] | No | 0
VD-9001-213A-DWG-106 | 1 | Wind Girder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-10-30 | 2014-12-28 15:31 | 2014-12-28 15:54 | Yes | 59 |  | 2015-01-03 15:21 | [6 empty] | 2015-01-03 15:22 | Yes | -8
VD-9001-205A-DWG-012 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-01 | 2014-10-25 15:45 |  | No | -7 | 2014-11-10 14:36 | [8 empty] | No | 0
VD-9001-205A-DWG-013 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-01 | 2015-04-21 09:09 |  | No | 171 | 2015-05-18 17:26 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-01 | 2014-10-29 10:02 |  | No | -3 | 2014-12-09 11:16 | [8 empty] | No | 0
VD-9001-205A-DWG-022 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-01 | 2015-02-04 13:12 |  | No | 95 | 2015-04-11 17:54 | [8 empty] | No | 0
VD-9001-206A-DWG-001 | 4 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2014-11-12 | 2014-11-17 10:14 |  | No | 5 |  | 2014-11-17 11:06 | [7 empty] | No | 0
VD-9001-206A-DWG-013 | 2 | NOZZLE DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-11-12 | 2015-01-22 12:52 |  | No | 71 | 2015-02-08 10:33 | [8 empty] | No | 0
VD-9001-206A-DWG-005 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-11-12 | 2014-11-29 11:32 |  | No | 17 | 2014-12-08 16:49 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-22 09:55
VD-9001-206A-CAL-003 | 2 | MECHANICAL CALCULATION BOOK ( T-3002 ) | PV-206A | TASHA | 2014-11-12 | 2015-01-14 13:41 |  | No | 63 |  | 2015-01-28 18:22 | [7 empty] | No | 0
VD-9001-206A-DWG-006 | 1 | INSULATION SUPPORT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-11-16 | 2014-11-12 16:19 | 2014-11-12 17:00 | Yes | -4 |  | 2014-11-30 16:26 | [6 empty] | 2014-11-30 16:27 | Yes | 4
VD-9001-205A-DWG-011 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-16 | 2014-11-06 12:36 |  | No | -10 | 2014-11-09 11:34 | [8 empty] | No | 0
VD-9001-213A-DWG-042 | 5 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2014-11-02 | 2014-11-03 09:16 |  | No | 1 |  | 2014-11-10 16:38 | [7 empty] | No | 0
VD-9001-213A-DWG-061 | 5 | Shell Plates for Tk-6401 | PV-213A | MachineSazi Pars | 2014-11-02 | 2014-11-03 09:17 | 2014-11-05 12:51 | Yes | 3 |  | 2014-11-10 16:39 | [6 empty] | 2014-11-10 16:40 | Yes | -7
VD-9001-213A-DWG-082 | 6 | Shell Plates for Tk-7101A | PV-213A | MachineSazi Pars | 2014-11-02 | 2014-11-03 09:18 | 2014-11-05 12:52 | Yes | 3 |  | 2014-11-10 16:40 | [6 empty] | 2014-11-10 16:41 | Yes | -7
VD-9001-213A-DWG-083 | 6 | Shell Plates for Tk-7101B | PV-213A | MachineSazi Pars | 2014-11-02 | 2014-11-03 09:19 | 2014-11-05 12:53 | Yes | 3 |  | 2014-11-10 16:40 | [6 empty] | 2014-11-10 16:41 | Yes | -7
VD-9001-213A-DWG-125 | 4 | Shell Plates for Tk-7201 | PV-213A | MachineSazi Pars | 2014-11-02 | 2014-11-03 09:20 | 2014-11-05 12:54 | Yes | 3 |  | 2014-11-10 16:40 | [6 empty] | 2014-11-10 16:41 | Yes | -7
VD-9001-213A-DWG-119 | 1 | Water Cooling System for Tk-7101A | PV-213A | MachineSazi Pars | 2014-11-22 | 2014-12-03 15:26 |  | No | 11 | 2015-01-26 17:34 | [8 empty] | No | 0
VD-9001-213A-DWG-120 | 1 | Water Cooling System for Tk-7101B | PV-213A | MachineSazi Pars | 2014-11-22 | 2014-12-03 15:30 |  | No | 11 | 2015-01-26 17:35 | [8 empty] | No | 0
VD-9001-213A-DWG-144 | 1 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2014-11-22 | 2014-12-03 15:39 |  | No | 11 | 2015-01-26 17:35 | [8 empty] | No | 0
VD-9001-205A-DWG-011 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-23 | 2014-11-09 13:40 |  | No | -14 | 2014-12-09 11:22 | [8 empty] | No | 0
VD-9001-213A-DWG-121 | 1 | Foam Protection System for Tk-7101A | PV-213A | MachineSazi Pars | 2014-11-23 | 2014-12-28 15:39 |  | No | 35 | 2015-01-26 17:44 | [8 empty] | No | 0
VD-9001-213A-DWG-122 | 1 | Foam Protection System for Tk-7101B | PV-213A | MachineSazi Pars | 2014-11-23 | 2014-12-28 15:42 |  | No | 35 | 2015-01-26 17:45 | [8 empty] | No | 0
VD-9001-213A-DWG-145 | 1 | Foam Protection System for Tk-7201 | PV-213A | MachineSazi Pars | 2014-11-23 | 2014-12-28 15:43 |  | No | 35 | 2015-01-26 17:45 | [8 empty] | No | 0
VD-9001-213A-DWG-041 | 2 | General Assembly for Tk-2201 | PV-213A | MachineSazi Pars | 2014-11-24 | 2014-11-13 10:24 |  | No | -11 |  | 2014-12-14 11:30 | [7 empty] | No | 0
VD-9001-205A-DWG-012 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-11-24 | 2014-11-10 16:54 |  | No | -14 | 2014-12-09 11:27 | [8 empty] | No | 0
VD-9001-213A-DWG-102 | 2 | Spiral Stairway for Tk-7101A | PV-213A | MachineSazi Pars | 2014-11-26 | 2014-12-27 12:05 |  | No | 31 |  | 2015-01-31 11:16 | [7 empty] | No | 0
VD-9001-213A-DWG-103 | 2 | Spiral Stairway for Tk-7101B | PV-213A | MachineSazi Pars | 2014-11-26 | 2014-12-27 12:06 |  | No | 31 |  | 2015-01-31 11:17 | [7 empty] | No | 0
VD-9001-213A-DWG-104 | 1 | Walkway With Handrail for Tk-7101A | PV-213A | MachineSazi Pars | 2014-11-26 | 2014-12-27 12:08 |  | No | 31 | 2015-01-31 11:17 | [8 empty] | No | 0
VD-9001-213A-DWG-105 | 1 | Walkway With Handrail for Tk-7101B | PV-213A | MachineSazi Pars | 2014-11-26 | 2014-12-27 12:09 |  | No | 31 | 2015-01-31 11:18 | [8 empty] | No | 0
VD-9001-213A-CAL-011 | 1 | Nozzle Load Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-11-29 | 2014-11-26 13:03 | 2014-11-26 15:04 | Yes | -3 |  | 2015-01-21 16:59 | [6 empty] | 2015-01-21 17:00 | Yes | 42
VD-9001-213A-CAL-018 | 1 | Nozzle Load Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-11-29 | 2014-11-26 13:06 |  | No | -3 | 2015-01-21 17:01 | [8 empty] | No | 0
VD-9001-213A-CAL-025 | 2 | Nozzle Load Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-11-29 | 2014-11-26 13:09 |  | No | -3 | 2015-01-21 17:02 | [8 empty] | No | 0
VD-9001-213A-CAL-004 | 1 | Nozzle Load Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-11-29 | 2014-11-26 13:00 |  | No | -3 | 2015-01-21 17:01 | [8 empty] | No | 0
VD-9001-205A-DWG-039 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-07 | 2014-12-11 11:36 |  | No | 4 | 2015-08-26 10:19 | [8 empty] | No | 0
VD-9001-205A-DWG-040 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-07 | 2014-12-11 11:37 |  | No | 4 | 2015-08-26 10:20 | [8 empty] | No | 0
VD-9001-205A-DWG-041 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-07 | 2014-12-11 11:37 | 2014-12-14 10:23 | Yes | 7 |  | 2015-08-26 10:20 | [6 empty] | 2015-08-26 10:21 | Yes | 244
VD-9001-206A-DWG-021 | 3 | GENERAL ARRANGMENT ( T-3003 ) | PV-206A | TASHA | 2014-12-09 | 2015-01-22 12:54 |  | No | 44 |  | 2015-02-28 15:53 | [7 empty] | No | 0
VD-9001-213A-CAL-015 | 6 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-12-09 | 2014-11-27 10:15 |  | No | -12 | 2014-12-14 11:33 | [8 empty] | No | 0
VD-9001-205A-DWG-016 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-09 | 2014-12-07 13:55 |  | No | -2 | 2015-02-04 11:21 | [8 empty] | No | 0
VD-9001-205A-DWG-021 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-09 | 2015-02-07 12:55 | 2015-02-07 14:10 | Yes | 60 |  | 2015-03-09 16:19 | [6 empty] | 2015-03-09 16:20 | Yes | 16
VD-9001-206A-DWG-017 | 1 | TOP DAVIT DRAWING ( T-3002 ) | PV-206A | TASHA | 2014-12-09 | 2014-12-30 08:54 |  | No | 21 | 2015-01-28 18:08 | [8 empty] | No | 0
VD-9001-206A-DWG-027 | 1 | TOP DAVIT DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-12-09 | 2015-01-29 11:03 |  | No | 51 |  | 2015-02-03 16:44 | [7 empty] | No | 0
VD-9001-206A-DWG-011 | 3 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2014-12-12 | 2015-01-10 18:39 |  | No | 29 | 2015-02-03 16:53 | [8 empty] | No | 0
VD-9001-213A-CAL-005 | 1 | Pipe Support Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2014-12-17 | 2015-01-17 13:26 |  | No | 31 | 2015-03-09 18:03 | [8 empty] | No | 0
VD-9001-213A-CAL-012 | 1 | Pipe Support Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2014-12-17 | 2015-01-17 13:31 |  | No | 31 | 2015-03-09 18:03 | [8 empty] | No | 0
VD-9001-213A-CAL-019 | 1 | Pipe Support Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-12-17 | 2015-01-17 13:29 |  | No | 31 | 2015-03-09 18:04 | [8 empty] | No | 0
VD-9001-213A-CAL-026 | 1 | Pipe Support Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2014-12-17 | 2015-01-17 13:34 |  | No | 31 | 2015-03-09 18:04 | [8 empty] | No | 0
VD-9001-213A-WMP-037 | 3 | Welding Maps for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2014-12-06 | 2014-12-14 12:48 | 2014-12-14 14:28 | Yes | 8 |  | 2014-12-25 11:14 | [6 empty] | 2014-12-25 11:15 | Yes | -3 | 1204-Owner-v | 2020-05-21 07:13
VD-9001-206A-DWG-007 | 2 | TOP DAVIT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-12-22 | 2014-12-15 09:19 |  | No | -7 |  | 2014-12-27 15:17 | [7 empty] | No | 0
VD-9001-206A-DWG-005 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-12-22 | 2014-12-27 16:47 |  | No | 5 | 2015-01-17 12:15 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-22 09:56
VD-9001-206A-DWG-028 | 1 | PIPE CLIP DRAWING ( T-3003 ) | PV-206A | TASHA | 2014-12-23 | 2015-01-29 11:07 |  | No | 37 | 2015-02-03 16:45 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-23 | 2014-12-09 15:33 |  | No | -14 | 2015-01-17 10:38 | [8 empty] | No | 0
VD-9001-205A-DWG-011 | 4 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-23 | 2014-12-09 15:31 |  | No | -14 |  | 2015-02-04 11:27 | [7 empty] | No | 0
VD-9001-205A-DWG-012 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-12-23 | 2014-12-09 15:32 |  | No | -14 | 2015-01-28 15:38 | [8 empty] | No | 0
VD-9001-213A-CAL-015 | 7 | Mechanical Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-12-28 | 2015-02-23 12:16 | 2015-02-23 14:12 | Yes | 57 |  | 2015-02-23 17:18 | [6 empty] | 2015-02-23 17:19 | Yes | -14
VD-9001-253(A)-DWG-006 | 1 | PLENUM for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-12-29 | 2014-12-27 15:42 |  | No | -2 |  | 2014-12-28 10:13 | [7 empty] | No | 0
VD-9001-253(A)-DWG-012 | 1 | NAME PLATE for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-12-29 | 2014-12-27 15:27 |  | No | -2 |  | 2014-12-28 10:09 | [7 empty] | No | 0
VD-9001-253(A)-DWG-004 | 1 | BUNDLE FRAME for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2014-12-29 | 2014-12-29 16:01 | 2014-12-30 10:25 | Yes | 1 |  | 2015-01-18 10:40 | [6 empty] | 2015-01-18 10:41 | Yes | 6 | 1204-Owner-v | 2018-08-14 17:17
VD-9001-253(A)-CAL-081 | 1 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-12-29 | 2015-01-10 14:47 |  | No | 12 | 2015-01-18 10:35 | [8 empty] | No | 0
VD-9001-213B-CAL-004 | 2 | Nozzle Load Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2014-12-31 | 2015-01-10 15:54 | 2015-01-10 16:05 | Yes | 10 |  | 2015-01-13 09:41 | [6 empty] | 2015-01-13 09:42 | Yes | -11
VD-9001-253(A)-DWG-072 | 1 | NAME PLATE for 3002 | HM-253A | FATEH SANAT KIMIA | 2014-12-31 | 2014-12-27 15:40 |  | No | -4 |  | 2014-12-28 10:13 | [7 empty] | No | 0
VD-9001-253(A)-DWG-064 | 1 | BUNDLE FRAME for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2014-12-31 | 2014-12-29 16:09 | 2014-12-30 10:24 | Yes | -1 |  | 2015-01-18 10:40 | [6 empty] | 2015-01-18 10:41 | Yes | 6 | 1204-Owner-v | 2018-01-28 15:27
VD-9001-253(A)-DWG-042 | 1 | NAME PLATE for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-01-05 | 2014-12-27 15:30 |  | No | -9 |  | 2014-12-28 10:11 | [7 empty] | No | 0
VD-9001-253(A)-DWG-036 | 1 | PLENUM for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-01-05 | 2014-12-27 15:45 |  | No | -9 |  | 2014-12-28 10:14 | [7 empty] | No | 0
VD-9001-253(A)-DWG-034 | 1 | BUNDLE FRAME for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2015-01-05 | 2014-12-29 16:04 | 2014-12-30 10:23 | Yes | -6 |  | 2015-01-18 10:40 | [6 empty] | 2015-01-18 10:41 | Yes | 6 | 1204-Owner-v | 2019-03-11 18:27
VD-9001-206A-DWG-018 | 1 | PIPE CLIP DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-01-10 | 2015-01-29 11:01 |  | No | 19 | 2015-02-17 11:28 | [8 empty] | No | 0
VD-9001-206A-DWG-023 | 2 | NOZZLE DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-01-10 | 2015-01-22 12:56 |  | No | 12 | 2015-02-03 17:01 | [8 empty] | No | 0
VD-9001-206A-DWG-007 | 3 | TOP DAVIT DRAWING ( T-3001 ) | PV-206A | TASHA | 2014-12-29 | 2014-12-30 08:53 | 2014-12-30 09:11 | Yes | 1 |  | 2015-01-28 18:07 | [6 empty] | 2015-01-28 18:08 | Yes | 15
VD-9001-213A-PCJ-034 | 2 | Erection Procedure forTk-2201 & Tk-6401 & Tk-7201 | PV-213A | MachineSazi Pars | 2015-01-13 | 2015-01-15 12:57 | 2015-01-17 14:06 | Yes | 4 |  | 2015-01-20 12:02 | [6 empty] | 2015-01-20 12:03 | Yes | -9
VD-9001-213A-DWG-111 | 5 | Drain Sump for Tk-7101A/B | PV-213A | MachineSazi Pars | 2014-12-31 | 2014-12-31 15:42 | 2014-12-31 15:58 | Yes | 0 |  | 2015-01-03 09:57 | [6 empty] | 2015-01-03 09:58 | Yes | -11
VD-9001-253(A)-RPT-022 | 2 | FOUNDATION LOADING for 2001 | HM-253A | FATEH SANAT KIMIA | 2014-12-31 | 2014-12-31 17:03 |  | No | 0 |  | 2015-02-03 09:26 | [7 empty] | No | 0
VD-9001-213A-DWG-066 | 2 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2015-01-17 | 2015-01-25 16:21 |  | No | 8 | 2015-01-31 11:25 | [8 empty] | No | 0
VD-9001-213A-DWG-067 | 1 | Walkway With Handrail for Tk-6401 | PV-213A | MachineSazi Pars | 2015-01-17 | 2015-01-25 16:23 |  | No | 8 |  | 2015-01-31 11:26 | [7 empty] | No | 0
VD-9001-213A-PCJ-014 | 2 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-01-17 | 2015-02-03 09:37 |  | No | 17 | 2015-02-23 16:56 | [8 empty] | No | 0
VD-9001-213A-DWG-041 | 3 | General Assembly for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:34 |  | No | 0 | 2015-01-08 11:45 | [8 empty] | No | 0
VD-9001-213A-DWG-042 | 6 | Shell Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:37 | 2015-01-05 12:44 | Yes | 0 |  | 2015-01-08 11:47 | [6 empty] | 2015-01-08 11:48 | Yes | -11
VD-9001-213A-DWG-043 | 3 | Bottom Plates for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:40 | 2015-01-05 12:44 | Yes | 0 |  | 2015-01-08 11:47 | [6 empty] | 2015-01-08 11:48 | Yes | -11
VD-9001-213A-DWG-044 | 4 | Fix Roof Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:44 | 2015-01-05 13:19 | Yes | 0 |  | 2015-01-08 11:48 | [6 empty] | 2015-01-08 11:49 | Yes | -11
VD-9001-213A-DWG-045 | 4 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:48 |  | No | 0 | 2015-01-08 11:46 | [8 empty] | No | 0
VD-9001-213A-DWG-047 | 3 | Spiral Stairway for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:52 | 2015-01-05 13:20 | Yes | 0 |  | 2015-01-08 11:49 | [6 empty] | 2015-01-08 11:50 | Yes | -11
VD-9001-213A-DWG-049 | 2 | Shell Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:55 |  | No | 0 | 2015-01-08 11:46 | [8 empty] | No | 0
VD-9001-213A-DWG-053 | 4 | Drain Sump for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 12:57 | 2015-01-05 13:22 | Yes | 0 |  | 2015-01-08 11:49 | [6 empty] | 2015-01-08 11:50 | Yes | -11
VD-9001-213A-DWG-054 | 3 | Anchor Chair for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 13:00 | 2015-01-05 13:23 | Yes | 0 |  | 2015-01-08 11:50 | [6 empty] | 2015-01-08 11:51 | Yes | -11
VD-9001-213A-DWG-058 | 2 | Instrument Cable Tray Support for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-05 | 2015-01-05 13:04 | 2015-01-05 13:24 | Yes | 0 |  | 2015-01-08 11:50 | [6 empty] | 2015-01-08 11:51 | Yes | -11
VD-9001-213A-DWG-041 | 4 | General Assembly for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-22 | 2015-01-10 12:09 | 2015-01-10 12:50 | Yes | -12 |  | 2015-01-13 09:25 | [6 empty] | 2015-01-13 09:26 | Yes | -11 | 1204-Owner-v | 2019-02-16 09:14
VD-9001-213A-DWG-045 | 5 | Fixed Roof Orientation for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-22 | 2015-01-10 12:12 | 2015-01-10 12:51 | Yes | -12 |  | 2015-01-13 09:25 | [6 empty] | 2015-01-13 09:26 | Yes | -11
VD-9001-213A-DWG-049 | 3 | Shell Nozzles for Tk-2201 | PV-213A | MachineSazi Pars | 2015-01-22 | 2015-01-10 12:15 | 2015-01-10 12:52 | Yes | -12 |  | 2015-01-13 09:26 | [6 empty] | 2015-01-13 09:27 | Yes | -11
VD-9001-213A-DWG-089 | 1 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-01-27 | 2015-01-19 07:34 |  | No | -8 | 2015-02-09 12:28 | [8 empty] | No | 0
VD-9001-213A-DWG-090 | 1 | Deck Plate for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-01-27 | 2015-01-24 11:08 | 2015-01-24 11:12 | Yes | -3 |  | 2015-01-27 09:56 | [6 empty] | 2015-01-27 09:57 | Yes | -11
VD-9001-213A-DWG-099 | 1 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-01-27 | 2015-03-03 17:16 |  | No | 35 | 2015-03-19 12:04 | [8 empty] | No | 0
VD-9001-213A-DWG-100 | 1 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-01-27 | 2015-03-03 17:16 |  | No | 35 | 2015-03-19 12:04 | [8 empty] | No | 0
VD-9001-213A-WPS-031 | 4 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2015-01-17 | 2015-02-25 10:00 |  | No | 39 | 2015-03-12 12:40 | [8 empty] | No | 0
VD-9001-206A-DWG-025 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-01-31 | 2015-02-25 16:34 |  | No | 25 | 2015-03-18 17:48 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-01-31 | 2015-02-02 13:36 |  | No | 2 |  | 2015-02-28 16:01 | [7 empty] | No | 0
VD-9001-206A-DWG-005 | 3 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-01-31 | 2015-01-24 10:36 |  | No | -7 | 2015-02-08 10:18 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-22 09:57
VD-9001-253(A)-CAL-021 | 1 | BASE PLATE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-02-01 | 2015-04-25 16:43 |  | No | 83 |  | 2015-05-06 10:51 | [7 empty] | No | 0
VD-9001-253(A)-CAL-081 | 2 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-02-01 | 2015-02-25 15:53 |  | No | 24 |  | 2015-03-09 10:43 | [7 empty] | No | 0
VD-9001-213A-DWG-133 | 2 | Shell Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2015-01-18 | 2015-01-19 07:38 | 2015-01-19 09:43 | Yes | 1 |  | 2015-01-20 12:11 | [6 empty] | 2015-01-20 12:12 | Yes | -13
VD-9001-213A-DWG-135 | 5 | Shell Manhole for Tk-7201 | PV-213A | MachineSazi Pars | 2015-01-18 | 2015-01-19 07:42 | 2015-01-19 09:44 | Yes | 1 |  | 2015-01-20 12:12 | [6 empty] | 2015-01-20 12:13 | Yes | -13
VD-9001-213A-DWG-137 | 3 | Drain Sump for Tk-7201 | PV-213A | MachineSazi Pars | 2015-01-18 | 2015-01-19 07:45 | 2015-01-19 09:45 | Yes | 1 |  | 2015-01-20 12:12 | [6 empty] | 2015-01-20 12:13 | Yes | -13
VD-9001-213A-CAL-004 | 2 | Nozzle Load Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2015-02-04 | 2015-02-17 08:43 |  | No | 13 | 2015-04-14 11:46 | [8 empty] | No | 0
VD-9001-213A-CAL-018 | 2 | Nozzle Load Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-04 | 2015-02-17 08:46 | 2015-02-17 09:57 | Yes | 13 |  | 2015-02-23 17:03 | [6 empty] | 2015-02-23 17:04 | Yes | -8
VD-9001-213A-CAL-025 | 3 | Nozzle Load Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-04 | 2015-02-17 08:49 |  | No | 13 | 2015-02-23 17:01 | [8 empty] | No | 0
VD-9001-213A-DWG-065 | 7 | Roof Structure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-01-22 | 2015-02-24 15:03 | 2015-02-24 16:41 | Yes | 33 |  | 2015-03-19 11:58 | [6 empty] | 2015-03-19 11:59 | Yes | 9 | 1204-Owner-v | 2019-12-30 09:16
VD-9001-213A-DWG-101 | 7 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-01-22 | 2015-01-22 11:34 |  | No | 0 | 2015-02-04 18:09 | [8 empty] | No | 0
VD-9001-206A-DWG-022 | 3 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-01-24 | 2015-01-24 13:15 |  | No | 0 |  | 2015-02-03 17:00 | [7 empty] | No | 0
VD-9001-253(A)-DWG-032 | 3 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2015-02-09 | 2015-05-13 14:59 |  | No | 93 | 2015-06-07 16:06 | [8 empty] | No | 0
VD-9001-213A-DWG-119 | 2 | Water Cooling System for Tk-7101A | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-04-29 16:17 |  | No | 79 | 2015-06-30 09:13 | [8 empty] | No | 0
VD-9001-213A-DWG-120 | 2 | Water Cooling System for Tk-7101B | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-04-29 16:17 |  | No | 79 | 2015-06-30 09:14 | [8 empty] | No | 0
VD-9001-213A-DWG-144 | 2 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-04-22 11:55 |  | No | 72 | 2015-06-30 09:06 | [8 empty] | No | 0
VD-9001-213A-DWG-121 | 2 | Foam Protection System for Tk-7101A | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-08-10 12:55 |  | No | 182 | 2015-09-30 11:45 | [8 empty] | No | 0
VD-9001-213A-DWG-122 | 2 | Foam Protection System for Tk-7101B | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-08-10 12:56 |  | No | 182 | 2015-09-30 11:45 | [8 empty] | No | 0
VD-9001-213A-DWG-145 | 2 | Foam Protection System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-08-18 16:07 |  | No | 190 | 2015-09-27 16:36 | [8 empty] | No | 0
VD-9001-213A-PCJ-033 | 1 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-09 | 2015-02-03 09:40 |  | No | -6 | 2015-02-04 18:14 | [8 empty] | No | 0
VD-9001-213B-PCJ-012 | 2 | Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-02-10 | 2015-02-08 08:24 |  | No | -2 | 2015-03-03 18:21 | [8 empty] | No | 0
VD-9001-205A-DWG-012 | 4 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-02-11 | 2015-02-02 10:05 |  | No | -9 |  | 2015-02-12 10:48 | [7 empty] | No | 0
VD-9001-206A-DWG-017 | 2 | TOP DAVIT DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-02-11 | 2015-02-03 14:39 | 2015-02-03 15:00 | Yes | -8 |  | 2015-03-04 16:52 | [6 empty] | 2015-03-04 16:53 | Yes | 15
VD-9001-206A-DWG-003 | 3 | NOZZLE DETAIL DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-02-11 | 2015-02-03 14:35 | 2015-02-03 14:59 | Yes | -8 |  | 2015-02-12 10:41 | [6 empty] | 2015-02-12 10:42 | Yes | -5 | 1204-Owner-v | 2019-07-22 11:42
VD-9001-213A-DWG-130 | 2 | Spiral Stairway for Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-14 | 2015-02-09 12:35 |  | No | -5 | 2015-03-10 17:29 | [8 empty] | No | 0
VD-9001-213A-DWG-131 | 1 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-14 | 2015-02-08 18:33 |  | No | -6 | 2015-03-11 11:29 | [8 empty] | No | 0
VD-9001-213A-DWG-104 | 2 | Walkway With Handrail for Tk-7101A | PV-213A | MachineSazi Pars | 2015-02-14 | 2015-02-16 16:49 |  | No | 2 | 2015-03-10 17:34 | [8 empty] | No | 0
VD-9001-213A-DWG-105 | 2 | Walkway With Handrail for Tk-7101B | PV-213A | MachineSazi Pars | 2015-02-14 | 2015-02-16 16:51 |  | No | 2 | 2015-03-10 17:34 | [8 empty] | No | 0
VD-9001-213A-DWG-066 | 3 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2015-02-14 | 2015-03-08 08:11 |  | No | 22 | 2015-03-19 12:08 | [8 empty] | No | 0
VD-9001-253(A)-CAL-080 | 1 | STRUCTURE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-02-17 | 2015-05-10 10:07 |  | No | 82 | 2015-05-24 15:35 | [8 empty] | No | 0
VD-9001-253(A)-CAL-020 | 1 | STRUCTURE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-02-17 | 2015-04-25 16:43 |  | No | 67 |  | 2015-05-03 17:22 | [7 empty] | No | 0
VD-9001-206A-DWG-028 | 2 | PIPE CLIP DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-02-17 | 2015-02-04 15:11 | 2015-02-04 15:31 | Yes | -13 |  | 2015-02-17 11:32 | [6 empty] | 2015-02-17 11:33 | Yes | -1 | 1204-Owner-v | 2019-12-21 13:58
VD-9001-206A-DWG-011 | 4 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2015-02-17 | 2015-02-17 09:48 |  | No | 0 | 2015-04-05 15:23 | [8 empty] | No | 0
VD-9001-206A-DWG-023 | 3 | NOZZLE DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-02-17 | 2015-02-17 09:57 | 2015-02-18 17:48 | Yes | 1 |  | 2015-03-18 17:45 | [6 empty] | 2015-03-18 17:46 | Yes | 15
VD-9001-205A-DWG-016 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-02-18 | 2015-02-07 16:25 |  | No | -11 | [9 empty] | No | 0
VD-9001-205A-QCP-057 | 1 | INSPECTION AND TEST PALN & PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-02-18 | 2015-06-18 09:50 |  | No | 120 | 2015-09-15 09:45 | [8 empty] | No | 0
VD-9001-205A-WPS-058 | 1 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-02-18 | 2015-05-10 10:21 |  | No | 81 | 2015-05-25 16:27 | [8 empty] | No | 0
VD-9001-213A-DWG-091 | 1 | Floating Roof Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-18 | 2015-03-02 11:41 |  | No | 12 | 2015-04-04 11:03 | [8 empty] | No | 0
VD-9001-213A-DWG-101 | 8 | Roof Structure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-18 | 2015-02-07 10:16 | 2015-02-07 11:21 | Yes | -11 |  | 2015-02-23 16:47 | [6 empty] | 2015-02-23 16:48 | Yes | 2
VD-9001-213A-PCJ-033 | 2 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-18 | 2015-02-17 08:52 |  | No | -1 | 2015-02-23 17:00 | [8 empty] | No | 0
VD-9001-213A-PCJ-035 | 2 | Hydro Test and Air test procedurefor Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2015-02-21 | 2015-02-17 08:55 | 2015-02-17 10:00 | Yes | -4 |  | 2015-02-23 17:04 | [6 empty] | 2015-02-23 17:05 | Yes | -8 | 1204-Owner-v | 2020-05-21 07:10
VD-9001-206A-DWG-005 | 4 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-02-22 | 2015-02-16 09:06 | 2015-02-17 09:48 | Yes | -5 |  | 2015-03-04 17:20 | [6 empty] | 2015-03-04 17:21 | Yes | 2 | 1204-Owner-v | 2019-07-22 09:55
VD-9001-206A-DWG-013 | 3 | NOZZLE DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-02-22 | 2015-02-17 09:51 |  | No | -5 | 2015-04-04 10:09 | [8 empty] | No | 0
VD-9001-213A-DWG-089 | 2 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-02-23 | 2015-02-28 11:11 |  | No | 5 | 2015-03-07 08:51 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-103 | 1 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-02-28 | 2015-05-07 16:29 |  | No | 68 | 2015-05-17 15:17 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-098 | 1 | WELDING DOCUMENT FOR HEADER BOX | HM-253A | FATEH SANAT KIMIA | 2015-02-28 | 2015-05-24 10:30 |  | No | 85 | 2015-06-21 15:58 | [8 empty] | No | 0
VD-9001-206A-DWG-016 | 1 | INSULATION SUPPORT DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-03-03 | 2015-02-25 16:31 | 2015-02-25 17:16 | Yes | -6 |  | 2015-03-04 17:09 | [6 empty] | 2015-03-04 17:10 | Yes | -7
VD-9001-206A-DWG-026 | 1 | INSULATION SUPPORT DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-03-03 | 2015-02-25 16:36 | 2015-02-25 17:19 | Yes | -6 |  | 2015-03-04 17:10 | [6 empty] | 2015-03-04 17:11 | Yes | -7
VD-9001-206A-DWG-018 | 2 | PIPE CLIP DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-03-03 | 2015-02-25 16:32 | 2015-02-25 17:17 | Yes | -6 |  | 2015-03-18 17:47 | [6 empty] | 2015-03-18 17:48 | Yes | 7
VD-9001-206A-DWG-015 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-03-03 | 2015-03-09 11:07 |  | No | 6 | 2015-04-19 10:45 | [8 empty] | No | 0
VD-9001-206A-CAL-003 | 3 | MECHANICAL CALCULATION BOOK ( T-3002 ) | PV-206A | TASHA | 2015-02-18 | 2015-02-18 17:11 | 2015-02-18 17:42 | Yes | 0 |  | 2015-03-04 17:29 | [6 empty] | 2015-03-04 17:30 | Yes | 0
VD-9001-206A-CAL-005 | 3 | MECHANICAL CALCULATION BOOK ( T-3003 ) | PV-206A | TASHA | 2015-02-18 | 2015-02-18 17:13 | 2015-02-18 17:43 | Yes | 0 |  | 2015-03-04 17:30 | [6 empty] | 2015-03-04 17:31 | Yes | 0
VD-9001-206A-DWG-012 | 3 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-02-18 | 2015-02-18 17:14 |  | No | 0 | 2015-04-05 15:24 | [8 empty] | No | 0
VD-9001-206A-DWG-022 | 4 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-02-18 | 2015-02-18 17:15 |  | No | 0 |  | 2015-03-04 16:57 | [7 empty] | No | 0
VD-9001-213A-DWG-093 | 2 | Deck Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-02 10:43 |  | No | -7 | 2015-03-07 08:59 | [8 empty] | No | 0
VD-9001-213A-DWG-092 | 1 | Floating Roof Earthing for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-14 17:07 | 2015-03-14 17:46 | Yes | 5 |  | 2015-03-19 11:39 | [6 empty] | 2015-03-19 11:40 | Yes | -9 | 1204-Owner-v | 2019-12-30 09:24
VD-9001-213A-DWG-094 | 2 | Pontoon Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-02 10:46 | 2015-03-02 14:56 | Yes | -7 |  | 2015-03-07 09:00 | [6 empty] | 2015-03-07 09:01 | Yes | -9
VD-9001-213A-PCJ-014 | 3 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-29 10:10 |  | No | 20 | 2015-04-30 10:49 | [8 empty] | No | 0
VD-9001-213A-PCJ-033 | 3 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-08 08:10 |  | No | -1 | 2015-03-10 17:44 | [8 empty] | No | 0
VD-9001-213A-CAL-025 | 4 | Nozzle Load Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-03-09 | 2015-03-02 17:43 | 2015-03-03 08:46 | Yes | -6 |  | 2015-03-19 12:16 | [6 empty] | 2015-03-19 12:17 | Yes | 3
VD-9001-213A-DWG-067 | 2 | Walkway With Handrail for Tk-6401 | PV-213A | MachineSazi Pars | 2015-02-23 | 2015-02-24 11:48 | 2015-02-24 12:33 | Yes | 1 |  | 2015-03-10 17:39 | [6 empty] | 2015-03-10 17:40 | Yes | 0
VD-9001-213B-CAL-005 | 2 | Pipe Support Calculation for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-03-12 | 2015-03-08 20:37 | 2015-03-09 11:05 | Yes | -3 |  | 2015-03-18 14:22 | [6 empty] | 2015-03-18 14:23 | Yes | -4
VD-9001-205A-DWG-018 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-03-14 | 2015-06-02 14:33 |  | No | 80 | 2015-06-08 17:50 | [8 empty] | No | 0
VD-9001-205A-DWG-023 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-03-14 | 2015-08-01 17:03 |  | No | 140 | 2015-08-19 10:46 | [8 empty] | No | 0
VD-9001-213B-PCJ-012 | 3 | Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-03-17 | 2015-05-09 12:19 |  | No | 53 | 2015-05-30 10:44 | [8 empty] | No | 0
VD-9001-257A-CAL-001 | 0 | Strength Calculation Book E-2004 | HM-257A | ABAN AIR COOLER. | 2015-03-14 | 2015-03-07 14:14 |  | No | -7 | 2015-05-31 17:39 | [8 empty] | No | 0
VD-9001-257A-CAL-002 | 0 | Strength Calculation Book E-3001 | HM-257A | ABAN AIR COOLER. | 2015-03-14 | 2015-03-07 14:15 |  | No | -7 | 2015-06-02 17:11 | [8 empty] | No | 0
VD-9001-257A-CAL-003 | 0 | Strength Calculation Book E-3002 | HM-257A | ABAN AIR COOLER. | 2015-03-14 | 2015-03-07 14:16 |  | No | -7 | 2015-06-04 11:00 | [8 empty] | No | 0
VD-9001-257A-CAL-004 | 0 | Strength Calculation Book E-3003A/B/C/D | HM-257A | ABAN AIR COOLER. | 2015-03-16 | 2015-03-07 14:17 |  | No | -9 | 2015-04-28 11:37 | [8 empty] | No | 0
VD-9001-257A-CAL-005 | 0 | Strength Calculation Book E-3004 | HM-257A | ABAN AIR COOLER. | 2015-03-16 | 2015-04-07 12:14 |  | No | 22 | 2015-05-09 10:38 | [8 empty] | No | 0
VD-9001-257A-CAL-006 | 0 | Strength Calculation Book E-3005 | HM-257A | ABAN AIR COOLER. | 2015-03-16 | 2015-04-07 12:14 |  | No | 22 | 2015-06-16 18:11 | [8 empty] | No | 0
VD-9001-257A-CAL-007 | 0 | Strength Calculation Book E-3012 | HM-257A | ABAN AIR COOLER. | 2015-03-18 | 2015-04-07 12:15 |  | No | 20 | 2015-06-07 14:53 | [8 empty] | No | 0
VD-9001-257A-CAL-008 | 0 | Strength Calculation Book E-3013 | HM-257A | ABAN AIR COOLER. | 2015-03-18 | 2015-04-07 12:16 |  | No | 20 | 2015-06-17 17:39 | [8 empty] | No | 0
VD-9001-257A-DWG-001 | 0 | General Arrangment Drawing E-2004 | HM-257A | ABAN AIR COOLER. | 2015-04-15 | 2015-04-20 09:24 |  | No | 5 | 2015-05-31 17:44 | [8 empty] | No | 0
VD-9001-257A-DWG-002 | 0 | General Arrangment Drawing E-3001 | HM-257A | ABAN AIR COOLER. | 2015-04-19 | 2015-04-27 14:54 |  | No | 8 | 2015-06-02 17:15 | [8 empty] | No | 0
VD-9001-257A-DWG-003 | 0 | General Arrangment Drawing E-3002 | HM-257A | ABAN AIR COOLER. | 2015-04-22 | 2015-04-22 12:19 |  | No | 0 | 2015-06-04 11:03 | [8 empty] | No | 0
VD-9001-257A-DWG-004 | 0 | General Arrangment Drawing E-3003A/B/C/D | HM-257A | ABAN AIR COOLER. | 2015-04-25 | 2015-03-17 12:23 |  | No | -39 | 2015-04-28 11:38 | [8 empty] | No | 0
VD-9001-257A-DWG-005 | 0 | General Arrangment Drawing E-3004 | HM-257A | ABAN AIR COOLER. | 2015-04-27 | 2015-04-18 11:56 |  | No | -9 | 2015-05-09 10:44 | [8 empty] | No | 0
VD-9001-257A-DWG-006 | 0 | General Arrangment Drawing E-3005 | HM-257A | ABAN AIR COOLER. | 2015-04-29 | 2015-05-06 09:33 |  | No | 7 | 2015-06-16 18:15 | [8 empty] | No | 0
VD-9001-257A-DWG-007 | 0 | General Arrangment Drawing E-3012 | HM-257A | ABAN AIR COOLER. | 2015-05-04 | 2015-05-06 12:09 |  | No | 2 | 2015-06-07 14:58 | [8 empty] | No | 0
VD-9001-257A-DWG-008 | 0 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2015-05-06 | 2015-05-04 09:09 |  | No | -2 | 2015-06-17 17:45 | [8 empty] | No | 0
VD-9001-257A-WMP-001 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-06-20 16:28 |  | No | 20 | 2015-06-30 10:01 | [8 empty] | No | 0
VD-9001-257A-WMP-002 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-06-20 16:31 |  | No | 20 | 2015-06-30 10:01 | [8 empty] | No | 0
VD-9001-257A-WMP-003 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-06-20 16:33 |  | No | 20 | 2015-06-30 10:01 | [8 empty] | No | 0
VD-9001-257A-WMP-004 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-06-22 16:03 |  | No | 22 | 2015-07-13 10:40 | [8 empty] | No | 0
VD-9001-257A-WMP-005 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-07-12 15:02 |  | No | 42 | 2015-08-19 12:00 | [8 empty] | No | 0
VD-9001-257A-WMP-006 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2015-07-12 15:06 |  | No | 42 | 2015-08-19 12:00 | [8 empty] | No | 0
VD-9001-257A-WMP-007 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2016-01-24 14:59 | 2016-01-24 15:00 | Yes | 238 |  | 2016-04-03 09:40 | [6 empty] | 2016-04-03 20:00 | Yes | 56
VD-9001-257A-WMP-008 | 0 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-05-31 | 2016-01-24 15:00 |  | No | 238 | 2016-04-03 09:41 | [7 empty] | 2016-04-03 20:00 | Yes | 0
VD-9001-257A-WPS-001 | 0 | Welding Procedure Specification (WPS) For CS | HM-257A | ABAN AIR COOLER. | 2015-05-27 | 2015-06-01 15:05 |  | No | 5 | 2015-06-13 15:32 | [8 empty] | No | 0
VD-9001-257A-PQR-001 | 0 | Procedure Qualification Record (PQR) For CS | HM-257A | ABAN AIR COOLER. | 2015-05-27 | 2015-06-01 15:17 |  | No | 5 | 2015-06-16 09:48 | [8 empty] | No | 0
VD-9001-257A-ITP-001 | 0 | Inspection & Test Plan | HM-257A | ABAN AIR COOLER. | 2015-03-07 | 2015-04-25 15:32 |  | No | 49 | 2015-06-07 11:25 | [8 empty] | No | 0
VD-9001-257A-PCJ-001 | 0 | Repair Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-02 | 2015-05-03 12:46 | 2015-05-03 14:17 | Yes | 1 |  | 2015-06-07 14:45 | [6 empty] | 2015-06-07 14:46 | Yes | 21
VD-9001-257A-PCJ-002 | 0 | Magnetic Particle Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-02 | 2015-04-28 15:07 | 2015-04-28 15:19 | Yes | -4 |  | 2017-06-12 15:31 | [6 empty] | 2017-06-12 20:00 | Yes | 762
VD-9001-257A-PCJ-003 | 0 | Ultrasonic Test Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-02 | 2015-05-03 12:47 | 2015-05-03 14:18 | Yes | 1 |  | 2015-06-07 14:46 | [6 empty] | 2015-06-07 14:47 | Yes | 21
VD-9001-257A-PCJ-004 | 0 | Liquid Penetrant Examination Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-02 | 2015-04-27 14:56 | 2015-04-27 15:24 | Yes | -5 |  | 2015-10-06 11:55 | [6 empty] | 2015-10-06 11:56 | Yes | 148
VD-9001-257A-PCJ-005 | 0 | Radiography Test Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-02 | 2015-04-28 15:08 | 2015-04-28 15:20 | Yes | -4 |  | 2015-06-07 15:08 | [6 empty] | 2015-06-07 15:09 | Yes | 26
VD-9001-257A-PCJ-006 | 0 | Hydrostatic Test Procedure * | HM-257A | ABAN AIR COOLER. | 2015-05-23 | 2015-07-20 15:57 |  | No | 58 | 2015-10-06 12:04 | [8 empty] | No | 0
VD-9001-257A-PCJ-007 | 0 | Tube Expand (Rolling) Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-09 | 2015-07-12 15:00 |  | No | 64 | 2015-10-06 12:00 | [8 empty] | No | 0
VD-9001-257A-PCJ-008 | 0 | Post Weld Heat Treatment Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-09 |  |  | No | 1868 | [9 empty] | No | 0
VD-9001-257A-PCJ-009 | 0 | Painting Procedure | HM-257A | ABAN AIR COOLER. | 2015-05-09 | 2015-07-20 10:23 |  | No | 72 | 2015-08-19 12:07 | [8 empty] | No | 0
VD-9001-257A-PCJ-010 | 0 | Packing and Shipping Procedure and Packing list | HM-257A | ABAN AIR COOLER. | 2015-05-24 | 2016-02-03 15:58 | 2016-02-03 15:59 | Yes | 255 |  | 2016-04-13 10:57 | [6 empty] | 2016-04-13 19:59 | Yes | 56
VD-9001-257A-DIS-001 | 0 | Vendor Print Index & Schedule | HM-257A | ABAN AIR COOLER. | 2015-03-01 | 2018-02-27 14:50 | 2018-02-27 14:50 | Yes | 1094 |  |  | 2018-04-18 16:58 | [5 empty] | 2018-04-18 16:58 | Yes | 36
VD-9001-257A-INX-001 | 0 | Final Data Book Index | HM-257A | ABAN AIR COOLER. | 2015-05-20 | 2017-02-13 08:58 |  | No | 635 | 2017-05-06 15:05 | 2017-05-06 11:38 | [6 empty] | 2017-05-06 20:59 | Yes | 0
VD-9001-257A-FDB-001 | 0 | Final Data Book | HM-257A | ABAN AIR COOLER. | 2015-05-20 | 2017-02-19 11:39 |  | No | 641 | 2017-05-06 11:38 | [7 empty] | 2017-05-06 20:59 | Yes | 0
VD-9001-257A-VLS-001 | 0 | Spare Parts For Pri-Commissioning, Commissining and Start up | HM-257A | ABAN AIR COOLER. | 2015-06-01 | 2015-12-07 12:34 |  | No | 189 | 2016-02-06 11:10 | [7 empty] | 2016-02-06 20:02 | Yes | 0
VD-9001-257A-VLS-002 | 0 | Spare Part For Two-Years Operation | HM-257A | ABAN AIR COOLER. | 2015-06-01 | 2015-12-07 12:35 |  | No | 189 | 2016-02-06 11:10 | [7 empty] | 2016-02-06 20:02 | Yes | 0
VD-9001-257A-VLS-003 | 0 | Sub Vendor List | HM-257A | ABAN AIR COOLER. | 2015-04-20 | 2015-05-03 08:02 | 2015-05-03 10:19 | Yes | 13 |  | 2015-06-02 16:22 | [6 empty] | 2015-06-02 16:23 | Yes | 16
VD-9001-257A-MPR-001 | 0 | Monthly Report | HM-257A | ABAN AIR COOLER. | 2015-05-20 |  |  | No | 1857 | [9 empty] | No | 0
VD-9001-257A-SCH-001 | 0 | Planing Schedule | HM-257A | ABAN AIR COOLER. | 2015-03-04 |  |  | No | 1934 | [9 empty] | No | 0
VD-9001-257A-SCH-002 | 0 | HSE Procedure(including electrical/rotating equipment/hot surface hazard and controls) | HM-257A | ABAN AIR COOLER. | 2015-04-20 | 2016-02-17 17:15 | 2016-02-17 17:16 | Yes | 303 |  | 2016-04-13 10:58 | [6 empty] | 2016-04-13 19:59 | Yes | 42
VD-9001-257A-INX-002 | 0 | INDEX OF QUALITY RECORD BOOK | HM-257A | ABAN AIR COOLER. | 2015-05-20 | 2015-03-07 14:19 |  | No | -74 | 2015-06-07 08:52 | [8 empty] | No | 0
VD-9001-213A-DWG-089 | 3 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-21 | 2015-03-14 13:09 |  | No | -7 | 2015-03-19 11:27 | [8 empty] | No | 0
VD-9001-213A-DWG-093 | 3 | Deck Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-21 | 2015-03-17 13:58 |  | No | -4 | 2015-03-19 11:54 | [8 empty] | No | 0
VD-9001-213A-DWG-096 | 1 | Auto Breather Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-21 | 2015-04-12 08:05 |  | No | 22 | 2015-04-25 10:04 | [8 empty] | No | 0
VD-9001-213A-DWG-098 | 1 | Rim Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-21 | 2015-06-14 15:34 |  | No | 85 | 2015-06-30 09:27 | [8 empty] | No | 0
VD-9001-205A-CAL-020 | 3 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-03-23 | 2015-03-16 13:55 |  | No | -7 | 2015-04-11 18:05 | [8 empty] | No | 0
VD-9001-213A-DWG-102 | 3 | Spiral Stairway for Tk-7101A | PV-213A | MachineSazi Pars | 2015-03-09 17:39 | 2015-03-09 17:41 | 2015-03-09 18:19 | Yes | 0 |  | 2015-03-10 17:45 | [6 empty] | 2015-03-10 17:46 | Yes | -13
VD-9001-213A-DWG-103 | 3 | Spiral Stairway for Tk-7101B | PV-213A | MachineSazi Pars | 2015-03-09 17:39 | 2015-03-09 17:42 | 2015-03-09 18:20 | Yes | 0 |  | 2015-03-10 17:46 | [6 empty] | 2015-03-10 17:47 | Yes | -13
VD-9001-213A-CAL-005 | 2 | Pipe Support Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2015-03-23 | 2015-03-29 10:07 | 2015-04-04 10:39 | Yes | 12 |  | 2015-04-09 11:43 | [6 empty] | 2015-04-09 11:44 | Yes | -3
VD-9001-213A-CAL-012 | 2 | Pipe Support Calculation for Tk-6401 | PV-213A | MachineSazi Pars | 2015-03-23 | 2015-08-25 17:35 | 2015-08-25 18:08 | Yes | 155 |  | 2015-08-29 16:45 | [6 empty] | 2015-08-29 16:46 | Yes | -10
VD-9001-213A-CAL-019 | 2 | Pipe Support Calculation for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-23 | 2015-03-29 10:07 | 2015-04-04 10:40 | Yes | 12 |  | 2015-06-30 09:00 | [6 empty] | 2015-06-30 09:01 | Yes | 79
VD-9001-213A-CAL-026 | 2 | Pipe Support Calculation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-03-23 | 2015-08-25 17:36 | 2015-08-25 18:09 | Yes | 155 |  | 2015-08-29 16:45 | [6 empty] | 2015-08-29 16:46 | Yes | -10
VD-9001-213A-DWG-130 | 3 | Spiral Stairway for Tk-7201 | PV-213A | MachineSazi Pars | 2015-03-24 | 2015-04-21 17:46 |  | No | 28 | 2015-04-25 15:54 | [8 empty] | No | 0
VD-9001-213A-DWG-104 | 3 | Walkway With Handrail for Tk-7101A | PV-213A | MachineSazi Pars | 2015-03-24 | 2015-03-15 13:05 | 2015-03-15 14:18 | Yes | -9 |  | 2015-03-19 11:45 | [6 empty] | 2015-03-19 11:46 | Yes | -10
VD-9001-213A-DWG-105 | 3 | Walkway With Handrail for Tk-7101B | PV-213A | MachineSazi Pars | 2015-03-24 | 2015-03-15 13:06 | 2015-03-15 14:20 | Yes | -9 |  | 2015-03-19 11:45 | [6 empty] | 2015-03-19 11:46 | Yes | -10
VD-9001-213A-PCJ-033 | 4 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-03-24 | 2015-05-04 10:01 |  | No | 41 | 2015-06-03 11:47 | [8 empty] | No | 0
VD-9001-253(A)-CAL-081 | 3 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-03-11 11:02 | 2015-03-11 11:26 |  | No | 0 |  | 2015-04-13 09:38 | [7 empty] | No | 0
VD-9001-108-CAL-001 | 0 | STRUCTURE CALCULATION SHEET | PR-108 | Farabard | 2015-10-01 | 2016-03-06 08:07 |  | No | 157 | 2016-04-27 15:47 | [7 empty] | 2016-04-27 19:59 | Yes | 0
VD-9001-108-CAL-002 | 0 | COOLING TOWER AND EQUIPMENTS CALCULATION & PERFORMANC CURVES BOOKLET | PR-108 | Farabard | 2015-05-15 | 2015-11-10 14:22 |  | No | 179 | 2015-12-14 17:13 | [8 empty] | No | 0
VD-9001-108-CAT-003 | 0 | CATALOGUE AND BROCHURE FOR GEAR REDUCER | PR-108 | Farabard | 2015-10-12 | 2015-09-20 15:05 | 2015-09-20 15:22 | Yes | -22 |  | 2015-10-10 15:10 | [6 empty] | 2015-10-10 15:11 | Yes | 6
VD-9001-108-CAT-004 | 0 | CATALOGUE AND BROCHURE FOR FAN | PR-108 | Farabard | 2015-10-12 | 2015-09-20 15:09 | 2015-09-20 15:22 | Yes | -22 |  | 2015-10-10 12:05 | [6 empty] | 2015-10-10 12:06 | Yes | 6
VD-9001-108-CER-005 | 0 | CERTIFICATE OF ORIGIN | PR-108 | Farabard | 2015-09-01 | 2015-10-12 13:12 | 2015-10-13 10:42 | Yes | 42 |  | 2015-10-25 17:41 | [6 empty] | 2015-10-25 17:42 | Yes | -1
VD-9001-108-DBS-006 | 0 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2015-04-25 | 2015-04-26 11:35 |  | No | 1 | 2015-05-31 15:22 | [8 empty] | No | 0
VD-9001-108-DSH-007 | 0 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:07 |  | No | -20 | 2015-04-15 11:41 | [8 empty] | No | 0
VD-9001-108-DSH-008 | 0 | FAN PACKAGE DATA SHEET | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:07 |  | No | -20 | 2015-04-22 17:24 | [8 empty] | No | 0
VD-9001-108-DSH-009 | 0 | GEAR REDUCER DATA SHEET | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:08 |  | No | -20 | 2015-05-05 17:14 | [8 empty] | No | 0
VD-9001-108-DSH-010 | 0 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:08 |  | No | -20 | 2015-04-07 14:27 | [8 empty] | No | 0
VD-9001-108-DSH-011 | 0 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:08 |  | No | -20 | 2015-04-14 08:47 | [8 empty] | No | 0
VD-9001-108-DSH-015 | 0 | VIBRATION SWITCH DATA SHEET | PR-108 | Farabard | 2015-04-19 | 2015-03-30 13:09 |  | No | -20 | 2015-04-14 08:48 | [8 empty] | No | 0
VD-9001-108-DWG-016 | 0 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-04-25 | 2015-03-30 13:09 |  | No | -26 | 2015-04-28 11:27 | [8 empty] | No | 0
VD-9001-108-DWG-017 | 0 | EXCAVATION DETAIL | PR-108 | Farabard | 2015-04-19 | 2015-03-11 15:51 |  | No | -39 |  | 2015-04-19 17:38 | [7 empty] | No | 0
VD-9001-108-DWG-018 | 0 | LEAN CONCRETE DETAIL | PR-108 | Farabard | 2015-05-27 | 2015-04-05 15:35 | 2015-04-05 15:57 | Yes | -52 |  | 2015-04-19 17:41 | [6 empty] | 2015-04-19 17:42 | Yes | 0
VD-9001-108-DWG-019 | 0 | FOUNDATION DETAIL | PR-108 | Farabard | 2015-06-07 | 2015-04-18 08:17 |  | No | -50 | 2015-05-12 15:41 | [8 empty] | No | 0
VD-9001-108-DWG-020 | 0 | COLUMNS DEATAIL | PR-108 | Farabard | 2015-07-02 | 2015-06-09 10:39 |  | No | -23 | 2015-06-14 12:17 | [8 empty] | No | 0
VD-9001-108-DWG-021 | 0 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2015-07-16 | 2015-07-11 16:08 |  | No | -5 | 2015-07-21 17:22 | [8 empty] | No | 0
VD-9001-108-DWG-022 | 0 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2015-08-08 | 2015-07-30 10:08 |  | No | -9 | 2015-08-02 15:41 | [8 empty] | No | 0
VD-9001-108-DWG-023 | 0 | SECONDERY BEAMS DETAIL | PR-108 | Farabard | 2015-08-14 | 2015-08-15 14:17 |  | No | 1 |  | 2015-08-19 17:21 | [7 empty] | No | 0
VD-9001-108-DWG-024 | 0 | WATER DISTRIBUTION CHANNEL DETAIL | PR-108 | Farabard | 2015-08-04 | 2015-09-01 13:11 |  | No | 28 |  | 2015-09-05 17:02 | [7 empty] | No | 0
VD-9001-108-DWG-025 | 0 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2015-08-24 | 2015-10-26 11:46 |  | No | 63 | 2015-11-01 11:25 | [8 empty] | No | 0
VD-9001-108-DWG-026 | 0 | HAND RAIL DETAIL | PR-108 | Farabard | 2015-08-20 | 2015-12-05 12:04 |  | No | 107 |  | 2015-12-14 10:56 | [7 empty] | No | 0
VD-9001-108-DWG-027 | 0 | LADDER DETAIL | PR-108 | Farabard | 2015-08-20 | 2015-12-05 15:05 |  | No | 107 |  | 2015-12-14 11:38 | [7 empty] | No | 0
VD-9001-108-DWG-028 | 0 | STAIR CASE DETAIL | PR-108 | Farabard | 2015-08-21 | 2015-12-01 11:58 |  | No | 102 |  | 2015-12-06 11:21 | [7 empty] | No | 0
VD-9001-108-DWG-029 | 0 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2015-02-17 | 2015-03-11 15:56 |  | No | 22 | 2015-04-05 17:58 | [8 empty] | No | 0
VD-9001-108-DWG-030 | 0 | GENERAL ARRANGMENT | PR-108 | Farabard | 2015-07-04 | 2015-12-08 11:09 |  | No | 157 | 2016-01-02 16:45 | [7 empty] | 2016-01-02 20:03 | Yes | 0
VD-9001-108-DWG-031 | 0 | INTERNAL ARRANGMENT | PR-108 | Farabard | 2015-07-04 | 2015-07-29 11:32 |  | No | 25 | 2015-08-02 15:45 | [8 empty] | No | 0
VD-9001-108-DWG-032 | 0 | PACKING ARRENGMANT | PR-108 | Farabard | 2015-07-04 | 2015-07-27 12:02 |  | No | 23 | 2015-08-02 15:50 | [8 empty] | No | 0
VD-9001-108-DWG-033 | 0 | DRIFT ELIMINATOR ARRANGMENT | PR-108 | Farabard | 2015-07-04 | 2015-07-14 13:30 |  | No | 10 | 2015-07-20 17:34 | [8 empty] | No | 0
VD-9001-108-DWG-034 | 0 | WATER DISTERIBUTION SYSTEM | PR-108 | Farabard | 2015-07-04 | 2015-07-29 11:32 |  | No | 25 | 2015-08-02 15:45 | [8 empty] | No | 0
VD-9001-108-DWG-035 | 0 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2015-08-13 | 2015-09-20 12:24 |  | No | 38 | 2015-10-13 10:02 | [8 empty] | No | 0
VD-9001-108-DWG-036 | 0 | DRIVE SHAFT ASSEMBLY | PR-108 | Farabard | 2015-08-13 | 2015-09-20 12:25 |  | No | 38 |  | 2015-10-13 10:02 | [7 empty] | No | 0
VD-9001-108-DWG-037 | 0 | FAN STACK DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2015-08-21 | 2015-09-19 14:46 |  | No | 29 |  | 2015-10-17 16:31 | [7 empty] | No | 0
VD-9001-108-DWG-038 | 0 | FAN DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2015-08-21 | 2015-09-19 14:46 |  | No | 29 |  | 2015-10-13 10:08 | [7 empty] | No | 0
VD-9001-108-DWG-039 | 0 | HUB DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2015-08-21 | 2015-09-19 14:47 | 2015-09-19 15:57 | Yes | 29 |  | 2015-10-13 10:08 | [6 empty] | 2015-10-13 10:09 | Yes | 10
VD-9001-108-DWG-040 | 0 | DRIVE SHAFT DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2015-08-21 | 2015-11-22 13:05 |  | No | 93 |  | 2015-12-14 17:18 | [7 empty] | No | 0
VD-9001-108-DWG-041 | 0 | GEAR REDUCER & ELECTRO MOTOR BASE PLATE DETAIL | PR-108 | Farabard | 2015-08-09 | 2015-09-19 14:47 |  | No | 41 | 2015-10-18 15:37 | [8 empty] | No | 0
VD-9001-108-DWG-042 | 0 | NOZZLE DETAIL | PR-108 | Farabard | 2015-04-19 | 2015-04-19 13:35 | 2015-04-19 14:50 | Yes | 0 |  | 2015-04-26 10:20 | [6 empty] | 2015-04-26 10:21 | Yes | -7
VD-9001-108-DWG-043 | 0 | DIMENSIONAL AND WEIGHT DRAWING | PR-108 | Farabard | 2015-09-01 | 2015-11-23 11:02 |  | No | 83 | 2016-01-02 16:41 | [7 empty] | 2016-01-02 20:03 | Yes | 0
VD-9001-108-DWG-044 | 0 | FABRICATION/ERECTION DRAWING | PR-108 | Farabard | 2015-09-06 | 2017-11-18 14:30 |  | No | 804 |  | 2017-11-20 16:46 | [6 empty] | 2017-11-20 19:59 | Yes | 0
VD-9001-108-DWG-045 | 0 | PLATFORM & LADDER DETAIL DRAWING | PR-108 | Farabard | 2015-09-11 | 2016-03-06 14:42 |  | No | 177 | 2016-03-15 16:54 | [7 empty] | 2016-03-15 20:00 | Yes | 0
VD-9001-108-DIG-046 | 0 | CAUSE AND EFFECT DIAGRAM | PR-108 | Farabard | 2015-06-05 | 2015-06-09 10:39 |  | No | 4 |  | 2015-06-30 15:19 | [7 empty] | No | 0
VD-9001-108-LST-047 | 0 | LOAD LIST | PR-108 | Farabard | 2015-04-19 | 2015-04-19 13:35 |  | No | 0 | 2015-04-25 17:07 | [8 empty] | No | 0
VD-9001-108-LST-048 | 0 | LIST OF SUB - SUPPLIERS AND SUB- CONTRACTORS | PR-108 | Farabard | 2015-06-05 | 2015-06-08 14:28 | 2015-06-08 17:37 | Yes | 3 |  | 2015-07-26 11:56 | [6 empty] | 2015-07-26 11:57 | Yes | 34
VD-9001-108-LST-050 | 0 | SPARE PARTS LIST FOR ERECTION AND PRECOMMISSIONING | PR-108 | Farabard | 2015-06-05 | 2015-06-08 14:28 |  | No | 3 | 2015-08-03 11:01 | [8 empty] | No | 0
VD-9001-108-LST-051 | 0 | SPARE PARTS LIST FOR 2 YEARS OF OPERATION | PR-108 | Farabard | 2015-06-05 | 2015-06-08 14:28 |  | No | 3 | 2015-06-27 17:12 | [8 empty] | No | 0
VD-9001-108-LST-052 | 0 | LIST OF SPECIAL TOOLS AND DEVICES | PR-108 | Farabard | 2015-06-05 | 2015-06-08 14:28 |  | No | 3 | 2015-06-27 10:54 | [8 empty] | No | 0
VD-9001-108-LST-053 | 0 | LUBRICANT LIST INCLUDING TYPE AND CONSUMPTION | PR-108 | Farabard | 2015-06-05 | 2015-03-11 11:09 | 2015-06-23 12:15 | Yes | 18 |  | 2015-07-15 16:19 | [6 empty] | 2015-07-15 16:20 | Yes | 112
VD-9001-108-MDL-054 | 0 | GENERAL INDEX | PR-108 | Farabard | 2015-06-05 | 2015-06-09 12:53 |  | No | 4 | 2015-06-28 15:36 | [8 empty] | No | 0
VD-9001-108-DIS-074 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | PR-108 | Farabard | 2015-02-19 | 2017-12-02 10:21 |  | No | 1017 | 2017-12-02 16:09 | [7 empty] | 2017-12-02 20:00 | Yes | 0
VD-9001-108-MNL-056 | 0 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2015-12-09 | 2015-09-05 12:50 |  | No | -95 | 2015-10-05 11:17 | [8 empty] | No | 0
VD-9001-108-MNL-057 | 0 | ISTALLATION MANUAL | PR-108 | Farabard | 2015-12-01 | 2015-09-22 09:04 |  | No | -70 | 2015-11-02 16:18 | [8 empty] | No | 0
VD-9001-108-MNL-058 | 0 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2015-12-01 | 2015-09-17 13:12 |  | No | -75 | 2015-10-18 10:33 | [8 empty] | No | 0
VD-9001-108-MTO-059 | 0 | MATRIAL TAKE OFF (INTERNALS) | PR-108 | Farabard | 2015-04-19 | 2015-04-19 13:36 |  | No | 0 | 2015-05-04 16:11 | [8 empty] | No | 0
VD-9001-108-MTO-060 | 0 | MATRIAL TAKE OFF FOR PLATES AND FLANGES | PR-108 | Farabard | 2015-04-21 | 2015-06-22 09:27 |  | No | 62 | 2015-07-04 14:49 | [8 empty] | No | 0
VD-9001-108-PCU-061 | 0 | PERFORMANCE CURVE FOR FAN | PR-108 | Farabard | 2015-12-01 | 2015-11-10 14:23 |  | No | -21 | 2015-12-01 16:31 | [8 empty] | No | 0
VD-9001-108-PCJ-064 | 0 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2015-07-01 | 2015-09-02 14:04 |  | No | 63 | 2015-09-16 16:30 | [8 empty] | No | 0
VD-9001-108-PFD-065 | 0 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2015-04-25 | 2015-04-23 11:45 |  | No | -2 | 2015-05-05 17:09 | [8 empty] | No | 0
VD-9001-108-QCP-066 | 0 | QUALITY CONTROL PLAN(QCP) | PR-108 | Farabard | 2015-03-06 | 2015-04-08 13:44 |  | No | 33 | 2015-05-25 16:19 | [8 empty] | No | 0
VD-9001-108-WBS-067 | 0 | WORK BREAKDOWN STRUCTURE | PR-108 | Farabard | 2015-02-23 | 2015-04-06 13:59 |  | No | 42 |  | 2015-04-08 11:28 | [7 empty] | No | 0
VD-9001-213A-DWG-131 | 2 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2015-03-25 | 2015-03-16 14:44 |  | No | -9 | 2015-03-19 11:50 | [8 empty] | No | 0
VD-9001-213A-WPS-031 | 5 | WPS for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2015-03-26 | 2015-03-14 09:51 | 2015-03-14 10:08 | Yes | -12 |  | 2015-04-09 11:39 | [6 empty] | 2015-04-09 11:40 | Yes | 12
VD-9001-206A-DWG-025 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-04-01 | 2015-06-07 17:45 |  | No | 67 | 2015-06-15 12:39 | [8 empty] | No | 0
VD-9001-213A-DWG-089 | 4 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-04-06 14:34 |  | No | 4 |  | 2015-04-06 15:45 | [7 empty] | No | 0
VD-9001-213A-DWG-131 | 3 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-06-24 16:32 |  | No | 83 | 2015-06-30 09:37 | [8 empty] | No | 0
VD-9001-213A-DWG-093 | 4 | Deck Manhole for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-04-12 09:36 | 2015-04-12 10:15 | Yes | 10 |  | 2015-04-14 12:05 | [6 empty] | 2015-04-14 12:06 | Yes | -12
VD-9001-213A-DWG-099 | 2 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-04-25 14:25 |  | No | 23 | 2015-06-09 08:48 | [8 empty] | No | 0
VD-9001-213A-DWG-100 | 2 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-04-25 14:25 |  | No | 23 | 2015-06-09 08:48 | [8 empty] | No | 0
VD-9001-213A-DWG-066 | 4 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2015-04-02 | 2015-04-21 17:46 |  | No | 19 | 2015-04-25 15:54 | [8 empty] | No | 0
VD-9001-206A-DWG-013 | 4 | NOZZLE DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-04-18 | 2015-04-28 19:38 | 2015-04-29 10:57 | Yes | 11 |  | 2015-05-17 11:45 | [6 empty] | 2015-05-17 11:46 | Yes | 5 | 1204-Owner-v | 2019-07-22 11:54
VD-9001-213A-DWG-060 | 2 | General Assembly for Tk-6401 | PV-213A | MachineSazi Pars | 2015-04-18 | 2015-04-18 11:51 | 2015-04-18 12:21 | Yes | 0 |  | 2015-04-25 10:14 | [6 empty] | 2015-04-25 10:15 | Yes | -7 | 1204-Owner-v | 2019-01-15 16:23
VD-9001-213A-DWG-124 | 2 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2015-04-18 | 2015-04-18 08:26 |  | No | 0 | 2015-04-25 10:10 | [8 empty] | No | 0
VD-9001-213A-DWG-091 | 2 | Floating Roof Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-18 | 2015-04-20 14:12 |  | No | 2 | 2015-04-25 15:48 | [8 empty] | No | 0
VD-9001-205A-DWG-016 | 4 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-04 16:55 | 2015-04-06 11:51 |  | No | 2 | 2015-04-11 18:00 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 4 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-04 16:55 | 2015-04-06 11:52 |  | No | 2 | [9 empty] | No | 0
VD-9001-206A-PCJ-014 | 1 | Erection procedure | PV-206A | TASHA | 2015-04-19 | 2015-04-15 10:30 |  | No | -4 | 2015-04-27 16:37 | [8 empty] | No | 0
VD-9001-206A-DWG-011 | 5 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2015-04-19 | 2015-04-15 10:28 |  | No | -4 | 2015-04-25 15:32 | [8 empty] | No | 0
VD-9001-206A-DWG-012 | 4 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-04-19 | 2015-04-15 10:28 |  | No | -4 | 2015-04-25 15:34 | [8 empty] | No | 0
VD-9001-108-DWG-029 | 1 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2015-04-19 | 2015-04-06 13:59 |  | No | -13 | 2015-04-08 17:41 | [8 empty] | No | 0
VD-9001-206A-DWG-019 | 1 | NAME PLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-04-20 | 2015-04-15 10:29 |  | No | -5 | 2015-04-19 11:55 | [8 empty] | No | 0
VD-9001-206A-DWG-029 | 1 | NAME PLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-04-20 | 2015-04-15 10:29 |  | No | -5 | 2015-04-19 11:56 | [8 empty] | No | 0
VD-9001-108-DSH-010 | 1 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2015-04-21 | 2015-04-18 08:15 |  | No | -3 | 2015-04-20 10:41 | [8 empty] | No | 0
VD-9001-108-DWG-029 | 2 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2015-04-22 | 2015-04-18 08:16 |  | No | -4 | 2015-04-28 10:11 | [8 empty] | No | 0
VD-9001-253(A)-DSH-026 | 1 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-04-25 | 2015-07-04 11:09 |  | No | 70 | 2015-07-15 16:07 | [8 empty] | No | 0
VD-9001-253(A)-DSH-056 | 1 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-04-25 | 2015-07-04 11:10 |  | No | 70 | 2015-07-15 16:07 | [8 empty] | No | 0
VD-9001-253(A)-DSH-086 | 1 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-04-25 | 2015-07-04 11:10 |  | No | 70 | 2015-07-15 16:08 | [8 empty] | No | 0
VD-9001-205A-DWG-044 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-04-20 10:56 |  | No | -5 | 2015-07-27 15:40 | [8 empty] | No | 0
VD-9001-205A-DWG-045 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-12-08 10:58 |  | No | 227 | 2016-01-05 14:20 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-205A-DWG-032 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-04-20 10:57 |  | No | -5 | 2015-07-27 15:46 | [8 empty] | No | 0
VD-9001-205A-DWG-033 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-04-20 15:18 |  | No | 1882 |  | 2015-04-20 15:25 | [6 empty] | 2015-04-20 15:26 | Yes | 0
VD-9001-205A-DWG-022 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-08-01 17:02 |  | No | 98 | 2015-08-12 17:39 | [8 empty] | No | 0
VD-9001-205A-CAL-020 | 4 | HYDRAULIC CALCULATION FOR INTERNALS OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-04-25 | 2015-04-13 14:57 | 2015-04-14 12:22 | Yes | -11 |  | 2015-10-05 16:22 | [6 empty] | 2015-10-05 16:23 | Yes | 161
VD-9001-213A-DWG-089 | 5 | Floating Roof Deatails - (Pontoon) for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-13 09:47 | 2015-04-13 10:59 | 2015-04-13 11:26 | Yes | 0 |  | 2015-04-14 12:09 | [6 empty] | 2015-04-14 12:10 | Yes | -13 | 1204-Owner-v | 2019-12-30 09:17
VD-9001-108-DSH-011 | 1 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2015-04-28 | 2015-05-17 12:26 |  | No | 19 | 2015-05-20 15:49 | [8 empty] | No | 0
VD-9001-108-DSH-015 | 1 | VIBRATION SWITCH DATA SHEET | PR-108 | Farabard | 2015-04-28 | 2015-07-01 13:10 |  | No | 64 |  | 2015-07-20 12:15 | [7 empty] | No | 0
VD-9001-213A-CAL-004 | 3 | Nozzle Load Calculation for Tk-2201 | PV-213A | MachineSazi Pars | 2015-04-28 | 2015-05-05 08:22 | 2015-05-05 10:00 | Yes | 7 |  | 2015-05-30 11:38 | [6 empty] | 2015-05-30 11:39 | Yes | 11 | 1204-Owner-v | 2019-01-15 16:25
VD-9001-213A-DWG-123 | 1 | Foam Dam for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-28 | 2015-04-25 09:55 |  | No | -3 | 2015-04-25 16:03 | [8 empty] | No | 0
VD-9001-213A-DWG-097 | 1 | LHD Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-04-28 | 2015-04-22 11:19 | 2015-04-22 11:31 | Yes | -6 |  | 2015-04-25 15:59 | [6 empty] | 2015-04-25 16:00 | Yes | -11
VD-9001-108-DSH-007 | 1 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2015-04-29 | 2015-04-18 08:15 |  | No | -11 | 2015-04-20 14:19 | [8 empty] | No | 0
VD-9001-206A-DWG-004 | 1 | INTERNAL ATTACHMENT DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-05-03 | 2015-04-28 19:36 |  | No | -5 | 2015-05-18 16:45 | [8 empty] | No | 0
VD-9001-206A-DWG-015 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-05-03 | 2015-07-29 09:32 |  | No | 87 | 2015-08-19 10:15 | [8 empty] | No | 0
VD-9001-206A-DWG-014 | 1 | INTERNAL ATTACHMENT DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-05-03 | 2015-04-28 19:39 |  | No | -5 | 2015-05-18 16:41 | [8 empty] | No | 0
VD-9001-206A-DWG-019 | 2 | NAME PLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-05-03 | 2015-04-28 19:39 |  | No | -5 | 2015-05-17 11:46 | [8 empty] | No | 0
VD-9001-206A-DWG-029 | 2 | NAME PLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-05-03 | 2015-04-28 19:40 |  | No | -5 | 2015-05-17 11:46 | [8 empty] | No | 0
VD-9001-108-DSH-010 | 2 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2015-05-04 | 2015-04-25 09:28 |  | No | -9 |  | 2015-04-28 16:56 | [7 empty] | No | 0
VD-9001-108-DSH-007 | 2 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2015-05-04 | 2015-04-25 09:26 |  | No | -9 |  | 2015-05-05 17:57 | [7 empty] | No | 0
VD-9001-108-WBS-067 | 1 | WORK BREAKDOWN STRUCTURE | PR-108 | Farabard | 2015-04-22 12:06 | 2015-04-22 12:57 |  | No | 0 | 2015-04-22 17:29 | [8 empty] | No | 0
VD-9001-108-DSH-008 | 1 | FAN PACKAGE DATA SHEET | PR-108 | Farabard | 2015-05-06 | 2015-04-25 09:28 |  | No | -11 |  | 2015-05-06 10:26 | [7 empty] | No | 0
VD-9001-108-WBS-067 | 2 | WORK BREAKDOWN STRUCTURE | PR-108 | Farabard | 2015-05-06 | 2015-04-23 10:55 | 2015-04-23 11:40 | Yes | -13 |  | 2015-04-25 12:25 | [6 empty] | 2015-04-25 12:26 | Yes | -12
VD-9001-213A-DWG-095 | 1 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-29 16:16 |  | No | -10 | 2015-05-30 11:29 | [8 empty] | No | 0
VD-9001-213A-DWG-096 | 2 | Auto Breather Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-29 16:16 |  | No | -10 |  | 2015-05-30 11:30 | [7 empty] | No | 0
VD-9001-213A-DWG-124 | 3 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-27 08:06 |  | No | -12 |  | 2015-05-30 17:30 | [7 empty] | No | 0
VD-9001-206A-DWG-011 | 6 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2015-05-09 | 2015-04-28 19:36 |  | No | -11 | 2015-06-17 10:59 | [8 empty] | No | 0
VD-9001-206A-DWG-012 | 5 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-05-09 | 2015-04-28 19:38 |  | No | -11 |  | 2015-05-17 11:42 | [7 empty] | No | 0
VD-9001-213A-DWG-091 | 3 | Floating Roof Support for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-27 08:05 | 2015-04-27 09:00 | Yes | -12 |  | 2015-05-05 09:47 | [6 empty] | 2015-05-05 09:48 | Yes | -6
VD-9001-213A-DWG-066 | 5 | Spiral Stairway for Tk-6401 | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-28 14:50 | 2015-04-28 15:03 | Yes | -11 |  | 2015-05-30 11:22 | [6 empty] | 2015-05-30 11:23 | Yes | 18
VD-9001-213A-DWG-130 | 4 | Spiral Stairway for Tk-7201 | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-28 14:50 | 2015-04-28 15:07 | Yes | -11 |  | 2015-05-30 11:23 | [6 empty] | 2015-05-30 11:24 | Yes | 18
VD-9001-213A-DWG-123 | 2 | Foam Dam for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-05-09 | 2015-04-27 08:05 | 2015-04-27 09:01 | Yes | -12 |  | 2015-05-05 09:47 | [6 empty] | 2015-05-05 09:48 | Yes | -6
VD-9001-108-LST-047 | 1 | LOAD LIST | PR-108 | Farabard | 2015-05-09 | 2015-09-16 13:25 |  | No | 130 | 2015-09-23 11:40 | [8 empty] | No | 0
VD-9001-253(A)-RPT-022 | 3 | FOUNDATION LOADING for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-04-26 15:07 | 2015-04-26 15:13 |  | No | 0 |  | 2015-05-06 10:50 | [7 empty] | No | 0
VD-9001-206A-PCJ-014 | 2 | Erection procedure | PV-206A | TASHA | 2015-05-11 | 2015-06-07 17:47 |  | No | 27 | 2015-08-12 16:10 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-099 | 1 | WELDING DOCUMENT FOR STRUCTURE | HM-253A | FATEH SANAT KIMIA | 2015-05-11 | 2015-06-16 09:19 |  | No | 36 | 2015-06-23 09:50 | [8 empty] | No | 0
VD-9001-108-DWG-029 | 3 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2015-05-12 | 2015-06-22 09:27 |  | No | 41 | 2015-07-21 17:12 | [8 empty] | No | 0
VD-9001-108-DWG-016 | 1 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-05-12 | 2015-05-25 09:53 |  | No | 13 | 2015-06-23 09:44 | [8 empty] | No | 0
VD-9001-257A-CAL-004 | 1 | Strength Calculation Book E-3003A/B/C/D | HM-257A | ABAN AIR COOLER. | 2015-05-12 | 2015-05-13 14:38 | 2015-05-13 16:23 | Yes | 1 |  | 2015-06-08 09:02 | [6 empty] | 2015-06-08 09:03 | Yes | 12
VD-9001-257A-DWG-004 | 1 | General Arrangment Drawing E-3003A/B/C/D | HM-257A | ABAN AIR COOLER. | 2015-05-12 | 2015-05-13 10:59 | 2015-05-13 16:24 | Yes | 1 |  | 2015-06-08 08:57 | [6 empty] | 2015-06-08 08:58 | Yes | 12
VD-9001-253(A)-ITP-100 | 2 | INSPECTION TEST PLAN | HM-253A | FATEH SANAT KIMIA | 2015-05-13 | 2015-05-06 08:53 |  | No | -7 | 2015-05-17 15:14 | [8 empty] | No | 0
VD-9001-213A-PCJ-014 | 4 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-05-14 | 2015-06-01 13:04 |  | No | 18 | 2015-06-30 09:19 | [8 empty] | No | 0
VD-9001-108-MTO-059 | 1 | MATRIAL TAKE OFF (INTERNALS) | PR-108 | Farabard | 2015-05-18 | 2015-06-22 09:27 |  | No | 35 | 2015-08-03 10:28 | [8 empty] | No | 0
VD-9001-108-PFD-065 | 1 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2015-05-19 | 2015-10-31 11:50 |  | No | 165 | 2015-11-16 16:54 | [8 empty] | No | 0
VD-9001-108-DSH-009 | 1 | GEAR REDUCER DATA SHEET | PR-108 | Farabard | 2015-05-19 | 2015-07-04 09:34 |  | No | 46 |  | 2015-07-13 15:20 | [7 empty] | No | 0
VD-9001-257A-CAL-005 | 1 | Strength Calculation Book E-3004 | HM-257A | ABAN AIR COOLER. | 2015-05-23 | 2015-05-12 15:25 | 2015-05-12 16:58 | Yes | -11 |  | 2015-06-07 16:43 | [6 empty] | 2015-06-07 16:44 | Yes | 12
VD-9001-257A-DWG-005 | 1 | General Arrangment Drawing E-3004 | HM-257A | ABAN AIR COOLER. | 2015-05-23 | 2015-05-12 14:21 | 2015-05-12 16:57 | Yes | -11 |  | 2015-06-07 16:39 | [6 empty] | 2015-06-07 16:40 | Yes | 12
VD-9001-108-DWG-019 | 1 | FOUNDATION DETAIL | PR-108 | Farabard | 2015-05-26 | 2015-05-13 11:16 |  | No | -13 | 2015-05-13 16:25 | [8 empty] | No | 0
VD-9001-254-MNL-100 | 0 | INSTRUCTION MANUAL FOR SOOT BLOWER | HM-254 | AZAR AB | 2016-01-25 |  |  | No | 1607 | [9 empty] | No | 0
VD-9001-254-INR-101 | 0 | TEST & INSPECTION MANUAL FOR SOOT BLOWER | HM-254 | AZAR AB | 2016-01-24 |  |  | No | 1608 | [9 empty] | No | 0
VD-9001-254-MNL-102 | 0 | INSTRUCTION & OPERATION MANUAL FOR BURNER | HM-254 | AZAR AB | 2016-03-09 |  |  | No | 1563 | [9 empty] | No | 0
VD-9001-254-MNL-103 | 0 | INSTRUCTION MANUAL FOR SAMPLING EQUIPMENT | HM-254 | AZAR AB | 2016-02-28 |  |  | No | 1573 | [9 empty] | No | 0
VD-9001-254-LST-104 | 0 | 2 years spare part list | HM-254 | AZAR AB | 2016-04-04 |  |  | No | 1537 | [9 empty] | No | 0
VD-9001-254-LST-105 | 0 | Spare part list for pre-commissioning ,commissioning and start-up | HM-254 | AZAR AB | 2016-04-04 |  |  | No | 1537 | [9 empty] | No | 0
VD-9001-254-LST-106 | 0 | UTILITY LIST | HM-254 | AZAR AB | 2016-04-03 | 2015-06-01 13:48 |  | No | -307 | 2015-06-17 15:17 | [8 empty] | No | 0
VD-9001-254-SPE-109 | 0 | TERMINAL POINT SPECIFICATION | HM-254 | AZAR AB | 2015-04-11 | 2015-05-17 12:34 |  | No | 36 | 2015-06-08 17:44 | [8 empty] | No | 0
VD-9001-254-EQL-110 | 0 | MAIN EQUIPMENT LIST | HM-254 | AZAR AB | 2015-07-18 | 2015-08-01 15:22 |  | No | 14 | 2015-10-18 15:47 | [8 empty] | No | 0
VD-9001-254-PFD-111 | 0 | PROCESS FLOW DIAGRAM (PFD) | HM-254 | AZAR AB | 2015-06-06 | 2015-06-01 13:50 |  | No | -5 | 2015-06-09 11:30 | [8 empty] | No | 0
VD-9001-254-LST-112 | 0 | SET POINT LIST FOR BOILER PLANT | HM-254 | AZAR AB | 2015-07-19 | 2019-10-21 15:02 | 2019-10-21 15:02 | Yes | 1555 |  |  |  | 2019-12-22 15:26 |  |  |  |  | 2019-12-22 15:26 | Yes | 48 | 1204-Owner-v | 2019-10-30 13:06
VD-9001-254-LST-113 | 0 | EFFELUENT LIST | HM-254 | AZAR AB | 2015-07-25 | 2015-12-27 07:48 |  | No | 155 | 2016-02-08 09:49 | [7 empty] | 2016-02-08 20:02 | Yes | 0
VD-9001-254-PID-114 | 0 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2015-04-27 | 2015-06-16 16:28 |  | No | 50 | 2015-08-05 14:19 | [8 empty] | No | 0 | 1204-Owner-v | 2018-01-25 11:22
VD-9001-254-PID-115 | 0 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2015-04-25 | 2015-06-16 16:29 |  | No | 52 | 2015-08-05 14:20 | [8 empty] | No | 0
VD-9001-254-PID-116 | 0 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2015-05-19 | 2015-06-16 16:30 |  | No | 28 | 2015-08-05 14:20 | [8 empty] | No | 0
VD-9001-254-PID-117 | 0 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2015-05-10 | 2015-06-16 16:31 |  | No | 37 | 2015-08-05 14:21 | [8 empty] | No | 0
VD-9001-254-PID-118 | 0 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2015-07-01 | 2015-06-16 16:31 |  | No | -15 | 2015-08-05 14:21 | [8 empty] | No | 0
VD-9001-254-PID-119 | 0 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2015-06-17 | 2015-09-27 09:17 |  | No | 102 | 2015-10-18 17:46 | [8 empty] | No | 0
VD-9001-254-PID-120 | 0 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2015-06-14 | 2015-06-16 16:32 |  | No | 2 | 2015-08-05 14:22 | [8 empty] | No | 0
VD-9001-254-PID-121 | 0 | STEAM TURBINE P&I DIAGRAM | HM-254 | AZAR AB | 2015-04-28 | 2015-09-27 09:17 |  | No | 152 | 2015-10-18 17:47 | [8 empty] | No | 0
VD-9001-254-LGD-122 | 0 | P&I DIAGRAM SYMBOLS & LEGENDS | HM-254 | AZAR AB | 2015-04-12 | 2015-06-16 16:35 |  | No | 65 |  | 2015-08-08 11:40 | [7 empty] | No | 0
VD-9001-254-MNL-123 | 0 | INSTRUCTION MANUAL OF PACKAGE BOILER | HM-254 | AZAR AB | 2015-11-22 | 2018-02-21 08:28 | 2018-02-21 08:29 | Yes | 822 |  |  | 2018-04-07 10:30 | [5 empty] | 2018-04-07 10:30 | Yes | 31 | 1204-Owner-v | 2018-04-17 15:26
VD-9001-254-PDS-124 | 0 | SYSTEM DESCRIPTION OF BOILER UNIT | HM-254 | AZAR AB | 2015-06-17 | 2016-06-14 17:10 | 2016-06-14 17:11 | Yes | 363 |  | 2016-07-09 09:54 | [6 empty] | 2016-07-09 19:58 | Yes | 11 | 1204-Owner-v | 2018-05-09 08:11
VD-9001-254-LST-125 | 0 | LUBRICANT & CHEMICAL DATA | HM-254 | AZAR AB | 2015-08-31 |  |  | No | 1754 | [9 empty] | No | 0
VD-9001-254-PCJ-126 | 0 | WATER FLUSHING PROCEDURE | HM-254 | AZAR AB | 2015-08-03 | 2017-08-22 08:02 | 2017-08-22 08:03 | Yes | 750 |  | 2017-09-03 16:00 | [6 empty] | 2017-09-03 19:57 | Yes | -2
VD-9001-254-PCJ-127 | 0 | CHEMICAL CLEANING PROCEDURE | HM-254 | AZAR AB | 2015-08-03 | 2017-08-22 08:02 |  | No | 750 | 2017-09-03 16:07 | [7 empty] | 2017-09-03 19:57 | Yes | 0
VD-9001-254-PCJ-128 | 0 | DRYING OUT PROCEDURE | HM-254 | AZAR AB | 2015-07-26 | 2017-08-22 08:02 |  | No | 758 | 2017-08-26 14:55 | [7 empty] | 2017-08-26 19:58 | Yes | 0
VD-9001-254-PCJ-129 | 0 | STEAM FLUSHING PROCEDURE | HM-254 | AZAR AB | 2015-08-24 | 2017-09-06 07:31 | 2017-09-06 07:32 | Yes | 744 |  | 2017-10-08 09:50 | [6 empty] | 2017-10-08 20:00 | Yes | 18
VD-9001-254-PCJ-130 | 0 | SAFETY VALVE SETING PROCEDURE | HM-254 | AZAR AB | 2015-08-15 | 2017-08-22 08:03 |  | No | 738 | 2017-10-07 17:22 | [7 empty] | 2017-10-07 20:00 | Yes | 0
VD-9001-254-PCJ-131 | 0 | START UP & SHUT DOWN PROCEDURE | HM-254 | AZAR AB | 2015-08-24 | 2017-09-24 13:31 | 2017-09-24 13:32 | Yes | 762 |  | 2017-10-16 09:17 | [6 empty] | 2017-10-16 19:59 | Yes | 8
VD-9001-254-PCJ-132 | 0 | TAKING THE BOILER OUT OF SERVICE PROCEDURE | HM-254 | AZAR AB | 2015-08-12 | 2017-09-04 08:20 |  | No | 754 | 2017-10-08 09:45 | [7 empty] | 2017-10-08 20:00 | Yes | 0
VD-9001-254-DSH-133 | 0 | DATA SHEET FOR SOOT BLOWER | HM-254 | AZAR AB | 2015-07-05 | 2015-10-18 09:48 |  | No | 105 | 2015-12-15 17:25 | [8 empty] | No | 0 | 1204-Owner-v | 2018-12-04 15:45
VD-9001-254-DSH-134 | 0 | DATA SHEET FOR BURNER | HM-254 | AZAR AB | 2015-06-24 | 2015-08-12 14:08 |  | No | 49 | 2015-10-06 14:33 | [8 empty] | No | 0 | 1204-Owner-v | 2018-02-27 12:21
VD-9001-254-DSH-135 | 0 | DATA SHEET FOR SAMPLING EQUIPMENT | HM-254 | AZAR AB | 2015-06-22 | 2015-08-09 08:06 |  | No | 48 | 2015-10-06 12:22 | [8 empty] | No | 0
VD-9001-254-LST-136 | 0 | SPECIAL TOOLS LIST FOR MAIN AUX. EQUIPMENT | HM-254 | AZAR AB | 2015-07-01 |  |  | No | 1815 | [9 empty] | No | 0
VD-9001-254-INR-137 | 0 | TEST & INSPECTION MANUAL FOR BURNER | HM-254 | AZAR AB | 2016-03-07 |  |  | No | 1565 | [9 empty] | No | 0
VD-9001-254-INR-138 | 0 | TEST & INSPECTION MANUAL FOR SAMPLING EQUIPMENT | HM-254 | AZAR AB | 2016-02-15 |  |  | No | 1586 | [9 empty] | No | 0
VD-9001-254-DSH-150 | 0 | DATA SHEET FOR STEAM TURBINE OF F.D. FAN | HM-254 | AZAR AB | 2015-06-09 | 2015-08-30 13:53 |  | No | 82 | 2015-11-01 11:08 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-10 11:42
VD-9001-254-DSH-151 | 0 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2015-05-19 | 2015-08-09 08:06 |  | No | 82 | 2015-11-01 11:13 | [8 empty] | No | 0
VD-9001-254-MNL-152 | 0 | INSTRUCTION MANUAL FOR F.D.FAN | HM-254 | AZAR AB | 2016-02-09 |  |  | No | 1592 | [9 empty] | No | 0
VD-9001-254-MNL-153 | 0 | INSTRUCTION MANUAL FOR STEAM TURBINE OF F.D.FAN | HM-254 | AZAR AB | 2016-03-16 |  |  | No | 1556 | [9 empty] | No | 0
VD-9001-254-INR-154 | 0 | TEST & INSPECTION MANUAL FOR F.D.FAN | HM-254 | AZAR AB | 2016-02-08 | 2020-05-06 15:04 | 2020-05-06 15:05 | Yes | 1549 |  |  |  | 2020-05-19 15:53 |  |  |  |  | 2020-05-19 15:53 | Yes | -1
VD-9001-254-INR-155 | 0 | TEST & INSPECTION MANUAL FOR STEAM TURBINE OF F.D.FAN | HM-254 | AZAR AB | 2016-03-13 |  |  | No | 1559 | [9 empty] | No | 0
VD-9001-254-SPE-200 | 0 | OUTLINE DRAWING & SPECIFICATION OF F.D.F MOTOR | HM-254 | AZAR AB | 2016-01-26 | 2018-12-30 10:26 | 2018-12-30 10:26 | Yes | 1069 |  |  |  | 2019-02-05 15:25 |  |  |  |  | 2019-02-05 15:25 | Yes | 23
VD-9001-254-SPE-201 | 0 | OUTLINE DRAWING & SPECIFICATION FOR LIGHTING FIXTURES & SOCKETS | HM-254 | AZAR AB | 2015-12-26 |  |  | No | 1637 | [9 empty] | No | 0
VD-9001-254-SPE-202 | 0 | DRAWING & SPECIFICTION OF AIRCRAFT WARNING LIGHTS | HM-254 | AZAR AB | 2016-02-21 |  |  | No | 1580 | [9 empty] | No | 0
VD-9001-254-SPE-203 | 0 | SPECIFICATION FOR CABLES & WIRES | HM-254 | AZAR AB | 2015-12-01 |  |  | No | 1662 | [9 empty] | No | 0
VD-9001-254-SPE-204 | 0 | OUTLINE DRWING & SPECIFICATION FOR CABLE TRAY & ACCESSORIES | HM-254 | AZAR AB | 2016-01-05 |  |  | No | 1627 | [9 empty] | No | 0
VD-9001-254-SPE-205 | 0 | OUTLINE DRWING & SPECIFICATION FOR CABLE GLANDS | HM-254 | AZAR AB | 2016-01-16 |  |  | No | 1616 | [9 empty] | No | 0
VD-9001-254-SPE-206 | 0 | OUTLINE DRAWING & SPECIFICATION FOR EARTHING MATERIALS & LIGHTING ROD | HM-254 | AZAR AB | 2015-10-27 |  |  | No | 1697 | [9 empty] | No | 0
VD-9001-254-DIG-207 | 0 | LAYOUT & WIRING DIAGRAM FOR DISTRIBUTION PANELS | HM-254 | AZAR AB | 2016-02-07 |  |  | No | 1594 | [9 empty] | No | 0
VD-9001-254-SPE-208 | 0 | OUTLINE DRAWING & SPECIFICATION & INST. MANUAL FOR DISTRIBUTION PANELS | HM-254 | AZAR AB | 2016-02-06 |  |  | No | 1595 | [9 empty] | No | 0
VD-9001-254-SPE-209 | 0 | OUTLINE DRAWING & SPECIFICATION FOR JUNCTION BOXES AND LOCAL CONTROL STATION | HM-254 | AZAR AB | 2016-01-27 |  |  | No | 1605 | [9 empty] | No | 0
VD-9001-254-SLD-210 | 0 | SINGLE LINE DIAGRAM | HM-254 | AZAR AB | 2015-06-29 | 2015-07-25 07:25 |  | No | 26 | 2015-08-22 10:48 | [8 empty] | No | 0
VD-9001-254-DWG-211 | 0 | CABLE TRAY LAYOUT | HM-254 | AZAR AB | 2015-08-08 | 2016-03-01 07:53 |  | No | 206 | 2016-04-03 14:37 | [7 empty] | 2016-04-03 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-09 16:50
VD-9001-254-DWG-212 | 0 | EARTHING LAYOUT OF BOILER | HM-254 | AZAR AB | 2015-07-19 | 2015-08-17 14:28 | 2015-08-18 10:36 | Yes | 30 |  | 2015-09-16 12:15 | [6 empty] | 2015-09-16 12:16 | Yes | 16 | 1204-Owner-v | 2018-04-09 16:53
VD-9001-254-DWG-213 | 0 | LIGHTING LAYOUT OF BOILERS | HM-254 | AZAR AB | 2015-07-13 | 2015-09-02 16:10 |  | No | 51 | 2015-09-16 14:46 | [8 empty] | No | 0 | 1204-Owner-v | 2018-04-09 16:58
VD-9001-254-DWG-214 | 0 | EARTHING INSTALLATION DETAIL | HM-254 | AZAR AB | 2015-07-28 | 2015-08-17 14:28 | 2015-08-18 10:37 | Yes | 21 |  | 2015-09-16 12:16 | [6 empty] | 2015-09-16 12:17 | Yes | 16 | 1204-Owner-v | 2018-04-09 17:02
VD-9001-254-DWG-215 | 0 | CONNECTION & TERMINATION DWG | HM-254 | AZAR AB | 2016-04-02 | 2018-12-16 08:41 | 2018-12-16 08:41 | Yes | 988 |  |  |  | 2019-01-12 10:17 |  |  |  |  | 2019-01-12 10:17 | Yes | 13
VD-9001-254-LST-216 | 0 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2015-05-26 | 2015-07-25 07:25 |  | No | 60 | 2015-08-22 10:49 | [8 empty] | No | 0
VD-9001-254-LST-217 | 0 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2015-08-17 | 2015-10-11 10:07 |  | No | 55 | 2015-11-25 14:51 | [8 empty] | No | 0
VD-9001-254-DSH-218 | 0 | DATA SHEET FOR MOTORS FOR FORCED DRAFT FANS | HM-254 | AZAR AB | 2015-06-14 | 2015-08-01 13:57 |  | No | 48 | 2015-08-18 17:27 | [8 empty] | No | 0
VD-9001-254-DIG-300 | 0 | SYSTEM ARCITECTURE & INTERCONNECTION DIAGRAM FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2016-03-09 | 2017-08-13 14:08 |  | No | 522 | 2017-08-22 17:42 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-LST-301 | 0 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2016-03-09 | 2017-08-13 14:15 |  | No | 522 | 2017-08-22 16:37 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-LST-302 | 0 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2016-03-09 | 2017-08-13 14:16 |  | No | 522 | 2017-08-22 16:34 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-ITP-303 | 0 | INSPECTION & TEST PROCEDURES FOR INSTRUMENTS | HM-254 | AZAR AB | 2016-03-26 | 2018-08-26 10:51 | 2018-08-26 10:51 | Yes | 883 |  |  | 2018-10-22 11:30 | [5 empty] | 2018-10-22 11:30 | Yes | 43 | 1204-Owner-v | 2020-01-01 10:27
VD-9001-254-ITP-304 | 0 | CONTROL SYSTEM AND BMS FACTORY ACCEPTANCE TEST (FAT) REPORT | HM-254 | AZAR AB | 2016-03-02 |  |  | No | 1570 | [9 empty] | No | 0
VD-9001-254-CAT-305 | 0 | OUTLINE DRAWING & SPECIFICATION SHEETS FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE TRANSMITTERS | HM-254 | AZAR AB | 2016-02-27 |  |  | No | 1574 | [9 empty] | No | 0
VD-9001-254-MNL-306 | 0 | INSTRUCTION MANUAL FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE TRANSMITTERS | HM-254 | AZAR AB | 2016-02-27 |  |  | No | 1574 | [9 empty] | No | 0
VD-9001-254-CAT-307 | 0 | OUTLINE DRAWINGS & SPECIFICATION SHEETS FOR FLOW ELEMENTS | HM-254 | AZAR AB | 2016-01-19 |  |  | No | 1613 | [9 empty] | No | 0
VD-9001-254-CAT-308 | 0 | OUTLINE DRAWING & SPECIFICATION SHEETS FOR O2 GAS ANALYZERS | HM-254 | AZAR AB | 2015-12-23 | 2019-01-21 11:31 | 2019-01-21 11:35 | Yes | 1125 |  |  |  | 2019-02-13 15:22 |  |  |  |  | 2019-02-13 15:22 | Yes | 9 | 1204-Owner-v | 2019-12-17 11:31
VD-9001-254-CAT-309 | 0 | OUTLINE DRAWING & SPECIFICATION SHEETS FOR FLUE GAS ANALYZERS | HM-254 | AZAR AB | 2015-12-29 |  |  | No | 1634 | [9 empty] | No | 0
VD-9001-254-MNL-310 | 0 | INSTRUCTION MANUAL FOR O2 GAS ANALYZERS | HM-254 | AZAR AB | 2015-12-23 | 2019-01-21 11:25 | 2019-01-21 11:29 | Yes | 1125 |  |  |  | 2019-02-05 09:47 |  |  |  |  | 2019-02-05 09:47 | Yes | 1
VD-9001-254-MNL-311 | 0 | INSTRUCTION MANUAL FOR FLUE GAS ANALYZERS | HM-254 | AZAR AB | 2015-12-29 |  |  | No | 1634 | [9 empty] | No | 0
VD-9001-254-CAT-312 | 0 | OUTLINE DRAWING & SPECIFICATION SHEETS FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE GAUGES | HM-254 | AZAR AB | 2016-02-24 |  |  | No | 1577 | [9 empty] | No | 0
VD-9001-254-MNL-313 | 0 | INSTRUCTION MANUAL FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE GAUGES | HM-254 | AZAR AB | 2016-02-24 |  |  | No | 1577 | [9 empty] | No | 0
VD-9001-254-CAT-316 | 0 | OUTLINE DRAWING AND SPECIFICATION SHEETS FOR DRUM LEVEL GAUGES | HM-254 | AZAR AB | 2016-03-02 |  |  | No | 1570 | [9 empty] | No | 0
VD-9001-254-MNL-317 | 0 | INSTRUCTION MANUAL FOR DRUM LEVEL GAUGES | HM-254 | AZAR AB | 2016-02-29 |  |  | No | 1572 | [9 empty] | No | 0
VD-9001-254-PPL-318 | 0 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2016-04-02 | 2017-08-13 14:22 |  | No | 498 | 2017-08-22 16:21 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-PPL-319 | 0 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2016-04-02 | 2017-08-13 14:26 |  | No | 498 | 2017-08-22 16:15 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-DIG-320 | 0 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2016-03-12 | 2017-08-13 14:10 |  | No | 519 | 2017-08-22 17:44 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-PPL-321 | 0 | CONTROL AND PANEL ROOM LAYOUT/ARRANGEMENT | HM-254 | AZAR AB | 2016-03-05 |  |  | No | 1567 | [9 empty] | No | 0
VD-9001-254-MNL-322 | 0 | OPERATION MANUAL FOR OPERATER STATIONS | HM-254 | AZAR AB | 2016-03-01 | 2018-05-13 07:54 | 2018-05-13 07:54 | Yes | 803 |  |  |  | 2018-06-25 14:41 |  |  |  |  | 2018-06-25 14:41 | Yes | 29
VD-9001-254-MNL-323 | 0 | CONTROL SYSTEM & BMS SOFTWARE MANUAL | HM-254 | AZAR AB | 2016-03-01 | 2018-05-13 08:19 | 2018-05-13 08:25 | Yes | 803 |  |  | 2018-06-25 14:44 | [5 empty] | 2018-06-25 14:44 | Yes | 29 | 1204-Owner-v | 2019-07-10 13:43
VD-9001-254-MNL-324 | 0 | OPERATION MANUAL FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2016-03-02 | 2018-08-28 14:32 | 2018-08-28 14:32 | Yes | 909 |  |  | 2018-10-22 11:53 | [5 empty] | 2018-10-22 11:53 | Yes | 41 | 1204-Owner-v | 2018-11-26 13:49
VD-9001-254-MNL-325 | 0 | TECHNICAL SPECIFICATION FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2016-03-05 | 2017-08-13 14:19 |  | No | 526 | 2017-08-22 16:24 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-ITP-326 | 0 | CONTROL SYSTEM AND BMS SITE ACCEPTANCE TEST (SAT) PROCEDURE | HM-254 | AZAR AB | 2016-03-01 | 2017-08-21 10:27 |  | No | 538 | 2017-10-03 16:23 | [7 empty] | 2017-10-03 20:01 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-254-ITP-327 | 0 | CONTROL SYSTEM AND BMS FACTORY ACCEPTANCE TEST (FAT) PROCEDURE | HM-254 | AZAR AB | 2016-03-01 | 2017-08-21 10:31 |  | No | 538 | 2017-10-03 14:35 | [7 empty] | 2017-10-03 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-254-LST-328 | 0 | CONTROL SYSTEM PROGRAM LIST | HM-254 | AZAR AB | 2016-02-29 | 2017-09-11 16:13 |  | No | 560 | 2017-10-03 16:29 | [7 empty] | 2017-10-03 20:01 | Yes | 0
VD-9001-254-LST-329 | 0 | BMS PROGRAM LIST | HM-254 | AZAR AB | 2016-02-29 | 2017-09-16 10:07 |  | No | 565 | 2017-10-03 16:34 | [7 empty] | 2017-10-03 20:01 | Yes | 0
VD-9001-254-DWG-330 | 0 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2016-03-12 | 2017-08-13 14:12 |  | No | 519 | 2017-08-28 16:32 | [7 empty] | 2017-08-28 19:57 | Yes | 0
VD-9001-254-SPE-331 | 0 | TECHNICAL SPECIFICATIONS FOR LBSP | HM-254 | AZAR AB | 2016-03-01 | 2018-08-07 09:09 | 2018-08-07 09:09 | Yes | 889 |  |  |  | 2018-10-01 15:03 |  |  |  |  | 2018-10-01 15:03 | Yes | 41
VD-9001-254-MNL-332 | 0 | INSTRUCTION MANUAL FOR LBSP | HM-254 | AZAR AB | 2016-03-01 |  |  | No | 1571 | [9 empty] | No | 0
VD-9001-254-DIG-333 | 0 | CONTROL SYSTEM & BMS LOOP DIAGRAM | HM-254 | AZAR AB | 2016-03-05 | 2018-11-05 14:22 | 2018-11-05 14:22 | Yes | 975 |  |  |  | 2018-12-08 09:25 |  |  |  |  | 2018-12-08 09:25 | Yes | 19
VD-9001-254-LST-334 | 0 | SPARE PART LIST FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2016-03-01 | 2017-08-21 10:36 |  | No | 538 | 2017-08-29 11:12 | [7 empty] | 2017-08-29 19:57 | Yes | 0
VD-9001-254-LST-335 | 0 | SPARE PART LIST FOR INSTRUMENTS | HM-254 | AZAR AB | 2016-03-09 |  |  | No | 1563 | [9 empty] | No | 0
VD-9001-254-DIG-336 | 0 | BMS LOGIC DIAGRAM | HM-254 | AZAR AB | 2015-10-12 | 2016-12-19 14:25 |  | No | 434 | 2017-02-04 11:33 | [7 empty] | 2017-02-04 19:59 | Yes | 0
VD-9001-254-PDS-337 | 0 | FUNCTION OF BMS | HM-254 | AZAR AB | 2015-11-04 | 2016-12-19 14:25 |  | No | 411 | 2017-03-26 14:53 | [7 empty] | 2017-03-26 21:00 | Yes | 0 | 1204-Owner-v | 2020-01-14 09:47
VD-9001-254-DIG-338 | 0 | CAUSE AND EFFECT DIAGRAM | HM-254 | AZAR AB | 2015-09-07 | 2015-09-26 08:19 |  | No | 19 | 2015-10-20 16:03 | [8 empty] | No | 0
VD-9001-254-DIG-339 | 0 | ABC & SUPERVISORY FLOW DIAGRAMS | HM-254 | AZAR AB | 2015-08-25 | 2016-05-04 14:34 |  | No | 253 | 2016-06-13 16:10 | [7 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-254-LST-340 | 0 | BMS I/O LIST | HM-254 | AZAR AB | 2015-07-14 | 2015-08-09 08:09 |  | No | 26 | 2015-08-19 10:36 | [8 empty] | No | 0
VD-9001-254-PDS-341 | 0 | FUNCTION OF ABC | HM-254 | AZAR AB | 2015-11-15 | 2015-10-31 17:04 |  | No | -15 | 2015-12-15 14:41 | [8 empty] | No | 0
VD-9001-254-LST-342 | 0 | CONTROL SYSTEM I/O LIST | HM-254 | AZAR AB | 2015-07-22 | 2015-08-09 08:09 |  | No | 18 | 2015-08-19 10:36 | [8 empty] | No | 0
VD-9001-254-LGD-343 | 0 | COLOR CODING FOR GRAPHIC SYMBOLE | HM-254 | AZAR AB | 2015-05-09 | 2015-05-31 07:32 |  | No | 22 | 2015-09-02 15:20 | [8 empty] | No | 0
VD-9001-254-PDS-344 | 0 | FUNCTION , CHARACTERISTIC CURVES & SETTINGS FOR ABC | HM-254 | AZAR AB | 2015-11-18 | 2016-09-11 10:44 |  | No | 298 | 2016-11-07 14:51 | [7 empty] | 2016-11-07 19:59 | Yes | 0 | 1204-Owner-v | 2019-12-09 08:33
VD-9001-254-DPH-345 | 0 | CONTROL SYSTEM ARCHITECTURE | HM-254 | AZAR AB | 2015-04-29 | 2015-05-17 08:56 |  | No | 18 | 2015-09-02 11:00 | [8 empty] | No | 0
VD-9001-254-LST-346 | 0 | INSTRUMENT LIST | HM-254 | AZAR AB | 2015-11-01 | 2016-01-02 13:27 |  | No | 62 | 2016-02-08 09:51 | [7 empty] | 2016-02-08 20:02 | Yes | 0
VD-9001-254-DWG-347 | 0 | INSTALLATION DRAWINGS & PROCEDURES FOR INSTRUMENTS | HM-254 | AZAR AB | 2015-08-08 | 2015-08-23 09:25 |  | No | 15 | 2015-11-01 11:17 | [8 empty] | No | 0
VD-9001-254-PPL-348 | 0 | INSTRUMENTATION LOCATION LAYOUT | HM-254 | AZAR AB | 2015-09-07 | 2019-05-07 15:51 | 2019-05-07 15:51 | Yes | 1338 |  |  |  | 2019-06-01 09:47 |  |  |  |  | 2019-06-01 09:47 | Yes | 11 | 1204-Owner-v | 2019-05-23 08:32
VD-9001-254-DSH-349 | 0 | DATA SHEET FOR FLAME DETECTOR | HM-254 | AZAR AB | 2015-08-29 | 2015-09-26 08:20 |  | No | 28 | 2015-12-28 14:11 | [7 empty] | 2015-12-28 20:03 | Yes | 0
VD-9001-254-DSH-350 | 0 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE TRANSMITTERS | HM-254 | AZAR AB | 2015-08-22 | 2015-09-06 08:54 |  | No | 15 | 2015-11-25 11:20 | [8 empty] | No | 0
VD-9001-254-DSH-351 | 0 | DATA SHEET FOR FLOW ELEMENTS | HM-254 | AZAR AB | 2015-06-16 | 2015-08-05 14:28 |  | No | 50 | 2015-09-20 11:00 | [8 empty] | No | 0
VD-9001-254-DSH-352 | 0 | DATA SHEET FOR O2 GAS ANALYZER | HM-254 | AZAR AB | 2015-06-07 | 2015-06-29 12:17 |  | No | 22 | 2015-10-21 16:12 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-28 11:59
VD-9001-254-DSH-353 | 0 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE GAUGES | HM-254 | AZAR AB | 2015-10-21 | 2015-11-21 07:12 |  | No | 31 | 2015-12-23 17:50 | [7 empty] | 2015-12-23 20:03 | Yes | 0
VD-9001-254-DSH-355 | 0 | DATA SHEET FOR DRUM LEVEL GAUGES | HM-254 | AZAR AB | 2015-09-02 | 2015-10-05 08:30 |  | No | 33 | 2015-11-25 14:46 | [8 empty] | No | 0
VD-9001-254-DSH-356 | 0 | DATA SHEET FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2015-08-04 | 2015-08-19 06:53 |  | No | 15 | 2015-10-20 15:47 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-28 12:14
VD-9001-254-DSH-357 | 0 | DATA SHEET FOR FLUE GAS ANALYZERS | HM-254 | AZAR AB | 2015-06-09 | 2015-06-29 12:17 |  | No | 20 | 2015-10-25 10:01 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-28 12:14
VD-9001-254-PPL-358 | 0 | LAYOUT & TYPICAL WIRING FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2015-05-13 | 2015-06-07 07:50 |  | No | 25 | 2015-08-19 10:29 | [8 empty] | No | 0
VD-9001-254-PPL-359 | 0 | LAYOUT & TYPICAL WIRING FOR BMS | HM-254 | AZAR AB | 2015-05-11 | 2015-06-07 07:52 |  | No | 27 | 2015-09-08 10:24 | [8 empty] | No | 0
VD-9001-254-PPL-360 | 0 | LAYOUT & TYPICAL WIRING FOR LBSP | HM-254 | AZAR AB | 2015-05-03 | 2015-06-07 07:52 |  | No | 35 | 2015-09-08 10:25 | [8 empty] | No | 0
VD-9001-254-CER-361 | 0 | TEST CERTIFICATES FOR INSTRUMENTS | HM-254 | AZAR AB | 2016-03-16 |  |  | No | 1556 | [9 empty] | No | 0
VD-9001-254-LST-362 | 0 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2015-11-24 | 2017-08-13 14:18 |  | No | 628 | 2017-08-22 16:30 | [7 empty] | 2017-08-22 19:58 | Yes | 0
VD-9001-254-LST-363 | 0 | MODBUS LIST | HM-254 | AZAR AB | 2015-11-24 | 2017-09-11 16:15 |  | No | 657 | 2017-10-03 16:31 | [7 empty] | 2017-10-03 20:01 | Yes | 0
VD-9001-254-DWG-400 | 0 | ASS. DWG. OF STEAM DRUM 1/3 (TUBE HOLE ARRANGMENT) | HM-254 | AZAR AB | 2015-05-19 | 2015-06-09 15:16 |  | No | 21 | 2015-08-03 16:59 | [8 empty] | No | 0
VD-9001-254-DWG-401 | 0 | ASS. DWG. OF STEAM DRUM 2/3 | HM-254 | AZAR AB | 2015-05-18 | 2015-06-09 15:25 |  | No | 22 | 2015-08-03 17:00 | [8 empty] | No | 0
VD-9001-254-DWG-402 | 0 | ASS. & FAB. DWG. OF STEAM DRUM 3/3 | HM-254 | AZAR AB | 2015-05-18 | 2015-06-09 15:26 |  | No | 22 | 2015-08-03 17:00 | [8 empty] | No | 0
VD-9001-254-DWG-403 | 0 | ASS. DWG. FOR S/D INTERNALS | HM-254 | AZAR AB | 2015-05-30 | 2015-06-09 15:26 | 2015-06-09 17:38 | Yes | 10 |  | 2015-08-03 17:03 | [6 empty] | 2015-08-03 17:04 | Yes | 41
VD-9001-254-DWG-404 | 0 | ASSEMBLY DWG. FOR W/D 1/2 | HM-254 | AZAR AB | 2015-05-26 | 2015-06-09 15:36 |  | No | 14 | 2015-08-03 17:03 | [8 empty] | No | 0
VD-9001-254-DWG-405 | 0 | ASSEMBLY DWG. FOR W/D 2/2 | HM-254 | AZAR AB | 2015-06-02 | 2015-06-09 15:37 |  | No | 7 | 2015-08-03 17:04 | [8 empty] | No | 0
VD-9001-254-DWG-406 | 0 | ASSEMBLY DWG FOR FRONT WALL HEADERS | HM-254 | AZAR AB | 2015-06-08 | 2015-07-01 08:51 | 2015-07-01 11:35 | Yes | 23 |  | 2015-08-23 15:47 | [6 empty] | 2015-08-23 15:48 | Yes | 39
VD-9001-254-DWG-407 | 0 | ASSEMBLY DWG FOR SADDLE OF FRONT WALL HDR | HM-254 | AZAR AB | 2015-06-14 | 2015-07-01 08:52 | 2015-07-01 11:36 | Yes | 17 |  | 2015-08-23 15:48 | [6 empty] | 2015-08-23 15:49 | Yes | 39
VD-9001-254-DWG-408 | 0 | ASSEMBLY DWG FOR REAR WALL HDR | HM-254 | AZAR AB | 2015-06-17 | 2015-07-01 08:53 | 2015-07-01 11:42 | Yes | 14 |  | 2015-08-23 15:48 | [6 empty] | 2015-08-23 15:49 | Yes | 39
VD-9001-254-DWG-409 | 0 | ASSEMBLY DWG FOR SADDLE OF REAR WALL HDR | HM-254 | AZAR AB | 2015-06-23 | 2015-07-01 08:54 | 2015-07-01 11:42 | Yes | 8 |  | 2015-08-23 15:49 | [6 empty] | 2015-08-23 15:50 | Yes | 39
VD-9001-254-DWG-410 | 0 | ASSEMBLY DWG FOR S.H HDR 1/2 | HM-254 | AZAR AB | 2015-06-29 | 2015-07-05 13:57 |  | No | 6 |  | 2015-08-23 15:54 | [7 empty] | No | 0
VD-9001-254-DWG-411 | 0 | ASSEMBLY DWG FOR S.H HDR 2/2 | HM-254 | AZAR AB | 2015-06-29 | 2015-07-05 13:58 | 2015-07-05 17:56 | Yes | 6 |  | 2015-08-23 15:55 | [6 empty] | 2015-08-23 15:56 | Yes | 35
VD-9001-254-DWG-412 | 0 | ASS. DWG. FOR ECO. HEADER | HM-254 | AZAR AB | 2015-07-05 | 2015-09-06 08:21 | 2015-09-06 14:17 | Yes | 63 |  | 2015-11-01 10:57 | [6 empty] | 2015-11-01 10:58 | Yes | 42 | 1204-Owner-v | 2019-01-22 17:24
VD-9001-254-DWG-413 | 0 | ASS. DWG. FOR FUR. FRONT WALL 1/3 | HM-254 | AZAR AB | 2015-05-25 | 2015-05-21 08:55 | 2015-05-21 10:54 | Yes | -4 |  | 2015-10-07 10:30 | [6 empty] | 2015-10-07 10:31 | Yes | 125 | 1204-Owner-v | 2019-02-16 10:51
VD-9001-254-DWG-414 | 0 | ASS. DWG. FOR FUR. FRONT WALL 2/3 | HM-254 | AZAR AB | 2015-05-25 | 2015-05-21 08:52 | 2015-05-21 10:58 | Yes | -4 |  | 2015-10-07 10:31 | [6 empty] | 2015-10-07 10:32 | Yes | 125 | 1204-Owner-v | 2019-02-16 10:51
VD-9001-254-DWG-415 | 0 | ASS. DWG. FOR FUR. FRONT WALL 3/3 | HM-254 | AZAR AB | 2015-05-25 | 2015-05-21 08:50 | 2015-05-21 10:59 | Yes | -4 |  | 2015-10-07 10:32 | [6 empty] | 2015-10-07 10:33 | Yes | 125 | 1204-Owner-v | 2019-02-16 10:49
VD-9001-254-DWG-416 | 0 | ASS. DWG. FOR FUR. REAR WALL 1/4 | HM-254 | AZAR AB | 2015-05-25 | 2015-05-21 08:44 | 2015-05-21 11:00 | Yes | -4 |  | 2015-07-01 10:10 | [6 empty] | 2015-07-01 10:11 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:50
VD-9001-254-DWG-417 | 0 | ASS. DWG. FOR FUR. REAR WALL 2/4 | HM-254 | AZAR AB | 2015-06-01 | 2015-05-21 08:34 | 2015-05-21 11:01 | Yes | -11 |  | 2015-07-01 10:10 | [6 empty] | 2015-07-01 10:11 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:50
VD-9001-254-DWG-418 | 0 | ASS. DWG. FOR FUR. REAR WALL 3/4 | HM-254 | AZAR AB | 2015-06-01 | 2015-05-21 08:31 | 2015-05-21 11:02 | Yes | -11 |  | 2015-07-01 10:11 | [6 empty] | 2015-07-01 10:12 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:50
VD-9001-254-DWG-419 | 0 | ASS. DWG. FOR FUR. REAR WALL 4/4 | HM-254 | AZAR AB | 2015-06-01 | 2015-05-21 08:29 | 2015-05-21 11:04 | Yes | -11 |  | 2015-07-01 10:11 | [6 empty] | 2015-07-01 10:12 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:50
VD-9001-254-DWG-420 | 0 | ASS. DWG. FOR FUR. SIDE WALL 1/4 | HM-254 | AZAR AB | 2015-06-08 | 2015-05-21 08:24 | 2015-05-21 11:05 | Yes | -18 |  | 2015-07-01 10:12 | [6 empty] | 2015-07-01 10:13 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:49
VD-9001-254-DWG-421 | 0 | ASS. DWG. FOR FUR. SIDE WALL 2/4 | HM-254 | AZAR AB | 2015-06-08 | 2015-05-21 08:22 | 2015-05-21 11:07 | Yes | -18 |  | 2015-07-01 10:12 | [6 empty] | 2015-07-01 10:13 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:44
VD-9001-254-DWG-422 | 0 | ASS. DWG. FOR FUR. SIDE WALL 3/4 | HM-254 | AZAR AB | 2015-06-08 | 2015-05-21 08:19 | 2015-05-21 11:08 | Yes | -18 |  | 2015-07-01 10:12 | [6 empty] | 2015-07-01 10:13 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:49
VD-9001-254-DWG-423 | 0 | ASS. DWG. FOR FUR. SIDE WALL 4/4 | HM-254 | AZAR AB | 2015-06-08 | 2015-05-21 08:16 | 2015-05-21 11:09 | Yes | -18 |  | 2015-07-01 10:13 | [6 empty] | 2015-07-01 10:14 | Yes | 27 | 1204-Owner-v | 2019-02-16 10:50
VD-9001-254-DWG-424 | 0 | ASS. DWG. FOR SCREEN & BAFFLE TUBE 1/2 | HM-254 | AZAR AB | 2015-07-13 | 2015-06-22 14:53 | 2015-06-23 10:10 | Yes | -20 |  | 2015-07-15 14:59 | [6 empty] | 2015-07-15 15:00 | Yes | 9
VD-9001-254-DWG-425 | 0 | ASS. DWG. FOR SCREEN & BAFFLE TUBE 2/2 | HM-254 | AZAR AB | 2015-07-13 | 2015-06-22 14:53 | 2015-06-23 10:11 | Yes | -20 |  | 2015-07-15 14:59 | [6 empty] | 2015-07-15 15:00 | Yes | 9
VD-9001-254-DWG-426 | 0 | ARRANGEMENT DWG. FOR BANK TUBE | HM-254 | AZAR AB | 2015-06-15 | 2015-05-21 08:12 | 2015-05-21 11:10 | Yes | -25 |  | 2015-07-01 10:13 | [6 empty] | 2015-07-01 10:14 | Yes | 27 | 1204-Owner-v | 2018-09-09 10:24
VD-9001-254-DWG-427 | 0 | ASSEMBLY DWG. FOR BANK TUBE FRONT WALL TUBE 1/3 | HM-254 | AZAR AB | 2015-06-22 | 2015-05-23 16:00 |  | No | -30 |  | 2015-10-06 16:21 | [7 empty] | No | 0
VD-9001-254-DWG-428 | 0 | ASSEMBLY DWG. FOR BANK TUBE FRONT WALL TUBE 2/3 | HM-254 | AZAR AB | 2015-06-22 | 2015-05-23 16:06 | 2015-05-23 17:29 | Yes | -30 |  | 2015-10-06 16:21 | [6 empty] | 2015-10-06 16:22 | Yes | 122 | 1204-Owner-v | 2019-02-16 10:55
VD-9001-254-DWG-429 | 0 | ASSEMBLY DWG. FOR BANK TUBE FRONT WALL TUBE 3/3 | HM-254 | AZAR AB | 2015-06-22 | 2015-05-23 16:09 | 2015-05-23 17:30 | Yes | -30 |  | 2015-10-06 16:22 | [6 empty] | 2015-10-06 16:23 | Yes | 122 | 1204-Owner-v | 2019-02-16 10:53
VD-9001-254-DWG-430 | 0 | ASSEMBLY DWG. FOR BANK REAR WALL TUBE 1/3 | HM-254 | AZAR AB | 2015-06-29 | 2015-05-23 16:18 | 2015-05-23 17:31 | Yes | -37 |  | 2015-10-06 16:26 | [6 empty] | 2015-10-06 16:27 | Yes | 122 | 1204-Owner-v | 2019-02-16 10:56
VD-9001-254-DWG-431 | 0 | ASSEMBLY DWG. FOR BANK REAR WALL TUBE 2/3 | HM-254 | AZAR AB | 2015-06-29 | 2015-05-23 16:21 | 2015-05-23 17:32 | Yes | -37 |  | 2015-10-06 16:27 | [6 empty] | 2015-10-06 16:28 | Yes | 122 | 1204-Owner-v | 2019-02-16 10:54
VD-9001-254-DWG-432 | 0 | ASSEMBLY DWG. FOR BANK REAR WALL TUBE 3/3 | HM-254 | AZAR AB | 2015-06-29 | 2015-05-23 16:22 | 2015-05-23 17:32 | Yes | -37 |  | 2015-10-06 16:27 | [6 empty] | 2015-10-06 16:28 | Yes | 122 | 1204-Owner-v | 2019-02-16 10:55
VD-9001-254-DWG-433 | 0 | ASSEMBLY DWG. FOR BANK SIDE WALL TUBE 1/3 | HM-254 | AZAR AB | 2015-07-06 | 2015-07-01 08:55 | 2015-07-01 11:44 | Yes | -5 |  | 2015-07-15 17:21 | [6 empty] | 2015-07-15 17:22 | Yes | 0 | 1204-Owner-v | 2019-02-16 10:54
VD-9001-254-DWG-434 | 0 | ASSEMBLY DWG. FOR BANK SIDE WALL TUBE 2/3 | HM-254 | AZAR AB | 2015-07-06 | 2015-07-01 08:59 | 2015-07-01 11:45 | Yes | -5 |  | 2015-07-15 17:21 | [6 empty] | 2015-07-15 17:22 | Yes | 0 | 1204-Owner-v | 2019-02-16 10:55
VD-9001-254-DWG-435 | 0 | ASSEMBLY DWG. FOR BANK SIDE WALL TUBE 3/3 | HM-254 | AZAR AB | 2015-07-06 | 2015-07-01 09:00 | 2015-07-01 11:46 | Yes | -5 |  | 2015-07-15 17:21 | [6 empty] | 2015-07-15 17:22 | Yes | 0 | 1204-Owner-v | 2019-02-16 10:54
VD-9001-254-DWG-436 | 0 | ASSEMBLY DWG. OF S/H TUBE 1/3 | HM-254 | AZAR AB | 2015-07-20 | 2015-09-06 08:22 | 2015-09-06 14:18 | Yes | 48 |  | 2015-10-11 15:13 | [6 empty] | 2015-10-11 15:14 | Yes | 21 | 1204-Owner-v | 2019-02-16 10:55
VD-9001-254-DWG-437 | 0 | ASSEMBLY DWG. OF S/H TUBE 2/3 | HM-254 | AZAR AB | 2015-07-20 | 2015-09-06 08:22 | 2015-09-06 14:15 | Yes | 48 |  | 2015-10-11 15:12 | [6 empty] | 2015-10-11 15:13 | Yes | 21 | 1204-Owner-v | 2019-02-16 10:56
VD-9001-254-DWG-438 | 0 | ASSEMBLY DWG. OF S/H TUBE 3/3 | HM-254 | AZAR AB | 2015-07-20 | 2015-09-06 08:23 | 2015-09-06 14:18 | Yes | 48 |  | 2015-10-11 15:13 | [6 empty] | 2015-10-11 15:14 | Yes | 21 | 1204-Owner-v | 2019-02-16 10:54
VD-9001-254-DWG-439 | 0 | ASS. DWG. FOR ECO. | HM-254 | AZAR AB | 2015-07-27 | 2015-07-27 13:55 | 2015-09-06 14:20 | Yes | 41 |  | 2015-09-14 17:04 | [6 empty] | 2015-09-14 17:05 | Yes | 35 | 1204-Owner-v | 2019-01-22 17:25
VD-9001-254-DWG-440 | 0 | INSTALLATION & FABRICATION FOR ECO. TUBE SHEET | HM-254 | AZAR AB | 2015-08-03 | 2015-07-27 13:56 |  | No | -7 |  | 2015-08-24 10:19 | [7 empty] | No | 0
VD-9001-254-DWG-441 | 0 | FABRICATION & INSULATION DWG FOR DOWNCOMER PIPE | HM-254 | AZAR AB | 2015-09-27 | 2015-09-06 08:24 | 2015-09-06 14:21 | Yes | -21 |  | 2015-10-11 15:16 | [6 empty] | 2015-10-11 15:17 | Yes | 21 | 1204-Owner-v | 2019-02-16 10:55
VD-9001-254-DWG-442 | 0 | ARRANGEMENT OF FEEDER PIPE | HM-254 | AZAR AB | 2015-09-30 | 2015-09-06 08:25 | 2015-09-06 14:22 | Yes | -24 |  | 2015-10-11 15:17 | [6 empty] | 2015-10-11 15:18 | Yes | 21 | 1204-Owner-v | 2018-09-09 10:26
VD-9001-254-DWG-443 | 0 | ARRANGEMENT OF RISER PIPE | HM-254 | AZAR AB | 2015-10-06 | 2015-09-06 08:26 | 2015-09-06 14:12 | Yes | -30 |  | 2015-10-11 15:18 | [6 empty] | 2015-10-11 15:19 | Yes | 21 | 1204-Owner-v | 2018-09-09 10:26
VD-9001-254-DWG-444 | 0 | ASSEMBLY DWG. FOR SATURATED STEAM PIPE | HM-254 | AZAR AB | 2015-10-12 | 2015-09-06 08:26 | 2015-09-06 14:23 | Yes | -36 |  | 2015-10-11 15:44 | [6 empty] | 2015-10-11 15:45 | Yes | 21 | 1204-Owner-v | 2019-02-17 16:13
VD-9001-254-DWG-445 | 0 | ASSEMBLY DWG FOR BUCKSTAY OF BOILER (1/3) | HM-254 | AZAR AB | 2015-10-25 | 2015-07-28 11:58 | 2015-07-28 15:50 | Yes | -89 |  | 2015-08-24 10:12 | [6 empty] | 2015-08-24 10:13 | Yes | 13 | 1204-Owner-v | 2019-02-17 16:14
VD-9001-254-DWG-446 | 0 | ASSEMBLY DWG FOR BUCKSTAY OF BOILER (2/3) | HM-254 | AZAR AB | 2015-11-04 | 2015-07-28 11:58 | 2015-07-28 15:52 | Yes | -99 |  | 2015-08-24 10:12 | [6 empty] | 2015-08-24 10:13 | Yes | 13 | 1204-Owner-v | 2018-05-29 10:20
VD-9001-254-DWG-447 | 0 | ASSEMBLY DWG FOR BUCKSTAY OF BOILER (3/3) | HM-254 | AZAR AB | 2015-11-17 | 2015-07-28 11:59 | 2015-07-28 15:53 | Yes | -112 |  | 2015-08-24 10:13 | [6 empty] | 2015-08-24 10:14 | Yes | 13 | 1204-Owner-v | 2019-02-17 16:14
VD-9001-254-DWG-448 | 0 | ASSEMBLY DWG. FOR BOILER SKID (1/2) | HM-254 | AZAR AB | 2015-11-24 | 2015-11-03 10:25 | 2015-11-03 17:29 | Yes | -21 |  | 2015-12-20 12:03 | [6 empty] | 2015-12-20 12:04 | Yes | 33 | 1204-Owner-v | 2019-02-17 16:53
VD-9001-254-DWG-449 | 0 | ASSEMBLY DWG. FOR BOILER SKID (2/2) | HM-254 | AZAR AB | 2015-11-24 | 2015-11-03 10:25 | 2015-11-03 17:30 | Yes | -21 |  | 2015-12-20 12:04 | [6 empty] | 2015-12-20 12:05 | Yes | 33 | 1204-Owner-v | 2019-02-17 16:14
VD-9001-254-DWG-450 | 0 | INSTALLATION DWG. OF EXTERNAL ATTACHMENT OF STEAM DRUM (1/2) | HM-254 | AZAR AB | 2015-07-27 | 2015-09-06 08:27 | 2015-09-06 14:24 | Yes | 41 |  | 2015-10-20 15:52 | [6 empty] | 2015-10-20 15:53 | Yes | 30 | 1204-Owner-v | 2019-02-17 16:14
VD-9001-254-DWG-451 | 0 | INSTALLATION DWG. OF EXTERNAL ATTACHMENT OF STEAM DRUM (2/2) | HM-254 | AZAR AB | 2015-07-27 | 2015-09-06 08:27 | 2015-09-06 14:25 | Yes | 41 |  | 2015-10-20 15:53 | [6 empty] | 2015-10-20 15:54 | Yes | 30 | 1204-Owner-v | 2019-02-17 16:15
VD-9001-254-DWG-452 | 0 | ERECTION DWG. FOR BOILER SKID | HM-254 | AZAR AB | 2015-08-02 | 2015-09-06 08:28 | 2015-09-06 14:25 | Yes | 35 |  | 2015-10-25 11:53 | [6 empty] | 2015-10-25 11:54 | Yes | 35 | 1204-Owner-v | 2019-02-17 16:13
VD-9001-254-DWG-453 | 0 | ERECTION DWG. FOR AIR & GAS DUCT 1/3 | HM-254 | AZAR AB | 2015-07-25 | 2017-05-30 14:34 | 2017-05-30 14:35 | Yes | 675 |  | 2017-06-10 14:43 | [6 empty] | 2017-06-10 20:00 | Yes | -3 | 1204-Owner-v | 2019-02-17 16:15
VD-9001-254-DWG-454 | 0 | ERECTION DWG. FOR AIR & GAS DUCT 2/3 | HM-254 | AZAR AB | 2015-07-25 | 2017-05-30 14:35 | 2017-05-30 14:36 | Yes | 675 |  | 2017-06-10 14:49 | [6 empty] | 2017-06-10 20:00 | Yes | -3 | 1204-Owner-v | 2019-02-17 16:15
VD-9001-254-DWG-455 | 0 | ERECTION DWG. FOR AIR & GAS DUCT 3/3 | HM-254 | AZAR AB | 2015-07-25 | 2017-05-30 14:35 | 2017-05-30 14:36 | Yes | 675 |  | 2017-06-10 14:47 | [6 empty] | 2017-06-10 20:00 | Yes | -3
VD-9001-254-DWG-456 | 0 | ERECTION DWG. FOR NAME PLATE OF BOILER | HM-254 | AZAR AB | 2015-08-04 | 2015-08-01 15:23 |  | No | -3 | 2015-08-24 11:50 | [8 empty] | No | 0
VD-9001-254-DWG-457 | 0 | INSTALATION DWG. FOR PEEP HOLE | HM-254 | AZAR AB | 2015-08-22 | 2015-09-06 08:29 | 2015-09-06 14:26 | Yes | 15 |  | 2015-10-11 15:45 | [6 empty] | 2015-10-11 15:46 | Yes | 21
VD-9001-254-DWG-458 | 0 | ASS. DWG. FOR WIND BOX | HM-254 | AZAR AB | 2015-07-28 |  |  | No | 1788 | [9 empty] | No | 0
VD-9001-254-DWG-459 | 0 | GENERAL ARRANGEMENT OF BOILER 1/4 | HM-254 | AZAR AB | 2015-05-11 | 2015-06-09 15:38 | 2015-06-09 17:42 | Yes | 29 |  | 2015-07-12 15:34 | [6 empty] | 2015-07-12 15:35 | Yes | 19 | 1204-Owner-v | 2018-04-09 14:38
VD-9001-254-DWG-460 | 0 | GENERAL ARRANGEMENT OF BOILER 2/4 | HM-254 | AZAR AB | 2015-05-11 | 2015-06-09 15:39 | 2015-06-09 17:43 | Yes | 29 |  | 2015-07-12 15:35 | [6 empty] | 2015-07-12 15:36 | Yes | 19 | 1204-Owner-v | 2018-04-09 14:38
VD-9001-254-DWG-461 | 0 | GENERAL ARRANGEMENT OF BOILER 3/4 | HM-254 | AZAR AB | 2015-05-11 | 2015-06-09 15:40 | 2015-06-09 17:44 | Yes | 29 |  | 2015-07-12 15:35 | [6 empty] | 2015-07-12 15:36 | Yes | 19 | 1204-Owner-v | 2018-04-09 14:38
VD-9001-254-DWG-462 | 0 | GENERAL ARRANGEMENT OF BOILER 4/4 | HM-254 | AZAR AB | 2015-05-11 | 2015-06-09 15:41 | 2015-06-09 17:45 | Yes | 29 |  | 2015-07-12 15:36 | [6 empty] | 2015-07-12 15:37 | Yes | 19 | 1204-Owner-v | 2018-04-09 14:38
VD-9001-254-DWG-463 | 0 | LOADING DATA & FOUNDATION OF BOILER 1/2 | HM-254 | AZAR AB | 2015-08-03 | 2015-09-16 12:10 |  | No | 44 | 2015-12-27 16:10 | [7 empty] | 2015-12-27 20:03 | Yes | 0
VD-9001-254-DWG-464 | 0 | LOADING DATA & FOUNDATION OF BOILER 2/2 | HM-254 | AZAR AB | 2015-08-03 | 2015-09-16 12:10 | 2015-09-16 16:46 | Yes | 44 |  | 2015-10-20 18:00 | [6 empty] | 2015-10-20 18:01 | Yes | 20 | 1204-Owner-v | 2018-09-09 10:28
VD-9001-254-PCJ-465 | 0 | LEAK TEST PROCEDURE | HM-254 | AZAR AB | 2015-08-10 | 2015-08-15 12:33 |  | No | 5 | 2015-09-14 17:01 | [8 empty] | No | 0
VD-9001-254-PCJ-466 | 0 | HYDROSTATIC TEST PROCEDURE FOR BOILER AT SITE | HM-254 | AZAR AB | 2015-08-10 | 2015-08-15 12:34 |  | No | 5 | 2015-09-08 17:11 | [8 empty] | No | 0
VD-9001-254-DWG-467 | 0 | GENERAL ARR. FOR AIR & FLUE GAS DUCT 1/3 | HM-254 | AZAR AB | 2015-06-14 | 2015-07-01 09:00 | 2015-07-01 11:47 | Yes | 17 |  | 2015-09-14 17:13 | [6 empty] | 2015-09-14 17:14 | Yes | 61
VD-9001-254-DWG-468 | 0 | GENERAL ARR. FOR AIR & FLUE GAS DUCT 2/3 | HM-254 | AZAR AB | 2015-06-14 | 2015-07-01 09:00 | 2015-07-01 11:48 | Yes | 17 |  | 2015-09-14 17:14 | [6 empty] | 2015-09-14 17:15 | Yes | 61
VD-9001-254-DWG-469 | 0 | GENERAL ARR. FOR AIR & FLUE GAS DUCT 3/3 | HM-254 | AZAR AB | 2015-06-14 | 2015-07-01 09:01 | 2015-07-01 11:50 | Yes | 17 |  | 2015-09-14 17:15 | [6 empty] | 2015-09-14 17:16 | Yes | 61
VD-9001-254-DWG-470 | 0 | ARR. OF MEASUREING TAP OF AIR & FLUE GAS DUCT | HM-254 | AZAR AB | 2015-08-03 | 2015-08-09 17:50 | 2015-08-09 18:06 | Yes | 6 |  | 2015-09-14 17:20 | [6 empty] | 2015-09-14 17:21 | Yes | 22 | 1204-Owner-v | 2019-03-07 16:42
VD-9001-254-DWG-471 | 0 | FAB. DWG OF STEAM DRUM FOR BOILER | HM-254 | AZAR AB | 2015-05-17 | 2015-05-21 08:10 |  | No | 4 | 2015-07-20 15:55 | [8 empty] | No | 0
VD-9001-254-DWG-472 | 0 | FAB. DWG FOR WATER DRUM | HM-254 | AZAR AB | 2015-05-17 | 2015-05-21 08:08 |  | No | 4 | 2015-07-20 15:56 | [8 empty] | No | 0
VD-9001-254-DWG-473 | 0 | INSTALLATION FAB. DWG. MANHOLE COVER (STEAM DRUM) | HM-254 | AZAR AB | 2015-07-29 | 2015-06-09 15:42 |  | No | -50 | 2015-07-27 14:12 | [8 empty] | No | 0
VD-9001-254-DWG-474 | 0 | INSTALLATION FAB. DWG. MANHOLE COVER (WATER DRUM) | HM-254 | AZAR AB | 2015-06-07 | 2015-06-09 15:42 |  | No | 2 | 2015-07-27 14:13 | [8 empty] | No | 0
VD-9001-254-DWG-475 | 0 | BRICK AND CASTABLE WORK OF BOILER 1/2 | HM-254 | AZAR AB | 2015-07-28 | 2015-07-29 13:55 | 2015-07-29 17:13 | Yes | 1 |  | 2015-08-23 11:40 | [6 empty] | 2015-08-23 11:41 | Yes | 11
VD-9001-254-DWG-476 | 0 | BRICK AND CASTABLE WORK OF BOILER 2/2 | HM-254 | AZAR AB | 2015-07-28 | 2015-07-29 13:55 | 2015-07-29 17:14 | Yes | 1 |  | 2015-08-23 11:40 | [6 empty] | 2015-08-23 11:41 | Yes | 11
VD-9001-254-DWG-477 | 0 | FAB. INSTALL. DWG FOR BOILER PROPER INSULATION 1/2 | HM-254 | AZAR AB | 2015-07-28 | 2015-07-29 13:56 | 2015-07-29 17:15 | Yes | 1 |  | 2015-08-23 16:15 | [6 empty] | 2015-08-23 16:16 | Yes | 11 | 1204-Owner-v | 2018-05-29 10:26
VD-9001-254-DWG-478 | 0 | FAB. INSTALL. DWG FOR BOILER PROPER INSULATION 2/2 | HM-254 | AZAR AB | 2015-07-28 | 2015-07-29 13:56 | 2015-07-29 17:16 | Yes | 1 |  | 2015-08-23 16:15 | [6 empty] | 2015-08-23 16:16 | Yes | 11 | 1204-Owner-v | 2019-02-17 16:18
VD-9001-254-CAL-479 | 0 | SUMMARY STRENGTH CALCULATION FOR BOILER PRESSURE PART | HM-254 | AZAR AB | 2015-11-15 | 2015-12-20 16:13 |  | No | 35 | 2016-01-02 11:44 | [7 empty] | 2016-01-02 20:03 | Yes | 0
VD-9001-254-DWG-500 | 0 | DETAIL DRAWING OF PIPING SUPPORT | HM-254 | AZAR AB | 2015-04-14 | 2015-06-01 13:42 | 2015-06-01 14:14 | Yes | 48 |  | 2015-06-20 11:12 | [6 empty] | 2015-06-20 11:13 | Yes | 5 | 1204-Owner-v | 2020-04-21 18:07
VD-9001-254-ISO-501 | 0 | HIGH PRESSURE STEAM LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-10-26 | 2019-02-05 10:30 | 2019-02-05 10:30 | Yes | 1198 |  |  |  | 2019-02-19 09:19 |  |  |  |  | 2019-02-19 09:19 | Yes | 0
VD-9001-254-ISO-502 | 0 | ISOMETRIC DWG. FOR SPRAY WATER LINE (BOILER 5) | HM-254 | AZAR AB | 2016-03-05 | 2018-02-26 10:58 | 2018-02-26 10:58 | Yes | 723 |  |  |  |  | 2018-03-11 10:23 |  |  |  | 2018-03-11 10:23 | Yes | -1
VD-9001-254-ISO-503 | 0 | HIGH PRESSURE STEAM LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-11-01 | 2019-02-05 10:31 | 2019-02-05 10:31 | Yes | 1192 |  |  |  | 2019-02-19 09:21 |  |  |  |  | 2019-02-19 09:21 | Yes | 0
VD-9001-254-ISO-504 | 0 | ISOMETRIC DWG. FOR SPRAY WATER LINE (BOILER 6) | HM-254 | AZAR AB | 2016-03-08 | 2018-02-26 10:58 | 2018-02-26 10:58 | Yes | 720 |  |  |  |  | 2018-03-11 10:18 |  |  |  | 2018-03-11 10:18 | Yes | -1
VD-9001-254-ISO-505 | 0 | HP STEAM INLET TO FDF TURBINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-11-07 | 2019-02-06 15:35 | 2019-02-06 15:36 | Yes | 1187 |  |  | 2019-02-19 09:33 | [5 empty] | 2019-02-19 09:33 | Yes | -1
VD-9001-254-ISO-506 | 0 | HP STEAM INLET TO FDF TURBINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-11-11 | 2019-02-06 15:33 | 2019-02-06 15:34 | Yes | 1183 |  |  | 2019-02-19 09:30 | [5 empty] | 2019-02-19 09:30 | Yes | -1
VD-9001-254-ISO-507 | 0 | LP STEAM OUTLET FROM FDF TURBINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2016-02-13 | 2019-02-13 12:24 | 2019-02-13 12:28 | Yes | 1096 |  |  |  | 2019-02-19 09:34 |  |  |  |  | 2019-02-19 09:34 | Yes | -8
VD-9001-254-ISO-508 | 0 | LP STEAM OUTLET FROM FDF TURBINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2016-02-17 | 2019-02-13 12:30 | 2019-02-13 12:33 | Yes | 1092 |  |  |  | 2019-02-19 09:36 |  |  |  |  | 2019-02-19 09:36 | Yes | -8
VD-9001-254-ISO-509 | 0 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF SAFETY VALVES OF STEAM DRUMS (BOILER 5) | HM-254 | AZAR AB | 2016-03-12 | 2017-12-05 08:06 | 2017-12-05 08:07 | Yes | 633 |  | 2017-12-11 15:18 | [6 empty] | 2017-12-11 20:00 | Yes | -8 | 1204-Owner-v | 2019-05-14 16:26
VD-9001-254-ISO-510 | 0 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF SAFETY VALVES OF STEAM DRUMS (BOILER 6) | HM-254 | AZAR AB | 2016-03-14 | 2017-12-05 08:07 | 2017-12-05 08:08 | Yes | 631 |  | 2017-12-11 15:20 | [6 empty] | 2017-12-11 20:00 | Yes | -8 | 1204-Owner-v | 2019-05-14 16:08
VD-9001-254-ISO-511 | 0 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF MAIN STEAM SAFETY VALVE (BOILER 5) | HM-254 | AZAR AB | 2015-12-19 | 2019-02-13 12:35 | 2019-02-13 12:35 | Yes | 1152 |  |  |  | 2019-02-19 09:38 |  |  |  |  | 2019-02-19 09:38 | Yes | -8
VD-9001-254-ISO-512 | 0 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF MAIN STEAM SAFETY VALVE (BOILER 6) | HM-254 | AZAR AB | 2015-12-21 | 2019-02-13 12:35 | 2019-02-13 12:37 | Yes | 1150 |  |  |  | 2019-02-19 09:37 |  |  |  |  | 2019-02-19 09:37 | Yes | -8
VD-9001-254-ISO-513 | 0 | HPS LINE START UP VENT LINE (BOILER 5) ISOMETRIC DWG. | HM-254 | AZAR AB | 2015-11-17 | 2019-02-05 10:35 | 2019-02-05 10:37 | Yes | 1176 |  |  | 2019-02-19 09:23 | [5 empty] | 2019-02-19 09:23 | Yes | 0
VD-9001-254-ISO-514 | 0 | HPS LINE START UP VENT LINE (BOILER 6) ISOMETRIC DWG. | HM-254 | AZAR AB | 2015-11-23 | 2019-02-05 10:39 | 2019-02-05 10:39 | Yes | 1170 |  |  | 2019-02-19 09:25 | [5 empty] | 2019-02-19 09:25 | Yes | 0
VD-9001-254-ISO-515 | 0 | BOILER FEED WATER LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-11-29 | 2018-02-26 10:57 | 2018-02-26 10:57 | Yes | 820 |  |  |  |  | 2018-03-11 10:22 |  |  |  | 2018-03-11 10:22 | Yes | -1
VD-9001-254-ISO-516 | 0 | BOILER FEED WATER LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-12-05 | 2018-02-26 10:57 | 2018-02-26 10:57 | Yes | 814 |  |  |  |  | 2018-03-11 10:20 |  |  |  | 2018-03-11 10:20 | Yes | -1
VD-9001-254-ISO-517 | 0 | ISOMETRIC DRAWING FOR COOLING WATER SUPPLY FOR F.D. FAN TURBINE (BOILER 5) | HM-254 | AZAR AB | 2016-03-16 | 2018-02-10 10:32 |  | No | 696 | 2018-02-18 11:34 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-254-ISO-518 | 0 | ISOMETRIC DRAWING FOR COOLING WATER SUPPLY FOR F.D. FAN TURBINE(BOILER 6) | HM-254 | AZAR AB | 2016-03-27 | 2018-02-10 10:32 |  | No | 685 | 2018-02-18 11:31 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-254-ISO-519 | 0 | ISOMETRIC DRAWING FOR COOLING WATER RETURN FROM F.D. FAN TURBINE(BOILER 5) | HM-254 | AZAR AB | 2016-03-27 | 2018-01-29 16:08 |  | No | 673 | 2018-02-13 10:41 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-254-ISO-520 | 0 | ISOMETRIC DRAWING FOR COOLING WATER RETURN FROM F.D. FAN TURBINE(BOILER 6) | HM-254 | AZAR AB | 2016-03-27 | 2018-01-29 16:09 |  | No | 673 | 2018-02-13 10:43 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-254-ISO-521 | 0 | FUEL GAS LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-12-09 | 2019-03-02 10:14 | 2019-03-02 10:15 | Yes | 1179 |  |  |  | 2019-03-05 09:13 |  |  |  |  | 2019-03-05 09:13 | Yes | -11
VD-9001-254-ISO-522 | 0 | FUEL GAS LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2015-12-15 | 2019-03-02 10:15 | 2019-03-02 10:15 | Yes | 1173 |  |  |  | 2019-03-05 09:10 |  |  |  |  | 2019-03-05 09:10 | Yes | -11
VD-9001-254-ISO-523 | 0 | ISOMETRIC DWG. FOR PILOT GAS LINE ( BOILER 5) | HM-254 | AZAR AB | 2016-01-30 | 2019-03-04 12:11 | 2019-03-04 12:12 | Yes | 1129 |  |  |  | 2019-03-06 09:12 |  |  |  |  | 2019-03-06 09:12 | Yes | -12
VD-9001-254-ISO-524 | 0 | ISOMETRIC DWG. FOR PILOT GAS LINE ( BOILER 6) | HM-254 | AZAR AB | 2016-02-03 | 2019-03-04 12:12 | 2019-03-04 12:14 | Yes | 1125 |  |  |  | 2019-03-06 09:10 |  |  |  |  | 2019-03-06 09:10 | Yes | -12
VD-9001-254-ISO-525 | 0 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER 5) | HM-254 | AZAR AB | 2015-12-27 | 2018-08-05 16:01 | 2018-08-05 16:01 | Yes | 952 |  |  |  | 2018-10-17 11:29 |  |  |  |  | 2018-10-17 11:29 | Yes | 59
VD-9001-254-ISO-526 | 0 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER6) | HM-254 | AZAR AB | 2016-01-02 | 2018-08-05 16:02 | 2018-08-05 16:02 | Yes | 946 |  |  |  | 2018-10-17 11:27 |  |  |  |  | 2018-10-17 11:27 | Yes | 59
VD-9001-254-ISO-527 | 0 | ISOMETRIC DWG. FOR SEALING AIR LINE (BOILER 5) | HM-254 | AZAR AB | 2016-01-06 | 2019-01-29 10:50 | 2019-01-29 10:50 | Yes | 1119 |  |  |  | 2019-02-05 14:22 |  |  |  |  | 2019-02-05 14:22 | Yes | -7
VD-9001-254-ISO-528 | 0 | ISOMETRIC DWG. FOR SEALING AIR LINE (BOILER 6) | HM-254 | AZAR AB | 2016-01-12 | 2019-01-29 10:51 | 2019-01-29 10:51 | Yes | 1113 |  |  |  | 2019-02-05 14:24 |  |  |  |  | 2019-02-05 14:24 | Yes | -7
VD-9001-254-ISO-529 | 0 | ISOMETRIC DWG. FOR CONTINOUS BLOW DOWN (BOILER 5) | HM-254 | AZAR AB | 2016-02-23 | 2018-04-29 15:11 | 2018-04-29 15:12 | Yes | 796 |  |  |  | 2018-05-21 10:28 |  |  |  |  | 2018-05-21 10:28 | Yes | 8
VD-9001-254-ISO-530 | 0 | ISOMETRIC DWG. FOR CONTINOUS BLOW DOWN (BOILER 6) | HM-254 | AZAR AB | 2016-02-29 | 2018-04-29 14:32 | 2018-04-29 14:32 | Yes | 790 |  |  |  | 2018-05-21 10:25 |  |  |  |  | 2018-05-21 10:25 | Yes | 8
VD-9001-254-ISO-531 | 0 | ISOMETRIC DWG. FOR INTERMITTENT BLOW DOWN (BOILER 5) | HM-254 | AZAR AB | 2016-01-18 | 2018-04-16 12:08 | 2018-04-16 12:08 | Yes | 819 |  |  |  | 2018-05-06 16:01 |  |  |  |  | 2018-05-06 16:01 | Yes | 6
VD-9001-254-ISO-532 | 0 | ISOMETRIC DWG. FOR INTERMITTENT BLOW DOWN (BOILER 6) | HM-254 | AZAR AB | 2016-01-24 | 2018-04-16 12:09 | 2018-04-16 12:09 | Yes | 813 |  |  |  | 2018-05-06 16:03 |  |  |  |  | 2018-05-06 16:03 | Yes | 6
VD-9001-254-MDB-533 | 0 | OUTLINE DRAWING & SPECIFICATION FOR DESUPERHEATERS | HM-254 | AZAR AB | 2015-11-28 |  |  | No | 1665 | [9 empty] | No | 0
VD-9001-254-MDB-534 | 0 | INSTRUCTION MANUAL FOR DESUPERHEATERS | HM-254 | AZAR AB | 2015-11-28 |  |  | No | 1665 | [9 empty] | No | 0
VD-9001-254-CSH-535 | 0 | CALCULATION SHEET FOR DESUPERHEATERS | HM-254 | AZAR AB | 2015-11-28 |  |  | No | 1665 | [9 empty] | No | 0
VD-9001-254-MDB-536 | 0 | OUTLINE DRAWING & SPECIFICATION OF HAND VALVES | HM-254 | AZAR AB | 2016-02-24 |  |  | No | 1577 | [9 empty] | No | 0
VD-9001-254-MDB-537 | 0 | OUTLINE DRAWING & SPECIFICATION OF MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2015-12-13 |  |  | No | 1650 | [9 empty] | No | 0
VD-9001-254-MDB-538 | 0 | INSTRUCTION MANUAL OF MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2015-12-13 |  |  | No | 1650 | [9 empty] | No | 0
VD-9001-254-MDB-539 | 0 | OUTLINE DRAWING & SPECIFICATION OF SAFETY VALVES | HM-254 | AZAR AB | 2015-10-07 |  |  | No | 1717 | [9 empty] | No | 0
VD-9001-254-MDB-540 | 0 | INSTRUCTION MANUAL OF SAFETY VALVES | HM-254 | AZAR AB | 2015-10-07 |  |  | No | 1717 | [9 empty] | No | 0
VD-9001-254-MDB-541 | 0 | OUTLINE DRAWING & SPECIFICATION OF PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2016-02-16 |  |  | No | 1585 | [9 empty] | No | 0
VD-9001-254-MDB-542 | 0 | INSTRUCTION MANUAL OF PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2016-01-17 |  |  | No | 1615 | [9 empty] | No | 0
VD-9001-254-MDB-543 | 0 | OUTLINE DRAWING & SPECIFICATION OF CONTROL VALVES | HM-254 | AZAR AB | 2016-01-25 |  |  | No | 1607 | [9 empty] | No | 0
VD-9001-254-MDB-544 | 0 | INSTRUCTION MANUAL OF CONTROL VALVES | HM-254 | AZAR AB | 2016-01-25 |  |  | No | 1607 | [9 empty] | No | 0
VD-9001-254-CSH-545 | 0 | CALCULATION SHEET FOR CONTROL VALVES | HM-254 | AZAR AB | 2016-01-25 |  |  | No | 1607 | [9 empty] | No | 0
VD-9001-254-MDB-546 | 0 | OUTLINE DRAWING & SPECIICATION OF STEAM TRAPS | HM-254 | AZAR AB | 2015-11-21 |  |  | No | 1672 | [9 empty] | No | 0
VD-9001-254-MDB-547 | 0 | OUTLINE DRAWING & SPECIICATION OF STRAINERS | HM-254 | AZAR AB | 2015-11-09 |  |  | No | 1684 | [9 empty] | No | 0
VD-9001-254-DWH-548 | 0 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2015-05-31 | 2015-05-17 09:37 |  | No | -14 | 2015-06-08 17:39 | [8 empty] | No | 0
VD-9001-254-PCJ-549 | 0 | INSULATION PROCEDURE FOR PIPING | HM-254 | AZAR AB | 2015-04-20 | 2015-05-31 13:15 | 2015-05-31 14:16 | Yes | 41 |  | 2015-06-20 11:13 | [6 empty] | 2015-06-20 11:14 | Yes | 6 | 1204-Owner-v | 2018-09-09 10:33
VD-9001-254-CAL-550 | 0 | PIPING STRENGTH CALCULATION | HM-254 | AZAR AB | 2015-05-03 | 2015-09-06 08:32 | 2015-09-06 14:13 | Yes | 126 |  | 2015-09-16 14:52 | [6 empty] | 2015-09-16 14:53 | Yes | -4
VD-9001-254-ARP-551 | 0 | STRESS ANALYSIS OF HIGH PRESSURE STEAM LINE | HM-254 | AZAR AB | 2015-08-03 |  |  | No | 1782 | [9 empty] | No | 0
VD-9001-254-ARP-552 | 0 | STRESS ANALYSIS OF FEED WATER LINE | HM-254 | AZAR AB | 2015-08-31 | 2017-12-24 13:47 |  | No | 846 | 2018-01-02 11:44 | [7 empty] | 2018-01-02 19:59 | Yes | 0
VD-9001-254-ARP-553 | 0 | STRESS ANALYSIS OF F.D.FAN TURBINES INLET STEAM PIPE | HM-254 | AZAR AB | 2015-09-08 |  |  | No | 1746 | [9 empty] | No | 0
VD-9001-254-LST-554 | 0 | PIPE LINE LIST | HM-254 | AZAR AB | 2015-09-30 | 2015-11-03 15:42 |  | No | 34 | 2016-01-04 11:11 | [7 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-254-LST-555 | 0 | VALVE LIST | HM-254 | AZAR AB | 2015-08-18 | 2015-10-26 07:18 |  | No | 69 | 2015-11-02 11:00 | [8 empty] | No | 0
VD-9001-254-PLN-556 | 0 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2015-09-20 | 2016-06-01 10:39 |  | No | 255 | 2016-06-20 14:56 | [7 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-254-PLN-557 | 0 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 3800 AND UP) | HM-254 | AZAR AB | 2015-09-29 | 2016-06-01 10:39 |  | No | 246 | 2016-06-20 14:53 | [7 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-254-PLN-558 | 0 | GENERAL PIPING ARRANGEMENT FOR BOILER 6 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2015-10-11 | 2016-06-01 10:40 | 2016-06-01 10:41 | Yes | 234 |  | 2016-06-20 14:58 | [6 empty] | 2016-06-20 19:57 | Yes | 5 | 1204-Owner-v | 2018-09-09 10:35
VD-9001-254-PLN-559 | 0 | GENERAL PIPING ARRANGEMENT FOR BOILER 6 (EL. 3800 AND UP) | HM-254 | AZAR AB | 2015-10-20 |  |  | No | 1704 | [9 empty] | No | 0
VD-9001-254-CAL-560 | 0 | PIPE SIZING & VELOCITY CALCULATION | HM-254 | AZAR AB | 2015-08-15 | 2015-08-17 14:05 |  | No | 2 | 2015-09-22 11:15 | [8 empty] | No | 0 | 1204-Owner-v | 2019-11-11 14:08
VD-9001-254-PCJ-561 | 0 | HYDROSTATIC TEST PROCEDURE FOR PIPING | HM-254 | AZAR AB | 2015-09-22 | 2018-09-15 13:17 | 2018-09-15 13:17 | Yes | 1089 |  |  | 2018-10-22 11:20 | [5 empty] | 2018-10-22 11:20 | Yes | 23
VD-9001-254-DSH-562 | 0 | DATA SHEET FOR DESUPERHEATER & SPRAY WATER CONTROL VALVE | HM-254 | AZAR AB | 2015-05-31 | 2015-07-05 13:56 |  | No | 35 | 2015-09-02 16:50 | [8 empty] | No | 0
VD-9001-254-DSH-563 | 0 | DATA SHEET FOR MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2015-04-28 | 2015-07-27 11:03 |  | No | 90 | 2015-09-08 09:58 | [8 empty] | No | 0 | 1204-Owner-v | 2018-01-29 08:45
VD-9001-254-DSH-564 | 0 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2015-04-19 | 2015-05-31 07:46 |  | No | 42 | 2015-09-20 10:45 | [8 empty] | No | 0
VD-9001-254-DSH-565 | 0 | DATA SHEET FOR PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2015-05-23 | 2015-07-27 11:02 |  | No | 65 | 2015-09-08 09:59 | [8 empty] | No | 0
VD-9001-254-DSH-566 | 0 | DATA SHEET FOR CONTROL VALVES | HM-254 | AZAR AB | 2015-06-02 | 2015-08-12 10:36 |  | No | 71 | 2015-09-20 17:20 | [8 empty] | No | 0
VD-9001-254-DSH-567 | 0 | DATA SHEET FOR PRESSURE REGULATORS | HM-254 | AZAR AB | 2015-06-10 | 2015-08-12 10:36 |  | No | 63 | 2015-09-20 17:21 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-28 12:16
VD-9001-254-ITP-569 | 0 | TEST & INSPECTION REPORT OF DESUPERHEATERS | HM-254 | AZAR AB | 2015-11-28 |  |  | No | 1665 | [9 empty] | No | 0
VD-9001-254-ITP-571 | 0 | TEST & INSPECTION REPORT OF HAND VALVES | HM-254 | AZAR AB | 2016-02-24 |  |  | No | 1577 | [9 empty] | No | 0
VD-9001-254-ITP-573 | 0 | TEST & INSPECTION REPORT OF MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2015-12-13 |  |  | No | 1650 | [9 empty] | No | 0
VD-9001-254-ITP-575 | 0 | TEST & INSPECTION REPORT OF SAFETY VALVES | HM-254 | AZAR AB | 2015-10-07 |  |  | No | 1717 | [9 empty] | No | 0
VD-9001-254-ITP-577 | 0 | TEST & INSPECTION REPORT OF PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2016-02-16 |  |  | No | 1585 | [9 empty] | No | 0
VD-9001-254-ITP-579 | 0 | TEST & INSPECTION REPORT OF CONTROL VALVES | HM-254 | AZAR AB | 2016-01-17 |  |  | No | 1615 | [9 empty] | No | 0
VD-9001-254-ITP-581 | 0 | TEST & INSPECTION REPORT OF STEAM TRAPS | HM-254 | AZAR AB | 2015-11-21 |  |  | No | 1672 | [9 empty] | No | 0
VD-9001-254-ITP-583 | 0 | TEST & INSPECTION REPORT OF STRAINERS | HM-254 | AZAR AB | 2015-11-09 | 2019-02-13 12:43 | 2019-02-13 12:43 | Yes | 1192 |  |  | 2019-02-18 09:28 | [5 empty] | 2019-02-18 09:28 | Yes | -9 | 1204-Owner-v | 2020-01-01 10:29
VD-9001-254-CAL-585 | 0 | CALCULATION SHEET FOR THERMOWELL | HM-254 | AZAR AB | 2015-05-03 | 2016-01-12 09:59 |  | No | 254 | 2016-02-14 16:43 | [7 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-254-DBS-600 | 0 | BOILER DESIGN BASE DATA SHEET | HM-254 | AZAR AB | 2015-06-09 | 2015-07-12 15:39 |  | No | 33 | 2015-08-24 17:30 | [8 empty] | No | 0 | 1204-Owner-v | 2018-01-25 11:19
VD-9001-254-PCU-601 | 0 | BOILER EXPECTED PERFORMANCE CURVES | HM-254 | AZAR AB | 2015-07-06 | 2015-07-12 15:40 |  | No | 6 | 2015-08-12 17:55 | [8 empty] | No | 0
VD-9001-254-PCJ-602 | 0 | BOILER PERFORMANCE TEST PROCEDURE | HM-254 | AZAR AB | 2016-04-02 | 2016-06-28 15:33 |  | No | 87 | 2016-07-25 17:52 | [7 empty] | 2016-07-25 19:58 | Yes | 0
VD-9001-254-PRT-603 | 0 | BOILER PERFORMANCE TEST REPORT | HM-254 | AZAR AB | 2016-04-02 |  |  | No | 1539 | [9 empty] | No | 0
VD-9001-254-DSH-604 | 0 | BOILER DATA SHEET | HM-254 | AZAR AB | 2015-06-24 | 2015-07-20 07:51 |  | No | 26 | 2015-08-12 17:48 | [8 empty] | No | 0
VD-9001-254-DSH-605 | 0 | PRESSURE VESSEL DATA SHEET (DRUM) | HM-254 | AZAR AB | 2015-06-21 | 2015-09-09 08:39 |  | No | 80 | 2015-10-06 14:43 | [8 empty] | No | 0
VD-9001-254-PPL-700 | 0 | STEAM GENERATION PLANT PLOT PLAN (KEY PLAN) | HM-254 | AZAR AB | 2015-04-27 | 2015-05-17 09:43 |  | No | 20 | 2015-06-08 14:14 | [8 empty] | No | 0 | 1204-Owner-v | 2018-01-27 14:35
VD-9001-254-PPL-701 | 0 | GENERAL ARRANGEMENT OF COLUMN BASE | HM-254 | AZAR AB | 2015-11-23 | 2015-08-19 06:55 |  | No | -96 | 2015-09-13 17:16 | [8 empty] | No | 0
VD-9001-254-DWG-702 | 0 | FOUNDATION LOADS FOR ST. STR. OF BLR FRONT & INSPEC. PLATFORM & AIR DUCT SUPP. | HM-254 | AZAR AB | 2015-07-12 | 2015-07-20 10:39 | 2015-07-20 17:32 | Yes | 8 |  | 2015-10-18 11:40 | [6 empty] | 2015-10-18 11:41 | Yes | 76 | 1204-Owner-v | 2019-03-03 17:02
VD-9001-254-DWG-703 | 0 | FOUNDATION LOADS FOR ST. STR. OF BLR REAR | HM-254 | AZAR AB | 2015-06-10 | 2015-06-16 16:22 | 2015-06-17 11:31 | Yes | 7 |  | 2015-10-25 11:38 | [6 empty] | 2015-10-25 11:39 | Yes | 117
VD-9001-254-DWG-704 | 0 | FOUNDATION LOADS FOR ST. STACK | HM-254 | AZAR AB | 2015-06-17 | 2015-06-15 12:40 |  | No | -2 | 2015-09-16 12:22 | [8 empty] | No | 0
VD-9001-254-DWG-705 | 0 | FOUNDATION LOADS FOR AIR DUCT SUPPORT | HM-254 | AZAR AB | 2015-10-31 | 2015-09-14 09:02 | 2015-09-14 16:56 | Yes | -47 |  | 2015-10-25 11:48 | [6 empty] | 2015-10-25 11:49 | Yes | 27
VD-9001-254-DWG-706 | 0 | FOUNDATION LOADS FOR ECONOMIZER SUPP. | HM-254 | AZAR AB | 2015-11-16 | 2015-09-05 10:24 | 2015-09-05 10:31 | Yes | -72 |  | 2015-10-25 11:45 | [6 empty] | 2015-10-25 11:46 | Yes | 36
VD-9001-254-PPL-708 | 0 | GENERAL LAYOUT OF PLANT | HM-254 | AZAR AB | 2015-05-20 | 2015-05-26 16:08 |  | No | 6 | 2015-06-06 17:53 | [8 empty] | No | 0 | 1204-Owner-v | 2018-04-17 15:06
VD-9001-254-PPL-709 | 0 | GENERAL LAYOUT OF BOILER (PLAN) | HM-254 | AZAR AB | 2015-05-20 | 2015-05-26 16:09 |  | No | 6 |  | 2015-06-06 17:53 | [7 empty] | No | 0
VD-9001-254-PPL-710 | 0 | GENERAL LAYOUT OF BOILER (front view) | HM-254 | AZAR AB | 2015-05-20 | 2015-05-26 16:10 |  | No | 6 |  | 2015-06-06 17:54 | [7 empty] | No | 0
VD-9001-254-PPL-711 | 0 | GENERAL LAYOUT OF BOILER (side view) | HM-254 | AZAR AB | 2015-05-20 | 2015-05-26 16:10 |  | No | 6 |  | 2015-06-06 17:54 | [7 empty] | No | 0
VD-9001-254-DWG-712 | 0 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 1/5 | HM-254 | AZAR AB | 2015-07-01 | 2015-07-01 09:46 |  | No | 0 |  | 2015-10-18 11:30 | [7 empty] | No | 0
VD-9001-254-DWG-713 | 0 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 2/5 | HM-254 | AZAR AB | 2015-07-01 | 2015-07-01 09:47 |  | No | 0 |  | 2015-10-18 11:31 | [7 empty] | No | 0
VD-9001-254-DWG-714 | 0 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 3/5 | HM-254 | AZAR AB | 2015-07-01 | 2015-07-01 09:48 |  | No | 0 |  | 2015-10-18 11:31 | [7 empty] | No | 0
VD-9001-254-DWG-715 | 0 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 4/5 | HM-254 | AZAR AB | 2015-07-01 | 2015-07-01 09:49 |  | No | 0 |  | 2015-10-18 11:32 | [7 empty] | No | 0
VD-9001-254-DWG-716 | 0 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 5/5 | HM-254 | AZAR AB | 2015-07-01 | 2015-07-01 09:50 |  | No | 0 |  | 2015-10-18 11:33 | [7 empty] | No | 0
VD-9001-254-DWG-717 | 0 | G.A. OF ST. STR. OF BLR REAR 1/2 | HM-254 | AZAR AB | 2015-05-31 | 2015-06-16 16:22 |  | No | 16 |  | 2015-10-21 12:22 | [7 empty] | No | 0
VD-9001-254-DWG-718 | 0 | G.A. OF ST. STR. OF BLR REAR 2/2 | HM-254 | AZAR AB | 2015-05-31 | 2015-06-16 16:21 |  | No | 16 |  | 2015-10-21 12:23 | [7 empty] | No | 0
VD-9001-254-DWG-719 | 0 | G.A. OF AIR DUCT SUPPORT | HM-254 | AZAR AB | 2015-08-18 | 2015-09-14 09:03 | 2015-09-14 16:57 | Yes | 27 |  | 2015-10-20 17:55 | [6 empty] | 2015-10-20 17:56 | Yes | 22 | 1204-Owner-v | 2019-02-17 16:29
VD-9001-254-DWG-720 | 0 | G.A. OF ECONOMIZER SUPP. | HM-254 | AZAR AB | 2015-11-14 | 2015-08-29 09:08 |  | No | -77 |  | 2015-10-21 16:08 | [7 empty] | No | 0
VD-9001-254-DWG-723 | 0 | G.A. OF ST. STACK 1/2 | HM-254 | AZAR AB | 2015-06-13 | 2015-06-17 16:35 | 2015-06-17 17:37 | Yes | 4 |  | 2015-11-28 14:48 | [6 empty] | 2015-11-28 14:49 | Yes | 150 | 1204-Owner-v | 2018-09-05 13:00
VD-9001-254-DWG-724 | 0 | G.A. OF ST. STACK 2/2 | HM-254 | AZAR AB | 2015-06-13 | 2015-06-17 16:36 | 2015-06-17 17:38 | Yes | 4 |  | 2015-10-21 16:05 | [6 empty] | 2015-10-21 16:06 | Yes | 112 | 1204-Owner-v | 2019-02-17 16:30
VD-9001-254-DWG-725 | 0 | ANCHOR BOLT FABRICATION DETAIL FOR ST. STR. OF BLR FRONT ,INSPECTIONS PLATFORM,AIR& GAS DUCT SUPPORT | HM-254 | AZAR AB | 2015-07-13 | 2015-07-20 14:16 | 2015-07-20 17:33 | Yes | 7 |  | 2015-10-18 11:41 | [6 empty] | 2015-10-18 11:42 | Yes | 76
VD-9001-254-DWG-726 | 0 | ANCHOR BOLT FABRICATION DETAIL FOR ST. STR. OF BOILER REAR | HM-254 | AZAR AB | 2015-06-17 | 2015-06-17 16:36 | 2015-06-17 17:39 | Yes | 0 |  | 2015-10-18 11:48 | [6 empty] | 2015-10-18 11:49 | Yes | 109
VD-9001-254-DWG-727 | 0 | ANCHOR BOLT FABRICATION DETAIL FOR AIR DUCT SUPPORT | HM-254 | AZAR AB | 2015-10-27 | 2015-09-20 17:08 |  | No | -37 | 2015-10-21 12:16 | [8 empty] | No | 0
VD-9001-254-DWG-728 | 0 | ANCHOR BOLT FABRICATION DETAIL FOR ST. STR. OF ECONOMIZER SUPPORT | HM-254 | AZAR AB | 2015-11-25 | 2015-09-20 17:07 |  | No | -66 | 2015-10-21 12:17 | [8 empty] | No | 0
VD-9001-254-DWG-730 | 0 | ANCHOR BOLT, ANCHOR PLATE &TEMPLATE FABRICATION DETAIL FOR STEEL STACK | HM-254 | AZAR AB | 2015-07-08 | 2015-06-15 12:12 |  | No | -23 | 2015-10-21 12:10 | [8 empty] | No | 0
VD-9001-254-CAL-731 | 0 | CALCULATION REPORT FOR STEEL STACK | HM-254 | AZAR AB | 2015-05-02 | 2015-05-31 13:18 |  | No | 29 | 2015-07-20 16:30 | [8 empty] | No | 0
VD-9001-254-PCJ-800 | 0 | PAINTING SCHEDULE , METHOD& DEGREE OF SURFACE PREPARATION | HM-254 | AZAR AB | 2015-06-10 | 2015-06-27 09:44 |  | No | 17 | 2015-07-05 12:44 | [8 empty] | No | 0
VD-9001-254-SPE-801 | 0 | PAINT SPECIFICATION | HM-254 | AZAR AB | 2015-06-10 | 2015-06-27 09:46 |  | No | 17 | 2015-07-22 10:08 | [8 empty] | No | 0 | 1204-Owner-v | 2018-01-25 10:53
VD-9001-254-WMP-802 | 0 | WELDING & NDE MAP FOR STEAM DRUM | HM-254 | AZAR AB | 2015-06-20 | 2015-05-17 10:00 |  | No | -34 | 2015-10-07 10:24 | [8 empty] | No | 0
VD-9001-254-WMP-803 | 0 | WELDING & NDE MAP FOR WATER DRUM | HM-254 | AZAR AB | 2015-07-06 | 2015-05-17 10:04 |  | No | -50 | 2015-06-08 15:06 | [8 empty] | No | 0
VD-9001-254-WMP-804 | 0 | WELDING & NDE MAP FOR WATER WALL HEADERS | HM-254 | AZAR AB | 2015-07-27 | 2015-10-05 15:09 | 2015-10-05 18:01 | Yes | 70 |  | 2015-11-25 11:34 | [6 empty] | 2015-11-25 11:35 | Yes | 37
VD-9001-254-WMP-805 | 0 | WELDING & NDE MAP FOR SUPER HEATER HEADERS | HM-254 | AZAR AB | 2015-08-16 | 2015-09-27 10:53 |  | No | 42 | 2015-10-11 11:18 | [8 empty] | No | 0
VD-9001-254-WMP-806 | 0 | WELDING & NDE MAP FOR ECONOMIZER HEADERS | HM-254 | AZAR AB | 2015-08-21 | 2015-10-07 09:27 | 2015-10-07 16:21 | Yes | 47 |  | 2015-10-26 12:37 | [6 empty] | 2015-10-26 12:38 | Yes | 5
VD-9001-254-PQR-808 | 0 | PQR FOR STEEL STACK | HM-254 | AZAR AB | 2015-08-11 | 2015-06-27 09:46 |  | No | -45 | 2015-06-30 15:49 | [8 empty] | No | 0
VD-9001-254-PQR-809 | 0 | PQR FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-05-20 | 2015-05-17 10:12 |  | No | -3 | 2015-06-09 10:47 | [8 empty] | No | 0
VD-9001-254-PQR-810 | 0 | PQR FOR STEAM DRUM (PART II) | HM-254 | AZAR AB | 2015-06-20 | 2015-10-03 08:57 | 2015-10-03 14:29 | Yes | 105 |  | 2015-10-20 16:08 | [6 empty] | 2015-10-20 16:09 | Yes | 3 | 1204-Owner-v | 2020-05-09 11:11
VD-9001-254-PQR-811 | 0 | PQR FOR WATER DRUM (PART I) | HM-254 | AZAR AB | 2015-03-02 | 2015-07-14 10:23 | 2015-07-14 17:06 | Yes | 134 |  | 2015-08-04 12:20 | [6 empty] | 2015-08-04 12:21 | Yes | 7
VD-9001-254-PQR-812 | 0 | PQR FOR WATER DRUM (PART II) | HM-254 | AZAR AB | 2015-07-06 | 2015-07-14 10:24 | 2015-07-14 17:07 | Yes | 8 |  | 2015-08-04 12:21 | [6 empty] | 2015-08-04 12:22 | Yes | 7
VD-9001-254-PQR-813 | 0 | PQR FOR WATER WALL (PART I) | HM-254 | AZAR AB | 2015-07-16 | 2015-07-01 09:55 | 2015-07-01 11:57 | Yes | -15 |  | 2015-07-12 15:47 | [6 empty] | 2015-07-12 15:48 | Yes | -3 | 1204-Owner-v | 2019-12-29 11:49
VD-9001-254-PQR-814 | 0 | PQR FOR WATER WALL (PART II) | HM-254 | AZAR AB | 2015-07-27 | 2015-10-05 14:26 | 2015-10-05 18:01 | Yes | 70 |  | 2015-12-15 17:11 | [6 empty] | 2015-12-15 17:12 | Yes | 57 | 1204-Owner-v | 2019-12-29 11:49
VD-9001-254-PQR-815 | 0 | PQR FOR SUPER HEATER (PART I) | HM-254 | AZAR AB | 2015-08-06 | 2015-09-06 08:38 |  | No | 31 |  | 2015-10-11 15:11 | [7 empty] | No | 0
VD-9001-254-PQR-816 | 0 | PQR FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2015-08-16 | 2015-09-27 10:53 |  | No | 42 |  | 2015-10-13 14:15 | [7 empty] | No | 0
VD-9001-254-PQR-817 | 0 | PQR FOR ECONOMIZER (PART I) | HM-254 | AZAR AB | 2015-08-21 | 2015-09-29 11:50 | 2015-09-29 15:59 | Yes | 39 |  | 2015-11-25 11:26 | [6 empty] | 2015-11-25 11:27 | Yes | 43
VD-9001-254-PQR-818 | 0 | PQR FOR ECONOMIZER (PART II) | HM-254 | AZAR AB | 2015-08-21 | 2015-10-07 09:29 | 2015-10-07 16:19 | Yes | 47 |  | 2015-10-25 17:04 | [6 empty] | 2015-10-25 17:05 | Yes | 4 | 1204-Owner-v | 2020-05-09 09:50
VD-9001-254-PQR-819 | 0 | PQR FOR INTEGRAL PIPES | HM-254 | AZAR AB | 2015-08-27 | 2015-09-07 10:54 | 2015-09-08 09:44 | Yes | 12 |  | 2015-09-16 14:58 | [6 empty] | 2015-09-16 14:59 | Yes | -5
VD-9001-254-PQR-820 | 0 | PQR FOR WATER COLUMN & CONDENSATE POT | HM-254 | AZAR AB | 2015-08-30 | 2015-10-07 09:28 | 2015-10-07 16:20 | Yes | 38 |  | 2015-12-15 17:17 | [6 empty] | 2015-12-15 17:18 | Yes | 55 | 1204-Owner-v | 2020-05-09 11:06
VD-9001-254-PQR-821 | 0 | PQR FOR NON PRESSURE PARTS | HM-254 | AZAR AB | 2015-09-01 | 2015-10-05 08:30 | 2015-10-05 17:59 | Yes | 34 |  | 2015-10-25 16:59 | [6 empty] | 2015-10-25 17:00 | Yes | 6
VD-9001-254-PQR-823 | 0 | PQR FOR THERMOWELL & SPECTACLE BLIND | HM-254 | AZAR AB | 2015-09-21 | 2016-01-17 10:20 | 2016-01-17 10:21 | Yes | 118 |  | 2017-08-12 09:57 | [6 empty] | 2017-08-12 19:58 | Yes | 559
VD-9001-254-WPS-826 | 0 | PREQUALIFIED WPS FOR STEEL STRUCTURE AND SUPPORTS | HM-254 | AZAR AB | 2015-10-17 | 2015-09-27 10:53 |  | No | -20 | 2015-10-26 12:32 | [8 empty] | No | 0
VD-9001-254-WPS-827 | 0 | WPS FOR STEEL STACK | HM-254 | AZAR AB | 2015-08-11 | 2015-06-27 09:47 |  | No | -45 | 2015-06-30 15:56 | [8 empty] | No | 0
VD-9001-254-WPS-828 | 0 | WPS FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-05-20 | 2015-05-17 10:16 |  | No | -3 | 2015-06-09 10:45 | [8 empty] | No | 0
VD-9001-254-WPS-829 | 0 | WPS FOR STEAM DRUM (PART II) | HM-254 | AZAR AB | 2015-06-20 | 2015-10-03 08:58 | 2015-10-03 14:30 | Yes | 105 |  | 2015-10-20 16:09 | [6 empty] | 2015-10-20 16:10 | Yes | 3
VD-9001-254-WPS-830 | 0 | WPS FOR WATER DRUM (PART I) | HM-254 | AZAR AB | 2015-03-02 | 2015-07-14 10:26 | 2015-07-14 17:12 | Yes | 134 |  | 2015-08-04 12:22 | [6 empty] | 2015-08-04 12:23 | Yes | 7
VD-9001-254-WPS-831 | 0 | WPS FOR WATER DRUM (PART II) | HM-254 | AZAR AB | 2015-07-06 | 2015-07-14 10:32 | 2015-07-14 17:10 | Yes | 8 |  | 2015-08-04 12:22 | [6 empty] | 2015-08-04 12:23 | Yes | 7
VD-9001-254-WPS-832 | 0 | WPS FOR WATER WALL (PART I) | HM-254 | AZAR AB | 2015-07-16 | 2015-07-01 09:56 | 2015-07-01 11:58 | Yes | -15 |  | 2015-07-12 15:48 | [6 empty] | 2015-07-12 15:49 | Yes | -3
VD-9001-254-WPS-833 | 0 | WPS FOR WATER WALL (PART II) | HM-254 | AZAR AB | 2015-07-27 | 2015-10-05 14:26 | 2015-10-05 17:59 | Yes | 70 |  | 2015-12-15 17:11 | [6 empty] | 2015-12-15 17:12 | Yes | 57
VD-9001-254-WPS-834 | 0 | WPS FOR SUPER HEATER (PART I) | HM-254 | AZAR AB | 2015-08-06 | 2015-09-06 08:38 |  | No | 31 |  | 2015-10-11 15:11 | [7 empty] | No | 0
VD-9001-254-WPS-835 | 0 | WPS FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2015-08-16 | 2015-09-27 10:53 |  | No | 42 |  | 2015-10-13 14:16 | [7 empty] | No | 0
VD-9001-254-WPS-836 | 0 | WPS FOR ECONOMIZER (PART I) | HM-254 | AZAR AB | 2015-08-21 | 2015-09-29 11:50 | 2015-09-29 16:00 | Yes | 39 |  | 2015-11-25 11:26 | [6 empty] | 2015-11-25 11:27 | Yes | 43
VD-9001-254-WPS-837 | 0 | WPS FOR ECONOMIZER (PART II) | HM-254 | AZAR AB | 2015-08-21 | 2015-10-07 09:27 | 2015-10-07 16:22 | Yes | 47 |  | 2015-10-25 17:05 | [6 empty] | 2015-10-25 17:06 | Yes | 4
VD-9001-254-WPS-838 | 0 | WPS FOR INTEGRAL PIPES | HM-254 | AZAR AB | 2015-08-27 | 2015-09-07 10:54 | 2015-09-08 09:43 | Yes | 12 |  | 2015-09-16 14:57 | [6 empty] | 2015-09-16 14:58 | Yes | -5
VD-9001-254-WPS-839 | 0 | WPS FOR WATER COLUMN & CONDENSATE POT | HM-254 | AZAR AB | 2015-08-30 | 2015-10-07 09:27 | 2015-10-07 16:23 | Yes | 38 |  | 2015-12-15 17:18 | [6 empty] | 2015-12-15 17:19 | Yes | 55
VD-9001-254-WPS-840 | 0 | WPS FOR NON PRESSURE PARTS | HM-254 | AZAR AB | 2015-09-01 | 2015-10-05 08:30 | 2015-10-05 17:58 | Yes | 34 |  | 2015-10-25 16:58 | [6 empty] | 2015-10-25 16:59 | Yes | 6
VD-9001-254-WPS-842 | 0 | WPS FOR THERMOWELL & SPECTACLE BLIND | HM-254 | AZAR AB | 2015-09-21 | 2016-01-17 10:20 | 2016-01-17 10:21 | Yes | 118 |  | 2017-08-12 09:54 | [6 empty] | 2017-08-12 19:58 | Yes | 559
VD-9001-255-WPS-845 | 0 | PWHT PROCEDURE | HM-254 | AZAR AB | 2015-05-22 | 2015-10-03 08:58 | 2015-10-03 14:33 | Yes | 134 |  | 2015-11-25 11:39 | [6 empty] | 2015-11-25 11:40 | Yes | 39 | 1204-Owner-v | 2018-09-09 10:40
VD-9001-254-DWG-900 | 0 | OUTER CASING OF BOILER FRONT SIDE | HM-254 | AZAR AB | 2015-12-22 | 2016-02-15 08:17 | 2016-02-15 08:18 | Yes | 55 |  | 2016-04-03 14:26 | [6 empty] | 2016-04-03 20:00 | Yes | 34 | 1204-Owner-v | 2019-02-13 11:34
VD-9001-254-DWG-901 | 0 | OUTER CASING OF BOILER REAR SIDE | HM-254 | AZAR AB | 2015-12-23 | 2016-02-15 08:18 | 2016-02-15 08:19 | Yes | 54 |  | 2016-03-08 14:14 | [6 empty] | 2016-03-08 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-13 11:35
VD-9001-254-DWG-902 | 0 | OUTER CASING OF BOILER ROOF SIDE | HM-254 | AZAR AB | 2015-12-24 | 2016-02-15 08:18 | 2016-02-15 08:19 | Yes | 53 |  | 2016-04-03 14:29 | [6 empty] | 2016-04-03 20:00 | Yes | 34 | 1204-Owner-v | 2019-02-13 11:34
VD-9001-254-DWG-903 | 0 | OUTER CASING OF BOILER FURNACE SIDE | HM-254 | AZAR AB | 2015-12-25 | 2016-02-15 08:18 | 2016-02-15 08:19 | Yes | 52 |  | 2016-03-08 14:11 | [6 empty] | 2016-03-08 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-13 11:36
VD-9001-254-DWG-904 | 0 | BANK SIDE CASING | HM-254 | AZAR AB | 2015-12-26 | 2016-02-15 08:19 | 2016-02-15 08:20 | Yes | 51 |  | 2016-03-08 15:25 | [6 empty] | 2016-03-08 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-13 11:34
VD-9001-254-DWG-905 | 0 | SUPERHEATER CASING | HM-254 | AZAR AB | 2015-12-27 | 2016-02-15 08:19 | 2016-02-15 08:20 | Yes | 50 |  | 2016-03-08 14:56 | [6 empty] | 2016-03-08 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-13 11:36
VD-9001-254-DWG-906 | 0 | SKIN CASING OF BOILER | HM-254 | AZAR AB | 2015-12-28 | 2016-02-15 08:19 | 2016-02-15 08:20 | Yes | 49 |  | 2016-03-08 15:28 | [6 empty] | 2016-03-08 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-13 11:35
VD-9001-254-DWG-907 | 0 | FOUNDATION OF CASING | HM-254 | AZAR AB | 2015-12-29 | 2016-02-15 08:19 |  | No | 48 | 2016-08-29 11:10 | [7 empty] | 2016-08-29 19:56 | Yes | 0
VD-9001-254-SOI-950 | 0 | ITP FOR BIOLER FABRICATION | HM-254 | AZAR AB | 2015-02-18 | 2015-06-14 09:12 |  | No | 116 | 2015-07-15 14:12 | [8 empty] | No | 0
VD-9001-254-MNL-951 | 0 | QUALITY ASSURANCE MANUAL | HM-254 | AZAR AB | 2015-05-22 | 2015-05-25 11:55 |  | No | 3 | 2015-06-20 11:06 | [8 empty] | No | 0
VD-9001-254-IPM-953 | 0 | HARDNESS TEST PROCEDURE | HM-254 | AZAR AB | 2015-05-22 | 2015-05-25 12:00 |  | No | 3 | 2015-06-09 17:10 | [8 empty] | No | 0
VD-9001-254-IPM-952 | 0 | GENERAL NDT PROCEDURE | HM-254 | AZAR AB | 2015-05-22 | 2015-05-25 11:59 |  | No | 3 | 2015-06-09 17:10 | [8 empty] | No | 0
VD-9001-254-LST-954 | 0 | LIST OF NDE PERSONAL | HM-254 | AZAR AB | 2015-05-22 | 2015-05-25 11:55 | 2015-05-25 12:25 | Yes | 3 |  | 2015-06-09 17:08 | [6 empty] | 2015-06-09 17:09 | Yes | 1 | 1204-Owner-v | 2018-09-09 10:31
VD-9001-254-SOI-955 | 0 | ITP FOR F.D.FAN & DRIVERS | HM-254 | AZAR AB | 2016-02-09 | 2018-02-07 09:04 |  | No | 729 | 2018-02-18 14:29 | [7 empty] | 2018-02-18 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-09 17:18
VD-9001-254-SOI-956 | 0 | ITP FOR BURNER | HM-254 | AZAR AB | 2016-03-09 | 2018-02-07 09:05 |  | No | 700 | 2018-02-18 09:56 | [7 empty] | 2018-02-18 19:59 | Yes | 0
VD-9001-254-SOI-957 | 0 | ITP FOR BIOLERS' ACCESSORIES | HM-254 | AZAR AB | 2016-02-20 | 2018-12-23 09:44 | 2018-12-23 09:44 | Yes | 1037 |  |  | 2019-02-10 10:02 | [5 empty] | 2019-02-10 10:02 | Yes | 35 | 1204-Owner-v | 2019-09-22 15:31
VD-9001-108-DWG-019 | 2 | FOUNDATION DETAIL | PR-108 | Farabard | 2015-05-27 | 2015-05-14 08:14 |  | No | -13 |  | 2015-05-17 12:03 | [7 empty] | No | 0
VD-9001-206A-DWG-019 | 3 | NAME PLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-05-31 | 2015-06-17 17:38 |  | No | 17 | 2015-07-09 10:27 | [8 empty] | No | 0
VD-9001-206A-DWG-029 | 3 | NAME PLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-05-31 | 2015-06-17 17:41 |  | No | 17 | 2015-07-09 10:28 | [8 empty] | No | 0
VD-9001-253(A)-DWG-002 | 5 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2015-05-31 | 2015-09-05 14:52 |  | No | 97 | 2015-09-20 15:21 | [8 empty] | No | 0
VD-9001-253(A)-ITP-100 | 3 | INSPECTION TEST PLAN | HM-253A | FATEH SANAT KIMIA | 2015-05-31 | 2015-05-19 09:55 |  | No | -12 | 2015-06-30 08:37 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-06 13:09
VD-9001-253(A)-PCJ-103 | 2 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-05-31 | 2015-08-25 15:07 |  | No | 86 | 2015-09-15 12:13 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-027 | 1 | FERRITE CONTENT PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-06-01 | 2015-05-23 11:48 | 2015-05-23 17:25 | Yes | -9 |  | 2015-05-27 14:37 | [6 empty] | 2015-05-27 14:38 | Yes | -10 | 1204-Owner-v | 2019-01-31 11:29
VD-9001-205A-DWG-011 | 5 | GENERAL ARRANGEMENT DRAWING FOR OF T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-05-18 14:28 | 2015-05-18 14:30 | 2015-05-18 14:37 | Yes | 0 |  | 2015-05-30 10:32 | [6 empty] | 2015-05-30 10:33 | Yes | -2
VD-9001-205A-DWG-012 | 5 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-05-18 14:28 | 2015-05-18 14:30 | 2015-05-18 14:38 | Yes | 0 |  | 2015-05-30 10:33 | [6 empty] | 2015-05-30 10:34 | Yes | -2
VD-9001-206A-DWG-014 | 2 | INTERNAL ATTACHMENT DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-06-01 | 2015-06-17 17:38 |  | No | 16 | 2015-07-20 18:19 | [8 empty] | No | 0
VD-9001-206A-DWG-004 | 2 | INTERNAL ATTACHMENT DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-06-01 | 2015-06-17 17:37 |  | No | 16 | 2015-08-23 12:26 | [8 empty] | No | 0
VD-9001-205A-DWG-013 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-06-01 | 2015-05-21 10:17 |  | No | -11 |  | 2015-05-30 10:38 | [7 empty] | No | 0
VD-9001-108-DSH-011 | 2 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2015-06-03 | 2015-09-16 13:25 |  | No | 105 | 2015-10-05 11:45 | [8 empty] | No | 0
VD-9001-253(A)-CAL-080 | 2 | STRUCTURE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-06-07 | 2015-06-14 16:19 |  | No | 7 | 2015-06-21 15:51 | [8 empty] | No | 0
VD-9001-253(A)-CAL-050 | 1 | STRUCTURE CALCULATION for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-06-07 | 2015-07-22 15:35 |  | No | 45 |  | 2015-08-22 15:47 | [7 empty] | No | 0
VD-9001-108-QCP-066 | 1 | QUALITY CONTROL PLAN(QCP) | PR-108 | Farabard | 2015-06-08 | 2015-05-27 11:06 |  | No | -12 | 2015-06-08 11:04 | [8 empty] | No | 0
VD-9001-205A-WPS-058 | 2 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-06-08 | 2015-10-03 13:16 |  | No | 117 | 2015-10-13 10:17 | [8 empty] | No | 0
VD-9001-206A-DWG-024 | 1 | INTERNAL ATTACHMENT DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-06-08 | 2015-06-17 17:39 |  | No | 9 | 2015-07-20 18:19 | [8 empty] | No | 0
VD-9001-108-DWG-019 | 3 | FOUNDATION DETAIL | PR-108 | Farabard | 2015-05-27 14:49 | 2015-05-28 12:01 |  | No | 1 |  | 2015-05-28 12:29 | [7 empty] | No | 0
VD-9001-213B-PCJ-012 | 4 | Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-06-13 | 2015-06-01 11:59 | 2015-06-01 12:08 | Yes | -12 |  | 2015-06-02 10:41 | [6 empty] | 2015-06-02 10:42 | Yes | -13
VD-9001-213A-DWG-095 | 2 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-06-13 | 2015-06-09 16:55 |  | No | -4 | 2015-06-30 09:23 | [8 empty] | No | 0
VD-9001-108-DBS-006 | 1 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2015-06-14 | 2015-09-23 08:20 |  | No | 101 | 2015-10-25 12:00 | [8 empty] | No | 0
VD-9001-257A-CAL-001 | 1 | Strength Calculation Book E-2004 | HM-257A | ABAN AIR COOLER. | 2015-06-14 | 2015-06-09 16:10 | 2015-06-10 09:57 | Yes | -4 |  | 2015-07-25 11:33 | [6 empty] | 2015-07-25 11:34 | Yes | 32
VD-9001-257A-DWG-001 | 1 | General Arrangment Drawing E-2004 | HM-257A | ABAN AIR COOLER. | 2015-06-14 | 2015-06-06 14:51 |  | No | -8 | 2015-07-25 11:28 | [8 empty] | No | 0
VD-9001-213A-DWG-096 | 3 | Auto Breather Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-06-02 12:14 | 2015-06-02 12:52 | 2015-06-02 13:26 | Yes | 0 |  | 2015-06-09 08:54 | [6 empty] | 2015-06-09 08:55 | Yes | -7 | 1204-Owner-v | 2019-06-02 15:09
VD-9001-257A-CAL-002 | 1 | Strength Calculation Book E-3001 | HM-257A | ABAN AIR COOLER. | 2015-06-16 | 2015-06-16 14:21 | 2015-06-16 16:39 | Yes | 0 |  | 2015-07-14 14:06 | [6 empty] | 2015-07-14 14:07 | Yes | 14
VD-9001-257A-DWG-002 | 1 | General Arrangment Drawing E-3001 | HM-257A | ABAN AIR COOLER. | 2015-06-16 | 2015-06-16 14:34 |  | No | 0 | 2015-07-14 14:07 | [8 empty] | No | 0
VD-9001-213A-PCJ-033 | 5 | Erection Procedure for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-06-17 | 2015-06-27 10:53 | 2015-06-27 11:14 | Yes | 10 |  | 2015-06-30 09:41 | [6 empty] | 2015-06-30 09:42 | Yes | -11 | 1204-Owner-v | 2020-05-21 07:17
VD-9001-257A-CAL-003 | 1 | Strength Calculation Book E-3002 | HM-257A | ABAN AIR COOLER. | 2015-06-18 | 2015-06-16 14:26 | 2015-06-16 16:41 | Yes | -2 |  | 2015-07-14 17:18 | [6 empty] | 2015-07-14 17:19 | Yes | 14
VD-9001-257A-DWG-003 | 1 | General Arrangment Drawing E-3002 | HM-257A | ABAN AIR COOLER. | 2015-06-18 | 2015-06-16 14:39 |  | No | -2 | 2015-07-14 17:19 | [8 empty] | No | 0
VD-9001-253(A)-CAL-021 | 2 | BASE PLATE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-06-06 11:39 | 2015-06-06 11:52 |  | No | 0 |  | 2015-06-20 11:25 | [7 empty] | No | 0
VD-9001-253(A)-CAL-020 | 2 | STRUCTURE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-06-06 11:39 | 2015-06-06 11:51 |  | No | 0 | 2015-06-21 15:46 | [8 empty] | No | 0
VD-9001-253(A)-RPT-022 | 4 | FOUNDATION LOADING for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-06-06 11:39 | 2015-06-06 11:58 | 2015-06-06 12:19 | Yes | 0 |  | 2015-06-20 11:26 | [6 empty] | 2015-06-20 11:27 | Yes | 0
VD-9001-253(A)-DWG-062 | 4 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2015-06-20 | 2015-07-13 10:49 |  | No | 23 | 2015-08-15 11:19 | [8 empty] | No | 0
VD-9001-254-PPL-708 | 1 | GENERAL LAYOUT OF PLANT | HM-254 | AZAR AB | 2015-06-20 | 2015-07-28 12:00 | 2015-07-28 15:56 | Yes | 38 |  | 2015-08-02 16:24 | [6 empty] | 2015-08-02 16:25 | Yes | -9 | 1204-Owner-v | 2018-11-06 10:39
VD-9001-257A-INX-002 | 1 | INDEX OF QUALITY RECORD BOOK | HM-257A | ABAN AIR COOLER. | 2015-06-21 |  |  | No | 1825 | [9 empty] | No | 0
VD-9001-257A-ITP-001 | 1 | Inspection & Test Plan | HM-257A | ABAN AIR COOLER. | 2015-06-21 | 2015-07-12 14:58 |  | No | 21 | 2015-08-19 11:59 | [8 empty] | No | 0
VD-9001-257A-CAL-007 | 1 | Strength Calculation Book E-3012 | HM-257A | ABAN AIR COOLER. | 2015-06-21 | 2015-06-16 14:30 | 2015-06-16 16:41 | Yes | -5 |  | 2015-08-22 11:06 | [6 empty] | 2015-08-22 11:07 | Yes | 53
VD-9001-257A-DWG-007 | 1 | General Arrangment Drawing E-3012 | HM-257A | ABAN AIR COOLER. | 2015-06-21 | 2015-06-16 14:44 | 2015-06-16 16:44 | Yes | -5 |  | 2015-07-25 12:00 | [6 empty] | 2015-07-25 12:01 | Yes | 25
VD-9001-253(A)-DWG-032 | 4 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2015-06-21 | 2015-07-22 15:18 |  | No | 31 | 2015-08-19 10:52 | [8 empty] | No | 0
VD-9001-108-QCP-066 | 2 | QUALITY CONTROL PLAN(QCP) | PR-108 | Farabard | 2015-06-22 | 2015-06-08 14:27 | 2015-06-08 17:36 | Yes | -14 |  | 2016-01-04 10:49 | [6 empty] | 2016-01-04 20:03 | Yes | 196
VD-9001-206A-DWG-027 | 2 | TOP DAVIT DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-06-08 12:02 | 2015-06-08 15:28 | 2015-06-08 17:58 | Yes | 0 |  | 2015-08-01 11:09 | [6 empty] | 2015-08-01 11:10 | Yes | 40
VD-9001-254-PPL-700 | 1 | STEAM GENERATION PLANT PLOT PLAN (KEY PLAN) | HM-254 | AZAR AB | 2015-06-22 | 2015-06-22 14:55 | 2015-06-23 10:13 | Yes | 1 |  | 2015-07-05 12:49 | [6 empty] | 2015-07-05 12:50 | Yes | -1 | 1204-Owner-v | 2018-09-09 10:36
VD-9001-254-WMP-803 | 1 | WELDING & NDE MAP FOR WATER DRUM | HM-254 | AZAR AB | 2015-06-22 | 2015-07-14 10:20 | 2015-07-14 17:09 | Yes | 22 |  | 2015-08-04 12:21 | [6 empty] | 2015-08-04 12:22 | Yes | 7
VD-9001-254-DWH-548 | 1 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2015-06-22 | 2015-11-02 07:47 |  | No | 133 | 2015-11-25 14:55 | [8 empty] | No | 0
VD-9001-254-SPE-109 | 1 | TERMINAL POINT SPECIFICATION | HM-254 | AZAR AB | 2015-06-22 | 2015-07-11 11:16 |  | No | 19 | 2015-08-04 11:09 | [8 empty] | No | 0
VD-9001-205A-DWG-018 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-06-22 | 2015-07-16 11:00 |  | No | 24 | 2015-08-23 11:21 | [8 empty] | No | 0
VD-9001-213A-DWG-099 | 3 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-06-23 | 2015-09-12 11:40 |  | No | 81 | 2015-09-19 09:04 | [8 empty] | No | 0
VD-9001-213A-DWG-100 | 3 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-06-23 | 2015-09-12 11:40 |  | No | 81 | 2015-09-19 09:04 | [8 empty] | No | 0
VD-9001-108-PCJ-068 | 0 | PACKING , HANDLING & STORAGE PROCEDURE | PR-108 | Farabard | 2014-08-06 | 2015-06-09 10:37 | 2015-06-09 11:26 | Yes | 307 |  | 2015-07-26 17:43 | [6 empty] | 2015-07-26 17:44 | Yes | 33
VD-9001-253(A)-PCJ-104 | 1 | PAINTING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-06-23 | 2015-06-18 08:07 |  | No | -5 |  | 2015-06-23 09:54 | [7 empty] | No | 0
VD-9001-254-WPS-828 | 1 | WPS FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-06-23 | 2015-06-27 09:49 |  | No | 4 | 2015-06-30 15:56 | [8 empty] | No | 0
VD-9001-254-PQR-809 | 1 | PQR FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-06-23 | 2015-06-27 09:48 |  | No | 4 | 2015-06-30 15:50 | [8 empty] | No | 0
VD-9001-254-PFD-111 | 1 | PROCESS FLOW DIAGRAM (PFD) | HM-254 | AZAR AB | 2015-06-23 | 2015-07-20 16:55 |  | No | 27 | 2015-08-05 15:17 | [8 empty] | No | 0
VD-9001-108-DWG-019 | 4 | FOUNDATION DETAIL | PR-108 | Farabard | 2015-06-09 14:35 | 2015-06-10 09:25 |  | No | 1 | [9 empty] | No | 0
VD-9001-254-IPM-952 | 1 | GENERAL NDT PROCEDURE | HM-254 | AZAR AB | 2015-06-23 | 2015-06-15 12:11 | 2015-06-15 15:02 | Yes | -8 |  | 2015-06-27 17:19 | [6 empty] | 2015-06-27 17:20 | Yes | -2 | 1204-Owner-v | 2018-09-05 16:23
VD-9001-254-IPM-953 | 1 | HARDNESS TEST PROCEDURE | HM-254 | AZAR AB | 2015-06-23 | 2015-06-15 12:11 | 2015-06-15 15:03 | Yes | -8 |  | 2015-06-27 17:19 | [6 empty] | 2015-06-27 17:20 | Yes | -2
VD-9001-213B-DWG-034 | 3 | Name Plate for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-06-10 15:08 | 2015-07-05 10:28 | 2015-07-05 10:39 | Yes | 25 |  | 2015-07-13 15:03 | [6 empty] | 2015-07-13 15:04 | Yes | -6
VD-9001-205A-DWG-013 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-06-11 12:05 | 2015-06-14 15:13 |  | No | 3 |  | 2015-06-15 11:51 | [7 empty] | No | 0
VD-9001-257A-WPS-001 | 1 | Welding Procedure Specification (WPS) For CS | HM-257A | ABAN AIR COOLER. | 2015-06-27 | 2015-09-07 14:37 |  | No | 72 | 2015-10-28 17:31 | [8 empty] | No | 0
VD-9001-253(A)-DWG-012 | 2 | NAME PLATE for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-06-13 16:19 | 2015-06-13 16:23 |  | No | 0 |  | 2015-06-14 10:13 | [7 empty] | No | 0
VD-9001-253(A)-DWG-042 | 2 | NAME PLATE for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-06-13 16:19 | 2015-06-13 16:24 |  | No | 0 |  | 2015-06-14 10:13 | [7 empty] | No | 0
VD-9001-253(A)-DWG-072 | 2 | NAME PLATE for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-06-13 16:19 | 2015-06-13 16:24 |  | No | 0 |  | 2015-06-14 10:14 | [7 empty] | No | 0
VD-9001-108-DWG-020 | 1 | COLUMNS DEATAIL | PR-108 | Farabard | 2015-06-28 | 2015-06-18 11:12 |  | No | -10 | 2015-07-21 17:18 | [8 empty] | No | 0
VD-9001-206A-DWG-025 | 3 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-06-29 | 2015-07-05 17:26 |  | No | 6 | 2015-07-26 18:04 | [8 empty] | No | 0
VD-9001-257A-PQR-001 | 1 | Procedure Qualification Record (PQR) For CS | HM-257A | ABAN AIR COOLER. | 2015-06-30 | 2015-09-07 14:12 |  | No | 69 | 2015-10-28 17:30 | [8 empty] | No | 0
VD-9001-257A-CAL-006 | 1 | Strength Calculation Book E-3005 | HM-257A | ABAN AIR COOLER. | 2015-06-30 | 2015-07-07 17:34 |  | No | 7 | 2015-07-27 17:57 | [8 empty] | No | 0
VD-9001-257A-DWG-006 | 1 | General Arrangment Drawing E-3005 | HM-257A | ABAN AIR COOLER. | 2015-06-30 | 2015-07-07 17:41 |  | No | 7 | 2015-07-27 17:58 | [8 empty] | No | 0
VD-9001-206A-SPL-001 | 1 | SPARE PART LIST FOR COMMISIONING & START UP | PV-206A | TASHA | 2015-07-01 | 2015-07-02 11:05 |  | No | 1 | 2015-07-26 17:58 | [8 empty] | No | 0
VD-9001-206A-DWG-011 | 7 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2015-07-01 | 2015-07-05 17:23 |  | No | 4 |  | 2015-07-26 18:03 | [7 empty] | No | 0
VD-9001-254-LST-106 | 1 | UTILITY LIST | HM-254 | AZAR AB | 2015-07-01 | 2015-08-02 07:33 |  | No | 32 | 2015-09-16 12:10 | [8 empty] | No | 0 | 1204-Owner-v | 2018-12-04 15:04
VD-9001-257A-CAL-008 | 1 | Strength Calculation Book E-3013 | HM-257A | ABAN AIR COOLER. | 2015-07-01 | 2015-07-05 12:11 |  | No | 4 | 2015-07-27 18:14 | [8 empty] | No | 0
VD-9001-257A-DWG-008 | 1 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2015-07-01 | 2015-07-05 16:21 |  | No | 4 | 2015-07-27 18:15 | [8 empty] | No | 0
VD-9001-206A-DWG-009 | 2 | NAME PLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-06-18 11:33 | 2015-06-20 16:39 |  | No | 2 | 2015-07-09 10:26 | [8 empty] | No | 0
VD-9001-253(A)-DSH-016 | 1 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-07-02 | 2015-07-11 16:40 |  | No | 9 | 2015-07-20 17:40 | [8 empty] | No | 0
VD-9001-253(A)-DSH-046 | 1 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-07-02 | 2015-07-11 16:41 |  | No | 9 | 2015-07-20 17:41 | [8 empty] | No | 0
VD-9001-253(A)-DSH-076 | 1 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-07-02 | 2015-07-11 16:42 |  | No | 9 | 2015-07-20 17:42 | [8 empty] | No | 0
VD-9001-254-MNL-951 | 1 | QUALITY ASSURANCE MANUAL | HM-254 | AZAR AB | 2015-07-04 | 2015-06-22 15:06 | 2015-06-23 10:09 | Yes | -11 |  | 2015-06-28 16:58 | [6 empty] | 2015-06-28 16:59 | Yes | -8
VD-9001-213A-DWG-143 | 4 | Gauge Hatch for Tk-7201 | PV-213A | MachineSazi Pars | 2015-06-21 10:03 | 2015-06-21 15:48 | 2015-06-21 16:29 | Yes | 0 |  | 2015-06-30 09:32 | [6 empty] | 2015-06-30 09:33 | Yes | -5
VD-9001-213A-DWG-079 | 4 | Gauge Hatch for Tk-6401 | PV-213A | MachineSazi Pars | 2015-06-21 10:04 | 2015-06-21 15:47 | 2015-06-21 16:27 | Yes | 0 |  | 2015-06-30 09:31 | [6 empty] | 2015-06-30 09:32 | Yes | -5
VD-9001-205A-PCJ-061 | 1 | PACKING PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-07-05 | 2015-06-21 12:14 |  | No | -14 | 2015-09-15 09:41 | [8 empty] | No | 0
VD-9001-253(A)-CAL-020 | 3 | STRUCTURE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-07-05 | 2015-09-05 14:56 | 2015-09-05 15:52 | Yes | 62 |  | 2015-09-08 16:49 | [6 empty] | 2015-09-08 16:50 | Yes | -11 | 1204-Owner-v | 2018-06-18 15:20
VD-9001-253(A)-CAL-080 | 3 | STRUCTURE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-07-05 | 2015-07-11 16:44 | 2015-07-11 17:50 | Yes | 6 |  | 2015-08-03 10:20 | [6 empty] | 2015-08-03 10:21 | Yes | 9
VD-9001-253(A)-PCJ-098 | 2 | WELDING DOCUMENT FOR HEADER BOX | HM-253A | FATEH SANAT KIMIA | 2015-07-05 | 2015-11-08 10:10 | 2015-11-08 11:34 | Yes | 126 |  | 2015-12-26 15:31 | [6 empty] | 2015-12-26 20:03 | Yes | 34 | 1204-Owner-v | 2019-06-23 09:17
VD-9001-108-DWG-016 | 2 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-07-07 | 2015-09-23 08:22 |  | No | 78 | 2015-10-10 12:11 | [8 empty] | No | 0
VD-9001-253(A)-PCJ-099 | 2 | WELDING DOCUMENT FOR STRUCTURE | HM-253A | FATEH SANAT KIMIA | 2015-07-07 | 2015-07-06 12:41 | 2015-07-06 16:50 | Yes | -1 |  | 2015-07-15 16:13 | [6 empty] | 2015-07-15 16:14 | Yes | -5
VD-9001-108-LST-052 | 1 | LIST OF SPECIAL TOOLS AND DEVICES | PR-108 | Farabard | 2015-07-11 | 2015-11-02 12:57 | 2015-11-02 15:14 | Yes | 114 |  | 2015-11-23 16:38 | [6 empty] | 2015-11-23 16:39 | Yes | 7
VD-9001-108-LST-051 | 1 | SPARE PARTS LIST FOR 2 YEARS OF OPERATION | PR-108 | Farabard | 2015-07-11 | 2015-11-02 12:59 |  | No | 114 | 2015-11-18 17:11 | [8 empty] | No | 0
VD-9001-108-MDL-054 | 1 | GENERAL INDEX | PR-108 | Farabard | 2015-07-12 | 2015-06-30 12:57 |  | No | -12 | 2015-07-04 17:51 | [8 empty] | No | 0
VD-9001-253(A)-ITP-100 | 4 | INSPECTION TEST PLAN | HM-253A | FATEH SANAT KIMIA | 2015-07-14 | 2015-07-27 12:44 | 2015-07-27 12:51 | Yes | 13 |  | 2015-08-05 09:36 | [6 empty] | 2015-08-05 09:37 | Yes | -5 | 1204-Owner-v | 2018-05-12 17:02
VD-9001-213A-DWG-144 | 3 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-08-31 17:00 |  | No | 48 | 2015-11-08 14:15 | [8 empty] | No | 0
VD-9001-213A-DWG-119 | 3 | Water Cooling System for Tk-7101A | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-07-29 11:51 |  | No | 15 | 2015-09-19 08:47 | [8 empty] | No | 0
VD-9001-213A-DWG-120 | 3 | Water Cooling System for Tk-7101B | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-07-29 11:52 |  | No | 15 | 2015-09-19 08:48 | [8 empty] | No | 0
VD-9001-213A-PCJ-014 | 5 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-08-03 12:29 |  | No | 20 | 2015-09-05 14:15 | [8 empty] | No | 0
VD-9001-213A-DWG-095 | 3 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-10-28 15:23 |  | No | 106 | 2015-11-11 10:31 | [8 empty] | No | 0
VD-9001-213A-DWG-098 | 2 | Rim Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-07-07 11:29 |  | No | -7 | 2015-07-12 17:14 | [8 empty] | No | 0
VD-9001-213A-DWG-131 | 4 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2015-07-14 | 2015-07-14 13:53 |  | No | 0 | 2016-03-10 10:22 | 2015-07-25 09:58 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-257A-WMP-001 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-07-14 | 2015-10-07 15:53 | 2015-10-07 18:19 | Yes | 85 |  | 2015-10-29 12:21 | [6 empty] | 2015-10-29 12:22 | Yes | 8
VD-9001-257A-WMP-002 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-07-14 | 2015-10-07 15:57 | 2015-10-07 18:20 | Yes | 85 |  | 2015-10-29 12:21 | [6 empty] | 2015-10-29 12:22 | Yes | 8
VD-9001-257A-WMP-003 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-07-14 | 2015-10-07 15:58 | 2015-10-07 18:21 | Yes | 85 |  | 2015-10-29 12:22 | [6 empty] | 2015-10-29 12:23 | Yes | 8
VD-9001-254-PQR-808 | 1 | PQR FOR STEEL STACK | HM-254 | AZAR AB | 2015-07-14 | 2015-08-23 09:24 | 2015-08-23 15:12 | Yes | 40 |  | 2015-09-01 16:13 | [6 empty] | 2015-09-01 16:14 | Yes | -5
VD-9001-254-PQR-809 | 2 | PQR FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-07-14 | 2016-06-28 11:02 | 2016-06-28 11:03 | Yes | 350 |  | 2016-07-10 14:18 | [6 empty] | 2016-07-10 19:58 | Yes | -2 | 1204-Owner-v | 2018-11-06 10:38
VD-9001-254-WPS-827 | 1 | WPS FOR STEEL STACK | HM-254 | AZAR AB | 2015-07-14 | 2015-08-23 09:18 | 2015-08-23 15:13 | Yes | 40 |  | 2015-09-08 10:08 | [6 empty] | 2015-09-08 10:09 | Yes | 2 | 1204-Owner-v | 2018-09-09 10:40
VD-9001-254-WPS-828 | 2 | WPS FOR STEAM DRUM (PART I) | HM-254 | AZAR AB | 2015-07-14 | 2016-06-28 11:01 | 2016-06-28 11:02 | Yes | 350 |  | 2016-07-10 14:17 | [6 empty] | 2016-07-10 19:58 | Yes | -2
VD-9001-108-MTO-060 | 1 | MATRIAL TAKE OFF FOR PLATES AND FLANGES | PR-108 | Farabard | 2015-07-18 | 2017-10-30 13:47 | 2017-10-30 13:48 | Yes | 835 |  | 2017-11-11 10:05 | [6 empty] | 2017-11-11 19:59 | Yes | -2
VD-9001-108-MDL-054 | 2 | GENERAL INDEX | PR-108 | Farabard | 2015-07-18 | 2015-09-23 08:22 |  | No | 67 | 2015-10-18 14:09 | [8 empty] | No | 0
VD-9001-254-PCJ-800 | 1 | PAINTING SCHEDULE , METHOD& DEGREE OF SURFACE PREPARATION | HM-254 | AZAR AB | 2015-07-19 | 2015-08-23 09:24 | 2015-08-23 15:11 | Yes | 35 |  | 2015-09-08 10:08 | [6 empty] | 2015-09-08 10:09 | Yes | 2
VD-9001-213A-DWG-056 | 3 | Name Plate for Tk-2201 | PV-213A | MachineSazi Pars | 2015-07-05 16:22 | 2015-07-06 08:17 | 2015-07-06 09:58 | Yes | 1 |  | 2015-07-12 17:06 | [6 empty] | 2015-07-12 17:07 | Yes | -8
VD-9001-213A-DWG-076 | 3 | Name Plate for Tk-6401 | PV-213A | MachineSazi Pars | 2015-07-05 16:22 | 2015-07-06 08:19 | 2015-07-06 09:59 | Yes | 1 |  | 2015-07-12 17:07 | [6 empty] | 2015-07-12 17:08 | Yes | -8
VD-9001-213A-DWG-114 | 3 | Name Plate for Tk-7101A | PV-213A | MachineSazi Pars | 2015-07-05 16:23 | 2015-07-06 08:19 |  | No | 1 |  | 2015-07-12 17:07 | [7 empty] | No | 0
VD-9001-213A-DWG-115 | 3 | Name Plate for Tk-7101B | PV-213A | MachineSazi Pars | 2015-07-05 16:23 | 2015-07-06 08:20 |  | No | 1 |  | 2015-07-12 17:07 | [7 empty] | No | 0
VD-9001-213A-DWG-140 | 3 | Name Plate for Tk-7201 | PV-213A | MachineSazi Pars | 2015-07-05 16:23 | 2015-07-06 08:20 | 2015-07-06 10:01 | Yes | 1 |  | 2015-07-12 17:08 | [6 empty] | 2015-07-12 17:09 | Yes | -8
VD-9001-206A-DWG-009 | 3 | NAME PLATE DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-07-23 | 2015-07-12 16:11 | 2015-07-12 17:28 | Yes | -11 |  | 2015-07-26 17:49 | [6 empty] | 2015-07-26 17:50 | Yes | 0
VD-9001-206A-DWG-019 | 4 | NAME PLATE DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-07-23 | 2015-07-12 16:12 | 2015-07-12 17:29 | Yes | -11 |  | 2015-07-26 17:50 | [6 empty] | 2015-07-26 17:51 | Yes | 0
VD-9001-206A-DWG-029 | 4 | NAME PLATE DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-07-23 | 2015-07-12 16:12 | 2015-07-12 17:29 | Yes | -11 |  | 2015-07-26 17:50 | [6 empty] | 2015-07-26 17:51 | Yes | 0
VD-9001-213A-DWG-098 | 3 | Rim Vent for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-07-26 | 2015-07-13 10:01 | 2015-07-13 10:41 | Yes | -13 |  | 2015-07-25 09:54 | [6 empty] | 2015-07-25 09:55 | Yes | -2
VD-9001-257A-WMP-004 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-07-27 | 2016-02-16 16:25 | 2016-02-16 16:26 | Yes | 204 |  | 2016-04-17 17:31 | [6 empty] | 2016-04-17 19:59 | Yes | 47
VD-9001-257A-DWG-002 | 2 | General Arrangment Drawing E-3001 | HM-257A | ABAN AIR COOLER. | 2015-07-28 | 2015-07-17 10:34 | 2015-07-20 11:37 | Yes | -8 |  | 2015-10-06 10:21 | [6 empty] | 2015-10-06 10:22 | Yes | 67
VD-9001-257A-DWG-003 | 2 | General Arrangment Drawing E-3002 | HM-257A | ABAN AIR COOLER. | 2015-07-28 | 2015-07-27 09:17 | 2015-07-27 10:54 | Yes | -1 |  | 2015-09-05 15:38 | [6 empty] | 2015-09-05 15:39 | Yes | 26
VD-9001-213A-DWG-114 | 4 | Name Plate for Tk-7101A | PV-213A | MachineSazi Pars | 2015-07-15 08:44 | 2015-07-15 11:02 | 2015-07-15 14:25 | Yes | 0 |  | 2015-07-25 09:56 | [6 empty] | 2015-07-25 09:57 | Yes | -4
VD-9001-213A-DWG-115 | 4 | Name Plate for Tk-7101B | PV-213A | MachineSazi Pars | 2015-07-15 08:45 | 2015-07-15 11:03 | 2015-07-15 14:26 | Yes | 0 |  | 2015-07-25 09:56 | [6 empty] | 2015-07-25 09:57 | Yes | -4
VD-9001-254-SOI-950 | 1 | ITP FOR BIOLER FABRICATION | HM-254 | AZAR AB | 2015-07-29 | 2015-08-01 13:57 |  | No | 3 | 2015-08-03 15:30 | [8 empty] | No | 0
VD-9001-253(A)-DSH-026 | 2 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-07-29 | 2015-09-15 09:52 |  | No | 48 |  | 2015-09-22 15:42 | [7 empty] | No | 0
VD-9001-253(A)-DSH-056 | 2 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-07-29 | 2015-09-15 09:52 |  | No | 48 |  | 2015-09-22 15:43 | [7 empty] | No | 0
VD-9001-253(A)-DSH-086 | 2 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2015-07-29 | 2015-09-15 09:53 |  | No | 48 |  | 2015-09-22 15:43 | [7 empty] | No | 0
VD-9001-205A-DWG-016 | 5 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-07-16 08:44 | 2015-07-16 10:58 |  | No | 0 | 2015-08-23 11:20 | [8 empty] | No | 0
VD-9001-205A-DWG-017 | 5 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-07-20 11:42 | 2015-07-20 11:46 |  | No | 0 | 2015-08-23 16:21 | [8 empty] | No | 0
VD-9001-254-DWG-471 | 1 | FAB. DWG OF STEAM DRUM FOR BOILER | HM-254 | AZAR AB | 2015-08-03 | 2018-12-12 07:51 | 2018-12-12 07:52 | Yes | 1227 |  |  | 2018-12-17 10:36 | [5 empty] | 2018-12-17 10:36 | Yes | -9
VD-9001-254-DWG-472 | 1 | FAB. DWG FOR WATER DRUM | HM-254 | AZAR AB | 2015-08-03 | 2017-10-16 15:32 |  | No | 805 | 2017-10-28 11:46 | [7 empty] | 2017-10-28 19:59 | Yes | 0
VD-9001-254-CAL-731 | 1 | CALCULATION REPORT FOR STEEL STACK | HM-254 | AZAR AB | 2015-08-03 | 2015-08-05 08:55 | 2015-08-05 15:16 | Yes | 2 |  | 2015-09-16 16:25 | [6 empty] | 2015-09-16 16:26 | Yes | 28 | 1204-Owner-v | 2018-01-16 15:06
VD-9001-108-DWG-033 | 1 | DRIFT ELIMINATOR ARRANGMENT | PR-108 | Farabard | 2015-08-03 | 2015-10-04 13:31 |  | No | 62 |  | 2015-10-13 09:55 | [7 empty] | No | 0
VD-9001-253(A)-DSH-016 | 2 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-08-03 | 2015-08-01 10:03 |  | No | -2 | 2015-08-08 11:33 | [8 empty] | No | 0
VD-9001-253(A)-DSH-046 | 2 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-08-03 | 2015-08-01 10:04 |  | No | -2 | 2015-08-08 11:33 | [8 empty] | No | 0
VD-9001-253(A)-DSH-076 | 2 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-03 | 2015-08-01 10:04 |  | No | -2 | 2015-08-08 11:34 | [8 empty] | No | 0
VD-9001-206A-DWG-014 | 3 | INTERNAL ATTACHMENT DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-08-03 | 2015-08-06 12:01 | 2015-08-08 11:09 | Yes | 5 |  | 2015-08-29 15:35 | [6 empty] | 2015-08-29 15:36 | Yes | 9
VD-9001-206A-DWG-024 | 2 | INTERNAL ATTACHMENT DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-08-03 | 2015-08-06 12:00 | 2015-08-08 11:11 | Yes | 5 |  | 2015-08-29 15:35 | [6 empty] | 2015-08-29 15:36 | Yes | 9
VD-9001-108-DWG-029 | 4 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2015-08-04 | 2016-03-10 12:27 |  | No | 219 | 2016-03-14 10:19 | 2015-07-27 17:21 | [6 empty] | 2016-03-14 20:00 | Yes | 0
VD-9001-108-DWG-020 | 2 | COLUMNS DEATAIL | PR-108 | Farabard | 2015-08-04 | 2015-10-05 07:47 |  | No | 62 | 2015-10-06 11:18 | [8 empty] | No | 0
VD-9001-108-DWG-021 | 1 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2015-08-04 | 2015-07-25 14:22 |  | No | -10 |  | 2015-07-29 11:32 | [7 empty] | No | 0
VD-9001-254-SPE-801 | 1 | PAINT SPECIFICATION | HM-254 | AZAR AB | 2015-08-05 | 2018-12-17 12:01 | 2018-12-17 12:01 | Yes | 1230 |  |  | 2019-02-05 10:48 | [5 empty] | 2019-02-05 10:48 | Yes | 36
VD-9001-253(A)-LST-093 | 1 | SPARE PART LIST | HM-253A | FATEH SANAT KIMIA | 2015-08-05 | 2017-05-01 16:23 |  | No | 635 | 2017-09-02 10:43 | [7 empty] | 2017-09-02 19:57 | Yes | 0
VD-9001-257A-DWG-001 | 2 | General Arrangment Drawing E-2004 | HM-257A | ABAN AIR COOLER. | 2015-08-08 | 2015-07-27 09:12 |  | No | -12 | 2015-09-05 12:10 | [8 empty] | No | 0
VD-9001-206A-SPL-001 | 2 | SPARE PART LIST FOR COMMISIONING & START UP | PV-206A | TASHA | 2015-08-09 | 2015-08-02 16:47 | 2015-08-02 17:41 | Yes | -7 |  | 2015-08-19 10:19 | [6 empty] | 2015-08-19 10:20 | Yes | 3
VD-9001-206A-DWG-025 | 4 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-08-09 | 2015-07-29 16:08 |  | No | -11 | 2015-08-01 11:13 | [8 empty] | No | 0
VD-9001-254-DWG-473 | 1 | INSTALLATION FAB. DWG. MANHOLE COVER (STEAM DRUM) | HM-254 | AZAR AB | 2015-08-10 | 2018-12-12 07:55 | 2018-12-12 07:55 | Yes | 1220 |  |  | 2018-12-17 10:43 | [5 empty] | 2018-12-17 10:43 | Yes | -9
VD-9001-254-DWG-474 | 1 | INSTALLATION FAB. DWG. MANHOLE COVER (WATER DRUM) | HM-254 | AZAR AB | 2015-08-10 | 2018-12-12 07:58 | 2018-12-12 07:58 | Yes | 1220 |  |  | 2018-12-17 10:45 | [5 empty] | 2018-12-17 10:45 | Yes | -9
VD-9001-205A-DWG-044 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-08-10 | 2015-09-26 12:59 |  | No | 47 | 2015-10-19 17:35 | [8 empty] | No | 0
VD-9001-205A-DWG-032 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-08-10 | 2015-09-26 12:50 |  | No | 47 | 2015-10-17 14:34 | [8 empty] | No | 0
VD-9001-205A-DWG-007 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-08-10 | 2015-09-22 16:26 |  | No | 43 | 2015-10-13 10:21 | [8 empty] | No | 0
VD-9001-257A-CAL-006 | 2 | Strength Calculation Book E-3005 | HM-257A | ABAN AIR COOLER. | 2015-08-10 | 2015-08-05 15:13 | 2015-08-05 16:57 | Yes | -5 |  | 2015-09-05 12:02 | [6 empty] | 2015-09-05 12:03 | Yes | 17
VD-9001-257A-DWG-006 | 2 | General Arrangment Drawing E-3005 | HM-257A | ABAN AIR COOLER. | 2015-08-10 | 2015-08-05 15:08 | 2015-08-05 16:58 | Yes | -5 |  | 2015-09-05 12:03 | [6 empty] | 2015-09-05 12:04 | Yes | 17
VD-9001-257A-CAL-008 | 2 | Strength Calculation Book E-3013 | HM-257A | ABAN AIR COOLER. | 2015-08-10 | 2015-08-23 17:34 | 2015-08-23 17:37 | Yes | 13 |  | 2015-09-05 16:52 | [6 empty] | 2015-09-05 16:53 | Yes | -1
VD-9001-257A-DWG-008 | 2 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2015-08-10 | 2015-08-20 08:31 |  | No | 10 | 2015-09-05 16:53 | [8 empty] | No | 0
VD-9001-254-PPL-709 | 1 | GENERAL LAYOUT OF BOILER (PLAN) | HM-254 | AZAR AB | 2015-07-29 09:31 | 2015-07-29 13:58 | 2015-07-29 17:17 | Yes | 0 |  | 2015-08-02 16:14 | [6 empty] | 2015-08-02 16:15 | Yes | -10 | 1204-Owner-v | 2018-11-06 10:38
VD-9001-254-PPL-710 | 1 | GENERAL LAYOUT OF BOILER (front view) | HM-254 | AZAR AB | 2015-07-29 09:31 | 2015-07-29 13:59 | 2015-07-29 17:19 | Yes | 0 |  | 2015-08-02 16:14 | [6 empty] | 2015-08-02 16:15 | Yes | -10 | 1204-Owner-v | 2018-11-06 10:39
VD-9001-254-PPL-711 | 1 | GENERAL LAYOUT OF BOILER (side view) | HM-254 | AZAR AB | 2015-07-29 09:31 | 2015-07-29 13:59 | 2015-07-29 17:20 | Yes | 0 |  | 2015-08-02 16:15 | [6 empty] | 2015-08-02 16:16 | Yes | -10 | 1204-Owner-v | 2018-11-06 10:40
VD-9001-206A-SPL-002 | 1 | SPARE PART LIST FOR TWO YEARS OPERATION | PV-206A | TASHA | 2015-08-15 | 2015-08-02 16:47 | 2015-08-02 17:42 | Yes | -13 |  | 2015-08-19 10:19 | [6 empty] | 2015-08-19 10:20 | Yes | 3
VD-9001-206A-DWG-025 | 5 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-08-15 | 2015-08-16 13:53 | 2015-08-16 14:50 | Yes | 1 |  | 2015-08-23 11:28 | [6 empty] | 2015-08-23 11:29 | Yes | -7 | 1204-Owner-v | 2019-12-21 09:05
VD-9001-108-DWG-022 | 1 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2015-08-16 | 2015-08-09 09:29 |  | No | -7 |  | 2015-08-18 14:50 | [7 empty] | No | 0
VD-9001-108-DWG-031 | 1 | INTERNAL ARRANGMENT | PR-108 | Farabard | 2015-08-16 | 2015-10-04 13:31 |  | No | 49 |  | 2015-10-21 12:03 | [7 empty] | No | 0
VD-9001-108-DWG-034 | 1 | WATER DISTERIBUTION SYSTEM | PR-108 | Farabard | 2015-08-16 | 2015-10-04 13:32 |  | No | 49 |  | 2015-10-21 12:29 | [7 empty] | No | 0
VD-9001-108-DWG-032 | 1 | PACKING ARRENGMANT | PR-108 | Farabard | 2015-08-16 | 2015-10-04 13:31 |  | No | 49 |  | 2015-10-21 12:04 | [7 empty] | No | 0
VD-9001-108-MTO-059 | 2 | MATRIAL TAKE OFF (INTERNALS) | PR-108 | Farabard | 2015-08-17 | 2015-10-04 13:32 |  | No | 48 |  | 2015-11-22 17:56 | [7 empty] | No | 0
VD-9001-108-LST-050 | 1 | SPARE PARTS LIST FOR ERECTION AND PRECOMMISSIONING | PR-108 | Farabard | 2015-08-17 | 2015-11-02 12:57 | 2015-11-02 15:12 | Yes | 77 |  | 2015-11-23 10:14 | [6 empty] | 2015-11-23 10:15 | Yes | 7
VD-9001-254-SOI-950 | 2 | ITP FOR BIOLER FABRICATION | HM-254 | AZAR AB | 2015-08-17 | 2015-08-15 09:46 |  | No | -2 | 2015-09-20 10:55 | [8 empty] | No | 0
VD-9001-254-DWG-400 | 1 | ASS. DWG. OF STEAM DRUM 1/3 (TUBE HOLE ARRANGMENT) | HM-254 | AZAR AB | 2015-08-17 | 2015-09-16 12:10 | 2015-09-16 16:44 | Yes | 30 |  | 2016-01-04 11:02 | [6 empty] | 2016-01-04 20:03 | Yes | 96
VD-9001-254-DWG-401 | 1 | ASS. DWG. OF STEAM DRUM 2/3 | HM-254 | AZAR AB | 2015-08-17 | 2015-09-20 17:07 | 2015-09-21 10:13 | Yes | 35 |  | 2016-01-04 11:05 | [6 empty] | 2016-01-04 20:03 | Yes | 92
VD-9001-254-DWG-402 | 1 | ASS. & FAB. DWG. OF STEAM DRUM 3/3 | HM-254 | AZAR AB | 2015-08-17 | 2018-12-12 07:42 | 2018-12-12 07:42 | Yes | 1213 |  |  | 2018-12-17 10:01 | [5 empty] | 2018-12-17 10:01 | Yes | -9
VD-9001-254-DWG-404 | 1 | ASSEMBLY DWG. FOR W/D 1/2 | HM-254 | AZAR AB | 2015-08-17 | 2018-04-10 08:28 | 2018-04-10 10:13 | Yes | 967 |  |  | 2018-04-11 14:42 | [5 empty] | 2018-04-11 14:42 | Yes | -13 | 1204-Owner-v | 2019-05-14 08:22
VD-9001-254-DWG-405 | 1 | ASSEMBLY DWG. FOR W/D 2/2 | HM-254 | AZAR AB | 2015-08-17 | 2018-04-10 08:28 | 2018-04-10 10:14 | Yes | 967 |  |  | 2018-04-11 14:41 | [5 empty] | 2018-04-11 14:41 | Yes | -13 | 1204-Owner-v | 2019-05-14 08:41
VD-9001-205A-CAL-024 | 2 | MECHANICAL CALCULATION FOR INTERNALS OF T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-08-04 10:03 | 2015-08-04 10:10 | 2015-08-04 11:02 | Yes | 0 |  | 2015-10-05 16:30 | [6 empty] | 2015-10-05 16:31 | Yes | 48
VD-9001-254-SPE-109 | 2 | TERMINAL POINT SPECIFICATION | HM-254 | AZAR AB | 2015-08-18 | 2016-01-17 10:21 |  | No | 152 | 2016-02-16 15:25 | [7 empty] | 2016-02-16 20:04 | Yes | 0
VD-9001-254-PID-114 | 1 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:16 |  | No | 39 | 2015-10-18 16:33 | [8 empty] | No | 0
VD-9001-254-PID-115 | 1 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:16 |  | No | 39 | 2015-10-18 16:34 | [8 empty] | No | 0
VD-9001-254-PID-116 | 1 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:16 |  | No | 39 | 2015-10-18 16:34 | [8 empty] | No | 0
VD-9001-254-PID-117 | 1 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:16 |  | No | 39 | 2015-10-18 16:35 | [8 empty] | No | 0
VD-9001-254-PID-118 | 1 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:17 |  | No | 39 | 2015-10-18 17:46 | [8 empty] | No | 0
VD-9001-254-PID-120 | 1 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2015-08-19 | 2015-09-27 09:17 |  | No | 39 | 2015-10-18 17:47 | [8 empty] | No | 0
VD-9001-254-PFD-111 | 2 | PROCESS FLOW DIAGRAM (PFD) | HM-254 | AZAR AB | 2015-08-19 | 2016-11-05 09:28 |  | No | 444 | 2016-11-29 10:57 | [7 empty] | 2016-11-29 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-28 15:07
VD-9001-253(A)-DWG-078 | 1 | MOTOR WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-19 | 2015-10-17 16:28 |  | No | 59 | 2015-11-04 15:00 | [8 empty] | No | 0
VD-9001-253(A)-DSH-016 | 3 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-08-22 | 2016-05-04 12:07 |  | No | 256 | 2016-05-15 11:12 | [7 empty] | 2016-05-15 19:58 | Yes | 0
VD-9001-253(A)-DSH-046 | 3 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-08-22 | 2016-05-04 11:41 |  | No | 256 | 2016-05-15 11:06 | [7 empty] | 2016-05-15 19:58 | Yes | 0
VD-9001-253(A)-DSH-076 | 3 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-22 | 2016-05-04 11:41 |  | No | 256 | 2016-05-15 11:09 | [7 empty] | 2016-05-15 19:58 | Yes | 0
VD-9001-206A-PCJ-014 | 3 | Erection procedure | PV-206A | TASHA | 2015-08-26 | 2015-08-20 07:56 |  | No | -6 |  | 2015-08-29 15:42 | [7 empty] | No | 0
VD-9001-205A-DWG-022 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-08-26 | 2015-09-22 16:39 | 2015-09-22 17:45 | Yes | 27 |  | 2016-02-29 09:08 | [6 empty] | 2016-02-29 20:00 | Yes | 146
VD-9001-254-DSH-604 | 1 | BOILER DATA SHEET | HM-254 | AZAR AB | 2015-08-26 | 2015-09-07 07:46 |  | No | 12 | 2015-10-06 14:39 | [8 empty] | No | 0
VD-9001-254-PCU-601 | 1 | BOILER EXPECTED PERFORMANCE CURVES | HM-254 | AZAR AB | 2015-08-26 | 2016-02-28 14:49 |  | No | 186 | 2016-03-12 17:26 | [7 empty] | 2016-03-12 20:00 | Yes | 0
VD-9001-253(A)-DWG-062 | 5 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-29 | 2016-01-10 10:54 |  | No | 134 | 2016-02-08 16:05 | [7 empty] | 2016-02-08 20:02 | Yes | 0
VD-9001-253(A)-DWG-065 | 1 | STEEL STRUCTURE for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-29 | 2015-08-27 12:07 |  | No | -2 | 2015-09-13 15:55 | [8 empty] | No | 0
VD-9001-253(A)-DWG-071 | 1 | HEADER WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-08-29 | 2015-08-26 16:09 |  | No | -3 |  | 2015-09-13 15:51 | [7 empty] | No | 0 | 1204-Owner-v | 2018-05-16 14:19
VD-9001-253(A)-DWG-041 | 1 | HEADER WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-01 | 2015-09-12 15:02 |  | No | 11 | 2015-09-27 12:08 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-16 14:18
VD-9001-253(A)-DWG-048 | 1 | MOTOR WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-01 | 2015-09-12 15:02 |  | No | 11 | 2015-09-15 12:17 | [8 empty] | No | 0 | 1204-Owner-v | 2018-05-16 09:43
VD-9001-254-DSH-218 | 1 | DATA SHEET FOR MOTORS FOR FORCED DRAFT FANS | HM-254 | AZAR AB | 2015-09-01 | 2018-05-06 15:50 | 2018-05-06 15:51 | Yes | 978 |  |  |  | 2018-06-11 14:59 |  |  |  |  | 2018-06-11 14:59 | Yes | 22 | 1204-Owner-v | 2018-08-19 09:41
VD-9001-206A-DWG-015 | 3 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-09-02 | 2015-08-25 11:42 |  | No | -8 |  | 2015-09-05 11:34 | [7 empty] | No | 0
VD-9001-254-PPL-358 | 1 | LAYOUT & TYPICAL WIRING FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2015-09-02 | 2017-12-24 08:05 |  | No | 844 | 2018-01-14 15:45 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-254-LST-340 | 1 | BMS I/O LIST | HM-254 | AZAR AB | 2015-09-02 | 2016-06-18 11:17 |  | No | 290 | 2016-07-16 09:41 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-254-LST-342 | 1 | CONTROL SYSTEM I/O LIST | HM-254 | AZAR AB | 2015-09-02 | 2016-06-18 11:17 |  | No | 290 | 2016-07-16 09:46 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-205A-DWG-023 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-02 | 2016-01-11 09:59 |  | No | 131 | 2016-02-22 10:42 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-253(A)-DWG-032 | 5 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-02 | 2016-01-19 12:03 |  | No | 139 | 2016-02-14 08:55 | [7 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-253(A)-DWG-035 | 1 | STEEL STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-02 | 2015-09-12 15:03 |  | No | 10 | 2015-09-27 12:09 | [8 empty] | No | 0
VD-9001-257A-ITP-001 | 2 | Inspection & Test Plan | HM-257A | ABAN AIR COOLER. | 2015-09-02 | 2015-08-30 12:31 |  | No | -3 | 2015-10-06 12:08 | [8 empty] | No | 0
VD-9001-257A-WMP-005 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-09-02 | 2016-02-16 16:25 | 2016-02-16 16:26 | Yes | 167 |  | 2016-04-17 17:31 | [6 empty] | 2016-04-17 19:59 | Yes | 47
VD-9001-257A-WMP-006 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2015-09-02 | 2016-02-17 16:42 | 2016-02-17 16:43 | Yes | 168 |  | 2016-04-17 17:31 | [6 empty] | 2016-04-17 19:59 | Yes | 46
VD-9001-257A-PCJ-009 | 1 | Painting Procedure | HM-257A | ABAN AIR COOLER. | 2015-09-02 | 2015-08-23 11:58 |  | No | -10 | 2015-08-29 16:07 | [8 empty] | No | 0
VD-9001-254-SLD-210 | 1 | SINGLE LINE DIAGRAM | HM-254 | AZAR AB | 2015-09-05 | 2015-09-13 14:56 |  | No | 8 | 2015-10-18 15:50 | [8 empty] | No | 0
VD-9001-254-LST-216 | 1 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2015-09-05 | 2015-09-13 14:55 |  | No | 8 | 2015-09-26 15:56 | [8 empty] | No | 0
VD-9001-205A-DWG-016 | 6 | GENERAL ARRANGEMENT DRAWING FOR OF T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-06 | 2015-10-10 13:10 | 2015-10-10 16:49 | Yes | 34 |  | 2015-10-19 17:39 | [6 empty] | 2015-10-19 17:40 | Yes | -5
VD-9001-205A-DWG-018 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-06 | 2015-08-23 11:37 |  | No | -14 |  | 2015-09-13 16:56 | [7 empty] | No | 0
VD-9001-206A-DWG-004 | 3 | INTERNAL ATTACHMENT DRAWING ( T-3001 ) | PV-206A | TASHA | 2015-09-06 | 2015-08-25 11:40 | 2015-08-25 16:09 | Yes | -12 |  | 2015-09-05 11:33 | [6 empty] | 2015-09-05 11:34 | Yes | -3
VD-9001-108-DWG-022 | 2 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2015-08-23 14:56 | 2015-08-23 15:06 |  | No | 0 |  | 2015-08-24 17:25 | [7 empty] | No | 0
VD-9001-205A-DWG-017 | 6 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-06 | 2015-08-23 16:31 | 2015-08-23 16:46 | Yes | -14 |  | 2015-09-13 16:55 | [6 empty] | 2015-09-13 16:56 | Yes | 7
VD-9001-254-DWG-456 | 1 | ERECTION DWG. FOR NAME PLATE OF BOILER | HM-254 | AZAR AB | 2015-09-07 | 2018-04-10 08:29 | 2018-04-10 10:14 | Yes | 946 |  |  |  | 2018-04-17 17:03 |  |  |  |  | 2018-04-17 17:03 | Yes | -7
VD-9001-254-DBS-600 | 1 | BOILER DESIGN BASE DATA SHEET | HM-254 | AZAR AB | 2015-09-07 | 2015-10-26 07:17 |  | No | 49 | 2016-01-17 11:17 | [7 empty] | 2016-01-17 20:03 | Yes | 0
VD-9001-205A-DWG-031 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-09-26 12:50 |  | No | 17 | 2015-10-17 09:38 | [8 empty] | No | 0
VD-9001-205A-DWG-047 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-09-28 11:40 |  | No | 19 | 2015-11-11 10:58 | [8 empty] | No | 0
VD-9001-205A-DWG-039 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-09-23 16:38 |  | No | 14 | 2015-10-17 11:01 | [8 empty] | No | 0
VD-9001-205A-DWG-040 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-09-23 16:38 |  | No | 14 | 2015-10-17 12:01 | [8 empty] | No | 0
VD-9001-205A-DWG-001 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-09-21 16:34 |  | No | 12 | 2015-11-11 10:54 | [8 empty] | No | 0
VD-9001-205A-CAL-004 | 1 | MECHANICAL CALCULATION FOR INTERNALS OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-09 | 2015-12-20 11:11 | 2015-12-20 15:32 | Yes | 102 |  | 2015-12-24 13:06 | [6 empty] | 2015-12-24 20:03 | Yes | -10
VD-9001-257A-PCJ-009 | 2 | Painting Procedure | HM-257A | ABAN AIR COOLER. | 2015-09-12 | 2016-02-03 12:20 | 2016-02-03 12:21 | Yes | 144 |  | 2016-02-16 15:58 | [6 empty] | 2016-02-16 20:04 | Yes | -1
VD-9001-253(A)-DWG-010 | 1 | LADDER for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-09-14 | 2015-09-15 15:25 | 2015-09-15 17:13 | Yes | 1 |  | 2015-09-16 15:12 | [6 empty] | 2015-09-16 15:13 | Yes | -13 | 1204-Owner-v | 2019-02-14 10:35
VD-9001-253(A)-DWG-040 | 1 | LADDER for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-14 | 2015-09-15 15:26 | 2015-09-15 17:14 | Yes | 1 |  | 2015-09-16 15:12 | [6 empty] | 2015-09-16 15:13 | Yes | -13 | 1204-Owner-v | 2018-08-14 17:37
VD-9001-253(A)-DWG-070 | 1 | LADDER for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-09-14 | 2015-09-15 15:26 | 2015-09-15 17:14 | Yes | 1 |  | 2015-09-16 15:13 | [6 empty] | 2015-09-16 15:14 | Yes | -13 | 1204-Owner-v | 2018-08-14 17:51
VD-9001-206A-WMP-001 | 3 | WELDING MAP & NDT TABLE | PV-206A | TASHA | 2015-09-01 11:20 | 2015-09-01 12:13 |  | No | 0 | 2015-09-08 10:11 | [8 empty] | No | 0
VD-9001-213A-DWG-128 | 3 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-09-02 09:48 | 2015-09-02 10:24 |  | No | 0 | 2015-09-13 15:41 | [8 empty] | No | 0
VD-9001-254-DPH-345 | 1 | CONTROL SYSTEM ARCHITECTURE | HM-254 | AZAR AB | 2015-09-16 | 2017-12-24 07:43 |  | No | 830 | 2018-01-14 15:49 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-254-LGD-343 | 1 | COLOR CODING FOR GRAPHIC SYMBOLE | HM-254 | AZAR AB | 2015-09-16 | 2017-12-24 07:49 | 2017-12-24 07:50 | Yes | 830 |  | 2018-01-14 15:47 | [6 empty] | 2018-01-14 19:59 | Yes | 7
VD-9001-254-DSH-562 | 1 | DATA SHEET FOR DESUPERHEATER & SPRAY WATER CONTROL VALVE | HM-254 | AZAR AB | 2015-09-16 | 2016-06-01 16:15 |  | No | 259 | 2016-08-14 14:35 | [7 empty] | 2016-08-14 19:57 | Yes | 0 | 1204-Owner-v | 2018-05-28 12:14
VD-9001-257A-DWG-001 | 3 | General Arrangment Drawing E-2004 | HM-257A | ABAN AIR COOLER. | 2015-09-19 | 2015-09-06 13:02 | 2015-09-06 14:59 | Yes | -13 |  | 2015-09-06 17:59 | [6 empty] | 2015-09-06 18:00 | Yes | -14
VD-9001-213A-PCJ-014 | 6 | Roof structure Erection Procedure for Tk-6401 | PV-213A | MachineSazi Pars | 2015-09-19 | 2016-01-03 16:08 | 2016-01-03 16:09 | Yes | 106 |  | 2016-01-25 19:20 | [6 empty] | 2016-01-25 20:02 | Yes | 8
VD-9001-213A-DWG-057 | 1 | Pipe Support for Tk-2201 | PV-213A | MachineSazi Pars | 2015-09-19 | 2015-09-13 11:13 | 2015-09-13 14:44 | Yes | -6 |  | 2015-09-30 11:55 | [6 empty] | 2015-09-30 11:56 | Yes | 3
VD-9001-213A-DWG-116 | 1 | Pipe Support for Tk-7101A | PV-213A | MachineSazi Pars | 2015-09-19 | 2015-09-13 11:14 | 2015-09-13 14:46 | Yes | -6 |  | 2015-09-30 11:57 | [6 empty] | 2015-09-30 11:58 | Yes | 3
VD-9001-213A-DWG-117 | 1 | Pipe Support for Tk-7101B | PV-213A | MachineSazi Pars | 2015-09-19 | 2015-09-13 11:14 | 2015-09-13 14:47 | Yes | -6 |  | 2015-09-30 11:58 | [6 empty] | 2015-09-30 11:59 | Yes | 3
VD-9001-213A-DWG-077 | 1 | Pipe Support for Tk-6401 | PV-213A | MachineSazi Pars | 2015-09-19 | 2015-09-13 11:13 |  | No | -6 | 2015-09-30 11:57 | [8 empty] | No | 0
VD-9001-213A-DWG-141 | 1 | Pipe Support for Tk-7201 | PV-213A | MachineSazi Pars | 2015-09-19 | 2015-09-13 11:14 |  | No | -6 | 2015-09-30 11:59 | [8 empty] | No | 0
VD-9001-257A-DWG-008 | 3 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2015-09-19 | 2015-09-07 12:41 |  | No | -12 |  | 2015-10-06 16:47 | [7 empty] | No | 0
VD-9001-213B-DWG-035 | 1 | Pipe Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-09-20 | 2015-09-13 11:15 |  | No | -7 | 2015-09-20 10:37 | [8 empty] | No | 0
VD-9001-204A-CAL-010 | 0 | Strength Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-16 10:25 |  | No | 25 | 2015-10-21 17:34 | [8 empty] | No | 0
VD-9001-204A-DWG-011 | 0 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-16 21:20 |  | No | -5 | 2015-09-27 10:48 | [8 empty] | No | 0
VD-9001-204A-DWG-012 | 0 | Nozzle Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-31 23:58 |  | No | 140 | 2016-05-02 15:46 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-013 | 0 | Name Plate Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:14 |  | No | 146 | 2016-05-02 16:09 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-014 | 0 | PF & LD Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-08 17:31 |  | No | 270 | 2016-09-27 12:11 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204A-DWG-015 | 0 | PF & LD Arrangement FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-05-16 12:06 |  | No | 186 | 2016-05-31 11:51 | [7 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-204A-DWG-016 | 0 | External Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:39 |  | No | 138 | 2016-05-01 16:14 | [7 empty] | 2016-05-01 19:59 | Yes | 0
VD-9001-204A-DWG-017 | 0 | Internal Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-07-10 13:40 |  | No | 241 | 2016-07-24 14:59 | [7 empty] | 2016-07-24 19:57 | Yes | 0
VD-9001-204A-DWG-018 | 0 | Template & Gauge Plate FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:08 |  | No | 147 | 2016-05-16 11:54 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-CAL-019 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0110 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-020 | 0 | Strength Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-06 17:42 |  | No | 45 | 2015-10-27 14:24 | [8 empty] | No | 0
VD-9001-204A-DWG-021 | 0 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-06 17:42 |  | No | 15 | 2015-10-27 14:25 | [8 empty] | No | 0
VD-9001-204A-DWG-022 | 0 | Nozzle Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:11 |  | No | 147 | 2016-05-17 11:58 | [7 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204A-DWG-023 | 0 | Name Plate Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:15 |  | No | 146 | 2016-05-03 17:27 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-024 | 0 | PF & LD Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-18 12:25 |  | No | 280 | 2016-10-04 11:13 | [7 empty] | 2016-10-04 18:56 | Yes | 0
VD-9001-204A-DWG-025 | 0 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-08 16:08 |  | No | 209 | 2016-06-19 15:34 | [7 empty] | 2016-06-19 19:58 | Yes | 0
VD-9001-204A-DWG-026 | 0 | External Attachment Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:12 |  | No | 147 | 2016-05-08 16:48 | [7 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-204A-DWG-027 | 0 | Internal Attachment Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-23 12:56 | 2016-06-23 12:57 | Yes | 224 |  | 2016-07-25 17:07 | [6 empty] | 2016-07-25 19:58 | Yes | 18 | 1204-Owner-v | 2019-07-09 12:11
VD-9001-204A-DWG-028 | 0 | Template & Gauge Plate FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-029 | 0 | Lifting Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2017-03-12 10:09 |  | No | 486 |  | 2017-05-17 11:33 | [6 empty] | 2017-05-17 20:00 | Yes | 0
VD-9001-204A-CAL-0210 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-030 | 0 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-17 16:20 |  | No | 26 | 2015-11-03 11:21 | [8 empty] | No | 0
VD-9001-204A-DWG-031 | 0 | General Arrangement Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-17 16:22 |  | No | -4 | 2015-11-03 11:21 | [8 empty] | No | 0
VD-9001-204A-DWG-032 | 0 | Nozzle Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-15 08:28 |  | No | 95 | 2016-02-20 09:51 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-204A-DWG-033 | 0 | Name Plate Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-14 17:04 |  | No | 94 | 2016-02-15 10:14 | [7 empty] | 2016-02-15 20:04 | Yes | 0
VD-9001-204A-DWG-034 | 0 | PF & LD Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-035 | 0 | PF & LD Arrangement FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-036 | 0 | External Attachment Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-037 | 0 | Internal Attachment Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-038 | 0 | Template & Gauge Plate FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-039 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0310 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-040 | 0 | Strength Calculation FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-28 20:27 |  | No | 37 | 2015-10-26 14:11 | [8 empty] | No | 0
VD-9001-204A-DWG-041 | 0 | General Arrangement Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-28 20:31 |  | No | 7 | 2015-10-26 14:11 | [8 empty] | No | 0
VD-9001-204A-DWG-042 | 0 | Nozzle Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-31 23:59 |  | No | 140 | 2016-05-03 11:52 | 2016-05-03 11:52 | [6 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-043 | 0 | Name Plate Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:17 |  | No | 146 | 2016-05-03 09:24 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-044 | 0 | PF & LD Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-16 18:13 |  | No | 278 | 2016-10-02 11:47 | [7 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-204A-DWG-045 | 0 | PF & LD Arrangement FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-19 14:36 |  | No | 220 | 2016-07-04 16:24 | [7 empty] | 2016-07-04 19:58 | Yes | 0
VD-9001-204A-DWG-046 | 0 | External Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:13 |  | No | 147 | 2016-04-20 10:22 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-204A-DWG-047 | 0 | Internal Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-048 | 0 | Template & Gauge Plate FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-049 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0410 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-050 | 0 | Strength Calculation FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-17 16:18 |  | No | 26 | 2015-10-04 17:11 | [8 empty] | No | 0
VD-9001-204A-DWG-051 | 0 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-17 16:23 |  | No | -4 | 2015-09-27 10:58 | [8 empty] | No | 0
VD-9001-204A-DWG-052 | 0 | Nozzle Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:40 |  | No | 138 | 2016-05-03 15:00 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-053 | 0 | Name Plate Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:18 |  | No | 146 |  | 2016-04-30 15:32 | [6 empty] | 2016-04-30 19:59 | Yes | 0
VD-9001-204A-DWG-054 | 0 | PF & LD Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-055 | 0 | PF & LD Arrangement FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-056 | 0 | External Attachment Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-057 | 0 | Internal Attachment Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-28 08:32 |  | No | 137 | 2016-04-11 09:09 | [7 empty] | 2016-04-11 19:59 | Yes | 0
VD-9001-204A-DWG-058 | 0 | Template & Gauge Plate FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-059 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0510 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-060 | 0 | Strength Calculation FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-28 20:26 |  | No | 37 | 2015-10-14 14:42 | [8 empty] | No | 0
VD-9001-204A-DWG-061 | 0 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-28 20:30 |  | No | 7 | 2015-10-17 10:24 | [8 empty] | No | 0
VD-9001-204A-DWG-062 | 0 | Nozzle Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:41 |  | No | 138 |  | 2016-05-03 15:03 | [6 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-063 | 0 | Name Plate Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:18 |  | No | 146 | 2016-05-03 15:59 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-064 | 0 | PF & LD Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-21 12:56 |  | No | 161 | 2016-05-16 15:21 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-065 | 0 | PF & LD Arrangement FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-21 12:56 |  | No | 161 | 2016-05-16 15:19 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-066 | 0 | External Attachment Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:14 |  | No | 147 | 2016-04-20 10:16 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-204A-DWG-067 | 0 | Internal Attachment Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-068 | 0 | Template & Gauge Plate FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-069 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0610 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-070 | 0 | Strength Calculation FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-28 20:28 |  | No | 37 | 2015-10-14 09:41 | [8 empty] | No | 0
VD-9001-204A-DWG-071 | 0 | General Arrangement Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-28 20:31 |  | No | 7 | 2015-10-17 11:31 | [8 empty] | No | 0
VD-9001-204A-DWG-072 | 0 | Nozzle Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:42 |  | No | 138 | 2016-05-01 10:51 | [7 empty] | 2016-05-01 19:59 | Yes | 0
VD-9001-204A-DWG-073 | 0 | Name Plate Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:19 |  | No | 146 | 2016-05-01 10:30 | [7 empty] | 2016-05-01 19:59 | Yes | 0
VD-9001-204A-DWG-074 | 0 | PF & LD Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:57 |  | No | 146 | 2016-05-16 14:38 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-075 | 0 | PF & LD Arrangement FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:57 |  | No | 146 | 2016-05-16 14:34 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-076 | 0 | External Attachment Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:15 |  | No | 147 | 2016-04-20 10:06 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-204A-DWG-077 | 0 | Internal Attachment Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-078 | 0 | Template & Gauge Plate FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-079 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0710 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-080 | 0 | Strength Calculation FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-16 10:26 |  | No | 25 | 2015-10-05 12:39 | [8 empty] | No | 0
VD-9001-204A-DWG-081 | 0 | General Arrangement Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-16 21:21 |  | No | -5 | 2015-10-25 12:46 | [8 empty] | No | 0
VD-9001-204A-DWG-082 | 0 | Nozzle Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:43 |  | No | 138 |  | 2016-05-03 15:05 | [6 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-083 | 0 | Name Plate Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:19 |  | No | 146 | 2016-05-03 16:25 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-084 | 0 | PF & LD Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-085 | 0 | PF & LD Arrangement FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-086 | 0 | External Attachment Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:16 |  | No | 147 | 2016-04-20 10:03 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-204A-DWG-087 | 0 | Internal Attachment Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-088 | 0 | Template & Gauge Plate FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-089 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0810 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-090 | 0 | Strength Calculation FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-06 17:44 |  | No | 45 | 2015-11-28 14:39 | [8 empty] | No | 0
VD-9001-204A-DWG-091 | 0 | General Arrangement Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-06 18:00 |  | No | 15 | 2015-11-28 14:40 | [8 empty] | No | 0
VD-9001-204A-DWG-092 | 0 | Nozzle Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-30 13:59 |  | No | 139 | 2016-05-02 11:42 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-093 | 0 | Name Plate Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:20 |  | No | 146 | 2016-05-03 16:30 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-094 | 0 | PF & LD Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-16 18:14 |  | No | 278 | 2016-09-05 12:11 | [7 empty] | 2016-09-05 19:56 | Yes | 0
VD-9001-204A-DWG-095 | 0 | PF & LD Arrangement FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-13 09:53 |  | No | 214 | 2016-06-19 15:39 | [7 empty] | 2016-06-19 19:58 | Yes | 0
VD-9001-204A-DWG-096 | 0 | External Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-02 17:37 |  | No | 142 | 2016-05-03 17:18 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-097 | 0 | Internal Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-098 | 0 | Template & Gauge Plate FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-099 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-0910 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-100 | 0 | Strength Calculation FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-06 17:45 |  | No | 45 | 2015-12-08 15:09 | [8 empty] | No | 0
VD-9001-204A-DWG-101 | 0 | General Arrangement Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-06 18:01 |  | No | 15 | 2015-12-07 14:16 | [8 empty] | No | 0
VD-9001-204A-DWG-102 | 0 | Nozzle Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:44 |  | No | 138 |  | 2016-05-03 15:07 | [6 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-103 | 0 | Name Plate Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:21 |  | No | 146 | 2016-05-01 16:59 | [7 empty] | 2016-05-01 19:59 | Yes | 0
VD-9001-204A-DWG-104 | 0 | PF & LD Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-21 12:29 |  | No | 283 | 2016-10-02 10:04 | [7 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-204A-DWG-105 | 0 | PF & LD Arrangement FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-05-26 08:41 |  | No | 196 | 2016-06-05 11:43 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-204A-DWG-106 | 0 | External Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:38 |  | No | 138 | 2016-04-11 09:21 | [7 empty] | 2016-04-11 19:59 | Yes | 0
VD-9001-204A-DWG-107 | 0 | Internal Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-108 | 0 | Template & Gauge Plate FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:09 |  | No | 147 | 2016-05-16 12:00 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-CAL-109 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1010 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-110 | 0 | Strength Calculation FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-17 16:19 |  | No | 26 | 2015-11-23 16:14 | [8 empty] | No | 0
VD-9001-204A-DWG-111 | 0 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-17 16:21 |  | No | -4 | 2015-11-23 16:33 | [8 empty] | No | 0
VD-9001-204A-DWG-112 | 0 | Nozzle Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-30 14:11 |  | No | 139 | 2016-05-02 17:20 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-113 | 0 | Name Plate Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:21 |  | No | 146 | 2016-05-02 17:08 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-114 | 0 | PF & LD Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-21 12:26 |  | No | 283 | 2016-10-05 09:01 | [7 empty] | 2016-10-05 18:55 | Yes | 0
VD-9001-204A-DWG-115 | 0 | PF & LD Arrangement FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-16 08:22 |  | No | 217 | 2016-07-04 16:18 | [7 empty] | 2016-07-04 19:58 | Yes | 0
VD-9001-204A-DWG-116 | 0 | External Attachment Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-02 11:21 |  | No | 142 |  | 2016-05-08 15:08 | [6 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-204A-DWG-117 | 0 | Internal Attachment Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-118 | 0 | Template & Gauge Plate FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:10 |  | No | 147 | 2016-05-16 12:11 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-CAL-119 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1110 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-120 | 0 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-14 14:27 |  | No | 53 | 2015-12-08 14:08 | [8 empty] | No | 0
VD-9001-204A-DWG-121 | 0 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-14 14:48 |  | No | 23 | 2015-12-08 14:09 | [8 empty] | No | 0
VD-9001-204A-DWG-122 | 0 | Nozzle Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-01 |  | No | 140 | 2016-05-03 15:38 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-123 | 0 | Name Plate Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:22 |  | No | 146 | 2016-05-03 15:53 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-124 | 0 | PF & LD Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-23 14:13 |  | No | 285 | 2016-10-05 15:10 | [7 empty] | 2016-10-05 18:56 | Yes | 0
VD-9001-204A-DWG-125 | 0 | PF & LD Arrangement FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-16 10:03 |  | No | 217 | 2016-07-04 16:21 | [7 empty] | 2016-07-04 19:58 | Yes | 0
VD-9001-204A-DWG-126 | 0 | External Attachment Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-127 | 0 | Internal Attachment Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-128 | 0 | Template & Gauge Plate FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-07 14:10 |  | No | 147 | 2016-05-16 12:22 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-CAL-129 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1210 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-130 | 0 | Strength Calculation FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-14 14:28 |  | No | 53 | 2015-11-11 10:43 | [8 empty] | No | 0
VD-9001-204A-DWG-131 | 0 | General Arrangement Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-14 14:51 |  | No | 23 | 2015-11-11 10:44 | [8 empty] | No | 0
VD-9001-204A-DWG-132 | 0 | Nozzle Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-10 10:22 |  | No | 150 | 2016-05-17 10:57 | [7 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204A-DWG-133 | 0 | Name Plate Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:26 |  | No | 146 | 2016-05-03 17:36 | [7 empty] | 2016-05-03 19:59 | Yes | 0
VD-9001-204A-DWG-134 | 0 | PF & LD Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-08-23 14:14 |  | No | 285 | 2016-10-05 14:45 | [7 empty] | 2016-10-05 18:56 | Yes | 0
VD-9001-204A-DWG-135 | 0 | PF & LD Arrangement FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-18 14:18 |  | No | 219 | 2016-06-28 15:45 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-204A-DWG-136 | 0 | External Attachment Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-06-23 11:57 |  | No | 224 | 2016-07-05 15:19 | [7 empty] | 2016-07-05 19:58 | Yes | 0
VD-9001-204A-DWG-137 | 0 | Internal Attachment Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-138 | 0 | Template & Gauge Plate FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-10 08:32 |  | No | 150 | 2016-05-16 14:16 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-CAL-139 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1310 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-140 | 0 | Strength Calculation FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-14 14:29 |  | No | 53 | 2015-11-04 11:39 | [8 empty] | No | 0
VD-9001-204A-DWG-141 | 0 | General Arrangement Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-14 15:53 |  | No | 23 | 2015-11-04 11:40 | [8 empty] | No | 0
VD-9001-204A-DWG-142 | 0 | Nozzle Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-10 16:25 |  | No | 90 | 2016-02-21 12:18 | [7 empty] | 2016-02-21 20:00 | Yes | 0
VD-9001-204A-DWG-143 | 0 | Name Plate Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-14 17:05 |  | No | 94 | 2016-02-16 13:39 | [7 empty] | 2016-02-16 20:04 | Yes | 0
VD-9001-204A-DWG-144 | 0 | PF & LD Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-08 10:31 |  | No | 88 | 2016-02-17 16:00 | [7 empty] | 2016-02-17 20:02 | Yes | 0
VD-9001-204A-DWG-145 | 0 | PF & LD Arrangement FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-08 10:35 |  | No | 88 | 2016-02-10 09:01 | [7 empty] | 2016-02-10 20:04 | Yes | 0
VD-9001-204A-DWG-146 | 0 | External Attachment Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-147 | 0 | Internal Attachment Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-148 | 0 | Template & Gauge Plate FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-149 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1410 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-150 | 0 | Strength Calculation FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-10-06 17:47 |  | No | 45 | 2015-10-31 14:10 | [8 empty] | No | 0
VD-9001-204A-DWG-151 | 0 | General Arrangement Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-10-06 18:01 |  | No | 15 | 2015-10-31 14:11 | [8 empty] | No | 0
VD-9001-204A-DWG-152 | 0 | Nozzle Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-15 14:19 |  | No | 95 | 2016-02-17 17:47 | [7 empty] | 2016-02-17 20:02 | Yes | 0
VD-9001-204A-DWG-153 | 0 | Name Plate Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-14 17:06 |  | No | 94 | 2016-02-20 10:20 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-204A-DWG-154 | 0 | PF & LD Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-10 10:12 |  | No | 90 | 2016-02-20 10:12 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-204A-DWG-155 | 0 | PF & LD Arrangement FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-02-10 10:11 |  | No | 90 | 2016-02-13 12:38 | [7 empty] | 2016-02-13 20:04 | Yes | 0
VD-9001-204A-DWG-156 | 0 | External Attachment Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-157 | 0 | Internal Attachment Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-158 | 0 | Template & Gauge Plate FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-159 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1510 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-160 | 0 | Strength Calculation FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-16 10:27 |  | No | 25 | 2015-11-08 10:28 | [8 empty] | No | 0
VD-9001-204A-DWG-161 | 0 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-16 21:22 |  | No | -5 | 2015-12-07 15:12 | [8 empty] | No | 0
VD-9001-204A-DWG-162 | 0 | Nozzle Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-02 11:07 |  | No | 142 | 2016-05-04 17:25 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204A-DWG-163 | 0 | Name Plate Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:27 |  | No | 146 | 2016-05-04 16:48 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204A-DWG-164 | 0 | PF & LD Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-165 | 0 | PF & LD Arrangement FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-166 | 0 | External Attachment Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-167 | 0 | Internal Attachment Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-168 | 0 | Template & Gauge Plate FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-169 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1610 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-170 | 0 | Strength Calculation FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-08-22 | 2015-09-28 20:25 |  | No | 37 | 2015-10-21 16:34 | [8 empty] | No | 0
VD-9001-204A-DWG-171 | 0 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-09-21 | 2015-09-28 20:29 |  | No | 7 | 2015-10-21 16:34 | [8 empty] | No | 0
VD-9001-204A-DWG-172 | 0 | Nozzle Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-29 14:45 |  | No | 138 | 2016-05-02 14:50 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-173 | 0 | Name Plate Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-06 15:28 |  | No | 146 | 2016-05-02 15:00 | [7 empty] | 2016-05-02 19:59 | Yes | 0
VD-9001-204A-DWG-174 | 0 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-28 07:23 |  | No | 168 | 2016-05-17 15:27 | [7 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204A-DWG-175 | 0 | PF & LD Arrangement FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-04-28 07:22 |  | No | 168 | 2016-05-17 14:48 | [7 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204A-DWG-176 | 0 | External Attachment Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 | 2016-03-28 13:38 |  | No | 137 | 2016-04-11 09:16 | [7 empty] | 2016-04-11 19:59 | Yes | 0
VD-9001-204A-DWG-177 | 0 | Internal Attachment Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-DWG-178 | 0 | Template & Gauge Plate FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-179 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-CAL-1710 | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2015-11-12 |  |  | No | 1681 | [9 empty] | No | 0
VD-9001-204A-QCP-001 | 0 | Quality Control Plan (QCP) | PV-204A | Asas Sanat Pars Inc. | 2015-09-10 | 2015-09-15 13:38 |  | No | 5 | 2015-11-18 17:23 | [8 empty] | No | 0
VD-9001-204A-WBK-001 | 0 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2015-11-21 13:18 |  | No | 47 | 2015-12-07 09:30 | [8 empty] | No | 0
VD-9001-204A-WPQ-001 | 0 | Welder Performance Qualification(WPQ) | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2015-10-10 16:24 | 2015-10-10 16:56 | Yes | 5 |  | 2015-10-26 11:25 | [6 empty] | 2015-10-26 11:26 | Yes | 2
VD-9001-204A-PCJ-001 | 0 | Magnetic Particle Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-17 | 2015-09-17 12:04 |  | No | 0 | 2015-10-10 09:19 | [8 empty] | No | 0
VD-9001-204A-PCJ-002 | 0 | Liquid Penetration Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-17 | 2015-09-17 12:04 |  | No | 0 | 2015-10-10 09:20 | [8 empty] | No | 0
VD-9001-204A-PCJ-003 | 0 | Ultrasonic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-17 | 2015-09-17 12:05 |  | No | 0 | 2015-10-21 16:27 | [8 empty] | No | 0
VD-9001-204A-PCJ-004 | 0 | Radiography Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-17 | 2015-09-17 12:06 |  | No | 0 | 2015-10-05 11:35 | [8 empty] | No | 0
VD-9001-204A-PCJ-005 | 0 | Post Weld Heat Treatment Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-30 | 2015-09-30 13:36 |  | No | 0 |  | 2015-10-10 11:32 | [7 empty] | No | 0
VD-9001-204A-PCJ-006 | 0 | Hardness Test Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-30 | 2015-09-30 13:35 |  | No | 0 | 2015-10-10 10:00 | [8 empty] | No | 0
VD-9001-204A-PCJ-007 | 0 | Hydrostatic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2015-10-11 08:59 |  | No | 6 | 2015-12-20 08:50 | [8 empty] | No | 0
VD-9001-204A-PCJ-008 | 0 | leak test Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-09-17 | 2015-09-17 12:07 |  | No | 0 | 2015-10-05 11:36 | [8 empty] | No | 0
VD-9001-204A-PCJ-009 | 0 | Welding Repair Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2015-10-10 16:26 | 2015-10-10 16:58 | Yes | 5 |  | 2015-12-14 14:08 | [6 empty] | 2015-12-14 14:09 | Yes | 51
VD-9001-204A-PCJ-010 | 0 | Painting Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2016-02-29 10:03 |  | No | 147 | 2016-04-04 15:35 | [7 empty] | 2016-04-04 20:00 | Yes | 0
VD-9001-204A-PCJ-011 | 0 | Packing, Marking & Shipping Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-05 | 2016-03-06 11:58 | 2016-03-06 11:59 | Yes | 153 |  | 2016-04-10 10:18 | [6 empty] | 2016-04-10 19:59 | Yes | 21
VD-9001-204A-PCJ-012 | 0 | Erection Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-03-20 |  |  | No | 1552 | [9 empty] | No | 0
VD-9001-204A-QAM-001 | 0 | Quality Management System Manual | PV-204A | Asas Sanat Pars Inc. | 2016-03-20 |  |  | No | 1552 | [9 empty] | No | 0
VD-9001-204A-SPL-001 | 0 | Spare Part List for Eriction / Pre Commissioning / Start up & Two Years | PV-204A | Asas Sanat Pars Inc. | 2015-12-29 | 2016-08-07 08:53 |  | No | 222 |  | 2016-09-05 16:29 | [6 empty] | 2016-09-05 19:56 | Yes | 0
VD-9001-204A-INX-001 | 0 | Fiinal Vendor Data Book Index | PV-204A | Asas Sanat Pars Inc. | 2016-08-10 | 2017-12-04 08:40 |  | No | 481 | 2017-12-04 09:05 | [7 empty] | 2017-12-04 20:00 | Yes | 0
VD-9001-204A-VDB-001 | 0 | Fiinal Vendor Data Book | PV-204A | Asas Sanat Pars Inc. | 2016-09-10 |  |  | No | 1378 | [9 empty] | No | 0
VD-9001-204A- | 0 | Reserved | PV-204A | Asas Sanat Pars Inc. | 2016-09-10 |  |  | No | 1378 | [9 empty] | No | 0
VD-9001-204A-SVL-001 | 0 | Sub Vendor List | PV-204A | Asas Sanat Pars Inc. | 2015-09-10 | 2015-09-16 09:50 |  | No | 6 | 2015-12-08 15:05 | [8 empty] | No | 0
VD-9001-254-DWG-440 | 1 | INSTALLATION & FABRICATION FOR ECO. TUBE SHEET | HM-254 | AZAR AB | 2015-09-06 17:01 | 2015-09-07 07:41 |  | No | 1 |  | 2015-10-13 14:23 | [7 empty] | No | 0
VD-9001-254-DSH-563 | 1 | DATA SHEET FOR MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2015-09-22 | 2016-05-10 07:19 |  | No | 231 | 2016-06-18 16:36 | [7 empty] | 2016-06-18 19:57 | Yes | 0
VD-9001-254-DSH-565 | 1 | DATA SHEET FOR PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2015-09-22 | 2017-12-04 10:54 |  | No | 804 | 2018-02-06 14:19 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-05-28 12:16
VD-9001-206A-WMP-001 | 4 | WELDING MAP & NDT TABLE | PV-206A | TASHA | 2015-09-22 | 2015-09-30 18:34 | 2015-10-01 11:52 | Yes | 9 |  | 2015-10-17 12:12 | [6 empty] | 2015-10-17 12:13 | Yes | 3
VD-9001-213A-DWG-134 | 3 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2015-09-22 | 2015-09-12 10:59 |  | No | -10 |  | 2015-09-30 11:49 | [7 empty] | No | 0
VD-9001-254-PPL-359 | 1 | LAYOUT & TYPICAL WIRING FOR BMS | HM-254 | AZAR AB | 2015-09-22 | 2017-12-24 13:38 |  | No | 824 | 2018-01-14 15:53 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-254-PPL-360 | 1 | LAYOUT & TYPICAL WIRING FOR LBSP | HM-254 | AZAR AB | 2015-09-22 | 2017-12-24 13:41 |  | No | 824 | 2018-01-14 15:56 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-254-DWH-586 | 0 | DRAIN LIST AND LOCATION | HM-254 | AZAR AB | 2015-09-10 | 2015-09-09 08:27 |  | No | -1 | 2015-11-01 11:01 | [8 empty] | No | 0
VD-9001-254-PCJ-466 | 1 | HYDROSTATIC TEST PROCEDURE FOR BOILER AT SITE | HM-254 | AZAR AB | 2015-09-22 | 2015-09-16 12:11 |  | No | -6 | 2015-10-06 16:39 | [8 empty] | No | 0
VD-9001-213A-DWG-128 | 4 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-09-27 | 2015-09-30 15:37 |  | No | 3 | 2015-11-11 10:24 | [8 empty] | No | 0
VD-9001-253(A)-DWG-065 | 2 | STEEL STRUCTURE for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-09-27 | 2015-10-10 16:52 | 2015-10-10 17:04 | Yes | 13 |  | 2016-05-14 15:21 | [6 empty] | 2016-05-14 19:58 | Yes | 203 | 1204-Owner-v | 2018-06-18 15:47
VD-9001-205A-DWG-035 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-27 | 2015-12-22 16:40 |  | No | 86 | 2016-01-10 15:53 | [7 empty] | 2016-01-10 20:03 | Yes | 0
VD-9001-205A-DWG-036 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-27 | 2015-12-22 16:40 | 2015-12-23 09:32 | Yes | 87 |  | 2015-12-24 13:24 | [6 empty] | 2015-12-24 20:03 | Yes | -12
VD-9001-205A-DWG-037 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-27 | 2015-12-22 16:41 |  | No | 86 | 2015-12-28 16:47 | [7 empty] | 2015-12-28 20:03 | Yes | 0
VD-9001-254-PPL-701 | 1 | GENERAL ARRANGEMENT OF COLUMN BASE | HM-254 | AZAR AB | 2015-09-27 | 2018-08-27 14:59 | 2018-08-27 14:59 | Yes | 1065 |  |  |  | 2018-12-23 15:42 |  |  |  |  | 2018-12-23 15:42 | Yes | 104 | 1204-Owner-v | 2018-09-09 10:37
VD-9001-254-PCJ-465 | 1 | LEAK TEST PROCEDURE | HM-254 | AZAR AB | 2015-09-28 | 2017-10-16 15:43 |  | No | 749 | 2017-11-15 10:43 | [7 empty] | 2017-11-15 19:59 | Yes | 0
VD-9001-205A-PCJ-061 | 2 | PACKING PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-29 | 2015-09-19 10:26 | 2015-09-19 14:39 | Yes | -10 |  | 2015-10-14 09:56 | [6 empty] | 2015-10-14 09:57 | Yes | 11
VD-9001-205A-QCP-057 | 2 | INSPECTION AND TEST PALN & PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-29 | 2015-09-19 10:26 | 2015-09-19 14:41 | Yes | -10 |  | 2015-09-30 16:57 | [6 empty] | 2015-09-30 16:58 | Yes | -3
VD-9001-253(A)-PCJ-103 | 3 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-09-29 | 2015-12-09 12:04 |  | No | 71 | 2015-12-26 10:00 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-253(A)-DWG-048 | 2 | MOTOR WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-09-29 | 2015-10-10 16:47 | 2015-10-10 17:02 | Yes | 11 |  | 2015-10-27 15:05 | [6 empty] | 2015-10-27 15:06 | Yes | 3 | 1204-Owner-v | 2018-03-12 13:40
VD-9001-206A-WBK-001 | 3 | WELDING BOOK (WPS & PQR) | PV-206A | TASHA | 2015-09-16 11:01 | 2015-09-16 15:08 |  | No | 0 | 2015-09-19 16:59 | [8 empty] | No | 0
VD-9001-206A-PCJ-014 | 4 | Erection procedure | PV-206A | TASHA | 2015-09-16 11:01 | 2015-09-16 15:06 | 2015-09-16 15:37 | Yes | 0 |  | 2015-09-16 18:17 | [6 empty] | 2015-09-16 18:18 | Yes | -14 | 1204-Owner-v | 2020-05-18 17:13
VD-9001-206A-DWG-011 | 8 | GENERAL ARRANGMENT ( T-3002 ) | PV-206A | TASHA | 2015-09-16 11:01 | 2015-09-16 14:52 | 2015-09-16 15:39 | Yes | 0 |  | 2015-09-16 18:09 | [6 empty] | 2015-09-16 18:10 | Yes | -14 | 1204-Owner-v | 2019-07-10 11:30
VD-9001-206A-DWG-012 | 6 | BODY & SUPPORT DETAIL DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-09-16 11:02 | 2015-09-16 14:53 | 2015-09-16 15:40 | Yes | 0 |  | 2015-09-16 18:10 | [6 empty] | 2015-09-16 18:11 | Yes | -14
VD-9001-206A-DWG-021 | 4 | GENERAL ARRANGMENT ( T-3003 ) | PV-206A | TASHA | 2015-09-16 11:02 | 2015-09-16 14:54 | 2015-09-16 15:41 | Yes | 0 |  | 2015-09-16 18:10 | [6 empty] | 2015-09-16 18:11 | Yes | -14 | 1204-Owner-v | 2019-07-10 11:31
VD-9001-206A-DWG-022 | 5 | BODY & SUPPORT DETAIL DRAWING ( T-3003 ) | PV-206A | TASHA | 2015-09-16 11:02 | 2015-09-16 15:03 | 2015-09-16 15:42 | Yes | 0 |  | 2015-09-16 18:10 | [6 empty] | 2015-09-16 18:11 | Yes | -14 | 1204-Owner-v | 2019-12-21 09:01
VD-9001-206A-DWG-031 | 0 | SADDLE DRAWING T-3002 | PV-206A | TASHA | 2015-09-15 | 2015-09-16 15:04 |  | No | 1 |  | 2015-09-16 18:21 | [7 empty] | No | 0
VD-9001-206A-DWG-032 | 0 | SADDLE DRAWING T-3003 | PV-206A | TASHA | 2015-09-15 | 2015-09-16 15:05 |  | No | 1 |  | 2015-09-16 18:22 | [7 empty] | No | 0
VD-9001-206A-PCJ-015 | 0 | N2 FILLING PROCEDURE | PV-206A | TASHA | 2015-09-15 | 2015-09-16 15:06 |  | No | 1 | 2015-09-16 18:17 | [8 empty] | No | 0
VD-9001-254-LST-106 | 2 | UTILITY LIST | HM-254 | AZAR AB | 2015-09-30 |  |  | No | 1724 | [9 empty] | No | 0
VD-9001-254-DWG-704 | 1 | FOUNDATION LOADS FOR ST. STACK | HM-254 | AZAR AB | 2015-09-30 | 2015-11-29 15:16 |  | No | 60 | 2015-12-30 16:33 | [7 empty] | 2015-12-30 20:03 | Yes | 0
VD-9001-254-DWG-213 | 1 | LIGHTING LAYOUT OF BOILERS | HM-254 | AZAR AB | 2015-09-30 | 2018-10-21 08:53 | 2018-10-21 08:53 | Yes | 1117 |  |  | 2018-11-14 09:58 | [5 empty] | 2018-11-14 09:58 | Yes | 10
VD-9001-108-PCJ-064 | 1 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2015-09-30 | 2015-11-24 08:14 |  | No | 55 | 2015-12-19 12:03 | [8 empty] | No | 0
VD-9001-206A-PCJ-015 | 1 | N2 FILLING PROCEDURE | PV-206A | TASHA | 2015-09-30 | 2015-09-19 16:20 |  | No | -11 | 2015-09-20 14:25 | [8 empty] | No | 0
VD-9001-213A-DWG-119 | 4 | Water Cooling System for Tk-7101A | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-11-02 11:21 | 2015-11-02 12:47 | Yes | 30 |  | 2015-11-18 17:28 | [6 empty] | 2015-11-18 17:29 | Yes | 2
VD-9001-213A-DWG-120 | 4 | Water Cooling System for Tk-7101B | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-11-02 11:22 | 2015-11-02 12:48 | Yes | 30 |  | 2015-11-18 17:28 | [6 empty] | 2015-11-18 17:29 | Yes | 2
VD-9001-213A-DWG-087 | 2 | Fixed Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-09-20 15:58 |  | No | -13 |  | 2015-09-30 16:14 | [7 empty] | No | 0
VD-9001-213A-DWG-088 | 2 | Fixed Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-09-20 15:59 |  | No | -13 |  | 2015-09-30 16:15 | [7 empty] | No | 0
VD-9001-213A-DWG-099 | 4 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-09-28 07:16 |  | No | -5 |  | 2015-09-30 16:20 | [7 empty] | No | 0
VD-9001-213A-DWG-100 | 4 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-10-03 | 2015-09-28 07:17 |  | No | -5 |  | 2015-09-30 16:20 | [7 empty] | No | 0
VD-9001-206A-WBK-001 | 4 | WELDING BOOK (WPS & PQR) | PV-206A | TASHA | 2015-10-03 | 2015-09-30 18:32 | 2015-10-01 11:53 | Yes | -2 |  | 2015-10-17 12:11 | [6 empty] | 2015-10-17 12:12 | Yes | 3
VD-9001-213B-DWG-035 | 2 | Pipe Support for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2015-10-04 | 2015-09-22 07:08 | 2015-09-22 09:59 | Yes | -12 |  | 2015-09-26 10:47 | [6 empty] | 2015-09-26 10:48 | Yes | -10
VD-9001-254-DSH-564 | 1 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2015-10-04 | 2016-10-26 07:55 |  | No | 388 | 2016-11-07 10:06 | [7 empty] | 2016-11-07 19:59 | Yes | 0
VD-9001-254-SOI-950 | 3 | ITP FOR BIOLER FABRICATION | HM-254 | AZAR AB | 2015-10-04 | 2015-10-18 09:51 | 2015-10-18 17:59 | Yes | 14 |  | 2015-10-26 12:45 | [6 empty] | 2015-10-26 12:46 | Yes | -6 | 1204-Owner-v | 2018-01-28 14:26
VD-9001-254-DSH-351 | 1 | DATA SHEET FOR FLOW ELEMENTS | HM-254 | AZAR AB | 2015-10-04 | 2016-05-11 12:52 |  | No | 220 | 2016-06-13 15:54 | [7 empty] | 2016-06-13 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-28 11:59
VD-9001-206A-PCJ-015 | 2 | N2 FILLING PROCEDURE | PV-206A | TASHA | 2015-10-04 | 2015-09-22 16:15 | 2015-09-22 17:32 | Yes | -12 |  | 2015-09-30 17:02 | [6 empty] | 2015-09-30 17:03 | Yes | -6 | 1204-Owner-v | 2019-07-17 14:12
VD-9001-253(A)-DWG-002 | 6 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2015-10-04 | 2016-07-09 14:48 |  | No | 279 | 2016-08-03 16:58 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-254-DSH-566 | 1 | DATA SHEET FOR CONTROL VALVES | HM-254 | AZAR AB | 2015-10-04 | 2017-12-04 10:55 |  | No | 792 | 2018-02-04 17:35 | [7 empty] | 2018-02-04 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-28 09:45
VD-9001-254-DSH-567 | 1 | DATA SHEET FOR PRESSURE REGULATORS | HM-254 | AZAR AB | 2015-10-04 | 2018-12-05 15:15 | 2018-12-05 15:15 | Yes | 1158 |  |  |  | 2018-12-26 09:28 |  |  |  |  | 2018-12-26 09:28 | Yes | 7 | 1204-Owner-v | 2019-06-26 15:08
VD-9001-254-CAL-560 | 1 | PIPE SIZING & VELOCITY CALCULATION | HM-254 | AZAR AB | 2015-10-06 |  |  | No | 1718 | [9 empty] | No | 0
VD-9001-108-LST-047 | 2 | LOAD LIST | PR-108 | Farabard | 2015-10-07 | 2015-10-31 13:40 |  | No | 24 | 2015-11-16 16:55 | [8 empty] | No | 0
VD-9001-254-LST-216 | 2 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2015-10-10 | 2015-11-10 08:32 |  | No | 31 | 2015-12-23 10:23 | [7 empty] | 2015-12-23 20:03 | Yes | 0
VD-9001-204A-DWG-011 | 1 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-10-04 | 2015-10-14 16:00 |  | No | 10 | 2015-12-07 14:19 | [8 empty] | No | 0
VD-9001-204A-DWG-051 | 1 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-10-04 | 2015-10-14 15:58 |  | No | 10 | 2015-11-18 17:02 | [8 empty] | No | 0
VD-9001-254-LGD-122 | 1 | P&I DIAGRAM SYMBOLS & LEGENDS | HM-254 | AZAR AB | 2015-09-27 11:07 | 2015-09-27 11:30 |  | No | 0 | 2015-10-18 17:48 | [8 empty] | No | 0
VD-9001-253(A)-DWG-041 | 2 | HEADER WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-10-11 | 2015-10-10 16:45 | 2015-10-10 17:01 | Yes | -1 |  | 2015-10-27 15:05 | [6 empty] | 2015-10-27 15:06 | Yes | 3 | 1204-Owner-v | 2018-08-14 17:39
VD-9001-253(A)-DWG-035 | 2 | STEEL STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-10-11 | 2015-10-10 16:49 |  | No | -1 | 2015-10-31 16:25 | [8 empty] | No | 0
VD-9001-213A-DWG-145 | 3 | Foam Protection System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-10-11 | 2015-11-18 10:26 |  | No | 38 | 2015-12-07 15:07 | [8 empty] | No | 0
VD-9001-205A-DWG-048 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-09-30 09:36 | 2015-09-30 09:38 |  | No | 0 | 2015-10-17 11:24 | [8 empty] | No | 0
VD-9001-213A-DWG-121 | 3 | Foam Protection System for Tk-7101A | PV-213A | MachineSazi Pars | 2015-10-14 | 2015-12-06 10:39 |  | No | 53 | 2015-12-22 09:58 | [8 empty] | No | 0
VD-9001-213A-DWG-122 | 3 | Foam Protection System for Tk-7101B | PV-213A | MachineSazi Pars | 2015-10-14 | 2015-12-06 10:40 |  | No | 53 | 2015-12-22 09:59 | [8 empty] | No | 0
VD-9001-213A-DWG-077 | 2 | Pipe Support for Tk-6401 | PV-213A | MachineSazi Pars | 2015-10-14 | 2015-10-04 07:07 | 2015-10-04 09:58 | Yes | -10 |  | 2015-10-14 17:28 | [6 empty] | 2015-10-14 17:29 | Yes | -4
VD-9001-213A-DWG-141 | 2 | Pipe Support for Tk-7201 | PV-213A | MachineSazi Pars | 2015-10-14 | 2015-10-04 07:08 | 2015-10-04 09:59 | Yes | -10 |  | 2015-10-14 17:29 | [6 empty] | 2015-10-14 17:30 | Yes | -4
VD-9001-205A-DWG-043 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-10-03 17:16 |  | No | -14 | 2016-01-05 17:14 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-205A-DWG-002 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-10-27 09:38 |  | No | 10 | 2015-12-24 12:36 | [7 empty] | 2015-12-24 20:03 | Yes | 0
VD-9001-205A-DWG-003 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-10-27 09:39 |  | No | 10 | 2015-12-24 12:37 | [7 empty] | 2015-12-24 20:03 | Yes | 0
VD-9001-205A-DWG-026 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-10-27 09:30 |  | No | 10 | 2015-12-07 11:37 | [8 empty] | No | 0
VD-9001-205A-DWG-027 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-12-20 17:26 | 2015-12-20 17:55 | Yes | 64 |  | 2015-12-24 13:14 | [6 empty] | 2015-12-24 20:03 | Yes | -10
VD-9001-205A-DWG-028 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-11-04 08:36 |  | No | 18 | 2015-12-08 12:18 | [8 empty] | No | 0
VD-9001-205A-DWG-006 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-10-11 11:08 |  | No | -6 | 2015-11-04 10:54 | [8 empty] | No | 0
VD-9001-205A-DWG-008 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-17 | 2015-11-04 08:36 |  | No | 18 |  | 2015-12-08 12:12 | [7 empty] | No | 0
VD-9001-105-PFD-101 | 0 | PFD & material balance | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-10-22 05:43 |  | No | 7 |  | 2015-10-26 11:56 | [7 empty] | No | 0 | 1204-Owner-v | 2019-06-11 14:53
VD-9001-105-PID-101 | 0 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-10-22 05:45 |  | No | 7 | 2015-11-01 15:43 | [8 empty] | No | 0
VD-9001-105-DWG-101 | 0 | Name plate drawings of HRU Package | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-05-03 15:19 |  | No | 155 | 2016-05-08 09:26 | [7 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-105-PDS-101 | 0 | Process description | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-05-03 15:20 | 2016-05-03 15:21 | Yes | 155 |  | 2016-05-28 09:44 | [6 empty] | 2016-05-28 19:58 | Yes | 11 | 1204-Owner-v | 2019-06-11 10:34
VD-9001-105-EQL-101 | 0 | Equipment list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-17 11:56 | 2016-02-17 11:57 | Yes | 94 |  | 2016-03-13 08:43 | [6 empty] | 2016-03-13 19:59 | Yes | 11 | 1204-Owner-v | 2019-01-04 21:41
VD-9001-105-DSH-101 | 0 | Data sheet of gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-17 11:51 |  | No | 94 | 2016-03-10 12:40 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-DSH-102 | 0 | Data sheet of heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-17 11:54 |  | No | 94 | 2016-03-10 11:24 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-DSH-103 | 0 | Data sheet of CMR membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-17 11:56 |  | No | 94 | 2016-03-13 08:37 | [7 empty] | 2016-03-13 19:59 | Yes | 0
VD-9001-105-DSH-105 | 0 | Data sheet of safety valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-10-30 15:16 |  | No | 0 | 2015-11-04 10:09 | [8 empty] | No | 0
VD-9001-105-DSH-107 | 0 | Data sheet of strainer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 14:41 | 2015-11-12 12:13 | Yes | 13 |  | 2015-11-16 16:44 | [6 empty] | 2015-11-16 16:45 | Yes | -9 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-105-DSH-108 | 0 | Data sheet of sight glass | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 14:55 | 2015-11-12 12:14 | Yes | 13 |  | 2015-11-28 11:57 | [6 empty] | 2015-11-28 11:58 | Yes | 3 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-105-CAL-101 | 0 | Calculation sheet of safety valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-10-30 15:07 |  | No | 15 | 2015-11-04 09:38 | [8 empty] | No | 0 | 1204-Owner-v | 2019-06-11 10:22
VD-9001-105-DPH-101 | 0 | Process control philosophy | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-11 15:02 |  | No | -19 | 2015-12-08 15:17 | [8 empty] | No | 0
VD-9001-105-DPH-102 | 0 | Process control requirement | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-11 15:05 |  | No | -19 |  | 2015-12-08 15:18 | [7 empty] | No | 0
VD-9001-105-DPH-103 | 0 | Cause and effect diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-11 15:08 |  | No | -19 | 2015-12-13 11:21 | [8 empty] | No | 0
VD-9001-105-DPH-104 | 0 | Interlock description | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-11 15:14 |  | No | -19 | 2015-12-08 15:17 | [8 empty] | No | 0
VD-9001-105-MNL-101 | 0 | Operation and maintenance manual | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2018-03-27 11:54 | 2018-03-27 11:54 | Yes | 848 |  |  | 2018-04-22 17:29 | [5 empty] | 2018-04-22 17:29 | Yes | 12 | 1204-Owner-v | 2019-04-27 11:08
VD-9001-105-LST-101 | 0 | Utility consumption list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-10-22 05:45 |  | No | 7 | 2015-10-28 16:14 | [8 empty] | No | 0
VD-9001-105-LST-102 | 0 | Line list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-10-22 05:47 |  | No | 7 | 2015-10-26 11:54 | [8 empty] | No | 0
VD-9001-105-LST-103 | 0 | Piping valve list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-11-11 15:39 |  | No | 27 | 2015-11-16 16:45 | [8 empty] | No | 0
VD-9001-105-MTO-101 | 0 | Data sheet of equipment insulation material | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-07-23 16:17 | 2016-07-23 16:18 | Yes | 206 |  | 2016-07-27 16:01 | [6 empty] | 2016-07-27 19:57 | Yes | -10 | 1204-Owner-v | 2019-06-17 10:52
VD-9001-105-MTO-102 | 0 | Data sheet of pipe insulation material | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-07-23 16:17 | 2016-07-23 16:18 | Yes | 206 |  | 2016-07-27 16:03 | [6 empty] | 2016-07-27 19:57 | Yes | -10
VD-9001-105-MTO-103 | 0 | Insulation material take off | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-07-23 16:17 | 2016-07-23 16:18 | Yes | 206 |  | 2016-07-27 16:05 | [6 empty] | 2016-07-27 19:57 | Yes | -10
VD-9001-105-PCJ-101 | 0 | Site acceptance test procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-05-03 15:19 | 2016-05-03 15:20 | Yes | 125 |  | 2016-05-09 18:18 | [6 empty] | 2016-05-09 19:59 | Yes | -8 | 1204-Owner-v | 2019-07-06 13:34
VD-9001-105-DSH-201 | 0 | Data sheet of pressure gauges | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:19 |  | No | 48 | 2016-01-09 10:30 | [7 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-DSH-202 | 0 | Data sheet of pressure transmitters | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:34 |  | No | 48 |  | 2016-01-09 10:36 | [6 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-DSH-203 | 0 | Data sheet of temp. gauges and thermowells | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:37 |  | No | 48 | 2016-01-09 10:40 | [7 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-DSH-204 | 0 | Data sheet of temperature elements and transmitter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:54 |  | No | 48 | 2016-01-09 10:45 | [7 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-DSH-205 | 0 | Data sheet of automatic valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-11-11 15:25 |  | No | 27 | 2015-11-29 11:52 | [8 empty] | No | 0
VD-9001-105-DSH-206 | 0 | Data sheet of level gauges | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2016-02-26 18:59 |  | No | 119 |  | 2016-03-10 11:38 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-DSH-207 | 0 | Data sheet of level transmitters(diaphragm sealed) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:58 | 2015-12-19 11:59 | Yes | 50 |  | 2016-01-09 10:49 | [6 empty] | 2016-01-09 20:03 | Yes | 9 | 1204-Owner-v | 2019-01-04 21:38
VD-9001-105-DSH-208 | 0 | Data sheet of level switch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2016-02-27 09:29 |  | No | 120 |  | 2016-03-10 11:42 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-DSH-209 | 0 | Data sheet of orifice plate flow meter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 18:59 |  | No | 48 | 2016-01-09 10:59 | [7 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-DSH-210 | 0 | Data sheet of restriction orifice | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 19:01 |  | No | 48 | 2016-01-07 11:04 | [7 empty] | 2016-01-07 20:03 | Yes | 0
VD-9001-105-DSH-211 | 0 | Data sheet of hydrogen analyzer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 15:26 |  | No | 12 | 2015-12-01 09:37 | [8 empty] | No | 0
VD-9001-105-DSH-212 | 0 | Data sheet of combustible gas detector | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 19:03 | 2015-12-19 12:01 | Yes | 50 |  | 2016-01-09 11:03 | [6 empty] | 2016-01-09 20:03 | Yes | 9 | 1204-Owner-v | 2019-01-04 21:39
VD-9001-105-LST-201 | 0 | Cable schedule with cable list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-02-23 15:33 |  | No | 85 | 2016-04-09 08:49 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-LST-202 | 0 | Instrument list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2016-06-01 13:00 |  | No | 215 | 2016-06-15 10:45 | [7 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-105-LST-203 | 0 | FCS I/O List | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 15:38 |  | No | 12 |  | 2015-12-01 09:35 | [7 empty] | No | 0
VD-9001-105-LST-204 | 0 | Set point list of HRU for FCS’s alarm and interlock | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 15:41 |  | No | 12 | 2015-11-29 17:42 | [8 empty] | No | 0
VD-9001-105-LST-205 | 0 | Set point list of HRU for FCS’s monitor and control | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 15:42 |  | No | 12 | 2015-11-29 17:42 | [8 empty] | No | 0
VD-9001-105-DIG-201 | 0 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-01-07 17:23 |  | No | 38 | 2016-02-21 13:53 | [7 empty] | 2016-02-21 20:00 | Yes | 0
VD-9001-105-DIG-202 | 0 | Interlock logic diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-27 18:03 |  | No | -3 | 2015-12-15 11:36 | [8 empty] | No | 0
VD-9001-105-DIG-203 | 0 | Instrument, cable, junction box and cable tray layout diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-01-07 17:24 |  | No | 38 | 2016-02-21 13:56 | [7 empty] | 2016-02-21 20:00 | Yes | 0
VD-9001-105-DIG-204 | 0 | Outline diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-02-23 15:30 |  | No | 85 | 2016-04-09 08:45 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-DIG-205 | 0 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-29 14:30 |  | No | -1 | 2015-12-15 11:39 | [8 empty] | No | 0
VD-9001-105-DIG-206 | 0 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-11-11 15:21 |  | No | 12 | 2015-12-01 09:38 | [8 empty] | No | 0
VD-9001-105-CAL-201 | 0 | Calculation sheet of control valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-15 | 2015-11-11 15:17 |  | No | 27 | 2015-11-28 12:05 | [8 empty] | No | 0
VD-9001-105-CAL-202 | 0 | Calculation sheet of temp. thermowells | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 19:07 | 2015-12-19 12:02 | Yes | 50 |  | 2016-01-09 11:08 | [6 empty] | 2016-01-09 20:03 | Yes | 9
VD-9001-105-CAL-203 | 0 | Calculation sheet of flowmeter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-12-17 19:08 |  | No | 48 | 2016-01-09 11:11 | [7 empty] | 2016-01-09 20:03 | Yes | 0
VD-9001-105-MAL-201 | 0 | Instrument installation bill of material | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-06-20 18:31 |  | No | 203 | 2016-06-28 15:45 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-105-PPL-301 | 0 | Plot plan of HRU | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-10-30 | 2015-10-30 15:17 |  | No | 0 | 2015-11-24 16:33 | [8 empty] | No | 0
VD-9001-105-DWG-301 | 0 | Piping general arrangement and tie-point list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-12 14:15 |  | No | -18 | 2015-11-28 09:46 | [8 empty] | No | 0
VD-9001-105-DWG-302 | 0 | Steel structure drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-06-16 18:50 |  | No | 169 |  | 2016-07-27 17:10 | [6 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-ISO-301 | 0 | Piping isometric | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-06-07 16:41 |  | No | 160 | 2016-06-28 15:09 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-105-LST-301 | 0 | Piping material list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-05-19 12:41 |  | No | 141 | 2016-05-28 10:06 | [7 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-105-CAL-301 | 0 | External nozzle load calculation | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-10 | 2016-06-28 11:29 | 2016-06-28 11:30 | Yes | 139 |  | 2016-07-16 10:48 | [6 empty] | 2016-07-16 19:58 | Yes | 4
VD-9001-105-CAL-302 | 0 | Stress analysis calculation sheet of critical lines | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-10 | 2017-11-05 12:59 | 2017-11-05 13:00 | Yes | 634 |  | 2017-11-08 14:40 | [6 empty] | 2017-11-08 19:59 | Yes | -12
VD-9001-105-PCJ-301 | 0 | Erection procedure at site | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-30 | 2018-05-31 08:12 | 2018-05-31 08:13 | Yes | 731 |  |  | 2018-06-13 11:31 | [5 empty] | 2018-06-13 11:31 | Yes | -1 | 1204-Owner-v | 2019-09-06 22:02
VD-9001-105-CAL-401 | 0 | Anchor bolt detail and calculation | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-13 14:58 | 2015-11-14 10:34 | Yes | -16 |  | 2015-11-24 16:58 | [6 empty] | 2015-11-24 16:59 | Yes | -3
VD-9001-105-DWG-401 | 0 | Foundations layout with distribution of load | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2015-11-13 15:04 | 2015-11-14 10:33 | Yes | -16 |  | 2015-11-24 16:57 | [6 empty] | 2015-11-24 16:58 | Yes | -3 | 1204-Owner-v | 2018-09-02 15:57
VD-9001-105-DWG-501 | 0 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 10:48 |  | No | 85 | 2016-04-09 09:24 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-DWG-502 | 0 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 10:50 |  | No | 85 | 2016-04-09 08:32 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-DWG-503 | 0 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 10:52 |  | No | 85 | 2016-04-09 08:37 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-CAL-501 | 0 | Calculation sheet of Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 16:40 |  | No | 85 | 2016-03-10 11:04 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-CAL-502 | 0 | Calculation sheet for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 11:05 |  | No | 85 | 2016-03-10 11:01 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-CAL-503 | 0 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-08 11:08 |  | No | 85 | 2016-03-10 11:03 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-CAL-505 | 0 | Thermal design calculation for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2016-02-17 11:48 |  | No | 94 |  | 2016-02-20 10:31 | [6 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-NPL-501 | 0 | Non-destructive examination procedures for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:07 | 2016-04-15 19:08 | Yes | 122 |  | 2016-07-16 10:29 | [6 empty] | 2016-07-16 19:58 | Yes | 78 | 1204-Owner-v | 2019-07-06 13:35
VD-9001-105-NPL-502 | 0 | Non-destructive examination procedures for piping | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:10 | 2016-04-15 19:11 | Yes | 122 |  | 2016-07-07 10:41 | [6 empty] | 2016-07-07 19:58 | Yes | 69
VD-9001-105-PCJ-501 | 0 | Hydrostatic test procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:10 |  | No | 122 | 2016-07-27 15:02 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-502 | 0 | Leak test procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:11 |  | No | 122 | 2016-07-27 15:09 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-503 | 0 | Hydrostatic and leak test procedure for piping | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:11 |  | No | 122 | 2016-07-27 15:06 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-504 | 0 | Heat treatment procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:12 |  | No | 122 | 2016-07-27 15:12 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-505 | 0 | Pickling & Passivating procedure for S.S surfaces | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:12 |  | No | 122 | 2016-07-27 15:15 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-506 | 0 | Repair welding procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:13 |  | No | 122 | 2016-07-27 15:20 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-PCJ-507 | 0 | Weld overlay procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-06-03 16:14 |  | No | 171 | 2016-07-07 11:01 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-PCJ-509 | 0 | Hardness test procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:14 |  | No | 122 | 2016-07-07 10:46 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-PCJ-510 | 0 | PMI test procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:15 | 2016-04-15 19:16 | Yes | 122 |  | 2016-07-07 10:49 | [6 empty] | 2016-07-07 19:58 | Yes | 69
VD-9001-105-PCJ-511 | 0 | Expanding procedure for heat exchangers tubes | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:17 |  | No | 122 | 2016-07-27 15:23 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-105-SPE-501 | 0 | Painting specification | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:19 |  | No | 122 | 2016-07-07 10:52 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-POR-501 | 0 | Un-priced copy of suborders for pressure vessels and heat exchanger | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-04-15 19:18 | 2016-04-15 19:19 | Yes | 137 |  | 2016-05-17 15:58 | [6 empty] | 2016-05-17 19:58 | Yes | 18
VD-9001-105-LST-501 | 0 | Spare parts list for two years | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2015-11-11 15:43 |  | No | -49 | 2015-11-25 11:50 | [8 empty] | No | 0
VD-9001-105-LST-502 | 0 | Spare parts list for commissioning | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2015-11-11 15:43 |  | No | -49 | 2015-11-25 11:50 | [8 empty] | No | 0
VD-9001-105-LST-503 | 0 | Spare parts list and interchangeability record | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-30 | 2016-08-10 10:09 |  | No | 224 | 2016-10-20 11:56 | [7 empty] | 2016-10-20 20:00 | Yes | 0
VD-9001-105-ITP-701 | 0 | Inspection and test plan for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-27 19:01 |  | No | 134 | 2016-05-07 16:08 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:04
VD-9001-105-ITP-702 | 0 | Inspection and test plan for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-29 06:01 |  | No | 136 | 2016-05-07 16:22 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:04
VD-9001-105-ITP-703 | 0 | Inspection and test plan for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-27 19:05 |  | No | 134 | 2016-05-07 16:13 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:11
VD-9001-105-ITP-705 | 0 | Inspection and test plan of piping and skid-structure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-27 19:06 |  | No | 134 | 2016-05-07 16:17 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:13
VD-9001-105-ITP-706 | 0 | Inspection and test plan of membrane modules | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-04-29 07:08 |  | No | 151 | 2016-05-07 16:26 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:14
VD-9001-105-ITP-707 | 0 | Inspection and test plan of instruments | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-04-29 07:09 |  | No | 151 | 2016-05-07 16:29 | [7 empty] | 2016-05-07 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:18
VD-9001-105-WPS-701 | 0 | WPS & PQR for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-06-08 15:41 |  | No | 176 | 2016-07-07 11:06 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-WPS-702 | 0 | WPS & PQR for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-06-08 15:43 |  | No | 176 | 2016-07-07 11:12 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-WPS-703 | 0 | WPS & PQR for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-06-08 15:43 |  | No | 176 | 2016-07-07 11:09 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-WPS-705 | 0 | WPS & PQR for piping | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-30 | 2017-11-06 05:37 | 2017-11-06 05:38 | Yes | 646 |  | 2017-11-18 14:59 | [6 empty] | 2017-11-18 19:59 | Yes | -2
VD-9001-105-CER-701 | 0 | Manufacturer certificate of compliance(use ASME code forms) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-30 | 2016-04-15 19:03 | 2016-04-15 19:04 | Yes | 76 |  | 2016-05-17 15:52 | [6 empty] | 2016-05-17 19:58 | Yes | 18
VD-9001-105-CER-702 | 0 | Certificate of authorization for utilization of U stamp | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-04-15 19:04 | 2016-04-15 19:05 | Yes | 122 |  | 2016-05-17 15:55 | [6 empty] | 2016-05-17 19:58 | Yes | 18
VD-9001-105-CER-703 | 0 | Certificates of calibration | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-30 |  |  | No | 1420 | [9 empty] | No | 0
VD-9001-105-CER-704 | 0 | Declaration of conformity | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-30 | 2018-07-04 12:11 | 2018-07-04 12:12 | Yes | 704 |  |  | 2018-07-08 09:49 | [5 empty] | 2018-07-08 09:49 | Yes | -10
VD-9001-105-CER-705 | 0 | Final certificate of inspection | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-30 | 2018-07-04 12:14 | 2018-07-04 12:18 | Yes | 673 |  |  | 2018-07-31 09:27 | [5 empty] | 2018-07-31 09:27 | Yes | 13
VD-9001-105-RPT-701 | 0 | QC records for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-30 | 2018-07-04 05:58 | 2018-07-04 06:06 | Yes | 886 |  |  |  | 2018-07-18 09:11 |  |  |  |  | 2018-07-18 09:11 | Yes | 0
VD-9001-105-RPT-702 | 0 | QC records for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-30 | 2018-07-04 06:17 | 2018-07-04 07:15 | Yes | 886 |  |  | 2018-07-31 08:51 | [5 empty] | 2018-07-31 08:51 | Yes | 13
VD-9001-105-RPT-703 | 0 | QC records for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-30 | 2018-07-04 07:44 | 2018-07-04 07:55 | Yes | 886 |  |  | 2018-07-31 08:52 | [5 empty] | 2018-07-31 08:52 | Yes | 13
VD-9001-105-RPT-705 | 0 | QC records for piping and structure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-10 | 2018-07-04 08:20 | 2018-07-04 08:23 | Yes | 724 |  |  | 2018-07-31 08:54 | [5 empty] | 2018-07-31 08:54 | Yes | 13
VD-9001-105-RPT-706 | 0 | QC records for membrane modules | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 | 2018-07-04 09:45 | 2018-07-04 09:51 | Yes | 688 |  |  | 2018-07-31 08:56 | [5 empty] | 2018-07-31 08:56 | Yes | 13
VD-9001-105-WPQ-701 | 0 | Welders performance qualification | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2018-07-05 10:36 | 2018-07-05 11:00 | Yes | 933 |  |  | 2018-07-31 09:29 | [5 empty] | 2018-07-31 09:29 | Yes | 12
VD-9001-105-SVDB-701 | 0 | Sub-vendor’s documents (including Material certificate, Calibration certificate, Test certificate, Instruction or Manual, Explosion-proof certificate, etc.) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-30 |  |  | No | 1420 | [9 empty] | No | 0
VD-9001-105-CER-801 | 0 | Original certificate of HRU | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 |  |  | No | 1404 | [9 empty] | No | 0
VD-9001-105-INT-001 | 0 | Background of vendor’s experience | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 |  |  | No | 1404 | [9 empty] | No | 0
VD-9001-105-SRN-801 | 0 | Release note for shipment | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 | 2018-07-04 12:27 | 2018-07-04 12:27 | Yes | 688 |  |  | 2018-07-31 10:21 | [5 empty] | 2018-07-31 10:21 | Yes | 13
VD-9001-105-LST-801 | 0 | Master packing list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 | 2018-07-04 12:19 | 2018-07-04 12:19 | Yes | 688 |  |  | 2018-07-31 08:44 | [5 empty] | 2018-07-31 08:44 | Yes | 13 | 1204-Owner-v | 2018-09-30 15:55
VD-9001-105-LST-802 | 0 | Detailed Packing List | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-15 | 2018-07-04 12:24 | 2018-07-04 12:24 | Yes | 688 |  |  | 2018-07-31 08:47 | [5 empty] | 2018-07-31 08:47 | Yes | 13 | 1204-Owner-v | 2018-09-30 16:00
VD-9001-105-WIN-801 | 0 | Handling and storage instruction at site | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-30 | 2016-07-22 10:14 | 2016-07-22 10:15 | Yes | 53 |  | 2016-08-13 16:44 | [6 empty] | 2016-08-13 19:57 | Yes | 8 | 1204-Owner-v | 2019-04-27 11:30
VD-9001-105-LAD-801 | 0 | Bill of lading(original copy) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-30 |  |  | No | 1389 | [9 empty] | No | 0
VD-9001-105-INV-801 | 0 | Commercial invoice(original copy) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-30 |  |  | No | 1389 | [9 empty] | No | 0
VD-9001-105-HSE-901 | 0 | Material safety data sheet (MSDS) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-05-30 18:57 | 2016-05-30 18:58 | Yes | 182 |  | 2016-07-16 09:27 | [6 empty] | 2016-07-16 19:58 | Yes | 33
VD-9001-105-HSE-902 | 0 | HSE instruction | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-05-30 19:01 |  | No | 182 | 2016-07-07 10:55 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-HSE-903 | 0 | HSE plans | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-05-30 19:08 |  | No | 182 | 2016-07-07 10:57 | [7 empty] | 2016-07-07 19:58 | Yes | 0 | 1204-Owner-v | 2019-06-17 10:55
VD-9001-204A-CAL-050 | 1 | Strength Calculation FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-10-18 | 2015-12-06 10:45 |  | No | 49 | 2015-12-26 17:57 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-108-DWG-021 | 2 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2015-10-05 10:14 | 2015-10-05 10:36 |  | No | 0 | 2015-10-06 14:56 | [8 empty] | No | 0
VD-9001-108-DWG-022 | 3 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2015-10-05 10:14 | 2015-10-10 11:48 |  | No | 5 |  | 2015-10-13 09:45 | [7 empty] | No | 0
VD-9001-108-DWG-023 | 1 | SECONDERY BEAMS DETAIL | PR-108 | Farabard | 2015-10-05 10:14 | 2015-10-05 10:38 |  | No | 0 |  | 2015-10-06 17:10 | [7 empty] | No | 0
VD-9001-108-DWG-024 | 1 | WATER DISTRIBUTION CHANNEL DETAIL | PR-108 | Farabard | 2015-10-05 10:14 | 2015-10-12 13:12 |  | No | 7 |  | 2015-10-19 10:44 | [7 empty] | No | 0
VD-9001-108-MNL-056 | 1 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2015-10-19 | 2015-10-07 13:13 |  | No | -12 | 2015-10-13 09:49 | [8 empty] | No | 0
VD-9001-204A-PCJ-004 | 1 | Radiography Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-19 | 2015-10-21 13:31 | 2015-10-21 17:43 | Yes | 2 |  | 2015-10-27 10:14 | [6 empty] | 2015-10-27 10:15 | Yes | -8
VD-9001-204A-PCJ-008 | 1 | leak test Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-19 | 2015-10-10 16:30 | 2015-10-10 16:58 | Yes | -9 |  | 2015-12-14 14:08 | [6 empty] | 2015-12-14 14:09 | Yes | 51
VD-9001-108-DSH-011 | 3 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2015-10-19 | 2015-11-17 13:08 |  | No | 29 | 2015-12-05 12:36 | [8 empty] | No | 0
VD-9001-204A-CAL-080 | 1 | Strength Calculation FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-10-19 | 2016-02-21 12:41 |  | No | 125 | 2016-03-01 16:53 | [7 empty] | 2016-03-01 20:00 | Yes | 0
VD-9001-108-DWG-020 | 3 | COLUMNS DEATAIL | PR-108 | Farabard | 2015-10-20 | 2015-10-06 11:34 |  | No | -14 |  | 2015-10-07 17:07 | [7 empty] | No | 0
VD-9001-257A-PCJ-007 | 1 | Tube Expand (Rolling) Procedure | HM-257A | ABAN AIR COOLER. | 2015-10-20 | 2016-04-02 14:46 | 2016-04-02 14:47 | Yes | 165 |  |  | 2018-03-27 10:25 | [5 empty] | 2018-03-27 10:25 | Yes | 710
VD-9001-257A-PCJ-006 | 1 | Hydrostatic Test Procedure * | HM-257A | ABAN AIR COOLER. | 2015-10-20 | 2016-02-03 15:56 | 2016-02-03 15:57 | Yes | 106 |  | 2016-02-16 15:59 | [6 empty] | 2016-02-16 20:04 | Yes | -1
VD-9001-257A-ITP-001 | 3 | Inspection & Test Plan | HM-257A | ABAN AIR COOLER. | 2015-10-20 | 2015-10-10 12:24 | 2015-10-10 15:20 | Yes | -10 |  | 2015-10-29 12:28 | [6 empty] | 2015-10-29 12:29 | Yes | 5
VD-9001-254-DSH-135 | 1 | DATA SHEET FOR SAMPLING EQUIPMENT | HM-254 | AZAR AB | 2015-10-20 | 2016-10-10 15:34 |  | No | 356 | 2016-11-12 15:24 | [7 empty] | 2016-11-12 20:00 | Yes | 0
VD-9001-254-DSH-134 | 1 | DATA SHEET FOR BURNER | HM-254 | AZAR AB | 2015-10-20 | 2016-05-14 16:09 |  | No | 207 | 2016-07-13 09:44 | [7 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-254-DSH-604 | 2 | BOILER DATA SHEET | HM-254 | AZAR AB | 2015-10-20 | 2015-10-14 11:13 |  | No | -6 | 2015-11-25 14:40 | [8 empty] | No | 0
VD-9001-254-DSH-605 | 1 | PRESSURE VESSEL DATA SHEET (DRUM) | HM-254 | AZAR AB | 2015-10-20 | 2015-10-25 07:41 |  | No | 5 | 2015-11-25 15:06 | [8 empty] | No | 0 | 1204-Owner-v | 2019-07-07 10:53
VD-9001-108-DWG-021 | 3 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2015-10-20 | 2015-10-11 10:23 |  | No | -9 |  | 2015-10-07 17:11 | [7 empty] | No | 0
VD-9001-254-PCJ-466 | 2 | HYDROSTATIC TEST PROCEDURE FOR BOILER AT SITE | HM-254 | AZAR AB | 2015-10-20 | 2015-10-13 08:02 | 2015-10-14 16:52 | Yes | -6 |  | 2015-10-26 12:41 | [6 empty] | 2015-10-26 12:42 | Yes | -1 | 1204-Owner-v | 2018-09-09 10:32
VD-9001-254-WMP-802 | 1 | WELDING & NDE MAP FOR STEAM DRUM | HM-254 | AZAR AB | 2015-10-21 | 2015-10-07 11:02 | 2015-10-07 12:21 | Yes | -14 |  | 2015-10-20 16:09 | [6 empty] | 2015-10-20 16:10 | Yes | -1
VD-9001-206B-DIS-001 | 0 | VENDOR DOCUMENT INDEX & SCHEDULE | PV-206B | TASHA | 2015-10-10 | 2018-09-04 15:44 | 2018-09-04 15:44 | Yes | 1060 |  |  | 2018-09-24 08:39 | [5 empty] | 2018-09-24 08:39 | Yes | 6
VD-9001-206B-ITP-004 | 0 | INSPECTION AND TEST PLAN | PV-206B | TASHA | 2015-10-10 | 2016-01-04 19:36 |  | No | 86 | 2016-05-31 11:15 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:55
VD-9001-206B-PCJ-005 | 0 | RADIOGRPHY TEST PROCEDURE (RT) | PV-206B | TASHA | 2015-10-15 | 2015-10-11 08:03 |  | No | -4 | 2016-02-20 14:48 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-206B-PCJ-006 | 0 | MAGNETIC TEST PROCEDURE (MT) | PV-206B | TASHA | 2015-10-15 | 2015-10-11 08:04 | 2015-10-11 14:12 | Yes | -4 |  | 2016-02-20 14:46 | [6 empty] | 2016-02-20 20:00 | Yes | 118
VD-9001-206B-PCJ-007 | 0 | LIQUID PENETRANT TEST PROCEDURE (PT) | PV-206B | TASHA | 2015-10-15 | 2015-10-11 08:04 |  | No | -4 | 2016-02-20 14:54 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-206B-PCJ-008 | 0 | ULTRASONIC TEST PROCEDURE (UT) | PV-206B | TASHA | 2015-10-15 | 2015-10-11 08:04 |  | No | -4 | 2016-02-20 14:50 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-206B-PCJ-009 | 0 | VISUAL INSPECTION PROCEDURE (VT) | PV-206B | TASHA | 2015-10-15 | 2015-10-11 08:05 |  | No | -4 | 2016-02-29 09:07 | [7 empty] | 2016-02-29 20:00 | Yes | 0
VD-9001-206B-PCJ-010 | 0 | PAUT PROCEDURE | PV-206B | TASHA | 2015-10-15 | 2016-01-04 19:42 | 2016-01-04 19:43 | Yes | 81 |  |  | 2018-06-09 17:39 | [5 empty] | 2018-06-09 17:39 | Yes | 873
VD-9001-206B-PCJ-011 | 0 | POST WELD HEAT TREATMENT PROCEDURE(P.W.H.T) | PV-206B | TASHA | 2016-01-30 | 2016-01-04 19:43 |  | No | -26 | 2016-01-31 16:55 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-206B-PCJ-012 | 0 | PACKING,MARKING & SHIPPING PROCEDURE | PV-206B | TASHA | 2016-01-30 | 2016-02-13 08:43 | 2016-02-13 08:44 | Yes | 14 |  | 2016-03-02 08:57 | [6 empty] | 2016-03-02 20:00 | Yes | 4
VD-9001-206B-PCJ-013 | 0 | HYDROSTATIC TEST PROCEDURE | PV-206B | TASHA | 2016-01-30 | 2016-02-13 08:44 |  | No | 14 | 2016-02-29 16:32 | [7 empty] | 2016-02-29 20:00 | Yes | 0
VD-9001-206B-PCJ-014 | 0 | REPAIR PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-01-04 19:44 |  | No | -55 | 2016-01-31 16:50 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-206B-PCJ-015 | 0 | PAINTING PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-02-13 08:44 |  | No | -15 | 2016-03-02 08:52 | [7 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-206B-PCJ-016 | 0 | HARDNESS TEST PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-01-04 19:35 |  | No | -55 | 2016-01-31 16:56 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-206B-PCJ-017 | 0 | PMI PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-01-04 19:43 |  | No | -55 | 2016-01-31 16:53 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-206B-PCJ-018 | 0 | FERRITE CHECKING PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-01-04 19:34 |  | No | -55 | 2016-01-31 16:58 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-206B-PCJ-019 | 0 | PICKLING&PASSIVATION PROCEDURE | PV-206B | TASHA | 2016-02-28 | 2016-02-13 08:46 |  | No | -15 | 2016-03-02 08:54 | [7 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-206B-PCJ-020 | 0 | CLADING PROCEDURE | PV-206B | TASHA | 2015-12-30 | 2017-01-12 08:14 |  | No | 379 | 2017-03-11 15:44 | [7 empty] | 2017-03-11 20:00 | Yes | 0
VD-9001-206B-WBK-021 | 0 | WELDING BOOK (WPS & PQR) | PV-206B | TASHA | 2015-12-30 | 2016-01-04 19:56 |  | No | 5 | 2016-02-02 13:59 | [7 empty] | 2016-02-02 20:02 | Yes | 0
VD-9001-206B-WMP-022 | 0 | WELDING MAP&NDT TABLE | PV-206B | TASHA | 2015-12-30 | 2016-01-04 20:00 |  | No | 5 | 2016-02-06 14:08 | [7 empty] | 2016-02-06 20:02 | Yes | 0
VD-9001-206B-INX-023 | 0 | FINAL VENDOR DATA BOOK INDEX | PV-206B | TASHA | 2016-11-30 | 2017-07-13 08:00 | 2017-07-13 08:01 | Yes | 225 |  |  |  | 2018-04-18 16:18 |  |  |  |  | 2018-04-18 16:18 | Yes | 265
VD-9001-206B-LST-024 | 0 | SUB VENDOR LIST | PV-206B | TASHA | 2015-10-10 | 2018-09-02 11:40 | 2018-09-02 11:40 | Yes | 1058 |  |  | 2018-09-09 16:14 | [5 empty] | 2018-09-09 16:14 | Yes | -7
VD-9001-206B-LST-025 | 0 | WQT/ WELDER LIST | PV-206B | TASHA | 2015-12-30 | 2018-09-02 13:54 | 2018-09-02 13:56 | Yes | 977 |  |  | 2018-09-24 08:26 | [5 empty] | 2018-09-24 08:26 | Yes | 8
VD-9001-206B-LST-026 | 0 | SPARE PART LIST (COMMISSIONING) | PV-206B | TASHA | 2016-09-30 | 2017-07-02 08:47 | 2017-07-02 08:48 | Yes | 275 |  | 2017-08-07 11:19 | [6 empty] | 2017-08-07 19:58 | Yes | 22 | 1204-Owner-v | 2018-04-04 15:04
VD-9001-206B-LST-027 | 0 | SPARE PART LIST (TWO YEARS) | PV-206B | TASHA | 2016-09-30 | 2017-07-02 08:47 | 2017-07-02 08:48 | Yes | 275 |  | 2017-08-07 11:23 | [6 empty] | 2017-08-07 19:58 | Yes | 22 | 1204-Owner-v | 2018-04-04 15:05
VD-9001-206B-ORC-028 | 0 | ORGANIZATION CHART | PV-206B | TASHA | 2015-10-10 | 2017-08-08 09:29 | 2017-08-08 09:29 | Yes | 668 |  | 2018-01-02 11:10 | [6 empty] | 2018-01-02 19:59 | Yes | 133
VD-9001-206B-PCJ-029 | 0 | NDT PESONAL QUALIFICATION | PV-206B | TASHA | 2015-12-30 | 2017-08-08 09:29 | 2017-08-08 09:30 | Yes | 587 |  | 2018-01-02 11:16 | [6 empty] | 2018-01-02 19:59 | Yes | 133
VD-9001-206B-PCJ-030 | 0 | FABRICATION SEQUENCE PROCEDURE | PV-206B | TASHA | 2015-10-30 | 2016-05-29 15:08 | 2016-05-29 15:05 | Yes | 212 |  | 2016-09-17 09:53 | [6 empty] | 2016-09-17 19:56 | Yes | 97
VD-9001-206B-CAL-001 | 0 | MECHANICAL CALCULATION BOOK -T-1001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 17:56 |  | No | 3 | 2015-10-28 16:08 | [8 empty] | No | 0
VD-9001-206B-CAL-002 | 0 | EXTERNAL ATTACHMENT CALCULATION-T-1001 | PV-206B | TASHA | 2016-03-30 | 2015-11-28 14:24 |  | No | -123 | 2016-01-05 14:25 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-206B-CAL-003 | 0 | FEA CALCULATION FOR CONE AND TRIPLE FORGE -T-1001 | PV-206B | TASHA | 2015-12-30 | 2015-10-10 18:54 |  | No | -81 |  | 2016-01-05 15:31 | [6 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-206B-CAL-004 | 0 | LIFTING/TAILING LUG CALCULATION-T-1001 | PV-206B | TASHA | 2015-10-31 | 2016-02-01 09:35 |  | No | 93 | 2016-02-29 16:03 | [7 empty] | 2016-02-29 20:00 | Yes | 0
VD-9001-206B-DWG-011 | 0 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 18:01 |  | No | 3 | 2015-10-20 08:53 | [8 empty] | No | 0 | 1204-Owner-v | 2020-05-11 11:36
VD-9001-206B-DWG-012 | 0 | BODY & SUPPORT DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2015-10-30 | 2016-02-08 11:56 |  | No | 101 | 2016-02-29 11:20 | [7 empty] | 2016-02-29 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:33
VD-9001-206B-DWG-013 | 0 | MANHOLE & NOZZLE DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2015-11-24 | 2016-02-29 15:52 |  | No | 97 | 2016-03-09 10:39 | [7 empty] | 2016-03-09 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:35
VD-9001-206B-DWG-014 | 0 | INTERNAL ATTACHMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-01-20 | 2016-02-29 15:54 |  | No | 40 | 2016-03-09 09:06 | [7 empty] | 2016-03-09 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:37
VD-9001-206B-DWG-015 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-03-16 17:51 |  | No | -14 | 2016-05-31 11:52 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2018-12-21 11:31
VD-9001-206B-DWG-016 | 0 | INSULATION SUPPORT DRAWING -T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-05-29 12:16 |  | No | 60 | 2016-07-10 14:30 | [7 empty] | 2016-07-10 19:58 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:34
VD-9001-206B-DWG-017 | 0 | TOP DAVIT DRAWING -T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-04-03 08:03 |  | No | 4 | 2016-04-12 15:48 | [7 empty] | 2016-04-12 19:59 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:34
VD-9001-206B-DWG-018 | 0 | PIPE CLIP DRAWING -T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-04-03 08:05 |  | No | 4 | 2016-05-04 15:56 | [7 empty] | 2016-05-04 19:59 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:34
VD-9001-206B-DWG-019 | 0 | NAME PLATE DRAWING -T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-03-28 14:19 |  | No | -2 | 2016-05-31 09:26 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:35
VD-9001-206B-DWG-020 | 0 | TEMPLATE DRAWING -T-1001 | PV-206B | TASHA | 2015-11-04 | 2016-01-03 10:45 | 2016-01-04 09:49 | Yes | 61 |  | 2016-02-20 14:03 | [6 empty] | 2016-02-20 20:00 | Yes | 34 | 1204-Owner-v | 2019-05-09 08:18
VD-9001-206B-DWG-021 | 0 | SHIPPING DRAWING-T-1001 | PV-206B | TASHA | 2016-03-30 | 2016-10-08 10:59 |  | No | 192 | 2016-12-28 10:50 | [7 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-206B-CAL-031 | 0 | MECHANICAL CALCULATION BOOK -T-2001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 18:04 |  | No | 3 | 2015-10-28 16:09 | [8 empty] | No | 0
VD-9001-206B-CAL-032 | 0 | EXTERNAL ATTACHMENT CALCULATION-T-2001 | PV-206B | TASHA | 2016-01-06 | 2015-11-29 15:11 |  | No | -38 | 2016-01-05 14:30 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-206B-CAL-033 | 0 | LIFTING/TAILING LUG CALCULATION-T-2001 | PV-206B | TASHA | 2015-10-31 | 2016-01-28 14:49 |  | No | 89 | 2016-02-22 10:58 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-206B-DWG-041 | 0 | GENERAL ARRANGMENT DRAWING -T-2001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 18:09 |  | No | 3 | 2015-10-20 12:04 | [8 empty] | No | 0 | 1204-Owner-v | 2020-05-11 11:38
VD-9001-206B-DWG-042 | 0 | BODY & SUPPORT DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2015-10-31 | 2015-12-26 17:09 |  | No | 56 | 2016-02-14 17:15 | [7 empty] | 2016-02-14 20:04 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:37
VD-9001-206B-DWG-043 | 0 | MANHOLE & NOZZLE DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2015-11-24 | 2016-01-24 16:39 |  | No | 61 | 2016-02-22 11:29 | [7 empty] | 2016-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:41
VD-9001-206B-DWG-044 | 0 | INTERNAL ATTACHMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-01-20 | 2016-01-24 16:36 |  | No | 4 |  | 2016-02-22 10:48 | [6 empty] | 2016-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:38
VD-9001-206B-DWG-045 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-2001 | PV-206B | TASHA | 2016-01-06 | 2016-03-16 17:46 |  | No | 70 | 2016-04-09 17:14 | [7 empty] | 2016-04-09 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:40
VD-9001-206B-DWG-046 | 0 | INSULATION SUPPORT DRAWING -T-2001 | PV-206B | TASHA | 2016-01-06 |  |  | No | 1626 | [9 empty] | No | 0
VD-9001-206B-DWG-047 | 0 | TOP DAVIT DRAWING -T-2001 | PV-206B | TASHA | 2016-01-06 | 2016-03-03 10:52 |  | No | 57 |  | 2016-03-12 09:18 | [6 empty] | 2016-03-12 19:59 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:39
VD-9001-206B-DWG-048 | 0 | PIPE CLIP DRAWING -T-2001 | PV-206B | TASHA | 2016-01-06 | 2016-03-07 14:31 |  | No | 61 | 2016-03-16 11:03 | [7 empty] | 2016-03-16 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:39
VD-9001-206B-DWG-049 | 0 | NAME PLATE DRAWING -T-2001 | PV-206B | TASHA | 2016-01-06 | 2016-03-03 10:53 |  | No | 57 | 2016-03-12 11:46 | [7 empty] | 2016-03-12 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:40
VD-9001-206B-DWG-050 | 0 | TEMPLATE DRAWING -T-2001 | PV-206B | TASHA | 2015-11-04 | 2016-01-03 10:47 | 2016-01-04 09:48 | Yes | 61 |  | 2016-02-20 14:05 | [6 empty] | 2016-02-20 20:00 | Yes | 34 | 1204-Owner-v | 2019-05-09 08:19
VD-9001-206B-DWG-051 | 0 | SHIPPING DRAWING-T-2001 | PV-206B | TASHA | 2016-01-06 | 2016-08-28 18:48 |  | No | 235 | 2016-12-28 10:38 | [7 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-206B-CAL-061 | 0 | MECHANICAL CALCULATION BOOK -T-4001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 18:12 |  | No | 3 | 2015-10-28 16:09 | [8 empty] | No | 0
VD-9001-206B-CAL-062 | 0 | EXTERNAL ATTACHMENT CALCULATION-T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-02-29 16:53 |  | No | -30 |  | 2016-03-02 08:50 | [6 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-206B-CAL-063 | 0 | LIFTING/TAILING LUG CALCULATION-T-4001 | PV-206B | TASHA | 2015-10-31 | 2016-01-28 14:50 |  | No | 89 | 2016-02-22 11:01 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-206B-DWG-071 | 0 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2015-10-07 | 2015-10-10 18:14 |  | No | 3 | 2015-10-20 12:04 | [8 empty] | No | 0 | 1204-Owner-v | 2020-05-11 11:41
VD-9001-206B-DWG-072 | 0 | BODY & SUPPORT DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2015-10-31 | 2015-12-26 17:23 |  | No | 56 | 2016-02-28 10:59 | [7 empty] | 2016-02-28 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:41
VD-9001-206B-DWG-073 | 0 | MANHOLE & NOZZLE DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2015-11-24 | 2016-01-24 16:47 |  | No | 61 | 2016-02-22 11:22 | [7 empty] | 2016-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:43
VD-9001-206B-DWG-074 | 0 | INTERNAL ATTACHMENT DRAWING -T-4001 | PV-206B | TASHA | 2016-01-20 | 2016-01-25 18:21 |  | No | 5 |  | 2016-02-22 10:53 | [6 empty] | 2016-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:41
VD-9001-206B-DWG-075 | 0 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-03-16 17:45 |  | No | -14 | 2016-04-13 10:24 | [7 empty] | 2016-04-13 19:59 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:43
VD-9001-206B-DWG-076 | 0 | INSULATION SUPPORT DRAWING -T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-05-29 12:18 |  | No | 60 | 2016-07-10 14:32 | [7 empty] | 2016-07-10 19:58 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:42
VD-9001-206B-DWG-077 | 0 | TOP DAVIT DRAWING -T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-03-07 14:37 |  | No | -23 |  | 2016-03-12 09:02 | [6 empty] | 2016-03-12 19:59 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:43
VD-9001-206B-DWG-078 | 0 | PIPE CLIP DRAWING -T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-03-07 14:38 |  | No | -23 | 2016-03-14 10:33 | [7 empty] | 2016-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 11:43
VD-9001-206B-DWG-079 | 0 | NAME PLATE DRAWING -T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-03-03 10:54 |  | No | -27 | 2016-03-12 11:51 | [7 empty] | 2016-03-12 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:33
VD-9001-206B-DWG-080 | 0 | TEMPLATE DRAWING -T-4001 | PV-206B | TASHA | 2015-11-04 | 2016-01-03 10:48 | 2016-01-04 09:46 | Yes | 61 |  | 2016-02-20 14:04 | [6 empty] | 2016-02-20 20:00 | Yes | 34 | 1204-Owner-v | 2019-05-09 08:19
VD-9001-206B-DWG-081 | 0 | SHIPPING DRAWING-T-4001 | PV-206B | TASHA | 2016-03-30 | 2016-08-27 08:58 |  | No | 150 | 2016-12-28 10:58 | [7 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-204A-PCJ-001 | 1 | Magnetic Particle Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-24 | 2015-12-21 13:44 |  | No | 58 | 2015-12-26 18:04 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-204A-PCJ-002 | 1 | Liquid Penetration Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-24 | 2015-12-21 13:51 | 2015-12-21 15:30 | Yes | 58 |  | 2015-12-27 11:31 | [6 empty] | 2015-12-27 20:03 | Yes | -8
VD-9001-204A-PCJ-006 | 1 | Hardness Test Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-10-24 | 2015-10-11 09:36 | 2015-10-11 10:20 | Yes | -13 |  | 2015-11-21 17:02 | [6 empty] | 2015-11-21 17:03 | Yes | 27
VD-9001-108-DWG-016 | 3 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-10-24 | 2015-10-26 11:49 |  | No | 2 | 2015-11-02 17:30 | [8 empty] | No | 0
VD-9001-254-WMP-805 | 1 | WELDING & NDE MAP FOR SUPER HEATER HEADERS | HM-254 | AZAR AB | 2015-10-25 | 2015-11-15 15:52 |  | No | 21 | [9 empty] | No | 0
VD-9001-108-MNL-056 | 2 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2015-10-27 | 2016-03-08 10:05 |  | No | 133 | 2016-03-15 16:44 | [7 empty] | 2016-03-15 20:00 | Yes | 0
VD-9001-108-DWG-035 | 1 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2015-10-27 | 2015-11-23 11:02 |  | No | 27 |  | 2015-12-15 17:31 | [7 empty] | No | 0
VD-9001-205A-WPS-058 | 3 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-27 | 2015-10-14 15:56 |  | No | -13 |  | 2015-10-19 17:43 | [7 empty] | No | 0
VD-9001-205A-DWG-007 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-27 | 2015-12-22 08:34 | 2015-12-22 10:16 | Yes | 56 |  | 2015-12-24 13:20 | [6 empty] | 2015-12-24 20:03 | Yes | -12
VD-9001-205A-PCJ-060 | 1 | PICKLING & PASSIVATION PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-27 | 2015-10-17 15:49 | 2015-10-25 11:25 | Yes | -2 |  | 2015-10-28 16:53 | [6 empty] | 2015-10-28 16:54 | Yes | -3
VD-9001-205A-WPQ-059 | 1 | WELDERS PERFORMANCE QUALIFICATION (WPQ) | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-27 | 2015-10-17 15:50 | 2015-10-25 11:26 | Yes | -2 |  | 2015-10-28 16:54 | [6 empty] | 2015-10-28 16:55 | Yes | -3
VD-9001-204A-CAL-070 | 1 | Strength Calculation FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-10-28 | 2015-11-01 14:14 |  | No | 4 | 2015-12-14 14:14 | [8 empty] | No | 0
VD-9001-204A-CAL-060 | 1 | Strength Calculation FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-10-28 | 2015-10-28 19:09 |  | No | 0 | 2015-12-09 17:06 | [8 empty] | No | 0
VD-9001-254-DSH-219 | 0 | DATA SHEET FOR JUNCTION BOXES | HM-254 | AZAR AB | 2015-10-14 | 2015-10-14 14:54 |  | No | 0 | 2015-11-25 14:41 | [8 empty] | No | 0
VD-9001-206A-DWG-015 | 4 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING ( T-3002 ) | PV-206A | TASHA | 2015-10-17 09:05 | 2015-10-17 11:38 | 2015-10-17 11:57 | Yes | 0 |  | 2015-10-18 14:28 | [6 empty] | 2015-10-18 14:29 | Yes | -13
VD-9001-205A-DWG-031 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-31 | 2015-12-13 13:17 |  | No | 43 | 2016-01-05 14:16 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-204A-DWG-061 | 1 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-10-31 | 2015-10-28 19:10 |  | No | -3 | 2015-12-09 17:07 | [8 empty] | No | 0
VD-9001-205A-DWG-039 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-31 | 2015-10-21 13:38 | 2015-10-22 11:31 | Yes | -9 |  | 2015-12-24 12:29 | [6 empty] | 2015-12-24 20:03 | Yes | 50
VD-9001-205A-DWG-048 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-31 | 2015-12-20 12:45 | 2015-12-20 15:34 | Yes | 50 |  | 2015-12-24 13:09 | [6 empty] | 2015-12-24 20:03 | Yes | -10
VD-9001-204A-DWG-071 | 1 | General Arrangement Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-10-31 | 2015-11-01 14:18 |  | No | 1 | 2015-12-14 14:15 | [8 empty] | No | 0
VD-9001-205A-DWG-040 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-31 | 2015-10-21 13:38 | 2015-10-22 11:32 | Yes | -9 |  | 2015-12-24 12:29 | [6 empty] | 2015-12-24 20:03 | Yes | 50
VD-9001-205A-DWG-032 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-10-31 | 2015-12-13 13:17 |  | No | 43 |  | 2015-12-24 12:53 | [6 empty] | 2015-12-24 20:03 | Yes | 0
VD-9001-108-MNL-058 | 1 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2015-11-01 | 2015-11-09 08:41 |  | No | 8 | 2015-12-01 16:24 | [8 empty] | No | 0
VD-9001-108-MDL-054 | 3 | GENERAL INDEX | PR-108 | Farabard | 2015-11-01 | 2015-11-02 12:57 |  | No | 1 | 2015-11-23 16:38 | [8 empty] | No | 0
VD-9001-108-DWG-041 | 1 | GEAR REDUCER & ELECTRO MOTOR BASE PLATE DETAIL | PR-108 | Farabard | 2015-11-01 | 2015-10-20 13:11 |  | No | -12 |  | 2015-10-26 10:36 | [7 empty] | No | 0
VD-9001-254-EQL-110 | 1 | MAIN EQUIPMENT LIST | HM-254 | AZAR AB | 2015-11-01 | 2016-11-05 08:46 |  | No | 370 | 2016-11-29 10:52 | [7 empty] | 2016-11-29 20:00 | Yes | 0 | 1204-Owner-v | 2018-09-09 13:22
VD-9001-254-SLD-210 | 2 | SINGLE LINE DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2015-11-10 08:33 |  | No | 9 | 2015-12-23 10:24 | [7 empty] | 2015-12-23 20:03 | Yes | 0
VD-9001-254-PID-114 | 2 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:04 |  | No | 69 | 2016-02-22 14:51 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-PID-115 | 2 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:06 |  | No | 69 | 2016-02-22 14:57 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-PID-116 | 2 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:07 |  | No | 69 | 2016-02-22 15:06 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-PID-117 | 2 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-05-10 07:21 |  | No | 191 | 2016-06-11 10:47 | [7 empty] | 2016-06-11 19:58 | Yes | 0
VD-9001-254-PID-118 | 2 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:08 |  | No | 69 | 2016-02-22 15:09 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-PID-119 | 1 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:09 |  | No | 69 | 2016-02-23 14:10 | [7 empty] | 2016-02-23 20:00 | Yes | 0
VD-9001-254-PID-120 | 2 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:09 |  | No | 69 | 2016-02-23 14:07 | [7 empty] | 2016-02-23 20:00 | Yes | 0
VD-9001-254-PID-121 | 1 | STEAM TURBINE P&I DIAGRAM | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:09 |  | No | 69 | 2016-02-23 14:14 | [7 empty] | 2016-02-23 20:00 | Yes | 0
VD-9001-254-LGD-122 | 2 | P&I DIAGRAM SYMBOLS & LEGENDS | HM-254 | AZAR AB | 2015-11-01 | 2016-01-09 15:10 |  | No | 69 | 2016-02-23 14:17 | [7 empty] | 2016-02-23 20:00 | Yes | 0 | 1204-Owner-v | 2019-07-10 10:28
VD-9001-205A-DWG-044 | 3 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-11-02 | 2015-12-08 10:57 | 2015-12-08 11:56 | Yes | 36 | 2015-12-24 12:48 | [7 empty] | 2015-12-24 20:03 | Yes | 2
VD-9001-206B-DWG-011 | 1 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2015-11-03 | 2015-11-28 10:18 |  | No | 25 | 2016-01-19 18:48 | [7 empty] | 2016-01-19 20:02 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:35
VD-9001-206B-DWG-041 | 1 | GENERAL ARRANGMENT DRAWING -T-2001 | PV-206B | TASHA | 2015-11-03 | 2015-11-29 15:12 |  | No | 26 | 2016-02-02 14:18 | [7 empty] | 2016-02-02 20:02 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:35
VD-9001-206B-DWG-071 | 1 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2015-11-03 | 2015-11-25 17:04 |  | No | 22 | 2016-01-19 18:46 | [7 empty] | 2016-01-19 20:02 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:35
VD-9001-254-DSH-356 | 1 | DATA SHEET FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2015-11-03 | 2018-08-26 14:02 | 2018-08-26 14:02 | Yes | 1027 |  |  | 2018-09-05 17:06 | [5 empty] | 2018-09-05 17:06 | Yes | -4 | 1204-Owner-v | 2019-12-09 08:40
VD-9001-254-DIG-338 | 1 | CAUSE AND EFFECT DIAGRAM | HM-254 | AZAR AB | 2015-11-03 | 2016-05-08 07:20 |  | No | 187 | 2016-06-08 14:33 | [7 empty] | 2016-06-08 19:58 | Yes | 0 | 1204-Owner-v | 2019-10-15 13:38
VD-9001-254-DWG-730 | 1 | ANCHOR BOLT, ANCHOR PLATE &TEMPLATE FABRICATION DETAIL FOR STEEL STACK | HM-254 | AZAR AB | 2015-11-04 | 2015-11-29 15:16 | 2015-11-29 17:34 | Yes | 25 |  | 2016-02-22 11:29 | [6 empty] | 2016-02-22 20:00 | Yes | 71 | 1204-Owner-v | 2019-05-09 08:19
VD-9001-254-DWG-727 | 1 | ANCHOR BOLT FABRICATION DETAIL FOR AIR DUCT SUPPORT | HM-254 | AZAR AB | 2015-11-04 | 2015-10-31 10:10 | 2015-10-31 14:47 | Yes | -4 |  | 2016-01-02 11:39 | [6 empty] | 2016-01-02 20:03 | Yes | 49
VD-9001-254-DWG-728 | 1 | ANCHOR BOLT FABRICATION DETAIL FOR ST. STR. OF ECONOMIZER SUPPORT | HM-254 | AZAR AB | 2015-11-04 | 2015-10-31 10:11 | 2015-10-31 14:50 | Yes | -4 |  | 2016-01-02 11:39 | [6 empty] | 2016-01-02 20:03 | Yes | 49
VD-9001-254-DSH-352 | 1 | DATA SHEET FOR O2 GAS ANALYZER | HM-254 | AZAR AB | 2015-11-04 | 2016-05-11 12:52 | 2016-05-11 12:53 | Yes | 189 |  | 2016-07-10 14:15 | [6 empty] | 2016-07-10 19:58 | Yes | 46 | 1204-Owner-v | 2019-09-22 14:44
VD-9001-204A-PCJ-003 | 1 | Ultrasonic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-11-04 | 2015-10-26 08:47 |  | No | -9 | 2015-11-14 11:09 | [8 empty] | No | 0
VD-9001-204A-CAL-170 | 1 | Strength Calculation FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-04 | 2015-12-24 14:38 |  | No | 50 | 2016-01-10 15:24 | [7 empty] | 2016-01-10 20:03 | Yes | 0
VD-9001-204A-DWG-171 | 1 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2015-11-04 | 2015-12-24 14:38 |  | No | 50 | 2016-01-19 10:40 | [7 empty] | 2016-01-19 20:02 | Yes | 0
VD-9001-204A-CAL-010 | 1 | Strength Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-04 | 2016-01-02 18:57 |  | No | 59 | 2016-01-19 15:18 | [7 empty] | 2016-01-19 20:02 | Yes | 0
VD-9001-254-DSH-357 | 1 | DATA SHEET FOR FLUE GAS ANALYZERS | HM-254 | AZAR AB | 2015-11-08 |  |  | No | 1685 | [9 empty] | No | 0
VD-9001-254-DSH-221 | 0 | DATA SHEET FOR LIGHTING FIXTURE & SOCKETS | HM-254 | AZAR AB | 2015-10-25 | 2015-10-25 10:23 | 2015-10-25 10:36 | Yes | 0 |  | 2015-11-25 15:07 | [6 empty] | 2015-11-25 15:08 | Yes | 17 | 1204-Owner-v | 2018-01-28 08:57
VD-9001-108-DBS-006 | 2 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2015-11-08 | 2015-10-31 13:40 |  | No | -8 | 2015-11-11 10:48 | [8 empty] | No | 0
VD-9001-204A-DWG-081 | 1 | General Arrangement Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-11-08 | 2015-11-02 17:08 |  | No | -6 | 2015-12-14 17:23 | [8 empty] | No | 0
VD-9001-105-LST-102 | 1 | Line list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-09 | 2015-10-27 12:16 |  | No | -13 |  | 2015-11-04 09:31 | [7 empty] | No | 0
VD-9001-254-WPS-826 | 1 | PREQUALIFIED WPS FOR STEEL STRUCTURE AND SUPPORTS | HM-254 | AZAR AB | 2015-11-09 | 2015-11-16 13:40 |  | No | 7 | 2015-12-16 11:07 | [8 empty] | No | 0
VD-9001-204A-CAL-040 | 1 | Strength Calculation FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-09 | 2017-09-20 11:06 |  | No | 1684 |  | 2017-10-31 11:37 | [6 empty] | 2017-10-31 19:59 | Yes | 0
VD-9001-204A-DWG-041 | 1 | General Arrangement Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-11-09 | 2015-11-07 17:36 |  | No | -2 | 2015-12-16 17:45 | [8 empty] | No | 0
VD-9001-204A-CAL-020 | 1 | Strength Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-10 | 2015-11-08 21:19 |  | No | -2 | 2015-12-23 15:00 | [7 empty] | 2015-12-23 20:03 | Yes | 0
VD-9001-204A-DWG-021 | 1 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2015-11-10 | 2015-11-08 21:27 |  | No | -2 | 2015-12-23 15:00 | [7 empty] | 2015-12-23 20:03 | Yes | 0
VD-9001-253(A)-DWG-005 | 1 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-11-11 | 2015-11-29 15:33 |  | No | 18 | 2016-01-06 09:05 | [7 empty] | 2016-01-06 20:03 | Yes | 0
VD-9001-206B-CAL-001 | 1 | MECHANICAL CALCULATION BOOK -T-1001 | PV-206B | TASHA | 2015-11-11 | 2015-11-28 10:14 |  | No | 17 | 2015-12-15 12:11 | [8 empty] | No | 0
VD-9001-206B-CAL-031 | 1 | MECHANICAL CALCULATION BOOK -T-2001 | PV-206B | TASHA | 2015-11-11 | 2015-11-29 14:49 |  | No | 18 | 2015-12-15 12:15 | [8 empty] | No | 0
VD-9001-206B-CAL-061 | 1 | MECHANICAL CALCULATION BOOK -T-4001 | PV-206B | TASHA | 2015-11-11 | 2015-11-25 16:54 |  | No | 14 | 2015-12-15 12:07 | [8 empty] | No | 0
VD-9001-105-LST-101 | 1 | Utility consumption list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-11 | 2015-11-11 15:32 | 2015-11-12 12:18 | Yes | 1 |  | 2015-11-25 11:51 | [6 empty] | 2015-11-25 11:52 | Yes | 0 | 1204-Owner-v | 2019-01-04 21:31
VD-9001-257A-PQR-001 | 2 | Procedure Qualification Record (PQR) For CS | HM-257A | ABAN AIR COOLER. | 2015-11-11 | 2016-02-24 08:06 | 2016-02-24 08:07 | Yes | 105 |  |  | 2018-03-25 10:40 | [5 empty] | 2018-03-25 10:40 | Yes | 746
VD-9001-257A-WPS-001 | 2 | Welding Procedure Specification (WPS) For CS | HM-257A | ABAN AIR COOLER. | 2015-11-11 | 2016-02-24 07:59 | 2016-02-24 08:00 | Yes | 105 |  | 2016-04-17 17:29 | [6 empty] | 2016-04-17 19:59 | Yes | 39
VD-9001-204A-CAL-150 | 1 | Strength Calculation FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-14 | 2015-11-09 20:26 |  | No | -5 | 2015-12-20 16:09 | [8 empty] | No | 0
VD-9001-204A-DWG-151 | 1 | General Arrangement Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2015-11-14 | 2015-11-09 20:27 |  | No | -5 | 2015-12-20 16:10 | [8 empty] | No | 0
VD-9001-253(A)-DWG-035 | 3 | STEEL STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-11-14 | 2015-11-18 08:20 | 2015-11-18 17:43 | Yes | 4 |  | 2015-12-16 10:55 | [6 empty] | 2015-12-16 10:56 | Yes | 14 | 1204-Owner-v | 2018-08-14 17:34
VD-9001-254-DWH-586 | 1 | DRAIN LIST AND LOCATION | HM-254 | AZAR AB | 2015-11-15 | 2015-11-01 11:48 |  | No | -14 | 2015-11-25 14:59 | [8 empty] | No | 0
VD-9001-254-DSH-150 | 1 | DATA SHEET FOR STEAM TURBINE OF F.D. FAN | HM-254 | AZAR AB | 2015-11-15 |  |  | No | 1678 | [9 empty] | No | 0
VD-9001-254-DSH-151 | 1 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2015-11-15 | 2016-10-03 10:27 |  | No | 323 | 2017-01-01 09:55 | [7 empty] | 2017-01-01 19:59 | Yes | 0
VD-9001-254-DWG-347 | 1 | INSTALLATION DRAWINGS & PROCEDURES FOR INSTRUMENTS | HM-254 | AZAR AB | 2015-11-15 | 2016-06-18 16:05 |  | No | 216 | 2016-07-04 11:33 | [7 empty] | 2016-07-04 19:58 | Yes | 0
VD-9001-108-DWG-025 | 1 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2015-11-15 | 2015-11-14 16:03 |  | No | -1 | 2015-11-24 11:33 | [8 empty] | No | 0
VD-9001-257A-CAL-009 | 0 | STRENGTH CALCULATION BOOK E-1001 | HM-257A | ABAN AIR COOLER. | 2015-11-14 | 2015-11-03 15:57 |  | No | -11 | 2015-12-06 11:05 | [8 empty] | No | 0
VD-9001-257A-CAL-010 | 0 | STRENGTH CALCULATION BOOK E-1009 | HM-257A | ABAN AIR COOLER. | 2015-11-14 | 2015-11-03 16:08 |  | No | -11 | 2015-12-06 11:05 | [8 empty] | No | 0
VD-9001-257A-DWG-009 | 0 | GENERAL ARRANGEMENT DRAWING E-1001 | HM-257A | ABAN AIR COOLER. | 2015-11-28 | 2015-12-20 12:10 |  | No | 22 | 2016-01-25 09:03 | [7 empty] | 2016-01-25 20:02 | Yes | 0
VD-9001-257A-DWG-010 | 0 | GENERAL ARRANGEMENT DRAWING E-1009 | HM-257A | ABAN AIR COOLER. | 2015-11-28 | 2015-12-08 09:39 |  | No | 10 | 2016-01-27 08:53 | [7 empty] | 2016-01-27 20:02 | Yes | 0
VD-9001-257A-WMP-009 | 0 | WELDING & NDT MAP E-1001 | HM-257A | ABAN AIR COOLER. | 2015-12-10 | 2016-01-24 15:00 |  | No | 45 | 2016-04-03 09:41 | [7 empty] | 2016-04-03 20:00 | Yes | 0
VD-9001-257A-WMP-010 | 0 | WELDING & NDT MAP E-9001 | HM-257A | ABAN AIR COOLER. | 2015-12-10 | 2016-01-24 15:01 |  | No | 45 | 2016-04-03 09:41 | [7 empty] | 2016-04-03 20:00 | Yes | 0
VD-9001-105-PID-101 | 1 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-15 | 2015-11-11 14:40 |  | No | -4 | 2015-12-14 17:29 | [8 empty] | No | 0
VD-9001-254-LST-555 | 1 | VALVE LIST | HM-254 | AZAR AB | 2015-11-16 | 2016-05-11 14:44 |  | No | 177 | 2016-06-18 17:38 | [7 empty] | 2016-06-18 19:58 | Yes | 0 | 1204-Owner-v | 2018-04-09 11:51
VD-9001-108-MNL-057 | 1 | ISTALLATION MANUAL | PR-108 | Farabard | 2015-11-16 | 2015-11-09 08:23 |  | No | -7 | 2015-12-01 16:25 | [8 empty] | No | 0
VD-9001-108-DWG-016 | 4 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-11-16 | 2015-11-21 12:57 |  | No | 5 | 2015-12-15 17:06 | [8 empty] | No | 0
VD-9001-204A-CAL-030 | 1 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-17 | 2015-11-11 18:32 |  | No | -6 | 2015-12-21 12:16 | [8 empty] | No | 0
VD-9001-204A-DWG-031 | 1 | General Arrangement Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2015-11-17 | 2015-11-11 18:33 |  | No | -6 | 2015-12-21 12:17 | [8 empty] | No | 0
VD-9001-105-CAL-101 | 1 | Calculation sheet of safety valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-18 | 2015-11-18 14:20 | 2015-11-18 17:53 | Yes | 0 |  | 2015-11-29 10:12 | [6 empty] | 2015-11-29 10:13 | Yes | -3
VD-9001-105-DSH-105 | 1 | Data sheet of safety valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-18 | 2015-11-18 14:46 |  | No | 0 | 2015-11-29 10:13 | [8 empty] | No | 0
VD-9001-205A-DWG-006 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-11-18 | 2015-11-05 12:59 |  | No | -13 | 2015-12-01 16:37 | [8 empty] | No | 0
VD-9001-204A-CAL-140 | 1 | Strength Calculation FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-18 | 2015-11-12 16:44 |  | No | -6 | 2015-12-22 14:05 | [7 empty] | 2015-12-22 20:03 | Yes | 0
VD-9001-204A-DWG-141 | 1 | General Arrangement Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2015-11-18 | 2015-11-12 16:43 |  | No | -6 | 2015-12-22 14:06 | [7 empty] | 2015-12-22 20:03 | Yes | 0
VD-9001-213A-DWG-087 | 3 | Fixed Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2015-11-04 11:48 | 2016-02-18 07:17 | 2016-02-18 07:18 | Yes | 106 |  | 2016-03-09 11:13 | [6 empty] | 2016-03-09 20:00 | Yes | 6
VD-9001-213A-DWG-088 | 3 | Fixed Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2015-11-04 11:48 | 2016-02-18 07:17 | 2016-02-18 07:18 | Yes | 106 |  | 2016-03-09 11:05 | [6 empty] | 2016-03-09 20:00 | Yes | 6
VD-9001-253(A)-DWG-078 | 2 | MOTOR WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-11-18 | 2016-08-20 15:44 | 2016-08-20 15:25 | Yes | 276 |  | 2016-09-11 15:16 | [6 empty] | 2016-09-11 19:56 | Yes | 8 | 1204-Owner-v | 2018-08-14 17:53
VD-9001-205A-PCJ-062 | 1 | INSTALLATION PROCEDURE | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-11-18 | 2016-04-14 12:42 | 2016-04-14 12:43 | Yes | 148 |  | 2016-04-17 11:18 | [6 empty] | 2016-04-17 19:59 | Yes | -11
VD-9001-253(A)-CAL-021 | 3 | BASE PLATE CALCULATION for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-11-04 17:12 | 2015-11-05 11:29 | 2015-11-08 11:32 | Yes | 4 |  | 2015-11-15 16:12 | [6 empty] | 2015-11-15 16:13 | Yes | -4
VD-9001-253(A)-CAL-051 | 1 | BASE PLATE CALCULATION for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-11-04 17:12 | 2015-11-05 11:30 | 2015-11-08 11:33 | Yes | 4 |  | 2015-11-15 16:13 | [6 empty] | 2015-11-15 16:14 | Yes | -4 | 1204-Owner-v | 2018-01-22 12:16
VD-9001-253(A)-CAL-081 | 4 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-11-04 17:12 | 2015-11-05 11:31 |  | No | 1 | 2015-11-15 16:13 | [8 empty] | No | 0
VD-9001-254-DWG-222 | 0 | CABLE TRENCH LAYOUT | HM-254 | AZAR AB | 2015-11-07 | 2015-11-07 11:09 |  | No | 0 | 2015-11-28 14:45 | [8 empty] | No | 0 | 1204-Owner-v | 2018-04-09 17:02
VD-9001-213A-DWG-108 | 3 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-11-21 | 2015-12-27 10:02 |  | No | 36 | 2016-01-30 14:57 | [7 empty] | 2016-01-30 20:02 | Yes | 0
VD-9001-204A-CAL-160 | 1 | Strength Calculation FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-11-22 | 2015-12-16 18:19 |  | No | 24 | 2016-01-04 11:24 | [7 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-213A-DWG-144 | 4 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-11-22 | 2015-12-16 17:30 |  | No | 24 | 2016-01-02 16:56 | [7 empty] | 2016-01-02 20:03 | Yes | 0
VD-9001-213A-DWG-128 | 5 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2015-11-25 | 2016-02-23 15:05 |  | No | 90 | 2016-03-09 11:51 | [7 empty] | 2016-03-09 20:00 | Yes | 0
VD-9001-213A-DWG-080 | 2 | General Assembly for Tk-7101A | PV-213A | MachineSazi Pars | 2015-11-25 | 2016-04-03 13:20 | 2016-04-03 13:21 | Yes | 130 |  | 2016-04-05 11:26 | [6 empty] | 2016-04-05 20:00 | Yes | -12 | 1204-Owner-v | 2019-01-15 16:29
VD-9001-213A-DWG-081 | 2 | General Assembly for Tk-7101B | PV-213A | MachineSazi Pars | 2015-11-25 | 2016-04-03 13:26 | 2016-04-03 13:26 | Yes | 130 |  | 2016-04-05 11:24 | [6 empty] | 2016-04-05 20:00 | Yes | -12 | 1204-Owner-v | 2019-02-16 09:16
VD-9001-213A-DWG-095 | 4 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-11-25 | 2015-11-16 08:54 |  | No | -9 | 2015-12-07 15:02 | [8 empty] | No | 0
VD-9001-204A-CAL-130 | 1 | Strength Calculation FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-25 | 2016-04-07 14:18 |  | No | 134 | 2016-08-06 10:12 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-204A-DWG-131 | 1 | General Arrangement Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2015-11-25 | 2016-04-06 13:31 |  | No | 133 | 2016-05-09 15:00 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-108-DBS-006 | 3 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2015-11-25 | 2016-01-30 13:35 |  | No | 66 | 2016-02-17 11:24 | [7 empty] | 2016-02-17 20:01 | Yes | 0
VD-9001-205A-DWG-001 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-11-25 | 2015-12-28 15:28 |  | No | 33 | 2016-01-31 16:38 | [7 empty] | 2016-01-31 20:02 | Yes | 0
VD-9001-205A-DWG-047 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-11-25 | 2015-12-20 12:44 |  | No | 25 | 2016-01-05 17:07 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-108-DWG-023 | 2 | SECONDERY BEAMS DETAIL | PR-108 | Farabard | 2015-11-11 11:31 | 2015-11-11 13:21 |  | No | 0 | 2015-11-24 10:29 | [8 empty] | No | 0
VD-9001-108-DWG-024 | 2 | WATER DISTRIBUTION CHANNEL DETAIL | PR-108 | Farabard | 2015-11-11 11:31 | 2015-11-11 13:22 |  | No | 0 |  | 2015-12-01 16:50 | [7 empty] | No | 0
VD-9001-204A-PCJ-003 | 2 | Ultrasonic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2015-11-28 | 2015-12-07 11:53 | 2015-12-07 12:42 | Yes | 9 |  | 2015-12-16 17:05 | [6 empty] | 2015-12-16 17:06 | Yes | -5
VD-9001-253(A)-CAL-081 | 5 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-11-29 | 2015-11-18 08:20 |  | No | -11 | 2015-11-22 10:30 | [8 empty] | No | 0
VD-9001-105-LST-103 | 1 | Piping valve list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-11-30 | 2016-04-29 07:11 |  | No | 151 | 2016-05-07 16:35 | [7 empty] | 2016-05-07 19:59 | Yes | 0
VD-9001-108-PFD-065 | 2 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2015-11-30 | 2017-11-22 14:27 |  | No | 723 | 2017-11-25 16:23 | [7 empty] | 2017-11-25 19:59 | Yes | 0
VD-9001-108-LST-047 | 3 | LOAD LIST | PR-108 | Farabard | 2015-11-30 | 2015-11-21 12:58 |  | No | -9 | 2015-12-05 12:39 | [8 empty] | No | 0
VD-9001-254-DWG-712 | 1 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 1/5 | HM-254 | AZAR AB | 2015-11-16 17:20 | 2015-11-21 09:42 | 2015-11-21 15:48 | Yes | 5 |  | 2016-02-08 10:18 | [6 empty] | 2016-02-08 20:02 | Yes | 65 | 1204-Owner-v | 2019-02-17 16:18
VD-9001-254-DWG-713 | 1 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 2/5 | HM-254 | AZAR AB | 2015-11-16 17:20 | 2015-11-21 09:42 | 2015-11-21 15:51 | Yes | 5 |  | 2016-02-08 10:19 | [6 empty] | 2016-02-08 20:02 | Yes | 65 | 1204-Owner-v | 2019-02-17 16:22
VD-9001-254-DWG-714 | 1 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 3/5 | HM-254 | AZAR AB | 2015-11-16 17:20 | 2015-11-21 09:44 | 2015-11-21 15:49 | Yes | 5 |  | 2016-02-08 10:19 | [6 empty] | 2016-02-08 20:02 | Yes | 65 | 1204-Owner-v | 2019-02-17 16:23
VD-9001-254-DWG-715 | 1 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 4/5 | HM-254 | AZAR AB | 2015-11-16 17:20 | 2015-11-21 09:50 | 2015-11-21 15:52 | Yes | 5 |  | 2016-02-08 10:20 | [6 empty] | 2016-02-08 20:02 | Yes | 65 | 1204-Owner-v | 2019-02-17 16:24
VD-9001-254-DWG-716 | 1 | G.A. OF ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT SUPP. 5/5 | HM-254 | AZAR AB | 2015-11-16 17:20 | 2015-11-21 09:52 | 2015-11-21 15:50 | Yes | 5 |  | 2016-02-08 10:20 | [6 empty] | 2016-02-08 20:02 | Yes | 65 | 1204-Owner-v | 2019-03-04 08:12
VD-9001-204A-DWG-051 | 2 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2015-12-02 | 2015-12-06 10:47 |  | No | 4 | 2016-01-06 09:14 | [7 empty] | 2016-01-06 20:03 | Yes | 0
VD-9001-108-LST-051 | 2 | SPARE PARTS LIST FOR 2 YEARS OF OPERATION | PR-108 | Farabard | 2015-12-02 | 2015-11-23 11:28 |  | No | -9 | 2015-12-15 17:32 | [8 empty] | No | 0
VD-9001-204A-QCP-001 | 1 | Quality Control Plan (QCP) | PV-204A | Asas Sanat Pars Inc. | 2015-12-02 | 2015-11-19 08:59 |  | No | -13 | 2015-12-09 14:23 | [8 empty] | No | 0
VD-9001-254-DSH-223 | 0 | DATA SHEET FOR POWER DISTRIBUTION PANELS | HM-254 | AZAR AB | 2015-11-21 | 2015-11-21 17:09 |  | No | 1672 |  | 2015-12-16 17:10 | [7 empty] | No | 0
VD-9001-254-PQR-815 | 1 | PQR FOR SUPER HEATER (PART I) | HM-254 | AZAR AB | 2015-11-21 15:07 | 2015-11-21 17:08 | 2015-11-21 17:22 | Yes | 0 |  | 2015-12-16 11:04 | [6 empty] | 2015-12-16 11:05 | Yes | 11 | 1204-Owner-v | 2020-05-09 11:05
VD-9001-254-PQR-816 | 1 | PQR FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2015-11-21 15:07 | 2015-11-21 17:09 |  | No | 0 |  | 2015-12-16 11:06 | [7 empty] | No | 0
VD-9001-254-WPS-834 | 1 | WPS FOR SUPER HEATER (PART I) | HM-254 | AZAR AB | 2015-11-21 15:07 | 2015-11-21 17:04 | 2015-11-21 17:21 | Yes | 0 |  | 2015-12-16 11:03 | [6 empty] | 2015-12-16 11:04 | Yes | 11
VD-9001-254-WPS-835 | 1 | WPS FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2015-11-21 15:07 | 2015-11-22 10:19 |  | No | 1 |  | 2015-12-16 11:05 | [7 empty] | No | 0
VD-9001-254-DWG-720 | 1 | G.A. OF ECONOMIZER SUPP. | HM-254 | AZAR AB | 2015-11-21 15:07 | 2015-11-21 17:10 | 2015-11-21 17:26 | Yes | 0 |  | 2016-01-02 17:50 | [6 empty] | 2016-01-02 20:03 | Yes | 28 | 1204-Owner-v | 2018-09-05 14:54
VD-9001-253(A)-CAL-081 | 6 | BASE PLATE CALCULATION for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-12-06 | 2015-11-23 11:39 | 2015-11-23 16:33 | Yes | -13 |  | 2015-11-28 11:45 | [6 empty] | 2015-11-28 11:46 | Yes | -9
VD-9001-253(A)-PCJ-104 | 2 | PAINTING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2015-11-23 09:06 | 2015-11-23 09:15 |  | No | 0 |  | 2015-12-14 10:02 | [7 empty] | No | 0
VD-9001-254-WMP-805 | 2 | WELDING & NDE MAP FOR SUPER HEATER HEADERS | HM-254 | AZAR AB | 2015-11-23 11:19 | 2015-12-01 11:33 |  | No | 8 | 2015-12-16 11:04 | [8 empty] | No | 0
VD-9001-204A-CAL-110 | 1 | Strength Calculation FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-12-07 | 2015-12-02 18:32 |  | No | -5 | 2015-12-26 17:54 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-204A-DWG-111 | 1 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2015-12-07 | 2015-12-02 18:33 |  | No | -5 | 2016-01-06 15:44 | [7 empty] | 2016-01-06 20:03 | Yes | 0
VD-9001-108-MDL-054 | 4 | GENERAL INDEX | PR-108 | Farabard | 2015-12-07 | 2015-11-28 09:34 |  | No | -9 |  | 2015-12-07 11:14 | [7 empty] | No | 0
VD-9001-108-DWG-023 | 3 | SECONDERY BEAMS DETAIL | PR-108 | Farabard | 2015-12-08 | 2015-11-24 12:12 |  | No | -14 |  | 2015-11-25 14:31 | [7 empty] | No | 0
VD-9001-108-DWG-025 | 2 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2015-12-08 | 2015-11-24 12:08 |  | No | -14 |  | 2015-11-25 14:32 | [7 empty] | No | 0
VD-9001-105-PPL-301 | 1 | Plot plan of HRU | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-08 | 2016-01-18 16:15 |  | No | 41 | 2016-02-20 11:09 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-254-DSH-350 | 1 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE TRANSMITTERS | HM-254 | AZAR AB | 2015-12-09 | 2016-04-24 14:50 |  | No | 137 | 2016-05-31 17:13 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2018-04-08 16:58
VD-9001-105-LST-501 | 1 | Spare parts list for two years | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-09 | 2016-07-22 10:13 |  | No | 226 | 2016-10-20 11:50 | [7 empty] | 2016-10-20 20:00 | Yes | 0
VD-9001-105-LST-502 | 1 | Spare parts list for commissioning | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-09 | 2016-07-22 10:13 |  | No | 226 | 2016-10-20 11:49 | [7 empty] | 2016-10-20 20:00 | Yes | 0
VD-9001-254-DSH-604 | 3 | BOILER DATA SHEET | HM-254 | AZAR AB | 2015-12-09 | 2015-12-01 07:31 |  | No | -8 | 2016-02-16 15:18 | [7 empty] | 2016-02-16 20:04 | Yes | 0
VD-9001-254-DSH-219 | 1 | DATA SHEET FOR JUNCTION BOXES | HM-254 | AZAR AB | 2015-12-09 | 2015-12-22 09:00 |  | No | 13 | 2015-12-30 16:26 | [7 empty] | 2015-12-30 20:03 | Yes | 0 | 1204-Owner-v | 2018-05-28 11:56
VD-9001-254-DSH-355 | 1 | DATA SHEET FOR DRUM LEVEL GAUGES | HM-254 | AZAR AB | 2015-12-09 | 2016-05-04 16:39 |  | No | 147 | 2016-05-31 17:21 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-28 12:13
VD-9001-254-LST-217 | 1 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2015-12-09 | 2015-12-22 09:00 |  | No | 13 | 2015-12-30 16:27 | [7 empty] | 2015-12-30 20:03 | Yes | 0
VD-9001-254-DWH-548 | 2 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2015-12-09 | 2016-03-09 15:09 |  | No | 91 | 2016-03-30 16:27 | [7 empty] | 2016-03-30 20:00 | Yes | 0
VD-9001-254-DWH-586 | 2 | DRAIN LIST AND LOCATION | HM-254 | AZAR AB | 2015-12-09 | 2018-11-17 15:22 | 2018-11-17 15:22 | Yes | 1074 |  |  | 2018-11-26 10:44 | [5 empty] | 2018-11-26 10:44 | Yes | -5
VD-9001-254-DSH-605 | 2 | PRESSURE VESSEL DATA SHEET (DRUM) | HM-254 | AZAR AB | 2015-12-09 | 2016-02-15 14:19 | 2016-02-15 14:20 | Yes | 68 |  | 2016-02-28 10:47 | [6 empty] | 2016-02-28 20:00 | Yes | -1
VD-9001-105-DWG-301 | 1 | Piping general arrangement and tie-point list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-12 | 2016-01-18 16:14 |  | No | 37 | 2016-02-20 11:44 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-CAL-201 | 1 | Calculation sheet of control valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-12 | 2015-12-05 17:59 | 2015-12-06 09:34 | Yes | -6 |  | 2015-12-26 11:15 | [6 empty] | 2015-12-26 20:03 | Yes | 7 | 1204-Owner-v | 2019-09-06 22:01
VD-9001-204A-CAL-090 | 1 | Strength Calculation FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-12-12 | 2015-12-16 18:18 |  | No | 4 | 2016-01-10 09:15 | [7 empty] | 2016-01-10 20:03 | Yes | 0
VD-9001-204A-DWG-091 | 1 | General Arrangement Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2015-12-12 | 2015-12-16 18:20 |  | No | 4 | 2016-01-16 11:02 | [7 empty] | 2016-01-16 20:03 | Yes | 0
VD-9001-254-DWG-222 | 1 | CABLE TRENCH LAYOUT | HM-254 | AZAR AB | 2015-12-12 | 2018-12-09 09:09 | 2018-12-09 09:09 | Yes | 1093 |  |  |  | 2019-02-19 15:23 |  |  |  |  | 2019-02-19 15:23 | Yes | 58
VD-9001-206A-DWG-001 | 5 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2015-11-28 16:35 | 2015-11-29 11:16 |  | No | 1 | 2015-12-08 14:31 | [8 empty] | No | 0
VD-9001-105-DSH-105 | 2 | Data sheet of safety valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-13 | 2015-12-15 15:52 | 2015-12-15 17:48 | Yes | 2 |  | 2016-01-09 10:32 | [6 empty] | 2016-01-09 20:03 | Yes | 11 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-105-DSH-205 | 1 | Data sheet of automatic valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-13 | 2015-12-05 18:01 |  | No | -8 |  | 2015-12-26 11:14 | [6 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-105-LST-204 | 1 | Set point list of HRU for FCS’s alarm and interlock | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-13 | 2016-01-17 07:21 |  | No | 35 |  | 2016-02-20 10:54 | [6 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-LST-205 | 1 | Set point list of HRU for FCS’s monitor and control | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-13 | 2016-01-17 07:22 |  | No | 35 | 2016-02-20 11:01 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-DSH-211 | 1 | Data sheet of hydrogen analyzer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-02-19 10:48 |  | No | 66 | 2016-02-28 11:07 | [7 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-105-DIG-206 | 1 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-15 | 2016-02-26 15:54 |  | No | 73 | 2016-04-09 09:04 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-253(A)-DWG-014 | 1 | ROTATING PART DETAIL for 2001 | HM-253A | FATEH SANAT KIMIA | 2015-12-01 10:06 | 2015-12-05 10:25 | 2015-12-05 10:59 | Yes | 4 |  | 2015-12-14 17:06 | [6 empty] | 2015-12-14 17:07 | Yes | -5 | 1204-Owner-v | 2018-07-03 18:57
VD-9001-253(A)-DWG-044 | 1 | ROTATING PART DETAIL for 3001 | HM-253A | FATEH SANAT KIMIA | 2015-12-01 10:06 | 2015-12-05 10:26 | 2015-12-05 11:00 | Yes | 4 |  | 2015-12-14 17:06 | [6 empty] | 2015-12-14 17:07 | Yes | -5 | 1204-Owner-v | 2019-01-31 11:26
VD-9001-253(A)-DWG-074 | 1 | ROTATING PART DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2015-12-01 10:06 | 2015-12-05 10:30 |  | No | 4 |  | 2015-12-14 17:07 | [7 empty] | No | 0
VD-9001-108-MNL-058 | 2 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2015-12-15 | 2015-12-14 09:30 |  | No | -1 |  | 2016-01-26 11:54 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-MNL-057 | 2 | ISTALLATION MANUAL | PR-108 | Farabard | 2015-12-15 | 2015-12-20 13:03 |  | No | 5 |  | 2016-01-26 15:20 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-PCU-061 | 1 | PERFORMANCE CURVE FOR FAN | PR-108 | Farabard | 2015-12-15 | 2017-10-30 13:00 | 2017-10-30 13:01 | Yes | 685 |  | 2017-11-06 11:34 | [6 empty] | 2017-11-06 19:59 | Yes | -7
VD-9001-205A-DWG-006 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-15 | 2015-12-22 08:34 |  | No | 7 | 2016-01-05 17:09 | [7 empty] | 2016-01-05 20:03 | Yes | 0
VD-9001-205A-CAL-005 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-15 | 2015-12-14 10:56 | 2015-12-14 11:05 | Yes | -1 |  | 2016-01-05 11:33 | [6 empty] | 2016-01-05 20:03 | Yes | 8
VD-9001-205A-CAL-010 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-15 | 2017-04-05 16:11 | 2017-04-05 16:12 | Yes | 477 |  | 2017-04-05 17:08 | [6 empty] | 2017-04-05 21:00 | Yes | -14
VD-9001-205A-CAL-030 | 1 | HYDRAULIC CALCULATION FOR INTERNALS OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-15 | 2017-04-05 16:16 | 2017-04-05 16:17 | Yes | 477 |  | 2017-04-05 17:12 | [6 empty] | 2017-04-05 21:00 | Yes | -14
VD-9001-108-DSH-011 | 4 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2015-12-19 | 2015-12-06 13:47 |  | No | -13 | 2015-12-26 17:49 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-108-LST-047 | 4 | LOAD LIST | PR-108 | Farabard | 2015-12-19 | 2015-12-07 15:26 |  | No | -12 |  | 2015-12-26 17:25 | [6 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-257A-CAL-009 | 1 | STRENGTH CALCULATION BOOK E-1001 | HM-257A | ABAN AIR COOLER. | 2015-12-20 | 2015-12-20 11:43 |  | No | 0 | 2016-01-25 09:02 | [7 empty] | 2016-01-25 20:02 | Yes | 0
VD-9001-257A-CAL-010 | 1 | STRENGTH CALCULATION BOOK E-1009 | HM-257A | ABAN AIR COOLER. | 2015-12-20 | 2015-12-09 08:14 |  | No | -11 | 2016-01-27 08:54 | [7 empty] | 2016-01-27 20:02 | Yes | 0
VD-9001-204A-WBK-001 | 1 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2015-12-21 | 2016-03-28 11:09 |  | No | 98 | 2016-04-30 15:10 | [7 empty] | 2016-04-30 19:59 | Yes | 0
VD-9001-205A-DWG-026 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-21 | 2015-12-20 17:26 | 2015-12-20 17:54 | Yes | -1 |  | 2015-12-24 13:13 | [6 empty] | 2015-12-24 20:03 | Yes | -10
VD-9001-204A-DWG-101 | 1 | General Arrangement Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-12-21 | 2016-01-03 20:11 |  | No | 13 | 2016-01-27 17:28 | [7 empty] | 2016-01-27 20:02 | Yes | 0
VD-9001-204A-DWG-011 | 2 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2015-12-21 | 2016-01-02 18:58 |  | No | 12 | 2016-01-19 15:11 | [7 empty] | 2016-01-19 20:02 | Yes | 0
VD-9001-213A-DWG-095 | 5 | Dip Hatch With Internal Ladder for Tk-7101A/B | PV-213A | MachineSazi Pars | 2015-12-21 | 2015-12-08 12:18 | 2015-12-08 12:40 | Yes | -13 |  | 2015-12-09 17:15 | [6 empty] | 2015-12-09 17:16 | Yes | -13
VD-9001-213A-DWG-145 | 4 | Foam Protection System for Tk-7201 | PV-213A | MachineSazi Pars | 2015-12-21 | 2015-12-08 13:18 | 2015-12-08 14:27 | Yes | -13 |  | 2015-12-09 17:19 | [6 empty] | 2015-12-09 17:20 | Yes | -13
VD-9001-204A-DWG-161 | 1 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2015-12-21 | 2015-12-16 18:21 |  | No | -5 | 2016-01-04 11:25 | [7 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-205A-DWG-028 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2015-12-22 | 2015-12-20 16:39 |  | No | -2 |  | 2016-01-10 16:08 | [6 empty] | 2016-01-10 20:03 | Yes | 0
VD-9001-204A-CAL-120 | 1 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-12-22 | 2016-04-07 14:17 |  | No | 107 | 2016-05-09 16:16 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-204A-DWG-121 | 1 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2015-12-22 | 2016-04-01 00:06 |  | No | 101 | 2016-05-09 14:50 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-206A-DWG-001 | 6 | GENERAL ARRANGMENT ( T-3001 ) | PV-206A | TASHA | 2015-12-22 | 2015-12-08 14:49 | 2015-12-09 11:18 | Yes | -13 |  | 2015-12-22 10:05 | [6 empty] | 2015-12-22 10:06 | Yes | 0 | 1204-Owner-v | 2019-07-10 11:30
VD-9001-204A-SVL-001 | 1 | Sub Vendor List | PV-204A | Asas Sanat Pars Inc. | 2015-12-22 | 2016-02-02 13:31 | 2016-02-02 13:32 | Yes | 42 |  | 2016-06-05 11:29 | [6 empty] | 2016-06-05 19:58 | Yes | 110
VD-9001-204A-CAL-100 | 1 | Strength Calculation FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2015-12-22 | 2016-01-03 20:05 |  | No | 12 | 2016-01-24 11:07 | [7 empty] | 2016-01-24 20:02 | Yes | 0
VD-9001-105-DPH-101 | 1 | Process control philosophy | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-22 | 2016-01-17 05:21 |  | No | 26 |  | 2016-02-18 10:37 | [6 empty] | 2016-02-18 20:00 | Yes | 0 | 1204-Owner-v | 2019-06-24 13:08
VD-9001-105-DPH-104 | 1 | Interlock description | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-22 | 2016-01-17 05:23 |  | No | 26 | 2016-02-20 09:45 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-PFD-101 | 1 | PFD & material balance | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-09 09:46 | 2015-12-15 16:10 | 2015-12-15 17:47 | Yes | 6 |  | 2015-12-26 11:22 | [6 empty] | 2015-12-26 20:03 | Yes | -3 | 1204-Owner-v | 2019-01-04 21:22
VD-9001-108-DWG-028 | 1 | STAIR CASE DETAIL | PR-108 | Farabard | 2015-12-09 13:25 | 2015-12-09 13:50 |  | No | 0 |  | 2015-12-14 11:41 | [7 empty] | No | 0
VD-9001-204A-QCP-001 | 2 | Quality Control Plan (QCP) | PV-204A | Asas Sanat Pars Inc. | 2015-12-23 | 2015-12-20 15:44 |  | No | -3 | 2015-12-26 18:01 | [7 empty] | 2015-12-26 20:03 | Yes | 0
VD-9001-204A-CAL-060 | 2 | Strength Calculation FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-12-23 | 2016-01-05 18:38 |  | No | 13 |  | 2016-01-24 11:55 | [6 empty] | 2016-01-24 20:03 | Yes | 0
VD-9001-204A-DWG-061 | 2 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2015-12-23 | 2016-01-05 18:40 |  | No | 13 | 2016-01-23 11:40 | [7 empty] | 2016-01-23 20:02 | Yes | 0
VD-9001-105-LST-203 | 1 | FCS I/O List | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-13 11:21 | 2016-01-20 18:53 |  | No | 38 |  | 2016-02-20 10:25 | [6 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-105-DPH-103 | 1 | Cause and effect diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-27 | 2016-01-17 05:22 |  | No | 21 | 2016-02-20 11:03 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-204A-CAL-070 | 2 | Strength Calculation FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-12-28 | 2016-01-05 18:39 |  | No | 8 |  | 2016-01-24 15:52 | [6 empty] | 2016-01-24 20:03 | Yes | 0
VD-9001-204A-DWG-071 | 2 | General Arrangement Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2015-12-28 | 2016-01-05 18:43 |  | No | 8 | 2016-01-24 15:40 | [7 empty] | 2016-01-24 20:03 | Yes | 0
VD-9001-108-CAL-002 | 1 | COOLING TOWER AND EQUIPMENTS CALCULATION & PERFORMANC CURVES BOOKLET | PR-108 | Farabard | 2015-12-28 | 2015-12-19 13:24 |  | No | -9 | 2015-12-30 17:36 | [7 empty] | 2015-12-30 20:03 | Yes | 0
VD-9001-204A-DWG-081 | 2 | General Arrangement Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2015-12-28 | 2016-02-15 18:10 |  | No | 49 |  | 2016-03-01 15:41 | [6 empty] | 2016-03-01 20:00 | Yes | 0
VD-9001-105-PID-101 | 2 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-28 | 2016-01-17 05:20 |  | No | 20 | 2016-04-16 10:40 | [7 empty] | 2016-04-16 19:59 | Yes | 0
VD-9001-108-PCJ-069 | 0 | BLADE BALANCING PROCEDURE | PR-108 | Farabard | 2015-12-21 | 2015-12-21 12:16 | 2015-12-21 12:52 | Yes | 0 |  | 2016-01-04 12:07 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-105-DIG-202 | 1 | Interlock logic diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-29 | 2016-02-16 15:12 |  | No | 49 | 2016-02-28 11:57 | [7 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-105-DIG-205 | 1 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2015-12-29 | 2015-12-24 16:55 |  | No | -5 | 2016-02-14 14:57 | [7 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-206B-CAL-061 | 2 | MECHANICAL CALCULATION BOOK -T-4001 | PV-206B | TASHA | 2015-12-29 | 2016-02-01 11:33 | 2016-02-01 11:33 | Yes | 34 |  | 2016-02-13 11:33 | [6 empty] | 2016-02-13 20:04 | Yes | -2
VD-9001-206B-CAL-001 | 2 | MECHANICAL CALCULATION BOOK -T-1001 | PV-206B | TASHA | 2015-12-29 | 2016-02-07 13:13 |  | No | 40 | 2016-02-28 10:54 | [7 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-206B-CAL-031 | 2 | MECHANICAL CALCULATION BOOK -T-2001 | PV-206B | TASHA | 2015-12-29 | 2016-02-02 11:02 | 2016-02-02 11:03 | Yes | 35 |  | 2016-02-13 10:52 | [6 empty] | 2016-02-13 20:04 | Yes | -3
VD-9001-254-PDS-341 | 1 | FUNCTION OF ABC | HM-254 | AZAR AB | 2015-12-29 | 2016-05-04 14:34 |  | No | 127 | 2016-06-13 16:03 | [7 empty] | 2016-06-13 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-14 09:49
VD-9001-254-DWG-717 | 1 | G.A. OF ST. STR. OF BLR REAR 1/2 | HM-254 | AZAR AB | 2015-12-15 15:32 | 2015-12-15 15:34 | 2015-12-15 17:51 | Yes | 0 |  | 2016-01-04 10:56 | [6 empty] | 2016-01-04 20:03 | Yes | 6 | 1204-Owner-v | 2019-02-17 16:29
VD-9001-254-DWG-718 | 1 | G.A. OF ST. STR. OF BLR REAR 2/2 | HM-254 | AZAR AB | 2015-12-15 15:32 | 2015-12-15 15:33 | 2015-12-15 17:52 | Yes | 0 |  | 2016-01-04 10:56 | [6 empty] | 2016-01-04 20:03 | Yes | 6 | 1204-Owner-v | 2019-02-17 16:29
VD-9001-108-DWG-016 | 5 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2015-12-29 | 2015-12-16 14:23 |  | No | -13 | 2016-01-26 11:55 | [7 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-254-DSH-133 | 1 | DATA SHEET FOR SOOT BLOWER | HM-254 | AZAR AB | 2015-12-29 |  |  | No | 1634 | [9 empty] | No | 0
VD-9001-108-LST-051 | 3 | SPARE PARTS LIST FOR 2 YEARS OF OPERATION | PR-108 | Farabard | 2015-12-29 | 2017-12-02 11:45 |  | No | 704 | 2017-12-03 09:31 | [7 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-254-WMP-805 | 3 | WELDING & NDE MAP FOR SUPER HEATER HEADERS | HM-254 | AZAR AB | 2015-12-30 |  |  | No | 1633 |  | 2015-12-19 12:12 | [6 empty] | 2015-12-19 12:13 | Yes | 0
VD-9001-254-WPS-826 | 2 | PREQUALIFIED WPS FOR STEEL STRUCTURE AND SUPPORTS | HM-254 | AZAR AB | 2015-12-30 | 2015-12-19 10:00 | 2015-12-20 17:14 | Yes | -10 |  | 2015-12-30 16:38 | [6 empty] | 2015-12-30 20:03 | Yes | -3
VD-9001-204A-DWG-041 | 2 | General Arrangement Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2015-12-30 | 2016-01-14 17:25 |  | No | 15 | 2016-02-01 17:46 | [7 empty] | 2016-02-01 20:02 | Yes | 0
VD-9001-108-PCJ-064 | 2 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2016-01-02 | 2015-12-20 13:05 |  | No | -13 | 2016-01-26 15:20 | [7 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-204A-PCJ-007 | 1 | Hydrostatic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-01-03 | 2015-12-20 11:46 |  | No | -14 | 2015-12-28 15:25 | [7 empty] | 2015-12-28 20:03 | Yes | 0
VD-9001-204A-CAL-150 | 2 | Strength Calculation FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-01-03 | 2016-02-02 17:45 |  | No | 30 | 2016-02-13 12:00 | [7 empty] | 2016-02-13 20:04 | Yes | 0
VD-9001-204A-DWG-151 | 2 | General Arrangement Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-01-03 | 2016-02-02 17:46 |  | No | 30 |  | 2016-02-13 11:55 | [6 empty] | 2016-02-13 20:04 | Yes | 0
VD-9001-204A-CAL-030 | 2 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-01-04 | 2016-02-25 16:14 |  | No | 52 | 2016-03-07 09:38 | [7 empty] | 2016-03-07 20:00 | Yes | 0
VD-9001-204A-DWG-031 | 2 | General Arrangement Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-01-04 | 2016-02-22 13:08 |  | No | 49 | 2016-03-07 09:20 | [7 empty] | 2016-03-07 20:00 | Yes | 0
VD-9001-213A-DWG-121 | 4 | Foam Protection System for Tk-7101A | PV-213A | MachineSazi Pars | 2016-01-05 | 2016-01-05 11:46 | 2016-01-19 14:51 | Yes | 14 |  | 2016-01-26 09:48 | [6 empty] | 2016-01-26 20:02 | Yes | 7
VD-9001-213A-DWG-122 | 4 | Foam Protection System for Tk-7101B | PV-213A | MachineSazi Pars | 2016-01-05 | 2016-01-05 11:48 | 2016-01-19 14:51 | Yes | 14 |  | 2016-01-26 09:40 | [6 empty] | 2016-01-26 20:02 | Yes | 7
VD-9001-204A-CAL-140 | 2 | Strength Calculation FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-01-05 | 2016-01-26 17:23 |  | No | 21 |  | 2016-02-08 16:27 | [6 empty] | 2016-02-08 20:02 | Yes | 0
VD-9001-204A-DWG-141 | 2 | General Arrangement Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-01-05 | 2016-01-26 17:25 |  | No | 21 |  | 2016-02-08 16:18 | [6 empty] | 2016-02-08 20:02 | Yes | 0
VD-9001-254-LST-216 | 3 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2016-01-06 | 2016-01-19 13:55 |  | No | 13 | 2016-02-14 16:47 | [7 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-254-SLD-210 | 3 | SINGLE LINE DIAGRAM | HM-254 | AZAR AB | 2016-01-06 | 2016-01-19 13:55 |  | No | 13 | 2016-02-14 16:50 | [7 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-204A-CAL-020 | 2 | Strength Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-06 | 2016-04-19 09:43 |  | No | 104 | 2016-05-16 10:54 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-021 | 2 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-06 | 2016-04-19 09:42 |  | No | 104 | 2016-05-16 10:56 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-254-DSH-353 | 1 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE GAUGES | HM-254 | AZAR AB | 2016-01-06 | 2016-04-24 14:50 |  | No | 109 | 2016-05-31 17:16 | [7 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-28 12:13
VD-9001-205A-DWG-002 | 2 | TOWER ATTACHMENT/SUPPORT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-07 | 2015-12-28 15:28 | 2015-12-28 16:33 | Yes | -10 |  | 2016-02-20 14:36 | [6 empty] | 2016-02-20 20:00 | Yes | 40
VD-9001-205A-DWG-003 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-07 | 2015-12-28 15:29 |  | No | -10 | 2016-02-20 14:29 | [7 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-205A-LST-055 | 1 | SPARE PART LIST FOR COMMISSIONING & START-UP | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-07 | 2015-12-30 10:31 |  | No | -8 |  | 2016-01-04 14:30 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-205A-LST-056 | 1 | SPARE PART LIST FOR 2 YEARS OPERATION | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-07 | 2015-12-30 10:31 |  | No | -8 |  | 2016-01-04 14:31 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-253(A)-PCJ-103 | 4 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-01-09 | 2016-01-12 16:46 |  | No | 3 | 2016-01-17 10:55 | [7 empty] | 2016-01-17 20:03 | Yes | 0 | 1204-Owner-v | 2019-06-22 11:47
VD-9001-213A-PCJ-038 | 3 | Painting procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2015-12-26 12:17 | 2015-12-27 13:26 |  | No | 1 | 2016-02-10 17:00 | [7 empty] | 2016-02-10 20:04 | Yes | 0
VD-9001-108-DSH-011 | 5 | DATA SHEET FOR FAN ELECTRO MOTOR | PR-108 | Farabard | 2016-01-09 | 2016-01-03 11:10 | 2016-01-03 11:11 | Yes | -6 |  | 2016-01-26 15:38 | [6 empty] | 2016-01-26 20:02 | Yes | 9
VD-9001-204A-CAL-110 | 2 | Strength Calculation FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-01-09 | 2016-04-11 08:55 |  | No | 93 |  | 2016-05-09 15:23 | [6 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-204A-CAL-050 | 2 | Strength Calculation FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-09 | 2016-02-25 16:52 |  | No | 47 |  | 2016-04-04 16:02 | [6 empty] | 2016-04-04 20:00 | Yes | 0
VD-9001-204A-QCP-001 | 3 | Quality Control Plan (QCP) | PV-204A | Asas Sanat Pars Inc. | 2016-01-09 | 2015-12-27 10:04 | 2015-12-27 10:05 | Yes | -13 |  | 2016-01-17 11:52 | [6 empty] | 2016-01-17 20:03 | Yes | 7
VD-9001-204A-PCJ-001 | 2 | Magnetic Particle Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-01-09 | 2015-12-27 10:04 | 2015-12-27 10:05 | Yes | -13 |  | 2016-01-17 11:44 | [6 empty] | 2016-01-17 20:03 | Yes | 7
VD-9001-254-DSH-224 | 0 | DATA SHEET FOR LOCAL CONTROL STATION | HM-254 | AZAR AB | 2015-12-27 | 2015-12-27 11:32 |  | No | 0 | 2016-02-06 10:28 | [7 empty] | 2016-02-06 20:02 | Yes | 0 | 1204-Owner-v | 2018-04-08 16:56
VD-9001-254-DSH-349 | 1 | DATA SHEET FOR FLAME DETECTOR | HM-254 | AZAR AB | 2016-01-11 | 2016-05-04 16:38 |  | No | 114 | 2016-07-13 09:37 | [7 empty] | 2016-07-13 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-28 11:58
VD-9001-204A-PCJ-007 | 2 | Hydrostatic Testing Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-01-11 | 2015-12-30 08:20 | 2015-12-30 08:21 | Yes | -12 |  | 2016-01-17 11:35 | [6 empty] | 2016-01-17 20:03 | Yes | 4
VD-9001-205A-DWG-037 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-11 20:03 | 2016-01-10 12:44 |  | No | -1 | 2016-02-22 10:18 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-DSH-219 | 2 | DATA SHEET FOR JUNCTION BOXES | HM-254 | AZAR AB | 2016-01-13 | 2018-10-16 07:44 | 2018-10-16 07:44 | Yes | 1007 |  |  |  | 2018-11-14 10:09 |  |  |  |  | 2018-11-14 10:09 | Yes | 15
VD-9001-254-LST-217 | 2 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2016-01-13 | 2016-11-26 12:59 |  | No | 318 | 2016-12-25 14:32 | [7 empty] | 2016-12-25 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-17 08:56
VD-9001-254-DWG-704 | 2 | FOUNDATION LOADS FOR ST. STACK | HM-254 | AZAR AB | 2016-01-13 | 2017-12-04 11:10 | 2017-12-04 11:11 | Yes | 691 |  | 2017-12-11 15:15 | [6 empty] | 2017-12-11 20:00 | Yes | -7
VD-9001-108-DSH-007 | 3 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 13:02 |  | No | 3 |  | 2016-01-26 15:34 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-DSH-008 | 2 | FAN PACKAGE DATA SHEET | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 13:02 |  | No | 3 |  | 2016-01-26 17:57 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-DSH-009 | 2 | GEAR REDUCER DATA SHEET | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 13:03 |  | No | 3 |  | 2016-01-26 15:35 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-DSH-010 | 3 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 13:03 |  | No | 3 |  | 2016-01-26 15:36 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-DWG-026 | 1 | HAND RAIL DETAIL | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 12:53 |  | No | 3 |  | 2016-01-04 09:59 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-108-DWG-027 | 1 | LADDER DETAIL | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 12:54 |  | No | 3 |  | 2016-01-04 09:59 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-108-DWG-028 | 2 | STAIR CASE DETAIL | PR-108 | Farabard | 2015-12-30 16:47 | 2016-01-02 13:08 |  | No | 3 |  | 2016-01-04 10:00 | [6 empty] | 2016-01-04 20:03 | Yes | 0
VD-9001-108-DWG-035 | 2 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2015-12-30 16:48 | 2016-01-02 13:05 |  | No | 3 |  | 2016-01-26 15:41 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-108-DWG-038 | 1 | FAN DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2015-12-30 16:48 | 2016-01-02 13:06 | 2016-01-02 14:21 | Yes | 3 |  | 2016-01-26 15:37 | [6 empty] | 2016-01-26 20:02 | Yes | 10
VD-9001-108-CAL-002 | 2 | COOLING TOWER AND EQUIPMENTS CALCULATION & PERFORMANC CURVES BOOKLET | PR-108 | Farabard | 2016-01-13 | 2016-01-02 13:05 |  | No | -11 |  | 2016-01-26 15:33 | [6 empty] | 2016-01-26 20:02 | Yes | 0
VD-9001-254-CAL-479 | 1 | SUMMARY STRENGTH CALCULATION FOR BOILER PRESSURE PART | HM-254 | AZAR AB | 2016-01-16 | 2017-10-16 14:58 | 2017-10-16 14:59 | Yes | 639 |  | 2017-10-23 17:19 | [6 empty] | 2017-10-23 20:00 | Yes | -7 | 1204-Owner-v | 2018-01-10 14:59
VD-9001-108-DWG-043 | 1 | DIMENSIONAL AND WEIGHT DRAWING | PR-108 | Farabard | 2016-01-16 | 2017-11-28 09:18 | 2017-11-28 09:19 | Yes | 682 |  | 2017-11-29 09:41 | [6 empty] | 2017-11-29 20:00 | Yes | -13
VD-9001-108-DWG-030 | 1 | GENERAL ARRANGMENT | PR-108 | Farabard | 2016-01-16 | 2017-02-22 12:33 |  | No | 403 | 2017-08-06 10:00 | [7 empty] | 2017-08-06 19:58 | Yes | 0
VD-9001-213A-DWG-144 | 5 | Water Cooling System for Tk-7201 | PV-213A | MachineSazi Pars | 2016-01-16 | 2016-01-04 13:38 | 2016-01-04 13:39 | Yes | -12 |  | 2016-01-19 11:29 | [6 empty] | 2016-01-19 20:02 | Yes | 1
VD-9001-254-LST-554 | 1 | PIPE LINE LIST | HM-254 | AZAR AB | 2016-01-18 | 2018-10-13 10:56 | 2018-10-13 10:56 | Yes | 999 |  |  |  | 2018-10-22 11:45 |  |  |  |  | 2018-10-22 11:45 | Yes | -5
VD-9001-213B-PCJ-016 | 3 | Painting & Pickling and Passivation procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-01-04 11:18 | 2016-01-04 11:33 |  | No | 0 | [9 empty] | No | 0
VD-9001-204A-CAL-160 | 2 | Strength Calculation FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-01-18 | 2016-05-28 11:05 |  | No | 131 |  | 2016-05-31 11:19 | [6 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-204A-DWG-161 | 2 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-01-18 | 2016-05-28 11:06 |  | No | 131 | 2016-06-05 16:33 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-205A-DWG-031 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-19 20:03 | 2016-02-21 09:25 | 2016-02-21 09:26 | Yes | 33 |  | 2016-03-01 09:14 | [6 empty] | 2016-03-01 20:00 | Yes | -5
VD-9001-205A-DWG-045 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-19 20:03 | 2016-04-04 15:39 | 2016-04-04 15:40 | Yes | 76 |  | 2016-05-31 11:59 | [6 empty] | 2016-05-31 19:58 | Yes | 43
VD-9001-206B-CAL-002 | 1 | EXTERNAL ATTACHMENT CALCULATION-T-1001 | PV-206B | TASHA | 2016-01-19 20:03 | 2016-07-16 10:38 | 2016-07-16 10:37 | Yes | 179 |  | 2016-08-01 16:00 | [6 empty] | 2016-08-01 19:57 | Yes | 2
VD-9001-206B-CAL-032 | 1 | EXTERNAL ATTACHMENT CALCULATION-T-2001 | PV-206B | TASHA | 2016-01-19 20:03 | 2016-03-03 10:23 | 2016-03-03 10:24 | Yes | 44 |  | 2016-03-14 11:50 | [6 empty] | 2016-03-14 20:00 | Yes | -3
VD-9001-205A-DWG-047 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF D-3007 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-19 20:03 | 2016-10-02 15:42 | 2016-10-02 15:43 | Yes | 257 |  | 2016-12-28 14:59 | [6 empty] | 2016-12-28 19:59 | Yes | 73
VD-9001-205A-DWG-006 | 4 | GENERAL ARRANGEMENT DRAWING FOR OF T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-19 20:03 | 2016-02-18 12:17 | 2016-02-18 12:18 | Yes | 30 |  | 2016-02-27 10:45 | [6 empty] | 2016-02-27 20:00 | Yes | -5
VD-9001-205A-DWG-043 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-19 20:03 | 2016-04-04 15:39 |  | No | 76 | 2016-07-10 14:39 | [7 empty] | 2016-07-10 19:58 | Yes | 0
VD-9001-253(A)-DWG-005 | 2 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-01-20 | 2016-02-08 14:46 |  | No | 19 | 2016-03-16 09:50 | [7 empty] | 2016-03-16 20:00 | Yes | 0
VD-9001-204A-DWG-051 | 3 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-20 | 2016-02-25 16:54 |  | No | 36 | 2016-04-03 14:32 | [7 empty] | 2016-04-03 20:00 | Yes | 0
VD-9001-204A-DWG-111 | 2 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-01-20 | 2016-04-11 08:56 |  | No | 82 | 2016-05-10 10:41 | [7 empty] | 2016-05-10 19:58 | Yes | 0
VD-9001-105-DSH-210 | 1 | Data sheet of restriction orifice | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-21 20:03 | 2016-05-30 20:22 | 2016-05-30 20:23 | Yes | 130 |  | 2016-06-02 09:04 | [6 empty] | 2016-06-02 19:58 | Yes | -11 | 1204-Owner-v | 2019-01-04 21:40
VD-9001-105-DSH-201 | 1 | Data sheet of pressure gauges | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-09 | 2016-02-26 15:56 |  | No | 48 |  | 2016-03-10 11:34 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-105-DSH-203 | 1 | Data sheet of temp. gauges and thermowells | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-09 | 2016-03-05 07:41 | 2016-03-05 07:42 | Yes | 56 |  | 2016-03-10 11:45 | [6 empty] | 2016-03-10 20:00 | Yes | -9 | 1204-Owner-v | 2019-01-04 21:38
VD-9001-105-DSH-204 | 1 | Data sheet of temperature elements and transmitter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-09 | 2016-03-05 07:44 | 2016-03-05 07:45 | Yes | 56 |  | 2016-03-10 11:48 | [6 empty] | 2016-03-10 20:00 | Yes | -9 | 1204-Owner-v | 2019-01-04 21:38
VD-9001-105-DSH-209 | 1 | Data sheet of orifice plate flow meter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-09 | 2016-05-27 07:59 | 2016-05-27 08:00 | Yes | 139 |  | 2016-06-02 08:43 | [6 empty] | 2016-06-02 19:58 | Yes | -8 | 1204-Owner-v | 2019-01-04 21:38
VD-9001-105-CAL-203 | 1 | Calculation sheet of flowmeter | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-09 | 2016-05-27 07:59 | 2016-05-27 08:00 | Yes | 139 |  | 2016-06-02 08:47 | [6 empty] | 2016-06-02 19:58 | Yes | -8
VD-9001-253(A)-PCJ-104 | 3 | PAINTING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-01-09 11:29 | 2016-01-10 08:43 |  | No | 1 |  | 2016-01-17 11:05 | [6 empty] | 2016-01-17 20:03 | Yes | 0
VD-9001-204A-CAL-090 | 2 | Strength Calculation FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-24 | 2016-02-01 13:06 |  | No | 8 |  | 2016-02-14 17:17 | [6 empty] | 2016-02-14 20:04 | Yes | 0
VD-9001-108-DWG-028 | 3 | STAIR CASE DETAIL | PR-108 | Farabard | 2016-01-10 16:37 | 2016-01-12 11:55 |  | No | 2 | [9 empty] | No | 0
VD-9001-204A-CAL-170 | 2 | Strength Calculation FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-01-24 20:03 | 2016-05-17 15:00 |  | No | 114 |  | 2016-05-23 10:17 | [6 empty] | 2016-05-23 19:58 | Yes | 0
VD-9001-205A-DWG-035 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-01-24 20:03 | 2016-02-21 09:17 | 2016-02-21 09:18 | Yes | 28 |  | 2016-03-01 09:18 | [6 empty] | 2016-03-01 20:00 | Yes | -5
VD-9001-204A-DWG-091 | 2 | General Arrangement Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-01-30 | 2016-02-01 13:08 |  | No | 2 | 2016-02-10 08:55 | [7 empty] | 2016-02-10 20:04 | Yes | 0
VD-9001-253(A)-PCJ-103 | 5 | HYDROSTATIC TEST PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-01-17 | 2016-01-20 12:37 | 2016-01-20 12:38 | Yes | 3 |  | 2016-01-31 16:21 | [6 empty] | 2016-01-31 20:02 | Yes | -3 | 1204-Owner-v | 2019-06-19 15:57
VD-9001-254-DBS-600 | 2 | BOILER DESIGN BASE DATA SHEET | HM-254 | AZAR AB | 2016-01-31 | 2016-01-24 17:18 |  | No | -7 | 2016-02-24 17:09 | [7 empty] | 2016-02-24 20:00 | Yes | 0
VD-9001-231A-LST-001 | 0 | GENERAL INDEX OF SCHEDULING DOCUMENTS | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-14 14:08 | 2016-02-14 14:09 | Yes | 36 |  | 2016-02-28 11:20 | [6 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-231A-ITP-001 | 0 | INSPECTION AND TEST PLAN | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-06-29 17:45 | 2016-06-29 17:46 | Yes | 172 |  | 2016-08-21 09:24 | [6 empty] | 2016-08-21 19:57 | Yes | 39
VD-9001-231A-PCJ-002 | 0 | VISUAL & DIMENTIONAL INSPECTION PROCEDURE (VT) | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-17 11:55 | 2016-02-17 11:56 | Yes | 39 |  | 2016-02-27 10:40 | [6 empty] | 2016-02-27 20:00 | Yes | -4
VD-9001-231A-PCJ-003 | 0 | FABRICATION PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-17 11:58 |  | No | 39 | 2016-02-27 10:42 | [7 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-231A-PCJ-004 | 0 | REPAIR PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-17 12:00 |  | No | 39 | 2016-02-29 09:46 | [7 empty] | 2016-02-29 20:00 | Yes | 0
VD-9001-231A-PCJ-005 | 0 | BLASTING & PAINTING PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-06-29 15:28 |  | No | 172 | 2016-07-27 16:41 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-231A-PCJ-006 | 0 | PACKING,MARKING ,LOADING&SHIPPING PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-17 12:03 | 2016-02-17 12:04 | Yes | 39 |  | 2016-03-02 08:46 | [6 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-231A-INX-007 | 0 | FINAL DATA BOOK INDEX | PV-231A | Tarh Mechanic Gostar | 2016-05-09 | 2016-11-14 14:30 | 2016-11-14 14:31 | Yes | 189 |  |  | 2018-04-18 16:13 | [5 empty] | 2018-04-18 16:13 | Yes | 506
VD-9001-231A-INX-008 | 0 | FINAL VENDOR DATA BOOK | PV-231A | Tarh Mechanic Gostar | 2016-05-09 |  |  | No | 1502 | [9 empty] | No | 0
VD-9001-231A-WMP-009 | 0 | WELDING BOOK (WPS & PQR) | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-17 12:11 |  | No | 39 | 2016-02-27 10:49 | [7 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-231A-DWG-010 | 0 | Ladder And Platform Drawing ( 3 - T- 3001 ) | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-14 11:55 |  | No | 36 |  | 2016-02-28 11:46 | [6 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-231A-DWG-011 | 0 | Ladder And Platform Drawing ( 3 - T - 3002 ) | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-14 12:11 |  | No | 36 |  | 2016-02-28 11:51 | [6 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-231A-DWG-012 | 0 | Ladder And Platform Drawing ( 3 - T - 3003 ) | PV-231A | Tarh Mechanic Gostar | 2016-01-09 | 2016-02-14 13:24 |  | No | 36 |  | 2016-02-28 11:53 | [6 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-204A-DWG-171 | 2 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-02-02 20:02 | 2016-04-02 17:36 |  | No | 60 | 2016-05-17 11:36 | [7 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204A-DWG-011 | 3 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-02-02 20:02 | 2016-05-24 10:50 |  | No | 112 | 2016-06-06 11:39 | [7 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-204A-CAL-010 | 2 | Strength Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-02-02 20:02 | 2016-05-10 13:23 |  | No | 98 |  | 2016-05-29 11:14 | [6 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-206B-DWG-071 | 2 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2016-02-02 20:02 | 2016-02-01 11:37 |  | No | -1 | 2016-02-23 16:53 | [7 empty] | 2016-02-23 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:35
VD-9001-206B-DWG-011 | 2 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-02-02 20:02 | 2016-02-07 13:16 |  | No | 5 | 2016-02-28 10:50 | [7 empty] | 2016-02-28 20:00 | Yes | 0
VD-9001-204A-DWG-061 | 3 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-02-06 20:02 | 2016-04-03 11:29 |  | No | 57 | 2016-05-10 11:37 | [7 empty] | 2016-05-10 19:59 | Yes | 0
VD-9001-204A-CAL-100 | 2 | Strength Calculation FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-02-07 20:02 | 2016-06-07 12:06 |  | No | 121 |  | 2016-06-13 17:23 | [6 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-204A-DWG-071 | 3 | General Arrangement Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-02-07 20:03 | 2016-05-26 12:26 |  | No | 109 |  | 2016-06-06 11:07 | [6 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-206A-DWG-031 | 1 | SADDLE DRAWING T-3002 | PV-206A | TASHA | 2016-01-25 09:03 | 2016-01-27 10:35 | 2016-01-27 10:36 | Yes | 2 |  | 2016-01-31 16:48 | [6 empty] | 2016-01-31 20:02 | Yes | -10
VD-9001-206A-DWG-032 | 1 | SADDLE DRAWING T-3003 | PV-206A | TASHA | 2016-01-25 09:03 | 2016-01-31 15:56 | 2016-01-31 15:57 | Yes | 6 |  | 2016-01-31 17:08 | [6 empty] | 2016-01-31 20:02 | Yes | -14
VD-9001-108-DWG-022 | 4 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2016-01-25 09:04 | 2016-01-25 10:14 |  | No | 0 | [9 empty] | No | 0
VD-9001-257A-CAL-009 | 2 | STRENGTH CALCULATION BOOK E-1001 | HM-257A | ABAN AIR COOLER. | 2016-02-08 | 2016-01-27 10:58 | 2016-01-27 10:43 | Yes | -12 |  | 2016-04-03 09:42 | [6 empty] | 2016-04-03 20:00 | Yes | 53
VD-9001-257A-DWG-009 | 1 | GENERAL ARRANGEMENT DRAWING E-1001 | HM-257A | ABAN AIR COOLER. | 2016-02-08 | 2016-01-27 11:44 |  | No | -12 | 2016-04-03 09:43 | [7 empty] | 2016-04-03 20:00 | Yes | 0
VD-9001-108-DWG-016 | 6 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2016-02-09 | 2016-01-27 13:01 |  | No | -13 | [9 empty] | No | 0
VD-9001-254-LST-220 | 0 | WIRING LIST AND CABLE ROUTH ( POWER ) | HM-254 | AZAR AB | 2016-01-26 | 2016-01-26 15:15 |  | No | 0 | 2016-02-14 16:53 | [7 empty] | 2016-02-14 20:04 | Yes | 0 | 1204-Owner-v | 2018-04-09 17:13
VD-9001-108-PCJ-064 | 3 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2016-02-09 | 2016-01-30 13:36 |  | No | -10 |  | 2016-02-17 11:25 | [6 empty] | 2016-02-17 20:01 | Yes | 0
VD-9001-257A-DWG-010 | 1 | GENERAL ARRANGEMENT DRAWING E-1009 | HM-257A | ABAN AIR COOLER. | 2016-02-10 | 2016-03-29 11:32 |  | No | 48 | 2016-04-17 08:58 | [7 empty] | 2016-04-17 19:59 | Yes | 0
VD-9001-257A-CAL-010 | 2 | STRENGTH CALCULATION BOOK E-1009 | HM-257A | ABAN AIR COOLER. | 2016-02-10 | 2016-03-29 11:15 |  | No | 48 | 2016-04-17 08:58 | [7 empty] | 2016-04-17 19:59 | Yes | 0
VD-9001-204A-DWG-101 | 2 | General Arrangement Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-02-10 20:02 | 2016-06-07 12:07 |  | No | 118 | 2016-06-13 12:30 | [7 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-105-DPH-102 | 1 | Process control requirement | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-28 10:42 | 2016-01-28 18:12 |  | No | 0 | 2016-03-12 12:08 | [7 empty] | 2016-03-12 20:00 | Yes | 0
VD-9001-105-DSH-205 | 2 | Data sheet of automatic valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-01-28 10:42 | 2016-01-28 18:11 |  | No | 0 |  | 2016-03-10 11:14 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-213A-DWG-108 | 4 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2016-01-30 | 2016-02-03 15:45 |  | No | 4 | 2016-02-13 15:50 | [7 empty] | 2016-02-13 20:04 | Yes | 0
VD-9001-205A-DWG-001 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-14 20:02 | 2016-04-19 11:12 | 2016-04-19 11:13 | Yes | 65 |  | 2016-06-29 14:11 | [6 empty] | 2016-06-29 19:58 | Yes | 57
VD-9001-206B-PCJ-014 | 1 | REPAIR PROCEDURE | PV-206B | TASHA | 2016-02-14 20:02 | 2016-05-07 08:52 |  | No | 83 | 2016-06-06 11:14 | [7 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-206B-PCJ-017 | 1 | PMI PROCEDURE | PV-206B | TASHA | 2016-02-14 20:02 | 2016-02-08 09:32 |  | No | -6 | 2016-02-27 11:58 | [7 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-206B-PCJ-011 | 1 | POST WELD HEAT TREATMENT PROCEDURE(P.W.H.T) | PV-206B | TASHA | 2016-02-14 20:02 | 2016-02-08 09:31 |  | No | -6 | 2016-02-27 11:56 | [7 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-206B-PCJ-016 | 1 | HARDNESS TEST PROCEDURE | PV-206B | TASHA | 2016-02-14 20:02 | 2016-02-08 09:31 |  | No | -6 |  | 2016-02-27 11:57 | [6 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-206B-PCJ-018 | 1 | FERRITE CHECKING PROCEDURE | PV-206B | TASHA | 2016-02-14 20:02 | 2016-02-08 09:33 | 2016-02-08 09:34 | Yes | -6 |  | 2016-02-27 12:00 | [6 empty] | 2016-02-27 20:00 | Yes | 5
VD-9001-204A-DWG-041 | 3 | General Arrangement Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-02-15 20:02 | 2016-02-15 18:09 |  | No | 0 |  | 2016-02-20 16:24 | [6 empty] | 2016-02-20 20:00 | Yes | 0 | 1204-Owner-v | 2020-02-12 16:22
VD-9001-254-DWG-427 | 1 | ASSEMBLY DWG. FOR BANK TUBE FRONT WALL TUBE 1/3 | HM-254 | AZAR AB | 2016-02-02 13:39 | 2016-02-03 09:27 | 2016-02-03 09:28 | Yes | 1 |  | 2016-02-16 16:15 | [6 empty] | 2016-02-16 20:04 | Yes | -1 | 1204-Owner-v | 2019-02-16 10:53
VD-9001-206B-WBK-021 | 1 | WELDING BOOK (WPS & PQR) | PV-206B | TASHA | 2016-02-16 20:02 | 2016-08-03 12:59 |  | No | 169 | 2016-09-17 09:40 | [7 empty] | 2016-09-17 19:56 | Yes | 0
VD-9001-206B-DWG-041 | 2 | GENERAL ARRANGMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-02-16 20:02 | 2016-02-03 08:12 |  | No | -13 | 2016-02-23 16:58 | [7 empty] | 2016-02-23 20:00 | Yes | 0 | 1204-Owner-v | 2020-05-11 14:37
VD-9001-205A-DWG-018 | 4 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-06 09:07 | 2016-02-06 09:30 |  | No | 0 | 2016-02-22 11:07 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-205A-DWG-023 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-06 09:08 | 2016-02-07 15:25 |  | No | 1 | 2016-02-22 11:34 | [7 empty] | 2016-02-22 20:00 | Yes | 0
VD-9001-254-DSH-224 | 1 | DATA SHEET FOR LOCAL CONTROL STATION | HM-254 | AZAR AB | 2016-02-16 | 2018-04-25 10:24 | 2018-04-25 10:25 | Yes | 799 |  |  |  | 2018-05-21 10:22 |  |  |  |  | 2018-05-21 10:22 | Yes | 12
VD-9001-257A-VLS-001 | 1 | Spare Parts For Pri-Commissioning, Commissining and Start up | HM-257A | ABAN AIR COOLER. | 2016-02-20 | 2016-04-11 14:34 | 2016-04-11 14:35 | Yes | 51 |  | 2016-04-17 17:30 | [6 empty] | 2016-04-17 19:59 | Yes | -8
VD-9001-257A-VLS-002 | 1 | Spare Part For Two-Years Operation | HM-257A | ABAN AIR COOLER. | 2016-02-20 | 2016-04-11 14:34 | 2016-04-11 14:35 | Yes | 51 |  | 2016-04-17 17:30 | [6 empty] | 2016-04-17 19:59 | Yes | -8
VD-9001-213A-DWG-099 | 5 | Floating Roof Orientation for Tk-7101A | PV-213A | MachineSazi Pars | 2016-02-06 15:51 | 2016-02-07 11:13 | 2016-02-07 11:14 | Yes | 1 |  | 2016-02-13 16:26 | [6 empty] | 2016-02-13 20:04 | Yes | -8
VD-9001-213A-DWG-100 | 5 | Floating Roof Orientation for Tk-7101B | PV-213A | MachineSazi Pars | 2016-02-06 15:51 | 2016-02-07 11:14 | 2016-02-07 11:15 | Yes | 1 |  | 2016-02-13 16:31 | [6 empty] | 2016-02-13 20:04 | Yes | -8 | 1204-Owner-v | 2019-12-30 09:19
VD-9001-206B-WMP-022 | 1 | WELDING MAP&NDT TABLE | PV-206B | TASHA | 2016-02-20 20:02 | 2016-08-03 17:28 |  | No | 165 | 2016-09-17 09:45 | [7 empty] | 2016-09-17 19:56 | Yes | 0
VD-9001-202F-DIS-001 | 0 | Vendor Documents Index & Schedule | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-15 |  |  | No | 1617 | [9 empty] | No | 0
VD-9001-202F-FAS-001 | 0 | Fabrication & Production Schedule | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 |  |  | No | 1610 | [9 empty] | No | 0
VD-9001-202F-MPR-001 | 0 | Progress Report (monthly) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-29 |  |  | No | 1603 | [9 empty] | No | 0
VD-9001-202F-DSH-001 | 0 | Technical Specifications | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 | 2016-03-03 18:04 |  | No | 41 | 2016-04-02 14:24 | [7 empty] | 2016-04-02 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:45
VD-9001-202F-PPL-001 | 0 | Arrangement and Piping Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-02-08 | 2018-02-08 22:06 | 2018-02-08 22:07 | Yes | 0 |  |  |  |  | 2018-04-23 15:55 |  |  |  | 2018-04-23 15:55 | Yes | 60 | 1204-Owner-v | 2018-02-17 10:29
VD-9001-202F-PPL-002 | 0 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 | 2018-06-11 21:32 | 2018-06-11 21:32 | Yes | 73 |  |  |  |  | 2018-06-25 18:00 |  |  |  | 2018-06-25 18:00 | Yes | 0
VD-9001-202F-ISO-001 | 0 | Riser & Downcomer Isometrics | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-ISO-002 | 0 | Steam Piping Isometrics | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-DWG-001 | 0 | Piping Support Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-SPE-001 | 0 | Spring Hanger Specification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 | 2018-08-21 15:26 | 2018-08-21 15:25 | Yes | 144 |  |  |  |  | 2018-09-08 11:14 |  |  |  | 2018-09-08 11:14 | Yes | 4 | 1204-Owner-v | 2019-05-11 08:48
VD-9001-202F-SPE-002 | 0 | Pipe Guides Specification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-CAL-001 | 0 | R&D Piping - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 | 2018-09-18 16:53 | 2018-09-18 17:45 | Yes | 172 |  |  | 2018-10-10 16:19 | [5 empty] | 2018-10-10 16:19 | Yes | 8 | 1204-Owner-v | 2019-05-11 08:35
VD-9001-202F-ARP-001 | 0 | Flexibility Analysis of Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 | 2018-09-18 16:32 | 2018-09-18 16:34 | Yes | 172 |  |  | 2018-09-30 10:41 | [5 empty] | 2018-09-30 10:41 | Yes | -2 | 1204-Owner-v | 2020-04-29 09:01
VD-9001-202F-ITP-001 | 0 | R&D Piping - Inspection Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-PPL-003 | 0 | Layout Plan for Steel Structure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 | 2018-02-23 22:03 | 2018-02-23 22:04 | Yes | 763 |  |  |  |  | 2018-04-09 16:45 |  |  |  | 2018-04-09 16:45 | Yes | 31 | 1204-Owner-v | 2019-05-11 08:45
VD-9001-202F-DWG-026 | 0 | Steelwork - Details | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-DWG-027 | 0 | Steelwork - Details | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-DWG-028 | 0 | Steelwork - Details | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-DWG-029 | 0 | Steelwork - Details | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 |  |  | No | 1568 | [9 empty] | No | 0
VD-9001-202F-DWG-030 | 0 | Steelwork - Details | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-CAL-006 | 0 | Steelwork - Design Calculation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-DWG-029 | 0 | Transfer Line 1 - Reformer to WHB - Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-CAL-005 | 0 | Transfer Line 1 - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-202F-DWG-025 | 0 | Transfer Line 1 - Refractory Lining Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-CAT-003 | 0 | Transfer Line 1 - Refractory Lining Documentation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-PPL-004 | 0 | Steam Superheater - General Arrangement | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 | 2016-02-12 22:03 | 2016-02-12 22:04 | Yes | 21 |  |  |  |  | 2018-04-09 17:25 |  |  |  | 2018-04-09 17:25 | Yes | 773 | 1204-Owner-v | 2018-02-18 08:47
VD-9001-202F-BOQ-001 | 0 | Steam Superheater - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2018-02-13 22:43 | 2018-02-13 22:44 | Yes | 711 |  |  | 2018-03-27 15:43 | [5 empty] | 2018-03-27 15:43 | Yes | 28 | 1204-Owner-v | 2018-02-18 08:45
VD-9001-202F-DWG-002 | 0 | Steam Superheater - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-02-12 | 2018-02-13 22:25 | 2018-02-13 22:26 | Yes | 732 |  |  |  |  | 2018-03-28 12:24 |  |  |  | 2018-03-28 12:24 | Yes | 29 | 1204-Owner-v | 2018-02-18 08:46
VD-9001-202F-DWG-003 | 0 | Steam Superheater - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-02-28 | 2018-07-25 15:25 | 2018-07-25 15:26 | Yes | 147 |  |  |  |  | 2018-09-30 15:15 |  |  |  | 2018-09-30 15:15 | Yes | 53 | 1204-Owner-v | 2018-11-27 17:26
VD-9001-202F-BOQ-002 | 0 | Steam Superheater - Part List - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-02-28 | 2018-07-25 15:23 | 2018-07-25 15:23 | Yes | 147 |  |  | 2018-08-04 15:37 | [5 empty] | 2018-08-04 15:37 | Yes | -4 | 1204-Owner-v | 2019-07-20 18:00
VD-9001-202F-DWG-004 | 0 | Steam Superheater - Manholes/ Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2018-02-13 22:25 | 2018-02-13 22:26 | Yes | 711 |  |  |  |  | 2018-03-28 12:18 |  |  |  | 2018-03-28 12:19 | Yes | 29 | 1204-Owner-v | 2018-02-18 08:46
VD-9001-202F-DWG-005 | 0 | Steam Superheater - Name plate | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-15 |  |  | No | 827 | [9 empty] | No | 0
VD-9001-202F-DWG-006 | 0 | Steam Superheater - Shipping Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-SPE-003 | 0 | Steam Superheater - Specification of Bypass Actuator | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-CAL-002 | 0 | Steam Superheater - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-04-27 17:10 | 2018-04-27 17:14 | Yes | 12 |  |  | 2018-06-02 16:40 | [5 empty] | 2018-06-02 16:40 | Yes | 22
VD-9001-202F-ARP-002 | 0 | Steam Superheater - FEA Calculation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-24 |  |  | No | 1548 | [9 empty] | No | 0
VD-9001-202F-INX-001 | 0 | Steam Superheater - Vendor Data Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 |  |  | No | 1520 | [9 empty] | No | 0
VD-9001-202F-VDB-001 | 0 | Steam Superheater - Vendor Data Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-DWG-007 | 0 | Steam Superheater - Refractory Lining Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-CAT-001 | 0 | Steam Superheater - Refractory Lining Documentation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-DWG-008 | 0 | Steam Superheater - Caps for Nitrogen Filling | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-BOQ-003 | 0 | Steam Superheater - Part List - Caps for Nitrogen Filling | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-ITP-002 | 0 | Steam Superheater - Inspection Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 14:47 | 2018-05-03 15:26 | Yes | 776 |  |  |  |  | 2018-06-17 16:14 |  |  |  | 2018-06-17 16:14 | Yes | 31 | 1204-Owner-v | 2018-05-12 17:00
VD-9001-202F-WMP-001 | 0 | Steam Superheater - Weld Map & Heat Treatment | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-08-03 21:46 | 2018-08-03 21:48 | Yes | 868 |  |  | 2018-08-26 15:22 | [5 empty] | 2018-08-26 15:22 | Yes | 9
VD-9001-202F-WPS-001 | 0 | Steam Superheater - Welding Procedure Specification (WPS) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 15:28 | 2018-05-03 15:31 | Yes | 776 |  |  |  |  | 2018-06-11 12:05 |  |  |  | 2018-06-11 12:05 | Yes | 25 | 1204-Owner-v | 2020-04-29 10:27
VD-9001-202F-PQR-001 | 0 | Steam Superheater - Procedure Qualification Record (PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 16:30 | 2018-05-03 16:41 | Yes | 776 |  |  |  |  | 2018-06-11 12:10 |  |  |  | 2018-06-11 12:10 | Yes | 25 | 1204-Owner-v | 2020-04-29 10:16
VD-9001-202F-PCJ-001 | 0 | Steam Superheater - Cleaning and Drying Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 13:08 | 2018-05-03 13:08 | Yes | 776 |  |  | 2018-06-11 12:12 | [5 empty] | 2018-06-11 12:12 | Yes | 25 | 1204-Owner-v | 2020-04-29 09:41
VD-9001-202F-PCJ-002 | 0 | Steam Superheater - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 13:14 | 2018-05-03 13:16 | Yes | 776 |  |  |  |  | 2018-05-17 10:00 |  |  |  | 2018-05-17 10:00 | Yes | 0
VD-9001-202F-PCJ-003 | 0 | Steam Superheater - Procedure for Hydrostatic Test Pressure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 13:43 | 2018-05-03 13:44 | Yes | 776 |  |  |  |  | 2018-05-17 10:04 |  |  |  | 2018-05-17 10:04 | Yes | 0
VD-9001-202F-PCJ-004 | 0 | Steam Superheater - Mock-Up Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 |  |  | No | 1554 | [9 empty] | No | 0
VD-9001-202F-PCJ-005 | 0 | Steam Superheater - NDE Procedures (RT, UT,VT,MT, PT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-09 20:05 | 2018-05-09 20:15 | Yes | 782 |  |  |  |  | 2018-06-12 10:52 |  |  |  | 2018-06-12 10:52 | Yes | 20
VD-9001-202F-PCJ-006 | 0 | Steam Superheater - Positive Material Identification Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-05-03 13:54 | 2018-05-03 14:07 | Yes | 776 |  |  |  |  | 2018-05-17 10:34 |  |  |  | 2018-05-17 10:34 | Yes | 0
VD-9001-202F-INX-002 | 0 | Steam Superheater - Quality Record Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 |  |  | No | 1520 | [9 empty] | No | 0
VD-9001-202F-QRB-001 | 0 | Steam Superheater - Quality Record Book Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-PPL-005 | 0 | Waste Heat Boiler - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 | 2016-02-29 16:20 |  | No | 38 | 2016-04-09 10:28 | [7 empty] | 2016-04-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:47
VD-9001-202F-BOQ-004 | 0 | Waste Heat Boiler - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2016-03-04 18:06 |  | No | 0 | 2016-04-09 10:33 | [7 empty] | 2016-04-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:45
VD-9001-202F-DWG-009 | 0 | Waste Heat Boiler - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-02-12 | 2016-03-04 18:08 |  | No | 21 | 2016-04-09 10:40 | [7 empty] | 2016-04-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:46
VD-9001-202F-DWG-010 | 0 | Waste Heat Boiler - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2016-03-04 18:10 |  | No | 0 | 2016-04-09 14:32 | [7 empty] | 2016-04-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:46
VD-9001-202F-BOQ-005 | 0 | Waste Heat Boiler - Part List - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 |  |  | No | 1568 | [9 empty] | No | 0
VD-9001-202F-DWG-011 | 0 | Waste Heat Boiler - Manholes / Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2016-03-04 18:10 | 2016-03-04 18:11 | Yes | 0 |  | 2016-04-09 14:46 | [6 empty] | 2016-04-09 19:59 | Yes | 22 | 1204-Owner-v | 2018-02-18 08:46
VD-9001-202F-DWG-012 | 0 | Waste Heat Boiler - Name Plate | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-03-15 | 2018-06-25 18:39 | 2018-06-25 18:40 | Yes | 102 |  |  |  |  | 2018-08-12 16:19 |  |  |  | 2018-08-12 16:19 | Yes | 34 | 1204-Owner-v | 2019-02-25 12:33
VD-9001-202F-DWG-013 | 0 | Waste Heat Boiler - Shipping Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-SPE-004 | 0 | Waste Heat Boiler - Specification of Bypass Actuator | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 | 2018-08-07 11:20 | 2018-08-07 11:21 | Yes | 99 |  |  |  |  | 2018-11-07 11:38 |  |  |  | 2018-11-07 11:38 | Yes | 78 | 1204-Owner-v | 2019-02-25 15:39
VD-9001-202F-CAL-003 | 0 | Waste Heat Boiler - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 | 2018-04-06 14:06 | 2018-04-06 14:58 | Yes | 763 |  |  | 2018-05-08 15:38 | [5 empty] | 2018-05-08 15:38 | Yes | 18
VD-9001-202F-ARP-003 | 0 | Waste Heat Boiler - FEA Calculation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-24 | 2018-06-11 18:51 | 2018-06-11 21:25 | Yes | 809 |  |  | 2018-07-09 16:38 | [5 empty] | 2018-07-09 16:38 | Yes | 14 | 1204-Owner-v | 2020-04-29 09:05
VD-9001-202F-INX-003 | 0 | Waste Heat Boiler - Vendor Data Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 |  |  | No | 1520 | [9 empty] | No | 0
VD-9001-202F-VDB-002 | 0 | Waste Heat Boiler - Vendor Data Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-DWG-014 | 0 | Waste Heat Boiler - Refractory Lining Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-15 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-202F-CAT-002 | 0 | Waste Heat Boiler - Refractory Lining Documentation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-15 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-202F-DWG-015 | 0 | Waste Heat Boiler - Caps for Nitrogen Filling | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 | 2018-06-15 16:38 | 2018-06-15 16:38 | Yes | 46 |  |  | 2018-07-08 18:05 | [5 empty] | 2018-07-08 18:05 | Yes | 9 | 1204-Owner-v | 2019-01-21 13:29
VD-9001-202F-BOQ-006 | 0 | Waste Heat Boiler - Part List - Caps for Nitrogen Filling | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-ITP-003 | 0 | Waste Heat Boiler - Inspection & Test Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:51 |  | No | 707 |  |  |  | 2018-03-25 10:36 |  |  |  |  | 2018-03-25 10:36 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:47
VD-9001-202F-WBK-001 | 0 | Waste Heat Boiler - Welding Book (WPS & PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:55 |  | No | 707 |  |  |  | 2018-03-25 10:38 |  |  |  |  | 2018-03-25 10:38 | Yes | 0
VD-9001-202F-PCJ-007 | 0 | Waste Heat Boiler - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:19 |  | No | 707 |  |  |  | 2018-04-18 17:40 |  |  |  |  | 2018-04-18 17:40 | Yes | 0
VD-9001-202F-PCJ-008 | 0 | Waste Heat Boiler - Hydrostatic Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-04-10 20:07 | 2018-04-10 20:07 | Yes | 753 |  |  | 2018-05-01 17:03 | [5 empty] | 2018-05-01 17:03 | Yes | 7 | 1204-Owner-v | 2018-10-16 17:06
VD-9001-202F-PCJ-009 | 0 | Waste Heat Boiler - Tube-to tubesheet Mock-Up Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-04-10 20:30 | 2018-04-10 20:32 | Yes | 753 |  |  |  | 2018-05-01 17:01 |  |  |  |  | 2018-05-01 17:01 | Yes | 7
VD-9001-202F-PCJ-010 | 0 | Waste Heat Boiler - Procedure for Magnetic Particle Examination (MT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:19 |  | No | 707 |  |  |  | 2018-04-18 17:41 |  |  |  |  | 2018-04-18 17:41 | Yes | 0
VD-9001-202F-PCJ-021 | 0 | Waste Heat Boiler - Procedure for Radiographic Examination of Welds (RT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:34 |  | No | 707 |  |  |  | 2018-04-18 17:48 |  |  |  |  | 2018-04-18 17:48 | Yes | 0
VD-9001-202F-PCJ-022 | 0 | Waste Heat Boiler - Procedure for Liquid Penetrant Examination (PT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:23 |  | No | 707 |  |  |  | 2018-04-18 17:46 |  |  |  |  | 2018-04-18 17:46 | Yes | 0
VD-9001-202F-PCJ-023 | 0 | Waste Heat Boiler - Procedure for Ultrasonic Testing of Welds (UT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:50 |  | No | 707 |  |  |  | 2018-04-18 17:52 |  |  |  |  | 2018-04-18 17:52 | Yes | 0
VD-9001-202F-PCJ-024 | 0 | Waste Heat Boiler - Procedure for Visual Examination (VT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:33 |  | No | 707 |  |  |  | 2018-04-18 17:47 |  |  |  |  | 2018-04-18 17:47 | Yes | 0
VD-9001-202F-PCJ-011 | 0 | Waste Heat Boiler - Nitrogen Fiiling Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-04-10 20:32 | 2018-04-10 20:33 | Yes | 753 |  |  |  | 2018-05-01 17:05 |  |  |  |  | 2018-05-01 17:05 | Yes | 7
VD-9001-202F-PCJ-012 | 0 | Waste Heat Boiler - TOFD Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:49 |  | No | 707 |  |  |  | 2018-04-18 17:51 |  |  |  |  | 2018-04-18 17:51 | Yes | 0
VD-9001-202F-PCJ-013 | 0 | Waste Heat Boiler - Positive Material Identification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:20 |  | No | 707 |  |  |  | 2018-04-18 17:43 |  |  |  |  | 2018-04-18 17:43 | Yes | 0
VD-9001-202F-PCJ-020 | 0 | Waste Heat Boiler - Procedure for Leak Testing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:20 |  | No | 707 |  |  |  | 2018-04-18 17:44 |  |  |  |  | 2018-04-18 17:44 | Yes | 0
VD-9001-202F-PCJ-014 | 0 | Waste Heat Boiler - Production Weld Test Coupons Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-02-23 21:35 |  | No | 707 |  |  |  | 2018-04-18 17:50 |  |  |  |  | 2018-04-18 17:50 | Yes | 0
VD-9001-202F-PCJ-015 | 0 | Waste Heat Boiler - Post Weld Heat Treatment Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 | 2018-04-10 20:34 | 2018-04-10 20:34 | Yes | 753 |  |  | 2018-05-01 17:07 | [5 empty] | 2018-05-01 17:07 | Yes | 7 | 1204-Owner-v | 2020-04-29 10:06
VD-9001-202F-INX-004 | 0 | Waste Heat Boiler - Quality Record Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 | 2018-02-23 21:51 |  | No | 673 |  |  |  | 2018-04-18 17:54 |  |  |  |  | 2018-04-18 17:54 | Yes | 0
VD-9001-202F-QRB-002 | 0 | Waste Heat Boiler - Quality Record Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-PPL-006 | 0 | Steam Drum - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-01-22 | 2016-02-12 22:05 |  | No | 21 |  |  |  |  | 2018-04-07 15:38 |  |  |  | 2018-04-07 15:38 | Yes | 0 | 1204-Owner-v | 2018-02-18 08:47
VD-9001-202F-BOQ-007 | 0 | Steam Drum - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-DWG-016 | 0 | Steam Drum - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:14 | 2018-07-07 00:14 | Yes | 83 |  |  |  | 2018-07-21 18:55 |  |  |  |  | 2018-07-21 18:55 | Yes | 0 | 1204-Owner-v | 2019-02-25 14:51
VD-9001-202F-DWG-017 | 0 | Steam Drum - Manhole | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:16 | 2018-07-07 00:16 | Yes | 83 |  |  | 2018-07-21 19:36 | [5 empty] | 2018-07-21 19:36 | Yes | 0 | 1204-Owner-v | 2019-01-21 13:29
VD-9001-202F-DWG-018 | 0 | Steam Drum - Saddle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:18 | 2018-07-07 00:18 | Yes | 83 |  |  |  |  | 2018-07-21 19:14 |  |  |  | 2018-07-21 19:14 | Yes | 0 | 1204-Owner-v | 2019-05-11 08:37
VD-9001-202F-DWG-019 | 0 | Steam Drum - Internals I | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:19 | 2018-07-07 00:19 | Yes | 83 |  |  |  |  | 2018-08-12 16:31 |  |  |  | 2018-08-12 16:31 | Yes | 22 | 1204-Owner-v | 2019-02-25 14:51
VD-9001-202F-BOQ-008 | 0 | Steam Drum - Part List - Internals | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-DWG-020 | 0 | Steam Drum - Internals II | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:20 | 2018-07-07 00:20 | Yes | 83 |  |  |  |  | 2018-08-12 17:33 |  |  |  | 2018-08-12 17:33 | Yes | 22 | 1204-Owner-v | 2019-02-25 14:51
VD-9001-202F-DWG-021 | 0 | Steam Drum - Internals III | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-07-07 00:21 | 2018-07-07 00:21 | Yes | 83 |  |  |  |  | 2018-08-12 17:40 |  |  |  | 2018-08-12 17:40 | Yes | 22 | 1204-Owner-v | 2019-02-25 14:51
VD-9001-202F-DWG-022 | 0 | Steam Drum - Name Plate | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-DWG-023 | 0 | Steam Drum - Shipping Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-DWG-024 | 0 | Steam Drum - N2 Filling | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-BOQ-009 | 0 | Steam Drum - N2 Filling - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-CAL-004 | 0 | Steam Drum - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-202F-SPE-005 | 0 | Steam Drum - Steam Separator Specification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 | 2018-09-11 21:09 | 2018-09-11 21:18 | Yes | 149 |  |  | 2018-10-09 09:41 | [5 empty] | 2018-10-09 09:41 | Yes | 14 | 1204-Owner-v | 2019-05-11 08:49
VD-9001-202F-INX-005 | 0 | Steam Drum - Vendor Data Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 |  |  | No | 1520 | [9 empty] | No | 0
VD-9001-202F-VDB-003 | 0 | Steam Drum - Vendor Data Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-ITP-004 | 0 | Steam Drum - Inspection & Test Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-202F-WBK-002 | 0 | Steam Drum - Welding Book (WPS & PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 |  |  | No | 1568 | [9 empty] | No | 0
VD-9001-202F-PCJ-016 | 0 | Steam Drum - Heat Treatment Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 |  |  | No | 1568 | [9 empty] | No | 0
VD-9001-202F-PCJ-017 | 0 | Steam Drum - Pressure Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-04 |  |  | No | 1568 | [9 empty] | No | 0
VD-9001-202F-INX-006 | 0 | Steam Drum - Quality Record Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-21 |  |  | No | 1520 | [9 empty] | No | 0
VD-9001-202F-QRB-003 | 0 | Steam Drum - Quality Record Book | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2017-01-06 |  |  | No | 1260 | [9 empty] | No | 0
VD-9001-202F-DSH-002 | 0 | Instrument List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 |  |  | No | 1554 | [9 empty] | No | 0
VD-9001-202F-DSH-003 | 0 | Alarm and trip setting list | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-18 |  |  | No | 1554 | [9 empty] | No | 0
VD-9001-202F-DSH-004 | 0 | Sizing and calculation for control valves | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-005 | 0 | Junction Boxes and Terminal arrangement | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-07-15 |  |  | No | 1435 | [9 empty] | No | 0
VD-9001-202F-DSH-006 | 0 | Stress analysis and calculation for thermowells | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-07-15 |  |  | No | 1435 | [9 empty] | No | 0
VD-9001-202F-DSH-007 | 0 | Instrument cable list | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-07-15 |  |  | No | 1435 | [9 empty] | No | 0
VD-9001-202F-DSH-008 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-009 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-010 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-011 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-012 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-013 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-014 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-015 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-016 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-DSH-017 | 0 | Instrument Data Sheet | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-15 |  |  | No | 1526 | [9 empty] | No | 0
VD-9001-202F-MNL-001 | 0 | Description of Erection (Installation/Erection Instructions) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-30 | 2018-08-07 11:16 | 2018-08-07 11:22 | Yes | 69 |  |  | 2018-08-12 16:13 | [5 empty] | 2018-08-12 16:13 | Yes | -9 | 1204-Owner-v | 2018-12-17 15:25
VD-9001-202F-MNL-002 | 0 | Operating Manual | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-30 | 2018-08-07 11:18 | 2018-08-07 11:22 | Yes | 69 |  |  |  |  | 2018-11-07 11:41 |  |  |  | 2018-11-07 11:41 | Yes | 78 | 1204-Owner-v | 2020-04-29 09:40
VD-9001-202F-PCJ-018 | 0 | Transport, Packing & Storage Instructions | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-03-24 |  |  | No | 1548 | [9 empty] | No | 0
VD-9001-202F-SPE-006 | 0 | Insulation Specification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-30 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-202F-PCJ-019 | 0 | Instructions on painting & conservation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-30 | 2018-06-15 16:23 | 2018-06-15 16:23 | Yes | 16 |  |  |  |  | 2018-06-28 15:46 |  |  |  | 2018-06-28 15:46 | Yes | -1 | 1204-Owner-v | 2020-04-29 10:08
VD-9001-202F-WPS-002 | 0 | WPS - Field Weld (for all field weld joints) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-01 |  |  | No | 1540 | [9 empty] | No | 0
VD-9001-253(A)-DWG-062 | 6 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2016-02-08 | 2016-05-17 16:15 |  | No | 99 | 2016-06-07 15:34 | [7 empty] | 2016-06-07 19:58 | Yes | 0 | 1204-Owner-v | 2018-06-19 09:35
VD-9001-254-LST-113 | 1 | EFFELUENT LIST | HM-254 | AZAR AB | 2016-02-22 20:02 | 2016-03-01 07:55 | 2016-03-01 07:56 | Yes | 8 |  | 2016-03-12 17:35 | [6 empty] | 2016-03-12 20:00 | Yes | -3 | 1204-Owner-v | 2020-04-20 12:40
VD-9001-254-LST-346 | 1 | INSTRUMENT LIST | HM-254 | AZAR AB | 2016-02-22 20:02 | 2016-07-13 12:26 |  | No | 142 | 2016-08-17 10:30 | [7 empty] | 2016-08-17 19:57 | Yes | 0 | 1204-Owner-v | 2018-04-09 09:05
VD-9001-205A-DWG-003 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-10 11:09 | 2016-02-10 14:06 |  | No | 0 | 2016-02-29 09:51 | [7 empty] | 2016-02-29 20:00 | Yes | 0
VD-9001-205A-DWG-008 | 2 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-10 11:09 | 2016-02-10 14:06 | 2016-02-10 14:07 | Yes | 0 |  | 2016-02-22 11:46 | [6 empty] | 2016-02-22 20:00 | Yes | -2
VD-9001-205A-DWG-028 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-4001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-02-10 11:10 | 2016-02-10 14:06 | 2016-02-10 14:07 | Yes | 0 |  | 2016-02-22 11:39 | [6 empty] | 2016-02-22 20:00 | Yes | -2
VD-9001-204A-DWG-145 | 1 | PF & LD Arrangement FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-02-10 14:28 | 2016-02-10 14:34 |  | No | 0 |  | 2016-02-17 15:10 | [6 empty] | 2016-02-17 20:01 | Yes | 0
VD-9001-213A-DWG-134 | 4 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2016-02-10 15:20 | 2016-02-10 15:21 |  | No | 0 | 2016-02-23 18:39 | [7 empty] | 2016-02-23 20:00 | Yes | 0
VD-9001-213A-PCJ-038 | 4 | Painting procedure for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2016-02-10 | 2016-02-13 10:14 | 2016-02-13 10:16 | Yes | 3 |  | 2016-02-13 11:48 | [6 empty] | 2016-02-13 20:04 | Yes | -14
VD-9001-204A-DWG-091 | 3 | General Arrangement Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-02-24 20:04 | 2016-02-16 17:40 |  | No | -8 |  | 2016-03-02 15:04 | [6 empty] | 2016-03-02 20:00 | Yes | 0
VD-9001-213A-DWG-108 | 5 | Roof Nozzles for Tk-7101A/B | PV-213A | MachineSazi Pars | 2016-02-13 | 2016-02-16 07:57 | 2016-02-16 07:58 | Yes | 3 |  | 2016-02-23 16:27 | [6 empty] | 2016-02-23 20:00 | Yes | -7
VD-9001-213B-PCJ-016 | 4 | Painting & Pickling and Passivation procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-02-13 17:15 | 2016-02-16 18:19 | 2016-02-16 18:20 | Yes | 3 |  | 2016-02-25 10:10 | [6 empty] | 2016-02-25 20:00 | Yes | -5
VD-9001-253(A)-CAL-050 | 2 | STRUCTURE CALCULATION for 3001 | HM-253A | FATEH SANAT KIMIA | 2016-02-13 17:16 | 2016-02-14 08:44 | 2016-02-14 08:43 | Yes | 1 |  | 2016-02-20 09:05 | [6 empty] | 2016-02-20 20:00 | Yes | -8
VD-9001-204A-CAL-150 | 3 | Strength Calculation FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-02-27 20:04 | 2016-06-16 12:54 |  | No | 110 |  | 2016-06-20 11:23 | [6 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-204A-DWG-155 | 1 | PF & LD Arrangement FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-02-27 20:04 | 2016-02-16 16:13 |  | No | -11 |  | 2016-02-21 08:50 | [6 empty] | 2016-02-21 20:00 | Yes | 0
VD-9001-253(A)-DWG-032 | 6 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2016-02-14 | 2016-05-17 16:21 | 2016-05-17 16:20 | Yes | 93 |  | 2016-06-07 15:42 | [6 empty] | 2016-06-07 19:58 | Yes | 7 | 1204-Owner-v | 2018-06-19 09:27
VD-9001-105-DIG-205 | 2 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-28 20:04 | 2016-02-16 15:21 |  | No | -12 | 2016-03-10 11:18 | [7 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-254-CAL-585 | 1 | CALCULATION SHEET FOR THERMOWELL | HM-254 | AZAR AB | 2016-02-28 20:04 | 2016-05-18 06:43 |  | No | 80 | 2016-06-13 16:16 | [7 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-254-LST-216 | 4 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2016-02-28 20:04 | 2016-03-26 13:39 |  | No | 27 | 2016-05-09 11:07 | [7 empty] | 2016-05-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-17 08:54
VD-9001-254-SLD-210 | 4 | SINGLE LINE DIAGRAM | HM-254 | AZAR AB | 2016-02-28 20:04 | 2016-03-26 13:40 | 2016-03-26 13:41 | Yes | 27 |  | 2016-05-09 10:56 | [6 empty] | 2016-05-09 19:59 | Yes | 30
VD-9001-254-LST-220 | 1 | WIRING LIST AND CABLE ROUTH ( POWER ) | HM-254 | AZAR AB | 2016-02-28 20:04 | 2018-06-11 16:25 | 2018-06-11 16:28 | Yes | 834 |  |  |  | 2018-07-07 15:19 |  |  |  |  | 2018-07-07 15:19 | Yes | 12
VD-9001-206B-DWG-042 | 1 | BODY & SUPPORT DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2016-02-28 20:04 | 2016-03-07 14:25 |  | No | 8 |  | 2016-03-14 11:44 | [6 empty] | 2016-03-14 20:00 | Yes | 0
VD-9001-204A-DWG-033 | 1 | Name Plate Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-02-29 20:04 | 2016-02-16 16:26 |  | No | -13 |  | 2016-02-17 16:52 | [6 empty] | 2016-02-17 20:02 | Yes | 0
VD-9001-204A-DWG-143 | 1 | Name Plate Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-03-01 20:04 | 2016-02-17 10:45 |  | No | -13 |  | 2016-02-20 17:29 | [6 empty] | 2016-02-20 20:00 | Yes | 0
VD-9001-254-DSH-604 | 4 | BOILER DATA SHEET | HM-254 | AZAR AB | 2016-03-01 20:04 | 2017-08-29 12:55 | 2017-08-29 12:56 | Yes | 546 |  | 2017-09-04 14:36 | [6 empty] | 2017-09-04 19:57 | Yes | -8 | 1204-Owner-v | 2018-01-25 11:15
VD-9001-254-SPE-109 | 3 | TERMINAL POINT SPECIFICATION | HM-254 | AZAR AB | 2016-03-01 20:04 | 2016-02-28 16:25 |  | No | -2 | 2016-03-12 17:30 | [7 empty] | 2016-03-12 20:00 | Yes | 0
VD-9001-108-DBS-006 | 4 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2016-03-02 | 2016-03-06 08:07 |  | No | 4 |  | 2016-03-15 11:11 | [6 empty] | 2016-03-15 20:00 | Yes | 0
VD-9001-204A-DWG-144 | 1 | PF & LD Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-03-02 20:02 | 2016-07-16 15:58 |  | No | 136 | 2016-08-03 10:46 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-204A-DWG-152 | 1 | Nozzle Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-03-02 20:02 | 2016-02-22 16:13 |  | No | -9 |  | 2016-03-01 16:32 | [6 empty] | 2016-03-01 20:00 | Yes | 0
VD-9001-105-DPH-104 | 2 | Interlock description | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-20 | 2016-05-31 18:16 | 2016-05-31 18:17 | Yes | 101 |  | 2016-06-09 11:55 | [6 empty] | 2016-06-09 19:58 | Yes | -5
VD-9001-105-LST-205 | 2 | Set point list of HRU for FCS’s monitor and control | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-20 | 2016-04-27 19:14 |  | No | 67 | 2016-05-09 18:14 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-105-DPH-103 | 2 | Cause and effect diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-20 | 2016-05-31 18:09 | 2016-05-31 18:10 | Yes | 101 |  | 2016-06-09 11:50 | [6 empty] | 2016-06-09 19:58 | Yes | -5 | 1204-Owner-v | 2019-01-07 08:22
VD-9001-105-PPL-301 | 2 | Plot plan of HRU | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-20 | 2016-05-19 12:42 |  | No | 89 | 2016-06-02 08:27 | [7 empty] | 2016-06-02 19:58 | Yes | 0 | 1204-Owner-v | 2019-08-15 14:37
VD-9001-105-DWG-301 | 2 | Piping general arrangement and tie-point list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-20 | 2016-05-19 12:38 |  | No | 89 | 2016-07-27 15:43 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-204A-DWG-032 | 1 | Nozzle Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-03-05 20:00 | 2016-03-06 14:02 |  | No | 1 |  | 2016-03-06 17:03 | [6 empty] | 2016-03-06 20:00 | Yes | 0
VD-9001-204A-DWG-154 | 1 | PF & LD Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-03-05 20:00 | 2016-07-25 09:42 |  | No | 142 | 2016-08-06 14:48 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-204A-DWG-153 | 1 | Name Plate Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-03-05 20:00 | 2016-02-21 09:41 |  | No | -13 |  | 2016-02-27 15:18 | [6 empty] | 2016-02-27 20:00 | Yes | 0
VD-9001-206B-PCJ-005 | 1 | RADIOGRPHY TEST PROCEDURE (RT) | PV-206B | TASHA | 2016-03-05 20:00 | 2016-05-07 08:48 | 2016-05-07 08:48 | Yes | 63 |  | 2016-06-06 11:02 | [6 empty] | 2016-06-06 19:58 | Yes | 16
VD-9001-206B-PCJ-008 | 1 | ULTRASONIC TEST PROCEDURE (UT) | PV-206B | TASHA | 2016-03-05 20:00 | 2016-05-07 08:51 | 2016-05-07 08:52 | Yes | 63 |  | 2016-06-06 11:03 | [6 empty] | 2016-06-06 19:58 | Yes | 16
VD-9001-206B-PCJ-007 | 1 | LIQUID PENETRANT TEST PROCEDURE (PT) | PV-206B | TASHA | 2016-03-05 20:00 | 2016-05-07 08:51 | 2016-05-07 08:52 | Yes | 63 |  | 2016-06-06 11:05 | [6 empty] | 2016-06-06 19:58 | Yes | 16
VD-9001-105-DIG-201 | 1 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-21 | 2016-02-23 14:13 |  | No | 2 | 2016-04-09 08:41 | [7 empty] | 2016-04-09 19:59 | Yes | 0
VD-9001-105-DIG-203 | 1 | Instrument, cable, junction box and cable tray layout diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-21 | 2016-06-14 10:24 |  | No | 114 | 2016-06-28 15:19 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-204A-DWG-142 | 1 | Nozzle Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-03-06 20:00 | 2016-02-25 08:03 |  | No | -10 | [9 empty] | No | 0
VD-9001-203-SCH-001 | 0 | Time Schedule | PV-203 | Masnout Felezi Sangin (MFS) | 2016-02-16 |  |  | No | 1585 | [9 empty] | No | 0
VD-9001-203-DIS-002 | 0 | Vendor Document Index & Schedule | PV-203 | Masnout Felezi Sangin (MFS) | 2016-02-16 |  |  | No | 1585 | [9 empty] | No | 0
VD-9001-203-ITP-003 | 0 | Inspection Test Plan | PV-203 | Masnout Felezi Sangin (MFS) | 2016-03-16 | 2016-04-02 15:05 |  | No | 17 | 2016-04-19 09:54 | [7 empty] | 2016-04-19 19:59 | Yes | 0
VD-9001-203-QCP-004 | 0 | Quality Assurance Plan | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-12-08 09:01 | 2016-12-08 09:02 | Yes | 177 |  | 2016-12-10 09:27 | [6 empty] | 2016-12-10 19:59 | Yes | -12
VD-9001-203-DSH-005 | 0 | Technical Data Sheet (Process&Mechanic) | PV-203 | Masnout Felezi Sangin (MFS) | 2016-03-03 | 2016-02-24 16:26 |  | No | -8 | 2016-04-19 09:49 | [7 empty] | 2016-04-19 19:59 | Yes | 0
VD-9001-203-HMB-006 | 0 | Deaerator Heat and Mass Balances | PV-203 | Masnout Felezi Sangin (MFS) | 2016-03-03 | 2016-02-29 17:29 |  | No | -3 | 2016-04-12 11:27 | [7 empty] | 2016-04-12 19:59 | Yes | 0
VD-9001-203-CAL-007 | 0 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-04-24 | 2016-05-19 14:00 |  | No | 25 | 2016-06-05 11:48 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-203-CAL-008 | 0 | Lifting Calculation | PV-203 | Masnout Felezi Sangin (MFS) | 2016-04-24 | 2016-07-16 14:10 |  | No | 83 | 2016-08-13 10:14 | [7 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-203-CAL-009 | 0 | Loading Data | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-10-01 12:13 |  | No | 135 | 2017-01-14 10:18 | [7 empty] | 2017-01-14 20:00 | Yes | 0
VD-9001-203-DWG-010 | 0 | Internal Parts Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-11 | 2016-07-13 16:47 |  | No | 32 | 2016-09-24 16:02 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-203-DWG-011 | 0 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-05-25 12:56 |  | No | 6 | 2016-06-26 11:05 | [7 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-203-DWG-012 | 0 | Shell Araangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-05-25 12:56 |  | No | 6 | 2016-06-29 08:29 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-203-DWG-013 | 0 | Detail of Manhole Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-05-29 09:47 |  | No | 10 | 2016-06-26 14:54 | [7 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-203-DWG-014 | 0 | Detail of Nozzle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-07-13 16:49 |  | No | 55 | 2016-10-04 17:38 | [7 empty] | 2016-10-04 18:56 | Yes | 0
VD-9001-203-DWG-015 | 0 | Detail of Saddle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-05-25 12:57 |  | No | 6 | 2016-07-05 09:09 | [7 empty] | 2016-07-05 19:58 | Yes | 0
VD-9001-203-DWG-016 | 0 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-07-16 16:26 |  | No | 58 | 2016-08-13 10:16 | [7 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-203-DWG-017 | 0 | Name Plate Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-06-01 11:23 |  | No | 13 | 2016-06-05 11:50 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-203-DWG-019 | 0 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-19 | 2016-11-13 09:36 |  | No | 178 | 2016-12-18 11:18 | [7 empty] | 2016-12-18 19:59 | Yes | 0
VD-9001-203-DWG-020 | 0 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-04-06 | 2016-03-12 17:41 |  | No | -25 | 2016-04-20 12:00 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-203-DWG-021 | 0 | Sprayer Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-21 | 2016-10-05 17:36 | 2016-10-05 17:37 | Yes | 106 |  | 2016-10-23 15:38 | [6 empty] | 2016-10-23 20:00 | Yes | 4
VD-9001-203-PCJ-022 | 0 | NDT Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-29 | 2016-08-30 12:23 | 2016-08-30 12:24 | Yes | 93 |  | 2016-09-04 07:53 | [6 empty] | 2016-09-04 19:56 | Yes | -9
VD-9001-203-PCJ-023 | 0 | Surface Preparation & Painting Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-11-22 12:45 |  | No | 161 | 2016-12-03 14:29 | [7 empty] | 2016-12-03 20:00 | Yes | 0
VD-9001-203-PCJ-024 | 0 | Hydrostatic Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-06 | 2016-12-10 15:01 |  | No | 187 | 2016-12-18 09:03 | [7 empty] | 2016-12-18 19:59 | Yes | 0
VD-9001-203-PCJ-025 | 0 | Packing, Shipping and Marking Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-22 | 2016-12-10 15:02 |  | No | 171 | 2017-01-07 08:27 | [7 empty] | 2017-01-07 19:58 | Yes | 0
VD-9001-203-MNL-026 | 0 | Operating & Maintenance Manual | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-10-16 09:45 |  | No | 124 | 2016-11-14 10:45 | [7 empty] | 2016-11-14 20:00 | Yes | 0
VD-9001-203-VLS-027 | 0 | Sub vendor List | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-04 | 2016-05-08 14:34 |  | No | -180 | 2016-05-10 11:07 | [7 empty] | 2016-05-10 19:58 | Yes | 0
VD-9001-203-VDR-028 | 0 | Spare Part List for 2 Years Operation | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-11-29 12:04 | 2016-11-29 12:05 | Yes | 168 |  | 2016-12-12 11:17 | [6 empty] | 2016-12-12 19:59 | Yes | -1
VD-9001-203-VDR-029 | 0 | Spare Part List for Pre-commissioning, Maintenance | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-11-29 12:06 | 2016-11-29 12:07 | Yes | 168 |  | 2016-12-12 11:16 | [6 empty] | 2016-12-12 19:59 | Yes | -1
VD-9001-203-WBK-030 | 0 | Welding Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-08-06 14:35 |  | No | 53 | 2016-08-22 08:03 | [7 empty] | 2016-08-22 19:57 | Yes | 0
VD-9001-203-NPL-031 | 0 | NDT Map | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-11 | 2016-08-01 09:28 |  | No | 51 |  | 2016-08-22 08:05 | [6 empty] | 2016-08-22 19:57 | Yes | 0
VD-9001-203-INX-032 | 0 | Final Data Book Index | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 | 2016-11-23 17:30 |  | No | 162 | 2016-12-21 09:49 | [7 empty] | 2016-12-21 19:59 | Yes | 0
VD-9001-205A-DWG-037 | 3 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-07 20:00 | 2016-05-28 17:31 | 2016-05-28 17:32 | Yes | 82 |  | 2016-06-05 11:20 | [6 empty] | 2016-06-05 19:58 | Yes | -6
VD-9001-206B-CAL-033 | 1 | LIFTING/TAILING LUG CALCULATION-T-2001 | PV-206B | TASHA | 2016-03-07 20:00 | 2016-03-07 14:14 | 2016-03-07 14:15 | Yes | 0 |  | 2016-03-12 09:21 | [6 empty] | 2016-03-12 19:59 | Yes | -9 | 1204-Owner-v | 2019-08-06 13:54
VD-9001-206B-CAL-063 | 1 | LIFTING/TAILING LUG CALCULATION-T-4001 | PV-206B | TASHA | 2016-03-07 20:00 | 2016-03-07 14:15 | 2016-03-07 14:16 | Yes | 0 |  | 2016-03-12 09:25 | [6 empty] | 2016-03-12 20:00 | Yes | -9
VD-9001-205A-DWG-018 | 5 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-07 20:00 | 2016-04-18 14:23 |  | No | 42 |  | 2016-04-20 11:53 | [6 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-206B-DWG-073 | 1 | MANHOLE & NOZZLE DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2016-03-07 20:00 | 2016-03-07 14:35 | 2016-03-07 14:36 | Yes | 0 |  | 2016-03-16 15:39 | [6 empty] | 2016-03-16 20:00 | Yes | -5
VD-9001-206B-DWG-043 | 1 | MANHOLE & NOZZLE DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2016-03-07 20:00 | 2016-03-09 07:59 |  | No | 2 | 2016-03-14 10:29 | [7 empty] | 2016-03-14 20:00 | Yes | 0
VD-9001-205A-DWG-023 | 4 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-07 20:00 | 2016-04-18 14:32 |  | No | 42 |  | 2016-04-20 11:46 | [6 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-254-PID-114 | 3 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-07 20:00 | 2016-05-10 07:22 |  | No | 64 | 2016-06-08 16:35 | [7 empty] | 2016-06-08 19:58 | Yes | 0
VD-9001-254-PID-115 | 3 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-07 20:00 | 2016-05-10 07:22 |  | No | 64 | 2016-06-11 10:54 | [7 empty] | 2016-06-11 19:58 | Yes | 0
VD-9001-254-PID-116 | 3 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-07 20:00 | 2016-05-10 07:20 |  | No | 64 | 2016-06-08 14:46 | [7 empty] | 2016-06-08 19:58 | Yes | 0
VD-9001-254-PID-118 | 3 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-07 20:00 | 2016-05-10 07:21 |  | No | 64 | 2016-06-08 16:22 | [7 empty] | 2016-06-08 19:58 | Yes | 0 | 1204-Owner-v | 2019-10-15 13:15
VD-9001-213B-WMP-015 | 4 | Welding Maps for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-02-23 10:01 | 2016-03-05 12:31 | 2016-03-05 12:32 | Yes | 11 |  | 2016-03-06 08:50 | [6 empty] | 2016-03-06 20:00 | Yes | -13
VD-9001-213A-DWG-134 | 5 | Roof Nozzles for Tk-7201 | PV-213A | MachineSazi Pars | 2016-02-23 | 2016-02-24 15:24 | 2016-02-24 15:25 | Yes | 1 |  | 2016-03-09 11:59 | [6 empty] | 2016-03-09 20:00 | Yes | 0
VD-9001-254-PID-120 | 3 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-08 20:00 | 2016-05-10 07:21 |  | No | 63 | 2016-06-08 16:26 | [7 empty] | 2016-06-08 19:58 | Yes | 0
VD-9001-254-PID-119 | 2 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-08 20:00 | 2016-05-10 07:21 |  | No | 63 | 2016-06-11 10:43 | [7 empty] | 2016-06-11 19:58 | Yes | 0 | 1204-Owner-v | 2019-07-10 10:29
VD-9001-254-PID-121 | 2 | STEAM TURBINE P&I DIAGRAM | HM-254 | AZAR AB | 2016-03-08 20:00 | 2016-05-10 07:21 |  | No | 63 | 2016-06-11 10:50 | [7 empty] | 2016-06-11 19:58 | Yes | 0 | 1204-Owner-v | 2018-04-17 14:35
VD-9001-254-LGD-122 | 3 | P&I DIAGRAM SYMBOLS & LEGENDS | HM-254 | AZAR AB | 2016-03-08 20:00 | 2016-05-10 07:23 | 2016-05-10 07:24 | Yes | 63 |  | 2016-06-11 10:57 | [6 empty] | 2016-06-11 19:58 | Yes | 18 | 1204-Owner-v | 2018-01-28 15:31
VD-9001-206B-DWG-071 | 3 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2016-03-08 20:00 | 2016-03-07 14:33 |  | No | -1 |  | 2016-03-16 16:56 | [6 empty] | 2016-03-16 20:00 | Yes | 0
VD-9001-206B-DWG-041 | 3 | GENERAL ARRANGMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-03-08 20:00 | 2016-03-07 14:17 |  | No | -1 |  | 2016-03-14 11:03 | [6 empty] | 2016-03-14 20:00 | Yes | 0
VD-9001-254-DBS-600 | 3 | BOILER DESIGN BASE DATA SHEET | HM-254 | AZAR AB | 2016-03-09 20:00 | 2016-03-01 07:55 |  | No | -8 | 2016-03-12 17:33 | [7 empty] | 2016-03-12 20:00 | Yes | 0 | 1204-Owner-v | 2019-01-22 17:32
VD-9001-213A-MTO-027 | 1 | MTO for Tk-7201 | PV-213A | MachineSazi Pars | 2016-02-25 | 2016-02-27 12:43 | 2016-02-27 12:44 | Yes | 2 |  | 2016-02-28 07:28 | [6 empty] | 2016-02-28 20:00 | Yes | -13
VD-9001-213A-MTO-20 | 1 | MTO for Tk-7101A/B | PV-213A | MachineSazi Pars | 2016-02-25 | 2016-02-27 12:45 | 2016-02-27 12:46 | Yes | 2 |  | 2016-02-28 07:31 | [6 empty] | 2016-02-28 20:00 | Yes | -13
VD-9001-213A-MTO-040 | 1 | MTO for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2016-02-25 | 2016-02-27 12:45 | 2016-02-27 12:46 | Yes | 2 |  | 2016-02-28 07:29 | [6 empty] | 2016-02-28 20:00 | Yes | -13
VD-9001-231A-PCJ-003 | 1 | FABRICATION PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-03-12 20:00 | 2016-06-29 15:25 | 2016-06-29 15:26 | Yes | 109 |  | 2016-12-28 12:18 | [6 empty] | 2016-12-28 19:59 | Yes | 168
VD-9001-231A-WMP-009 | 1 | WELDING BOOK (WPS & PQR) | PV-231A | Tarh Mechanic Gostar | 2016-03-12 20:00 | 2016-06-29 16:03 |  | No | 109 | 2016-07-27 16:17 | [7 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-206B-PCJ-011 | 2 | POST WELD HEAT TREATMENT PROCEDURE(P.W.H.T) | PV-206B | TASHA | 2016-03-12 20:00 | 2016-03-08 10:25 | 2016-03-08 10:26 | Yes | -4 |  | 2016-06-29 14:16 | [6 empty] | 2016-06-29 19:58 | Yes | 99 | 1204-Owner-v | 2018-10-08 10:37
VD-9001-206B-PCJ-017 | 2 | PMI PROCEDURE | PV-206B | TASHA | 2016-03-12 20:00 | 2016-05-04 14:58 | 2016-05-04 14:59 | Yes | 53 |  | 2016-06-06 11:20 | [6 empty] | 2016-06-06 19:58 | Yes | 19
VD-9001-105-DSH-211 | 2 | Data sheet of hydrogen analyzer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-28 | 2016-05-17 20:11 |  | No | 79 | 2016-06-02 08:22 | [7 empty] | 2016-06-02 19:58 | Yes | 0
VD-9001-105-DIG-202 | 2 | Interlock logic diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-02-28 | 2016-03-05 07:53 |  | No | 6 |  | 2016-03-10 11:54 | [6 empty] | 2016-03-10 20:00 | Yes | 0
VD-9001-206B-DWG-011 | 3 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-03-13 20:00 | 2016-03-08 13:14 |  | No | -5 |  | 2016-03-12 10:27 | [6 empty] | 2016-03-12 20:00 | Yes | 0
VD-9001-206B-CAL-001 | 3 | MECHANICAL CALCULATION BOOK -T-1001 | PV-206B | TASHA | 2016-03-13 20:00 | 2016-03-08 15:26 |  | No | -5 |  | 2016-03-09 18:08 | [6 empty] | 2016-03-09 20:00 | Yes | 0
VD-9001-206B-DWG-072 | 1 | BODY & SUPPORT DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2016-03-13 20:00 | 2016-03-07 14:34 |  | No | -6 |  | 2016-03-14 11:47 | [6 empty] | 2016-03-14 20:00 | Yes | 0
VD-9001-206B-PCJ-009 | 1 | VISUAL INSPECTION PROCEDURE (VT) | PV-206B | TASHA | 2016-03-14 | 2016-06-26 15:21 | 2016-06-26 15:22 | Yes | 104 |  | 2016-07-27 16:34 | [6 empty] | 2016-07-27 19:57 | Yes | 17
VD-9001-231A-PCJ-004 | 1 | REPAIR PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-03-14 20:00 | 2016-11-14 14:30 | 2016-11-14 14:31 | Yes | 245 |  | 2017-01-01 16:58 | [6 empty] | 2017-01-01 19:59 | Yes | 34
VD-9001-205A-DWG-003 | 4 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-14 20:00 | 2016-05-28 17:30 |  | No | 75 | 2016-06-05 11:30 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-206B-DWG-012 | 1 | BODY & SUPPORT DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2016-03-14 20:00 | 2016-03-16 18:07 |  | No | 2 | 2016-04-11 11:30 | [7 empty] | 2016-04-11 19:59 | Yes | 0
VD-9001-206B-CAL-004 | 1 | LIFTING/TAILING LUG CALCULATION-T-1001 | PV-206B | TASHA | 2016-03-14 20:00 | 2016-03-08 15:27 |  | No | -6 |  | 2016-03-16 16:59 | [6 empty] | 2016-03-16 20:00 | Yes | 0
VD-9001-206B-PCJ-013 | 1 | HYDROSTATIC TEST PROCEDURE | PV-206B | TASHA | 2016-03-14 20:00 | 2016-04-02 12:01 |  | No | 19 | 2016-05-31 10:54 | [7 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-206B-CAL-003 | 1 | FEA CALCULATION FOR CONE AND TRIPLE FORGE -T-1001 | PV-206B | TASHA | 2016-03-01 09:15 | 2016-03-03 10:15 |  | No | 2 | 2016-03-06 13:53 | [7 empty] | 2016-03-06 20:00 | Yes | 0
VD-9001-205A-DWG-051 | 1 | GENERAL ARRANGEMENT DRAWING FOR OF D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-15 20:00 | 2016-04-04 15:40 |  | No | 20 | 2016-07-23 15:05 | [7 empty] | 2016-07-23 19:57 | Yes | 0
VD-9001-204A-CAL-080 | 2 | Strength Calculation FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-03-15 20:00 | 2016-05-26 12:23 |  | No | 72 |  | 2016-05-31 10:12 | [6 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-253(A)-PCJ-112 | 1 | REPAIR PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-03-02 | 2016-06-15 09:03 |  | No | 105 | 2016-08-23 10:51 | [7 empty] | 2016-08-23 19:57 | Yes | 0 | 1204-Owner-v | 2019-07-06 14:08
VD-9001-206B-PCJ-015 | 1 | PAINTING PROCEDURE | PV-206B | TASHA | 2016-03-16 20:00 | 2016-05-04 14:59 |  | No | 49 | 2016-06-06 11:18 | [7 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-206B-PCJ-019 | 1 | PICKLING&PASSIVATION PROCEDURE | PV-206B | TASHA | 2016-03-16 20:00 | 2016-03-08 10:29 | 2016-03-08 10:29 | Yes | -8 |  | 2016-03-15 17:40 | [6 empty] | 2016-03-15 20:00 | Yes | -7
VD-9001-205A-DWG-053 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-03-16 20:00 | 2016-04-04 15:42 | 2016-04-04 15:43 | Yes | 19 |  | 2016-07-10 11:40 | [6 empty] | 2016-07-10 19:58 | Yes | 83
VD-9001-206B-CAL-062 | 1 | EXTERNAL ATTACHMENT CALCULATION-T-4001 | PV-206B | TASHA | 2016-03-06 09:04 | 2016-03-26 11:30 | 2016-03-26 11:31 | Yes | 20 |  | 2016-04-13 10:17 | [6 empty] | 2016-04-13 19:59 | Yes | 4 | 1204-Owner-v | 2018-05-14 09:45
VD-9001-206B-CAL-003 | 2 | FEA CALCULATION FOR CONE AND TRIPLE FORGE -T-1001 | PV-206B | TASHA | 2016-03-20 20:00 | 2016-04-20 10:09 | 2016-04-20 10:10 | Yes | 31 |  | 2016-07-09 11:53 | [6 empty] | 2016-07-09 19:58 | Yes | 66
VD-9001-204B-CAL-001 | 0 | Strength Calculation Book D-1002 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-04-27 17:18 |  | No | 7 | 2016-05-21 09:12 | [7 empty] | 2016-05-21 19:58 | Yes | 0
VD-9001-204B-CAL-002 | 0 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-04-12 18:37 |  | No | -8 | 2016-05-04 15:53 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204B-CAL-003 | 0 | Strength Calculation Book D-3006 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-05-08 17:02 |  | No | 18 | 2016-06-11 16:50 | [7 empty] | 2016-06-11 19:58 | Yes | 0
VD-9001-204B-CAL-004 | 0 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-05-04 16:58 |  | No | 14 | 2016-06-07 12:02 | [7 empty] | 2016-06-07 19:58 | Yes | 0
VD-9001-204B-CAL-005 | 0 | Local Stress Calculation D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-10-17 07:40 |  | No | 156 | 2016-11-08 14:45 | [7 empty] | 2016-11-08 19:59 | Yes | 0
VD-9001-204B-CAL-006 | 0 | Local Stress Calculation D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-10-18 11:20 |  | No | 157 | 2016-11-08 14:46 | [7 empty] | 2016-11-08 19:59 | Yes | 0
VD-9001-204B-CAL-007 | 0 | Local Stress Calculation D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-10-18 12:03 |  | No | 157 | 2016-11-08 14:47 | [7 empty] | 2016-11-08 19:59 | Yes | 0
VD-9001-204B-CAL-008 | 0 | Local Stress Calculation D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-10-18 07:54 |  | No | 157 | 2016-11-08 14:49 | [7 empty] | 2016-11-08 19:59 | Yes | 0
VD-9001-204B-CAL-009 | 0 | Transportation Saddle Calculation D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-06 08:38 |  | No | 112 | 2016-09-24 11:43 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-CAL-010 | 0 | Transportation Saddle Calculation D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-06 08:38 |  | No | 112 | 2016-09-24 11:47 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-CAL-011 | 0 | Transportation Saddle Calculation D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-06 08:38 |  | No | 112 | 2016-09-24 11:51 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-CAL-012 | 0 | Transportation Saddle Calculation D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-06 08:39 |  | No | 112 | 2016-09-24 11:52 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-DWG-001 | 0 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-04-27 17:15 |  | No | 7 | 2016-05-21 09:14 | [7 empty] | 2016-05-21 19:58 | Yes | 0
VD-9001-204B-DWG-002 | 0 | General Arrangment Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-04-12 17:59 |  | No | -8 | 2016-05-04 15:54 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204B-DWG-003 | 0 | General Arrangment Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-05-08 12:13 |  | No | 18 | 2016-06-21 09:47 | [7 empty] | 2016-06-21 19:57 | Yes | 0
VD-9001-204B-DWG-004 | 0 | General Arrangment Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-04-20 | 2016-05-04 18:07 |  | No | 14 | 2016-06-07 12:09 | [7 empty] | 2016-06-07 19:58 | Yes | 0
VD-9001-204B-DWG-005 | 0 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-12-11 09:59 |  | No | 211 | 2016-12-15 10:20 | [7 empty] | 2016-12-15 19:59 | Yes | 0
VD-9001-204B-DWG-006 | 0 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-12-04 11:58 |  | No | 204 | 2016-12-15 10:29 | [7 empty] | 2016-12-15 19:59 | Yes | 0
VD-9001-204B-DWG-007 | 0 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-11-22 09:05 |  | No | 192 | 2016-12-04 15:31 | [7 empty] | 2016-12-04 20:00 | Yes | 0
VD-9001-204B-DWG-008 | 0 | Ladder & Platform Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-11-14 10:18 |  | No | 184 | 2016-12-04 15:43 | [7 empty] | 2016-12-04 20:00 | Yes | 0
VD-9001-204B-DWG-009 | 0 | Body Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-04-30 12:01 |  | No | -7 | 2016-05-21 09:15 | [7 empty] | 2016-05-21 19:58 | Yes | 0
VD-9001-204B-DWG-010 | 0 | Body Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-04-12 18:06 |  | No | -25 | 2016-05-04 15:54 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204B-DWG-011 | 0 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-05-14 09:38 |  | No | 7 | 2016-06-22 15:37 | [7 empty] | 2016-06-22 19:57 | Yes | 0
VD-9001-204B-DWG-012 | 0 | Body Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-05-10 11:32 |  | No | 3 | 2016-06-07 12:13 | [7 empty] | 2016-06-07 19:58 | Yes | 0
VD-9001-204B-DWG-013 | 0 | Nozzle Detail Drawing D-1002 * | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-05-01 16:45 |  | No | -6 | 2016-05-21 09:18 | [7 empty] | 2016-05-21 19:58 | Yes | 0
VD-9001-204B-DWG-014 | 0 | Nozzle Detail Drawing D-1003 * | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-04-12 18:10 |  | No | -25 | 2016-05-04 15:54 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204B-DWG-015 | 0 | Nozzle Detail Drawing D-3006 * | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-05-22 09:11 |  | No | 15 | 2016-06-25 17:44 | [7 empty] | 2016-06-25 19:58 | Yes | 0
VD-9001-204B-DWG-016 | 0 | Nozzle Detail Drawing D-3007 * | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-05-17 17:22 |  | No | 10 | 2016-06-19 12:35 | [7 empty] | 2016-06-19 19:57 | Yes | 0
VD-9001-204B-DWG-017 | 0 | Name Plate Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-09-04 11:11 |  | No | 113 |  | 2016-09-18 14:53 | [6 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-DWG-018 | 0 | Name Plate Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-09-04 11:13 |  | No | 113 |  | 2016-09-18 14:56 | [6 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-DWG-019 | 0 | Name Plate Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-09-04 11:14 |  | No | 113 |  | 2016-09-18 14:59 | [6 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-DWG-020 | 0 | Name Plate Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-09-04 11:17 |  | No | 113 |  | 2016-09-18 15:02 | [6 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-DWG-021 | 0 | Transportation Saddle Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-27 14:30 | 2016-09-27 14:31 | Yes | 133 |  | 2016-10-01 17:02 | [6 empty] | 2016-10-01 18:56 | Yes | -10
VD-9001-204B-DWG-022 | 0 | Transportation Saddle Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-09-28 13:28 | 2016-09-28 13:29 | Yes | 134 |  | 2016-10-01 17:05 | [6 empty] | 2016-10-01 18:56 | Yes | -11
VD-9001-204B-DWG-023 | 0 | Transportation Saddle Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-10-02 12:17 | 2016-10-02 12:18 | Yes | 138 |  | 2016-10-05 14:53 | [6 empty] | 2016-10-05 18:56 | Yes | -11
VD-9001-204B-DWG-024 | 0 | Transportation Saddle Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-17 | 2016-10-03 08:43 | 2016-10-03 08:44 | Yes | 139 |  | 2016-10-05 15:44 | [6 empty] | 2016-10-05 18:56 | Yes | -12
VD-9001-204B-DWG-025 | 0 | Internall attachment drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-10-05 11:28 |  | No | 151 | 2016-10-23 12:29 | [7 empty] | 2016-10-23 20:00 | Yes | 0
VD-9001-204B-DWG-026 | 0 | Internall attachment drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-10-08 09:19 |  | No | 154 | 2016-10-23 12:36 | [7 empty] | 2016-10-23 20:00 | Yes | 0
VD-9001-204B-DWG-027 | 0 | Internall attachment drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-10-09 11:37 |  | No | 155 | 2016-10-26 11:41 | [7 empty] | 2016-10-26 20:00 | Yes | 0
VD-9001-204B-DWG-028 | 0 | Internall attachment drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-07 | 2016-10-09 12:32 |  | No | 155 | 2016-10-23 15:00 | [7 empty] | 2016-10-23 20:00 | Yes | 0
VD-9001-204B-DWG-029 | 0 | Template Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-04-30 11:40 |  | No | -14 | 2016-05-21 09:19 | 2016-05-17 14:55 | [6 empty] | 2016-05-21 19:58 | Yes | 0
VD-9001-204B-DWG-030 | 0 | Template Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-04-12 18:46 |  | No | -32 |  | 2016-05-08 11:38 | [6 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-204B-DWG-031 | 0 | Template Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-05-14 09:42 |  | No | 0 |  | 2016-06-11 16:52 | [6 empty] | 2016-06-11 19:58 | Yes | 0
VD-9001-204B-DWG-032 | 0 | Template Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-14 | 2016-05-10 11:33 |  | No | -4 |  | 2016-05-17 15:35 | [6 empty] | 2016-05-17 19:58 | Yes | 0
VD-9001-204B-WMP-001 | 0 | Welding & NDT Map D-1002 | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2017-02-21 14:45 |  | No | 272 | 2017-03-18 16:17 | [7 empty] | 2017-03-18 20:00 | Yes | 0
VD-9001-204B-WMP-002 | 0 | Welding & NDT Map D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2017-03-12 07:59 |  | No | 291 | 2017-04-15 15:03 | [7 empty] | 2017-04-15 20:59 | Yes | 0
VD-9001-204B-WMP-003 | 0 | Welding & NDT Map D-3006 | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2017-03-12 07:57 |  | No | 291 | 2017-04-15 14:50 | [7 empty] | 2017-04-15 20:59 | Yes | 0
VD-9001-204B-WMP-004 | 0 | Welding & NDT Map D-3007 | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2017-03-12 08:00 |  | No | 291 | 2017-04-15 15:09 | [7 empty] | 2017-04-15 20:59 | Yes | 0
VD-9001-204B-WPS-001 | 0 | Welding Procedure Specification (WPS) For S.S | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2017-02-21 13:56 |  | No | 279 | 2017-03-14 09:22 | [7 empty] | 2017-03-14 20:00 | Yes | 0
VD-9001-204B-WPS-002 | 0 | Welding Procedure Specification (WPS) For C.S | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2017-02-21 14:33 |  | No | 279 | 2017-03-18 16:21 | [7 empty] | 2017-03-18 20:00 | Yes | 0
VD-9001-204B-PQR-001 | 0 | Procedure Qualification Record (PQR) For S.S | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2017-02-21 13:52 |  | No | 279 | 2017-03-14 09:09 | [7 empty] | 2017-03-14 20:00 | Yes | 0
VD-9001-204B-PQR-002 | 0 | Procedure Qualification Record (PQR) For C.S | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2017-02-21 13:53 |  | No | 279 | 2017-03-18 16:24 | [7 empty] | 2017-03-18 20:00 | Yes | 0
VD-9001-204B-ITP-001 | 0 | Inspection & Test Plan | PV-204B | ABAN AIR COOLER. | 2016-04-10 | 2016-08-16 09:32 |  | No | 128 | 2016-09-18 14:24 | [7 empty] | 2016-09-18 19:56 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:51
VD-9001-204B-PCJ-001 | 0 | Repair Procedure | PV-204B | ABAN AIR COOLER. | 2016-05-11 | 2016-08-20 14:12 |  | No | 101 | 2016-09-24 14:22 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-PCJ-002 | 0 | Magnetic Particle Procedure | PV-204B | ABAN AIR COOLER. | 2016-04-10 | 2016-08-16 09:33 |  | No | 128 | 2016-09-18 14:27 | [7 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-PCJ-003 | 0 | Ultrasonic Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-04-10 | 2016-08-16 09:34 |  | No | 128 | 2016-09-18 14:28 | [7 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-PCJ-004 | 0 | Liquid Penetrant Examination Procedure | PV-204B | ABAN AIR COOLER. | 2016-04-10 | 2016-08-16 12:26 |  | No | 128 | 2016-09-18 14:30 | [7 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-PCJ-005 | 0 | Radiography Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-04-10 | 2016-08-16 12:27 |  | No | 128 | 2016-09-18 14:31 | [7 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-PCJ-006 | 0 | Hydrostatic and Air Leak Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-08-17 13:50 |  | No | 91 | 2016-09-21 14:06 | [7 empty] | 2016-09-21 18:56 | Yes | 0
VD-9001-204B-PCJ-007 | 0 | Pickling Procedure | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-08-17 13:58 |  | No | 91 | 2016-09-24 11:59 | [7 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-204B-PCJ-008 | 0 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-08-20 14:11 |  | No | 94 | 2016-09-18 14:33 | [7 empty] | 2016-09-18 19:56 | Yes | 0
VD-9001-204B-PCJ-009 | 0 | Painting Procedure | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-08-17 09:09 |  | No | 91 | 2016-10-03 11:32 | [7 empty] | 2016-10-03 18:56 | Yes | 0 | 1204-Owner-v | 2019-01-20 13:40
VD-9001-204B-PCJ-010 | 0 | Packing and Shipping Procedure and Packing list | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2016-12-27 12:28 | 2016-12-27 12:29 | Yes | 216 |  | 2017-01-22 11:43 | [6 empty] | 2017-01-22 20:00 | Yes | 12 | 1204-Owner-v | 2020-04-29 08:41
VD-9001-204B-DIS-001 | 0 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2016-02-24 | 2016-03-08 11:34 |  | No | 13 | [9 empty] | No | 0
VD-9001-204B-INX-001 | 0 | Final Data Book Index | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2017-01-30 11:39 |  | No | 250 | 2017-02-19 15:39 | [7 empty] | 2017-02-19 20:00 | Yes | 0
VD-9001-204B-MDB-001 | 0 | Final Data Book | PV-204B | ABAN AIR COOLER. | 2016-05-25 | 2019-05-07 11:52 | 2019-05-07 11:59 | Yes | 1077 |  |  | 2019-05-26 10:40 | [5 empty] | 2019-05-26 20:58 | Yes | 5 | 1204-Owner-v | 2020-04-29 08:36
VD-9001-204B-LST-001 | 0 | Spare Parts For Pri-Commissioning, Commissining and Start up | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-12-07 17:30 | 2016-12-07 17:28 | Yes | 203 |  | 2016-12-11 11:07 | [6 empty] | 2016-12-11 19:59 | Yes | -10 | 1204-Owner-v | 2020-04-29 08:29
VD-9001-204B-LST-002 | 0 | Spare Part For Two-Years Operation | PV-204B | ABAN AIR COOLER. | 2016-05-18 | 2016-12-07 17:32 | 2016-12-07 17:33 | Yes | 203 |  | 2016-12-11 11:08 | [6 empty] | 2016-12-11 19:59 | Yes | -10 | 1204-Owner-v | 2019-07-13 17:49
VD-9001-206B-DWG-044 | 1 | INTERNAL ATTACHMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-03-07 16:31 | 2016-03-09 08:03 |  | No | 2 |  | 2016-03-27 11:58 | [6 empty] | 2016-03-27 20:00 | Yes | 0
VD-9001-206B-DWG-074 | 1 | INTERNAL ATTACHMENT DRAWING -T-4001 | PV-206B | TASHA | 2016-03-07 16:31 | 2016-03-09 08:08 | 2016-03-09 08:09 | Yes | 2 |  | 2016-03-16 17:03 | [6 empty] | 2016-03-16 20:00 | Yes | -7 | 1204-Owner-v | 2020-05-11 14:40
VD-9001-204A-DWG-031 | 3 | General Arrangement Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-03-21 20:00 | 2016-04-19 08:06 |  | No | 29 |  | 2016-04-26 11:01 | [6 empty] | 2016-04-26 19:59 | Yes | 0 | 1204-Owner-v | 2019-10-01 17:37
VD-9001-204A-CAL-030 | 3 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-03-21 20:00 | 2016-04-19 08:04 |  | No | 29 |  | 2016-05-16 15:04 | [6 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-201-DWG-001 | 0 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2016-02-25 | 2016-11-07 18:25 |  | No | 256 | 2016-11-21 14:45 | [7 empty] | 2016-11-21 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 11:19
VD-9001-201-DWG-002 | 0 | WELD DETAILS - ND EXAMINATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-21 | 2017-06-21 19:39 |  | No | 457 | 2017-07-10 11:49 | [7 empty] | 2017-07-10 19:59 | Yes | 0
VD-9001-201-DWG-003 | 0 | TOP COVER & MAIN FLANGE | PV-201 | ATB RIVA CALZONI SpA | 2016-03-07 | 2016-04-01 19:32 |  | No | 25 | 2016-12-24 15:02 | [7 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-201-DWG-004 | 0 | TEMPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-07 | 2017-07-26 18:10 |  | No | 506 | 2017-09-18 16:08 | [7 empty] | 2017-09-18 19:57 | Yes | 0
VD-9001-201-DWG-005 | 0 | SUPPORT SKIRT EXTERNAL DETAILS TAILING LUG | PV-201 | ATB RIVA CALZONI SpA | 2016-03-07 | 2017-06-21 19:39 |  | No | 471 | 2017-08-09 11:34 | [7 empty] | 2017-08-09 19:58 | Yes | 0
VD-9001-201-DWG-006 | 0 | INTERNAL MISCELLANEOUS DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-22 | 2017-09-15 19:49 |  | No | 542 | 2017-12-03 10:16 | [7 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-201-DWG-007 | 0 | NAMEPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-29 | 2017-09-21 12:03 |  | No | 541 | 2017-09-27 11:55 | [7 empty] | 2017-09-27 20:00 | Yes | 0
VD-9001-201-DWG-008 | 0 | SHIPPING DRAWING | PV-201 | ATB RIVA CALZONI SpA | 2016-03-29 | 2017-10-27 18:25 |  | No | 577 | 2018-01-30 15:53 | [7 empty] | 2018-01-30 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-04 13:37
VD-9001-201-DWG-009 | 0 | INSULATION SUPPORT DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-22 | 2017-09-01 12:47 |  | No | 528 | 2017-09-19 14:54 | [7 empty] | 2017-09-19 19:57 | Yes | 0
VD-9001-201-CAL-001 | 0 | PRESSURE PARTS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-21 | 2016-04-01 19:31 |  | No | 11 | 2016-12-24 15:12 | [7 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-201-CAL-002 | 0 | FOUNDATION LOADS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-21 | 2016-11-07 16:35 |  | No | 231 | 2016-11-26 10:27 | [7 empty] | 2016-11-26 20:00 | Yes | 0
VD-9001-201-CAL-003 | 0 | LIFTING CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-07 | 2017-06-21 19:39 |  | No | 471 | 2017-08-09 11:33 | [7 empty] | 2017-08-09 19:58 | Yes | 0 | 1204-Owner-v | 2019-08-06 13:59
VD-9001-201-CAL-004 | 0 | SHIPPING SADDLES CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-29 | 2017-10-27 18:25 |  | No | 577 | 2018-01-30 16:00 | [7 empty] | 2018-01-30 20:00 | Yes | 0
VD-9001-201-CAL-005 | 0 | STRESS ANALYSIS OF TOP FLANGED JOINT | PV-201 | ATB RIVA CALZONI SpA | 2016-04-15 | 2018-05-30 20:37 | 2018-05-30 20:39 | Yes | 775 |  |  |  | 2018-10-09 11:32 |  |  |  |  | 2018-10-09 11:32 | Yes | 118
VD-9001-201-CAL-006 | 0 | STRESS ANALYSIS FOR BOTTOM HEAD | PV-201 | ATB RIVA CALZONI SpA | 2016-04-15 | 2018-05-30 20:42 | 2018-05-30 20:44 | Yes | 775 |  |  |  | 2018-11-20 11:48 |  |  |  |  | 2018-11-20 11:48 | Yes | 160
VD-9001-201-CAL-007 | 0 | FATIGUE ANALYSIS SCREENING | PV-201 | ATB RIVA CALZONI SpA | 2016-04-15 | 2018-05-14 15:01 | 2018-05-14 15:03 | Yes | 759 |  |  | 2018-06-12 14:45 | [5 empty] | 2018-06-12 14:45 | Yes | 15 | 1204-Owner-v | 2018-12-16 21:34
VD-9001-201-WBK-001 | 0 | WELDING DATA BOOK | PV-201 | ATB RIVA CALZONI SpA | 2016-03-25 | 2017-05-30 11:02 |  | No | 431 | 2017-06-14 11:20 | [7 empty] | 2017-06-14 20:00 | Yes | 0
VD-9001-201-MDB-001 | 0 | MANUFACTURING DATA BOOK INDEX | PV-201 | ATB RIVA CALZONI SpA | 2016-03-25 | 2017-05-16 18:19 |  | No | 417 | 2017-08-15 11:08 | [7 empty] | 2017-08-15 19:58 | Yes | 0
VD-9001-201-MDB-002 | 0 | MANUFACTURING DATA BOOK | PV-201 | ATB RIVA CALZONI SpA | 2017-03-15 |  |  | No | 1192 | [9 empty] | No | 0
VD-9001-201-ITP-001 | 0 | QUALITY CONTROL PLAN | PV-201 | ATB RIVA CALZONI SpA | 2016-03-25 | 2017-06-12 13:44 |  | No | 444 | 2017-06-24 16:48 | [7 empty] | 2017-06-24 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:44
VD-9001-201-MSS-001 | 0 | PLATE MATERIAL SPECIFICATION (SA 387 Gr 11 Cl.3) | PV-201 | ATB RIVA CALZONI SpA | 2016-02-25 | 2016-11-07 18:31 |  | No | 256 | 2016-11-19 11:42 | [7 empty] | 2016-11-19 20:00 | Yes | 0
VD-9001-201-MSS-002 | 0 | FORGING MATERIAL SPECIFICATION (SA 182 F5) | PV-201 | ATB RIVA CALZONI SpA | 2016-03-07 |  |  | No | 1565 | [9 empty] | No | 0
VD-9001-201-MSS-003 | 0 | FORGING MATERIAL SPECIFICATION (SA 336 F11 CL3) | PV-201 | ATB RIVA CALZONI SpA | 2016-02-25 | 2016-11-07 18:56 |  | No | 256 | 2016-11-19 11:48 | [7 empty] | 2016-11-19 20:00 | Yes | 0
VD-9001-201-PCJ-001 | 0 | HOT FORMING OF HEADS | PV-201 | ATB RIVA CALZONI SpA | 2016-02-29 | 2017-10-18 13:16 |  | No | 597 | 2017-11-25 15:50 | [7 empty] | 2017-11-25 19:59 | Yes | 0
VD-9001-201-PCJ-002 | 0 | PWHT/ISR/DHT PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-10-18 13:16 |  | No | 582 | 2017-11-25 18:00 | [7 empty] | 2017-11-25 19:59 | Yes | 0
VD-9001-201-PCJ-003 | 0 | BOLT TIGHTENING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-04-10 | 2017-11-10 19:31 |  | No | 579 |  |  |  | 2018-04-18 14:26 |  |  |  |  | 2018-04-18 14:26 | Yes | 0
VD-9001-201-PCJ-004 | 0 | DOUBLE CONE INSTALLATION PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-04-29 | 2017-11-07 20:35 |  | No | 557 |  |  |  | 2018-04-18 14:27 |  |  |  |  | 2018-04-18 14:27 | Yes | 0
VD-9001-201-PCJ-005 | 0 | HYDROTEST PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-04-10 | 2017-11-07 20:35 |  | No | 576 | 2017-11-25 11:09 | [7 empty] | 2017-11-25 19:59 | Yes | 0
VD-9001-201-PCJ-006 | 0 | NITROGEN PRESSURIZING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-05-16 | 2018-04-12 19:40 | 2018-04-12 19:43 | Yes | 696 |  |  |  | 2018-05-23 11:37 |  |  |  |  | 2018-05-23 11:37 | Yes | 27
VD-9001-201-PCJ-008 | 0 | PAINTING/CLEANING/DRYING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-05-16 | 2018-01-12 19:47 |  | No | 606 | 2018-01-29 11:23 | [7 empty] | 2018-01-29 20:00 | Yes | 0 | 1204-Owner-v | 2019-05-28 18:09
VD-9001-201-PCJ-009 | 0 | MINIMUM PRESSURIZATION TEMPERATURE (MPT) | PV-201 | ATB RIVA CALZONI SpA | 2016-02-27 | 2018-07-17 19:46 | 2018-07-17 19:47 | Yes | 871 |  |  | 2018-08-11 16:14 | [5 empty] | 2018-08-11 16:14 | Yes | 11 | 1204-Owner-v | 2018-12-16 21:37
VD-9001-201-PCJ-010 | 0 | RT EXAMINATION OF WELDS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-30 | 2017-09-20 11:24 | 2017-09-20 11:25 | Yes | 539 |  | 2017-10-08 09:12 | [6 empty] | 2017-10-08 20:00 | Yes | 4 | 1204-Owner-v | 2018-12-16 21:38
VD-9001-201-PCJ-011 | 0 | UT EXAMINATION OF WELDS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-30 | 2017-09-20 11:27 | 2017-09-20 11:28 | Yes | 539 |  | 2017-10-08 09:30 | [6 empty] | 2017-10-08 20:00 | Yes | 4
VD-9001-201-PCJ-012 | 0 | UT PHASED ARRAY | PV-201 | ATB RIVA CALZONI SpA | 2016-04-15 | 2017-10-13 15:05 |  | No | 546 |  | 2017-11-25 11:19 | [6 empty] | 2017-11-25 19:59 | Yes | 0
VD-9001-201-PCJ-013 | 0 | UT EXAMINATION OF WELD OVERLAY | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-09-20 11:28 | 2017-09-20 11:29 | Yes | 554 |  | 2017-10-08 09:22 | [6 empty] | 2017-10-08 20:00 | Yes | 4 | 1204-Owner-v | 2018-12-16 21:38
VD-9001-201-PCJ-014 | 0 | TOFD PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-04-15 | 2017-10-13 15:07 | 2017-10-13 15:08 | Yes | 546 |  | 2017-10-22 17:04 | [6 empty] | 2017-10-22 20:00 | Yes | -5 | 1204-Owner-v | 2018-12-16 21:38
VD-9001-201-PCJ-015 | 0 | MT EXAMINATION OF WELDS | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-07-03 18:30 | 2017-07-03 18:31 | Yes | 475 |  | 2017-07-10 11:58 | [6 empty] | 2017-07-10 19:59 | Yes | -7 | 1204-Owner-v | 2019-01-13 14:53
VD-9001-201-PCJ-016 | 0 | PT EXAMINATION | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-07-03 18:31 | 2017-07-03 18:32 | Yes | 475 |  | 2017-07-10 12:03 | [6 empty] | 2017-07-10 19:59 | Yes | -7 | 1204-Owner-v | 2019-01-13 14:54
VD-9001-201-PCJ-017 | 0 | REPAIR PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-07-06 17:22 |  | No | 478 | 2017-07-10 12:08 | [7 empty] | 2017-07-10 19:59 | Yes | 0
VD-9001-201-PCJ-018 | 0 | PRODUCTION TEST PLATES PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-02-29 | 2017-05-16 18:20 |  | No | 442 | 2017-06-14 15:18 | [7 empty] | 2017-06-14 20:00 | Yes | 0
VD-9001-201-PCJ-019 | 0 | HARDNESS TEST PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-05-16 18:20 | 2017-05-16 18:21 | Yes | 427 |  | 2017-06-14 15:10 | [6 empty] | 2017-06-14 20:00 | Yes | 15 | 1204-Owner-v | 2019-01-13 15:02
VD-9001-201-PCJ-020 | 0 | PMI PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2016-03-15 | 2017-05-16 18:20 | 2017-05-16 18:21 | Yes | 427 |  | 2017-05-24 11:36 | [6 empty] | 2017-05-24 20:00 | Yes | -6 | 1204-Owner-v | 2019-01-13 15:02
VD-9001-201-PCJ-022 | 0 | SPARE PART LIST | PV-201 | ATB RIVA CALZONI SpA | 2016-07-19 |  |  | No | 1431 | [9 empty] | No | 0
VD-9001-213A-DWG-128 | 6 | Fixed Roof Orientation for Tk-7201 | PV-213A | MachineSazi Pars | 2016-03-09 | 2016-03-14 18:02 | 2016-03-14 18:04 | Yes | 5 |  | 2016-03-15 18:54 | [6 empty] | 2016-03-15 20:00 | Yes | -13
VD-9001-108-DWG-025 | 3 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2016-03-09 16:32 | 2016-03-10 10:34 |  | No | 1 |  | 2016-03-16 11:57 | [6 empty] | 2016-03-16 20:00 | Yes | 0
VD-9001-206B-DWG-014 | 1 | INTERNAL ATTACHMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-03-23 20:00 | 2016-03-28 14:07 |  | No | 5 |  | 2016-07-09 12:03 | [6 empty] | 2016-07-09 19:58 | Yes | 0
VD-9001-206B-DWG-013 | 1 | MANHOLE & NOZZLE DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2016-03-23 20:00 | 2016-03-16 18:07 |  | No | -7 | 2016-05-31 09:22 | [7 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-213A-LST-039 | 1 | SPLIR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2016-03-10 | 2016-04-13 08:58 |  | No | 34 | 2016-04-14 15:31 | [7 empty] | 2016-04-14 19:59 | Yes | 0
VD-9001-213A-DWG-131 | 5 | Walkway With Handrail for Tk-7201 | PV-213A | MachineSazi Pars | 2016-03-10 | 2016-03-14 18:06 | 2016-03-14 18:07 | Yes | 4 |  | 2016-03-15 18:56 | [6 empty] | 2016-03-15 20:00 | Yes | -13
VD-9001-105-CAL-502 | 1 | Calculation sheet for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-04-22 17:53 |  | No | 43 |  | 2016-05-08 16:46 | [6 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-105-CAL-503 | 1 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-04-22 17:54 |  | No | 43 | 2016-05-08 16:48 | [7 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-105-CAL-501 | 1 | Calculation sheet of Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-04-22 17:50 |  | No | 43 | 2016-05-08 16:45 | [7 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-105-DIG-205 | 3 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-03-14 18:50 |  | No | 4 |  | 2016-04-17 08:38 | [6 empty] | 2016-04-17 19:59 | Yes | 0
VD-9001-105-DSH-102 | 1 | Data sheet of heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-04-24 13:41 |  | No | 45 | 2016-05-09 18:04 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-105-DSH-101 | 1 | Data sheet of gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-10 | 2016-04-24 13:41 |  | No | 45 | 2016-05-09 18:09 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-105-DPH-102 | 2 | Process control requirement | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-12 | 2016-05-31 18:08 | 2016-05-31 18:09 | Yes | 80 |  | 2016-06-09 11:46 | [6 empty] | 2016-06-09 19:58 | Yes | -5 | 1204-Owner-v | 2019-09-06 22:03
VD-9001-206B-DWG-049 | 1 | NAME PLATE DRAWING -T-2001 | PV-206B | TASHA | 2016-03-26 20:00 | 2016-05-07 10:08 |  | No | 42 |  | 2016-07-10 14:22 | [6 empty] | 2016-07-10 19:58 | Yes | 0
VD-9001-206B-DWG-079 | 1 | NAME PLATE DRAWING -T-4001 | PV-206B | TASHA | 2016-03-26 20:00 | 2016-05-07 10:07 |  | No | 42 |  | 2016-07-10 14:20 | [6 empty] | 2016-07-10 19:58 | Yes | 0
VD-9001-254-PCU-601 | 2 | BOILER EXPECTED PERFORMANCE CURVES | HM-254 | AZAR AB | 2016-03-26 20:00 | 2016-03-26 13:40 |  | No | 0 |  | 2016-04-24 10:52 | [6 empty] | 2016-04-24 19:59 | Yes | 0
VD-9001-254-SPE-109 | 4 | TERMINAL POINT SPECIFICATION | HM-254 | AZAR AB | 2016-03-26 20:00 |  |  | No | 1546 | [9 empty] | No | 0
VD-9001-254-DBS-600 | 4 | BOILER DESIGN BASE DATA SHEET | HM-254 | AZAR AB | 2016-03-26 20:00 |  |  | No | 1546 | [9 empty] | No | 0
VD-9001-105-DSH-103 | 1 | Data sheet of CMR membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-03-13 | 2016-04-24 13:42 | 2016-04-24 13:43 | Yes | 42 |  | 2016-05-09 18:11 | [6 empty] | 2016-05-09 19:59 | Yes | 1 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-108-DWG-029 | 5 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2016-03-28 20:00 | 2017-10-30 14:30 |  | No | 581 | 2017-11-11 12:20 | [7 empty] | 2017-11-11 19:59 | Yes | 0
VD-9001-206B-DWG-043 | 2 | MANHOLE & NOZZLE DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2016-03-28 20:00 | 2016-04-03 08:07 | 2016-04-03 08:08 | Yes | 6 |  | 2016-04-13 09:16 | [6 empty] | 2016-04-13 19:59 | Yes | -4
VD-9001-206B-DWG-078 | 1 | PIPE CLIP DRAWING -T-4001 | PV-206B | TASHA | 2016-03-28 20:00 | 2016-04-03 08:09 |  | No | 6 | 2016-04-20 16:17 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-108-MNL-056 | 3 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2016-03-29 20:00 | 2017-10-30 13:04 |  | No | 580 | 2017-11-08 12:01 | [7 empty] | 2017-11-08 19:59 | Yes | 0
VD-9001-108-DWG-045 | 1 | PLATFORM & LADDER DETAIL DRAWING | PR-108 | Farabard | 2016-03-29 20:00 | 2017-03-18 10:57 |  | No | 354 | 2017-04-03 15:58 | [7 empty] | 2017-04-03 21:00 | Yes | 0
VD-9001-253(A)-DWG-005 | 3 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-03-16 | 2016-04-25 17:46 |  | No | 40 | 2016-05-07 11:34 | [7 empty] | 2016-05-07 19:59 | Yes | 0
VD-9001-206B-DWG-048 | 1 | PIPE CLIP DRAWING -T-2001 | PV-206B | TASHA | 2016-03-30 20:00 | 2016-04-07 07:55 | 2016-04-07 07:56 | Yes | 8 |  | 2016-04-12 09:33 | [6 empty] | 2016-04-12 19:59 | Yes | -9 | 1204-Owner-v | 2020-05-11 14:40
VD-9001-254-DWH-548 | 3 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2016-04-13 20:00 | 2017-12-05 16:29 | 2017-12-05 16:30 | Yes | 601 |  | 2017-12-11 15:22 | [6 empty] | 2017-12-11 20:00 | Yes | -8
VD-9001-206B-PCJ-032 | 0 | PNEUMATIC TEST PROCEDURE | PV-206B | TASHA | 2016-04-02 | 2016-04-02 12:00 |  | No | 0 | 2016-04-20 16:35 | [7 empty] | 2016-04-20 19:59 | Yes | 0
VD-9001-202F-DSH-001 | 1 | Technical Specifications | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-16 20:00 |  |  | No | 1525 | [9 empty] | No | 0
VD-9001-257A-WMP-008 | 1 | Welding & NDT Map | HM-257A | ABAN AIR COOLER. | 2016-04-17 | 2016-04-18 19:02 | 2016-04-18 19:03 | Yes | 1 |  | 2016-04-26 11:42 | [6 empty] | 2016-04-26 19:59 | Yes | -6
VD-9001-257A-WMP-009 | 1 | WELDING & NDT MAP E-1001 | HM-257A | ABAN AIR COOLER. | 2016-04-17 | 2016-04-18 19:02 | 2016-04-18 19:03 | Yes | 1 |  | 2016-04-26 11:42 | [6 empty] | 2016-04-26 19:59 | Yes | -6
VD-9001-257A-WMP-010 | 1 | WELDING & NDT MAP E-9001 | HM-257A | ABAN AIR COOLER. | 2016-04-17 | 2016-04-18 19:02 | 2016-04-18 19:03 | Yes | 1 |  | 2016-04-26 11:42 | [6 empty] | 2016-04-26 19:59 | Yes | -6
VD-9001-257A-DWG-009 | 2 | GENERAL ARRANGEMENT DRAWING E-1001 | HM-257A | ABAN AIR COOLER. | 2016-04-17 | 2016-04-13 11:20 |  | No | -4 | 2016-05-04 11:49 | [7 empty] | 2016-05-04 19:59 | Yes | 0
VD-9001-204A-DWG-051 | 4 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-04-17 20:00 | 2016-04-05 15:50 |  | No | -12 |  | 2016-04-26 08:49 | [6 empty] | 2016-04-26 19:59 | Yes | 0
VD-9001-254-DWG-211 | 1 | CABLE TRAY LAYOUT | HM-254 | AZAR AB | 2016-04-17 20:00 | 2020-05-19 09:00 | 2020-05-19 09:00 | Yes | 1493 | [9 empty] | No | 17
VD-9001-213A-CAL-024 | 1 | Roof Structure Lifting Calculation for Erection. for Tk-7201 | PV-213A | MachineSazi Pars | 2016-04-04 09:54 | 2016-04-04 10:40 | 2016-04-04 10:36 | Yes | 0 |  | 2016-04-05 10:57 | [6 empty] | 2016-04-05 20:00 | Yes | -13
VD-9001-213A-DWG-124 | 4 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2016-04-04 09:54 | 2016-04-04 10:05 |  | No | 0 |  | 2016-04-05 11:15 | [6 empty] | 2016-04-05 20:00 | Yes | 0
VD-9001-213A-PCJ-028 | 1 | Roof structure Erection Procedure for Tk-7201 | PV-213A | MachineSazi Pars | 2016-04-04 14:14 | 2016-04-04 14:31 | 2016-04-04 14:32 | Yes | 0 |  | 2016-04-05 11:04 | [6 empty] | 2016-04-05 20:00 | Yes | -13
VD-9001-205A-DWG-052 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-04-04 16:43 | 2016-04-05 11:22 | 2016-04-05 11:23 | Yes | 1 |  | 2016-04-13 09:58 | [6 empty] | 2016-04-13 19:59 | Yes | -6
VD-9001-204A-PCJ-010 | 1 | Painting Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-04-18 20:00 | 2016-05-02 12:36 |  | No | 14 | 2016-05-16 09:46 | [7 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-108-DWG-017 | 1 | EXCAVATION DETAIL | PR-108 | Farabard | 2016-04-06 14:01 | 2016-04-07 09:09 |  | No | 1 |  | 2016-04-10 08:51 | [6 empty] | 2016-04-10 19:59 | Yes | 0
VD-9001-108-DWG-020 | 4 | COLUMNS DEATAIL | PR-108 | Farabard | 2016-04-06 14:01 | 2016-07-21 14:55 |  | No | 106 | 2016-07-23 15:50 | [7 empty] | 2016-07-23 19:58 | Yes | 0
VD-9001-108-DWG-021 | 4 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-07-28 14:20 |  | No | 113 | 2016-08-02 11:36 | [7 empty] | 2016-08-02 19:57 | Yes | 0
VD-9001-108-DWG-019 | 5 | FOUNDATION DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-07-20 15:55 | 2016-07-20 15:56 | Yes | 105 |  | 2016-07-31 11:18 | [6 empty] | 2016-07-31 19:57 | Yes | -3
VD-9001-108-DWG-022 | 5 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-11-26 14:58 | 2016-11-26 14:59 | Yes | 234 |  | 2016-11-27 12:01 | [6 empty] | 2016-11-27 20:00 | Yes | -13
VD-9001-108-DWG-023 | 4 | SECONDERY BEAMS DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-12-18 14:56 | 2016-12-18 14:57 | Yes | 256 |  | 2016-12-21 15:56 | [6 empty] | 2016-12-21 19:59 | Yes | -11
VD-9001-108-DWG-024 | 3 | WATER DISTRIBUTION CHANNEL DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-08-10 15:14 | 2016-08-10 15:15 | Yes | 126 |  | 2016-08-24 09:31 | [6 empty] | 2016-08-24 19:57 | Yes | 0
VD-9001-108-DWG-025 | 4 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2016-08-15 14:51 | 2016-08-15 14:52 | Yes | 131 |  | 2016-08-24 09:34 | [6 empty] | 2016-08-24 19:57 | Yes | -5
VD-9001-108-DWG-026 | 2 | HAND RAIL DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2017-03-18 10:56 | 2017-03-18 10:57 | Yes | 346 |  | 2017-04-03 15:37 | [6 empty] | 2017-04-03 21:00 | Yes | 2
VD-9001-108-DWG-027 | 2 | LADDER DETAIL | PR-108 | Farabard | 2016-04-06 14:02 | 2017-03-18 10:57 |  | No | 346 | 2017-04-03 15:32 | [7 empty] | 2017-04-03 21:00 | Yes | 0
VD-9001-108-DWG-028 | 4 | STAIR CASE DETAIL | PR-108 | Farabard | 2016-04-06 14:03 | 2016-11-22 09:56 | 2016-11-22 09:56 | Yes | 230 |  | 2016-11-26 09:55 | [6 empty] | 2016-11-26 20:00 | Yes | -10
VD-9001-213B-DWG-018 | 3 | General Assembly for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-04-06 16:03 | 2016-04-11 14:42 | 2016-04-11 14:43 | Yes | 5 |  | 2016-04-13 16:37 | [6 empty] | 2016-04-13 19:59 | Yes | -12
VD-9001-213B-DWG-019 | 5 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-04-06 16:03 | 2016-04-06 17:51 |  | No | 0 |  | 2016-04-11 09:02 | [6 empty] | 2016-04-11 19:59 | Yes | 0
VD-9001-213B-DWG-027 | 3 | Shell Nozzles for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-04-06 16:04 | 2016-04-06 17:51 | 2016-04-06 17:52 | Yes | 0 |  | 2016-04-10 09:41 | [6 empty] | 2016-04-10 19:59 | Yes | -10
VD-9001-105-DWG-502 | 1 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-04-22 17:14 |  | No | 13 | 2016-05-09 18:00 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-105-DWG-503 | 1 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-04-22 17:16 |  | No | 13 | 2016-05-09 18:02 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-105-DIG-201 | 2 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-06-03 10:12 |  | No | 55 | 2016-06-09 08:56 | [7 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-105-DIG-204 | 1 | Outline diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-06-02 17:11 |  | No | 54 |  | 2016-06-09 08:43 | [6 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-105-LST-201 | 1 | Cable schedule with cable list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-06-02 17:16 |  | No | 54 | 2016-06-09 12:17 | [7 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-105-DIG-206 | 2 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-05-25 18:45 |  | No | 46 | 2016-06-02 08:37 | [7 empty] | 2016-06-02 19:58 | Yes | 0
VD-9001-105-DWG-501 | 1 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-09 | 2016-04-22 17:11 |  | No | 13 | 2016-05-09 17:59 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-254-DSH-225 | 0 | DATA SHEET FOR CABLES AND WIRES | HM-254 | AZAR AB | 2016-04-09 | 2016-04-09 17:43 |  | No | 0 | 2016-05-09 11:11 | [7 empty] | 2016-05-09 19:59 | Yes | 0 | 1204-Owner-v | 2018-04-08 16:57
VD-9001-202F-PPL-005 | 1 | Waste Heat Boiler - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-23 19:59 | 2018-04-11 18:03 | 2018-04-11 18:03 | Yes | 718 |  |  |  |  | 2018-05-09 16:51 |  |  |  | 2018-05-09 16:51 | Yes | 14 | 1204-Owner-v | 2018-05-26 16:27
VD-9001-202F-BOQ-004 | 1 | Waste Heat Boiler - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-23 19:59 | 2018-04-10 21:17 | 2018-04-10 21:19 | Yes | 717 |  |  | 2018-04-25 15:26 | [5 empty] | 2018-04-25 15:26 | Yes | 1 | 1204-Owner-v | 2020-03-11 13:57
VD-9001-202F-DWG-009 | 1 | Waste Heat Boiler - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-23 19:59 | 2018-04-11 17:55 | 2018-04-11 18:02 | Yes | 718 |  |  | 2018-05-30 16:30 | [5 empty] | 2018-05-30 16:30 | Yes | 35
VD-9001-202F-DWG-010 | 1 | Waste Heat Boiler - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2016-04-23 19:59 | 2018-04-11 17:55 | 2018-04-11 17:55 | Yes | 718 |  |  |  |  | 2018-06-02 10:45 |  |  |  | 2018-06-02 10:45 | Yes | 38 | 1204-Owner-v | 2018-05-15 16:44
VD-9001-206B-DWG-045 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-2001 | PV-206B | TASHA | 2016-04-23 20:00 | 2016-05-07 10:09 |  | No | 14 |  | 2016-05-31 11:27 | [6 empty] | 2016-05-31 19:58 | Yes | 0 | 1204-Owner-v | 2018-12-21 11:31
VD-9001-213A-DWG-124 | 5 | General Assembly for Tk-7201 | PV-213A | MachineSazi Pars | 2016-04-11 09:47 | 2016-04-11 11:21 | 2016-04-11 11:22 | Yes | 0 |  | 2016-04-14 14:44 | [6 empty] | 2016-04-14 19:59 | Yes | -11 | 1204-Owner-v | 2019-01-15 16:27
VD-9001-204A-DWG-057 | 1 | Internal Attachment Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-04-25 19:59 | 2016-05-29 17:53 | 2016-05-29 17:53 | Yes | 34 |  | 2016-06-06 11:44 | [6 empty] | 2016-06-06 19:58 | Yes | -6
VD-9001-204A-DWG-176 | 1 | External Attachment Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-04-25 19:59 | 2016-04-12 14:33 |  | No | -13 | 2016-05-08 16:34 | [7 empty] | 2016-05-08 19:59 | Yes | 0
VD-9001-204A-DWG-106 | 1 | External Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-04-25 19:59 | 2016-07-04 15:47 |  | No | 70 | 2016-07-12 15:49 | [7 empty] | 2016-07-12 19:58 | Yes | 0
VD-9001-206B-DWG-012 | 2 | BODY & SUPPORT DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2016-04-25 19:59 | 2016-07-16 10:52 | 2016-07-16 10:41 | Yes | 82 |  | 2016-08-21 09:21 | [6 empty] | 2016-08-21 19:57 | Yes | 22 | 1204-Owner-v | 2018-04-27 14:18
VD-9001-203-HMB-006 | 1 | Deaerator Heat and Mass Balances | PV-203 | Masnout Felezi Sangin (MFS) | 2016-04-26 19:59 | 2016-05-25 10:29 |  | No | 29 | 2016-06-05 12:05 | 2017-09-04 09:11 | [6 empty] | 2017-09-04 19:57 | Yes | 0
VD-9001-206B-DWG-017 | 1 | TOP DAVIT DRAWING -T-1001 | PV-206B | TASHA | 2016-04-26 19:59 | 2016-05-07 10:10 |  | No | 11 |  | 2016-07-09 11:56 | [6 empty] | 2016-07-09 19:58 | Yes | 0
VD-9001-206B-DWG-075 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-4001 | PV-206B | TASHA | 2016-04-27 19:59 | 2016-05-31 12:10 |  | No | 34 | 2016-07-16 18:04 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-213A-LST-039 | 2 | SPLIR for Tk-2201 & Tk-6401Tk-7101A/B & Tk-7201 | PV-213A | MachineSazi Pars | 2016-04-14 | 2016-04-16 08:19 | 2016-04-16 08:20 | Yes | 2 |  | 2016-04-16 09:37 | [6 empty] | 2016-04-16 19:59 | Yes | -14 | 1204-Owner-v | 2020-05-21 07:16
VD-9001-105-PID-101 | 3 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-16 | 2016-04-27 19:25 |  | No | 11 | 2016-05-28 09:42 | [7 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-257A-CAL-010 | 3 | STRENGTH CALCULATION BOOK E-1009 | HM-257A | ABAN AIR COOLER. | 2016-05-01 | 2016-04-17 11:51 | 2016-04-17 11:35 | Yes | -14 |  | 2016-04-17 17:28 | [6 empty] | 2016-04-17 19:59 | Yes | -14
VD-9001-257A-DWG-010 | 2 | GENERAL ARRANGEMENT DRAWING E-1009 | HM-257A | ABAN AIR COOLER. | 2016-05-01 | 2016-04-17 11:58 | 2016-04-17 11:57 | Yes | -14 |  | 2016-04-17 17:28 | [6 empty] | 2016-04-17 19:59 | Yes | -14
VD-9001-108-DSH-015 | 2 | VIBRATION SWITCH DATA SHEET | PR-108 | Farabard | 2016-04-19 15:06 | 2016-08-13 11:49 |  | No | 116 | 2016-08-22 10:22 | [7 empty] | 2016-08-22 19:57 | Yes | 0
VD-9001-203-DSH-005 | 1 | Technical Data Sheet (Process&Mechanic) | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-03 19:59 | 2016-04-27 12:38 |  | No | -6 | 2016-05-31 16:26 | [7 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-203-DWG-020 | 1 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-03 19:59 | 2016-05-01 16:25 |  | No | -2 | 2016-05-31 16:27 | [7 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-203-ITP-003 | 1 | Inspection Test Plan | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-03 19:59 | 2016-06-22 15:30 |  | No | 50 | 2016-08-21 08:39 | [7 empty] | 2016-08-21 19:57 | Yes | 0
VD-9001-204A-DWG-086 | 1 | External Attachment Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-05-04 19:59 | 2016-05-17 16:10 |  | No | 13 |  | 2016-05-30 16:31 | [6 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-076 | 1 | External Attachment Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-04 19:59 | 2016-05-17 16:10 |  | No | 13 | 2016-05-30 09:49 | [7 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-066 | 1 | External Attachment Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-04 19:59 | 2016-05-17 16:09 |  | No | 13 |  | 2016-05-23 09:35 | [6 empty] | 2016-05-23 19:58 | Yes | 0
VD-9001-204A-DWG-046 | 1 | External Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-04 19:59 | 2016-05-17 16:16 |  | No | 13 | 2016-05-30 10:10 | [7 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-206B-DWG-078 | 2 | PIPE CLIP DRAWING -T-4001 | PV-206B | TASHA | 2016-05-04 19:59 | 2016-08-13 18:55 | 2016-08-13 18:56 | Yes | 101 |  | 2016-08-28 12:02 | [6 empty] | 2016-08-28 19:56 | Yes | 1 | 1204-Owner-v | 2020-05-11 14:40
VD-9001-206B-PCJ-032 | 1 | PNEUMATIC TEST PROCEDURE | PV-206B | TASHA | 2016-05-04 19:59 | 2016-05-07 08:53 | 2016-05-07 08:54 | Yes | 3 |  | 2016-06-06 11:16 | [6 empty] | 2016-06-06 19:58 | Yes | 16
VD-9001-253(A)-DWG-011 | 1 | HEADER WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-04-24 | 2016-06-05 10:44 |  | No | 42 | 2016-06-20 14:37 | [7 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-108-DWG-017 | 2 | EXCAVATION DETAIL | PR-108 | Farabard | 2016-04-24 11:40 | 2016-04-24 12:22 |  | No | 0 |  | 2016-05-07 12:14 | [6 empty] | 2016-05-07 19:59 | Yes | 0
VD-9001-253(A)-DWG-018 | 1 | MOTOR WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-04-24 | 2016-05-30 11:26 |  | No | 36 | 2016-06-20 15:27 | [7 empty] | 2016-06-20 19:57 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:40
VD-9001-213B-DWG-037 | 3 | Gauge Hatch for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-04-27 10:36 | 2016-04-27 11:20 | 2016-04-27 11:21 | Yes | 0 |  | 2016-04-30 10:50 | [6 empty] | 2016-04-30 19:59 | Yes | -11
VD-9001-253(A)-PCJ-104 | 4 | PAINTING PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-04-27 15:37 | 2016-04-30 11:32 | 2016-04-30 11:19 | Yes | 3 |  | 2016-05-03 14:23 | [6 empty] | 2016-05-03 19:59 | Yes | -11
VD-9001-105-DPH-101 | 2 | Process control philosophy | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:40 | 2016-05-31 18:08 | 2016-05-31 18:09 | Yes | 34 |  | 2016-06-09 11:41 | [6 empty] | 2016-06-09 19:58 | Yes | -5 | 1204-Owner-v | 2019-09-06 22:03
VD-9001-105-DSH-205 | 3 | Data sheet of automatic valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:41 | 2016-05-05 10:42 |  | No | 8 |  | 2016-05-28 09:52 | [6 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-105-DSH-208 | 1 | Data sheet of level switch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:41 | 2016-05-29 14:29 | 2016-05-29 14:30 | Yes | 32 |  | 2016-06-02 08:58 | [6 empty] | 2016-06-02 19:58 | Yes | -10 | 1204-Owner-v | 2019-01-04 21:40
VD-9001-105-LST-102 | 2 | Line list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:41 | 2016-04-29 07:10 | 2016-04-29 07:11 | Yes | 2 |  | 2016-05-09 18:15 | [6 empty] | 2016-05-09 19:59 | Yes | -4 | 1204-Owner-v | 2019-01-07 08:26
VD-9001-105-LST-203 | 2 | FCS I/O List | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:41 | 2016-04-27 19:10 |  | No | 0 | 2016-05-07 16:32 | [7 empty] | 2016-05-07 19:59 | Yes | 0
VD-9001-105-LST-204 | 2 | Set point list of HRU for FCS’s alarm and interlock | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-04-27 17:42 | 2016-04-27 19:13 |  | No | 0 | 2016-05-09 18:12 | [7 empty] | 2016-05-09 19:59 | Yes | 0
VD-9001-108-CAL-001 | 1 | STRUCTURE CALCULATION SHEET | PR-108 | Farabard | 2016-05-11 19:59 | 2016-05-01 13:13 |  | No | -10 |  | 2016-05-01 17:56 | [6 empty] | 2016-05-01 19:59 | Yes | 0
VD-9001-204A-DWG-052 | 1 | Nozzle Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-14 19:59 | 2016-05-31 13:49 |  | No | 17 |  | 2016-06-06 11:14 | [6 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-204A-DWG-062 | 1 | Nozzle Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-14 19:59 | 2017-03-07 13:48 |  | No | 297 |  | 2017-03-11 16:49 | [6 empty] | 2017-03-11 20:00 | Yes | 0
VD-9001-204A-WBK-001 | 2 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2016-05-14 19:59 | 2016-05-11 17:32 |  | No | -3 | 2016-05-25 10:35 | [7 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-073 | 1 | Name Plate Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 | 2016-05-09 14:15 |  | No | -6 |  | 2016-05-25 10:15 | [6 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-072 | 1 | Nozzle Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 | 2016-05-29 17:54 |  | No | 14 |  | 2016-05-31 12:01 | [6 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-204A-DWG-016 | 1 | External Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 | 2016-05-24 10:15 |  | No | 9 |  | 2016-05-30 16:36 | [6 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-082 | 1 | Nozzle Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 | 2017-06-20 10:37 |  | No | 401 | 2017-09-26 09:39 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-103 | 1 | Name Plate Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 | 2016-05-09 14:20 |  | No | -6 |  | 2016-05-28 15:12 | [6 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-204A-DWG-102 | 1 | Nozzle Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 19:59 |  |  | No | 1496 | [9 empty] | No | 0
VD-9001-204A-DWG-092 | 1 | Nozzle Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-31 12:53 |  | No | 15 |  | 2016-05-31 17:03 | [6 empty] | 2016-05-31 19:58 | Yes | 0
VD-9001-204A-DWG-172 | 1 | Nozzle Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-29 17:55 |  | No | 13 |  | 2016-06-06 11:53 | [6 empty] | 2016-06-06 19:58 | Yes | 0
VD-9001-204A-DWG-173 | 1 | Name Plate Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-09 14:30 |  | No | -7 | 2016-05-29 15:13 | [7 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-204A-DWG-012 | 1 | Nozzle Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-29 17:51 |  | No | 13 | 2016-06-05 16:55 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-204A-DWG-013 | 1 | Name Plate Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-09 14:03 |  | No | -7 |  | 2016-05-23 11:43 | [6 empty] | 2016-05-23 19:58 | Yes | 0
VD-9001-204A-DWG-113 | 1 | Name Plate Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-05-09 14:22 |  | No | -7 |  | 2016-05-28 16:38 | [6 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-204A-DWG-112 | 1 | Nozzle Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-16 19:59 | 2016-06-19 08:08 |  | No | 34 | 2016-06-26 16:54 | [7 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-213B-DWG-026 | 2 | Wind Girder for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-05-03 11:11 | 2016-05-03 11:46 | 2016-05-03 11:47 | Yes | 0 |  | 2016-05-07 12:10 | [6 empty] | 2016-05-07 19:59 | Yes | -10
VD-9001-204A-DWG-043 | 1 | Name Plate Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:11 |  | No | -8 |  | 2016-05-25 10:03 | [6 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-042 | 1 | Nozzle Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-06-23 13:22 |  | No | 37 | 2016-07-04 16:27 | [7 empty] | 2016-07-04 19:58 | Yes | 0
VD-9001-204A-DWG-122 | 1 | Nozzle Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-06-19 07:48 |  | No | 33 |  | 2016-06-22 16:42 | [6 empty] | 2016-06-22 19:57 | Yes | 0
VD-9001-204A-DWG-123 | 1 | Name Plate Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:24 |  | No | -8 | 2016-05-25 15:10 | [7 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-063 | 1 | Name Plate Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:13 |  | No | -8 |  | 2016-05-25 10:08 | [6 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-083 | 1 | Name Plate Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:17 |  | No | -8 |  | 2016-05-28 14:35 | [6 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-204A-DWG-093 | 1 | Name Plate Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:18 |  | No | -8 |  | 2016-05-28 14:42 | [6 empty] | 2016-05-28 19:58 | Yes | 0
VD-9001-204A-DWG-096 | 1 | External Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-07-04 16:11 |  | No | 48 | 2016-07-16 15:30 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-204A-DWG-023 | 1 | Name Plate Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:08 |  | No | -8 |  | 2016-05-24 10:32 | [6 empty] | 2016-05-24 19:58 | Yes | 0
VD-9001-204A-DWG-133 | 1 | Name Plate Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-05-17 19:59 | 2016-05-09 14:25 |  | No | -8 | 2016-05-29 11:37 | [7 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-257A-DWG-009 | 3 | GENERAL ARRANGEMENT DRAWING E-1001 | HM-257A | ABAN AIR COOLER. | 2016-05-11 | 2016-05-04 15:33 |  | No | -7 | 2016-06-05 14:44 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-257A-DWG-008 | 4 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2016-05-04 11:50 | 2016-05-04 12:14 |  | No | 0 | 2016-05-30 12:02 | [7 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204B-CAL-002 | 1 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-11 | 2016-06-22 18:01 |  | No | 42 | 2016-07-09 14:56 | [7 empty] | 2016-07-09 19:58 | Yes | 0
VD-9001-204B-DWG-002 | 1 | General Arrangment Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-11 | 2016-06-22 18:10 |  | No | 42 | 2016-07-18 16:04 | [7 empty] | 2016-07-18 19:58 | Yes | 0
VD-9001-204B-DWG-010 | 1 | Body Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-05-11 | 2016-07-02 12:36 |  | No | 52 | 2016-07-24 17:05 | [7 empty] | 2016-07-24 19:58 | Yes | 0
VD-9001-204B-DWG-014 | 1 | Nozzle Detail Drawing D-1003 * | PV-204B | ABAN AIR COOLER. | 2016-05-11 | 2016-07-14 16:05 |  | No | 64 | 2016-08-10 15:21 | [7 empty] | 2016-08-10 19:57 | Yes | 0
VD-9001-206B-DWG-018 | 1 | PIPE CLIP DRAWING -T-1001 | PV-206B | TASHA | 2016-05-18 19:59 | 2016-05-31 12:08 |  | No | 13 | 2016-06-29 14:07 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-204A-DWG-163 | 1 | Name Plate Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-05-18 19:59 | 2016-05-09 14:29 |  | No | -9 |  | 2016-05-29 11:57 | [6 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-204A-DWG-162 | 1 | Nozzle Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-05-18 19:59 | 2016-06-16 08:53 |  | No | 29 |  | 2016-06-20 11:18 | [6 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-253(A)-DWG-005 | 4 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-05-07 | 2016-05-15 12:09 |  | No | 8 | 2016-05-29 14:41 | [7 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-105-ITP-701 | 1 | Inspection and test plan for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-09 19:52 |  | No | 2 |  | 2016-05-28 09:56 | [6 empty] | 2016-05-28 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:04
VD-9001-105-ITP-703 | 1 | Inspection and test plan for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-09 19:53 |  | No | 2 |  | 2016-05-28 09:58 | [6 empty] | 2016-05-28 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:11
VD-9001-105-ITP-705 | 1 | Inspection and test plan of piping and skid-structure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-09 19:53 |  | No | 2 |  | 2016-05-28 10:02 | [6 empty] | 2016-05-28 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:13
VD-9001-105-ITP-702 | 1 | Inspection and test plan for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-09 19:53 |  | No | 2 |  | 2016-05-28 10:00 | [6 empty] | 2016-05-28 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:04
VD-9001-105-ITP-707 | 1 | Inspection and test plan of instruments | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-30 18:42 |  | No | 23 |  | 2016-06-09 08:28 | [6 empty] | 2016-06-09 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:18
VD-9001-105-LST-203 | 3 | FCS I/O List | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-31 18:17 | 2016-05-31 18:18 | Yes | 24 |  | 2016-06-09 08:31 | [6 empty] | 2016-06-09 19:58 | Yes | -5
VD-9001-105-LST-103 | 2 | Piping valve list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-07 | 2016-05-29 19:02 | 2016-05-29 19:03 | Yes | 22 |  | 2016-06-02 09:01 | [6 empty] | 2016-06-02 19:58 | Yes | -10 | 1204-Owner-v | 2019-01-04 21:15
VD-9001-105-ITP-706 | 1 | Inspection and test plan of membrane modules | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-21 19:59 | 2016-05-23 18:12 |  | No | 2 |  | 2016-06-02 08:31 | [6 empty] | 2016-06-02 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:14
VD-9001-105-DWG-101 | 1 | Name plate drawings of HRU Package | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-08 | 2016-05-16 19:47 |  | No | 8 |  | 2016-05-18 09:15 | [6 empty] | 2016-05-18 19:58 | Yes | 0
VD-9001-105-CAL-501 | 2 | Calculation sheet of Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-08 | 2016-05-19 17:23 |  | No | 11 | 2016-06-15 10:54 | [7 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-105-CAL-503 | 2 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-08 | 2016-05-19 17:30 |  | No | 11 | 2016-06-15 10:25 | [7 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-204A-DWG-176 | 2 | External Attachment Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-22 19:59 | 2016-05-17 16:11 | 2016-05-17 16:12 | Yes | -5 |  | 2016-05-30 15:50 | [6 empty] | 2016-05-30 19:58 | Yes | -1
VD-9001-204A-DWG-026 | 1 | External Attachment Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-22 19:59 | 2016-05-24 12:05 | 2016-05-24 12:06 | Yes | 2 |  | 2016-05-31 09:57 | [6 empty] | 2016-05-31 19:58 | Yes | -7 | 1204-Owner-v | 2019-07-09 11:53
VD-9001-204A-PCJ-005 | 1 | Post Weld Heat Treatment Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-05-09 14:24 | 2016-05-10 08:13 | 2016-05-10 08:13 | Yes | 1 |  | 2016-05-11 16:35 | [6 empty] | 2016-05-11 19:59 | Yes | -13
VD-9001-105-DWG-501 | 2 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-19 17:34 |  | No | 10 | 2016-06-15 10:27 | [7 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-105-DWG-502 | 2 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-19 17:40 |  | No | 10 | 2016-06-09 08:25 | [7 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-105-DWG-503 | 2 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-19 17:43 |  | No | 10 |  | 2016-06-15 10:37 | [6 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-105-DSH-102 | 2 | Data sheet of heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-06-20 11:32 | 2016-06-20 11:33 | Yes | 42 |  | 2016-07-07 11:27 | [6 empty] | 2016-07-07 19:58 | Yes | 3 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-105-DSH-101 | 2 | Data sheet of gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-29 13:57 | 2016-05-29 13:58 | Yes | 20 |  | 2016-06-15 10:40 | [6 empty] | 2016-06-15 19:58 | Yes | 3 | 1204-Owner-v | 2019-01-07 08:23
VD-9001-105-LST-204 | 3 | Set point list of HRU for FCS’s alarm and interlock | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-31 18:18 | 2016-05-31 18:19 | Yes | 22 |  | 2016-06-09 12:03 | [6 empty] | 2016-06-09 19:58 | Yes | -5
VD-9001-105-LST-205 | 3 | Set point list of HRU for FCS’s monitor and control | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-09 | 2016-05-31 18:19 | 2016-05-31 18:20 | Yes | 22 |  | 2016-06-09 12:19 | [6 empty] | 2016-06-09 19:58 | Yes | -5
VD-9001-254-LST-216 | 5 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2016-05-23 19:59 | 2018-05-22 09:21 | 2018-05-22 09:21 | Yes | 729 |  |  |  | 2018-06-03 11:30 |  |  |  |  | 2018-06-03 11:30 | Yes | -2
VD-9001-254-DSH-225 | 1 | DATA SHEET FOR CABLES AND WIRES | HM-254 | AZAR AB | 2016-05-23 19:59 | 2018-04-23 13:00 | 2018-04-23 13:00 | Yes | 700 |  |  |  | 2018-06-11 15:01 |  |  |  |  | 2018-06-11 15:01 | Yes | 35 | 1204-Owner-v | 2018-05-28 11:57
VD-9001-204A-DWG-121 | 2 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-23 19:59 | 2016-05-14 08:27 |  | No | -9 | 2016-05-25 16:44 | [7 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-131 | 2 | General Arrangement Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-05-23 19:59 | 2016-05-28 15:48 |  | No | 5 | 2016-06-14 10:39 | [7 empty] | 2016-06-14 19:58 | Yes | 0
VD-9001-204A-CAL-120 | 2 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-23 19:59 | 2016-05-14 08:26 |  | No | -9 | 2016-05-25 16:48 | [7 empty] | 2016-05-25 19:58 | Yes | 0
VD-9001-204A-DWG-111 | 3 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-24 19:58 | 2016-05-26 12:27 |  | No | 2 |  | 2016-06-05 16:49 | [6 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-203-VLS-027 | 1 | Sub vendor List | PV-203 | Masnout Felezi Sangin (MFS) | 2016-05-24 19:58 | 2016-07-04 11:58 | 2016-07-04 11:59 | Yes | 41 |  | 2016-07-04 14:20 | [6 empty] | 2016-07-04 19:58 | Yes | -14
VD-9001-204A-DWG-061 | 4 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-24 19:59 | 2016-05-26 12:25 |  | No | 2 |  | 2016-06-01 11:56 | [6 empty] | 2016-06-01 19:58 | Yes | 0
VD-9001-108-DWG-017 | 3 | EXCAVATION DETAIL | PR-108 | Farabard | 2016-05-14 13:10 | 2016-05-15 08:40 | 2016-05-15 08:41 | Yes | 1 |  | 2016-05-16 10:37 | [6 empty] | 2016-05-16 19:58 | Yes | -13
VD-9001-204A-DWG-033 | 2 | Name Plate Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 09:18 | 2016-05-15 13:40 |  | No | 0 |  | 2016-05-16 15:53 | [6 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-053 | 1 | Name Plate Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 09:19 | 2016-05-15 13:41 |  | No | 0 |  | 2016-05-29 15:19 | [6 empty] | 2016-05-29 19:58 | Yes | 0
VD-9001-204A-DWG-143 | 2 | Name Plate Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 09:19 | 2016-05-15 13:42 |  | No | 0 |  | 2016-05-16 15:57 | [6 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-204A-DWG-153 | 2 | Name Plate Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-05-15 09:19 | 2016-05-15 13:46 |  | No | 0 |  | 2016-05-16 16:00 | [6 empty] | 2016-05-16 19:58 | Yes | 0
VD-9001-253(A)-DSH-046 | 4 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2016-05-15 | 2016-07-23 16:27 |  | No | 69 | 2016-08-06 08:25 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-253(A)-DSH-076 | 4 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-05-15 | 2016-07-23 16:28 |  | No | 69 | 2016-08-06 08:30 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-253(A)-DSH-016 | 4 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-05-15 | 2016-07-23 16:27 |  | No | 69 | 2016-08-06 17:01 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-204A-PCJ-010 | 2 | Painting Procedure | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-21 13:43 | 2016-05-21 13:44 | Yes | -9 |  | 2016-05-24 16:29 | [6 empty] | 2016-05-24 19:58 | Yes | -11
VD-9001-204A-CAL-020 | 3 | Strength Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-08-07 08:39 |  | No | 69 | [8 empty] | 2016-09-25 18:56 | No | 0
VD-9001-204A-DWG-021 | 3 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-08-07 08:40 |  | No | 69 |  | 2016-09-04 16:44 | [6 empty] | 2016-09-04 19:56 | Yes | 0
VD-9001-204A-DWG-018 | 1 | Template & Gauge Plate FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-19 09:54 |  | No | -11 |  | 2016-05-30 11:40 | [6 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-108 | 1 | Template & Gauge Plate FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-19 11:23 | 2016-05-19 11:24 | Yes | -11 |  | 2016-05-30 11:23 | [6 empty] | 2016-05-30 19:58 | Yes | -3 | 1204-Owner-v | 2019-05-09 08:19
VD-9001-204A-DWG-118 | 1 | Template & Gauge Plate FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-19 12:28 |  | No | -11 |  | 2016-05-30 11:27 | [6 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-128 | 1 | Template & Gauge Plate FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-21 08:26 |  | No | -9 |  | 2016-05-30 11:32 | [6 empty] | 2016-05-30 19:58 | Yes | 0
VD-9001-204A-DWG-138 | 1 | Template & Gauge Plate FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-05-21 08:27 | 2016-05-21 08:28 | Yes | -9 |  | 2016-05-30 15:52 | [6 empty] | 2016-05-30 19:58 | Yes | -5 | 1204-Owner-v | 2019-05-09 08:20
VD-9001-204A-DWG-075 | 1 | PF & LD Arrangement FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-06-20 12:37 |  | No | 21 | 2016-07-10 10:18 | [7 empty] | 2016-07-10 19:58 | Yes | 0
VD-9001-204A-DWG-074 | 1 | PF & LD Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-06-27 11:53 |  | No | 28 | 2016-07-26 14:24 | [7 empty] | 2016-07-26 19:57 | Yes | 0
VD-9001-204A-DWG-065 | 1 | PF & LD Arrangement FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-06-19 14:50 |  | No | 20 |  | 2016-06-28 14:56 | [6 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-204A-DWG-064 | 1 | PF & LD Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-05-30 19:58 | 2016-08-13 08:05 |  | No | 75 | 2016-10-02 16:17 | [7 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-204A-DWG-132 | 1 | Nozzle Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-05-31 19:58 | 2016-07-12 14:25 |  | No | 42 |  | 2016-07-25 16:36 | [6 empty] | 2016-07-25 19:57 | Yes | 0
VD-9001-204A-DWG-171 | 3 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-31 19:58 | 2016-05-26 12:28 |  | No | -5 |  | 2016-06-14 10:47 | [6 empty] | 2016-06-14 19:58 | Yes | 0
VD-9001-204A-DWG-022 | 1 | Nozzle Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-05-31 19:58 | 2016-08-07 13:03 |  | No | 68 | 2016-08-27 11:32 | [7 empty] | 2016-08-27 19:56 | Yes | 0
VD-9001-204A-DWG-175 | 1 | PF & LD Arrangement FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-31 19:58 | 2016-06-22 08:53 | 2016-06-22 08:54 | Yes | 22 |  | 2016-06-25 16:32 | [6 empty] | 2016-06-25 19:58 | Yes | -11 | 1204-Owner-v | 2018-12-29 10:23
VD-9001-204A-DWG-174 | 1 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-05-31 19:58 | 2016-06-22 10:55 |  | No | 22 | 2016-07-24 17:52 | [7 empty] | 2016-07-24 19:58 | Yes | 0
VD-9001-204B-CAL-001 | 1 | Strength Calculation Book D-1002 | PV-204B | ABAN AIR COOLER. | 2016-06-04 19:58 | 2016-06-25 12:30 |  | No | 21 | 2016-07-13 14:56 | [7 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-204B-DWG-001 | 1 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-06-04 19:58 | 2016-06-26 12:07 |  | No | 22 | 2016-08-01 15:45 | [7 empty] | 2016-08-01 19:57 | Yes | 0
VD-9001-204B-DWG-009 | 1 | Body Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-06-04 19:58 | 2016-07-04 15:04 |  | No | 30 |  | 2016-07-24 17:26 | [6 empty] | 2016-07-24 19:58 | Yes | 0
VD-9001-204B-DWG-013 | 1 | Nozzle Detail Drawing D-1002 * | PV-204B | ABAN AIR COOLER. | 2016-06-04 19:58 | 2016-08-09 13:52 |  | No | 66 | 2016-08-23 16:05 | [7 empty] | 2016-08-23 19:57 | Yes | 0
VD-9001-204B-DWG-029 | 1 | Template Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-06-04 19:58 | 2016-10-24 10:58 |  | No | 142 |  | 2016-10-24 11:51 | [6 empty] | 2016-10-24 20:00 | Yes | 0
VD-9001-204A-WBK-001 | 3 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2016-06-08 19:58 | 2016-06-20 09:53 |  | No | 12 | 2016-06-29 11:49 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-204A-DWG-123 | 2 | Name Plate Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-06-08 19:58 | 2016-08-21 12:32 |  | No | 74 |  | 2016-09-04 16:52 | [6 empty] | 2016-09-04 19:57 | Yes | 0
VD-9001-204A-DWG-121 | 3 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-06-08 19:58 | 2016-06-18 10:24 |  | No | 10 | 2016-07-12 09:48 | [7 empty] | 2016-07-12 19:58 | Yes | 0
VD-9001-204A-CAL-120 | 3 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-06-08 19:58 | 2016-06-16 12:38 |  | No | 8 | 2016-06-26 15:13 | [7 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-105-PID-101 | 4 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-28 | 2016-06-01 12:40 | 2016-06-01 12:41 | Yes | 4 |  | 2016-07-18 15:10 | [6 empty] | 2016-07-18 19:58 | Yes | 33 | 1204-Owner-v | 2019-07-08 14:39
VD-9001-105-LST-301 | 1 | Piping material list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-05-28 | 2016-06-06 12:10 |  | No | 9 | 2016-06-09 09:09 | [7 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-253(A)-DWG-005 | 5 | STEEL STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-05-29 | 2016-06-01 17:18 | 2016-06-01 17:19 | Yes | 3 |  | 2016-06-21 09:32 | [6 empty] | 2016-06-21 19:57 | Yes | 6 | 1204-Owner-v | 2018-06-18 15:01
VD-9001-204A-DWG-133 | 2 | Name Plate Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-06-12 19:58 | 2016-07-04 16:20 |  | No | 22 |  | 2016-07-05 11:54 | [6 empty] | 2016-07-05 19:58 | Yes | 0
VD-9001-204A-DWG-173 | 2 | Name Plate Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-06-12 19:58 | 2016-06-25 17:06 |  | No | 13 |  | 2016-06-26 11:08 | [6 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-257A-DWG-008 | 5 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2016-06-06 | 2016-05-30 12:13 |  | No | -7 | 2016-06-05 14:44 | [7 empty] | 2016-06-05 19:58 | Yes | 0
VD-9001-204A-DWG-076 | 2 | External Attachment Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-06-13 19:58 | 2016-07-09 15:24 |  | No | 26 |  | 2016-07-27 13:56 | [6 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-204A-DWG-046 | 2 | External Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-06-13 19:58 | 2016-07-25 14:02 |  | No | 42 |  | 2016-08-06 15:16 | [6 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-206B-DWG-013 | 2 | MANHOLE & NOZZLE DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2016-06-14 19:58 | 2016-07-16 10:55 | 2016-07-16 10:55 | Yes | 32 |  | 2016-08-21 09:28 | [6 empty] | 2016-08-21 19:57 | Yes | 22
VD-9001-206B-DWG-019 | 1 | NAME PLATE DRAWING -T-1001 | PV-206B | TASHA | 2016-06-14 19:58 | 2016-07-16 10:59 |  | No | 32 |  | 2016-10-04 11:24 | [6 empty] | 2016-10-04 18:56 | Yes | 0
VD-9001-206B-PCJ-013 | 2 | HYDROSTATIC TEST PROCEDURE | PV-206B | TASHA | 2016-06-14 19:58 | 2016-06-26 15:21 | 2016-06-26 15:22 | Yes | 12 |  | 2016-10-04 11:06 | [6 empty] | 2016-10-04 18:55 | Yes | 86
VD-9001-206B-ITP-004 | 1 | INSPECTION AND TEST PLAN | PV-206B | TASHA | 2016-06-14 19:58 | 2016-06-26 15:20 |  | No | 12 | 2016-07-27 16:37 | [7 empty] | 2016-07-27 19:57 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:55
VD-9001-204A-DWG-015 | 1 | PF & LD Arrangement FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-06-14 19:58 | 2016-06-01 11:11 |  | No | -13 |  | 2016-06-13 17:15 | [6 empty] | 2016-06-13 19:58 | Yes | 0
VD-9001-206B-DWG-015 | 1 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-1001 | PV-206B | TASHA | 2016-06-14 19:58 | 2016-08-02 11:56 | 2016-08-03 12:20 | Yes | 49 |  | 2016-08-20 11:36 | [6 empty] | 2016-08-20 19:57 | Yes | 4 | 1204-Owner-v | 2018-04-27 14:18
VD-9001-203-DSH-005 | 2 | Technical Data Sheet (Process&Mechanic) | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 19:58 | 2016-06-07 17:13 |  | No | -7 | 2016-06-26 11:03 | [7 empty] | 2016-06-26 19:58 | Yes | 0
VD-9001-203-DWG-020 | 2 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-14 19:58 | 2016-07-04 15:50 |  | No | 20 | 2016-08-13 10:10 | [7 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-254-DSH-350 | 2 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE TRANSMITTERS | HM-254 | AZAR AB | 2016-06-14 19:58 | 2019-05-25 12:25 | 2019-05-25 12:25 | Yes | 1075 |  |  | 2019-06-26 15:24 | [5 empty] | 2019-06-26 15:24 | Yes | 18 | 1204-Owner-v | 2019-06-15 16:38
VD-9001-254-DSH-353 | 2 | DATA SHEET FOR PRESSURE, DIFFERENTIAL PRESSURE & TEMPERATURE GAUGES | HM-254 | AZAR AB | 2016-06-14 19:58 | 2019-05-25 15:02 | 2019-05-25 15:02 | Yes | 1075 |  |  | 2019-06-26 15:22 | [5 empty] | 2019-06-26 15:22 | Yes | 18 | 1204-Owner-v | 2019-05-28 17:30
VD-9001-254-DSH-355 | 2 | DATA SHEET FOR DRUM LEVEL GAUGES | HM-254 | AZAR AB | 2016-06-14 19:58 |  |  | No | 1466 | [9 empty] | No | 0
VD-9001-105-DSH-206 | 1 | Data sheet of level gauges | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-01 14:38 | 2016-06-01 18:53 | 2016-06-01 18:54 | Yes | 0 |  | 2016-06-09 08:36 | [6 empty] | 2016-06-09 19:58 | Yes | -6 | 1204-Owner-v | 2019-01-04 21:40
VD-9001-105-DIG-205 | 4 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-01 14:38 | 2016-06-02 17:14 |  | No | 1 | 2016-06-09 08:49 | [7 empty] | 2016-06-09 19:58 | Yes | 0
VD-9001-105-DIG-202 | 3 | Interlock logic diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-01 14:38 | 2016-06-02 17:07 | 2016-06-02 17:08 | Yes | 1 |  | 2016-06-09 08:39 | [6 empty] | 2016-06-09 19:58 | Yes | -7
VD-9001-105-DSH-211 | 3 | Data sheet of hydrogen analyzer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-02 | 2016-06-07 16:46 |  | No | 5 | 2016-06-15 10:50 | [7 empty] | 2016-06-15 19:58 | Yes | 0
VD-9001-105-PPL-301 | 3 | Plot plan of HRU | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-02 | 2016-06-06 08:58 | 2016-06-06 08:59 | Yes | 4 |  | 2016-07-07 11:03 | [6 empty] | 2016-07-07 19:58 | Yes | 17 | 1204-Owner-v | 2018-10-31 15:01
VD-9001-105-DIG-206 | 3 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-02 | 2016-06-20 18:29 |  | No | 18 |  | 2016-06-28 15:42 | [6 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-257A-DWG-008 | 6 | General Arrangment Drawing E-3013 | HM-257A | ABAN AIR COOLER. | 2016-06-12 | 2016-06-06 12:37 | 2016-06-06 12:37 | Yes | -6 |  | 2016-06-20 11:11 | [6 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-257A-DWG-009 | 4 | GENERAL ARRANGEMENT DRAWING E-1001 | HM-257A | ABAN AIR COOLER. | 2016-06-12 | 2016-06-08 10:03 | 2016-06-08 10:03 | Yes | -4 |  | 2016-06-20 12:08 | [6 empty] | 2016-06-20 19:57 | Yes | -2
VD-9001-205A-DWG-003 | 5 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-06-19 19:58 | 2016-06-06 17:49 |  | No | -13 |  | 2016-06-07 17:22 | [6 empty] | 2016-06-07 19:58 | Yes | 0
VD-9001-204A-DWG-105 | 1 | PF & LD Arrangement FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-06-19 19:58 | 2016-06-22 07:28 |  | No | 3 | 2016-06-29 14:37 | [7 empty] | 2016-06-29 19:58 | Yes | 0
VD-9001-203-CAL-007 | 1 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-19 19:58 | 2016-07-04 15:54 |  | No | 15 | 2016-07-16 17:50 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-203-DWG-017 | 1 | Name Plate Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-19 19:58 | 2016-07-13 16:49 |  | No | 24 |  | 2016-07-13 17:25 | [6 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-203-HMB-006 | 2 | Deaerator Heat and Mass Balances | PV-203 | Masnout Felezi Sangin (MFS) | 2016-06-19 19:58 |  |  | No | 1461 | [9 empty] | No | 0
VD-9001-204A-DWG-161 | 3 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-06-19 19:58 | 2016-06-16 09:33 |  | No | -3 |  | 2016-06-20 11:54 | [6 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-204A-DWG-012 | 2 | Nozzle Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-06-19 19:58 | 2016-06-28 16:05 |  | No | 9 |  | 2016-07-05 15:35 | [6 empty] | 2016-07-05 19:58 | Yes | 0
VD-9001-254-PCU-601 | 3 | BOILER EXPECTED PERFORMANCE CURVES | HM-254 | AZAR AB | 2016-06-06 09:29 | 2016-06-06 10:01 | 2016-06-06 10:02 | Yes | 0 | 2016-07-05 14:59 | 2016-07-05 15:00 | [6 empty] | 2016-07-05 19:58 | Yes | 15
VD-9001-206B-PCJ-014 | 2 | REPAIR PROCEDURE | PV-206B | TASHA | 2016-06-20 19:58 | 2016-06-26 15:21 | 2016-06-26 15:22 | Yes | 6 |  | 2016-09-17 09:47 | [6 empty] | 2016-09-17 19:56 | Yes | 69
VD-9001-206B-PCJ-015 | 2 | PAINTING PROCEDURE | PV-206B | TASHA | 2016-06-20 19:58 | 2016-08-07 09:57 |  | No | 48 | 2016-08-28 12:11 | [7 empty] | 2016-08-28 19:57 | Yes | 0
VD-9001-204A-DWG-011 | 4 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-06-20 19:58 | 2016-06-16 09:35 |  | No | -4 | 2016-06-20 12:18 | [7 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-253(A)-DWG-062 | 7 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2016-06-07 | 2016-12-11 17:21 | 2016-12-11 17:22 | Yes | 187 |  | 2017-01-23 15:39 | [6 empty] | 2017-01-23 20:00 | Yes | 29
VD-9001-204B-CAL-004 | 1 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2016-06-21 19:58 | 2016-06-25 15:29 |  | No | 4 | 2016-07-13 17:50 | [7 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-204B-DWG-004 | 1 | General Arrangment Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-06-21 19:58 | 2016-06-28 15:58 |  | No | 7 | 2016-07-20 17:29 | [7 empty] | 2016-07-20 19:58 | Yes | 0
VD-9001-204B-DWG-012 | 1 | Body Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-06-21 19:58 | 2016-07-05 17:47 |  | No | 14 | 2016-07-26 15:39 | [7 empty] | 2016-07-26 19:58 | Yes | 0
VD-9001-254-DIG-338 | 2 | CAUSE AND EFFECT DIAGRAM | HM-254 | AZAR AB | 2016-06-22 19:58 | 2017-12-24 13:34 | 2017-12-24 13:35 | Yes | 550 |  | 2018-02-18 11:26 | [6 empty] | 2018-02-18 20:00 | Yes | 42 | 1204-Owner-v | 2018-01-30 14:48
VD-9001-254-PID-116 | 4 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-22 19:58 | 2016-08-01 08:42 |  | No | 40 | 2016-09-13 14:24 | [7 empty] | 2016-09-13 19:56 | Yes | 0 | 1204-Owner-v | 2018-04-17 14:33
VD-9001-254-PID-118 | 4 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-22 19:58 | 2016-08-01 08:43 | 2016-08-01 08:44 | Yes | 40 |  | 2016-09-13 17:19 | [6 empty] | 2016-09-13 19:56 | Yes | 29 | 1204-Owner-v | 2018-01-27 15:24
VD-9001-254-PID-120 | 4 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-22 19:58 | 2016-08-01 08:43 |  | No | 40 | 2016-09-13 14:26 | [7 empty] | 2016-09-13 19:56 | Yes | 0 | 1204-Owner-v | 2019-10-15 13:16
VD-9001-254-PID-114 | 4 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-22 19:58 | 2016-08-01 08:41 |  | No | 40 | 2016-09-13 10:57 | [7 empty] | 2016-09-13 19:56 | Yes | 0 | 1204-Owner-v | 2018-04-17 14:33
VD-9001-105-DWG-502 | 3 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-09 | 2016-06-20 11:37 |  | No | 11 |  | 2016-07-07 11:30 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-DIG-205 | 5 | Control loop sketch | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-09 | 2016-06-14 10:27 | 2016-06-14 10:28 | Yes | 5 |  | 2016-06-20 14:17 | [6 empty] | 2016-06-20 19:57 | Yes | -8
VD-9001-105-DIG-201 | 3 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-09 | 2016-06-14 09:56 |  | No | 5 | 2016-06-28 15:14 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-105-LST-301 | 2 | Piping material list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-09 | 2016-06-16 18:51 |  | No | 7 | 2016-06-20 13:49 | [7 empty] | 2016-06-20 19:57 | Yes | 0
VD-9001-105-LST-201 | 2 | Cable schedule with cable list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-09 | 2016-06-14 10:27 |  | No | 5 | 2016-06-28 15:22 | [7 empty] | 2016-06-28 19:58 | Yes | 0
VD-9001-254-PID-119 | 3 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-25 19:58 | 2016-08-01 08:43 | 2016-08-01 08:44 | Yes | 37 |  | 2017-08-12 09:59 | [6 empty] | 2017-08-12 19:58 | Yes | 362 | 1204-Owner-v | 2018-04-17 14:34
VD-9001-254-PID-117 | 3 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-25 19:58 | 2016-08-01 08:43 |  | No | 37 | 2016-09-13 17:15 | [7 empty] | 2016-09-13 19:56 | Yes | 0 | 1204-Owner-v | 2019-10-15 13:14
VD-9001-254-PID-121 | 3 | STEAM TURBINE P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-25 19:58 |  |  | No | 1455 | [9 empty] | No | 0
VD-9001-254-PID-115 | 4 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2016-06-25 19:58 | 2016-08-01 08:42 |  | No | 37 | 2016-09-13 14:21 | [7 empty] | 2016-09-13 19:56 | Yes | 0 | 1204-Owner-v | 2018-04-17 14:33
VD-9001-204B-CAL-003 | 1 | Strength Calculation Book D-3006 | PV-204B | ABAN AIR COOLER. | 2016-06-25 19:58 | 2016-06-22 18:06 |  | No | -3 | 2016-07-11 17:23 | [7 empty] | 2016-07-11 19:58 | Yes | 0
VD-9001-253(A)-DWG-083 | 1 | ASSEMBLY MARKING FOR STRUCTURE for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-06-13 10:25 | 2016-06-15 10:47 | 2016-06-15 10:47 | Yes | 2 |  | 2016-06-21 09:54 | [6 empty] | 2016-06-21 19:57 | Yes | -8 | 1204-Owner-v | 2018-08-14 17:54
VD-9001-204A-DWG-101 | 3 | General Arrangement Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-06-27 19:58 | 2016-06-15 10:18 |  | No | -12 |  | 2016-06-18 09:52 | [6 empty] | 2016-06-18 19:57 | Yes | 0
VD-9001-254-DSH-351 | 2 | DATA SHEET FOR FLOW ELEMENTS | HM-254 | AZAR AB | 2016-06-27 19:58 | 2019-05-22 15:06 | 2019-05-22 15:06 | Yes | 1059 |  |  | 2019-07-13 11:57 | [5 empty] | 2019-07-13 11:57 | Yes | 38 | 1204-Owner-v | 2019-05-23 07:17
VD-9001-254-LST-555 | 2 | VALVE LIST | HM-254 | AZAR AB | 2016-06-27 19:58 | 2018-10-13 15:52 | 2018-10-13 15:52 | Yes | 838 |  |  |  | 2018-10-22 12:10 |  |  |  |  | 2018-10-22 12:10 | Yes | -5
VD-9001-254-PDS-341 | 2 | FUNCTION OF ABC | HM-254 | AZAR AB | 2016-06-27 19:58 | 2017-12-30 17:15 | 2017-12-30 17:16 | Yes | 551 |  | 2018-02-06 14:24 | [6 empty] | 2018-02-07 20:00 | Yes | 24 | 1204-Owner-v | 2019-12-09 08:32
VD-9001-254-DIG-339 | 1 | ABC & SUPERVISORY FLOW DIAGRAMS | HM-254 | AZAR AB | 2016-06-27 19:58 | 2017-12-30 17:13 |  | No | 551 | 2018-02-06 14:22 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-29 14:10
VD-9001-254-CAL-585 | 2 | CALCULATION SHEET FOR THERMOWELL | HM-254 | AZAR AB | 2016-06-27 19:58 |  |  | No | 1453 | [9 empty] | No | 0
VD-9001-204A-DWG-131 | 3 | General Arrangement Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-06-28 19:58 | 2016-08-04 11:55 |  | No | 37 |  | 2016-08-13 15:23 | [6 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-105-CAL-503 | 3 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-15 | 2016-06-17 19:04 |  | No | 2 | 2016-07-07 11:15 | [7 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-DWG-501 | 3 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-15 | 2016-06-17 19:08 |  | No | 2 |  | 2016-07-07 11:20 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-LST-202 | 1 | Instrument list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-15 | 2016-06-17 19:26 | 2016-06-17 19:27 | Yes | 2 |  | 2016-06-20 13:46 | [6 empty] | 2016-06-20 19:57 | Yes | -11 | 1204-Owner-v | 2019-01-04 21:29
VD-9001-105-DSH-211 | 4 | Data sheet of hydrogen analyzer | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-15 | 2016-06-18 11:05 | 2016-06-18 11:06 | Yes | 3 |  | 2016-06-28 15:36 | [6 empty] | 2016-06-28 19:58 | Yes | -4 | 1204-Owner-v | 2019-01-04 21:39
VD-9001-105-CAL-501 | 3 | Calculation sheet of Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-15 | 2016-06-17 19:06 |  | No | 2 |  | 2016-07-07 11:18 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-DSH-202 | 1 | Data sheet of pressure transmitters | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-18 11:54 | 2017-10-17 09:08 | 2017-10-17 09:09 | Yes | 486 |  |  | 2018-03-03 19:12 | [5 empty] | 2018-03-03 19:13 | Yes | 123 | 1204-Owner-v | 2019-01-04 21:34
VD-9001-105-DSH-205 | 4 | Data sheet of automatic valves | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-18 11:54 | 2016-06-18 13:51 | 2016-06-18 13:52 | Yes | 0 |  | 2016-06-20 13:44 | [6 empty] | 2016-06-20 19:57 | Yes | -12 | 1204-Owner-v | 2019-01-04 21:38
VD-9001-254-DSH-563 | 2 | DATA SHEET FOR MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2016-07-02 19:57 | 2016-09-25 12:18 |  | No | 85 | 2016-11-07 10:09 | [7 empty] | 2016-11-07 19:59 | Yes | 0 | 1204-Owner-v | 2018-05-28 12:15
VD-9001-204B-DWG-016 | 1 | Nozzle Detail Drawing D-3007 * | PV-204B | ABAN AIR COOLER. | 2016-07-03 19:57 | 2016-07-17 11:15 |  | No | 14 | 2016-08-10 15:11 | [7 empty] | 2016-08-10 19:57 | Yes | 0
VD-9001-204A-DWG-025 | 1 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-07-03 19:57 | 2016-06-26 12:10 |  | No | -7 | 2016-07-11 10:19 | [7 empty] | 2016-07-11 19:58 | Yes | 0
VD-9001-204A-DWG-095 | 1 | PF & LD Arrangement FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-07-03 19:58 | 2016-06-26 12:41 |  | No | -7 | 2016-07-05 14:56 | [7 empty] | 2016-07-05 19:58 | Yes | 0
VD-9001-105-CAL-502 | 2 | Calculation sheet for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-20 10:36 | 2016-06-20 11:28 |  | No | 0 |  | 2016-07-07 11:25 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-CAL-505 | 1 | Thermal design calculation for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-20 10:36 | 2016-06-20 11:31 | 2016-06-20 11:32 | Yes | 0 |  | 2016-07-07 11:23 | [6 empty] | 2016-07-07 19:58 | Yes | 3
VD-9001-105-DSH-201 | 2 | Data sheet of pressure gauges | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-20 10:38 | 2016-06-20 11:49 | 2016-06-20 11:50 | Yes | 0 |  | 2016-06-28 15:40 | [6 empty] | 2016-06-28 19:58 | Yes | -6 | 1204-Owner-v | 2019-01-07 08:24
VD-9001-105-LST-301 | 3 | Piping material list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-20 | 2016-06-22 12:49 | 2016-06-22 12:50 | Yes | 2 |  | 2016-06-28 17:38 | [6 empty] | 2016-06-28 19:58 | Yes | -8 | 1204-Owner-v | 2020-01-27 14:00
VD-9001-253(A)-DWG-011 | 2 | HEADER WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-06-20 | 2016-07-09 11:58 |  | No | 19 | 2016-08-16 13:38 | [7 empty] | 2016-08-16 19:57 | Yes | 0 | 1204-Owner-v | 2018-05-16 14:17
VD-9001-253(A)-DWG-018 | 2 | MOTOR WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-06-20 | 2016-07-09 12:00 | 2016-07-09 12:01 | Yes | 19 |  | 2016-08-06 08:45 | [6 empty] | 2016-08-06 19:57 | Yes | 14 | 1204-Owner-v | 2018-02-03 14:33
VD-9001-204A-DWG-011 | 5 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-07-04 19:57 | 2016-07-04 16:42 |  | No | 0 |  | 2016-07-12 15:59 | [6 empty] | 2016-07-12 19:58 | Yes | 0
VD-9001-254-PLN-557 | 1 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 3800 AND UP) | HM-254 | AZAR AB | 2016-07-04 19:57 | 2018-10-31 16:05 | 2018-10-31 16:05 | Yes | 849 |  |  |  | 2018-11-24 09:58 |  |  |  |  | 2018-11-24 09:59 | Yes | 10 | 1204-Owner-v | 2019-05-13 09:10
VD-9001-254-PLN-556 | 1 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2016-07-04 19:57 | 2018-10-31 16:04 | 2018-10-31 16:04 | Yes | 849 |  |  |  | 2018-11-24 09:56 |  |  |  |  | 2018-11-24 09:56 | Yes | 10 | 1204-Owner-v | 2019-05-13 09:12
VD-9001-253(A)-DWG-087 | 1 | MOTOR WALKWAY GRATING DETAIL AE-3002 | HM-253A | FATEH SANAT KIMIA | 2016-06-21 | 2016-06-25 15:39 |  | No | 4 |  | 2016-06-25 16:13 | [6 empty] | 2016-06-25 19:58 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:46
VD-9001-204B-DWG-003 | 1 | General Arrangment Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-07-05 19:57 | 2016-06-25 15:33 |  | No | -10 | 2016-07-26 14:42 | [7 empty] | 2016-07-26 19:58 | Yes | 0
VD-9001-204B-DWG-011 | 1 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-07-06 19:57 | 2016-07-14 16:01 |  | No | 8 | 2016-08-03 14:30 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-204A-DWG-142 | 2 | Nozzle Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-06-25 16:57 | 2016-06-25 17:05 | 2016-06-25 17:05 | Yes | 0 |  | 2016-07-05 15:12 | [6 empty] | 2016-07-05 19:58 | Yes | -4
VD-9001-105-ITP-701 | 2 | Inspection and test plan for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:14 |  | No | 0 |  | 2016-07-07 11:34 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-ITP-702 | 2 | Inspection and test plan for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:14 |  | No | 0 |  | 2016-07-07 11:32 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-ITP-703 | 2 | Inspection and test plan for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:15 |  | No | 0 | 2016-07-07 11:42 | [7 empty] | 2016-07-07 19:58 | Yes | 0 | 1204-Owner-v | 2020-01-01 11:12
VD-9001-105-ITP-705 | 2 | Inspection and test plan of piping and skid-structure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:16 |  | No | 0 |  | 2016-07-07 11:45 | [6 empty] | 2016-07-07 19:58 | Yes | 0 | 1204-Owner-v | 2018-06-24 09:28
VD-9001-105-ITP-706 | 2 | Inspection and test plan of membrane modules | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:19 |  | No | 0 |  | 2016-07-07 11:47 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-105-ITP-707 | 2 | Inspection and test plan of instruments | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-25 17:15 | 2016-06-25 18:23 |  | No | 0 |  | 2016-07-07 11:49 | [6 empty] | 2016-07-07 19:58 | Yes | 0
VD-9001-204B-DWG-015 | 1 | Nozzle Detail Drawing D-3006 * | PV-204B | ABAN AIR COOLER. | 2016-07-09 19:58 | 2016-08-09 14:06 |  | No | 31 |  | 2016-08-27 14:18 | [6 empty] | 2016-08-27 19:57 | Yes | 0
VD-9001-203-DSH-005 | 3 | Technical Data Sheet (Process&Mechanic) | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-10 19:58 | 2016-06-30 10:21 |  | No | -10 | 2016-07-16 09:38 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-203-DWG-011 | 1 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-10 19:58 | 2016-07-11 16:54 |  | No | 1 | 2016-08-13 10:11 | [7 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-203-DWG-013 | 1 | Detail of Manhole Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-10 19:58 | 2016-07-16 16:26 |  | No | 6 | 2016-08-14 11:32 | [7 empty] | 2016-08-14 19:57 | Yes | 0
VD-9001-204A-CAL-120 | 4 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-07-10 19:58 | 2016-07-12 13:37 |  | No | 2 |  | 2016-07-16 09:29 | [6 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-204A-DWG-112 | 2 | Nozzle Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-07-10 19:58 | 2016-06-30 11:59 |  | No | -10 |  | 2016-07-11 10:50 | [6 empty] | 2016-07-11 19:58 | Yes | 0
VD-9001-105-ISO-301 | 1 | Piping isometric | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-28 | 2016-07-13 07:33 |  | No | 15 | 2016-08-08 16:59 | [7 empty] | 2016-08-08 19:57 | Yes | 0
VD-9001-105-DIG-201 | 4 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-28 | 2016-07-29 12:43 | 2016-07-29 12:44 | Yes | 31 |  | 2016-08-09 11:44 | [6 empty] | 2016-08-09 19:57 | Yes | -3
VD-9001-105-DIG-203 | 2 | Instrument, cable, junction box and cable tray layout diagram | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-28 | 2016-07-01 13:14 | 2016-07-01 13:15 | Yes | 3 |  | 2016-07-18 15:06 | [6 empty] | 2016-07-18 19:58 | Yes | 3
VD-9001-105-LST-201 | 3 | Cable schedule with cable list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-28 | 2016-07-29 13:15 | 2016-07-29 13:16 | Yes | 31 |  | 2016-08-09 11:48 | [6 empty] | 2016-08-09 19:57 | Yes | -3
VD-9001-105-MAL-201 | 1 | Instrument installation bill of material | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-06-28 | 2016-07-14 05:27 |  | No | 16 | 2016-08-08 16:35 | [7 empty] | 2016-08-08 19:57 | Yes | 0
VD-9001-204A-DWG-135 | 1 | PF & LD Arrangement FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-07-12 19:58 | 2016-06-30 09:05 |  | No | -12 | 2016-07-13 15:47 | [7 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-253(A)-DSH-047 | 1 | MOTOR GENERAL ARRANGEMENT DWG. For 3001 | HM-253A | FATEH SANAT KIMIA | 2016-06-29 | 2016-07-24 10:10 |  | No | 25 | 2016-08-03 17:04 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-253(A)-DSH-017 | 1 | MOTOR GENERAL ARRANGEMENT DWG. For 2001 | HM-253A | FATEH SANAT KIMIA | 2016-06-29 | 2016-07-23 16:27 |  | No | 24 | 2016-08-03 17:02 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-253(A)-DSH-077 | 1 | MOTOR GENERAL ARRANGEMENT DWG. For 3002 | HM-253A | FATEH SANAT KIMIA | 2016-06-29 | 2016-07-23 16:29 |  | No | 24 | 2016-08-06 16:58 | [7 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-203-DWG-012 | 1 | Shell Araangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-13 19:58 | 2016-07-11 16:52 |  | No | -2 | 2016-08-21 12:18 | [7 empty] | 2016-08-21 19:57 | Yes | 0
VD-9001-204A-WBK-001 | 4 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2016-07-13 19:58 | 2016-08-03 13:21 |  | No | 21 |  | 2016-08-10 09:28 | [6 empty] | 2016-08-10 19:57 | Yes | 0
VD-9001-206B-DWG-018 | 2 | PIPE CLIP DRAWING -T-1001 | PV-206B | TASHA | 2016-07-13 19:58 | 2016-07-16 10:58 | 2016-07-16 10:59 | Yes | 3 |  | 2016-08-21 09:18 | [6 empty] | 2016-08-21 19:57 | Yes | 22 | 1204-Owner-v | 2020-05-11 14:41
VD-9001-204A-DWG-105 | 2 | PF & LD Arrangement FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-07-13 19:58 | 2016-06-30 09:59 |  | No | -13 | 2016-07-25 16:42 | [7 empty] | 2016-07-25 19:57 | Yes | 0
VD-9001-214A-DIS-001 | 0 | Vendor Documents Index & Schedule | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-09-22 09:01 |  | No | 1440 | [9 empty] | No | 0
VD-9001-214A-CAT-001 | 0 | Catalogue and brochure | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 11:08 | 2016-07-12 11:09 | Yes | 2 |  | 2016-08-12 12:49 | [6 empty] | 2016-08-12 19:57 | Yes | 17
VD-9001-214A-CSH-001 | 0 | Breather valves/Emergency sizing calculations | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 11:54 |  | No | 2 | 2016-08-11 16:59 | [7 empty] | 2016-08-11 19:57 | Yes | 0
VD-9001-214A-PCU-001 | 0 | Performance Curve (Capacity) | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:29 | 2016-07-12 12:30 | Yes | 2 |  | 2016-08-11 17:04 | [6 empty] | 2016-08-11 19:57 | Yes | 16
VD-9001-214A-DWG-001 | 0 | Dimensional and weight Drawings for Tag No TK-7101A | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 11:55 |  | No | 2 | 2016-08-12 12:32 | [7 empty] | 2016-08-12 19:57 | Yes | 0
VD-9001-214A-DWG-002 | 0 | Name plat drawing for Tag No TK-7101A | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 11:56 | 2016-07-12 11:57 | Yes | 2 |  | 2016-08-12 12:40 | [6 empty] | 2016-08-12 19:57 | Yes | 17
VD-9001-214A-DWG-003 | 0 | Dimensional and weight Drawings for Tag No TK-7101B | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:06 |  | No | 2 | 2016-08-12 12:44 | [7 empty] | 2016-08-12 19:57 | Yes | 0
VD-9001-214A-DWG-004 | 0 | Name plat drawing for Tag No TK-7101B | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:07 | 2016-07-12 12:08 | Yes | 2 |  | 2016-08-12 12:38 | [6 empty] | 2016-08-12 19:57 | Yes | 17
VD-9001-214A-DWG-005 | 0 | Dimensional and weight Drawings for Tag No TK-7201 | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:15 |  | No | 2 | 2016-08-12 12:15 | [7 empty] | 2016-08-12 19:57 | Yes | 0
VD-9001-214A-DWG-006 | 0 | Name plat drawing for Tag No TK-7201 | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:15 |  | No | 2 | 2016-08-12 12:22 | [7 empty] | 2016-08-12 19:57 | Yes | 0
VD-9001-214A-ITP-001 | 0 | Inspection and test plan for Breather Valve | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:16 |  | No | 2 | 2016-08-11 15:48 | [7 empty] | 2016-08-11 19:57 | Yes | 0
VD-9001-214A-ITP-002 | 0 | Inspection and test plan for Rim Vent | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:16 |  | No | 2 | 2016-08-11 15:52 | [7 empty] | 2016-08-11 19:57 | Yes | 0
VD-9001-214A-ITP-003 | 0 | Inspection and test plan for Emergency Vent | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:17 |  | No | 2 | 2016-08-11 15:54 | [7 empty] | 2016-08-11 19:57 | Yes | 0
VD-9001-214A-PCJ-001 | 0 | Inspection and test procedures for Breather Valve | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:21 | 2016-07-12 12:22 | Yes | 2 |  | 2016-08-27 11:32 | [6 empty] | 2016-08-27 19:56 | Yes | 32
VD-9001-214A-PCJ-002 | 0 | Inspection and test procedures for Rim Vent | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:24 | 2016-07-12 12:25 | Yes | 2 |  | 2016-08-24 10:55 | [6 empty] | 2016-08-24 19:57 | Yes | 29
VD-9001-214A-PCJ-003 | 0 | Inspection and test procedures for Emergency Vent | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:25 | 2016-07-12 12:26 | Yes | 2 |  | 2016-08-24 10:52 | [6 empty] | 2016-08-24 19:57 | Yes | 29
VD-9001-214A-PCJ-004 | 0 | Painting procedures | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:28 |  | No | 2 | 2016-08-27 11:28 | [7 empty] | 2016-08-27 19:56 | Yes | 0
VD-9001-214A-LST-001 | 0 | Spare Part List for start up | PV-214A | TANKTECH KSPC | 2016-07-10 | 2016-07-12 12:18 |  | No | 2 | 2016-08-12 13:10 | [7 empty] | 2016-08-12 19:57 | Yes | 0
VD-9001-214A-PCJ-005 | 0 | Packing Procedure | PV-214A | TANKTECH KSPC | 2016-07-25 | 2016-07-12 12:29 | 2016-07-12 12:30 | Yes | -13 |  | 2016-08-28 15:06 | [6 empty] | 2016-08-28 19:57 | Yes | 33
VD-9001-214A-MNL-001 | 0 | Installation, operating and Mainteance Manuals | PV-214A | TANKTECH KSPC | 2016-07-25 | 2016-07-12 12:20 |  | No | -13 | 2016-08-28 15:01 | [7 empty] | 2016-08-28 19:57 | Yes | 0
VD-9001-205A-DWG-013 | 4 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-07-03 14:21 | 2016-07-09 12:29 | 2016-07-09 12:30 | Yes | 6 |  | 2016-07-16 17:58 | [6 empty] | 2016-07-16 19:58 | Yes | -7
VD-9001-205A-DWG-018 | 6 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-07-03 14:21 | 2016-07-04 12:04 | 2016-07-04 12:05 | Yes | 1 |  | 2016-07-16 17:57 | [6 empty] | 2016-07-16 19:58 | Yes | -2
VD-9001-254-DWG-347 | 2 | INSTALLATION DRAWINGS & PROCEDURES FOR INSTRUMENTS | HM-254 | AZAR AB | 2016-07-18 19:58 | 2018-01-16 09:19 |  | No | 547 | 2018-02-05 14:45 | [7 empty] | 2018-02-05 20:00 | Yes | 0
VD-9001-204A-DWG-115 | 1 | PF & LD Arrangement FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-07-18 19:58 | 2016-07-09 07:38 |  | No | -9 | 2016-07-13 14:55 | [7 empty] | 2016-07-13 19:58 | Yes | 0
VD-9001-204A-DWG-125 | 1 | PF & LD Arrangement FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-07-18 19:58 | 2016-07-12 08:43 |  | No | -6 | 2016-07-19 17:33 | [7 empty] | 2016-07-19 19:58 | Yes | 0
VD-9001-204A-DWG-045 | 1 | PF & LD Arrangement FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-07-18 19:58 | 2016-07-11 08:53 |  | No | -7 |  | 2016-07-27 14:02 | [6 empty] | 2016-07-27 19:57 | Yes | 0
VD-9001-204A-DWG-042 | 2 | Nozzle Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-07-18 19:58 | 2016-07-05 14:12 |  | No | -13 |  | 2016-07-11 10:10 | [6 empty] | 2016-07-11 19:58 | Yes | 0
VD-9001-203-DWG-015 | 1 | Detail of Saddle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-19 19:58 | 2016-07-11 16:57 |  | No | -8 | 2016-08-14 11:57 | [7 empty] | 2016-08-14 19:57 | Yes | 0
VD-9001-204A-DWG-095 | 2 | PF & LD Arrangement FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-07-19 19:58 | 2016-07-19 15:25 |  | No | 0 |  | 2016-08-06 15:06 | [6 empty] | 2016-08-06 19:57 | Yes | 0
VD-9001-204A-DWG-136 | 1 | External Attachment Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-07-19 19:58 | 2016-07-17 14:06 |  | No | -2 |  | 2016-07-24 14:55 | [6 empty] | 2016-07-24 19:57 | Yes | 0
VD-9001-105-PCJ-509 | 1 | Hardness test procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-09-20 18:40 |  | No | 75 | 2016-11-19 15:15 | [7 empty] | 2016-11-19 20:00 | Yes | 0
VD-9001-105-SPE-501 | 1 | Painting specification | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2017-09-26 06:32 |  | No | 446 | 2017-10-04 11:37 | [7 empty] | 2017-10-04 20:00 | Yes | 0
VD-9001-105-HSE-902 | 1 | HSE instruction | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2018-04-17 18:18 | 2018-04-17 18:18 | Yes | 649 |  |  | 2018-04-28 10:02 | [5 empty] | 2018-04-28 10:02 | Yes | -3
VD-9001-105-HSE-903 | 1 | HSE plans | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2018-04-17 18:18 | 2018-04-17 18:19 | Yes | 649 |  |  | 2018-04-28 09:51 | [5 empty] | 2018-04-28 09:51 | Yes | -3
VD-9001-105-PCJ-507 | 1 | Weld overlay procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-09-01 15:53 | 2016-09-01 15:54 | Yes | 56 |  | 2016-10-02 16:40 | [6 empty] | 2016-10-02 18:56 | Yes | 17
VD-9001-105-WPS-701 | 1 | WPS & PQR for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-09-27 07:15 |  | No | 82 | 2016-10-29 12:20 | [7 empty] | 2016-10-29 20:00 | Yes | 0
VD-9001-105-WPS-703 | 1 | WPS & PQR for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-09-27 07:36 |  | No | 82 | 2016-10-20 11:46 | [7 empty] | 2016-10-20 20:00 | Yes | 0
VD-9001-105-WPS-702 | 1 | WPS & PQR for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-09-27 07:25 |  | No | 82 | 2016-10-29 12:26 | [7 empty] | 2016-10-29 20:00 | Yes | 0
VD-9001-105-CAL-503 | 4 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-07-13 06:53 |  | No | 6 |  | 2016-08-08 16:26 | [6 empty] | 2016-08-08 19:57 | Yes | 0
VD-9001-105-ITP-703 | 3 | Inspection and test plan for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-07 | 2016-07-08 12:14 |  | No | 1 |  | 2016-07-09 14:42 | [6 empty] | 2016-07-09 19:58 | Yes | 0
VD-9001-105-DSH-109 | 0 | Data Sheet of Flame Arrester | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-10 | 2016-07-09 14:08 |  | No | -1 | 2016-07-16 10:24 | [7 empty] | 2016-07-16 19:58 | Yes | 0
VD-9001-204B-CAL-002 | 2 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2016-07-23 19:58 | 2016-07-10 16:10 |  | No | -13 | 2016-08-03 15:41 | [7 empty] | 2016-08-03 19:57 | Yes | 0
VD-9001-204A-DWG-075 | 2 | PF & LD Arrangement FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-07-24 19:58 | 2016-07-17 14:08 |  | No | -7 | 2016-07-26 11:52 | [7 empty] | 2016-07-26 19:57 | Yes | 0
VD-9001-206B-DWG-016 | 1 | INSULATION SUPPORT DRAWING -T-1001 | PV-206B | TASHA | 2016-07-24 19:58 | 2016-07-16 10:57 | 2016-07-16 10:58 | Yes | -8 |  | 2016-10-04 11:46 | [6 empty] | 2016-10-04 18:56 | Yes | 66 | 1204-Owner-v | 2019-06-22 10:31
VD-9001-206B-DWG-076 | 1 | INSULATION SUPPORT DRAWING -T-4001 | PV-206B | TASHA | 2016-07-24 19:58 | 2016-08-13 18:56 |  | No | 20 |  | 2016-10-04 11:48 | [6 empty] | 2016-10-04 18:56 | Yes | 0
VD-9001-205A-DWG-043 | 3 | GENERAL ARRANGEMENT DRAWING FOR OF D-3006 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-07-24 19:58 | 2016-09-26 10:05 | 2016-09-26 10:06 | Yes | 64 |  | 2016-12-28 14:22 | [6 empty] | 2016-12-28 19:59 | Yes | 79
VD-9001-204A-DWG-025 | 2 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-07-25 19:58 | 2016-07-12 11:55 |  | No | -13 | 2016-07-25 15:26 | [7 empty] | 2016-07-25 19:57 | Yes | 0
VD-9001-204B-CAL-003 | 2 | Strength Calculation Book D-3006 | PV-204B | ABAN AIR COOLER. | 2016-07-25 19:58 | 2016-08-14 15:52 |  | No | 20 | 2016-08-24 12:18 | [7 empty] | 2016-08-24 19:57 | Yes | 0
VD-9001-204A-DWG-121 | 4 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-07-26 19:58 | 2016-07-28 11:03 |  | No | 2 |  | 2016-08-21 15:08 | [6 empty] | 2016-08-21 19:57 | Yes | 0
VD-9001-204A-DWG-106 | 2 | External Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-07-26 19:58 | 2016-07-23 11:08 |  | No | -3 |  | 2016-08-14 10:14 | [6 empty] | 2016-08-14 19:57 | Yes | 0
VD-9001-105-DIG-206 | 4 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-13 14:17 | 2016-07-14 05:24 |  | No | 1 | 2016-08-08 16:33 | [7 empty] | 2016-08-08 19:57 | Yes | 0
VD-9001-105-DWG-502 | 4 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-13 14:18 | 2016-07-14 15:21 |  | No | 1 |  | 2016-07-18 14:37 | [6 empty] | 2016-07-18 19:58 | Yes | 0
VD-9001-254-DSH-349 | 2 | DATA SHEET FOR FLAME DETECTOR | HM-254 | AZAR AB | 2016-07-27 19:58 | 2019-06-02 13:39 | 2019-06-02 13:39 | Yes | 1040 |  |  | 2019-09-01 09:24 | [5 empty] | 2019-09-01 09:24 | Yes | 77
VD-9001-254-DSH-134 | 2 | DATA SHEET FOR BURNER | HM-254 | AZAR AB | 2016-07-27 19:58 | 2018-06-18 09:26 | 2018-06-18 09:26 | Yes | 691 |  |  |  | 2018-08-06 16:35 |  |  |  |  | 2018-08-06 16:35 | Yes | 35
VD-9001-204A-DWG-115 | 2 | PF & LD Arrangement FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-07-27 19:58 | 2016-07-19 15:25 |  | No | -8 |  | 2016-08-17 09:54 | [6 empty] | 2016-08-17 19:57 | Yes | 0
VD-9001-204B-CAL-001 | 2 | Strength Calculation Book D-1002 | PV-204B | ABAN AIR COOLER. | 2016-07-27 19:58 | 2016-08-14 15:52 | 2016-08-14 15:53 | Yes | 18 |  | 2016-08-24 10:45 | [6 empty] | 2016-08-24 19:57 | Yes | -4 | 1204-Owner-v | 2018-01-22 11:05
VD-9001-204A-DWG-135 | 2 | PF & LD Arrangement FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-07-27 19:58 | 2016-07-21 10:30 | 2016-07-21 10:30 | Yes | -6 |  | 2016-08-17 10:52 | [6 empty] | 2016-08-17 19:57 | Yes | 13 | 1204-Owner-v | 2018-12-29 10:21
VD-9001-204B-CAL-004 | 2 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2016-07-27 19:58 | 2016-08-14 08:56 |  | No | 18 | 2016-08-24 10:49 | [7 empty] | 2016-08-24 19:57 | Yes | 0
VD-9001-105-DSH-109 | 1 | Data Sheet of Flame Arrester | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-16 | 2016-07-18 17:34 | 2016-07-18 17:35 | Yes | 2 |  | 2016-07-19 08:25 | [6 empty] | 2016-07-19 19:57 | Yes | -13 | 1204-Owner-v | 2019-01-07 08:24
VD-9001-105-DWG-503 | 3 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-16 10:52 | 2016-07-17 17:05 |  | No | 1 |  | 2016-08-08 16:38 | [6 empty] | 2016-08-08 19:57 | Yes | 0
VD-9001-203-DSH-005 | 4 | Technical Data Sheet (Process&Mechanic) | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-30 19:58 | 2016-07-17 09:31 | 2016-07-17 09:32 | Yes | -13 |  | 2016-07-17 10:07 | [6 empty] | 2016-07-17 19:58 | Yes | -14
VD-9001-254-LST-340 | 2 | BMS I/O LIST | HM-254 | AZAR AB | 2016-07-30 19:58 | 2016-11-27 12:04 |  | No | 120 | 2016-12-25 14:38 | [7 empty] | 2016-12-25 19:59 | Yes | 0
VD-9001-254-LST-342 | 2 | CONTROL SYSTEM I/O LIST | HM-254 | AZAR AB | 2016-07-30 19:58 | 2016-11-27 12:04 |  | No | 120 | 2016-12-25 14:35 | [7 empty] | 2016-12-25 19:59 | Yes | 0
VD-9001-204A-DWG-096 | 2 | External Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-07-30 19:58 | 2016-07-17 14:03 |  | No | -13 |  | 2016-08-13 16:39 | [6 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-203-CAL-007 | 2 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-07-30 19:58 | 2016-07-21 11:28 |  | No | -9 | 2016-08-13 10:18 | [7 empty] | 2016-08-13 19:57 | Yes | 0
VD-9001-206B-DWG-075 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-4001 | PV-206B | TASHA | 2016-07-30 19:58 | 2016-08-13 18:58 |  | No | 14 | 2016-08-28 12:06 | [7 empty] | 2016-08-28 19:56 | Yes | 0 | 1204-Owner-v | 2018-12-21 11:31
VD-9001-253(A)-DWG-074 | 2 | ROTATING PART DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-07-17 15:32 | 2016-07-17 15:40 | 2016-07-17 15:40 | Yes | 0 |  | 2016-07-18 08:44 | [6 empty] | 2016-07-18 19:58 | Yes | -13 | 1204-Owner-v | 2019-01-31 11:28
VD-9001-253(A)-DWG-066 | 1 | PLENUM for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-07-18 14:45 | 2016-07-18 15:08 |  | No | 0 |  | 2016-07-31 14:39 | [6 empty] | 2016-07-31 19:57 | Yes | 0
VD-9001-204B-DWG-002 | 2 | General Arrangment Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-08-01 19:58 | 2016-08-13 09:06 |  | No | 12 |  | 2016-08-29 14:16 | [6 empty] | 2016-08-29 19:57 | Yes | 0
VD-9001-204A-DWG-125 | 2 | PF & LD Arrangement FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-08-02 19:58 | 2016-08-30 16:36 |  | No | 28 |  | 2016-09-25 16:35 | [6 empty] | 2016-09-25 18:56 | Yes | 0
VD-9001-204B-DWG-004 | 2 | General Arrangment Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-08-03 19:58 | 2016-08-15 14:42 |  | No | 12 | 2016-09-03 12:41 | [7 empty] | 2016-09-03 19:56 | Yes | 0 | 1204-Owner-v | 2018-12-02 09:13
VD-9001-205A-DWG-051 | 2 | GENERAL ARRANGEMENT DRAWING FOR OF D-2201 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-08-06 19:57 | 2016-10-18 16:05 | 2016-10-18 16:06 | Yes | 73 |  | 2016-12-28 15:07 | [6 empty] | 2016-12-28 19:59 | Yes | 57
VD-9001-205A-DWG-023 | 5 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-07-24 16:38 | 2016-07-24 17:15 |  | No | 0 |  | 2016-08-01 15:56 | [6 empty] | 2016-08-01 19:57 | Yes | 0
VD-9001-204A-DWG-017 | 1 | Internal Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-08-07 19:57 | 2016-08-02 09:27 |  | No | -5 |  | 2016-08-21 15:13 | [6 empty] | 2016-08-21 19:57 | Yes | 0
VD-9001-204B-DWG-010 | 2 | Body Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-08-07 19:58 | 2016-08-13 14:56 |  | No | 6 | 2016-08-20 17:20 | [7 empty] | 2016-08-20 19:57 | Yes | 0
VD-9001-204A-DWG-174 | 2 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-08-07 19:58 | 2016-09-08 11:03 |  | No | 32 | 2016-09-27 09:28 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204A-DWG-025 | 3 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-08-08 19:57 | 2016-08-27 07:34 |  | No | 19 |  | 2016-09-19 10:55 | [6 empty] | 2016-09-19 19:56 | Yes | 0
VD-9001-204A-DWG-105 | 3 | PF & LD Arrangement FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-08-08 19:57 | 2016-08-30 16:35 |  | No | 22 |  | 2016-09-25 16:29 | [6 empty] | 2016-09-25 18:56 | Yes | 0 | 1204-Owner-v | 2019-04-06 16:02
VD-9001-254-PCJ-602 | 1 | BOILER PERFORMANCE TEST PROCEDURE | HM-254 | AZAR AB | 2016-08-08 19:58 | 2016-08-08 09:32 |  | No | 0 | 2016-08-14 14:39 | [7 empty] | 2016-08-14 19:57 | Yes | 0
VD-9001-204A-DWG-075 | 3 | PF & LD Arrangement FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-08-09 19:57 | 2016-08-31 16:36 |  | No | 22 |  | 2016-09-04 17:26 | [6 empty] | 2016-09-04 19:57 | Yes | 0
VD-9001-204A-DWG-074 | 2 | PF & LD Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-08-09 19:57 | 2016-08-31 16:37 |  | No | 22 | 2016-10-10 11:42 | [7 empty] | 2016-10-10 18:55 | Yes | 0
VD-9001-204B-DWG-003 | 2 | General Arrangment Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-08-09 19:58 | 2016-10-05 12:09 |  | No | 57 |  | 2016-10-19 09:50 | [6 empty] | 2016-10-19 20:00 | Yes | 0 | 1204-Owner-v | 2018-12-02 09:09
VD-9001-204B-DWG-012 | 2 | Body Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-08-09 19:58 | 2016-08-21 08:21 |  | No | 12 |  | 2016-09-03 09:16 | [6 empty] | 2016-09-03 19:56 | Yes | 0
VD-9001-105-PCJ-501 | 1 | Hydrostatic test procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-08-13 17:28 | 2016-08-13 17:29 | Yes | 17 |  | 2016-09-01 11:42 | [6 empty] | 2016-09-01 19:56 | Yes | 5
VD-9001-105-PCJ-503 | 1 | Hydrostatic and leak test procedure for piping | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-07-28 07:24 | 2016-07-28 07:25 | Yes | 1 |  | 2016-08-13 16:40 | [6 empty] | 2016-08-13 19:57 | Yes | 2
VD-9001-105-PCJ-502 | 1 | Leak test procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-08-13 17:29 |  | No | 17 | 2016-08-16 10:48 | [7 empty] | 2016-08-16 19:57 | Yes | 0
VD-9001-105-PCJ-504 | 1 | Heat treatment procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-07-28 07:33 | 2016-07-28 07:34 | Yes | 1 |  | 2016-08-10 16:12 | [6 empty] | 2016-08-10 19:57 | Yes | -1
VD-9001-105-PCJ-505 | 1 | Pickling & Passivating procedure for S.S surfaces | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-08-13 17:29 |  | No | 17 | 2016-08-16 10:44 | [7 empty] | 2016-08-16 19:57 | Yes | 0
VD-9001-105-PCJ-506 | 1 | Repair welding procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-09-21 10:34 | 2016-09-21 10:35 | Yes | 56 |  | 2016-11-19 15:17 | [6 empty] | 2016-11-19 20:00 | Yes | 45
VD-9001-105-PCJ-511 | 1 | Expanding procedure for heat exchangers tubes | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-09-03 17:32 | 2016-09-03 17:33 | Yes | 38 |  | 2016-10-02 16:42 | [6 empty] | 2016-10-02 18:56 | Yes | 15
VD-9001-105-DWG-301 | 3 | Piping general arrangement and tie-point list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-27 | 2016-07-28 06:12 | 2016-07-28 06:13 | Yes | 1 |  | 2016-08-08 16:40 | [6 empty] | 2016-08-08 19:57 | Yes | -3 | 1204-Owner-v | 2018-06-23 14:49
VD-9001-231A-WMP-009 | 2 | WELDING BOOK (WPS & PQR) | PV-231A | Tarh Mechanic Gostar | 2016-08-10 19:57 | 2016-11-12 15:55 | 2016-11-12 15:56 | Yes | 94 |  | 2017-01-01 16:55 | [6 empty] | 2017-01-01 19:59 | Yes | 36
VD-9001-206B-ITP-004 | 2 | INSPECTION AND TEST PLAN | PV-206B | TASHA | 2016-08-10 19:57 | 2016-08-03 12:50 | 2016-08-03 12:50 | Yes | -7 |  | 2016-08-21 09:29 | [6 empty] | 2016-08-21 19:57 | Yes | 4 | 1204-Owner-v | 2020-01-01 12:54
VD-9001-231A-PCJ-005 | 1 | BLASTING & PAINTING PROCEDURE | PV-231A | Tarh Mechanic Gostar | 2016-08-10 19:57 | 2016-11-12 15:51 | 2016-11-12 15:52 | Yes | 94 |  | 2016-12-28 09:09 | [6 empty] | 2016-12-28 19:59 | Yes | 32
VD-9001-105-DIG-204 | 2 | Outline diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-07-31 08:49 | 2016-07-31 18:26 |  | No | 0 | 2016-08-09 11:52 | [7 empty] | 2016-08-09 19:57 | Yes | 0
VD-9001-108-DWG-020 | 5 | COLUMNS DEATAIL | PR-108 | Farabard | 2016-08-01 11:25 | 2016-08-01 15:50 | 2016-08-01 15:46 | Yes | 0 |  | 2016-08-02 11:43 | [6 empty] | 2016-08-02 19:57 | Yes | -13
VD-9001-213B-CAL-003 | 2 | Roof Structure Lifting Calculation for Erection. For Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-08-01 15:20 | 2016-08-07 15:25 | 2016-08-07 15:26 | Yes | 6 |  | 2016-08-22 11:23 | [6 empty] | 2016-08-22 19:57 | Yes | 1
VD-9001-204B-DWG-001 | 2 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-08-15 19:57 | 2016-08-15 09:14 |  | No | 0 | 2016-09-03 16:26 | [7 empty] | 2016-09-03 19:56 | Yes | 0
VD-9001-108-DWG-021 | 5 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2016-08-16 19:57 | 2016-11-27 09:49 |  | No | 103 |  | 2016-11-27 12:06 | [6 empty] | 2016-11-27 20:00 | Yes | 0
VD-9001-253(A)-DWG-002 | 7 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2016-08-03 | 2016-08-08 16:50 |  | No | 5 | 2016-09-11 15:02 | [7 empty] | 2016-09-11 19:56 | Yes | 0 | 1204-Owner-v | 2018-06-19 09:35
VD-9001-253(A)-DSH-017 | 2 | MOTOR GENERAL ARRANGEMENT DWG. For 2001 | HM-253A | FATEH SANAT KIMIA | 2016-08-03 | 2017-05-22 09:57 | 2017-05-22 09:58 | Yes | 292 |  | 2017-06-13 16:27 | [6 empty] | 2017-06-13 20:00 | Yes | 8 | 1204-Owner-v | 2018-01-19 14:15
VD-9001-253(A)-DSH-047 | 2 | MOTOR GENERAL ARRANGEMENT DWG. For 3001 | HM-253A | FATEH SANAT KIMIA | 2016-08-03 | 2017-05-22 09:58 | 2017-05-22 09:59 | Yes | 292 |  | 2017-06-13 16:31 | [6 empty] | 2017-06-13 20:00 | Yes | 8 | 1204-Owner-v | 2019-02-14 10:33
VD-9001-204A-DWG-144 | 2 | PF & LD Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-08-17 19:57 | 2016-08-10 15:54 |  | No | -7 |  | 2016-10-05 10:15 | [6 empty] | 2016-10-05 18:55 | Yes | 0
VD-9001-204B-DWG-011 | 2 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-08-17 19:57 | 2016-08-21 10:56 |  | No | 4 |  | 2016-09-03 11:21 | [6 empty] | 2016-09-03 19:56 | Yes | 0
VD-9001-204B-CAL-002 | 3 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2016-08-17 19:57 | 2016-08-14 10:39 |  | No | -3 | 2016-08-24 10:47 | [7 empty] | 2016-08-24 19:57 | Yes | 0
VD-9001-253(A)-DSH-046 | 5 | MOTOR DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2016-08-06 | 2017-05-13 14:57 | 2017-05-13 14:58 | Yes | 280 |  | 2017-05-15 15:11 | [6 empty] | 2017-05-15 20:00 | Yes | -12 | 1204-Owner-v | 2018-01-19 14:16
VD-9001-253(A)-DSH-076 | 5 | MOTOR DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-06 | 2017-05-13 14:59 | 2017-05-13 15:00 | Yes | 280 |  | 2017-05-15 15:17 | [6 empty] | 2017-05-15 20:00 | Yes | -12 | 1204-Owner-v | 2019-03-10 14:35
VD-9001-206B-PCJ-033 | 0 | N2 FILLING PROCEDURE | PV-206B | TASHA | 2016-08-06 | 2016-08-07 08:02 |  | No | 1 | 2016-08-20 10:38 | [7 empty] | 2016-08-20 19:57 | Yes | 0
VD-9001-253(A)-DSH-077 | 2 | MOTOR GENERAL ARRANGEMENT DWG. For 3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-06 | 2017-05-22 09:59 | 2017-05-22 10:00 | Yes | 289 |  | 2017-06-13 16:29 | [6 empty] | 2017-06-13 20:00 | Yes | 8 | 1204-Owner-v | 2019-04-16 15:55
VD-9001-253(A)-DSH-016 | 5 | MOTOR DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-08-06 | 2017-05-13 14:47 | 2017-05-13 14:48 | Yes | 280 |  | 2017-05-15 15:06 | [6 empty] | 2017-05-15 20:00 | Yes | -12 | 1204-Owner-v | 2018-01-19 14:13
VD-9001-204A-CAL-130 | 2 | Strength Calculation FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-08-20 19:57 | 2016-10-02 17:31 |  | No | 43 |  | 2016-10-05 10:40 | [6 empty] | 2016-10-05 18:55 | Yes | 0
VD-9001-204A-DWG-154 | 2 | PF & LD Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-08-20 19:57 | 2016-08-11 09:28 |  | No | -9 |  | 2016-09-17 17:33 | [6 empty] | 2016-09-17 19:56 | Yes | 0 | 1204-Owner-v | 2018-12-22 16:41
VD-9001-206B-CAL-001 | 4 | MECHANICAL CALCULATION BOOK -T-1001 | PV-206B | TASHA | 2016-08-07 10:51 | 2016-08-10 15:45 | 2016-08-10 15:46 | Yes | 3 |  | 2016-10-04 11:33 | [6 empty] | 2016-10-04 18:56 | Yes | 41 | 1204-Owner-v | 2018-01-22 11:03
VD-9001-206B-CAL-004 | 2 | LIFTING/TAILING LUG CALCULATION-T-1001 | PV-206B | TASHA | 2016-08-07 10:51 | 2016-08-10 15:45 | 2016-08-10 15:46 | Yes | 3 |  | 2016-10-04 11:42 | [6 empty] | 2016-10-04 18:56 | Yes | 41
VD-9001-206B-DWG-011 | 4 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-08-07 10:52 | 2016-08-08 15:12 |  | No | 1 |  | 2016-10-04 11:28 | [6 empty] | 2016-10-04 18:56 | Yes | 0
VD-9001-206B-DWG-014 | 2 | INTERNAL ATTACHMENT DRAWING -T-1001 | PV-206B | TASHA | 2016-08-07 10:52 | 2016-08-10 15:47 | 2016-08-10 15:48 | Yes | 3 |  | 2016-11-01 09:29 | [6 empty] | 2016-11-01 19:59 | Yes | 69 | 1204-Owner-v | 2018-01-03 16:04
VD-9001-206B-DWG-017 | 2 | TOP DAVIT DRAWING -T-1001 | PV-206B | TASHA | 2016-08-07 10:52 | 2016-08-10 15:47 | 2016-08-10 15:48 | Yes | 3 |  | 2016-10-04 11:51 | [6 empty] | 2016-10-04 18:56 | Yes | 41 | 1204-Owner-v | 2019-05-13 18:21
VD-9001-206B-DWG-041 | 4 | GENERAL ARRANGMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-08-07 10:53 | 2016-08-20 09:58 | 2016-08-20 09:59 | Yes | 13 |  | 2016-08-28 12:09 | [6 empty] | 2016-08-28 19:56 | Yes | -6 | 1204-Owner-v | 2018-08-09 11:42
VD-9001-206B-DWG-071 | 4 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2016-08-07 10:53 | 2016-10-18 10:24 | 2016-10-18 10:25 | Yes | 72 |  | 2016-11-01 09:10 | [6 empty] | 2016-11-01 19:59 | Yes | 0 | 1204-Owner-v | 2019-06-22 13:19
VD-9001-206B-DWG-047 | 1 | TOP DAVIT DRAWING -T-2001 | PV-206B | TASHA | 2016-08-08 11:43 | 2016-08-08 15:08 | 2016-08-08 15:09 | Yes | 0 |  | 2016-08-21 09:35 | [6 empty] | 2016-08-21 19:57 | Yes | -1 | 1204-Owner-v | 2019-05-13 18:21
VD-9001-206B-DWG-077 | 1 | TOP DAVIT DRAWING -T-4001 | PV-206B | TASHA | 2016-08-08 11:44 | 2016-08-08 15:09 | 2016-08-08 15:10 | Yes | 0 |  | 2016-08-21 09:31 | [6 empty] | 2016-08-21 19:57 | Yes | -1 | 1204-Owner-v | 2019-05-13 18:21
VD-9001-206B-DWG-044 | 2 | INTERNAL ATTACHMENT DRAWING -T-2001 | PV-206B | TASHA | 2016-08-08 11:44 | 2016-08-08 14:04 | 2016-08-08 14:05 | Yes | 0 |  | 2016-10-25 10:40 | [6 empty] | 2016-10-25 20:00 | Yes | 64 | 1204-Owner-v | 2019-04-09 14:59
VD-9001-206B-DWG-045 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-2001 | PV-206B | TASHA | 2016-08-08 11:44 | 2016-08-08 14:05 | 2016-08-08 14:06 | Yes | 0 |  | 2016-09-17 09:17 | [6 empty] | 2016-09-17 19:56 | Yes | 26 | 1204-Owner-v | 2018-11-19 13:46
VD-9001-206B-DWG-042 | 2 | BODY & SUPPORT DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2016-08-08 11:44 | 2016-08-08 14:03 | 2016-08-08 14:04 | Yes | 0 |  | 2016-09-17 09:22 | [6 empty] | 2016-09-17 19:56 | Yes | 26 | 1204-Owner-v | 2019-04-09 15:02
VD-9001-105-DIG-206 | 5 | Instrument process and air piping hook-up | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-08 | 2017-09-29 07:26 | 2017-09-29 07:27 | Yes | 417 |  | 2017-10-11 08:06 | [6 empty] | 2017-10-11 20:00 | Yes | -2 | 1204-Owner-v | 2019-01-07 08:22
VD-9001-105-MAL-201 | 2 | Instrument installation bill of material | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-08 | 2017-09-29 07:27 | 2017-09-29 07:28 | Yes | 417 |  | 2017-10-11 08:09 | [6 empty] | 2017-10-11 20:00 | Yes | -2 | 1204-Owner-v | 2019-01-04 21:24
VD-9001-105-ISO-301 | 2 | Piping isometric | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-08 | 2016-08-29 13:18 | 2016-08-29 13:19 | Yes | 21 |  | 2016-10-02 16:32 | [6 empty] | 2016-10-02 18:56 | Yes | 20 | 1204-Owner-v | 2019-01-04 21:16
VD-9001-105-DIG-204 | 3 | Outline diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-09 | 2016-08-11 13:04 | 2016-08-11 13:05 | Yes | 2 |  | 2016-08-16 10:40 | [6 empty] | 2016-08-16 19:57 | Yes | -9 | 1204-Owner-v | 2018-06-23 14:46
VD-9001-204B-DWG-016 | 2 | Nozzle Detail Drawing D-3007 * | PV-204B | ABAN AIR COOLER. | 2016-08-24 19:57 | 2016-08-28 09:18 | 2016-08-28 09:19 | Yes | 4 |  | 2016-09-07 16:43 | [6 empty] | 2016-09-07 19:56 | Yes | -4 | 1204-Owner-v | 2018-08-29 09:57
VD-9001-204B-DWG-014 | 2 | Nozzle Detail Drawing D-1003 * | PV-204B | ABAN AIR COOLER. | 2016-08-24 19:57 | 2016-08-28 09:14 |  | No | 4 | 2016-09-10 14:42 | [7 empty] | 2016-09-10 19:56 | Yes | 0
VD-9001-214A-ITP-001 | 1 | Inspection and test plan for Breather Valve | PV-214A | TANKTECH KSPC | 2016-08-11 | 2016-08-12 10:22 | 2016-08-12 10:23 | Yes | 1 |  | 2016-08-28 10:33 | [6 empty] | 2016-08-28 19:56 | Yes | 2
VD-9001-214A-ITP-002 | 1 | Inspection and test plan for Rim Vent | PV-214A | TANKTECH KSPC | 2016-08-11 | 2016-08-12 10:23 | 2016-08-12 10:24 | Yes | 1 |  | 2016-08-28 10:35 | [6 empty] | 2016-08-28 19:56 | Yes | 2
VD-9001-214A-ITP-003 | 1 | Inspection and test plan for Emergency Vent | PV-214A | TANKTECH KSPC | 2016-08-11 | 2016-08-12 10:24 | 2016-08-12 10:25 | Yes | 1 |  | 2016-08-28 10:37 | [6 empty] | 2016-08-28 19:56 | Yes | 2
VD-9001-214A-CSH-001 | 1 | Breather valves/Emergency sizing calculations | PV-214A | TANKTECH KSPC | 2016-08-11 | 2016-08-18 07:24 | 2016-08-18 07:25 | Yes | 7 |  | 2016-08-28 11:19 | [6 empty] | 2016-08-28 19:56 | Yes | -4
VD-9001-214A-DWG-005 | 1 | Dimensional and weight Drawings for Tag No TK-7201 | PV-214A | TANKTECH KSPC | 2016-08-12 | 2016-08-15 13:12 | 2016-08-15 13:13 | Yes | 3 |  | 2016-08-28 11:02 | [6 empty] | 2016-08-28 19:56 | Yes | -1
VD-9001-214A-DWG-006 | 1 | Name plat drawing for Tag No TK-7201 | PV-214A | TANKTECH KSPC | 2016-08-12 | 2016-08-15 13:12 | 2016-08-15 13:13 | Yes | 3 |  | 2016-08-28 10:41 | [6 empty] | 2016-08-28 19:56 | Yes | -1
VD-9001-214A-DWG-001 | 1 | Dimensional and weight Drawings for Tag No TK-7101A | PV-214A | TANKTECH KSPC | 2016-08-12 | 2016-08-15 13:01 | 2016-08-15 13:02 | Yes | 3 |  | 2016-08-28 10:54 | [6 empty] | 2016-08-28 19:56 | Yes | -1
VD-9001-214A-DWG-003 | 1 | Dimensional and weight Drawings for Tag No TK-7101B | PV-214A | TANKTECH KSPC | 2016-08-12 | 2016-08-15 13:02 | 2016-08-15 13:03 | Yes | 3 |  | 2016-08-28 11:00 | [6 empty] | 2016-08-28 19:56 | Yes | -1
VD-9001-214A-LST-001 | 1 | Spare Part List for start up | PV-214A | TANKTECH KSPC | 2016-08-12 | 2016-08-16 16:45 |  | No | 4 | 2016-08-28 14:50 | [7 empty] | 2016-08-28 19:57 | Yes | 0
VD-9001-204A-DWG-145 | 2 | PF & LD Arrangement FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-08-13 10:36 | 2016-08-27 07:30 |  | No | 14 |  | 2016-09-17 09:59 | [6 empty] | 2016-09-17 19:56 | Yes | 0
VD-9001-204A-DWG-155 | 2 | PF & LD Arrangement FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-08-13 10:36 | 2016-08-27 07:31 |  | No | 14 |  | 2016-09-17 17:30 | [6 empty] | 2016-09-17 19:56 | Yes | 0
VD-9001-203-DWG-020 | 3 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-27 19:57 | 2016-08-20 12:02 |  | No | -7 |  | 2016-08-21 10:17 | [6 empty] | 2016-08-21 19:57 | Yes | 0
VD-9001-203-DWG-011 | 2 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-27 19:57 | 2016-08-22 11:42 |  | No | -5 | 2016-09-06 12:10 | [7 empty] | 2016-09-06 19:56 | Yes | 0
VD-9001-203-CAL-008 | 1 | Lifting Calculation | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-27 19:57 | 2016-09-03 14:28 |  | No | 7 | 2016-10-02 13:16 | [7 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-203-DWG-016 | 1 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-27 19:57 | 2016-09-18 15:54 |  | No | 22 |  | 2016-10-09 15:26 | [6 empty] | 2016-10-09 18:56 | Yes | 0
VD-9001-203-CAL-007 | 3 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-27 19:57 | 2016-08-22 16:12 |  | No | -5 | 2016-09-07 09:03 | [7 empty] | 2016-09-07 19:56 | Yes | 0
VD-9001-108-CAL-001 | 2 | STRUCTURE CALCULATION SHEET | PR-108 | Farabard | 2016-08-14 11:17 | 2017-10-30 12:50 |  | No | 442 | 2017-11-07 12:06 | [7 empty] | 2017-11-07 19:59 | Yes | 0
VD-9001-108-CAL-002 | 3 | COOLING TOWER AND EQUIPMENTS CALCULATION & PERFORMANC CURVES BOOKLET | PR-108 | Farabard | 2016-08-14 11:17 | 2017-02-15 15:20 |  | No | 185 | 2017-03-07 14:52 | [7 empty] | 2017-03-07 19:59 | Yes | 0
VD-9001-108-DBS-006 | 5 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2016-08-14 11:17 | 2017-01-14 13:37 |  | No | 153 | 2017-12-04 14:31 | [7 empty] | 2017-12-04 20:00 | Yes | 0
VD-9001-108-DSH-007 | 4 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2016-08-14 11:18 | 2017-02-15 15:20 |  | No | 185 | 2017-08-05 15:48 | [7 empty] | 2017-08-05 19:58 | Yes | 0
VD-9001-108-DSH-008 | 3 | FAN PACKAGE DATA SHEET | PR-108 | Farabard | 2016-08-14 11:18 | 2017-02-15 15:28 |  | No | 185 | 2017-08-05 16:11 | [7 empty] | 2017-08-05 19:59 | Yes | 0
VD-9001-108-DSH-009 | 3 | GEAR REDUCER DATA SHEET | PR-108 | Farabard | 2016-08-14 11:18 | 2017-02-15 15:31 |  | No | 185 | 2017-03-07 15:18 | [7 empty] | 2017-03-07 19:59 | Yes | 0
VD-9001-108-DSH-010 | 4 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2016-08-14 11:18 | 2017-02-16 10:47 |  | No | 186 | 2017-08-05 16:00 | [7 empty] | 2017-08-05 19:59 | Yes | 0
VD-9001-108-DWG-016 | 7 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2016-08-14 11:18 | 2017-10-31 14:11 |  | No | 443 | 2017-11-13 16:20 | [7 empty] | 2017-11-13 19:59 | Yes | 0
VD-9001-108-DWG-031 | 2 | INTERNAL ARRANGMENT | PR-108 | Farabard | 2016-08-14 11:18 | 2017-02-16 10:48 | 2017-02-16 10:49 | Yes | 186 | 2017-03-08 12:21 | 2017-08-02 14:51 | [6 empty] | 2017-08-02 19:58 | Yes | 6
VD-9001-108-DWG-032 | 2 | PACKING ARRENGMANT | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 10:48 | 2017-02-16 10:49 | Yes | 186 | 2017-03-08 17:11 | 2017-08-02 15:00 | [6 empty] | 2017-08-02 19:58 | Yes | 6
VD-9001-108-DWG-033 | 2 | DRIFT ELIMINATOR ARRANGMENT | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 10:49 | 2017-02-16 10:50 | Yes | 186 | 2017-03-08 12:08 | 2017-08-02 11:57 | [6 empty] | 2017-08-02 19:58 | Yes | 6
VD-9001-108-DWG-034 | 2 | WATER DISTERIBUTION SYSTEM | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 10:49 | 2017-02-16 10:50 | Yes | 186 |  | 2017-04-24 11:34 | [6 empty] | 2017-04-24 20:59 | Yes | 53
VD-9001-108-DWG-035 | 3 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 11:26 |  | No | 186 | 2017-09-16 12:06 | [7 empty] | 2017-09-16 19:57 | Yes | 0
VD-9001-108-DWG-040 | 1 | DRIVE SHAFT DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 11:40 | 2017-02-16 11:41 | Yes | 186 |  | 2017-03-07 16:21 | [6 empty] | 2017-03-07 20:00 | Yes | 5
VD-9001-108-DWG-041 | 2 | GEAR REDUCER & ELECTRO MOTOR BASE PLATE DETAIL | PR-108 | Farabard | 2016-08-14 11:19 | 2017-02-16 11:46 | 2017-02-16 11:47 | Yes | 186 |  | 2017-03-07 15:38 | [6 empty] | 2017-03-07 19:59 | Yes | 5
VD-9001-108-DIG-046 | 1 | CAUSE AND EFFECT DIAGRAM | PR-108 | Farabard | 2016-08-14 11:19 | 2017-11-30 13:54 |  | No | 473 | 2017-12-09 14:15 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-108-LST-047 | 5 | LOAD LIST | PR-108 | Farabard | 2016-08-14 11:20 | 2017-01-28 11:29 |  | No | 167 | 2017-08-05 15:19 | [7 empty] | 2017-08-05 19:58 | Yes | 0
VD-9001-108-MDL-054 | 5 | GENERAL INDEX | PR-108 | Farabard | 2016-08-14 11:20 | 2017-06-01 12:01 |  | No | 291 | 2017-09-02 17:09 | [7 empty] | 2017-09-02 19:58 | Yes | 0
VD-9001-108-MNL-057 | 3 | ISTALLATION MANUAL | PR-108 | Farabard | 2016-08-14 11:20 | 2017-01-15 13:26 |  | No | 154 |  | 2017-03-11 11:10 | [6 empty] | 2017-03-11 20:00 | Yes | 0
VD-9001-108-MNL-058 | 3 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2016-08-14 11:20 | 2017-01-15 13:27 |  | No | 154 | 2017-03-11 11:23 | [7 empty] | 2017-03-11 20:00 | Yes | 0
VD-9001-108-MTO-059 | 3 | MATRIAL TAKE OFF (INTERNALS) | PR-108 | Farabard | 2016-08-14 11:20 | 2017-10-30 14:24 | 2017-10-30 14:25 | Yes | 442 |  | 2017-11-11 10:44 | [6 empty] | 2017-11-11 19:59 | Yes | -2
VD-9001-108-PCJ-064 | 4 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2016-08-14 11:20 | 2017-01-17 08:58 |  | No | 156 | 2017-08-05 15:08 | [7 empty] | 2017-08-05 19:58 | Yes | 0
VD-9001-203-DWG-013 | 2 | Detail of Manhole Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-28 19:57 | 2016-08-22 11:44 |  | No | -6 | 2016-09-13 11:06 | [7 empty] | 2016-09-13 19:56 | Yes | 0
VD-9001-203-DWG-015 | 2 | Detail of Saddle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-28 19:57 | 2016-08-22 11:44 |  | No | -6 |  | 2016-09-07 09:18 | [6 empty] | 2016-09-07 19:56 | Yes | 0
VD-9001-254-DSH-562 | 2 | DATA SHEET FOR DESUPERHEATER & SPRAY WATER CONTROL VALVE | HM-254 | AZAR AB | 2016-08-28 19:57 |  |  | No | 1391 | [9 empty] | No | 0
VD-9001-254-PCJ-602 | 2 | BOILER PERFORMANCE TEST PROCEDURE | HM-254 | AZAR AB | 2016-08-28 19:57 | 2016-09-07 11:04 | 2016-09-07 11:05 | Yes | 10 |  | 2016-11-08 09:48 | [6 empty] | 2016-11-08 19:59 | Yes | 47 | 1204-Owner-v | 2018-09-09 10:33
VD-9001-105-PCJ-505 | 2 | Pickling & Passivating procedure for S.S surfaces | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-16 | 2016-08-26 16:39 | 2016-08-26 16:40 | Yes | 10 |  | 2016-09-06 17:01 | [6 empty] | 2016-09-06 19:56 | Yes | -3 | 1204-Owner-v | 2019-07-06 13:35
VD-9001-105-PCJ-502 | 2 | Leak test procedure for pressure vessels and heat exchangers | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-08-16 | 2016-08-26 16:38 | 2016-08-26 16:39 | Yes | 10 |  | 2016-10-01 15:09 | [6 empty] | 2016-10-01 18:56 | Yes | 22 | 1204-Owner-v | 2019-09-06 22:05
VD-9001-253(A)-DWG-011 | 3 | HEADER WALK WAY for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-08-16 | 2016-10-10 11:31 | 2016-10-10 11:32 | Yes | 55 |  | 2016-12-12 08:06 | [6 empty] | 2016-12-12 19:59 | Yes | 49 | 1204-Owner-v | 2018-08-14 17:21
VD-9001-205A-DWG-066 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-11-14 12:11 | 2016-11-14 12:12 | Yes | 821 |  | 2016-12-28 15:18 | [6 empty] | 2016-12-28 19:59 | Yes | 30
VD-9001-205A-DWG-067 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 11:22 |  | No | 733 |  | 2016-12-13 09:17 | [6 empty] | 2016-12-13 19:59 | Yes | 0
VD-9001-205A-DWG-068 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 11:25 |  | No | 733 | 2016-12-13 09:35 | [7 empty] | 2016-12-13 19:59 | Yes | 0
VD-9001-205A-CAL-069 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2017-04-05 16:35 | 2017-04-05 16:36 | Yes | 963 |  | 2017-04-10 09:38 | [6 empty] | 2017-04-10 20:59 | Yes | -9
VD-9001-205A-DWG-070 | 0 | GENERAL ARRANGEMENT DRAWING FOR OF D-1002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 10:49 | 2016-08-18 10:50 | Yes | 733 |  | 2016-12-28 14:52 | [6 empty] | 2016-12-28 19:59 | Yes | 118
VD-9001-205A-DWG-071 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 10:50 |  | No | 733 | 2016-09-28 10:51 | [7 empty] | 2016-09-28 18:56 | Yes | 0
VD-9001-205A-DWG-072 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-1002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 10:54 | 2016-08-18 10:55 | Yes | 733 |  | 2016-09-28 10:59 | [6 empty] | 2016-09-28 18:56 | Yes | 27
VD-9001-205A-CAL-073 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-1002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2017-04-05 16:37 | 2017-04-05 16:38 | Yes | 963 |  | 2017-04-10 09:41 | [6 empty] | 2017-04-10 20:59 | Yes | -9
VD-9001-205A-DWG-074 | 0 | GENERAL ARRANGEMENT DRAWING FOR D-1003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 11:06 | 2016-08-18 11:07 | Yes | 733 |  | 2016-12-28 14:56 | [6 empty] | 2016-12-28 19:59 | Yes | 118
VD-9001-205A-DWG-075 | 0 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 11:07 |  | No | 733 | 2016-09-28 10:55 | [7 empty] | 2016-09-28 18:56 | Yes | 0
VD-9001-205A-DWG-076 | 0 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-1003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2016-08-18 11:07 | 2016-08-18 11:08 | Yes | 733 |  | 2016-09-28 10:57 | [6 empty] | 2016-09-28 18:56 | Yes | 27
VD-9001-205A-CAL-077 | 0 | MECHANICAL CALCULATION FOR INTERNALS OF D-1003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2014-08-16 | 2017-04-05 16:39 | 2017-04-05 16:40 | Yes | 963 |  | 2017-04-10 09:44 | [6 empty] | 2017-04-10 20:59 | Yes | -9
VD-9001-204B-DWG-009 | 2 | Body Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-08-17 10:08 | 2016-08-17 13:49 | 2016-08-17 13:50 | Yes | 0 |  | 2016-08-22 17:01 | [6 empty] | 2016-08-22 19:57 | Yes | -9 | 1204-Owner-v | 2018-07-13 00:26
VD-9001-254-LST-346 | 2 | INSTRUMENT LIST | HM-254 | AZAR AB | 2016-08-31 19:57 |  |  | No | 1388 | [9 empty] | No | 0
VD-9001-204B-DWG-010 | 3 | Body Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-08-20 | 2016-09-21 11:44 | 2016-09-21 11:45 | Yes | 32 |  | 2016-09-25 15:01 | [6 empty] | 2016-09-25 18:56 | Yes | -10 | 1204-Owner-v | 2018-12-02 09:39
VD-9001-206B-PCJ-033 | 1 | N2 FILLING PROCEDURE | PV-206B | TASHA | 2016-09-03 19:57 | 2016-11-02 08:36 | 2016-11-02 08:36 | Yes | 60 |  | 2016-12-28 09:27 | [6 empty] | 2016-12-28 19:59 | Yes | 42 | 1204-Owner-v | 2018-08-13 12:58
VD-9001-253(A)-DWG-071 | 2 | HEADER WALK WAY for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-21 09:36 | 2016-08-21 11:21 | 2016-08-21 11:19 | Yes | 0 |  | 2016-09-11 15:22 | [6 empty] | 2016-09-11 19:56 | Yes | 7 | 1204-Owner-v | 2019-04-09 16:09
VD-9001-253(A)-DWG-075 | 1 | GRATING DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-21 09:36 | 2016-08-21 11:54 |  | No | 0 |  | 2016-08-23 14:52 | [6 empty] | 2016-08-23 19:57 | Yes | 0
VD-9001-253(A)-DWG-087 | 2 | MOTOR WALKWAY GRATING DETAIL AE-3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-21 09:37 | 2016-08-21 11:54 | 2016-08-21 11:55 | Yes | 0 |  | 2016-08-23 14:13 | [6 empty] | 2016-08-23 19:57 | Yes | -12 | 1204-Owner-v | 2018-01-03 16:00
VD-9001-203-ITP-003 | 2 | Inspection Test Plan | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-04 19:57 | 2016-08-27 17:22 | 2016-08-27 17:23 | Yes | -8 |  | 2016-09-04 07:55 | [6 empty] | 2016-09-04 19:56 | Yes | -6
VD-9001-203-DWG-012 | 2 | Shell Araangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-04 19:57 | 2016-08-22 11:43 |  | No | -13 |  | 2016-09-04 08:13 | [6 empty] | 2016-09-04 19:56 | Yes | 0
VD-9001-203-WBK-030 | 1 | Welding Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-05 19:57 | 2016-09-10 17:13 | 2016-09-10 17:14 | Yes | 5 |  | 2016-09-17 08:53 | [6 empty] | 2016-09-17 19:56 | Yes | -7
VD-9001-108-DSH-015 | 3 | VIBRATION SWITCH DATA SHEET | PR-108 | Farabard | 2016-09-05 19:57 | 2017-07-04 14:35 |  | No | 302 | 2017-08-05 16:38 | [7 empty] | 2017-08-05 19:59 | Yes | 0
VD-9001-253(A)-PCJ-112 | 2 | REPAIR PROCEDURE | HM-253A | FATEH SANAT KIMIA | 2016-08-23 | 2017-03-13 14:39 | 2017-03-13 14:40 | Yes | 202 |  | 2017-03-14 11:21 | [6 empty] | 2017-03-14 20:00 | Yes | -13
VD-9001-204B-DWG-013 | 2 | Nozzle Detail Drawing D-1002 * | PV-204B | ABAN AIR COOLER. | 2016-08-23 | 2016-08-28 11:24 |  | No | 5 | 2016-09-07 17:12 | [7 empty] | 2016-09-07 19:56 | Yes | 0
VD-9001-203-NPL-031 | 1 | NDT Map | PV-203 | Masnout Felezi Sangin (MFS) | 2016-08-24 10:18 | 2016-08-24 10:50 | 2016-08-24 10:51 | Yes | 0 |  | 2016-09-04 07:50 | [6 empty] | 2016-09-04 19:56 | Yes | -3
VD-9001-204B-CAL-002 | 4 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2016-08-24 | 2016-08-29 09:16 | 2016-08-29 09:17 | Yes | 5 |  | 2016-08-30 11:02 | [6 empty] | 2016-08-30 19:56 | Yes | -13
VD-9001-204B-CAL-004 | 3 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2016-08-24 | 2016-08-27 13:41 | 2016-08-27 13:42 | Yes | 3 |  | 2016-08-27 15:11 | [6 empty] | 2016-08-27 19:57 | Yes | -14
VD-9001-204B-CAL-003 | 3 | Strength Calculation Book D-3006 | PV-204B | ABAN AIR COOLER. | 2016-08-24 | 2016-08-28 12:45 | 2016-08-28 12:46 | Yes | 4 |  | 2016-08-28 14:34 | [6 empty] | 2016-08-28 19:57 | Yes | -14
VD-9001-214A-PCJ-004 | 1 | Painting procedures | PV-214A | TANKTECH KSPC | 2016-08-27 | 2016-08-29 06:39 | 2016-08-29 06:40 | Yes | 2 |  | 2016-09-17 10:16 | [6 empty] | 2016-09-17 19:56 | Yes | 5
VD-9001-206B-PCJ-034 | 0 | PRODUCTION TEST PLATE PROCEDURE | PV-206B | TASHA | 2014-08-27 | 2016-10-03 11:18 |  | No | 768 | 2016-10-25 10:44 | [7 empty] | 2016-10-25 20:00 | Yes | 0
VD-9001-205A-DWG-003 | 6 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-08-27 11:56 | 2016-08-27 14:21 | 2016-08-27 14:22 | Yes | 0 |  | 2016-08-28 11:14 | [6 empty] | 2016-08-28 19:56 | Yes | -13
VD-9001-204A-DWG-022 | 2 | Nozzle Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-09-10 19:56 | 2016-08-30 16:34 |  | No | -11 |  | 2016-09-19 10:58 | [6 empty] | 2016-09-19 19:56 | Yes | 0
VD-9001-214A-LST-001 | 2 | Spare Part List for start up | PV-214A | TANKTECH KSPC | 2016-08-28 | 2016-08-29 06:40 | 2016-08-29 06:41 | Yes | 1 |  | 2016-09-04 17:32 | [6 empty] | 2016-09-04 19:57 | Yes | -8
VD-9001-214A-MNL-001 | 1 | Installation, operating and Mainteance Manuals | PV-214A | TANKTECH KSPC | 2016-08-28 | 2016-08-30 11:21 | 2016-08-30 11:22 | Yes | 2 |  | 2016-09-04 18:57 | [6 empty] | 2016-09-04 19:57 | Yes | -9
VD-9001-206B-DWG-075 | 3 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-4001 | PV-206B | TASHA | 2016-09-11 19:56 | 2016-09-26 08:36 | 2016-09-26 08:36 | Yes | 15 |  | 2016-10-16 17:14 | [6 empty] | 2016-10-16 18:56 | Yes | 6 | 1204-Owner-v | 2018-12-29 10:34
VD-9001-206B-PCJ-015 | 3 | PAINTING PROCEDURE | PV-206B | TASHA | 2016-09-11 19:57 | 2016-09-01 15:15 |  | No | -10 |  | 2016-12-05 16:09 | [6 empty] | 2016-12-05 20:00 | Yes | 0
VD-9001-254-DWG-907 | 1 | FOUNDATION OF CASING | HM-254 | AZAR AB | 2016-09-12 19:56 | 2017-12-11 14:34 |  | No | 455 |  |  |  | 2018-03-28 10:52 |  |  |  |  | 2018-03-28 10:52 | Yes | 0
VD-9001-253(A)-DWG-012 | 3 | NAME PLATE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-08-30 10:33 | 2016-08-30 11:26 | 2016-08-30 11:27 | Yes | 0 |  | 2016-09-11 15:29 | [6 empty] | 2016-09-11 19:56 | Yes | -2
VD-9001-253(A)-DWG-042 | 3 | NAME PLATE for 3001 | HM-253A | FATEH SANAT KIMIA | 2016-08-30 10:34 | 2016-08-30 11:26 | 2016-08-30 11:27 | Yes | 0 |  | 2016-09-11 15:35 | [6 empty] | 2016-09-11 19:56 | Yes | -2 | 1204-Owner-v | 2018-02-03 14:37
VD-9001-253(A)-DWG-072 | 3 | NAME PLATE for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-08-30 10:34 | 2016-08-30 11:26 | 2016-08-30 11:27 | Yes | 0 |  | 2016-09-11 15:32 | [6 empty] | 2016-09-11 19:56 | Yes | -2
VD-9001-204B-DWG-004 | 3 | General Arrangment Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-09-17 19:56 | 2016-09-21 17:39 | 2016-09-21 17:38 | Yes | 4 |  | 2016-10-02 11:13 | [6 empty] | 2016-10-02 18:56 | Yes | -3 | 1204-Owner-v | 2018-08-29 14:04
VD-9001-204B-DWG-001 | 3 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-09-17 19:56 | 2016-10-23 07:54 |  | No | 36 | 2016-11-07 12:28 | [7 empty] | 2016-11-07 19:59 | Yes | 0
VD-9001-105-CAL-501 | 4 | Calculation sheet of Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:35 | 2016-09-04 19:53 | 2016-09-04 19:54 | Yes | 0 |  | 2016-10-02 16:44 | [6 empty] | 2016-10-02 18:56 | Yes | 14 | 1204-Owner-v | 2018-09-26 12:43
VD-9001-105-CAL-502 | 3 | Calculation sheet for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:35 | 2016-09-04 19:55 | 2016-09-04 19:56 | Yes | 0 |  | 2016-10-02 16:46 | [6 empty] | 2016-10-02 18:56 | Yes | 14
VD-9001-105-CAL-503 | 5 | Calculation sheet for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:35 | 2016-09-04 19:59 | 2016-09-04 20:00 | Yes | 0 |  | 2016-10-02 16:47 | [6 empty] | 2016-10-02 18:56 | Yes | 14
VD-9001-105-DWG-501 | 4 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:36 | 2016-09-04 20:00 |  | No | 0 |  | 2016-10-02 16:49 | [6 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-105-DWG-502 | 5 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:36 | 2016-09-04 20:02 |  | No | 0 |  | 2016-10-02 16:50 | [6 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-105-DWG-503 | 4 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-09-04 11:36 | 2016-09-04 20:16 |  | No | 0 |  | 2016-10-02 16:52 | [6 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-204A-DWG-094 | 1 | PF & LD Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-09-19 19:56 | 2016-09-14 07:51 |  | No | -5 |  | 2016-10-10 14:09 | [6 empty] | 2016-10-10 18:55 | Yes | 0
VD-9001-203-DWG-011 | 3 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-20 19:56 | 2016-09-24 11:42 |  | No | 4 | 2016-10-02 13:35 | [7 empty] | 2016-10-02 18:56 | Yes | 0
VD-9001-203-DWG-017 | 2 | Name Plate Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-07 09:26 | 2016-09-24 11:43 |  | No | 17 |  | 2016-09-24 14:24 | [6 empty] | 2016-09-24 18:56 | Yes | 0
VD-9001-203-CAL-007 | 4 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-21 19:56 | 2016-09-10 10:36 |  | No | -11 |  | 2016-09-11 09:58 | [6 empty] | 2016-09-11 19:56 | Yes | 0
VD-9001-204B-DWG-013 | 3 | Nozzle Detail Drawing D-1002 * | PV-204B | ABAN AIR COOLER. | 2016-09-21 19:56 | 2016-11-26 15:05 | 2016-11-26 15:04 | Yes | 66 |  | 2016-12-04 15:01 | [6 empty] | 2016-12-04 20:00 | Yes | -6 | 1204-Owner-v | 2018-08-29 09:55
VD-9001-204B-MSS-001 | 0 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2014-09-10 | 2016-10-16 13:21 |  | No | 767 | 2016-10-19 14:07 | [7 empty] | 2016-10-19 20:00 | Yes | 0
VD-9001-204B-DWG-014 | 3 | Nozzle Detail Drawing D-1003 * | PV-204B | ABAN AIR COOLER. | 2016-09-24 19:56 | 2016-10-29 13:59 | 2016-10-29 14:00 | Yes | 35 |  | 2016-11-23 10:28 | [6 empty] | 2016-11-23 20:00 | Yes | 11 | 1204-Owner-v | 2018-08-29 09:56
VD-9001-253(A)-DWG-002 | 8 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2016-09-11 | 2017-03-13 12:09 | 2017-03-13 12:10 | Yes | 183 |  | 2017-04-09 16:52 | [6 empty] | 2017-04-09 21:00 | Yes | 13 | 1204-Owner-v | 2018-06-18 15:00
VD-9001-253(A)-DWG-008 | 1 | MOTOR SUPPORT for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-09-13 09:01 | 2016-09-13 09:35 | 2016-09-13 09:35 | Yes | 0 |  | 2016-09-25 14:25 | [6 empty] | 2016-09-25 18:56 | Yes | -2 | 1204-Owner-v | 2018-02-03 12:59
VD-9001-253(A)-DWG-038 | 1 | MOTOR SUPPORT for 3001 | HM-253A | FATEH SANAT KIMIA | 2016-09-13 09:01 | 2016-09-13 09:35 | 2016-09-13 09:36 | Yes | 0 |  | 2016-09-25 14:17 | [6 empty] | 2016-09-25 18:56 | Yes | -2 | 1204-Owner-v | 2018-02-03 14:36
VD-9001-253(A)-DWG-068 | 1 | MOTOR SUPPORT for 3002 | HM-253A | FATEH SANAT KIMIA | 2016-09-13 09:02 | 2016-09-13 09:36 | 2016-09-13 09:37 | Yes | 0 |  | 2016-09-25 14:13 | [6 empty] | 2016-09-25 18:56 | Yes | -2 | 1204-Owner-v | 2018-08-14 17:50
VD-9001-254-PID-114 | 5 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2016-09-27 19:56 | 2016-10-10 16:00 | 2016-10-10 16:01 | Yes | 13 |  | 2016-11-29 10:50 | [6 empty] | 2016-11-29 20:00 | Yes | 36 | 1204-Owner-v | 2018-01-27 15:21
VD-9001-203-DWG-013 | 3 | Detail of Manhole Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-09-27 19:56 | 2016-09-18 15:53 | 2016-09-18 15:54 | Yes | -9 |  | 2016-09-24 09:44 | [6 empty] | 2016-09-24 18:56 | Yes | -8
VD-9001-254-PID-115 | 5 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2016-09-27 19:56 | 2019-03-17 15:11 | 2019-03-17 15:11 | Yes | 901 |  |  | 2019-04-30 15:58 | [5 empty] | 2019-04-30 15:58 | Yes | 30 | 1204-Owner-v | 2019-06-15 12:31
VD-9001-254-PID-116 | 5 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2016-09-27 19:56 | 2016-10-10 16:01 | 2016-10-10 16:02 | Yes | 13 |  | 2016-11-07 14:57 | [6 empty] | 2016-11-07 19:59 | Yes | 14 | 1204-Owner-v | 2018-01-27 15:22
VD-9001-254-PID-120 | 5 | COOLING WATER P&I DIAGRAM | HM-254 | AZAR AB | 2016-09-27 19:56 | 2016-10-10 16:00 | 2016-10-10 16:01 | Yes | 13 |  | 2016-11-07 14:55 | [6 empty] | 2016-11-07 19:59 | Yes | 14 | 1204-Owner-v | 2018-03-18 12:58
VD-9001-254-PID-117 | 4 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2016-09-27 19:56 | 2016-10-10 16:02 | 2016-10-10 16:03 | Yes | 13 |  | 2016-11-07 15:01 | [6 empty] | 2016-11-07 19:59 | Yes | 14 | 1204-Owner-v | 2018-01-27 15:23
VD-9001-231A-DWG-010 | 1 | Ladder And Platform Drawing ( 3 - T- 3001 ) | PV-231A | Tarh Mechanic Gostar | 2016-09-17 11:53 | 2016-11-13 13:04 | 2016-11-13 13:05 | Yes | 57 |  | 2016-12-28 15:23 | [6 empty] | 2016-12-28 19:59 | Yes | 31
VD-9001-231A-DWG-011 | 1 | Ladder And Platform Drawing ( 3 - T - 3002 ) | PV-231A | Tarh Mechanic Gostar | 2016-09-17 11:53 | 2016-11-13 13:11 |  | No | 57 | 2017-01-22 09:02 | [7 empty] | 2017-01-22 19:59 | Yes | 0
VD-9001-231A-DWG-012 | 1 | Ladder And Platform Drawing ( 3 - T - 3003 ) | PV-231A | Tarh Mechanic Gostar | 2016-09-17 11:53 | 2016-11-13 13:17 |  | No | 57 | 2017-02-04 16:02 | [7 empty] | 2017-02-04 19:59 | Yes | 0
VD-9001-206B-WBK-021 | 2 | WELDING BOOK (WPS & PQR) | PV-206B | TASHA | 2016-10-01 19:56 | 2016-12-21 08:50 |  | No | 81 | 2017-01-14 10:32 | [7 empty] | 2017-01-14 20:00 | Yes | 0
VD-9001-206B-WMP-022 | 2 | WELDING MAP&NDT TABLE | PV-206B | TASHA | 2016-10-01 19:56 | 2016-12-22 07:59 |  | No | 82 |  | 2017-01-14 10:34 | [6 empty] | 2017-01-14 20:00 | Yes | 0
VD-9001-204B-ITP-001 | 1 | Inspection & Test Plan | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-11-15 12:24 |  | No | 58 | 2018-02-19 09:21 | [7 empty] | 2018-02-19 19:59 | Yes | 0
VD-9001-204B-PCJ-002 | 1 | Magnetic Particle Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-10-10 09:55 |  | No | 22 | 2016-10-19 11:19 | [7 empty] | 2016-10-19 20:00 | Yes | 0
VD-9001-204B-PCJ-003 | 1 | Ultrasonic Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-12-27 10:50 |  | No | 100 | 2017-01-01 08:59 | [7 empty] | 2017-01-01 19:59 | Yes | 0
VD-9001-204B-PCJ-004 | 1 | Liquid Penetrant Examination Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-10-10 14:01 |  | No | 22 | 2016-10-19 11:26 | [7 empty] | 2016-10-19 20:00 | Yes | 0
VD-9001-204B-PCJ-005 | 1 | Radiography Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-12-27 10:49 | 2016-12-27 10:50 | Yes | 100 |  | 2016-12-31 17:36 | [6 empty] | 2016-12-31 19:59 | Yes | -10 | 1204-Owner-v | 2020-04-29 08:39
VD-9001-204B-PCJ-008 | 1 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-18 | 2016-10-26 11:41 |  | No | 38 |  | 2016-11-13 08:53 | [6 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204B-DWG-012 | 3 | Body Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-09-19 10:35 | 2016-11-27 12:40 | 2016-11-27 12:39 | Yes | 69 |  | 2016-12-04 14:47 | [6 empty] | 2016-12-04 20:00 | Yes | -7
VD-9001-204B-PCJ-006 | 1 | Hydrostatic and Air Leak Test Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-21 | 2016-09-24 09:05 |  | No | 3 |  | 2016-11-12 14:19 | [6 empty] | 2016-11-12 20:00 | Yes | 0
VD-9001-204A-SPL-001 | 1 | Spare Part List for Eriction / Pre Commissioning / Start up & Two Years | PV-204A | Asas Sanat Pars Inc. | 2016-09-24 10:06 | 2016-09-24 17:22 | 2016-09-24 17:23 | Yes | 0 |  | 2016-09-27 09:13 | [6 empty] | 2016-09-27 18:56 | Yes | -11 | 1204-Owner-v | 2019-03-07 15:25
VD-9001-204B-CAL-009 | 1 | Transportation Saddle Calculation D-1002 | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-09-26 11:53 |  | No | 2 | 2016-09-27 10:41 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204B-CAL-010 | 1 | Transportation Saddle Calculation D-1003 | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-09-26 11:54 |  | No | 2 | 2016-09-27 10:43 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204B-CAL-011 | 1 | Transportation Saddle Calculation D-3006 | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-09-26 11:54 |  | No | 2 | 2016-09-27 10:46 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204B-CAL-012 | 1 | Transportation Saddle Calculation D-3007 | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-09-26 11:54 |  | No | 2 | 2016-09-27 10:45 | [7 empty] | 2016-09-27 18:56 | Yes | 0
VD-9001-204B-PCJ-007 | 1 | Pickling Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-12-03 10:31 |  | No | 70 | 2016-12-06 16:32 | [7 empty] | 2016-12-06 20:00 | Yes | 0
VD-9001-204B-PCJ-001 | 1 | Repair Procedure | PV-204B | ABAN AIR COOLER. | 2016-09-24 | 2016-11-15 12:23 |  | No | 52 | 2016-11-27 14:11 | [7 empty] | 2016-11-27 20:00 | Yes | 0
VD-9001-203-DWG-010 | 1 | Internal Parts Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-08 18:56 | 2016-09-27 10:35 |  | No | -11 | 2016-10-17 16:46 | [7 empty] | 2016-10-17 18:55 | Yes | 0
VD-9001-253(A)-DWG-028 | 1 | MOTOR WALKWAY GRATING DETAIL AE-2001 | HM-253A | FATEH SANAT KIMIA | 2016-09-25 | 2016-10-30 11:39 | 2016-10-30 11:40 | Yes | 35 |  | 2016-11-07 16:32 | [6 empty] | 2016-11-07 19:59 | Yes | -6 | 1204-Owner-v | 2018-08-14 17:32
VD-9001-253(A)-DWG-015 | 1 | GRATING DETAIL for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-09-25 | 2016-10-30 11:38 | 2016-10-30 11:40 | Yes | 35 |  | 2016-12-12 08:33 | [6 empty] | 2016-12-12 19:59 | Yes | 29 | 1204-Owner-v | 2018-08-14 17:22
VD-9001-253(A)-DWG-057 | 1 | MOTOR WALKWAY GRATING DETAIL FOR AE-3001 | HM-253A | FATEH SANAT KIMIA | 2016-09-25 | 2016-10-30 15:03 | 2016-10-30 15:04 | Yes | 35 |  | 2016-11-07 16:11 | [6 empty] | 2016-11-07 19:59 | Yes | -6 | 1204-Owner-v | 2018-08-14 17:46
VD-9001-213B-PCJ-007 | 1 | Roof structure Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-10-09 18:56 | 2016-11-06 16:50 |  | No | 28 | 2016-11-21 16:07 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204B-CAL-009 | 2 | Transportation Saddle Calculation D-1002 | PV-204B | ABAN AIR COOLER. | 2016-09-27 | 2016-09-27 11:58 | 2016-09-27 11:59 | Yes | 0 |  | 2016-09-28 09:47 | [6 empty] | 2016-09-28 18:56 | Yes | -13 | 1204-Owner-v | 2020-04-29 08:02
VD-9001-204B-CAL-010 | 2 | Transportation Saddle Calculation D-1003 | PV-204B | ABAN AIR COOLER. | 2016-09-27 | 2016-09-27 11:58 | 2016-09-27 11:59 | Yes | 0 |  | 2016-09-28 09:51 | [6 empty] | 2016-09-28 18:56 | Yes | -13 | 1204-Owner-v | 2020-04-29 08:02
VD-9001-204B-CAL-012 | 2 | Transportation Saddle Calculation D-3007 | PV-204B | ABAN AIR COOLER. | 2016-09-27 | 2016-09-27 11:59 | 2016-09-27 12:00 | Yes | 0 |  | 2016-09-28 09:54 | [6 empty] | 2016-09-28 18:56 | Yes | -13 | 1204-Owner-v | 2019-01-01 11:24
VD-9001-204B-CAL-011 | 2 | Transportation Saddle Calculation D-3006 | PV-204B | ABAN AIR COOLER. | 2016-09-27 | 2016-09-27 11:59 | 2016-09-27 12:00 | Yes | 0 |  | 2016-09-28 09:52 | [6 empty] | 2016-09-28 18:56 | Yes | -13 | 1204-Owner-v | 2020-04-29 08:02
VD-9001-204A-DWG-174 | 3 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2016-10-11 18:56 | 2016-10-09 10:29 |  | No | -2 |  | 2016-10-29 10:54 | [6 empty] | 2016-10-29 19:59 | Yes | 0
VD-9001-204A-DWG-014 | 1 | PF & LD Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-10-11 18:56 | 2016-10-16 14:34 | 2016-10-16 14:34 | Yes | 5 |  | 2016-10-29 16:07 | [6 empty] | 2016-10-29 20:00 | Yes | -1 | 1204-Owner-v | 2018-12-22 16:37
VD-9001-205A-DWG-071 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1002 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-10-12 18:56 | 2016-10-20 10:40 | 2016-10-20 10:41 | Yes | 8 |  | 2016-12-13 09:11 | [6 empty] | 2016-12-13 19:59 | Yes | 40
VD-9001-205A-DWG-075 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-10-12 18:56 | 2016-10-20 10:41 | 2016-10-20 10:42 | Yes | 8 |  | 2016-12-13 09:14 | [6 empty] | 2016-12-13 19:59 | Yes | 40
VD-9001-204A-DWG-104 | 1 | PF & LD Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-10-16 18:56 | 2016-10-25 15:34 |  | No | 9 | 2016-10-30 10:42 | [7 empty] | 2016-10-30 19:59 | Yes | 0
VD-9001-204A-DWG-044 | 1 | PF & LD Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-10-16 18:56 | 2016-10-09 10:25 |  | No | -7 |  | 2016-10-29 09:58 | [6 empty] | 2016-10-29 19:59 | Yes | 0
VD-9001-203-CAL-008 | 2 | Lifting Calculation | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-16 18:56 | 2016-10-08 14:53 |  | No | -8 |  | 2016-10-09 15:15 | [6 empty] | 2016-10-09 18:56 | Yes | 0
VD-9001-203-DWG-011 | 4 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-16 18:56 | 2016-10-09 17:36 |  | No | -7 | 2016-10-23 15:11 | [7 empty] | 2016-10-23 20:00 | Yes | 0
VD-9001-204A-DWG-064 | 2 | PF & LD Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2016-10-16 18:56 | 2016-10-09 10:27 |  | No | -7 |  | 2016-10-29 10:07 | [6 empty] | 2016-10-29 19:59 | Yes | 0
VD-9001-204B-PCJ-009 | 1 | Painting Procedure | PV-204B | ABAN AIR COOLER. | 2016-10-03 | 2016-10-22 13:51 | 2016-10-22 13:52 | Yes | 19 |  | 2016-11-12 14:23 | [6 empty] | 2016-11-12 20:00 | Yes | 7 | 1204-Owner-v | 2019-01-30 10:21
VD-9001-204A-DWG-024 | 1 | PF & LD Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-10-18 18:56 | 2016-10-22 16:18 |  | No | 4 |  | 2016-10-30 09:58 | [6 empty] | 2016-10-30 19:59 | Yes | 0
VD-9001-203-DWG-014 | 1 | Detail of Nozzle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-18 18:56 | 2016-10-05 17:35 |  | No | -13 | 2016-10-23 12:14 | [7 empty] | 2016-10-23 20:00 | Yes | 0
VD-9001-204A-CAL-019 | 0 | LIFTING CALCULATION D-1001 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-18 11:54 |  | No | 744 | 2016-11-13 10:18 | [7 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-CAL-059 | 0 | LIFTING CALCULATION D-3002 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-13 11:00 |  | No | 739 |  | 2016-10-30 10:54 | [6 empty] | 2016-10-30 19:59 | Yes | 0
VD-9001-204A-CAL-099 | 0 | LIFTING CALCULATION D-4002 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-15 15:40 |  | No | 741 |  | 2016-11-09 16:05 | [6 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-204A-CAL-109 | 0 | LIFTING CALCULATION D-4003 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-18 12:02 |  | No | 744 |  | 2016-11-09 16:07 | [6 empty] | 2016-11-09 20:00 | Yes | 0
VD-9001-204A-CAL-119 | 0 | LIFTING CALCULATION D-4004 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-22 16:21 |  | No | 748 |  | 2016-11-09 16:02 | [6 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-204A-CAL-129 | 0 | LIFTING CALCULATION D-6201 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-18 12:04 |  | No | 744 | 2016-11-13 16:42 | [7 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-CAL-139 | 0 | LIFTING CALCULATION D-6202 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-22 16:21 |  | No | 748 | 2016-11-13 16:59 | [7 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-CAL-169 | 0 | LIFTING CALCULATION D-6501 | PV-204A | Asas Sanat Pars Inc. | 2014-10-05 | 2016-10-13 13:02 |  | No | 739 |  | 2016-11-13 17:24 | [6 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-DWG-114 | 1 | PF & LD Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-10-19 18:55 | 2016-10-13 12:50 | 2016-10-13 12:50 | Yes | -6 |  | 2016-10-29 11:28 | [6 empty] | 2016-10-29 20:00 | Yes | 2 | 1204-Owner-v | 2018-12-22 16:40
VD-9001-204A-DWG-134 | 1 | PF & LD Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-10-19 18:56 | 2016-10-20 10:03 | 2016-10-20 10:03 | Yes | 1 |  | 2016-10-29 16:36 | [6 empty] | 2016-10-29 20:00 | Yes | -5 | 1204-Owner-v | 2018-12-22 16:41
VD-9001-204A-DWG-124 | 1 | PF & LD Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-10-19 18:56 | 2016-10-13 12:52 |  | No | -6 |  | 2016-10-29 11:41 | [6 empty] | 2016-10-29 20:00 | Yes | 0
VD-9001-204A-DWG-074 | 3 | PF & LD Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-10-24 18:55 | 2016-10-17 09:07 |  | No | -7 |  | 2016-10-29 16:29 | [6 empty] | 2016-10-29 20:00 | Yes | 0
VD-9001-204A-CAL-011 | 0 | Shipping Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-07 16:39 |  | No | 2 | 2016-11-21 11:42 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-019 | 0 | Shipping Drawing for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-07 16:40 |  | No | 2 | 2016-11-13 17:36 | [7 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-CAL-021 | 0 | Shipping Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-06 14:13 |  | No | 1 | 2017-08-05 15:43 | [7 empty] | 2017-08-05 19:58 | Yes | 0
VD-9001-204A-DWG-029 | 0 | Shipping Drawing for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-06 14:21 |  | No | 1 | 2016-11-15 12:01 | [7 empty] | 2016-11-15 20:00 | Yes | 0
VD-9001-204A-CAL-051 | 0 | Shipping Calculation for D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-10-31 15:38 |  | No | -5 | 2016-11-14 16:13 | [7 empty] | 2016-11-14 20:00 | Yes | 0
VD-9001-204A-DWG-059 | 0 | Shipping Drawing for D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-16 09:26 |  | No | 11 | 2016-11-19 10:06 | [7 empty] | 2016-11-19 20:00 | Yes | 0
VD-9001-204A-CAL-091 | 0 | Shipping Calculation for D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:21 |  | No | -3 | 2016-11-21 12:08 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-099 | 0 | Shipping Drawing for D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:30 |  | No | -3 | 2016-11-09 15:38 | [7 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-204A-CAL-101 | 0 | Shipping Calculation for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:23 |  | No | -3 | 2016-11-21 11:46 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-109 | 0 | Shipping Drawing for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:31 |  | No | -3 | 2016-11-09 15:42 | [7 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-204A-CAL-111 | 0 | Shipping Calculation for D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:24 |  | No | -3 | 2016-11-21 14:31 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-119 | 0 | Shipping Drawing for D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:32 |  | No | -3 | 2016-11-09 15:55 | [7 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-204A-CAL-121 | 0 | Shipping Calculation for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-03 08:14 |  | No | -2 | 2016-11-21 11:50 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-129 | 0 | Shipping Drawing for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-16 09:30 |  | No | 11 | 2016-11-19 10:23 | [7 empty] | 2016-11-19 20:00 | Yes | 0
VD-9001-204A-CAL-131 | 0 | Shipping Calculation for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-07 16:40 |  | No | 2 | 2016-11-21 12:33 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-139 | 0 | Shipping Drawing for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-07 16:41 |  | No | 2 | 2016-11-15 14:47 | [7 empty] | 2016-11-15 20:00 | Yes | 0
VD-9001-204A-CAL-161 | 0 | Shipping Calculation for D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:28 |  | No | -3 | 2016-11-21 14:39 | [7 empty] | 2016-11-21 20:00 | Yes | 0
VD-9001-204A-DWG-169 | 0 | Shipping Drawing for D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-11-05 | 2016-11-02 14:33 |  | No | -3 | 2016-11-09 15:47 | [7 empty] | 2016-11-09 19:59 | Yes | 0
VD-9001-203-CAL-008 | 3 | Lifting Calculation | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-16 09:22 | 2016-10-16 09:44 | 2016-10-16 09:45 | Yes | 0 |  | 2016-10-16 13:47 | [6 empty] | 2016-10-16 18:55 | Yes | -14
VD-9001-203-DWG-016 | 2 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-16 09:22 | 2016-10-16 09:44 |  | No | 0 |  | 2016-10-16 13:51 | [6 empty] | 2016-10-16 18:55 | Yes | 0
VD-9001-203-DWG-010 | 2 | Internal Parts Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-31 18:55 | 2016-10-19 12:38 |  | No | -12 |  | 2016-10-19 13:13 | [6 empty] | 2016-10-19 20:00 | Yes | 0
VD-9001-204B-PCJ-002 | 2 | Magnetic Particle Procedure | PV-204B | ABAN AIR COOLER. | 2016-10-19 | 2016-12-26 16:52 | 2016-12-26 16:53 | Yes | 68 |  | 2016-12-28 08:48 | [6 empty] | 2016-12-28 19:59 | Yes | -12 | 1204-Owner-v | 2020-04-29 08:38
VD-9001-204B-PCJ-004 | 2 | Liquid Penetrant Examination Procedure | PV-204B | ABAN AIR COOLER. | 2016-10-19 | 2016-12-27 10:49 |  | No | 69 |  | 2017-01-01 08:52 | [6 empty] | 2017-01-01 19:59 | Yes | 0
VD-9001-204B-MSS-001 | 1 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2016-10-19 | 2016-11-02 09:52 |  | No | 14 | 2016-11-15 11:27 | [7 empty] | 2016-11-15 20:00 | Yes | 0
VD-9001-105-WPS-703 | 2 | WPS & PQR for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-20 | 2016-12-05 09:40 | 2016-12-05 09:41 | Yes | 46 |  | 2016-12-20 08:02 | [6 empty] | 2016-12-20 19:59 | Yes | 1
VD-9001-105-LST-502 | 2 | Spare parts list for commissioning | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-20 | 2017-10-17 05:54 | 2017-10-17 05:55 | Yes | 362 |  | 2017-10-23 10:36 | [6 empty] | 2017-10-23 19:59 | Yes | -8 | 1204-Owner-v | 2018-06-24 13:34
VD-9001-105-LST-501 | 2 | Spare parts list for two years | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-20 | 2017-10-17 05:54 | 2017-10-17 05:55 | Yes | 362 |  | 2017-10-25 14:49 | [6 empty] | 2017-10-25 20:00 | Yes | -6 | 1204-Owner-v | 2018-06-23 17:24
VD-9001-105-LST-503 | 1 | Spare parts list and interchangeability record | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-20 | 2018-01-22 17:43 | 2018-01-22 17:44 | Yes | 459 |  | 2018-02-17 09:17 | [6 empty] | 2018-02-17 19:59 | Yes | 12
VD-9001-206B-DWG-072 | 2 | BODY & SUPPORT DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2016-10-22 15:36 | 2016-10-22 15:45 | 2016-10-22 15:46 | Yes | 0 |  | 2016-10-25 10:35 | [6 empty] | 2016-10-25 20:00 | Yes | -11
VD-9001-204B-DWG-025 | 1 | Internall attachment drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-10-23 | 2016-11-12 10:38 |  | No | 20 | 2016-11-23 09:58 | [7 empty] | 2016-11-23 20:00 | Yes | 0
VD-9001-204B-DWG-026 | 1 | Internall attachment drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-10-23 | 2016-10-30 11:51 |  | No | 7 | 2016-11-05 09:58 | [7 empty] | 2016-11-05 19:59 | Yes | 0
VD-9001-204B-DWG-028 | 1 | Internall attachment drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-10-23 | 2016-11-16 13:46 | 2016-11-16 13:47 | Yes | 24 |  | 2016-11-24 09:44 | [6 empty] | 2016-11-24 20:00 | Yes | -6 | 1204-Owner-v | 2018-12-02 09:45
VD-9001-204B-DWG-002 | 3 | General Arrangment Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-10-23 15:41 | 2016-10-26 11:25 |  | No | 3 | 2016-11-13 16:28 | [7 empty] | 2016-11-13 20:00 | Yes | 0
VD-9001-204A-DWG-042 | 3 | Nozzle Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2016-10-23 16:41 | 2017-06-20 08:25 |  | No | 240 | 2017-09-26 10:15 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-203-DWG-014 | 2 | Detail of Nozzle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-06 20:00 | 2016-10-24 11:18 |  | No | -13 |  | 2016-10-24 11:25 | [6 empty] | 2016-10-24 20:00 | Yes | 0
VD-9001-203-DWG-011 | 5 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-06 20:00 | 2016-11-06 09:03 |  | No | 0 | 2016-11-15 15:48 | [7 empty] | 2016-11-15 20:00 | Yes | 0
VD-9001-206B-PCJ-034 | 1 | PRODUCTION TEST PLATE PROCEDURE | PV-206B | TASHA | 2016-11-08 20:00 | 2016-11-02 08:47 |  | No | -6 | 2016-12-28 08:54 | [7 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-204B-DWG-027 | 1 | Internall attachment drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-10-26 | 2016-11-15 12:28 |  | No | 20 | 2016-11-22 14:47 | [7 empty] | 2016-11-22 20:00 | Yes | 0
VD-9001-253(A)-DSH-026 | 3 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2016-10-26 15:01 | 2016-10-26 16:08 | 2016-10-26 16:09 | Yes | 0 |  | 2016-11-07 15:47 | [6 empty] | 2016-11-07 19:59 | Yes | -2 | 1204-Owner-v | 2018-02-03 12:56
VD-9001-253(A)-DSH-056 | 3 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2016-10-26 15:02 | 2016-10-26 16:08 | 2016-10-26 16:09 | Yes | 0 |  | 2016-11-07 15:40 | [6 empty] | 2016-11-07 19:59 | Yes | -2 | 1204-Owner-v | 2018-08-08 10:48
VD-9001-253(A)-DSH-086 | 3 | VIBRATION SWITCH DATA SHEET | HM-253A | FATEH SANAT KIMIA | 2016-10-26 15:02 | 2016-10-26 16:09 | 2016-10-26 16:10 | Yes | 0 |  | 2016-11-07 15:49 | [6 empty] | 2016-11-07 19:59 | Yes | -2
VD-9001-203-DWG-020 | 4 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-27 09:49 | 2016-10-27 10:00 |  | No | 0 | 2016-11-15 15:50 | [7 empty] | 2016-11-15 20:00 | Yes | 0
VD-9001-105-WPS-701 | 2 | WPS & PQR for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-29 | 2016-12-05 08:53 |  | No | 37 |  | 2016-12-20 07:57 | [6 empty] | 2016-12-20 19:59 | Yes | 0
VD-9001-105-WPS-702 | 2 | WPS & PQR for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-10-29 | 2016-12-05 09:02 | 2016-12-05 09:03 | Yes | 37 |  | 2016-12-20 08:00 | [6 empty] | 2016-12-20 19:59 | Yes | 1
VD-9001-204A-DWG-104 | 2 | PF & LD Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-11-13 19:59 | 2016-10-31 12:00 |  | No | -13 |  | 2016-11-08 09:30 | [6 empty] | 2016-11-08 19:59 | Yes | 0
VD-9001-203-DWG-014 | 3 | Detail of Nozzle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-10-31 08:48 | 2016-10-31 09:20 | 2016-10-31 09:21 | Yes | 0 |  | 2016-11-15 15:57 | [6 empty] | 2016-11-15 20:00 | Yes | 1
VD-9001-204B-DWG-026 | 2 | Internall attachment drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-11-05 | 2016-11-08 12:19 |  | No | 3 | 2016-11-23 10:04 | [7 empty] | 2016-11-23 20:00 | Yes | 0
VD-9001-204B-DWG-001 | 4 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-11-07 | 2016-11-13 08:02 |  | No | 6 |  | 2016-11-23 10:40 | [6 empty] | 2016-11-23 20:00 | Yes | 0 | 1204-Owner-v | 2018-12-02 08:55
VD-9001-254-DSH-564 | 2 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2016-11-21 19:59 | 2017-12-05 07:51 |  | No | 379 | 2018-02-04 17:41 | [7 empty] | 2018-02-04 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-28 09:46
VD-9001-254-DSH-563 | 3 | DATA SHEET FOR MOTOR OPERATED VALVES | HM-254 | AZAR AB | 2016-11-21 19:59 | 2017-06-10 13:11 | 2017-06-10 13:12 | Yes | 201 |  | 2017-07-03 16:20 | [6 empty] | 2017-07-03 19:59 | Yes | 9 | 1204-Owner-v | 2018-01-19 14:19
VD-9001-254-PDS-344 | 1 | FUNCTION , CHARACTERISTIC CURVES & SETTINGS FOR ABC | HM-254 | AZAR AB | 2016-11-21 19:59 | 2020-04-21 14:42 | 2020-04-21 14:43 | Yes | 1247 |  |  | 2020-04-27 18:07 | [5 empty] | 2020-04-27 18:07 | Yes | -8
VD-9001-204B-CAL-005 | 1 | Local Stress Calculation D-1002 | PV-204B | ABAN AIR COOLER. | 2016-11-08 | 2016-11-12 10:01 | 2016-11-12 10:02 | Yes | 4 |  | 2016-11-24 11:56 | [6 empty] | 2016-11-24 20:00 | Yes | -2 | 1204-Owner-v | 2020-04-29 08:00
VD-9001-204B-CAL-006 | 1 | Local Stress Calculation D-1003 | PV-204B | ABAN AIR COOLER. | 2016-11-08 | 2016-11-12 10:03 | 2016-11-12 10:04 | Yes | 4 |  | 2016-11-24 12:00 | [6 empty] | 2016-11-24 20:00 | Yes | -2 | 1204-Owner-v | 2020-04-29 08:01
VD-9001-204B-CAL-007 | 1 | Local Stress Calculation D-3006 | PV-204B | ABAN AIR COOLER. | 2016-11-08 | 2016-11-12 10:03 | 2016-11-12 10:04 | Yes | 4 |  | 2016-11-24 11:50 | [6 empty] | 2016-11-24 20:00 | Yes | -2 | 1204-Owner-v | 2020-04-29 08:01
VD-9001-204B-CAL-008 | 1 | Local Stress Calculation D-3007 | PV-204B | ABAN AIR COOLER. | 2016-11-08 | 2016-11-12 10:05 | 2016-11-12 10:06 | Yes | 4 |  | 2016-11-24 11:53 | [6 empty] | 2016-11-24 20:00 | Yes | -2 | 1204-Owner-v | 2020-04-29 08:01
VD-9001-204A-DWG-099 | 1 | Shipping Drawing for D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-23 19:59 | 2016-12-05 15:05 | 2016-12-05 15:06 | Yes | 12 |  | 2016-12-12 09:27 | [6 empty] | 2016-12-12 19:59 | Yes | -7
VD-9001-204A-DWG-109 | 1 | Shipping Drawing for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-11-23 19:59 | 2016-12-05 15:07 |  | No | 12 |  | 2016-12-12 10:17 | [6 empty] | 2016-12-12 19:59 | Yes | 0
VD-9001-204A-DWG-169 | 1 | Shipping Drawing for D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-11-23 19:59 | 2016-12-05 16:10 | 2016-12-05 16:10 | Yes | 12 |  | 2016-12-12 11:38 | [6 empty] | 2016-12-12 20:00 | Yes | -7
VD-9001-204A-DWG-119 | 1 | Shipping Drawing for D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-11-23 19:59 | 2016-12-05 15:11 | 2016-12-05 15:11 | Yes | 12 |  | 2016-12-12 10:29 | [6 empty] | 2016-12-12 19:59 | Yes | -7
VD-9001-254-DSH-135 | 2 | DATA SHEET FOR SAMPLING EQUIPMENT | HM-254 | AZAR AB | 2016-11-26 20:00 |  |  | No | 1301 | [9 empty] | No | 0
VD-9001-204B-DWG-002 | 4 | General Arrangment Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-11-13 | 2016-11-27 10:12 | 2016-11-27 10:11 | Yes | 14 |  | 2016-11-27 16:30 | [6 empty] | 2016-11-27 20:00 | Yes | -14 | 1204-Owner-v | 2018-08-29 14:02
VD-9001-204A-CAL-019 | 1 | LIFTING CALCULATION D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-11-27 20:00 | 2017-06-21 08:44 | 2017-06-21 08:45 | Yes | 206 |  | 2017-08-12 17:41 | [6 empty] | 2017-08-12 19:59 | Yes | 38
VD-9001-204A-CAL-129 | 1 | LIFTING CALCULATION D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-11-27 20:00 | 2017-06-20 13:57 | 2017-06-20 13:57 | Yes | 205 |  | 2017-08-22 12:31 | [6 empty] | 2017-08-22 19:58 | Yes | 49
VD-9001-204A-CAL-139 | 1 | LIFTING CALCULATION D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-11-27 20:00 | 2017-06-21 07:57 | 2017-06-21 07:58 | Yes | 206 |  | 2017-08-22 15:05 | [6 empty] | 2017-08-22 19:58 | Yes | 48
VD-9001-204A-DWG-019 | 1 | Shipping Drawing for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-11-27 20:00 | 2016-12-05 14:28 |  | No | 8 |  | 2016-12-12 16:10 | [6 empty] | 2016-12-12 20:00 | Yes | 0
VD-9001-203-MNL-026 | 1 | Operating & Maintenance Manual | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-28 20:00 | 2016-12-08 11:03 | 2016-12-08 11:04 | Yes | 10 |  | 2016-12-27 16:39 | [6 empty] | 2016-12-27 19:59 | Yes | 5
VD-9001-204A-CAL-051 | 1 | Shipping Calculation for D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-28 20:00 | 2016-12-06 15:25 |  | No | 8 |  | 2016-12-24 11:25 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204B-MSS-001 | 2 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2016-11-15 | 2016-11-22 11:21 |  | No | 7 |  | 2016-11-22 14:42 | [6 empty] | 2016-11-22 20:00 | Yes | 0
VD-9001-204A-DWG-029 | 1 | Shipping Drawing for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2016-11-29 20:00 | 2016-12-06 12:58 |  | No | 7 |  | 2016-12-19 10:46 | [6 empty] | 2016-12-19 19:59 | Yes | 0
VD-9001-204A-DWG-139 | 1 | Shipping Drawing for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-11-29 20:00 | 2016-12-05 15:19 |  | No | 6 |  | 2016-12-12 16:24 | [6 empty] | 2016-12-12 20:00 | Yes | 0
VD-9001-203-DWG-011 | 6 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-29 20:00 | 2016-11-22 12:42 |  | No | -7 |  | 2016-12-07 16:43 | [6 empty] | 2016-12-07 20:00 | Yes | 0
VD-9001-203-DWG-020 | 5 | Layout Sizing Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-29 20:00 | 2016-11-22 12:44 | 2016-11-22 12:45 | Yes | -7 |  | 2016-12-07 16:40 | [6 empty] | 2016-12-07 20:00 | Yes | 1
VD-9001-105-PCJ-509 | 2 | Hardness test procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2016-11-19 | 2016-11-21 07:22 | 2016-11-21 07:23 | Yes | 2 |  | 2016-11-26 08:53 | [6 empty] | 2016-11-26 20:00 | Yes | -9
VD-9001-204A-DWG-059 | 1 | Shipping Drawing for D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-12-03 20:00 | 2016-12-05 14:31 | 2016-12-05 14:31 | Yes | 2 |  | 2016-12-12 09:05 | [6 empty] | 2016-12-12 19:59 | Yes | -7
VD-9001-204A-DWG-129 | 1 | Shipping Drawing for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-12-03 20:00 | 2016-12-05 15:14 |  | No | 2 |  | 2016-12-12 10:58 | [6 empty] | 2016-12-12 19:59 | Yes | 0
VD-9001-201-MSS-001 | 1 | PLATE MATERIAL SPECIFICATION (SA 387 Gr 11 Cl.3) | PV-201 | ATB RIVA CALZONI SpA | 2016-12-03 20:00 | 2016-12-22 18:22 |  | No | 19 | 2017-01-11 11:34 | [7 empty] | 2017-01-11 19:58 | Yes | 0
VD-9001-201-MSS-003 | 1 | FORGING MATERIAL SPECIFICATION (SA 336 F11 CL3) | PV-201 | ATB RIVA CALZONI SpA | 2016-12-03 20:00 | 2016-12-22 18:22 |  | No | 19 | 2017-01-11 11:31 | [7 empty] | 2017-01-11 19:58 | Yes | 0
VD-9001-204A-CAL-011 | 1 | Shipping Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:25 | 2016-12-06 15:26 | Yes | 1 |  | 2017-08-05 15:04 | [6 empty] | 2017-08-05 19:58 | Yes | 228
VD-9001-204A-CAL-101 | 1 | Shipping Calculation for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:28 |  | No | 1 |  | 2016-12-24 10:54 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204A-CAL-121 | 1 | Shipping Calculation for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:29 |  | No | 1 |  | 2016-12-24 11:00 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204A-CAL-091 | 1 | Shipping Calculation for D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:26 |  | No | 1 |  | 2016-12-24 10:38 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204A-CAL-131 | 1 | Shipping Calculation for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:30 |  | No | 1 |  | 2016-12-24 11:03 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204A-CAL-111 | 1 | Shipping Calculation for D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:28 |  | No | 1 |  | 2016-12-24 10:56 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-204A-CAL-161 | 1 | Shipping Calculation for D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-12-05 20:00 | 2016-12-06 15:31 |  | No | 1 |  | 2016-12-24 11:08 | [6 empty] | 2016-12-24 19:59 | Yes | 0
VD-9001-201-DWG-001 | 1 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2016-12-05 20:00 | 2016-12-22 18:14 |  | No | 17 | 2017-01-28 10:53 | [7 empty] | 2017-01-28 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 11:18
VD-9001-213B-PCJ-007 | 2 | Roof structure Erection Procedure for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2016-12-05 20:00 | 2016-11-29 08:59 | 2016-11-29 09:00 | Yes | -6 |  | 2016-12-11 08:49 | [6 empty] | 2016-12-11 19:59 | Yes | -2
VD-9001-204B-DWG-011 | 3 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-11-22 12:10 | 2016-11-22 15:11 |  | No | 0 |  | 2016-12-04 14:51 | [6 empty] | 2016-12-04 20:00 | Yes | 0
VD-9001-203-DWG-010 | 3 | Internal Parts Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-22 14:05 | 2016-11-23 12:42 | 2016-11-23 12:43 | Yes | 1 |  | 2016-12-10 14:50 | [6 empty] | 2016-12-10 20:00 | Yes | 3
VD-9001-203-DWG-012 | 3 | Shell Araangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-22 14:05 | 2016-11-22 15:48 | 2016-11-22 15:49 | Yes | 0 |  | 2016-12-07 17:12 | [6 empty] | 2016-12-07 20:00 | Yes | 1
VD-9001-203-DWG-016 | 3 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2016-11-22 14:05 | 2016-11-23 12:43 |  | No | 1 |  | 2016-12-07 17:33 | [6 empty] | 2016-12-07 20:00 | Yes | 0
VD-9001-204B-DWG-027 | 2 | Internall attachment drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-11-22 | 2016-11-23 14:17 |  | No | 1 |  | 2016-11-24 12:53 | [6 empty] | 2016-11-24 20:00 | Yes | 0
VD-9001-204B-DWG-025 | 2 | Internall attachment drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-11-23 | 2016-11-23 15:34 |  | No | 0 | 2016-11-26 14:53 | [7 empty] | 2016-11-26 20:00 | Yes | 0
VD-9001-204B-DWG-026 | 3 | Internall attachment drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-11-23 | 2016-11-26 15:14 | 2016-11-26 15:13 | Yes | 3 |  | 2016-11-26 17:58 | [6 empty] | 2016-11-26 20:00 | Yes | -14 | 1204-Owner-v | 2018-12-02 09:43
VD-9001-204B-DWG-025 | 3 | Internall attachment drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-11-26 | 2016-11-26 15:57 |  | No | 0 |  | 2016-11-27 14:16 | [6 empty] | 2016-11-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-12-02 09:40
VD-9001-204B-DWG-015 | 2 | Nozzle Detail Drawing D-3006 * | PV-204B | ABAN AIR COOLER. | 2016-11-26 15:14 | 2016-11-26 16:04 |  | No | 0 |  | 2016-11-26 17:52 | [6 empty] | 2016-11-26 20:00 | Yes | 0
VD-9001-201-CAL-002 | 1 | FOUNDATION LOADS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2016-12-10 20:00 | 2017-05-05 19:24 |  | No | 146 | 2017-06-14 17:13 | [7 empty] | 2017-06-14 20:00 | Yes | 0
VD-9001-204B-PCJ-001 | 2 | Repair Procedure | PV-204B | ABAN AIR COOLER. | 2016-11-27 | 2016-12-03 10:32 | 2016-12-03 10:33 | Yes | 6 |  | 2017-03-14 09:30 | [6 empty] | 2017-03-14 20:00 | Yes | 87 | 1204-Owner-v | 2020-04-29 08:38
VD-9001-254-EQL-110 | 2 | MAIN EQUIPMENT LIST | HM-254 | AZAR AB | 2016-12-13 20:00 |  |  | No | 1284 | [9 empty] | No | 0
VD-9001-254-PFD-111 | 3 | PROCESS FLOW DIAGRAM (PFD) | HM-254 | AZAR AB | 2016-12-13 20:00 | 2018-09-09 12:41 | 2018-09-09 12:41 | Yes | 635 |  |  |  | 2018-12-23 09:48 |  |  |  |  | 2018-12-23 09:48 | Yes | 91 | 1204-Owner-v | 2019-07-10 10:32
VD-9001-203-PCJ-023 | 1 | Surface Preparation & Painting Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-12-17 20:00 | 2017-01-01 17:19 |  | No | 15 | 2017-01-02 13:40 | [7 empty] | 2017-01-02 19:59 | Yes | 0
VD-9001-204B-DWG-007 | 1 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2016-12-04 | 2017-01-30 11:24 |  | No | 57 | 2017-02-08 10:58 | [7 empty] | 2017-02-08 19:59 | Yes | 0
VD-9001-204B-DWG-008 | 1 | Ladder & Platform Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2016-12-04 | 2017-01-09 09:11 |  | No | 36 | 2017-01-22 16:04 | [7 empty] | 2017-01-22 20:00 | Yes | 0
VD-9001-204B-PCJ-007 | 2 | Pickling Procedure | PV-204B | ABAN AIR COOLER. | 2016-12-06 | 2016-12-27 12:29 |  | No | 21 | 2017-01-01 09:02 | [7 empty] | 2017-01-01 19:59 | Yes | 0
VD-9001-108-DWG-021 | 6 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2016-12-08 10:26 | 2016-12-10 12:45 |  | No | 2 | 2016-12-20 09:57 | [7 empty] | 2016-12-20 19:59 | Yes | 0
VD-9001-204A-DWG-072 | 2 | Nozzle Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2016-12-10 08:56 | 2016-12-10 11:59 | 2016-12-10 12:00 | Yes | 0 |  | 2016-12-11 15:24 | [6 empty] | 2016-12-11 19:59 | Yes | -13
VD-9001-204A-DWG-104 | 3 | PF & LD Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-12-10 14:32 | 2016-12-11 11:07 | 2016-12-11 11:07 | Yes | 1 |  | 2016-12-11 15:08 | [6 empty] | 2016-12-11 19:59 | Yes | -14 | 1204-Owner-v | 2018-12-22 16:40
VD-9001-204A-DWG-105 | 4 | PF & LD Arrangement FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-12-10 14:32 | 2016-12-11 11:07 | 2016-12-11 11:08 | Yes | 1 |  | 2016-12-11 14:59 | [6 empty] | 2016-12-11 19:59 | Yes | -14 | 1204-Owner-v | 2018-12-29 10:19
VD-9001-204A-DWG-106 | 3 | External Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-12-10 14:32 | 2016-12-11 11:13 |  | No | 1 |  | 2016-12-12 10:46 | [6 empty] | 2016-12-12 19:59 | Yes | 0
VD-9001-205A-DWG-068 | 1 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-12-27 19:59 | 2016-12-26 13:51 | 2016-12-26 13:52 | Yes | -1 |  | 2016-12-28 16:43 | [6 empty] | 2016-12-28 19:59 | Yes | -12
VD-9001-205A-DWG-023 | 6 | INTERNAL ASSEMBLY/LAYOUT DRAWING FOR T-3003 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2016-12-14 08:55 | 2016-12-14 10:30 | 2016-12-14 10:31 | Yes | 0 |  | 2016-12-19 15:52 | [6 empty] | 2016-12-19 19:59 | Yes | -9
VD-9001-204B-DWG-005 | 1 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2016-12-15 | 2017-02-27 08:29 |  | No | 74 | 2017-03-11 10:35 | [7 empty] | 2017-03-11 20:00 | Yes | 0
VD-9001-204B-DWG-006 | 1 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2016-12-15 | 2017-02-07 15:13 | 2017-02-07 15:14 | Yes | 54 |  | 2017-02-19 16:47 | [6 empty] | 2017-02-19 20:00 | Yes | -2
VD-9001-203-PCJ-024 | 1 | Hydrostatic Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-01 19:59 | 2017-01-25 17:00 |  | No | 24 | 2017-02-21 09:07 | 2017-02-20 12:21 | [6 empty] | 2017-02-21 19:59 | Yes | 0
VD-9001-203-DWG-019 | 1 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-01 19:59 | 2017-01-01 15:08 |  | No | 0 | 2017-01-14 14:52 | [7 empty] | 2017-01-14 20:00 | Yes | 0
VD-9001-204A-DWG-051 | 5 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:36 | 2016-12-19 17:06 |  | No | 0 |  | 2016-12-20 17:07 | [6 empty] | 2016-12-20 19:59 | Yes | 0 | 1204-Owner-v | 2020-02-12 16:21
VD-9001-204A-DWG-081 | 3 | General Arrangement Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:36 | 2016-12-27 13:40 |  | No | 8 |  | 2016-12-28 10:44 | [6 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-204A-DWG-091 | 4 | General Arrangement Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:36 | 2016-12-31 16:39 | 2016-12-31 16:40 | Yes | 12 |  | 2017-01-01 11:38 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 08:57
VD-9001-204A-DWG-101 | 4 | General Arrangement Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:37 | 2016-12-19 17:10 | 2016-12-19 17:10 | Yes | 0 |  | 2016-12-21 14:49 | [6 empty] | 2016-12-21 19:59 | Yes | -12 | 1204-Owner-v | 2020-04-25 08:57
VD-9001-204A-DWG-111 | 4 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:37 | 2016-12-19 17:10 |  | No | 0 |  | 2016-12-21 11:25 | [6 empty] | 2016-12-21 19:59 | Yes | 0
VD-9001-204A-DWG-121 | 5 | General Arrangement Drawing FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:37 | 2016-12-19 17:11 | 2016-12-19 17:11 | Yes | 0 |  | 2016-12-21 11:10 | [6 empty] | 2016-12-21 19:59 | Yes | -12 | 1204-Owner-v | 2020-04-25 08:57
VD-9001-204A-DWG-161 | 4 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-12-19 10:37 | 2016-12-27 13:40 |  | No | 8 |  | 2016-12-28 11:06 | [6 empty] | 2016-12-28 19:59 | Yes | 0
VD-9001-108-DWG-021 | 7 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2017-01-03 19:59 | 2016-12-21 11:27 | 2016-12-21 11:17 | Yes | -13 |  | 2016-12-21 16:08 | [6 empty] | 2016-12-21 19:59 | Yes | -14
VD-9001-203-INX-032 | 1 | Final Data Book Index | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-04 19:59 | 2016-12-26 16:24 |  | No | -9 |  | 2016-12-27 14:18 | [6 empty] | 2016-12-27 19:59 | Yes | 0
VD-9001-201-DWG-003 | 1 | TOP COVER & MAIN FLANGE | PV-201 | ATB RIVA CALZONI SpA | 2017-01-07 19:59 | 2017-04-14 13:12 |  | No | 97 | 2017-05-21 17:49 | [7 empty] | 2017-05-21 20:00 | Yes | 0
VD-9001-201-CAL-001 | 1 | PRESSURE PARTS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2017-01-07 19:59 | 2017-09-15 19:49 |  | No | 251 | 2018-02-21 16:48 | [7 empty] | 2018-02-21 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-22 15:32
VD-9001-253(A)-DWG-023 | 1 | ASSEMBLY MARKING FOR STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2016-12-25 | 2016-12-27 16:08 |  | No | 2 |  | 2016-12-31 11:08 | [6 empty] | 2016-12-31 19:59 | Yes | 0
VD-9001-254-LST-217 | 3 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2017-01-08 19:59 | 2018-10-13 07:50 | 2018-10-13 07:50 | Yes | 643 |  |  |  | 2018-11-14 10:11 |  |  |  |  | 2018-11-14 10:11 | Yes | 18
VD-9001-254-LST-342 | 3 | CONTROL SYSTEM I/O LIST | HM-254 | AZAR AB | 2017-01-08 19:59 |  |  | No | 1258 | [9 empty] | No | 0
VD-9001-254-LST-340 | 3 | BMS I/O LIST | HM-254 | AZAR AB | 2017-01-08 19:59 | 2018-01-07 09:41 |  | No | 364 | 2018-02-05 14:38 | [7 empty] | 2018-02-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-27 15:51
VD-9001-203-PCJ-033 | 0 | Repair Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2016-12-27 | 2016-12-29 09:30 |  | No | 2 | 2017-01-02 13:42 | [7 empty] | 2017-01-02 19:59 | Yes | 0
VD-9001-206B-PCJ-034 | 2 | PRODUCTION TEST PLATE PROCEDURE | PV-206B | TASHA | 2017-01-11 19:59 | 2017-01-01 11:36 | 2017-01-01 11:37 | Yes | -10 |  | 2017-01-14 10:36 | [6 empty] | 2017-01-14 20:00 | Yes | -1
VD-9001-206B-DWG-051 | 1 | SHIPPING DRAWING-T-2001 | PV-206B | TASHA | 2017-01-11 19:59 | 2017-01-07 09:56 |  | No | -4 |  | 2017-01-28 16:29 | [6 empty] | 2017-01-28 19:59 | Yes | 0
VD-9001-206B-DWG-021 | 1 | SHIPPING DRAWING-T-1001 | PV-206B | TASHA | 2017-01-11 19:59 | 2017-01-07 09:55 | 2017-01-07 09:56 | Yes | -4 |  | 2017-01-28 16:38 | [6 empty] | 2017-01-28 19:59 | Yes | 7 | 1204-Owner-v | 2018-01-03 16:12
VD-9001-206B-DWG-081 | 1 | SHIPPING DRAWING-T-4001 | PV-206B | TASHA | 2017-01-11 19:59 | 2017-01-07 09:57 | 2017-01-07 09:58 | Yes | -4 |  | 2017-01-28 16:24 | [6 empty] | 2017-01-28 19:59 | Yes | 7 | 1204-Owner-v | 2019-07-10 11:22
VD-9001-254-DWG-440 | 2 | INSTALLATION & FABRICATION FOR ECO. TUBE SHEET | HM-254 | AZAR AB | 2016-12-31 14:13 | 2016-12-31 15:33 | 2016-12-31 15:34 | Yes | 0 |  | 2017-06-14 15:05 | [6 empty] | 2017-06-14 20:00 | Yes | 11 | 1204-Owner-v | 2019-01-22 17:25
VD-9001-204A-DWG-031 | 4 | General Arrangement Drawing FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:04 | 2016-12-31 16:33 | 2016-12-31 16:34 | Yes | 0 |  | 2017-01-01 11:15 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2019-09-14 15:21
VD-9001-204A-DWG-051 | 6 | General Arrangement Drawing FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:05 | 2016-12-31 16:38 | 2016-12-31 16:38 | Yes | 0 |  | 2017-01-01 11:48 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-09 11:51
VD-9001-204A-DWG-081 | 4 | General Arrangement Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:05 | 2016-12-31 16:32 | 2016-12-31 16:33 | Yes | 0 |  | 2017-01-01 11:06 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2019-09-14 15:24
VD-9001-204A-DWG-141 | 3 | General Arrangement Drawing FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:05 | 2016-12-31 16:34 | 2016-12-31 16:35 | Yes | 0 |  | 2017-01-01 11:23 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 08:58
VD-9001-204A-DWG-151 | 3 | General Arrangement Drawing FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:05 | 2016-12-31 16:36 | 2016-12-31 16:36 | Yes | 0 |  | 2017-01-01 11:43 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 08:58
VD-9001-204A-DWG-161 | 5 | General Arrangement Drawing FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2016-12-31 15:05 | 2016-12-31 16:42 | 2016-12-31 16:42 | Yes | 0 |  | 2017-01-01 11:33 | [6 empty] | 2017-01-01 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 08:58
VD-9001-204B-PCJ-003 | 2 | Ultrasonic Test Procedure | PV-204B | ABAN AIR COOLER. | 2017-01-01 | 2017-01-14 11:54 |  | No | 13 | 2017-01-17 09:42 | [7 empty] | 2017-01-17 20:00 | Yes | 0
VD-9001-204B-PCJ-007 | 3 | Pickling Procedure | PV-204B | ABAN AIR COOLER. | 2017-01-01 | 2017-01-14 11:54 | 2017-01-14 11:55 | Yes | 13 |  | 2017-01-17 09:39 | [6 empty] | 2017-01-17 20:00 | Yes | -11 | 1204-Owner-v | 2020-04-29 08:40
VD-9001-203-DWG-018 | 0 | Pipe Clips Support Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-01 | 2017-01-11 12:36 |  | No | 10 | 2017-01-11 17:16 | [7 empty] | 2017-01-11 19:59 | Yes | 0
VD-9001-254-DSH-151 | 2 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2017-01-15 19:59 | 2018-02-18 11:06 |  | No | 399 |  |  |  | 2018-08-12 15:04 |  |  |  |  | 2018-08-12 15:04 | Yes | 0 | 1204-Owner-v | 2018-04-09 14:33
VD-9001-206B-PCJ-015 | 4 | PAINTING PROCEDURE | PV-206B | TASHA | 2017-01-02 15:33 | 2017-01-03 13:04 |  | No | 1 |  | 2017-01-28 16:48 | [6 empty] | 2017-01-28 19:59 | Yes | 0
VD-9001-203-CAL-007 | 5 | Mechanical Strength & Calculation Book | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-02 17:34 | 2017-01-04 10:48 | 2017-01-04 10:49 | Yes | 2 |  | 2017-01-11 09:42 | [6 empty] | 2017-01-11 19:58 | Yes | -7
VD-9001-203-DWG-011 | 7 | General Arrangement Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-02 17:34 | 2017-01-04 10:47 | 2017-01-04 10:48 | Yes | 2 |  | 2017-01-14 10:13 | [6 empty] | 2017-01-14 20:00 | Yes | -4
VD-9001-203-DWG-015 | 3 | Detail of Saddle Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-02 17:34 | 2017-01-03 11:56 | 2017-01-03 11:57 | Yes | 1 |  | 2017-01-14 09:44 | [6 empty] | 2017-01-14 20:00 | Yes | -3
VD-9001-203-PCJ-023 | 2 | Surface Preparation & Painting Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-16 19:59 | 2017-01-03 12:26 |  | No | -13 | 2017-01-11 10:37 | [7 empty] | 2017-01-11 19:58 | Yes | 0
VD-9001-203-PCJ-033 | 1 | Repair Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-16 19:59 | 2017-01-05 11:55 | 2017-01-05 11:56 | Yes | -11 |  | 2017-01-11 10:34 | [6 empty] | 2017-01-11 19:58 | Yes | -8
VD-9001-203-PCJ-034 | 0 | Nitrogen Filling Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-04 | 2017-01-04 10:53 | 2017-01-04 10:54 | Yes | 0 |  | 2017-01-16 11:59 | [6 empty] | 2017-01-16 20:00 | Yes | -2
VD-9001-203-DWG-016 | 4 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-04 11:45 | 2017-01-04 14:41 |  | No | 0 | 2017-01-09 09:19 | [7 empty] | 2017-01-09 19:58 | Yes | 0
VD-9001-203-PCJ-025 | 1 | Packing, Shipping and Marking Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-21 19:58 | 2017-01-16 11:53 |  | No | -5 | 2017-01-18 09:16 | [7 empty] | 2017-01-18 20:00 | Yes | 0
VD-9001-203-DWG-017 | 3 | Name Plate Detail Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-08 09:12 | 2017-01-08 10:22 | 2017-01-08 10:23 | Yes | 0 |  | 2017-01-11 09:50 | [6 empty] | 2017-01-11 19:58 | Yes | -11
VD-9001-203-DWG-016 | 5 | External Attachment Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-23 19:58 | 2017-01-11 12:35 | 2017-01-11 12:36 | Yes | -12 |  | 2017-01-11 13:05 | [6 empty] | 2017-01-11 19:59 | Yes | -14
VD-9001-204B-PCJ-008 | 2 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2017-01-11 10:07 | 2017-01-11 10:30 |  | No | 0 | 2017-02-12 11:15 | [7 empty] | 2017-02-12 19:59 | Yes | 0
VD-9001-204B-DWG-011 | 4 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-01-11 10:07 | 2017-01-11 14:15 |  | No | 0 |  | 2017-01-12 12:15 | [6 empty] | 2017-01-12 20:00 | Yes | 0
VD-9001-213B-DWG-019 | 6 | Shell Plates for Tk-6402 | PV-213B | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-01-11 17:08 | 2017-01-23 08:50 | 2017-01-23 08:51 | Yes | 12 |  | 2017-01-24 09:15 | [6 empty] | 2017-01-24 19:59 | Yes | -13
VD-9001-203-PCJ-023 | 3 | Surface Preparation & Painting Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-25 19:58 | 2017-01-16 11:52 |  | No | -9 | 2017-01-16 15:08 | [7 empty] | 2017-01-16 20:00 | Yes | 0
VD-9001-201-MSS-003 | 2 | FORGING MATERIAL SPECIFICATION (SA 336 F11 CL3) | PV-201 | ATB RIVA CALZONI SpA | 2017-01-25 19:58 | 2017-03-03 19:51 |  | No | 37 |  | 2017-04-08 11:36 | [6 empty] | 2017-04-08 20:59 | Yes | 0
VD-9001-201-MSS-001 | 2 | PLATE MATERIAL SPECIFICATION (SA 387 Gr 11 Cl.3) | PV-201 | ATB RIVA CALZONI SpA | 2017-01-25 19:58 | 2017-03-03 19:50 | 2017-03-03 19:51 | Yes | 37 |  | 2017-04-08 11:33 | [6 empty] | 2017-04-08 20:59 | Yes | 22 | 1204-Owner-v | 2018-12-16 21:35
VD-9001-203-DWG-018 | 1 | Pipe Clips Support Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-25 19:59 | 2017-01-14 16:21 | 2017-01-14 16:22 | Yes | -11 |  | 2017-01-18 09:01 | [6 empty] | 2017-01-18 19:59 | Yes | -10
VD-9001-206B-DWG-076 | 2 | INSULATION SUPPORT DRAWING -T-4001 | PV-206B | TASHA | 2017-01-14 15:50 | 2017-01-15 10:54 |  | No | 1 | 2017-02-05 16:08 | [7 empty] | 2017-02-05 19:59 | Yes | 0
VD-9001-203-CAL-009 | 1 | Loading Data | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-28 20:00 | 2017-01-24 16:32 | 2017-01-24 16:33 | Yes | -4 |  | 2017-01-25 09:26 | [6 empty] | 2017-01-25 19:59 | Yes | -13
VD-9001-206B-WBK-021 | 3 | WELDING BOOK (WPS & PQR) | PV-206B | TASHA | 2017-01-28 20:00 | 2017-02-08 09:38 |  | No | 1238 |  | 2017-04-10 09:35 | [6 empty] | 2017-04-10 20:59 | Yes | 0
VD-9001-203-DWG-019 | 2 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-28 20:00 | 2017-01-16 14:29 |  | No | -12 | 2017-01-23 10:06 | [7 empty] | 2017-01-23 19:59 | Yes | 0
VD-9001-203-PCJ-023 | 4 | Surface Preparation & Painting Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-30 20:00 | 2017-01-22 12:35 | 2017-01-22 12:36 | Yes | -8 |  | 2017-02-11 17:20 | [6 empty] | 2017-02-11 19:59 | Yes | 6
VD-9001-204B-PCJ-003 | 3 | Ultrasonic Test Procedure | PV-204B | ABAN AIR COOLER. | 2017-01-17 | 2017-03-12 11:56 |  | No | 54 | 2017-03-18 16:13 | [7 empty] | 2017-03-18 20:00 | Yes | 0
VD-9001-203-PCJ-025 | 2 | Packing, Shipping and Marking Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-02-01 20:00 | 2017-01-30 11:35 |  | No | -2 | 2017-03-06 11:56 | [7 empty] | 2017-03-06 19:59 | Yes | 0
VD-9001-204A-DWG-013 | 2 | Name Plate Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:31 | 2017-01-22 13:38 |  | No | 1 |  | 2017-01-23 14:29 | [6 empty] | 2017-01-23 20:00 | Yes | 0
VD-9001-204A-DWG-023 | 2 | Name Plate Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:31 | 2017-01-22 13:39 |  | No | 1 |  | 2017-01-25 11:19 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204A-DWG-063 | 2 | Name Plate Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:31 | 2017-01-22 13:40 |  | No | 1 |  | 2017-01-25 09:54 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204A-DWG-073 | 2 | Name Plate Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:32 | 2017-01-22 13:41 |  | No | 1 |  | 2017-01-25 09:59 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204A-DWG-103 | 2 | Name Plate Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:32 | 2017-01-22 13:42 |  | No | 1 |  | 2017-01-25 10:41 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204A-DWG-113 | 2 | Name Plate Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:32 | 2017-01-22 13:43 |  | No | 1 |  | 2017-01-25 10:46 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204A-DWG-163 | 2 | Name Plate Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-01-21 14:32 | 2017-01-22 13:45 |  | No | 1 |  | 2017-01-25 11:11 | [6 empty] | 2017-01-25 19:59 | Yes | 0
VD-9001-204B-DWG-008 | 2 | Ladder & Platform Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2017-01-22 | 2017-03-12 09:54 | 2017-03-12 09:55 | Yes | 49 |  | 2017-03-18 16:07 | [6 empty] | 2017-03-18 20:00 | Yes | -8 | 1204-Owner-v | 2018-12-02 09:22
VD-9001-231A-DWG-011 | 2 | Ladder And Platform Drawing ( 3 - T - 3002 ) | PV-231A | Tarh Mechanic Gostar | 2017-02-05 19:59 | 2017-02-06 16:02 | 2017-02-06 16:03 | Yes | 1 |  |  | 2018-05-07 09:54 | [5 empty] | 2018-05-07 09:54 | Yes | 441
VD-9001-203-INX-032 | 2 | Final Data Book Index | PV-203 | Masnout Felezi Sangin (MFS) | 2017-01-23 10:10 | 2017-01-23 12:24 | 2017-01-23 12:25 | Yes | 0 |  | 2017-01-23 13:36 | [6 empty] | 2017-01-23 19:59 | Yes | -14
VD-9001-203-DWG-019 | 3 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-02-06 19:59 | 2017-01-26 10:02 |  | No | -11 | 2017-02-07 10:56 | [7 empty] | 2017-02-07 19:59 | Yes | 0
VD-9001-201-DWG-001 | 2 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2017-02-11 19:59 | 2017-05-05 19:25 |  | No | 83 | 2017-05-23 16:33 | [7 empty] | 2017-05-23 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 11:18
VD-9001-253(A)-DWG-053 | 1 | ASSEMBLY MARKING FOR STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-01-30 | 2017-02-18 08:38 |  | No | 19 |  | 2017-03-12 16:18 | [6 empty] | 2017-03-12 20:00 | Yes | 0
VD-9001-205A-DWG-067 | 1 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-1001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-01-30 16:29 | 2017-01-30 17:12 | 2017-01-30 17:13 | Yes | 0 |  | 2017-02-15 12:02 | [6 empty] | 2017-02-15 19:59 | Yes | 2
VD-9001-204B-DWG-029 | 2 | Template Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-02-04 11:30 | 2017-02-04 14:08 | 2017-02-04 14:09 | Yes | 0 |  | 2017-02-07 14:01 | [6 empty] | 2017-02-07 19:59 | Yes | -11 | 1204-Owner-v | 2019-01-13 09:17
VD-9001-204B-DWG-030 | 1 | Template Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2017-02-04 11:30 | 2017-02-04 14:37 | 2017-02-04 14:15 | Yes | 0 |  | 2017-02-07 14:04 | [6 empty] | 2017-02-07 19:59 | Yes | -11 | 1204-Owner-v | 2019-01-13 09:17
VD-9001-204B-DWG-031 | 1 | Template Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-04 11:30 | 2017-02-05 08:21 | 2017-02-05 08:22 | Yes | 1 |  | 2017-02-07 14:10 | [6 empty] | 2017-02-07 19:59 | Yes | -12 | 1204-Owner-v | 2019-01-13 09:17
VD-9001-204B-DWG-032 | 1 | Template Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2017-02-04 11:30 | 2017-02-05 08:22 | 2017-02-05 08:23 | Yes | 1 |  | 2017-02-07 14:13 | [6 empty] | 2017-02-07 19:59 | Yes | -12 | 1204-Owner-v | 2019-01-13 09:18
VD-9001-205A-LST-055 | 2 | SPARE PART LIST FOR COMMISSIONING & START-UP | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-02-04 15:09 | 2017-02-05 15:27 | 2017-02-05 15:28 | Yes | 1 |  | 2017-02-15 11:59 | [6 empty] | 2017-02-15 19:59 | Yes | -4
VD-9001-205A-LST-056 | 2 | SPARE PART LIST FOR 2 YEARS OPERATION | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-02-04 15:09 | 2017-02-05 15:29 | 2017-02-05 15:30 | Yes | 1 |  | 2017-02-15 11:57 | [6 empty] | 2017-02-15 19:59 | Yes | -4
VD-9001-253(A)-DWG-055 | 1 | ASSEMBLY MARKING FOR HEADER WALK WAY for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-02-04 | 2017-04-09 16:16 | 2017-04-09 16:27 | Yes | 64 |  | 2017-04-10 10:31 | [6 empty] | 2017-04-10 20:59 | Yes | -13 | 1204-Owner-v | 2018-08-14 17:45
VD-9001-254-DIG-336 | 1 | BMS LOGIC DIAGRAM | HM-254 | AZAR AB | 2017-02-18 19:59 | 2018-01-07 09:23 |  | No | 323 | 2018-02-13 10:36 | [7 empty] | 2018-02-13 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-30 14:46
VD-9001-231A-DWG-012 | 2 | Ladder And Platform Drawing ( 3 - T - 3003 ) | PV-231A | Tarh Mechanic Gostar | 2017-02-18 19:59 | 2019-06-24 18:13 | 2019-06-24 18:13 | Yes | 856 |  |  | 2019-07-02 16:29 | [5 empty] | 2019-07-02 20:58 | Yes | -6
VD-9001-204B-DWG-003 | 3 | General Arrangment Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-05 11:01 | 2017-02-05 11:05 | 2017-02-05 11:05 | Yes | 0 |  | 2017-02-19 15:50 | [6 empty] | 2017-02-19 20:00 | Yes | 0 | 1204-Owner-v | 2018-07-12 23:22
VD-9001-206B-DWG-076 | 3 | INSULATION SUPPORT DRAWING -T-4001 | PV-206B | TASHA | 2017-02-19 19:59 | 2017-02-19 13:15 | 2017-02-19 13:16 | Yes | 0 |  | 2017-03-07 17:11 | [6 empty] | 2017-03-07 20:00 | Yes | 2 | 1204-Owner-v | 2019-06-22 11:50
VD-9001-203-DWG-019 | 4 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-02-07 10:56 | 2017-02-18 16:31 |  | No | 11 | 2017-02-27 14:56 | [7 empty] | 2017-02-27 19:59 | Yes | 0
VD-9001-204B-DWG-007 | 2 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-08 | 2017-03-12 09:53 |  | No | 32 | 2017-03-18 17:05 | [7 empty] | 2017-03-18 20:00 | Yes | 0
VD-9001-253(A)-DWG-023 | 2 | ASSEMBLY MARKING FOR STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2017-02-11 11:36 | 2017-02-11 12:50 |  | No | 0 | 2017-02-11 14:07 | [7 empty] | 2017-02-11 19:59 | Yes | 0
VD-9001-204A-DWG-041 | 4 | General Arrangement Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-02-11 12:03 | 2017-02-27 12:23 | 2017-02-27 12:24 | Yes | 16 |  | 2017-03-11 14:35 | [6 empty] | 2017-03-11 20:00 | Yes | -2 | 1204-Owner-v | 2018-12-30 14:25
VD-9001-253(A)-DWG-023 | 3 | ASSEMBLY MARKING FOR STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2017-02-11 | 2017-02-14 15:58 |  | No | 3 | 2017-02-15 09:38 | [7 empty] | 2017-02-15 19:59 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:41
VD-9001-204B-PCJ-008 | 3 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2017-02-12 | 2017-02-13 09:07 |  | No | 1 |  | 2017-02-19 15:26 | [6 empty] | 2017-02-19 20:00 | Yes | 0
VD-9001-204A-DWG-071 | 4 | General Arrangement Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-02-12 15:03 | 2017-02-18 07:59 | 2017-02-18 08:00 | Yes | 6 |  | 2017-02-19 09:28 | [6 empty] | 2017-02-19 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 08:56
VD-9001-204A-DWG-075 | 4 | PF & LD Arrangement FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-02-12 15:03 | 2017-02-18 08:01 | 2017-02-18 08:02 | Yes | 6 |  | 2017-02-19 09:38 | [6 empty] | 2017-02-19 19:59 | Yes | -13 | 1204-Owner-v | 2018-12-29 10:18
VD-9001-204A-DWG-074 | 4 | PF & LD Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-02-12 15:04 | 2017-02-18 08:00 | 2017-02-18 08:01 | Yes | 6 |  | 2017-02-19 09:31 | [6 empty] | 2017-02-19 19:59 | Yes | -13 | 1204-Owner-v | 2018-12-22 16:39
VD-9001-204A-DWG-076 | 3 | External Attachment Drawing FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-02-12 15:04 | 2017-02-18 08:02 | 2017-02-18 08:02 | Yes | 6 |  | 2017-02-19 09:32 | [6 empty] | 2017-02-19 19:59 | Yes | -13
VD-9001-206B-WMP-022 | 3 | WELDING MAP&NDT TABLE | PV-206B | TASHA | 2017-02-12 15:08 | 2017-02-12 15:29 |  | No | 0 |  | 2017-08-07 08:44 | [6 empty] | 2017-08-07 19:58 | Yes | 0
VD-9001-205A-WPS-058 | 4 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-02-13 11:42 | 2017-02-13 17:14 |  | No | 0 | 2017-03-06 09:44 | [7 empty] | 2017-03-06 19:59 | Yes | 0
VD-9001-253(A)-DWG-023 | 4 | ASSEMBLY MARKING FOR STRUCTURE for 2001 | HM-253A | FATEH SANAT KIMIA | 2017-02-15 | 2017-02-18 08:31 | 2017-02-18 08:32 | Yes | 3 |  | 2017-02-22 12:29 | [6 empty] | 2017-02-22 19:59 | Yes | -10 | 1204-Owner-v | 2018-08-14 17:26
VD-9001-204B-INX-001 | 1 | Final Data Book Index | PV-204B | ABAN AIR COOLER. | 2017-02-19 | 2017-02-22 10:21 |  | No | 3 | 2017-03-14 09:45 | [7 empty] | 2017-03-14 20:00 | Yes | 0
VD-9001-204B-DWG-011 | 5 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-20 08:53 | 2017-02-20 11:33 |  | No | 0 | 2017-02-27 14:15 | [7 empty] | 2017-02-27 19:59 | Yes | 0
VD-9001-204B-DWG-015 | 3 | Nozzle Detail Drawing D-3006 * | PV-204B | ABAN AIR COOLER. | 2017-02-20 08:53 | 2017-02-20 11:58 | 2017-02-20 11:59 | Yes | 0 |  | 2017-03-05 17:06 | [6 empty] | 2017-03-05 20:00 | Yes | -1 | 1204-Owner-v | 2018-01-10 15:26
VD-9001-204B-DWG-027 | 3 | Internall attachment drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-20 08:53 | 2017-02-20 12:07 | 2017-02-20 12:06 | Yes | 0 |  | 2017-03-01 11:47 | [6 empty] | 2017-03-01 19:59 | Yes | -5 | 1204-Owner-v | 2018-12-02 09:44
VD-9001-203-PCJ-024 | 2 | Hydrostatic Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-02-21 14:54 | 2017-02-21 15:13 |  | No | 0 | 2017-02-21 16:13 | [7 empty] | 2017-02-21 20:00 | Yes | 0
VD-9001-203-PCJ-024 | 3 | Hydrostatic Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-03-07 20:00 | 2017-02-22 12:18 | 2017-02-22 12:19 | Yes | -13 |  | 2017-02-22 14:00 | [6 empty] | 2017-02-22 19:59 | Yes | -14
VD-9001-206B-DWG-051 | 2 | SHIPPING DRAWING-T-2001 | PV-206B | TASHA | 2017-02-26 11:03 | 2017-02-26 11:23 | 2017-02-26 11:23 | Yes | 0 |  | 2017-03-06 10:02 | [6 empty] | 2017-03-06 19:59 | Yes | -6
VD-9001-203-DWG-019 | 5 | Ladder & Platform Drawing | PV-203 | Masnout Felezi Sangin (MFS) | 2017-02-26 14:45 | 2017-03-01 18:17 | 2017-03-01 18:18 | Yes | 3 |  | 2017-05-15 17:27 | [6 empty] | 2017-05-15 20:00 | Yes | 61
VD-9001-204B-DWG-011 | 6 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-02-27 | 2017-02-28 14:32 |  | No | 1 | 2017-03-07 11:39 | [7 empty] | 2017-03-07 19:59 | Yes | 0
VD-9001-203-PCJ-025 | 3 | Packing, Shipping and Marking Procedure | PV-203 | Masnout Felezi Sangin (MFS) | 2017-03-19 19:59 | 2017-03-11 16:28 | 2017-03-11 16:29 | Yes | -8 |  | 2017-03-14 10:23 | [6 empty] | 2017-03-14 20:00 | Yes | -11
VD-9001-205A-WPS-058 | 5 | WPS & PQR | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-03-20 19:59 | 2017-03-08 12:04 | 2017-03-08 12:05 | Yes | -12 |  | 2017-03-13 16:26 | [6 empty] | 2017-03-13 20:00 | Yes | -9
VD-9001-204A-DWG-061 | 5 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-03-07 08:42 | 2017-03-07 13:46 |  | No | 0 |  | 2017-03-11 14:42 | [6 empty] | 2017-03-11 20:00 | Yes | 0 | 1204-Owner-v | 2020-04-25 08:56
VD-9001-204A-DWG-064 | 3 | PF & LD Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-03-07 08:42 | 2017-03-07 13:49 |  | No | 0 | 2017-03-12 10:18 | [7 empty] | 2017-03-12 20:00 | Yes | 0
VD-9001-204A-DWG-065 | 2 | PF & LD Arrangement FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-03-07 08:42 | 2017-03-07 13:48 | 2017-03-07 13:49 | Yes | 0 |  | 2017-03-11 16:58 | [6 empty] | 2017-03-11 20:00 | Yes | -10 | 1204-Owner-v | 2018-12-29 10:17
VD-9001-204B-DWG-011 | 7 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-03-07 | 2017-03-08 08:18 | 2017-03-08 08:17 | Yes | 1 |  | 2017-03-08 16:38 | [6 empty] | 2017-03-08 19:59 | Yes | -14
VD-9001-108-CAL-002 | 4 | COOLING TOWER AND EQUIPMENTS CALCULATION & PERFORMANC CURVES BOOKLET | PR-108 | Farabard | 2017-03-21 19:59 | 2017-08-14 10:32 | 2017-08-14 10:33 | Yes | 146 |  | 2017-08-26 17:40 | [6 empty] | 2017-08-26 19:58 | Yes | -2
VD-9001-108-DSH-009 | 4 | GEAR REDUCER DATA SHEET | PR-108 | Farabard | 2017-03-21 19:59 | 2017-08-30 11:56 | 2017-08-30 11:57 | Yes | 162 |  | 2017-09-05 16:00 | [6 empty] | 2017-09-05 19:57 | Yes | -8
VD-9001-204B-DWG-005 | 2 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-03-11 | 2017-04-10 15:35 |  | No | 30 | 2017-05-07 08:44 | [7 empty] | 2017-05-07 20:58 | Yes | 0
VD-9001-254-DWG-410 | 1 | ASSEMBLY DWG FOR S.H HDR 1/2 | HM-254 | AZAR AB | 2017-03-11 11:50 | 2017-03-11 14:01 | 2017-03-11 14:02 | Yes | 0 |  | 2017-03-29 09:41 | [6 empty] | 2017-03-29 20:59 | Yes | 4
VD-9001-108-MNL-058 | 4 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2017-03-25 20:00 | 2017-11-16 13:04 |  | No | 236 | 2017-11-20 09:30 | [7 empty] | 2017-11-20 19:59 | Yes | 0
VD-9001-206B-PCJ-020 | 1 | CLADING PROCEDURE | PV-206B | TASHA | 2017-03-25 20:00 | 2018-11-18 09:53 | 2018-11-18 09:53 | Yes | 603 |  |  |  | 2018-12-10 10:54 |  |  |  |  | 2018-12-10 10:54 | Yes | 8
VD-9001-462A-ITP-001-0 | 0 | Inspection & Test Plan | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-02-09 | 2017-03-13 10:42 |  | No | 32 | 2017-04-08 16:58 | [7 empty] | 2017-04-08 21:00 | Yes | 0
VD-9001-462A-PCJ-001-0 | 0 | Hardness Test Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-02-15 | 2017-03-13 10:43 |  | No | 26 | 2017-04-08 10:45 | [7 empty] | 2017-04-08 20:59 | Yes | 0
VD-9001-462A-PCJ-002-0 | 0 | Heat Treatment Procedure (Nomalizing) | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-02-15 | 2017-03-13 10:44 |  | No | 26 | 2017-04-08 11:38 | [7 empty] | 2017-04-08 20:59 | Yes | 0
VD-9001-462A-PCJ-004-0 | 0 | Rust Inhibitor Coating Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-02-15 | 2017-03-13 10:47 |  | No | 26 | 2017-04-08 16:41 | [7 empty] | 2017-04-08 21:00 | Yes | 0
VD-9001-204A-DWG-064 | 4 | PF & LD Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-03-26 20:00 | 2017-03-13 13:53 | 2017-03-13 13:53 | Yes | -13 |  | 2017-04-17 17:13 | [6 empty] | 2017-04-17 20:59 | Yes | 21 | 1204-Owner-v | 2018-12-22 16:39
VD-9001-204B-PQR-001 | 1 | Procedure Qualification Record (PQR) For S.S | PV-204B | ABAN AIR COOLER. | 2017-03-14 | 2017-06-17 14:12 |  | No | 95 | 2017-06-25 12:25 | [7 empty] | 2017-06-25 19:59 | Yes | 0
VD-9001-204B-WPS-001 | 1 | Welding Procedure Specification (WPS) For S.S | PV-204B | ABAN AIR COOLER. | 2017-03-14 | 2017-06-17 14:09 |  | No | 95 | 2017-06-25 12:20 | [7 empty] | 2017-06-25 19:59 | Yes | 0
VD-9001-204B-INX-001 | 2 | Final Data Book Index | PV-204B | ABAN AIR COOLER. | 2017-03-14 | 2018-12-25 11:50 | 2018-12-25 14:55 | Yes | 651 |  |  | 2018-12-30 14:51 | [5 empty] | 2018-12-30 20:01 | Yes | -9 | 1204-Owner-v | 2019-02-02 13:47
VD-9001-254-WPS-835 | 2 | WPS FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2017-03-15 10:16 | 2017-03-15 11:23 | 2017-03-15 11:24 | Yes | 0 |  | 2017-04-17 16:17 | [6 empty] | 2017-04-17 20:59 | Yes | 19
VD-9001-254-PQR-816 | 2 | PQR FOR SUPER HEATER (PART II) | HM-254 | AZAR AB | 2017-03-15 10:16 | 2017-03-15 11:25 | 2017-03-15 11:26 | Yes | 0 |  | 2017-04-17 16:20 | [6 empty] | 2017-04-17 20:59 | Yes | 19
VD-9001-204B-PCJ-003 | 4 | Ultrasonic Test Procedure | PV-204B | ABAN AIR COOLER. | 2017-03-18 | 2017-04-04 09:18 | 2017-04-04 09:19 | Yes | 17 |  | 2017-04-06 09:58 | [6 empty] | 2017-04-06 20:59 | Yes | -12 | 1204-Owner-v | 2020-04-29 08:39
VD-9001-204B-WMP-001 | 1 | Welding & NDT Map D-1002 | PV-204B | ABAN AIR COOLER. | 2017-03-18 | 2017-06-17 14:15 |  | No | 91 | 2017-07-04 10:39 | [7 empty] | 2017-07-04 19:59 | Yes | 0
VD-9001-204B-WPS-002 | 1 | Welding Procedure Specification (WPS) For C.S | PV-204B | ABAN AIR COOLER. | 2017-03-18 | 2017-06-17 14:09 |  | No | 91 | 2017-06-28 09:01 | [7 empty] | 2017-06-28 19:59 | Yes | 0
VD-9001-204B-PQR-002 | 1 | Procedure Qualification Record (PQR) For C.S | PV-204B | ABAN AIR COOLER. | 2017-03-18 | 2017-06-17 14:13 |  | No | 91 | 2017-06-25 12:28 | [7 empty] | 2017-06-25 19:59 | Yes | 0
VD-9001-204B-DWG-007 | 3 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-03-18 | 2017-04-10 15:32 | 2017-04-10 15:33 | Yes | 23 |  | 2017-04-19 15:46 | [6 empty] | 2017-04-19 20:59 | Yes | -5
VD-9001-254-PDS-337 | 1 | FUNCTION OF BMS | HM-254 | AZAR AB | 2017-04-09 21:00 | 2018-01-07 09:35 | 2018-01-07 09:36 | Yes | 273 |  | 2018-02-06 14:26 | [6 empty] | 2018-02-07 20:00 | Yes | 16 | 1204-Owner-v | 2019-12-09 08:32
VD-9001-204A-DWG-017 | 2 | Internal Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-04-03 14:24 | 2017-04-04 13:02 |  | No | 1 |  | 2017-04-08 11:58 | [6 empty] | 2017-04-08 20:59 | Yes | 0
VD-9001-108-DWG-027 | 3 | LADDER DETAIL | PR-108 | Farabard | 2017-04-17 21:00 | 2017-04-08 13:04 | 2017-04-08 13:03 | Yes | -9 |  | 2017-04-12 12:23 | [6 empty] | 2017-04-12 20:59 | Yes | -10
VD-9001-108-DWG-045 | 2 | PLATFORM & LADDER DETAIL DRAWING | PR-108 | Farabard | 2017-04-17 21:00 | 2017-04-08 16:40 |  | No | -9 |  | 2017-04-12 12:17 | [6 empty] | 2017-04-12 20:59 | Yes | 0
VD-9001-462A-PCJ-001 | 1 | Hardness Test Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-08 | 2019-07-29 16:17 | 2019-07-30 09:44 | Yes | 843 |  |  | 2019-07-31 14:27 | [5 empty] | 2019-07-31 14:27 | Yes | -12
VD-9001-462A-PCJ-002 | 1 | Heat Treatment Procedure (Nomalizing) | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-08 | 2019-07-29 16:19 | 2019-07-30 09:44 | Yes | 843 |  |  | 2019-07-31 14:22 | [5 empty] | 2019-07-31 14:22 | Yes | -12
VD-9001-253(A)-DWG-036 | 2 | PLENUM for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-04-08 14:52 | 2017-04-08 15:09 |  | No | 0 | 2017-04-10 09:58 | [7 empty] | 2017-04-10 20:59 | Yes | 0
VD-9001-462A-PCJ-004 | 1 | Rust Inhibitor Coating Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-08 | 2019-07-30 09:45 | 2019-07-30 09:47 | Yes | 843 |  |  | 2019-07-30 10:15 | [5 empty] | 2019-07-30 10:15 | Yes | -14
VD-9001-462A-ITP-001-0 | 1 | Inspection & Test Plan | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-08 | 2017-04-25 10:04 | 2017-04-25 10:05 | Yes | 17 |  | 2017-05-02 17:40 | [6 empty] | 2017-05-02 20:59 | Yes | -7
VD-9001-253(A)-DWG-036 | 3 | PLENUM for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-04-10 | 2017-04-12 16:14 | 2017-04-12 16:15 | Yes | 2 |  | 2017-04-12 16:57 | [6 empty] | 2017-04-12 21:00 | Yes | -14
VD-9001-253(A)-DWG-075 | 2 | GRATING DETAIL for 3002 | HM-253A | FATEH SANAT KIMIA | 2017-04-12 14:30 | 2017-04-12 14:48 | 2017-04-12 14:49 | Yes | 0 |  | 2017-04-12 15:02 | [6 empty] | 2017-04-12 20:59 | Yes | -14 | 1204-Owner-v | 2018-08-14 17:52
VD-9001-204B-PCJ-006 | 2 | Hydrostatic and Air Leak Test Procedure | PV-204B | ABAN AIR COOLER. | 2017-04-15 14:48 | 2017-04-17 11:35 |  | No | 2 | 2017-04-26 08:51 | [7 empty] | 2017-04-26 20:59 | Yes | 0
VD-9001-204B-PCJ-008 | 4 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2017-04-15 14:48 | 2017-05-17 10:52 |  | No | 32 | 2017-05-24 16:42 | [7 empty] | 2017-05-24 20:00 | Yes | 0
VD-9001-204B-MSS-001 | 3 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2017-04-15 14:49 | 2017-04-17 11:33 |  | No | 2 | 2017-04-24 17:30 | [7 empty] | 2017-04-24 20:59 | Yes | 0
VD-9001-204B-WMP-003 | 1 | Welding & NDT Map D-3006 | PV-204B | ABAN AIR COOLER. | 2017-04-15 | 2017-06-17 14:25 |  | No | 63 | 2017-07-24 14:21 | [7 empty] | 2017-07-24 19:58 | Yes | 0
VD-9001-204B-PCJ-004 | 3 | Liquid Penetrant Examination Procedure | PV-204B | ABAN AIR COOLER. | 2017-04-15 14:51 | 2017-04-17 11:34 |  | No | 2 | 2017-04-24 17:36 | [7 empty] | 2017-04-24 20:59 | Yes | 0
VD-9001-204B-WMP-002 | 1 | Welding & NDT Map D-1003 | PV-204B | ABAN AIR COOLER. | 2017-04-15 | 2017-06-18 10:21 |  | No | 64 | 2017-07-24 14:16 | [7 empty] | 2017-07-24 19:58 | Yes | 0
VD-9001-204B-WMP-004 | 1 | Welding & NDT Map D-3007 | PV-204B | ABAN AIR COOLER. | 2017-04-15 | 2017-06-17 14:26 |  | No | 63 | 2017-07-24 14:24 | [7 empty] | 2017-07-24 19:58 | Yes | 0
VD-9001-201-MSS-003 | 3 | FORGING MATERIAL SPECIFICATION (SA 336 F11 CL3) | PV-201 | ATB RIVA CALZONI SpA | 2017-04-15 15:12 | 2017-04-18 10:40 | 2017-04-18 10:41 | Yes | 3 |  | 2017-05-02 09:16 | [6 empty] | 2017-05-02 20:59 | Yes | 0 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-253(A)-DWG-006 | 2 | PLENUM for 2001 | HM-253A | FATEH SANAT KIMIA | 2017-04-16 08:55 | 2017-04-16 09:05 | 2017-04-16 09:06 | Yes | 0 |  | 2017-04-16 17:26 | [6 empty] | 2017-04-16 20:59 | Yes | -14
VD-9001-464A-ITP-001 | 0 | INSPECTION AND TEST PLAN(ITP) | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-18 08:34 |  | No | 3 | 2017-04-26 09:52 | [7 empty] | 2017-04-26 20:59 | Yes | 0
VD-9001-464A-PCJ-001 | 0 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 14:31 |  | No | 2 | 2017-04-26 09:24 | [7 empty] | 2017-04-26 20:59 | Yes | 0
VD-9001-464A-PCJ-002 | 0 | Repair Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 14:35 |  | No | 2 | 2017-05-06 09:26 | [7 empty] | 2017-05-06 20:58 | Yes | 0
VD-9001-464A-PCJ-003 | 0 | NDT Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 14:39 |  | No | 2 | 2017-04-26 08:56 | [7 empty] | 2017-04-26 20:59 | Yes | 0
VD-9001-464A-PCJ-004 | 0 | Painting Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 14:38 |  | No | 2 | 2017-04-26 09:35 | [7 empty] | 2017-04-26 20:59 | Yes | 0
VD-9001-464A-PCJ-005 | 0 | Packing & Marking Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-18 16:09 |  | No | 3 | 2017-05-03 13:50 | [7 empty] | 2017-05-03 20:59 | Yes | 0
VD-9001-464A-VLS-001 | 0 | Sub Vendor List | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 14:41 |  | No | 2 | 2017-05-03 13:56 | [7 empty] | 2017-05-03 20:59 | Yes | 0
VD-9001-464A-DIS-001 | 0 | Documents Index and Schedule | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 |  | 2017-04-18 09:04 | Yes | 1161 | [9 empty] | No | 0
VD-9001-464A-DWG-001 | 0 | General Drawings (Sectional/ Assembly/ BOM) | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-04-15 | 2017-04-17 16:12 |  | No | 2 |  | 2017-04-18 10:32 | [6 empty] | 2017-04-18 20:59 | Yes | 0
VD-9001-253(A)-DWG-053 | 2 | ASSEMBLY MARKING FOR STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-04-17 14:11 | 2017-04-17 14:27 |  | No | 0 | 2017-04-18 15:47 | [7 empty] | 2017-04-18 20:59 | Yes | 0 | 1204-Owner-v | 2018-05-16 09:45
VD-9001-253(A)-DWG-066 | 2 | PLENUM for 3002 | HM-253A | FATEH SANAT KIMIA | 2017-04-17 14:11 | 2017-04-17 14:29 | 2017-04-17 14:30 | Yes | 0 |  | 2017-04-30 08:03 | [6 empty] | 2017-04-30 20:59 | Yes | -1 | 1204-Owner-v | 2018-01-28 15:27
VD-9001-253(A)-DWG-053 | 3 | ASSEMBLY MARKING FOR STRUCTURE for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-04-18 | 2017-04-23 15:57 | 2017-04-23 15:58 | Yes | 5 |  | 2017-04-30 08:56 | [6 empty] | 2017-04-30 20:59 | Yes | -7 | 1204-Owner-v | 2018-08-14 17:44
VD-9001-108-DWG-045 | 3 | PLATFORM & LADDER DETAIL DRAWING | PR-108 | Farabard | 2017-04-24 09:28 | 2017-04-24 09:39 | 2017-04-24 09:40 | Yes | 0 |  | 2017-04-30 10:58 | [6 empty] | 2017-04-30 20:59 | Yes | -8
VD-9001-204B-MSS-001 | 4 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2017-04-24 | 2017-05-17 10:48 |  | No | 23 |  | 2017-05-28 09:15 | [6 empty] | 2017-05-28 19:59 | Yes | 0
VD-9001-204B-PCJ-004 | 4 | Liquid Penetrant Examination Procedure | PV-204B | ABAN AIR COOLER. | 2017-04-24 | 2017-05-17 10:49 | 2017-05-17 10:50 | Yes | 23 |  | 2017-05-24 15:06 | [6 empty] | 2017-05-24 20:00 | Yes | -7 | 1204-Owner-v | 2020-04-29 08:39
VD-9001-204B-PCJ-006 | 3 | Hydrostatic and Air Leak Test Procedure | PV-204B | ABAN AIR COOLER. | 2017-04-26 | 2017-05-17 10:51 |  | No | 21 |  | 2017-05-24 15:01 | [6 empty] | 2017-05-24 20:00 | Yes | 0
VD-9001-464A-PCJ-003 | 1 | NDT Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-10 | 2017-05-21 16:52 |  | No | 11 | 2017-05-28 16:16 | [7 empty] | 2017-05-28 20:00 | Yes | 0
VD-9001-464A-PCJ-001 | 1 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-10 | 2017-05-21 17:05 |  | No | 11 | 2017-05-28 16:35 | [7 empty] | 2017-05-28 20:00 | Yes | 0
VD-9001-464A-PCJ-004 | 1 | Painting Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-10 | 2017-05-21 16:55 |  | No | 11 | 2017-05-28 16:10 | [7 empty] | 2017-05-28 20:00 | Yes | 0
VD-9001-464A-ITP-001 | 1 | INSPECTION AND TEST PLAN(ITP) | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-10 | 2017-05-21 17:07 |  | No | 11 | 2017-05-28 15:49 | [7 empty] | 2017-05-28 20:00 | Yes | 0
VD-9001-204A-DWG-011 | 6 | General Arrangement Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-04-30 10:33 | 2017-04-30 10:47 | 2017-04-30 10:48 | Yes | 0 |  | 2017-04-30 18:00 | [6 empty] | 2017-04-30 20:59 | Yes | -14 | 1204-Owner-v | 2019-09-23 18:27
VD-9001-204A-DWG-131 | 4 | General Arrangement Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-04-30 10:33 | 2017-04-30 10:50 | 2017-04-30 10:51 | Yes | 0 |  | 2017-04-30 17:57 | [6 empty] | 2017-04-30 20:59 | Yes | -14 | 1204-Owner-v | 2020-04-25 08:58
VD-9001-204B-DWG-001 | 5 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-04-30 15:47 | 2017-05-01 09:03 | 2017-05-01 09:02 | Yes | 1 |  | 2017-05-09 15:36 | [6 empty] | 2017-05-09 20:59 | Yes | -6 | 1204-Owner-v | 2018-07-13 00:24
VD-9001-204B-DWG-025 | 4 | Internall attachment drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-05-01 11:02 | 2017-05-01 11:07 | 2017-05-01 11:06 | Yes | 0 |  | 2017-05-07 14:20 | [6 empty] | 2017-05-07 20:59 | Yes | -8 | 1204-Owner-v | 2018-05-19 07:32
VD-9001-464A-PCJ-005 | 1 | Packing & Marking Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-03 |  |  | No | 1143 | [9 empty] | No | 0
VD-9001-464A-VLS-001 | 1 | Sub Vendor List | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-03 | 2017-05-21 17:04 | 2017-05-21 17:05 | Yes | 18 |  | 2018-02-25 09:49 | [6 empty] | 2018-02-25 19:59 | Yes | 266
VD-9001-464A-PCJ-002 | 1 | Repair Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-06 |  |  | No | 1140 | [9 empty] | No | 0
VD-9001-257A-INX-001 | 1 | Final Data Book Index | HM-257A | ABAN AIR COOLER. | 2017-05-06 15:18 | 2017-05-06 15:25 | 2017-05-06 15:26 | Yes | 0 |  | 2017-05-06 16:40 | [6 empty] | 2017-05-06 20:59 | Yes | -14
VD-9001-257A-FDB-001 | 1 | Final Data Book | HM-257A | ABAN AIR COOLER. | 2017-05-20 20:59 | 2017-05-14 13:47 | 2017-05-14 13:48 | Yes | -6 |  | 2017-06-10 16:24 | [6 empty] | 2017-06-10 20:00 | Yes | 13
VD-9001-204B-DWG-005 | 3 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-05-07 | 2017-05-29 14:47 |  | No | 22 | 2017-05-31 14:19 | [7 empty] | 2017-05-31 20:00 | Yes | 0
VD-9001-253(A)-DSH-001 | 4 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2017-05-13 10:52 | 2017-05-13 11:56 | 2017-05-13 11:57 | Yes | 0 |  | 2017-08-30 14:09 | [6 empty] | 2017-08-30 19:57 | Yes | 95 | 1204-Owner-v | 2019-03-05 10:57
VD-9001-740A-ITP-001 | 0 | Inspection and Test Plan | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:16 |  | No | 35 | 2017-06-12 13:37 | [7 empty] | 2017-06-12 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:58
VD-9001-740A-PRC-001 | 0 | NDE Procedures (UT,MT,PT,RT) | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:23 |  | No | 35 | 2017-06-12 11:26 | [7 empty] | 2017-06-12 20:00 | Yes | 0
VD-9001-740A-PRC-002 | 0 | Welding Documents (WPS and PQR) | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:28 |  | No | 35 | 2017-06-12 11:41 | [7 empty] | 2017-06-12 20:00 | Yes | 0
VD-9001-740A-LST-001 | 0 | Vendor Print Index Schedule | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-12-11 15:45 | 2017-12-11 15:46 | Yes | 233 |  |  | 2019-02-19 09:05 | [5 empty] | 2019-02-19 09:05 | Yes | 421
VD-9001-740A-LST-002 | 0 | Sub-Supplier List | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-11-21 11:47 | 2017-11-21 11:48 | Yes | 213 |  |  | 2019-02-19 09:07 | [5 empty] | 2019-02-19 09:07 | Yes | 441
VD-9001-740A-LST-003 | 0 | Reference/Experience list | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-11-21 11:48 |  | No | 213 | 2017-12-03 11:54 | [7 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-740A-PRC-004 | 0 | Packing and Marking Procedure | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:31 |  | No | 35 | [9 empty] | No | 0
VD-9001-740A-FRM-008 | 0 | Welder Performance Qualification Certificates | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-11-21 11:45 | 2017-11-21 11:46 | Yes | 213 |  | 2017-12-31 16:50 | [6 empty] | 2017-12-31 19:59 | Yes | 26
VD-9001-740A-FRM-009 | 0 | NDE Operator Certificates | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:20 |  | No | 35 | 2017-06-12 13:41 | [7 empty] | 2017-06-12 20:00 | Yes | 0
VD-9001-740A-FRM-007 | 0 | Welding Map | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-28 10:56 |  | No | 36 | 2017-05-29 11:28 | [7 empty] | 2017-05-29 19:59 | Yes | 0
VD-9001-740A-PRC-005 | 0 | Surface Preparation and Painting Procedure/HDG Procedure | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-05-27 12:33 |  | No | 35 | 2017-06-12 14:05 | [7 empty] | 2017-06-12 20:00 | Yes | 0
VD-9001-740A-LST-007 | 0 | Vendor Data Book Index List | ST-740A | Pars Tadbir Gostar | 2017-04-22 | 2017-12-11 15:47 |  | No | 233 | [9 empty] | No | 0
VD-9001-740A-MOD-00088 | 0 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-29 09:49 |  | No | 15 | 2017-06-04 10:52 | [7 empty] | 2017-06-04 19:59 | Yes | 0
VD-9001-740A-GAD-00088 | 0 | General Arrangement Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-25 13:35 |  | No | 42 | 2017-06-25 18:45 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-SAD-00088 | 0 | Shop Assembly Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-25 14:05 |  | No | 42 | 2017-06-25 18:46 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-SPD-00088 | 0 | Single Part Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-25 14:07 | 2017-06-25 14:08 | Yes | 42 |  | 2018-02-27 09:02 | [6 empty] | 2018-02-27 19:59 | Yes | 233
VD-9001-740A-RPT-00088 | 0 | Reports-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-25 13:44 |  | No | 42 |  | 2017-07-02 11:33 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-MOD-00085 | 0 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-18 07:39 |  | No | 4 | 2017-05-22 11:34 | [7 empty] | 2017-05-22 20:00 | Yes | 0
VD-9001-740A-GAD-00085 | 0 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-03 10:59 |  | No | 50 |  | 2017-07-06 10:16 | [6 empty] | 2017-07-06 19:59 | Yes | 0
VD-9001-740A-SAD-00085 | 0 | Shop Assembly Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-03 12:01 |  | No | 50 | [9 empty] | No | 0
VD-9001-740A-SPD-00085 | 0 | Single Part Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-03 12:04 | 2017-07-03 12:05 | Yes | 50 |  | 2018-02-27 09:05 | [6 empty] | 2018-02-27 19:59 | Yes | 225
VD-9001-740A-RPT-00085 | 0 | Reports-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-03 11:39 |  | No | 50 |  | 2017-07-06 10:09 | [6 empty] | 2017-07-06 19:59 | Yes | 0
VD-9001-740A-MOD-00086 | 0 | Models-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-07 12:38 |  | No | 24 | 2017-06-18 17:33 | [7 empty] | 2017-06-18 20:00 | Yes | 0
VD-9001-740A-GAD-00086 | 0 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-16 11:34 |  | No | 63 | 2017-07-17 18:12 | [7 empty] | 2017-07-17 19:59 | Yes | 0
VD-9001-740A-SAD-00086 | 0 | Shop Assembly Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-05 09:47 |  | No | 52 | [9 empty] | No | 0
VD-9001-740A-SPD-00086 | 0 | Single Part Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-05 09:49 | 2017-07-05 09:50 | Yes | 52 |  | 2018-02-27 09:07 | [6 empty] | 2018-02-27 19:59 | Yes | 223
VD-9001-740A-RPT-00086 | 0 | Reports-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-05 09:17 |  | No | 52 |  | 2017-07-09 10:02 | [6 empty] | 2017-07-09 19:59 | Yes | 0
VD-9001-740A-MOD-00302 | 0 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-29 09:37 |  | No | 15 | 2017-06-01 09:56 | [7 empty] | 2017-06-01 19:59 | Yes | 0
VD-9001-740A-GAD-00302 | 0 | General Arrangement Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-10 10:22 |  | No | 57 |  | 2017-07-11 15:14 | [6 empty] | 2017-07-11 19:59 | Yes | 0
VD-9001-740A-SAD-00302 | 0 | Shop Assembly Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-10 11:00 |  | No | 57 | [9 empty] | No | 0
VD-9001-740A-SPD-00302 | 0 | Single Part Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-10 11:03 | 2017-07-10 11:04 | Yes | 57 |  | 2018-02-27 08:50 | [6 empty] | 2018-02-27 19:59 | Yes | 218
VD-9001-740A-RPT-00302 | 0 | Reports-STR.B | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-07-10 10:35 |  | No | 57 |  | 2017-07-11 15:01 | [6 empty] | 2017-07-11 19:59 | Yes | 0
VD-9001-740A-MOD-00332 | 0 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-21 08:54 |  | No | 7 | 2017-05-28 15:14 | [7 empty] | 2017-05-28 20:00 | Yes | 0
VD-9001-740A-GAD-00332 | 0 | General Arrangement Drawings-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:28 |  | No | 44 |  | 2017-07-02 11:03 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-SAD-00332 | 0 | Shop Assembly Drawings-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:46 |  | No | 44 | [9 empty] | No | 0
VD-9001-740A-SPD-00332 | 0 | Single Part Drawings-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:48 | 2017-06-27 09:49 | Yes | 44 |  | 2018-02-27 09:00 | [6 empty] | 2018-02-27 19:59 | Yes | 231
VD-9001-740A-RPT-00332 | 0 | Reports-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:36 |  | No | 44 |  | 2017-07-02 10:36 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-MOD-00353 | 0 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-04 12:02 |  | No | 21 | 2017-06-05 13:17 | [7 empty] | 2017-06-05 19:59 | Yes | 0
VD-9001-740A-GAD-00353 | 0 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-24 13:30 |  | No | 41 | 2017-06-25 17:16 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-SAD-00353 | 0 | Shop Assembly Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-24 13:56 |  | No | 41 | 2017-06-25 17:13 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-SPD-00353 | 0 | Single Part Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-24 13:59 |  | No | 41 | 2017-06-25 17:14 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-RPT-00353 | 0 | Reports-STR.F | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-24 13:31 |  | No | 41 | 2017-06-25 17:12 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-MOD-00316 | 0 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-18 07:28 |  | No | 4 | 2017-05-22 10:26 | [7 empty] | 2017-05-22 20:00 | Yes | 0
VD-9001-740A-GAD-00316 | 0 | General Arrangement Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:53 |  | No | 44 | 2017-07-04 10:07 | [7 empty] | 2017-07-04 19:59 | Yes | 0
VD-9001-740A-SAD-00316 | 0 | Shop Assembly Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:58 |  | No | 44 | [9 empty] | No | 0
VD-9001-740A-SPD-00316 | 0 | Single Part Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 10:00 | 2017-06-27 10:01 | Yes | 44 |  | 2018-02-27 08:58 | [6 empty] | 2018-02-27 19:59 | Yes | 231
VD-9001-740A-RPT-00316 | 0 | Reports-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 09:54 |  | No | 44 |  | 2017-07-02 11:08 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-MOD-00112 | 0 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-05-20 16:01 |  | No | 6 | 2017-05-27 13:59 | [7 empty] | 2017-05-27 20:00 | Yes | 0
VD-9001-740A-GAD-00112 | 0 | General Arrangement Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 10:03 |  | No | 44 |  | 2017-07-02 11:21 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-SAD-00112 | 0 | Shop Assembly Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 10:20 |  | No | 44 | [9 empty] | No | 0
VD-9001-740A-SPD-00112 | 0 | Single Part Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 10:21 | 2017-06-27 10:22 | Yes | 44 |  | 2018-02-27 08:56 | [6 empty] | 2018-02-27 19:59 | Yes | 231
VD-9001-740A-RPT-00112 | 0 | Reports-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-14 | 2017-06-27 10:13 |  | No | 44 |  | 2017-07-02 11:24 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-201-PCJ-023 | 0 | Dimensional Check Procedure | PV-201 | ATB RIVA CALZONI SpA | 2017-05-16 | 2017-05-16 18:22 | 2017-05-16 18:21 | Yes | 0 |  | 2017-06-19 15:52 | [6 empty] | 2017-06-19 20:00 | Yes | 20 | 1204-Owner-v | 2018-03-13 13:26
VD-9001-204B-DIS-001 | 1 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2017-05-16 14:44 | 2017-05-17 08:56 |  | No | 1 | 2017-05-25 12:44 | [7 empty] | 2017-05-25 19:59 | Yes | 0
VD-9001-204B-PCJ-011 | 0 | PMI Procedure | PV-204B | ABAN AIR COOLER. | 2017-05-16 | 2017-05-17 10:53 |  | No | 1 | 2017-05-24 14:55 | [7 empty] | 2017-05-24 20:00 | Yes | 0
VD-9001-201-DWG-003 | 2 | TOP COVER & MAIN FLANGE | PV-201 | ATB RIVA CALZONI SpA | 2017-06-04 20:00 | 2017-09-15 19:49 |  | No | 103 | 2017-12-05 11:19 | [7 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-740A-MOD-00316 | 1 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-22 | 2017-05-23 15:01 |  | No | 1 | 2017-05-24 17:32 | [7 empty] | 2017-05-24 20:00 | Yes | 0
VD-9001-740A-MOD-00085 | 1 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-22 | 2017-05-28 11:07 |  | No | 6 | 2017-05-30 10:34 | [7 empty] | 2017-05-30 19:59 | Yes | 0
VD-9001-201-DWG-001 | 3 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2017-06-06 20:00 | 2017-10-05 19:44 |  | No | 121 | 2017-11-04 18:39 | [7 empty] | 2017-11-04 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 11:17
VD-9001-204B-PCJ-011 | 1 | PMI Procedure | PV-204B | ABAN AIR COOLER. | 2017-05-24 | 2017-05-27 08:44 | 2017-05-27 08:45 | Yes | 3 |  | 2017-05-29 16:44 | [6 empty] | 2017-05-29 20:00 | Yes | -12 | 1204-Owner-v | 2020-04-29 08:42
VD-9001-204B-PCJ-008 | 5 | Post Weld Heat Treatment Procedure | PV-204B | ABAN AIR COOLER. | 2017-05-24 | 2017-05-27 08:44 | 2017-05-27 08:45 | Yes | 3 |  | 2017-05-29 16:48 | [6 empty] | 2017-05-29 20:00 | Yes | -12 | 1204-Owner-v | 2019-02-02 09:01
VD-9001-740A-MOD-00316 | 2 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-24 | 2017-05-28 11:10 |  | No | 4 | 2017-05-29 10:12 | [7 empty] | 2017-05-29 19:59 | Yes | 0
VD-9001-204B-DIS-001 | 2 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2017-05-25 | 2017-05-27 12:23 |  | No | 2 |  | 2017-05-27 14:16 | [6 empty] | 2017-05-27 20:00 | Yes | 0
VD-9001-740A-MOD-00112 | 1 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-27 | 2017-05-28 11:14 |  | No | 1 | 2017-05-29 11:34 | [7 empty] | 2017-05-29 19:59 | Yes | 0
VD-9001-740A-MOD-00332 | 1 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-28 | 2017-05-29 12:18 |  | No | 1 | 2017-05-29 17:59 | [7 empty] | 2017-05-29 20:00 | Yes | 0
VD-9001-464A-ITP-001 | 2 | INSPECTION AND TEST PLAN(ITP) | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-28 | 2017-05-29 11:29 | 2017-05-29 11:30 | Yes | 1 |  | 2017-05-30 09:13 | [6 empty] | 2017-05-30 19:59 | Yes | -13
VD-9001-464A-PCJ-004 | 2 | Painting Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-28 | 2017-05-29 12:11 | 2017-05-29 12:13 | Yes | 1 |  | 2017-05-30 09:23 | [6 empty] | 2017-05-30 19:59 | Yes | -13
VD-9001-464A-PCJ-003 | 2 | NDT Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-28 | 2017-05-29 12:10 | 2017-05-29 12:11 | Yes | 1 |  | 2017-05-30 09:16 | [6 empty] | 2017-05-30 19:59 | Yes | -13
VD-9001-464A-PCJ-001 | 2 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-05-28 | 2017-05-29 12:09 |  | No | 1 |  | 2017-05-30 09:20 | [6 empty] | 2017-05-30 19:59 | Yes | 0
VD-9001-206B-PCJ-015 | 5 | PAINTING PROCEDURE | PV-206B | TASHA | 2017-05-29 09:55 | 2017-05-29 11:08 | 2017-05-29 11:08 | Yes | 0 |  | 2018-01-02 11:05 | [6 empty] | 2018-01-02 19:59 | Yes | 204
VD-9001-740A-MOD-00316 | 3 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-05-29 | 2017-05-31 15:31 |  | No | 2 | 2017-06-01 10:18 | [7 empty] | 2017-06-01 19:59 | Yes | 0
VD-9001-740A-MOD-00112 | 2 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-05-29 | 2017-06-03 15:01 |  | No | 5 | 2017-06-04 10:51 | [7 empty] | 2017-06-04 19:59 | Yes | 0
VD-9001-740A-MOD-00332 | 2 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-29 | 2017-05-31 09:03 |  | No | 2 | 2017-05-31 16:41 | [7 empty] | 2017-05-31 20:00 | Yes | 0
VD-9001-740A-FRM-007 | 1 | Welding Map | ST-740A | Pars Tadbir Gostar | 2017-06-12 19:59 | 2017-06-17 09:15 | 2017-06-17 09:14 | Yes | 5 |  | 2017-06-21 17:06 | [6 empty] | 2017-06-21 20:00 | Yes | -10
VD-9001-740A-MOD-00085 | 2 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-05-30 | 2017-06-04 12:09 |  | No | 5 | 2017-06-18 09:55 | [7 empty] | 2017-06-18 19:59 | Yes | 0
VD-9001-204B-DWG-005 | 4 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-05-31 | 2017-06-14 09:54 | 2017-06-14 09:55 | Yes | 14 |  | 2017-06-18 14:32 | [6 empty] | 2017-06-18 20:00 | Yes | -10
VD-9001-740A-MOD-00332 | 3 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-05-31 | 2017-06-03 10:07 |  | No | 3 | 2017-06-04 10:48 | [7 empty] | 2017-06-04 19:59 | Yes | 0
VD-9001-740A-MOD-00302 | 1 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-06-01 | 2017-06-07 13:25 |  | No | 6 | 2017-06-17 14:08 | [7 empty] | 2017-06-17 20:00 | Yes | 0
VD-9001-740A-MOD-00316 | 4 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-06-01 | 2017-06-03 09:57 |  | No | 2 |  | 2017-07-04 17:03 | [6 empty] | 2017-07-04 19:59 | Yes | 0
VD-9001-740A-MOD-00332 | 4 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-06-04 | 2017-06-07 13:36 |  | No | 3 | 2017-06-08 12:58 | [7 empty] | 2017-06-09 20:00 | Yes | 0
VD-9001-740A-MOD-00112 | 3 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-06-04 | 2017-06-07 13:07 |  | No | 3 |  | 2017-07-04 17:00 | [6 empty] | 2017-07-04 19:59 | Yes | 0
VD-9001-740A-MOD-00088 | 1 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-06-04 | 2017-06-07 13:04 |  | No | 3 | 2017-06-08 13:00 | [7 empty] | 2017-06-09 20:00 | Yes | 0
VD-9001-740A-MOD-00353 | 1 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-05 | 2017-06-08 10:35 |  | No | 3 | 2017-06-13 14:23 | [7 empty] | 2017-06-13 20:00 | Yes | 0
VD-9001-740A-MOD-00332 | 5 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-06-08 | 2017-06-27 09:35 |  | No | 19 |  | 2017-07-04 16:23 | [6 empty] | 2017-07-04 19:59 | Yes | 0
VD-9001-740A-MOD-00088 | 2 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-06-08 | 2017-06-19 09:35 |  | No | 11 | 2017-06-20 09:52 | [7 empty] | 2017-06-20 19:59 | Yes | 0
VD-9001-740A-PRC-001 | 1 | NDE Procedures (UT,MT,PT,RT) | ST-740A | Pars Tadbir Gostar | 2017-06-12 | 2017-06-17 09:05 | 2017-06-17 09:06 | Yes | 5 |  | 2017-11-29 17:05 | [6 empty] | 2017-11-29 20:00 | Yes | 151
VD-9001-740A-PRC-002 | 1 | Welding Documents (WPS and PQR) | ST-740A | Pars Tadbir Gostar | 2017-06-12 | 2017-06-19 15:38 |  | No | 7 | 2017-07-16 12:27 | [7 empty] | 2017-07-16 19:59 | Yes | 0
VD-9001-740A-ITP-001 | 1 | Inspection and Test Plan | ST-740A | Pars Tadbir Gostar | 2017-06-12 | 2017-06-17 09:03 | 2017-06-17 09:04 | Yes | 5 |  | 2017-06-19 18:38 | [6 empty] | 2017-06-19 20:00 | Yes | -12 | 1204-Owner-v | 2020-01-01 12:58
VD-9001-740A-FRM-009 | 1 | NDE Operator Certificates | ST-740A | Pars Tadbir Gostar | 2017-06-12 | 2017-06-17 09:03 | 2017-06-17 09:04 | Yes | 5 |  | 2017-06-21 17:08 | [6 empty] | 2017-06-21 20:00 | Yes | -10
VD-9001-740A-PRC-005 | 1 | Surface Preparation and Painting Procedure/HDG Procedure | ST-740A | Pars Tadbir Gostar | 2017-06-12 | 2017-06-17 09:08 | 2017-06-17 09:08 | Yes | 5 |  | 2017-06-21 17:05 | [6 empty] | 2017-06-21 20:00 | Yes | -10
VD-9001-206B-DWG-011 | 5 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2017-06-13 14:08 | 2017-06-20 16:22 |  | No | 7 | 2018-02-03 17:19 | [7 empty] | 2018-02-03 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-07 14:06
VD-9001-740A-MOD-00353 | 2 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-13 | 2017-06-15 08:15 |  | No | 2 | 2017-06-17 14:15 | [7 empty] | 2017-06-17 20:00 | Yes | 0
VD-9001-204A-DWG-021 | 4 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:20 | 2017-08-13 14:20 |  | No | 60 |  | 2017-08-13 16:41 | [6 empty] | 2017-08-13 19:58 | Yes | 0 | 1204-Owner-v | 2019-07-09 13:17
VD-9001-204A-DWG-061 | 6 | General Arrangement Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:20 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-DWG-111 | 5 | General Arrangement Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:20 | 2017-06-21 15:37 | 2017-06-21 15:38 | Yes | 7 |  | 2017-06-25 16:56 | [6 empty] | 2017-06-25 20:00 | Yes | -10 | 1204-Owner-v | 2020-04-25 08:57
VD-9001-204A-DWG-171 | 4 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:21 | 2017-06-20 12:18 |  | No | 6 | 2017-09-23 10:38 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-016 | 2 | External Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:21 | 2017-09-17 17:08 | 2017-09-17 17:08 | Yes | 95 |  | 2017-09-25 15:15 | [6 empty] | 2017-09-25 18:58 | Yes | -6
VD-9001-204A-DWG-046 | 3 | External Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:21 | 2017-06-20 08:59 |  | No | 6 | 2017-09-26 10:05 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-086 | 2 | External Attachment Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:21 | 2017-06-20 10:43 |  | No | 6 | 2017-09-26 09:33 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-096 | 3 | External Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:21 | 2017-06-21 12:44 |  | No | 7 | 2017-09-26 11:04 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-106 | 4 | External Attachment Drawing FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:22 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-DWG-116 | 1 | External Attachment Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:22 | 2017-06-22 07:41 |  | No | 8 | 2017-10-22 15:13 | [7 empty] | 2017-10-22 19:59 | Yes | 0
VD-9001-204A-DWG-136 | 2 | External Attachment Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:22 | 2017-06-22 11:56 |  | No | 8 | 2017-09-26 11:53 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-015 | 2 | PF & LD Arrangement FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:22 | 2017-06-21 11:00 |  | No | 7 | 2017-09-23 11:15 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-025 | 4 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:22 | 2017-07-03 14:13 |  | No | 19 | 2017-09-26 14:36 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-045 | 2 | PF & LD Arrangement FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-20 08:44 |  | No | 6 | 2017-09-26 10:20 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-095 | 3 | PF & LD Arrangement FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-21 13:02 | 2017-06-21 13:01 | Yes | 7 |  | 2017-06-25 16:42 | [6 empty] | 2017-06-25 20:00 | Yes | -10 | 1204-Owner-v | 2018-12-29 10:19
VD-9001-204A-DWG-115 | 3 | PF & LD Arrangement FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-22 07:54 | 2017-06-22 07:54 | Yes | 8 |  | 2017-06-25 16:48 | [6 empty] | 2017-06-25 20:00 | Yes | -11 | 1204-Owner-v | 2018-12-29 10:20
VD-9001-204A-DWG-125 | 3 | PF & LD Arrangement FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-22 09:22 | 2017-06-22 09:22 | Yes | 8 |  | 2017-06-25 16:39 | [6 empty] | 2017-06-25 20:00 | Yes | -11 | 1204-Owner-v | 2018-12-29 10:21
VD-9001-204A-DWG-145 | 3 | PF & LD Arrangement FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-20 11:30 |  | No | 6 | 2017-09-26 09:11 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-155 | 3 | PF & LD Arrangement FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-06-20 11:41 |  | No | 6 | 2017-09-23 12:16 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-024 | 2 | PF & LD Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:23 | 2017-07-03 15:29 |  | No | 19 | 2017-09-26 14:50 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-044 | 2 | PF & LD Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-20 08:54 |  | No | 6 | 2017-09-26 10:10 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-124 | 2 | PF & LD Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-22 10:18 |  | No | 8 | 2017-09-26 11:14 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-144 | 3 | PF & LD Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-24 14:17 |  | No | 10 | 2017-09-26 14:23 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-174 | 4 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-20 13:06 |  | No | 6 | 2017-09-26 15:21 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-012 | 3 | Nozzle Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-21 10:48 |  | No | 7 | 2017-09-23 11:33 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-022 | 3 | Nozzle Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-07-03 13:48 |  | No | 19 | 2017-09-26 14:27 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-032 | 2 | Nozzle Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-20 08:10 |  | No | 6 | 2017-09-26 10:36 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-052 | 2 | Nozzle Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-21 10:16 |  | No | 7 | 2017-09-23 11:43 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-062 | 2 | Nozzle Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:24 | 2017-06-20 09:28 |  | No | 6 | 2017-09-26 09:57 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-092 | 2 | Nozzle Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-21 13:20 |  | No | 7 | 2017-09-26 12:13 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-112 | 3 | Nozzle Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-22 08:03 |  | No | 8 | 2017-09-26 11:09 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-122 | 2 | Nozzle Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-22 10:27 |  | No | 8 | 2017-09-26 11:34 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-132 | 2 | Nozzle Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-22 12:06 |  | No | 8 | 2017-09-26 12:02 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-152 | 2 | Nozzle Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-20 12:02 |  | No | 6 | 2017-09-23 12:09 | [7 empty] | 2017-09-23 18:58 | Yes | 0
VD-9001-204A-DWG-172 | 2 | Nozzle Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-06-24 08:57 |  | No | 10 | 2017-09-26 12:08 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-029 | 2 | Shipping Drawing for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:25 | 2017-07-03 15:37 |  | No | 19 | 2017-10-22 15:15 | [7 empty] | 2017-10-22 19:59 | Yes | 0 | 1204-Owner-v | 2019-07-31 17:21
VD-9001-204A-DWG-109 | 2 | Shipping Drawing for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-21 13:36 | 2017-06-21 13:36 | Yes | 7 |  | 2017-06-24 16:30 | [6 empty] | 2017-06-24 20:00 | Yes | -11
VD-9001-204A-DWG-129 | 2 | Shipping Drawing for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-22 10:31 | 2017-06-22 10:32 | Yes | 8 |  | 2017-06-25 10:38 | [6 empty] | 2017-06-25 19:59 | Yes | -11
VD-9001-204A-DWG-139 | 2 | Shipping Drawing for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-22 12:39 | 2017-06-22 12:40 | Yes | 8 |  | 2017-06-25 10:27 | [6 empty] | 2017-06-25 19:59 | Yes | -11
VD-9001-204A-DWG-017 | 3 | Internal Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-21 12:17 |  | No | 7 | 2017-09-26 10:55 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-018 | 2 | Template & Gauge Plate FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-21 12:28 | 2017-06-21 12:28 | Yes | 7 |  | 2017-06-24 16:52 | [6 empty] | 2017-06-24 20:00 | Yes | -11 | 1204-Owner-v | 2019-05-09 08:21
VD-9001-204A-DWG-118 | 2 | Template & Gauge Plate FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-22 08:33 | 2017-06-22 08:33 | Yes | 8 |  | 2017-06-25 10:43 | [6 empty] | 2017-06-25 19:59 | Yes | -11 | 1204-Owner-v | 2019-05-09 08:21
VD-9001-204A-DWG-128 | 2 | Template & Gauge Plate FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:26 | 2017-06-22 10:50 | 2017-06-22 10:50 | Yes | 8 |  | 2017-06-25 10:50 | [6 empty] | 2017-06-25 19:59 | Yes | -11 | 1204-Owner-v | 2019-05-09 08:21
VD-9001-204A-CAL-010 | 3 | Strength Calculation for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:27 | 2017-06-21 11:23 | 2017-06-21 11:24 | Yes | 7 |  | 2017-08-12 17:04 | [6 empty] | 2017-08-12 19:59 | Yes | 38
VD-9001-204A-CAL-030 | 4 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:28 | 2017-06-20 08:17 |  | No | 6 | 2017-09-20 13:35 | [7 empty] | 2017-09-20 18:57 | Yes | 0
VD-9001-204A-CAL-050 | 3 | Strength Calculation FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:28 | 2017-09-18 16:33 | 2017-09-18 16:34 | Yes | 96 |  | 2017-09-19 15:08 | [6 empty] | 2017-09-19 19:57 | Yes | -13
VD-9001-204A-CAL-060 | 3 | Strength Calculation FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:28 | 2017-06-20 10:27 | 2017-06-20 10:26 | Yes | 6 |  | 2017-09-10 17:04 | [6 empty] | 2017-09-10 19:57 | Yes | 68
VD-9001-204A-CAL-070 | 3 | Strength Calculation FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:28 | 2017-06-20 10:30 | 2017-06-20 10:30 | Yes | 6 |  | 2017-09-11 09:24 | [6 empty] | 2017-09-11 19:57 | Yes | 69
VD-9001-204A-CAL-080 | 3 | Strength Calculation FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-18 12:49 | 2017-06-18 12:49 | Yes | 4 |  | 2017-08-05 16:36 | [6 empty] | 2017-08-05 19:59 | Yes | 34
VD-9001-204A-CAL-090 | 3 | Strength Calculation FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-18 14:31 | 2017-06-18 14:29 | Yes | 4 |  | 2017-08-13 11:39 | [6 empty] | 2017-08-13 19:58 | Yes | 42
VD-9001-204A-CAL-100 | 3 | Strength Calculation FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-21 15:25 | 2017-06-21 15:26 | Yes | 7 |  | 2017-08-13 11:51 | [6 empty] | 2017-08-13 19:58 | Yes | 39
VD-9001-204A-CAL-110 | 3 | Strength Calculation FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-22 08:57 | 2017-06-22 08:57 | Yes | 8 |  | 2017-08-13 12:06 | [6 empty] | 2017-08-13 19:58 | Yes | 38
VD-9001-204A-CAL-120 | 5 | Strength Calculation FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-22 11:47 | 2017-06-22 11:47 | Yes | 8 |  | 2017-08-13 12:12 | [6 empty] | 2017-08-13 19:58 | Yes | 38
VD-9001-204A-CAL-130 | 3 | Strength Calculation FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-22 12:58 | 2017-06-22 12:57 | Yes | 8 |  | 2017-08-22 14:48 | [6 empty] | 2017-08-22 19:58 | Yes | 47
VD-9001-204A-CAL-140 | 3 | Strength Calculation FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-20 11:13 | 2017-06-20 11:12 | Yes | 6 |  | 2017-08-23 15:54 | [6 empty] | 2017-08-23 19:58 | Yes | 50
VD-9001-204A-CAL-150 | 4 | Strength Calculation FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-20 11:50 | 2017-06-20 11:51 | Yes | 6 |  | 2017-09-05 14:16 | [6 empty] | 2017-09-05 19:57 | Yes | 63
VD-9001-204A-CAL-160 | 3 | Strength Calculation FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:29 | 2017-06-24 07:52 | 2017-06-24 07:51 | Yes | 10 |  | 2017-09-05 14:20 | [6 empty] | 2017-09-05 19:57 | Yes | 59
VD-9001-204A-CAL-170 | 3 | Strength Calculation FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:30 | 2017-06-20 13:40 | 2017-06-20 13:40 | Yes | 6 |  | 2017-09-05 15:19 | [6 empty] | 2017-09-05 19:57 | Yes | 63
VD-9001-204A-CAL-029 | 1 | Lifting Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:30 | 2017-06-21 09:59 | 2017-06-21 10:00 | Yes | 7 |  | 2017-08-13 11:21 | [6 empty] | 2017-08-13 19:58 | Yes | 39
VD-9001-204A-CAL-059 | 1 | LIFTING CALCULATION D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:30 | 2017-06-21 08:47 | 2017-06-21 08:47 | Yes | 7 |  | 2017-08-13 11:25 | [6 empty] | 2017-08-13 19:58 | Yes | 39
VD-9001-204A-CAL-099 | 1 | LIFTING CALCULATION D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:30 | 2017-06-20 14:08 | 2017-06-20 14:07 | Yes | 6 |  | 2017-08-13 11:44 | [6 empty] | 2017-08-13 19:58 | Yes | 40
VD-9001-204A-CAL-109 | 1 | LIFTING CALCULATION D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:30 | 2017-06-20 14:24 | 2017-06-20 14:25 | Yes | 6 |  | 2017-08-13 11:58 | [6 empty] | 2017-08-13 19:58 | Yes | 40
VD-9001-204A-CAL-119 | 1 | LIFTING CALCULATION D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 | 2017-06-20 14:32 | 2017-06-20 14:33 | Yes | 6 |  | 2017-08-13 12:08 | [6 empty] | 2017-08-13 19:58 | Yes | 40
VD-9001-204A-CAL-169 | 1 | LIFTING CALCULATION D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 | 2017-06-21 09:28 | 2017-06-21 09:29 | Yes | 7 |  | 2017-09-05 14:25 | [6 empty] | 2017-09-05 19:57 | Yes | 62
VD-9001-204A-CAL-051 | 2 | Shipping Calculation for D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-091 | 2 | Shipping Calculation for D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-101 | 2 | Shipping Calculation for D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-111 | 2 | Shipping Calculation for D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-121 | 2 | Shipping Calculation for D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-131 | 2 | Shipping Calculation for D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:31 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-204A-CAL-161 | 2 | Shipping Calculation for D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-06-14 10:32 |  |  | No | 1101 | [9 empty] | No | 0
VD-9001-201-WBK-001 | 1 | WELDING DATA BOOK | PV-201 | ATB RIVA CALZONI SpA | 2017-06-28 20:00 | 2017-10-10 18:21 |  | No | 104 | 2017-10-23 17:15 | [7 empty] | 2017-10-23 20:00 | Yes | 0
VD-9001-201-PCJ-018 | 1 | PRODUCTION TEST PLATES PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2017-06-28 20:00 | 2017-06-22 19:35 | 2017-06-22 19:30 | Yes | -6 |  | 2017-07-04 12:01 | [6 empty] | 2017-07-04 19:59 | Yes | -2 | 1204-Owner-v | 2018-04-04 13:40
VD-9001-201-CAL-002 | 2 | FOUNDATION LOADS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2017-06-28 20:00 | 2017-06-21 19:38 |  | No | -7 | 2017-08-01 16:41 | [7 empty] | 2017-08-01 19:59 | Yes | 0
VD-9001-740A-MOD-00302 | 2 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-06-17 | 2017-06-21 10:24 |  | No | 4 | 2017-06-24 10:52 | [7 empty] | 2017-06-24 19:59 | Yes | 0
VD-9001-740A-MOD-00353 | 3 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-17 | 2017-06-19 09:17 |  | No | 2 | 2017-07-05 10:09 | [7 empty] | 2017-07-05 19:59 | Yes | 0
VD-9001-740A-MOD-00085 | 3 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-06-18 | 2017-06-22 09:36 |  | No | 4 | 2017-06-25 17:12 | [7 empty] | 2017-06-25 20:00 | Yes | 0
VD-9001-740A-MOD-00086 | 1 | Models-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-06-18 | 2017-06-21 15:27 |  | No | 3 | 2017-06-27 13:14 | [7 empty] | 2017-06-27 19:59 | Yes | 0
VD-9001-206B-DWG-019 | 2 | NAME PLATE DRAWING -T-1001 | PV-206B | TASHA | 2017-06-19 09:42 | 2017-06-20 16:31 |  | No | 1 | [9 empty] | No | 0
VD-9001-206B-DWG-049 | 2 | NAME PLATE DRAWING -T-2001 | PV-206B | TASHA | 2017-06-19 09:42 | 2017-06-20 16:32 |  | No | 1 | [9 empty] | No | 0
VD-9001-206B-DWG-079 | 2 | NAME PLATE DRAWING -T-4001 | PV-206B | TASHA | 2017-06-19 09:42 | 2017-06-20 16:33 |  | No | 1 | [9 empty] | No | 0
VD-9001-740A-MOD-00353 | 4 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-19 | 2017-06-24 13:27 |  | No | 5 | 2017-06-25 10:31 | [7 empty] | 2017-06-25 19:59 | Yes | 0
VD-9001-204A-WBK-001 | 5 | Welding Book (WPS,PQR and Welding/NDT Map) | PV-204A | Asas Sanat Pars Inc. | 2017-06-19 16:08 | 2017-06-19 17:58 | 2017-06-19 17:59 | Yes | 0 |  | 2017-09-11 10:13 | [6 empty] | 2017-09-11 19:57 | Yes | 70
VD-9001-740A-MOD-00088 | 3 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-06-20 | 2017-06-25 13:41 |  | No | 5 | 2017-07-01 11:54 | [7 empty] | 2017-07-01 19:59 | Yes | 0
VD-9001-740A-MOD-00302 | 3 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-06-24 | 2017-07-03 10:09 |  | No | 9 | 2017-07-06 11:09 | [7 empty] | 2017-07-06 19:59 | Yes | 0
VD-9001-201-ITP-001 | 1 | QUALITY CONTROL PLAN | PV-201 | ATB RIVA CALZONI SpA | 2017-07-08 20:00 | 2017-06-26 13:02 |  | No | -12 | 2017-07-10 15:00 | [7 empty] | 2017-07-10 19:59 | Yes | 0
VD-9001-740A-MOD-00353 | 5 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 10:39 |  | No | 6 | 2017-07-02 14:31 | [7 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-204B-WPS-001 | 2 | Welding Procedure Specification (WPS) For S.S | PV-204B | ABAN AIR COOLER. | 2017-06-25 | 2018-01-31 12:01 |  | No | 220 | 2018-02-26 09:41 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-204B-PQR-001 | 2 | Procedure Qualification Record (PQR) For S.S | PV-204B | ABAN AIR COOLER. | 2017-06-25 | 2018-01-31 13:55 |  | No | 220 | 2018-02-26 09:38 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-204B-PQR-002 | 2 | Procedure Qualification Record (PQR) For C.S | PV-204B | ABAN AIR COOLER. | 2017-06-25 | 2018-01-31 14:06 |  | No | 220 | 2018-02-26 09:34 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-740A-MOD-00085 | 4 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-03 11:37 |  | No | 8 |  | 2017-07-09 09:50 | [6 empty] | 2017-07-09 19:59 | Yes | 0
VD-9001-740A-RPT-00353 | 1 | Reports-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 10:39 |  | No | 6 |  | 2017-07-02 14:20 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-SAD-00353 | 1 | Shop Assembly Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 11:28 |  | No | 6 | [9 empty] | No | 0
VD-9001-740A-SPD-00353 | 1 | Single Part Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 11:31 | 2017-07-01 11:32 | Yes | 6 |  | 2018-02-27 08:53 | [6 empty] | 2018-02-27 19:59 | Yes | 227
VD-9001-740A-GAD-00353 | 1 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 10:10 |  | No | 6 |  | 2017-07-02 14:24 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-GAD-00088 | 1 | General Arrangement Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 11:34 |  | No | 6 |  | 2017-07-02 11:36 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-SAD-00088 | 1 | Shop Assembly Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-06-25 | 2017-07-01 14:16 |  | No | 6 | [9 empty] | No | 0
VD-9001-740A-MOD-00086 | 2 | Models-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-06-27 | 2017-07-05 09:16 |  | No | 8 |  | 2017-07-09 10:03 | [6 empty] | 2017-07-09 19:59 | Yes | 0
VD-9001-204B-WPS-002 | 2 | Welding Procedure Specification (WPS) For C.S | PV-204B | ABAN AIR COOLER. | 2017-06-28 | 2018-01-31 12:03 |  | No | 217 | 2018-02-26 09:40 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-740A-MOD-00088 | 4 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-07-01 | 2017-07-01 13:56 |  | No | 0 |  | 2017-07-02 11:37 | [6 empty] | 2017-07-02 19:59 | Yes | 0
VD-9001-740A-MOD-00353 | 6 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-07-02 | 2017-07-09 11:35 |  | No | 7 |  | 2017-07-09 11:47 | [6 empty] | 2017-07-09 19:59 | Yes | 0
VD-9001-740A-GAD-00316 | 1 | General Arrangement Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-07-04 | 2017-07-05 10:06 |  | No | 1 |  | 2017-07-05 16:56 | [6 empty] | 2017-07-05 19:59 | Yes | 0
VD-9001-204B-WMP-001 | 2 | Welding & NDT Map D-1002 | PV-204B | ABAN AIR COOLER. | 2017-07-04 | 2018-02-25 08:20 | 2018-02-25 08:20 | Yes | 236 |  |  |  |  | 2018-03-10 17:25 |  |  |  | 2018-03-10 17:25 | Yes | -1
VD-9001-740A-MOD-00302 | 4 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-07-06 | 2017-07-10 10:34 |  | No | 4 |  | 2017-07-11 15:15 | [6 empty] | 2017-07-11 19:59 | Yes | 0
VD-9001-201-DWG-002 | 1 | WELD DETAILS - ND EXAMINATION | PV-201 | ATB RIVA CALZONI SpA | 2017-07-10 | 2017-08-11 18:12 |  | No | 32 |  | 2017-09-17 11:09 | [6 empty] | 2017-09-17 19:57 | Yes | 0
VD-9001-201-PCJ-017 | 1 | REPAIR PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2017-07-10 | 2018-01-09 19:51 | 2018-01-09 19:52 | Yes | 183 |  | 2018-01-29 11:30 | [6 empty] | 2018-01-29 20:00 | Yes | 6 | 1204-Owner-v | 2019-01-13 14:55
VD-9001-201-ITP-001 | 2 | QUALITY CONTROL PLAN | PV-201 | ATB RIVA CALZONI SpA | 2017-07-10 | 2017-11-08 11:10 | 2017-11-08 11:11 | Yes | 121 |  | 2017-11-25 10:38 | [6 empty] | 2017-11-25 19:59 | Yes | 3 | 1204-Owner-v | 2018-05-12 16:56
VD-9001-740A-PRC-002 | 2 | Welding Documents (WPS and PQR) | ST-740A | Pars Tadbir Gostar | 2017-07-16 | 2017-07-17 09:11 |  | No | 1069 |  | 2017-07-19 17:40 | [6 empty] | 2017-07-19 19:59 | Yes | 0
VD-9001-740A-GAD-00086 | 1 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-07-17 | 2017-07-23 09:15 |  | No | 6 |  | 2017-07-24 11:23 | [6 empty] | 2017-07-24 19:58 | Yes | 0
VD-9001-108-DWG-071 | 0 | Louver Detail | PR-108 | Farabard | 2017-07-17 | 2017-07-24 16:03 |  | No | 7 | 2017-07-24 18:08 | [7 empty] | 2017-07-24 19:59 | Yes | 0
VD-9001-108-DWG-072 | 0 | Mesh Screen Detail | PR-108 | Farabard | 2017-07-17 | 2017-07-24 16:03 |  | No | 7 | 2017-07-24 17:33 | [7 empty] | 2017-07-24 19:59 | Yes | 0
VD-9001-108-DWG-073 | 0 | Gate Detail | PR-108 | Farabard | 2017-07-17 | 2017-11-18 09:48 |  | No | 124 | 2017-11-18 15:34 | [7 empty] | 2017-11-18 19:59 | Yes | 0
VD-9001-206B-DWG-019 | 3 | NAME PLATE DRAWING -T-1001 | PV-206B | TASHA | 2017-07-22 14:18 | 2017-07-25 19:27 |  | No | 3 |  | 2017-08-07 08:42 | [6 empty] | 2017-08-07 19:58 | Yes | 0
VD-9001-206B-DWG-049 | 3 | NAME PLATE DRAWING -T-2001 | PV-206B | TASHA | 2017-07-22 14:18 | 2017-07-25 19:28 | 2017-07-25 19:29 | Yes | 3 |  | 2017-08-07 08:24 | [6 empty] | 2017-08-07 19:58 | Yes | -1 | 1204-Owner-v | 2020-05-11 14:44
VD-9001-206B-DWG-079 | 3 | NAME PLATE DRAWING -T-4001 | PV-206B | TASHA | 2017-07-22 14:18 | 2017-07-25 19:28 |  | No | 3 |  | 2017-08-07 08:28 | [6 empty] | 2017-08-07 19:58 | Yes | 0
VD-9001-204B-WMP-002 | 2 | Welding & NDT Map D-1003 | PV-204B | ABAN AIR COOLER. | 2017-07-24 | 2018-02-25 08:25 | 2018-02-25 08:25 | Yes | 216 |  |  |  |  | 2018-03-10 17:14 |  |  |  | 2018-03-10 17:14 | Yes | -1
VD-9001-204B-WMP-003 | 2 | Welding & NDT Map D-3006 | PV-204B | ABAN AIR COOLER. | 2017-07-24 | 2018-02-25 08:38 | 2018-02-25 08:38 | Yes | 216 |  |  |  |  | 2018-03-10 17:16 |  |  |  | 2018-03-10 17:16 | Yes | -1
VD-9001-204B-WMP-004 | 2 | Welding & NDT Map D-3007 | PV-204B | ABAN AIR COOLER. | 2017-07-24 | 2018-02-25 08:47 | 2018-02-25 08:47 | Yes | 216 |  |  |  |  | 2018-03-10 17:20 |  |  |  | 2018-03-10 17:20 | Yes | -1
VD-9001-108-DWG-072 | 1 | Mesh Screen Detail | PR-108 | Farabard | 2017-08-07 19:59 | 2017-07-25 14:41 | 2017-07-25 14:42 | Yes | -13 |  | 2017-07-29 14:54 | [6 empty] | 2017-07-29 19:59 | Yes | -10
VD-9001-108-DWG-071 | 1 | Louver Detail | PR-108 | Farabard | 2017-08-07 19:59 | 2017-07-25 14:41 |  | No | -13 |  | 2017-07-29 14:48 | [6 empty] | 2017-07-29 19:59 | Yes | 0
VD-9001-204A-DWG-013 | 3 | Name Plate Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 12:29 |  | No | 5 | 2017-08-14 16:21 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-023 | 3 | Name Plate Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 10:14 |  | No | 5 | 2017-08-14 16:32 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-033 | 3 | Name Plate Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 10:24 |  | No | 5 | 2017-08-14 16:34 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-043 | 2 | Name Plate Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 10:33 |  | No | 5 | 2017-08-14 16:36 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-053 | 2 | Name Plate Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 12:40 |  | No | 5 | 2017-08-14 16:45 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-063 | 3 | Name Plate Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:49 | 2017-08-05 10:45 |  | No | 5 | 2017-08-14 16:37 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-073 | 3 | Name Plate Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 11:05 |  | No | 5 | 2017-08-14 16:38 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-083 | 2 | Name Plate Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 11:54 |  | No | 5 | 2017-08-14 16:39 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-093 | 2 | Name Plate Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 12:58 |  | No | 5 | 2017-08-14 16:46 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-103 | 3 | Name Plate Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 13:05 |  | No | 5 | 2017-08-14 16:48 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-113 | 3 | Name Plate Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 13:13 |  | No | 5 | 2017-08-14 16:49 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-123 | 3 | Name Plate Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 13:19 |  | No | 5 | 2017-08-14 16:50 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-133 | 3 | Name Plate Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 13:24 |  | No | 5 | 2017-08-14 16:51 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-143 | 3 | Name Plate Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 12:05 |  | No | 5 | 2017-08-14 16:41 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-153 | 3 | Name Plate Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:50 | 2017-08-05 12:15 |  | No | 5 | 2017-08-14 16:43 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-163 | 3 | Name Plate Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:51 | 2017-08-05 13:30 |  | No | 5 | 2017-08-14 16:54 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-173 | 3 | Name Plate Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:51 | 2017-08-05 12:20 |  | No | 5 | 2017-08-14 16:44 | [7 empty] | 2017-08-14 19:58 | Yes | 0
VD-9001-204A-DWG-162 | 2 | Nozzle Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:51 | 2017-08-05 14:26 |  | No | 5 | 2017-09-26 15:00 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-DWG-094 | 2 | PF & LD Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-07-31 12:51 | 2017-08-05 15:44 |  | No | 5 | 2017-09-26 15:08 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-201-CAL-002 | 3 | FOUNDATION LOADS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2017-08-01 | 2017-10-05 19:44 |  | No | 65 | 2017-11-04 17:37 | [7 empty] | 2017-11-04 20:00 | Yes | 0
VD-9001-204A-CAL-020 | 4 | Strength Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-05 10:03 | 2017-08-05 11:24 | 2017-08-05 11:24 | Yes | 0 |  | 2017-08-13 11:03 | [6 empty] | 2017-08-13 19:58 | Yes | -6
VD-9001-204A-CAL-021 | 1 | Shipping Calculation for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-05 | 2017-09-18 17:16 | 2017-09-18 17:17 | Yes | 44 |  | 2017-09-19 14:12 | [6 empty] | 2017-09-19 19:57 | Yes | -13
VD-9001-108-PCJ-064 | 5 | PERFORMANCE TEST PROCEDURE | PR-108 | Farabard | 2017-08-19 19:58 | 2017-10-31 10:37 | 2017-10-31 10:38 | Yes | 73 |  | 2017-11-11 12:45 | [6 empty] | 2017-11-11 19:59 | Yes | -3
VD-9001-108-LST-047 | 6 | LOAD LIST | PR-108 | Farabard | 2017-08-19 19:58 | 2017-10-31 14:08 | 2017-10-31 14:09 | Yes | 73 |  | 2017-11-08 15:01 | [6 empty] | 2017-11-08 20:00 | Yes | -6
VD-9001-108-DSH-007 | 5 | COOLING TOWER DATA SHEET | PR-108 | Farabard | 2017-08-19 19:58 | 2017-08-30 11:03 | 2017-08-30 11:04 | Yes | 11 |  | 2017-09-03 17:38 | [6 empty] | 2017-09-03 19:58 | Yes | -10
VD-9001-108-DSH-010 | 5 | INTERNAL PARTS DATA SHEET | PR-108 | Farabard | 2017-08-19 19:59 | 2017-08-30 12:52 | 2017-08-30 12:53 | Yes | 11 |  | 2017-09-03 10:16 | [6 empty] | 2017-09-03 19:57 | Yes | -10
VD-9001-108-DSH-008 | 4 | FAN PACKAGE DATA SHEET | PR-108 | Farabard | 2017-08-19 19:59 | 2017-08-30 11:51 | 2017-08-30 11:52 | Yes | 11 |  | 2017-09-02 14:54 | [6 empty] | 2017-09-02 19:58 | Yes | -11
VD-9001-108-DSH-015 | 4 | VIBRATION SWITCH DATA SHEET | PR-108 | Farabard | 2017-08-19 19:59 | 2017-08-12 14:33 | 2017-08-12 14:34 | Yes | -7 |  | 2017-08-14 09:42 | [6 empty] | 2017-08-14 19:58 | Yes | -12
VD-9001-108-DWG-030 | 2 | GENERAL ARRANGMENT | PR-108 | Farabard | 2017-08-20 19:58 | 2017-11-06 11:30 | 2017-11-06 11:31 | Yes | 78 |  | 2017-11-11 15:16 | [6 empty] | 2017-11-11 19:59 | Yes | -9
VD-9001-201-CAL-003 | 1 | LIFTING CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2017-08-09 | 2017-08-11 18:11 | 2017-08-11 18:12 | Yes | 2 |  | 2018-02-27 10:46 | [6 empty] | 2018-02-27 19:59 | Yes | 186 | 1204-Owner-v | 2018-12-16 21:34
VD-9001-201-DWG-005 | 1 | SUPPORT SKIRT EXTERNAL DETAILS TAILING LUG | PV-201 | ATB RIVA CALZONI SpA | 2017-08-09 | 2017-08-11 18:12 |  | No | 2 |  | 2017-08-15 10:26 | [6 empty] | 2017-08-15 19:58 | Yes | 0
VD-9001-464A-PCJ-001 | 3 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-08-12 14:47 | 2017-08-15 08:22 |  | No | 3 | 2017-08-19 17:44 | [7 empty] | 2017-08-19 19:58 | Yes | 0
VD-9001-254-DWG-960 | 0 | HAZARD AREA CLASSIFICATION LAYOUT | HM-254 | AZAR AB | 2017-08-14 | 2017-08-14 09:33 |  | No | 0 | 2017-08-26 14:53 | [7 empty] | 2017-08-26 19:58 | Yes | 0 | 1204-Owner-v | 2018-04-09 17:05
VD-9001-204A-DWG-013 | 4 | Name Plate Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:07 | 2017-09-03 17:08 | Yes | 20 |  | 2017-09-05 09:55 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-023 | 4 | Name Plate Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:17 | 2017-09-03 17:18 | Yes | 20 |  | 2017-09-05 10:01 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-033 | 4 | Name Plate Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:18 | 2017-09-03 17:18 | Yes | 20 |  | 2017-09-05 10:10 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-043 | 3 | Name Plate Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:20 | 2017-09-03 17:21 | Yes | 20 |  | 2017-09-05 10:38 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-063 | 4 | Name Plate Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:22 | 2017-09-03 17:22 | Yes | 20 |  | 2017-09-05 10:46 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-073 | 4 | Name Plate Detail FOR D-3004 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:22 | 2017-09-03 17:23 | Yes | 20 |  | 2017-09-05 10:49 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-083 | 3 | Name Plate Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:23 | 2017-09-03 17:24 | Yes | 20 |  | 2017-09-05 10:55 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-143 | 4 | Name Plate Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:24 | 2017-09-03 17:25 | Yes | 20 |  | 2017-09-05 11:17 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-153 | 4 | Name Plate Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:25 | 2017-09-03 17:26 | Yes | 20 |  | 2017-09-05 11:20 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-173 | 4 | Name Plate Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:26 | 2017-09-03 17:27 | Yes | 20 |  | 2017-09-05 11:26 | [6 empty] | 2017-09-05 19:57 | Yes | -12 | 1204-Owner-v | 2019-07-09 13:56
VD-9001-204A-DWG-053 | 3 | Name Plate Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:09 | 2017-09-03 17:09 | Yes | 20 |  | 2017-09-05 10:41 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-093 | 3 | Name Plate Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:10 | 2017-09-03 17:11 | Yes | 20 |  | 2017-09-05 11:03 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-103 | 4 | Name Plate Detail FOR D-4003 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:11 | 2017-09-03 17:12 | Yes | 20 |  | 2017-09-05 11:06 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-113 | 4 | Name Plate Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:13 | 2017-09-03 17:14 | Yes | 20 |  | 2017-09-05 11:09 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-123 | 4 | Name Plate Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:14 | 2017-09-03 17:15 | Yes | 20 |  | 2017-09-05 11:11 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-133 | 4 | Name Plate Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:15 | 2017-09-03 17:16 | Yes | 20 |  | 2017-09-05 11:14 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-204A-DWG-163 | 4 | Name Plate Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-08-14 | 2017-09-03 17:16 | 2017-09-03 17:17 | Yes | 20 |  | 2017-09-05 11:22 | [6 empty] | 2017-09-05 19:57 | Yes | -12
VD-9001-201-MDB-001 | 1 | MANUFACTURING DATA BOOK INDEX | PV-201 | ATB RIVA CALZONI SpA | 2017-08-15 | 2018-08-27 16:33 | 2018-08-27 16:36 | Yes | 377 |  |  |  | 2018-11-20 16:49 |  |  |  |  | 2018-11-20 16:49 | Yes | 71 | 1204-Owner-v | 2019-08-06 14:02
VD-9001-204B-DWG-017 | 1 | Name Plate Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-08-15 14:19 | 2017-08-15 14:26 |  | No | 0 | 2017-08-16 11:47 | [7 empty] | 2017-08-16 19:58 | Yes | 0
VD-9001-204B-DWG-018 | 1 | Name Plate Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2017-08-15 14:19 | 2017-08-15 14:31 |  | No | 0 | 2017-08-16 11:46 | [7 empty] | 2017-08-16 19:58 | Yes | 0
VD-9001-204B-DWG-019 | 1 | Name Plate Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-08-15 14:19 | 2017-08-15 14:33 |  | No | 0 | 2017-08-16 11:44 | [7 empty] | 2017-08-16 19:58 | Yes | 0
VD-9001-204B-DWG-020 | 1 | Name Plate Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2017-08-15 14:19 | 2017-08-15 14:34 |  | No | 0 | 2017-08-16 11:43 | [7 empty] | 2017-08-16 19:58 | Yes | 0
VD-9001-204B-DWG-020 | 2 | Name Plate Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2017-08-16 | 2017-08-16 13:48 | 2017-08-16 13:48 | Yes | 0 |  | 2017-08-22 10:05 | [6 empty] | 2017-08-22 19:58 | Yes | -8 | 1204-Owner-v | 2019-01-13 09:13
VD-9001-204B-DWG-019 | 2 | Name Plate Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2017-08-16 | 2017-08-16 13:46 | 2017-08-16 13:46 | Yes | 0 |  | 2017-08-22 10:04 | [6 empty] | 2017-08-22 19:58 | Yes | -8 | 1204-Owner-v | 2019-01-13 09:13
VD-9001-204B-DWG-018 | 2 | Name Plate Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2017-08-16 | 2017-08-16 13:44 | 2017-08-16 13:44 | Yes | 0 |  | 2017-08-22 10:02 | [6 empty] | 2017-08-22 19:58 | Yes | -8 | 1204-Owner-v | 2019-01-13 09:13
VD-9001-204B-DWG-017 | 2 | Name Plate Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2017-08-16 | 2017-08-16 13:41 | 2017-08-16 13:41 | Yes | 0 |  | 2017-08-22 10:01 | [6 empty] | 2017-08-22 19:58 | Yes | -8 | 1204-Owner-v | 2019-01-13 09:13
VD-9001-464A-PCJ-001 | 4 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-08-19 | 2017-08-20 13:18 |  | No | 1 | 2017-08-21 12:04 | [7 empty] | 2017-08-21 19:58 | Yes | 0
VD-9001-464A-PCJ-001 | 5 | Valve Hydro test Procedure | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2017-09-04 19:58 | 2017-08-23 11:10 | 2017-08-23 11:11 | Yes | -12 |  | 2017-08-23 18:12 | [6 empty] | 2017-08-23 19:58 | Yes | -14
VD-9001-254-PPL-319 | 1 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 08:29 |  | No | -13 | 2017-08-26 14:50 | [7 empty] | 2017-08-26 19:58 | Yes | 0
VD-9001-254-PPL-318 | 1 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 08:36 |  | No | -13 | 2017-08-27 16:24 | [7 empty] | 2017-08-27 19:58 | Yes | 0
VD-9001-254-MNL-325 | 1 | TECHNICAL SPECIFICATION FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-12-03 15:16 |  | No | 89 | 2017-12-24 10:02 | [7 empty] | 2017-12-24 19:59 | Yes | 0
VD-9001-254-LST-362 | 1 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 08:48 |  | No | -13 | 2017-08-29 11:16 | [7 empty] | 2017-08-29 19:57 | Yes | 0
VD-9001-254-LST-302 | 1 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 10:30 |  | No | -13 | 2017-08-29 11:19 | [7 empty] | 2017-08-29 19:57 | Yes | 0
VD-9001-254-LST-301 | 1 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 10:36 |  | No | -13 | 2017-08-29 11:22 | [7 empty] | 2017-08-29 19:57 | Yes | 0
VD-9001-254-DIG-300 | 1 | SYSTEM ARCITECTURE & INTERCONNECTION DIAGRAM FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-05 19:58 | 2017-08-23 10:43 |  | No | -13 | 2017-08-28 16:39 | [7 empty] | 2017-08-28 19:57 | Yes | 0
VD-9001-254-DIG-320 | 1 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2017-09-05 19:58 | 2018-01-07 14:06 |  | No | 124 | 2018-02-06 14:29 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-30 14:43
VD-9001-254-PPL-319 | 2 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2017-09-09 19:58 | 2017-12-03 15:33 |  | No | 85 | 2017-12-27 10:56 | [7 empty] | 2017-12-27 19:59 | Yes | 0
VD-9001-254-DWG-960 | 1 | HAZARD AREA CLASSIFICATION LAYOUT | HM-254 | AZAR AB | 2017-09-09 19:58 | 2018-05-14 13:44 | 2018-05-14 13:54 | Yes | 247 |  |  | 2018-06-03 11:23 | [5 empty] | 2018-06-03 11:23 | Yes | 6 | 1204-Owner-v | 2018-10-08 15:28
VD-9001-254-PCJ-128 | 1 | DRYING OUT PROCEDURE | HM-254 | AZAR AB | 2017-09-09 19:58 |  |  | No | 1014 | [9 empty] | No | 0
VD-9001-204A-DWG-021 | 5 | General Arrangement Drawing FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-08-27 11:04 | 2017-08-27 12:22 | 2017-08-27 12:23 | Yes | 0 |  | 2017-08-29 11:40 | [6 empty] | 2017-08-29 19:57 | Yes | -12 | 1204-Owner-v | 2019-07-03 09:17
VD-9001-254-PPL-318 | 2 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2017-09-10 19:58 | 2017-12-03 15:29 |  | No | 84 | 2017-12-27 10:54 | [7 empty] | 2017-12-27 19:59 | Yes | 0
VD-9001-254-DWG-330 | 1 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2017-09-11 19:57 | 2017-12-03 14:19 |  | No | 83 | 2018-01-14 11:58 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-254-DIG-300 | 2 | SYSTEM ARCITECTURE & INTERCONNECTION DIAGRAM FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-11 19:57 | 2018-08-28 12:16 | 2018-08-28 12:17 | Yes | 351 |  |  |  | 2018-10-01 14:58 |  |  |  |  | 2018-10-01 14:58 | Yes | 20
VD-9001-254-LST-334 | 1 | SPARE PART LIST FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-12 19:57 | 2017-08-30 07:51 |  | No | -13 | 2017-09-04 10:13 | [7 empty] | 2017-09-04 19:57 | Yes | 0
VD-9001-254-LST-362 | 2 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2017-09-12 19:57 | 2017-09-23 14:01 |  | No | 11 | 2017-10-11 09:29 | [7 empty] | 2017-10-11 20:00 | Yes | 0
VD-9001-254-LST-302 | 2 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2017-09-12 19:57 | 2017-09-11 16:07 |  | No | -1 | 2017-10-11 09:24 | [7 empty] | 2017-10-11 20:00 | Yes | 0
VD-9001-254-LST-301 | 2 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-12 19:57 | 2017-09-11 16:05 |  | No | -1 | 2017-10-11 09:26 | [7 empty] | 2017-10-11 20:00 | Yes | 0
VD-9001-253(A)-LST-093 | 2 | SPARE PART LIST | HM-253A | FATEH SANAT KIMIA | 2017-09-02 | 2017-10-14 12:08 | 2017-10-14 12:09 | Yes | 42 |  | 2017-10-21 15:38 | [6 empty] | 2017-10-21 20:00 | Yes | -7 | 1204-Owner-v | 2018-03-12 13:42
VD-9001-108-MDL-054 | 6 | GENERAL INDEX | PR-108 | Farabard | 2017-09-16 19:58 | 2017-10-30 12:46 | 2017-10-30 12:47 | Yes | 44 |  | 2017-11-04 10:34 | [6 empty] | 2017-11-04 19:59 | Yes | -9
VD-9001-254-PCJ-139 | 0 | BOILER FEED WATER & BOILER WATER CONDITIONING | HM-254 | AZAR AB | 2017-09-03 | 2017-09-24 08:38 | 2017-09-24 08:39 | Yes | 21 |  | 2017-10-14 11:33 | [6 empty] | 2017-10-14 20:00 | Yes | 6 | 1204-Owner-v | 2018-12-04 15:43
VD-9001-254-PCJ-127 | 1 | CHEMICAL CLEANING PROCEDURE | HM-254 | AZAR AB | 2017-09-17 19:57 | 2019-02-25 16:09 | 2019-02-25 16:09 | Yes | 526 |  |  | 2019-03-05 09:15 | [5 empty] | 2019-03-05 09:15 | Yes | -6
VD-9001-254-LST-334 | 2 | SPARE PART LIST FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-09-18 19:57 | 2017-10-23 12:08 |  | No | 35 | 2017-11-04 09:48 | [7 empty] | 2017-11-04 19:59 | Yes | 0
VD-9001-108-DWG-035 | 4 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2017-09-30 19:57 | 2017-10-30 14:52 |  | No | 30 | 2017-11-08 08:58 | [7 empty] | 2017-11-08 19:59 | Yes | 0
VD-9001-201-DWG-004 | 1 | TEMPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2017-09-18 | 2017-09-21 12:02 |  | No | 3 |  | 2017-09-26 11:35 | [6 empty] | 2017-09-26 20:00 | Yes | 0 | 1204-Owner-v | 2019-08-06 14:50
VD-9001-201-DWG-009 | 1 | INSULATION SUPPORT DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2017-09-19 | 2017-09-21 12:03 |  | No | 2 | 2017-09-26 11:19 | [7 empty] | 2017-09-26 20:00 | Yes | 0
VD-9001-204A-CAL-030 | 5 | Strength Calculation FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-09-20 | 2017-10-29 12:51 | 2017-10-29 12:51 | Yes | 39 |  | 2017-10-29 15:37 | [6 empty] | 2017-10-29 20:00 | Yes | -14
VD-9001-204A-DWG-171 | 5 | General Arrangement Drawing FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-24 09:46 | 2017-10-24 09:47 | Yes | 31 |  | 2017-10-24 15:56 | [6 empty] | 2017-10-24 20:00 | Yes | -14 | 1204-Owner-v | 2019-07-09 13:49
VD-9001-204A-DWG-015 | 3 | PF & LD Arrangement FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-21 12:24 | 2017-10-21 12:25 | Yes | 28 |  | 2017-10-22 15:36 | [6 empty] | 2017-10-22 19:59 | Yes | -13 | 1204-Owner-v | 2018-12-29 10:12
VD-9001-204A-DWG-012 | 4 | Nozzle Detail FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-21 11:37 | 2017-10-21 11:37 | Yes | 28 |  | 2017-10-22 15:30 | [6 empty] | 2017-10-22 19:59 | Yes | -13
VD-9001-204A-DWG-052 | 3 | Nozzle Detail FOR D-3002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-22 10:59 | 2017-10-22 11:00 | Yes | 29 |  | 2017-10-22 15:55 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-152 | 3 | Nozzle Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-24 09:43 | 2017-10-24 09:43 | Yes | 31 |  | 2017-10-24 15:51 | [6 empty] | 2017-10-24 20:00 | Yes | -14
VD-9001-204A-DWG-155 | 4 | PF & LD Arrangement FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-09-23 | 2017-10-23 11:12 | 2017-10-23 11:13 | Yes | 30 |  | 2017-10-24 11:51 | [6 empty] | 2017-10-24 20:00 | Yes | -13 | 1204-Owner-v | 2018-12-29 10:22
VD-9001-253(A)-MDB-115 | 1 | FINAL DATA BOOK INDEX | HM-253A | FATEH SANAT KIMIA | 2017-09-24 | 2017-10-24 12:11 |  | No | 30 | 2017-11-14 15:57 | [7 empty] | 2017-11-14 19:59 | Yes | 0
VD-9001-201-DWG-005 | 2 | SUPPORT SKIRT EXTERNAL DETAILS TAILING LUG | PV-201 | ATB RIVA CALZONI SpA | 2017-09-25 08:45 | 2017-09-26 14:14 |  | No | 1 |  | 2017-09-26 15:45 | [6 empty] | 2017-09-26 20:01 | Yes | 0
VD-9001-205A-PCJ-063 | 0 | NDT Procedure | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-09-25 | 2017-10-10 09:01 | 2017-10-10 09:02 | Yes | 15 |  | 2018-01-22 15:45 | [6 empty] | 2018-01-22 19:59 | Yes | 90
VD-9001-204A-DWG-145 | 4 | PF & LD Arrangement FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 10:28 | 2017-10-23 10:29 | Yes | 27 |  | 2017-10-24 11:08 | [6 empty] | 2017-10-24 19:59 | Yes | -13 | 1204-Owner-v | 2018-12-29 10:21
VD-9001-204A-DWG-086 | 3 | External Attachment Drawing FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 12:40 | 2017-10-22 12:41 | Yes | 26 |  | 2017-10-22 16:16 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-082 | 2 | Nozzle Detail FOR D-3005 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 12:31 | 2017-10-22 12:32 | Yes | 26 |  | 2017-10-22 16:04 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-062 | 3 | Nozzle Detail FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 12:09 | 2017-10-22 12:10 | Yes | 26 |  | 2017-10-22 16:33 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-046 | 4 | External Attachment Drawing FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-25 | 2017-10-22 10:28 | 2017-10-22 10:29 | Yes | 27 |  | 2017-10-22 15:51 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-044 | 3 | PF & LD Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 10:21 | 2017-10-22 10:21 | Yes | 26 |  | 2017-10-22 15:45 | [6 empty] | 2017-10-22 20:00 | Yes | -14 | 1204-Owner-v | 2018-12-22 16:39
VD-9001-204A-DWG-042 | 4 | Nozzle Detail FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 09:52 | 2017-10-22 09:53 | Yes | 26 |  | 2017-10-22 15:43 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-045 | 3 | PF & LD Arrangement FOR D-3001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 10:10 | 2017-10-22 10:10 | Yes | 26 |  | 2017-10-24 08:58 | [6 empty] | 2017-10-24 19:59 | Yes | -14 | 1204-Owner-v | 2018-12-29 10:17
VD-9001-204A-DWG-032 | 3 | Nozzle Detail FOR D-2201 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 09:24 | 2017-10-22 09:24 | Yes | 26 |  | 2017-10-22 15:40 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-017 | 4 | Internal Attachment Drawing FOR D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-24 11:06 | 2017-10-24 11:07 | Yes | 28 |  | 2017-10-24 16:56 | [6 empty] | 2017-10-24 20:00 | Yes | -14
VD-9001-204A-DWG-096 | 4 | External Attachment Drawing FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 13:38 | 2017-10-23 13:39 | Yes | 27 |  | 2017-10-24 14:51 | [6 empty] | 2017-10-24 20:00 | Yes | -13
VD-9001-204A-DWG-112 | 4 | Nozzle Detail FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 13:33 | 2017-10-22 13:33 | Yes | 26 |  | 2017-10-22 16:25 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-124 | 3 | PF & LD Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 07:49 | 2017-10-23 07:50 | Yes | 27 |  | 2017-10-24 10:53 | [6 empty] | 2017-10-24 19:59 | Yes | -13 | 1204-Owner-v | 2018-12-22 16:40
VD-9001-201-DWG-009 | 2 | INSULATION SUPPORT DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2017-09-26 | 2017-10-27 18:25 | 2017-10-27 18:26 | Yes | 31 |  | 2017-11-25 10:49 | [6 empty] | 2017-11-25 19:59 | Yes | 15 | 1204-Owner-v | 2018-06-27 12:33
VD-9001-204A-DWG-122 | 3 | Nozzle Detail FOR D-6201 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 14:03 | 2017-10-22 14:04 | Yes | 26 |  | 2017-10-22 16:28 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-136 | 3 | External Attachment Drawing FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 08:29 | 2017-10-23 08:30 | Yes | 27 |  | 2017-10-24 11:04 | [6 empty] | 2017-10-24 19:59 | Yes | -13
VD-9001-204A-DWG-132 | 3 | Nozzle Detail FOR D-6202 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 08:18 | 2017-10-23 08:19 | Yes | 27 |  | 2017-10-24 11:00 | [6 empty] | 2017-10-24 19:59 | Yes | -13
VD-9001-204A-DWG-172 | 3 | Nozzle Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 11:48 |  | No | 27 | 2017-10-24 14:30 | [7 empty] | 2017-10-24 20:00 | Yes | 0
VD-9001-204A-DWG-092 | 3 | Nozzle Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 13:04 | 2017-10-22 13:05 | Yes | 26 |  | 2017-10-22 16:19 | [6 empty] | 2017-10-22 20:00 | Yes | -14
VD-9001-204A-DWG-144 | 4 | PF & LD Detail FOR D-6401 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-24 09:39 | 2017-10-24 09:40 | Yes | 28 |  | 2017-10-24 14:56 | [6 empty] | 2017-10-24 20:00 | Yes | -14 | 1204-Owner-v | 2018-12-22 16:41
VD-9001-204A-DWG-022 | 4 | Nozzle Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 07:31 | 2017-10-23 07:32 | Yes | 27 |  | 2017-10-24 10:47 | [6 empty] | 2017-10-24 19:59 | Yes | -13 | 1204-Owner-v | 2019-07-09 12:06
VD-9001-204A-DWG-025 | 5 | PF & LD Arrangement FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-24 11:36 | 2017-10-24 11:37 | Yes | 28 |  | 2017-10-24 17:06 | [6 empty] | 2017-10-24 20:00 | Yes | -14 | 1204-Owner-v | 2018-12-29 10:14
VD-9001-204A-DWG-024 | 3 | PF & LD Detail FOR D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 08:57 | 2017-10-22 08:58 | Yes | 26 |  | 2017-10-22 15:33 | [6 empty] | 2017-10-22 19:59 | Yes | -14 | 1204-Owner-v | 2018-12-22 16:39
VD-9001-204A-DWG-162 | 3 | Nozzle Detail FOR D-6501 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 11:37 | 2017-10-23 11:38 | Yes | 27 |  | 2017-10-24 14:24 | [6 empty] | 2017-10-24 20:00 | Yes | -13
VD-9001-204A-DWG-094 | 3 | PF & LD Detail FOR D-4002 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-22 13:16 | 2017-10-22 13:17 | Yes | 26 |  | 2017-10-22 16:22 | [6 empty] | 2017-10-22 20:00 | Yes | -14 | 1204-Owner-v | 2018-12-22 16:39
VD-9001-204A-DWG-174 | 5 | PF & LD Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-09-26 | 2017-10-23 12:01 | 2017-10-23 12:01 | Yes | 27 |  | 2017-10-24 14:35 | [6 empty] | 2017-10-24 20:00 | Yes | -13 | 1204-Owner-v | 2018-12-22 16:42
VD-9001-201-DWG-007 | 1 | NAMEPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2017-09-27 | 2017-10-05 19:44 |  | No | 8 | 2018-01-29 15:13 | [7 empty] | 2018-01-29 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-22 15:35
VD-9001-206B-DWG-019 | 4 | NAME PLATE DRAWING -T-1001 | PV-206B | TASHA | 2017-10-02 10:17 | 2017-10-04 10:52 | 2017-10-04 10:53 | Yes | 2 |  | 2018-02-03 17:27 | [6 empty] | 2018-02-03 20:00 | Yes | 108 | 1204-Owner-v | 2018-05-18 08:42
VD-9001-206B-DWG-079 | 4 | NAME PLATE DRAWING -T-4001 | PV-206B | TASHA | 2017-10-02 10:17 | 2017-10-04 10:52 | 2017-10-04 10:54 | Yes | 2 |  | 2018-01-02 11:23 | [6 empty] | 2018-01-02 19:59 | Yes | 76 | 1204-Owner-v | 2020-05-11 14:44
VD-9001-254-ITP-327 | 1 | CONTROL SYSTEM AND BMS FACTORY ACCEPTANCE TEST (FAT) PROCEDURE | HM-254 | AZAR AB | 2017-10-17 20:00 | 2017-10-04 08:30 |  | No | -13 | 2017-10-04 14:31 | [7 empty] | 2017-10-04 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-254-ITP-326 | 1 | CONTROL SYSTEM AND BMS SITE ACCEPTANCE TEST (SAT) PROCEDURE | HM-254 | AZAR AB | 2017-10-17 20:01 | 2017-10-04 08:29 |  | No | -13 | 2017-10-04 14:34 | [7 empty] | 2017-10-04 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-254-LST-328 | 1 | CONTROL SYSTEM PROGRAM LIST | HM-254 | AZAR AB | 2017-10-17 20:01 | 2020-03-10 07:52 | 2020-03-10 07:52 | Yes | 875 |  |  | 2020-04-15 11:54 | [5 empty] | 2020-04-15 11:54 | Yes | 22
VD-9001-254-LST-363 | 1 | MODBUS LIST | HM-254 | AZAR AB | 2017-10-17 20:01 |  |  | No | 976 | [9 empty] | No | 0
VD-9001-254-LST-329 | 1 | BMS PROGRAM LIST | HM-254 | AZAR AB | 2017-10-17 20:01 | 2017-10-23 11:59 |  | No | 6 | 2017-11-04 09:43 | [7 empty] | 2017-11-04 19:59 | Yes | 0 | 1204-Owner-v | 2018-11-26 13:46
VD-9001-105-SPE-501 | 2 | Painting specification | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-10-04 | 2017-11-06 05:39 |  | No | 33 | 2017-11-18 15:42 | [7 empty] | 2017-11-18 19:59 | Yes | 0
VD-9001-254-ITP-327 | 2 | CONTROL SYSTEM AND BMS FACTORY ACCEPTANCE TEST (FAT) PROCEDURE | HM-254 | AZAR AB | 2017-10-18 20:00 | 2017-10-23 11:41 |  | No | 5 | 2017-11-01 15:04 | [7 empty] | 2017-11-01 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:29
VD-9001-254-ITP-326 | 2 | CONTROL SYSTEM AND BMS SITE ACCEPTANCE TEST (SAT) PROCEDURE | HM-254 | AZAR AB | 2017-10-18 20:00 | 2017-10-23 11:41 |  | No | 5 | 2017-11-01 15:10 | [7 empty] | 2017-11-01 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-254-PCJ-130 | 1 | SAFETY VALVE SETING PROCEDURE | HM-254 | AZAR AB | 2017-10-21 20:00 | 2019-03-02 10:31 | 2019-03-02 10:32 | Yes | 497 |  |  | 2019-04-15 15:09 | [5 empty] | 2019-04-15 15:09 | Yes | 30 | 1204-Owner-v | 2019-06-15 16:41
VD-9001-104-MDL-001 | 0 | Master Customer document List | PR-104 | AIR LIQUIDE | 2017-10-10 |  |  | No | 983 | [9 empty] | No | 0
VD-9001-104-ORC-001 | 0 | Project Organization Chart | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-11-20 13:56 |  | No | 41 |  | 2017-11-21 10:47 | [6 empty] | 2017-11-21 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:16
VD-9001-104-DCR-001 | 0 | Site data sheet | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-11 12:28 |  | No | 1 | 2017-12-19 10:44 | [7 empty] | 2017-12-19 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:00
VD-9001-104-MDB-001 | 0 | Manufacturing Data Book | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-12 13:17 |  | No | 2 | 2017-10-23 15:25 | [7 empty] | 2017-10-23 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:16
VD-9001-104-QCP-001 | 0 | Quality Control Plan | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-12 13:16 |  | No | 2 | 2017-10-15 15:26 | [7 empty] | 2017-10-15 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:23
VD-9001-104-INP-001 | 0 | Inspection and regulating rules | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:36 |  | No | -1 | 2017-10-17 09:24 | [7 empty] | 2017-10-17 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:14
VD-9001-104-PCJ-005 | 0 | Project equipments numbering procedure | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-12 12:59 |  | No | 2 | 2017-10-18 10:59 | [7 empty] | 2017-10-18 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:17
VD-9001-104-PCJ-001 | 0 | Particular specification for equipment labeling, packaging, marking and storage administrative procedure for supplier orders | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-11-10 13:09 |  | No | 31 | 2018-02-10 15:04 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:17
VD-9001-104-PCJ-002 | 0 | External communication procedure ALE / Customer | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-12 12:58 |  | No | 2 | 2017-10-23 10:55 | [7 empty] | 2017-10-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:17
VD-9001-104-PFD-001 | 0 | PFD Compression and purification | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 11:58 |  | No | -1 | 2017-10-17 09:40 | [7 empty] | 2017-10-17 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:18
VD-9001-104-PFD-002 | 0 | PFD Cold box | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 12:07 |  | No | -1 | 2017-10-17 09:43 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:19
VD-9001-104-PFD-003 | 0 | PFD Liquid Nitrogen storage and vaporization | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:33 |  | No | -1 | 2017-10-17 10:23 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:20
VD-9001-104-PFD-004 | 0 | PFD Gas utilities | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:33 |  | No | -1 | 2017-10-17 10:28 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:20
VD-9001-104-PFD-005 | 0 | PFD Cryogenic disposal | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:34 |  | No | -1 | 2017-10-17 10:38 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:21
VD-9001-104-PFD-006 | 0 | PFD Water utilities | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:34 |  | No | -1 | 2017-10-17 10:33 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:21
VD-9001-104-PFD-007 | 0 | PFD Steam utilities | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:34 |  | No | -1 | 2017-10-17 10:48 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:22
VD-9001-104-PFD-008 | 0 | PFD Interconnection | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-09 17:34 |  | No | -1 | 2017-10-17 10:43 | [7 empty] | 2017-10-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:22
VD-9001-104-DPH-001 | 0 | Instrumentation and control general requirement | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-11-30 16:40 |  | No | 51 | 2017-12-12 17:30 | [7 empty] | 2017-12-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:05
VD-9001-104-SPE-005 | 0 | Piping General Specification | PR-104 | AIR LIQUIDE | 2017-10-10 | 2017-10-20 12:49 |  | No | 10 | 2017-10-22 15:15 | [7 empty] | 2017-10-22 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:27
VD-9001-104-DSH-001 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-10-10 | 2018-04-24 14:00 | 2018-04-24 14:10 | Yes | 196 |  |  |  | 2018-05-29 18:15 |  |  |  |  | 2018-05-29 19:59 | Yes | 21
VD-9001-104-DSH-002 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-10-10 | 2018-04-24 14:01 | 2018-04-24 14:22 | Yes | 196 |  |  |  | 2018-06-03 15:17 |  |  |  |  | 2018-06-03 19:59 | Yes | 26
VD-9001-104-DSH-003 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-10-10 | 2018-04-24 14:01 | 2018-04-24 14:22 | Yes | 196 |  |  |  | 2018-06-03 15:04 |  |  |  |  | 2018-06-03 19:59 | Yes | 26
VD-9001-104-LST-001 | 0 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-11-09 17:14 |  | No | 8 | 2017-11-18 14:16 | [7 empty] | 2017-11-18 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:15
VD-9001-104-DSH-004 | 0 | EQUIPMENT DATA SHEET FOR DISTILLATION COLUMN: HP COLUMN T-6101, LP COLUMN T-6102 | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-20 12:23 |  | No | -12 | 2017-10-25 15:57 | [7 empty] | 2017-10-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:06
VD-9001-104-DSH-005 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-20 12:23 |  | No | -12 | 2017-11-12 12:07 | [7 empty] | 2017-11-12 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:06
VD-9001-104-PPL-001 | 0 | Plot plan - Top view | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-12-22 14:04 |  | No | 51 | 2018-01-17 14:29 | [7 empty] | 2018-01-17 19:59 | Yes | 0 | 1204-Owner-v | 2017-12-31 14:50
VD-9001-104-VLS-001 | 0 | SUB SUPPLIER LIST | PR-104 | AIR LIQUIDE | 2017-11-01 | 2018-03-20 19:17 | 2018-03-20 19:25 | Yes | 139 |  |  |  | 2018-07-21 17:29 |  |  |  |  | 2018-07-21 20:00 | Yes | 109 | 1204-Owner-v | 2018-04-28 10:23
VD-9001-104-PLC-001 | 0 | Air Liquide HSE plans | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-23 10:40 |  | No | -9 | 2017-11-11 10:30 | [7 empty] | 2017-11-11 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:22
VD-9001-104-STR-001 | 0 | Project management plan | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-03-20 15:52 | 2018-03-20 15:59 | Yes | 109 |  |  |  | 2018-06-30 17:53 |  |  |  |  | 2018-06-30 20:00 | Yes | 88
VD-9001-104-LST-002 | 0 | Utilities consumption | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-02-23 17:11 |  | No | 84 |  |  |  | 2018-03-12 16:28 |  |  |  |  | 2018-03-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-24 11:14
VD-9001-104-LST-003 | 0 | Effluent list | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-05-02 19:24 | 2018-05-03 13:24 | Yes | 152 |  |  |  | 2018-05-22 16:13 |  |  |  |  | 2018-05-22 19:59 | Yes | 6 | 1204-Owner-v | 2018-05-13 10:07
VD-9001-104-SPE-006 | 0 | Piping specifications | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-11-08 14:10 |  | No | -23 | 2017-11-15 15:25 | [7 empty] | 2017-11-15 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:27
VD-9001-104-PCJ-003 | 0 | Deriming procedure | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-01-15 15:11 |  | No | 45 | 2018-01-23 14:29 | [7 empty] | 2018-01-23 19:59 | Yes | 0
VD-9001-104-DSH-007 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-11-09 16:42 |  | No | -112 | 2017-11-11 17:35 | [7 empty] | 2017-11-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:07
VD-9001-104-DSH-008 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-10-31 11:54 |  | No | -121 | 2017-11-11 17:26 | [7 empty] | 2017-11-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:07
VD-9001-104-DSH-009 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-04-27 12:31 | 2018-04-27 12:47 | Yes | 57 |  |  |  | 2018-06-11 17:44 |  |  |  |  | 2018-06-11 19:59 | Yes | 31
VD-9001-104-DSH-010 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2017-12-05 14:35 |  | No | -27 | 2017-12-12 17:13 | [7 empty] | 2017-12-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:08
VD-9001-104-DSH-011 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-12-15 16:43 |  | No | -76 | 2017-12-31 14:28 | [7 empty] | 2017-12-31 19:59 | Yes | 0 | 1204-Owner-v | 2017-12-30 17:06
VD-9001-104-DSH-012 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-12-08 17:51 |  | No | -83 | 2017-12-26 15:43 | [7 empty] | 2017-12-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:08
VD-9001-104-DSH-013 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 |  |  | No | 841 | [9 empty] | No | 0
VD-9001-104-DSH-014 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-04-19 15:02 | 2018-04-19 15:09 | Yes | 108 |  |  |  | 2018-05-22 16:19 |  |  |  |  | 2018-05-22 19:59 | Yes | 19
VD-9001-104-DSH-015 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-04-19 15:02 | 2018-04-19 15:10 | Yes | 108 |  |  |  | 2018-05-22 17:14 |  |  |  |  | 2018-05-22 19:59 | Yes | 19
VD-9001-104-PID-001 | 0 | P&ID Index | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:05 |  | No | 21 | 2018-02-03 09:46 | 2018-01-31 16:16 | [6 empty] | 2018-02-03 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-24 09:10
VD-9001-104-PID-002 | 0 | Piping symbols schematic | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:05 | 2018-01-22 12:06 | Yes | 21 |  | 2018-01-31 16:11 | [6 empty] | 2018-01-31 20:00 | Yes | -5 | 1204-Owner-v | 2018-01-24 09:11
VD-9001-104-PID-003 | 0 | Instrumentation symbols schematic | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:06 |  | No | 21 | 2018-01-31 17:35 | [7 empty] | 2018-01-31 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-24 09:11
VD-9001-104-PID-004 | 0 | Piping detail diagram | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:06 |  | No | 21 | 2018-02-01 12:30 | [7 empty] | 2018-02-01 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-24 09:12
VD-9001-104-PID-005 | 0 | Instrumentation detail diagram | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:06 |  | No | 21 | 2018-01-31 17:16 | [7 empty] | 2018-01-31 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-24 09:13
VD-9001-104-PID-006 | 0 | P&ID LEGEND - INTERLOCK & FLUID CODES | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-01-22 12:06 |  | No | 21 | 2018-02-01 13:41 | [7 empty] | 2018-02-01 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-24 09:13
VD-9001-104-STR-002 | 0 | Control strategy | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-02-09 18:48 |  | No | 39 |  |  |  | 2018-03-11 17:55 |  |  |  |  | 2018-03-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-19 11:29
VD-9001-104-PPL-002 | 0 | Plot plan - Required maintenance / access space | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-01-29 14:06 | 2018-01-29 14:07 | Yes | -31 |  | 2018-02-20 15:32 | [6 empty] | 2018-02-20 19:59 | Yes | 8 | 1204-Owner-v | 2018-02-19 11:29
VD-9001-104-PPL-003 | 0 | ASU 3D model view | PR-104 | AIR LIQUIDE | 2018-03-01 |  |  | No | 841 | [9 empty] | No | 0
VD-9001-104-DSH-016 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-04-27 12:57 | 2018-04-27 13:00 | Yes | 116 |  |  |  | 2018-06-11 16:07 |  |  |  |  | 2018-06-11 19:59 | Yes | 31
VD-9001-104-DSH-017 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-04-27 12:57 | 2018-04-27 13:00 | Yes | 116 |  |  |  | 2018-06-11 15:31 |  |  |  |  | 2018-06-11 19:59 | Yes | 31
VD-9001-104-DSH-018 | 0 | EDS Equipment Data Sheet for ACC | PR-104 | AIR LIQUIDE | 2018-01-01 | 2018-02-02 12:01 |  | No | 32 | 2018-02-22 16:16 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-104-LST-004 | 0 | Spare parts list for erection, precommissioning, commissiong and start-up | PR-104 | AIR LIQUIDE | 2018-01-01 | 2017-12-15 13:47 |  | No | -17 | 2018-01-06 14:45 | [7 empty] | 2018-01-06 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:15
VD-9001-104-LST-005 | 0 | Spare parts list for 2 Years of operation | PR-104 | AIR LIQUIDE | 2018-01-01 |  |  | No | 900 | [9 empty] | No | 0
VD-9001-104-LST-006 | 0 | Capital Spare parts list (if needed) | PR-104 | AIR LIQUIDE | 2018-01-01 |  |  | No | 900 | [9 empty] | No | 0
VD-9001-104-DSH-019 | 0 | EDS Equipment data sheet - PBUC | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 19:02 |  | No | -20 | 2018-02-21 12:06 | [7 empty] | 2018-02-21 19:59 | Yes | 0
VD-9001-104-DSH-020 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 19:02 |  | No | -20 | 2018-02-21 12:10 | [7 empty] | 2018-02-21 19:59 | Yes | 0
VD-9001-104-EQL-001 | 0 | Main equipment list | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-03-08 17:37 | 2018-03-08 18:09 | Yes | 7 |  |  |  | 2018-03-27 16:19 |  |  |  |  | 2018-03-27 21:00 | Yes | 5 | 1204-Owner-v | 2018-04-24 16:32
VD-9001-104-PDS-001 | 0 | Process description | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-12 13:01 |  | No | -17 |  |  |  | 2018-03-07 18:47 |  |  |  |  | 2018-03-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-14 10:16
VD-9001-104-DIG-001 | 0 | Material selection P&ID | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-01-15 14:37 |  | No | -45 | 2018-01-22 11:22 | [7 empty] | 2018-01-22 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-16 15:01
VD-9001-104-HMB-001 | 0 | Mass and enthalpy balance "for information" | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-11-27 13:25 |  | No | -94 | 2017-12-24 10:05 | [7 empty] | 2017-12-24 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:13
VD-9001-104-LST-007 | 0 | Line list | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-04-04 14:07 | 2018-04-04 14:12 | Yes | 34 |  |  |  | 2018-04-25 16:24 |  |  |  |  | 2018-04-25 20:00 | Yes | 7 | 1204-Owner-v | 2018-05-15 10:36
VD-9001-104-PID-007 | 0 | PID AIR FILTER & MAC 1 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:07 |  | No | -20 |  |  |  | 2018-03-13 16:05 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:40
VD-9001-104-PID-008 | 0 | PID AIR FILTER & MAC 2 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:08 |  | No | -20 |  |  |  | 2018-03-14 09:36 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:43
VD-9001-104-PID-009 | 0 | PID ACC INTEGRATION | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:08 |  | No | -20 |  |  |  | 2018-03-18 12:46 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:43
VD-9001-104-PID-010 | 0 | PID Air Purification Vessel | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:08 |  | No | -20 |  |  |  | 2018-03-18 15:32 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:43
VD-9001-104-PID-011 | 0 | PID Reactivation Heater | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:08 |  | No | -20 |  |  |  | 2018-03-17 11:14 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:44
VD-9001-104-PID-012 | 0 | PID Booster turbine air interface with cold booster | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-14 09:42 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:30
VD-9001-104-PID-013 | 0 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-17 12:08 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:44
VD-9001-104-PID-014 | 0 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-18 13:11 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:46
VD-9001-104-PID-015 | 0 | PID DETAILS FOR MAIN HEAT EXCHANGER | PR-104 | AIR LIQUIDE | 2018-03-01 |  | 2018-04-19 19:51 | Yes | 841 | [6 empty] | 2018-04-23 10:10 | 2018-04-23 10:10 |  | Yes | 0
VD-9001-104-PID-016 | 0 | PID Main Heat Exchanger | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-13 11:04 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:30
VD-9001-104-PID-017 | 0 | PID Subcooler | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-13 10:48 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:30
VD-9001-104-PID-018 | 0 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-14 17:38 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:46
VD-9001-104-PID-019 | 0 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-14 17:41 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:46
VD-9001-104-PID-020 | 0 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-18 12:10 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:46
VD-9001-104-PID-021 | 0 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:09 |  | No | -20 |  |  |  | 2018-03-18 12:49 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:47
VD-9001-104-PID-022 | 0 | PID HP Column / Main Vaporizer | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-13 11:58 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:31
VD-9001-104-PID-023 | 0 | PID LP Column / Pure Nitrogen Column | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-13 14:32 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:31
VD-9001-104-PID-024 | 0 | PID Liquid Nitrogen Storage | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:40 |  | No | -27 |  |  |  | 2018-03-14 11:15 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:32
VD-9001-104-PID-025 | 0 | PID Liquid Nitrogen Vaporizer | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:41 |  | No | -27 |  |  |  | 2018-03-14 11:54 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:32
VD-9001-104-PID-026 | 0 | PID Cryogenic Disposal Purges | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:10 |  | No | -20 |  |  |  | 2018-03-18 12:36 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:47
VD-9001-104-PID-027 | 0 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:10 |  | No | -20 |  |  |  | 2018-04-09 15:36 |  |  |  |  | 2018-04-09 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:53
VD-9001-104-PID-028 | 0 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:10 |  | No | -20 |  |  |  | 2018-04-09 15:36 |  |  |  |  | 2018-04-09 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:53
VD-9001-104-PID-029 | 0 | PID Air interface | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:41 |  | No | -27 |  |  |  | 2018-03-18 11:24 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:32
VD-9001-104-PID-030 | 0 | PID Gaseous Oxygen Production | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:41 |  | No | -27 |  |  |  | 2018-03-17 17:37 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:32
VD-9001-104-PID-031 | 0 | PID Gaseous Nitrogen Production | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:10 |  | No | -20 |  |  |  | 2018-03-17 18:24 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:53
VD-9001-104-PID-032 | 0 | PID Tie-ins | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:41 |  | No | -27 |  |  |  | 2018-03-14 15:44 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:33
VD-9001-104-PID-033 | 0 | PID Cooling Water Distribution | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:41 |  | No | -27 |  |  |  | 2018-03-18 10:45 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:33
VD-9001-104-PID-034 | 0 | PID UTILITIES TIE-INS WASTE WATER PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-09 16:10 |  | No | -20 |  |  |  | 2018-03-13 10:21 |  |  |  |  | 2018-03-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-10 08:53
VD-9001-104-PID-035 | 0 | PID UTILITIES TIE-INS OIL PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:42 |  | No | -27 |  |  |  | 2018-03-17 12:12 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:33
VD-9001-104-PID-036 | 0 | PID Derime | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:42 |  | No | -27 |  |  |  | 2018-03-18 15:39 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:34
VD-9001-104-PID-037 | 0 | PID Instrument Air System | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:42 |  | No | -27 |  |  |  | 2018-03-17 16:44 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:34
VD-9001-104-PID-038 | 0 | PID Service Nitrogen | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:42 |  | No | -27 |  |  |  | 2018-03-14 15:37 |  |  |  |  | 2018-03-14 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:34
VD-9001-104-PID-039 | 0 | PID Steam | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:42 |  | No | -27 |  |  |  | 2018-03-17 16:51 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:34
VD-9001-104-PID-040 | 0 | PID Utilities tie-in | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-02-02 18:47 |  | No | -27 |  |  |  | 2018-03-18 15:51 |  |  |  |  | 2018-03-18 21:00 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:35
VD-9001-104-DSH-021 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-DSH-022 | 0 | Gas Analysers - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-02-01 10:59 |  | No | -59 | 2018-02-22 12:45 | [7 empty] | 2018-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2019-12-11 10:06
VD-9001-104-DIG-024 | 0 | Cause & effect diagram | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-DSH-023 | 0 | EDS Equipment Data Sheet fo Steam ejector | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-DSH-024 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-DSH-025 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-PCJ-004 | 0 | Painting specification & procedure | PR-104 | AIR LIQUIDE | 2018-05-01 | 2017-12-20 18:41 |  | No | -132 | 2018-01-02 09:41 | [7 empty] | 2018-01-02 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:17
VD-9001-104-DWG-001 | 0 | Area X - Civil work guide drawing | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-LST-008 | 0 | List of special tools and device (if needed) | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-DSH-026 | 0 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-PLN-001 | 0 | MP/BP Section views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-002 | 0 | MP/BP Elevation views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-003 | 0 | MP/BP Elevation views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-001 | 0 | MP/BP Isometric views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-004 | 0 | EXC Section views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-005 | 0 | EXC Elevation views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-002 | 0 | EXC Isometric views piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-006 | 0 | P03 piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-007 | 0 | P05 piping drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PLN-008 | 0 | Casing interconnection piping drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-003 | 0 | MP/BP CS Isometric drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-004 | 0 | EXC CS Isometric drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-005 | 0 | P03 CS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-006 | 0 | P05 CS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-007 | 0 | Casing interconnection CS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-008 | 0 | MP/BP SS Isometric drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-009 | 0 | EXC SS Isometric drawing | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-010 | 0 | P03 SS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-011 | 0 | P05 SS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-ISO-012 | 0 | Casing interconnection SS isometric drawings | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-001 | 0 | MP/BP CS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-002 | 0 | EXC CS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-003 | 0 | P03 CS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-004 | 0 | P05 CS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-005 | 0 | Casing interconnection CS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-006 | 0 | MP/BP SS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-007 | 0 | EXC SS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-008 | 0 | P03 SS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-009 | 0 | P05 SS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-010 | 0 | CB - Casing interconnection SS piping BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-011 | 0 | CB - Bolting BOM | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-LST-009 | 0 | Range, Alarms and Threshold list (RAT list) | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-LST-013 | 0 | Compliance check list for Gaseous Oxygen lines (specification for oxygen service) | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-002 | 0 | BPCS Functional Diagram_Air Purification | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-003 | 0 | SIS Functional Diagram_Air Purification | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-004 | 0 | BPCS Functional Diagram_Exchangers | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-005 | 0 | SIS Functional Diagram_Exchangers | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-006 | 0 | BPCS Functional Diagram_Distillation | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-007 | 0 | SIS Functional Diagram_Distillation | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-008 | 0 | BPCS Functional Diagram_Cryogenic Pumps | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-009 | 0 | SIS Functional Diagram_Cryogenic Pumps | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-010 | 0 | BPCS Functional Diagram_Cooling Water, Cryo Purges, Steam & Clean Condensate | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-011 | 0 | BPCS Functional Diagram_NL storage | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-012 | 0 | SIS Functional Diagram_NL storage | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-013 | 0 | BPCS Functional Diagram_NL Backup Vaporizers | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-014 | 0 | SIS Functional Diagram_NL Backup Vaporizers | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-015 | 0 | BPCS Functional Diagram_Main Air Compressor | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-016 | 0 | BPCS Functional Diagram_Warm Air Expander | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-017 | 0 | BPCS Functional Diagram_Cold Air Expander | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-018 | 0 | SIS Functional Diagram_Main Air Compressor | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-019 | 0 | SIS Functional Diagram_Warm Air Expander | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-020 | 0 | SIS Functional Diagram_Cold Air Expander | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-021 | 0 | BPCS Functional Diagram_Interconnections | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-022 | 0 | BPCS Functional Diagram_Gas & Instrumentation Utilities | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIG-023 | 0 | BPCS Functional Diagram_Electricity & Instrumentation Fault | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PPL-004 | 0 | Machine building - Civil work guide drawing - Plan view | PR-104 | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104-PPL-005 | 0 | Machine building - Civil work guide drawing - Elevation views | PR-104 | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104-PLN-009 | 0 | Outside CB equipment - piping drawing 1 | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-PLN-010 | 0 | Outside CB equipment - piping drawing 2 | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-PLN-011 | 0 | Outside CB equipment - piping drawing 3 | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-PLN-012 | 0 | Outside CB equipment - piping drawing 3 | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-ISO-013 | 0 | Outside CB equipment - CS isometric drawing | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-ISO-014 | 0 | Outside CB equipment - SS isometric drawing | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MAL-012 | 0 | Outside CB - Reinforced pads BOM | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MAL-013 | 0 | CB (inside & outside) - General piping supports BOM | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MAL-014 | 0 | Outside CB - CS piping BOM | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MAL-015 | 0 | Outside CB - SS piping BOM | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MAL-016 | 0 | Outside CB - Bolting BOM | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-MNL-001 | 0 | Operating Manual | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-MNL-002 | 0 | Construction - Erection Guideline | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-MNL-003 | 0 | Operating Manual - Table of contents START UP section | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-REQ-005 | 0 | TRS Technical Requisition Sheet for Piping insulation (Cold&Warm) | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-REQ-006 | 0 | TRS Technical Requisition Sheet for insulation- Perlite | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-REQ-007 | 0 | TRS Technical Requisition Sheet for insulation- Rockwool | PR-104 | AIR LIQUIDE | 2018-12-01 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-104-MAL-017 | 0 | BOM for insulation- Permali shims | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-018 | 0 | BOM for insulation- Teflon shims | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-019 | 0 | BOM for insulation- Piping insulation (Cold&Warm) | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-020 | 0 | BOM for insulation- - Perlite | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-021 | 0 | BOM for insulation- Rockwool | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-022 | 0 | CB - Reinforced pads BOM | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MAL-023 | 0 | CB - Seal boot for cryogenic valve BOM | PR-104 | AIR LIQUIDE | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-104-MNL-004 | 0 | Health Safety and Environment Plan for erection | PR-104 | AIR LIQUIDE | 2019-03-01 | 2017-10-23 10:39 |  | No | -494 | 2017-11-11 11:42 | [7 empty] | 2017-11-11 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:16
VD-9001-104-MNL-005 | 0 | Health Safety and Environment Plan for commissioning | PR-104 | AIR LIQUIDE | 2019-03-01 | 2017-10-23 10:38 |  | No | -494 | 2017-11-11 16:39 | [7 empty] | 2017-11-11 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:16
VD-9001-104-REQ-001 | 0 | Battery Charger (BC-501)_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DIS-001 | 0 | Battery Charger (BC-501)_VDR Vendor Documents Register | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-QCP-002 | 0 | Battery Charger (BC-501)_IDS Inspection Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DSH-027 | 0 | Battery Charger (BC-501)_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-LST-010 | 0 | Instrumentation electrical consumption | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-LST-011 | 0 | Instrumentation list | PR-104 | AIR LIQUIDE | 2018-06-01 | 2018-02-16 15:27 |  | No | -105 | 2018-02-21 10:42 | [7 empty] | 2018-02-21 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-19 11:26
VD-9001-104-DSH-028 | 0 | Pressure - EDS Equipment Data Sheet for pressure gauge | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-029 | 0 | Levels - EDS Equipment Data Sheet (level indicator) | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-030 | 0 | Levels - EDS Equipment Data Sheet (level switch) | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-031 | 0 | Levels - EDS Equipment Data Sheet (capacitive transmitter) | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104-DSH-032 | 0 | Flowmeter - EDS Equipment Data Sheet (diaphragm FE) | PR-104 | AIR LIQUIDE | 2018-06-01 | 2018-03-26 17:06 | 2018-03-26 17:06 | Yes | -67 |  |  |  | 2018-06-02 10:58 |  |  |  |  | 2018-06-02 19:59 | Yes | 54 | 1204-Owner-v | 2018-05-15 16:54
VD-9001-104-DSH-033 | 0 | Flowmeter - EDS Equipment Data Sheet (flow orifice) | PR-104 | AIR LIQUIDE | 2018-06-01 | 2018-03-26 17:08 | 2018-03-26 17:09 | Yes | -67 |  |  |  | 2018-04-22 15:34 |  |  |  |  | 2018-04-22 20:00 | Yes | 13
VD-9001-104-DSH-034 | 0 | Flowmeter - EDS Equipment Data Sheet (pitot) | PR-104 | AIR LIQUIDE | 2018-06-01 | 2018-03-26 17:10 | 2018-03-26 17:10 | Yes | -67 |  |  |  | 2018-05-14 15:36 |  |  |  |  | 2018-05-14 20:00 | Yes | 35
VD-9001-104-DSH-035 | 0 | Flowmeter - EDS Equipment Data Sheet (electromagnetic) | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-036 | 0 | Flowmeter - EDS Equipment Data Sheet (variable area flowmeter) | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104-DSH-037 | 0 | Cryo Temperature - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-07-01 | 2018-03-08 17:40 | 2018-03-08 18:09 | Yes | -115 |  |  |  | 2018-06-10 17:30 |  |  |  |  | 2018-06-10 19:59 | Yes | 80
VD-9001-104-DSH-038 | 0 | Warm Temperature - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-07-01 | 2018-03-08 17:38 | 2018-03-08 18:09 | Yes | -115 |  |  |  | 2018-05-23 16:48 |  |  |  |  | 2018-05-23 19:59 | Yes | 62
VD-9001-104-DSH-039 | 0 | Temperature - EDS Equipment Data Sheet for temperature gauge | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-040 | 0 | Pressure transmitter - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104-DSH-041 | 0 | Differential Pressure transmitter - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104-DSH-042 | 0 | Temperature transmitter - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104-DSH-043 | 0 | Cryo automatic valve - EDS Equipment Data Sheet for globe valves | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-12-06 11:35 |  | No | -85 | 2017-12-17 16:34 | [7 empty] | 2017-12-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:10
VD-9001-104-DSH-044 | 0 | Cryo automatic valve - EDS Equipment Data Sheet for butterfly valves | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-12-06 11:34 |  | No | -85 | 2017-12-18 11:42 | [7 empty] | 2017-12-18 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:12
VD-9001-104-DSH-045 | 0 | Cryo automatic valve - EDS Equipment Data Sheet for JT globe valves | PR-104 | AIR LIQUIDE | 2018-03-01 | 2017-12-06 11:35 |  | No | -85 | 2017-12-17 15:53 | [7 empty] | 2017-12-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:12
VD-9001-104-DSH-046 | 0 | Cryo PSV - EDS Equipment Data Sheet (pressure) | PR-104 | AIR LIQUIDE | 2018-05-01 | 2017-12-20 15:01 |  | No | -132 | 2017-12-25 16:57 | [7 empty] | 2017-12-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:13
VD-9001-104-DSH-047 | 0 | Cryo TSV - EDS Equipment Data Sheet (thermal) | PR-104 | AIR LIQUIDE | 2018-05-01 | 2017-12-20 15:02 |  | No | -132 | 2017-12-25 17:40 | [7 empty] | 2017-12-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:13
VD-9001-104-DSH-048 | 0 | Cryo PSE - EDS Equipment Data Sheet (rupture disks) | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-DSH-049 | 0 | Warm automatic globe valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-01-29 13:00 |  | No | -62 | 2018-02-22 18:17 | [7 empty] | 2018-02-22 20:00 | Yes | 0 | 1204-Owner-v | 2018-07-22 10:21
VD-9001-104-DSH-050 | 0 | Warm automatic butterfly valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-01-29 12:35 |  | No | -62 | 2018-02-18 18:02 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-104-DSH-051 | 0 | Warm automatic 3-lever valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2017-12-08 16:37 |  | No | -114 | 2017-12-23 16:00 | [7 empty] | 2017-12-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:13
VD-9001-104-DSH-052 | 0 | Warm automatic ball valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-DSH-053 | 0 | Warm PSV - EDS Equipment Data Sheet (pressure) | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-02-26 16:01 | 2018-02-26 16:01 | Yes | -34 |  |  |  | 2018-05-03 12:26 |  |  |  |  | 2018-05-03 19:59 | Yes | 52 | 1204-Owner-v | 2018-03-07 15:58
VD-9001-104-DSH-054 | 0 | Warm TSV - EDS Equipment Data Sheet (thermal) | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-02-26 15:59 | 2018-02-26 15:59 | Yes | -34 |  |  |  | 2018-03-12 14:48 |  |  |  |  | 2018-03-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 15:56
VD-9001-104-DSH-055 | 0 | PCV - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 | 2018-04-04 12:51 | 2018-04-04 12:51 | Yes | 34 |  |  |  | 2018-05-27 17:34 |  |  |  |  | 2018-05-27 19:59 | Yes | 39 | 1204-Owner-v | 2018-07-22 10:06
VD-9001-104-SLD-001 | 0 | LV One line diagram | PR-104 | AIR LIQUIDE | 2018-05-01 | 2018-03-05 12:09 | 2018-03-07 14:16 | Yes | -57 |  |  |  | 2018-04-11 16:00 |  |  |  |  | 2018-04-11 20:00 | Yes | 23 | 1204-Owner-v | 2018-03-13 13:52
VD-9001-104-LST-012 | 0 | Consumers list | PR-104 | AIR LIQUIDE | 2018-05-01 | 2018-01-16 11:17 |  | No | -105 | 2018-01-30 12:18 | [7 empty] | 2018-01-30 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-22 11:44
VD-9001-104-PPL-006 | 0 | Electrical main cable routing Basic Design - Plot plan top view | PR-104 | AIR LIQUIDE | 2018-07-01 | 2018-01-29 15:01 |  | No | -153 | 2018-02-17 15:59 | [7 empty] | 2018-02-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-04 12:20
VD-9001-104-SPE-001 | 0 | Lighting installation specific requirements | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PPL-007 | 0 | Lighting installation Basic Design - Plot plan top view | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-SPE-002 | 0 | Earthing network specific requirements and Basic Design layout | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-SPE-003 | 0 | Lightning protection specific requirements and Basic Design layout | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-MAL-024 | 0 | Master packing list | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-REQ-002 | 0 | LV Motor Control Center (Y201)_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DIS-002 | 0 | LV Motor Control Center (Y201)_VDR Vendor Documents Register | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-QCP-003 | 0 | LV Motor Control Center (Y201)_IDS Inspection Data Sheet | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-DSH-056 | 0 | LV Motor Control Center (Y201)_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-REQ-003 | 0 | Power distribution bord for DCS&SIS_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DIS-003 | 0 | Power distribution bord for DCS&SIS_VDR Vendor Documents Register | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-QCP-004 | 0 | Power distribution bord for DCS&SIS_IDS Inspection Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DSH-057 | 0 | Power distribution bord for DCS&SIS_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DSH-058 | 0 | SIS & BPCS_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-SPE-004 | 0 | SIS & BPCS_Configuration specification | PR-104 | AIR LIQUIDE | 2019-02-01 |  |  | No | 504 | [9 empty] | No | 0
VD-9001-104-INR-001 | 0 | SIS & BPCS_Software test report | PR-104 | AIR LIQUIDE | 2019-04-01 |  |  | No | 445 | [9 empty] | No | 0
VD-9001-104-DSH-059 | 0 | UPS_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-REQ-004 | 0 | UPS _TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-DIS-004 | 0 | UPS _VDR Vendor Documents Register | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-QCP-005 | 0 | UPS _IDS Inspection Data Sheet | PR-104 | AIR LIQUIDE | 2018-11-01 |  |  | No | 596 | [9 empty] | No | 0
VD-9001-104-KPL-001 | 0 | Plot plan - Key plan | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-12 12:56 |  | No | -20 | 2017-10-15 16:28 | [7 empty] | 2017-10-15 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:14
VD-9001-104-DIS-001 | 0 | VENDOR DOCUMENTS INDEX and SCHEDULE for ALE documents list | PR-104 | AIR LIQUIDE | 2017-10-10 |  |  | No | 983 | [9 empty] | No | 0
VD-9001-104-DIS-002 | 0 | VENDOR DOCUMENTS INDEX and SCHEDULE (VDIS) for Sub-vendor documents | PR-104 | AIR LIQUIDE | 2017-11-01 |  |  | No | 961 | [9 empty] | No | 0
VD-9001-254-PCJ-132 | 1 | TAKING THE BOILER OUT OF SERVICE PROCEDURE | HM-254 | AZAR AB | 2017-10-22 20:00 | 2018-12-11 13:20 | 2018-12-11 13:20 | Yes | 415 |  |  | 2018-12-26 09:16 | [5 empty] | 2018-12-26 09:16 | Yes | 1
VD-9001-254-LST-302 | 3 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2017-10-25 20:00 | 2017-10-23 11:49 |  | No | -2 | 2017-11-04 09:40 | [7 empty] | 2017-11-04 19:59 | Yes | 0
VD-9001-254-LST-301 | 3 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-10-25 20:00 | 2017-10-23 11:48 |  | No | -2 | 2017-11-04 09:36 | [7 empty] | 2017-11-04 19:59 | Yes | 0
VD-9001-254-LST-362 | 3 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2017-10-25 20:00 | 2017-10-23 12:09 |  | No | -2 | 2017-11-04 09:50 | [7 empty] | 2017-11-04 19:59 | Yes | 0
VD-9001-104-PFD-006 | 1 | PFD Water utilities | PR-104 | AIR LIQUIDE | 2017-10-28 20:00 | 2017-12-01 12:56 |  | No | 34 | 2017-12-16 16:01 | [7 empty] | 2017-12-16 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:21
VD-9001-104-PFD-001 | 1 | PFD Compression and purification | PR-104 | AIR LIQUIDE | 2017-10-28 20:00 | 2017-12-01 12:51 |  | No | 34 | 2017-12-10 15:52 | [7 empty] | 2017-12-10 20:00 | Yes | 0 | 1204-Owner-v | 2017-12-31 12:52
VD-9001-104-PFD-002 | 1 | PFD Cold box | PR-104 | AIR LIQUIDE | 2017-10-28 20:00 | 2017-12-01 12:51 |  | No | 34 | 2017-12-11 17:42 | [7 empty] | 2017-12-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:19
VD-9001-104-PFD-003 | 1 | PFD Liquid Nitrogen storage and vaporization | PR-104 | AIR LIQUIDE | 2017-10-28 20:00 | 2017-12-01 12:56 |  | No | 34 | 2017-12-16 12:13 | [7 empty] | 2017-12-16 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:20
VD-9001-104-PFD-004 | 1 | PFD Gas utilities | PR-104 | AIR LIQUIDE | 2017-10-28 20:00 | 2017-12-01 12:56 |  | No | 34 | 2017-12-16 11:47 | [7 empty] | 2017-12-16 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:20
VD-9001-104-PFD-005 | 1 | PFD Cryogenic disposal | PR-104 | AIR LIQUIDE | 2017-10-29 20:00 | 2017-12-01 12:56 |  | No | 33 | 2017-12-16 14:31 | [7 empty] | 2017-12-16 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:21
VD-9001-104-PFD-008 | 1 | PFD Interconnection | PR-104 | AIR LIQUIDE | 2017-10-29 20:00 | 2017-12-01 12:57 |  | No | 33 | 2017-12-18 14:52 | [7 empty] | 2017-12-18 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:22
VD-9001-104-PFD-007 | 1 | PFD Steam utilities | PR-104 | AIR LIQUIDE | 2017-10-29 20:00 | 2017-12-01 12:57 |  | No | 33 | 2017-12-16 16:33 | [7 empty] | 2017-12-16 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:21
VD-9001-104-QCP-001 | 1 | Quality Control Plan | PR-104 | AIR LIQUIDE | 2017-10-29 20:00 | 2017-10-23 16:02 |  | No | -6 | 2017-11-12 15:25 | [7 empty] | 2017-11-12 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:23
VD-9001-104-KPL-001 | 1 | Plot plan - Key plan | PR-104 | AIR LIQUIDE | 2017-10-29 20:00 | 2018-01-30 17:54 |  | No | 93 | 2018-02-20 15:25 | [7 empty] | 2018-02-20 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-07 09:38
VD-9001-104-INP-001 | 1 | Inspection and regulating rules | PR-104 | AIR LIQUIDE | 2017-10-31 19:59 |  |  | No | 962 | [9 empty] | No | 0
VD-9001-104-REQ-008 | 0 | E-6101/E-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-11-07 13:27 |  | No | 6 | 2017-11-20 14:50 | [7 empty] | 2017-11-20 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:23
VD-9001-104-REQ-009 | 0 | E-6101/E-6103_TRS Technical Requisition Sheet for transition joints | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-02-05 16:15 |  | No | 66 |  | 2018-02-17 14:47 | [6 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-104-REQ-010 | 0 | E-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2018-02-02 12:43 |  | No | 93 | 2018-02-19 17:13 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-104-REQ-011 | 0 | E-6180_TRS Technical Requisition Sheet Liquid disposal vaporizer | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-REQ-012 | 0 | E-6151_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2018-03-30 16:56 | 2018-03-30 16:57 | Yes | 119 |  |  |  | 2018-05-01 10:41 |  |  |  |  | 2018-05-01 19:59 | Yes | 18
VD-9001-104-REQ-013 | 0 | PU-6101_HP COLUMN T-6101, LP COLUMN T-6102 LOWER PART, HP AL SEPARATOR DRUM D-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-20 11:41 |  | No | -12 | 2017-10-25 11:38 | [7 empty] | 2017-10-25 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:24
VD-9001-104-REQ-014 | 0 | LP COLUMN T-6102 UPPER PART_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-11-09 17:02 |  | No | 8 | 2017-11-15 18:16 | [7 empty] | 2017-11-15 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:24
VD-9001-104-REQ-015 | 0 | TK-6150_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-01 | 2017-10-20 11:42 |  | No | -73 | 2017-10-25 12:12 | [7 empty] | 2017-10-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:24
VD-9001-104-REQ-016 | 0 | DR-6101A&B_TRS Technical Requisition Sheet Adsorber | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-12-05 14:35 |  | No | 34 | 2017-12-13 11:37 | [7 empty] | 2017-12-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:24
VD-9001-104-REQ-017 | 0 | E-6124_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-15 16:43 |  | No | 14 | 2017-12-19 16:00 | [7 empty] | 2017-12-19 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:25
VD-9001-104-REQ-018 | 0 | PU-6101_E-6108/ E-6108-D1_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-08 14:10 |  | No | 7 | 2017-12-19 15:20 | [7 empty] | 2017-12-19 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:25
VD-9001-104-REQ-019 | 0 | FT-6101/FT-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2018-01-31 17:16 |  | No | 91 | 2018-02-10 18:33 | [7 empty] | 2018-02-10 20:00 | Yes | 0
VD-9001-104-REQ-020 | 0 | E-6187_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-04 12:25 |  | No | 3 | 2017-12-26 09:34 | [7 empty] | 2017-12-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:25
VD-9001-104-REQ-021 | 0 | C-6101 / C-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2018-01-23 18:52 |  | No | 83 | 2018-02-21 19:12 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104-REQ-022 | 0 | P-6103A / P-6103B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-12-06 12:33 |  | No | 35 | 2017-12-13 17:05 | [7 empty] | 2017-12-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:25
VD-9001-104-REQ-023 | 0 | P-6105A / P-6105B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 |  | 2018-05-22 12:43 | Yes | 961 | [6 empty] | 2018-05-26 11:31 | 2018-05-26 11:31 |  | Yes | 0
VD-9001-104-REQ-024 | 0 | P-6108A/B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-01 |  |  | No | 841 | [9 empty] | No | 0
VD-9001-104-REQ-025 | 0 | STC-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-12-06 12:33 |  | No | 35 | 2017-12-13 15:42 | [7 empty] | 2017-12-13 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:25
VD-9001-104-REQ-026 | 0 | STC-6104_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-01 |  |  | No | 961 | [9 empty] | No | 0
VD-9001-104-REQ-027 | 0 | VFD of P-6103-A&B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-REQ-028 | 0 | VFD of P-6105-A&B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-DIG-025 | 0 | Control System Interconecting Diagram | PR-104 | AIR LIQUIDE | 2017-11-01 | 2017-10-20 11:21 |  | No | -12 | 2017-10-22 17:22 | [7 empty] | 2017-10-22 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:04
VD-9001-104-PPL-008 | 0 | Underground Piping plot plan (Basic Design) | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-22 14:04 |  | No | 21 | 2018-01-17 16:41 | [7 empty] | 2018-01-17 19:59 | Yes | 0 | 1204-Owner-v | 2017-12-31 12:47
VD-9001-104-DWG-002 | 0 | Structure-TEKLA Model ( native File) | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-TBL-001 | 0 | Pipe rack- Table Load | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-TBL-002 | 0 | Compressor shelther - Table Load | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-SPE-007 | 0 | Handrail and platform ALE standard | PR-104 | AIR LIQUIDE | 2018-05-01 | 2018-01-15 13:17 |  | No | -106 | 2018-01-21 17:29 | [7 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-104-SPE-008 | 0 | Welding repair procedure (CPY-GS-3-0-4) | PR-104 | AIR LIQUIDE | 2017-11-01 |  |  | No | 961 | [9 empty] | No | 0
VD-9001-104-RPT-001 | 0 | Hazop study report | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-02-19 17:06 |  | No | -41 |  |  |  | 2018-05-03 12:52 |  |  |  |  | 2018-05-03 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-21 12:32
VD-9001-104-RPT-002 | 0 | SIL study Report | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-029 | 0 | Gas Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-02-01 10:59 |  | No | 0 | 2018-02-13 10:48 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-104-REQ-030 | 0 | Moisture Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-02-09 13:23 |  | No | 8 | 2018-02-19 17:49 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-104-REQ-031 | 0 | Pressure Gauges - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-032 | 0 | Level switch - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-033 | 0 | Flowmeter - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-03-26 16:29 | 2018-03-26 16:33 | Yes | -6 |  |  |  | 2018-04-18 09:16 |  |  |  |  | 2018-04-18 20:00 | Yes | 9
VD-9001-104-REQ-034 | 0 | Temperature - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-03-05 12:12 | 2018-03-07 16:16 | Yes | -27 |  |  |  | 2018-03-18 16:20 |  |  |  |  | 2018-03-18 21:00 | Yes | -1
VD-9001-104-REQ-035 | 0 | Transmitters - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-036 | 0 | Cryogenic Globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-06 11:29 |  | No | 5 | 2017-12-20 16:59 | [7 empty] | 2017-12-20 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:26
VD-9001-104-REQ-037 | 0 | Cryogenic Butterfly automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-06 11:33 |  | No | 5 | 2017-12-20 17:05 | [7 empty] | 2017-12-20 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:26
VD-9001-104-REQ-038 | 0 | Cryogenic JT globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-06 11:33 |  | No | 5 | 2017-12-20 17:09 | [7 empty] | 2017-12-20 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:26
VD-9001-104-REQ-039 | 0 | Cryo PSV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-12-20 15:00 |  | No | 19 | 2017-12-25 16:29 | [7 empty] | 2017-12-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:26
VD-9001-104-REQ-040 | 0 | Warm automatic globe valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-01-29 12:47 |  | No | -3 | 2018-02-13 10:41 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-104-REQ-041 | 0 | Warm automatic butterfly valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-01-29 12:20 |  | No | -3 | 2018-02-13 10:25 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-104-REQ-042 | 0 | Warm automatic 3-lever valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2017-12-08 16:37 |  | No | -55 | 2017-12-23 15:45 | [7 empty] | 2017-12-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:27
VD-9001-104-REQ-043 | 0 | Warm automatic ball valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-REQ-044 | 0 | Warm PSV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-02-26 15:45 | 2018-02-26 15:45 | Yes | 25 |  |  |  | 2018-03-18 16:24 |  |  |  |  | 2018-03-18 21:00 | Yes | 6
VD-9001-104-REQ-045 | 0 | PCV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-04-04 12:39 | 2018-04-04 12:41 | Yes | 3 |  |  |  | 2018-04-17 10:00 |  |  |  |  | 2018-04-17 20:00 | Yes | -1
VD-9001-104-REQ-046 | 0 | SIS & DCS - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-REQ-047 | 0 | Analyser Shelther - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 |  |  | No | 869 | [9 empty] | No | 0
VD-9001-104-DSH-061 | 0 | Moisture Analysers_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-02-01 | 2018-02-09 13:49 |  | No | 8 | 2018-02-22 14:07 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-104-REQ-048 | 0 | Differential Pressure Gauges - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-049 | 0 | Electromagnetic Flowmeter - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-050 | 0 | Rotameter - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-051 | 0 | Junction boxes - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104-PCJ-005 | 1 | Project equipments numbering procedure | PR-104 | AIR LIQUIDE | 2017-11-01 20:00 | 2017-12-01 11:44 | 2017-12-01 11:46 | Yes | 30 |  | 2017-12-05 10:54 | [6 empty] | 2017-12-05 20:00 | Yes | -10 | 1204-Owner-v | 2018-01-03 16:14
VD-9001-253(A)-DIS-097 | 1 | VENDOR DOCUMENT INDEX AND SCHEDULE | HM-253A | FATEH SANAT KIMIA | 2017-10-21 11:58 | 2017-10-21 12:07 | 2017-10-21 12:08 | Yes | 0 |  | 2017-10-21 16:28 | [6 empty] | 2017-10-21 20:00 | Yes | -14 | 1204-Owner-v | 2018-07-12 11:21
VD-9001-253(A)-RPT-113 | 1 | HSE PLAN | HM-253A | FATEH SANAT KIMIA | 2017-10-22 | 2017-12-24 11:50 | 2017-12-24 11:51 | Yes | 63 |  | 2018-01-20 09:28 | [6 empty] | 2018-01-20 19:59 | Yes | 13
VD-9001-204A-DWG-116 | 2 | External Attachment Drawing FOR D-4004 | PV-204A | Asas Sanat Pars Inc. | 2017-10-22 | 2017-10-23 12:58 | 2017-10-23 12:59 | Yes | 1 |  | 2017-10-24 14:45 | [6 empty] | 2017-10-24 20:00 | Yes | -13 | 1204-Owner-v | 2019-03-07 15:23
VD-9001-204A-DWG-029 | 3 | Shipping Drawing for D-2002 | PV-204A | Asas Sanat Pars Inc. | 2017-10-22 | 2017-10-23 12:52 | 2017-10-23 12:53 | Yes | 1 |  | 2017-10-24 14:41 | [6 empty] | 2017-10-24 20:00 | Yes | -13
VD-9001-104-SPE-005 | 1 | Piping General Specification | PR-104 | AIR LIQUIDE | 2017-11-05 19:59 | 2017-11-24 16:27 |  | No | 19 | 2017-11-26 16:32 | [7 empty] | 2017-11-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:27
VD-9001-104-DIG-025 | 1 | Control System Interconecting Diagram | PR-104 | AIR LIQUIDE | 2017-11-05 20:00 |  |  | No | 957 | [9 empty] | No | 0
VD-9001-108-DWG-037 | 1 | FAN STACK DETAIL FOR COOLING TOWER | PR-108 | Farabard | 2017-10-23 14:59 | 2017-10-25 10:53 | 2017-10-25 10:54 | Yes | 2 |  | 2017-10-25 17:14 | [6 empty] | 2017-10-25 20:00 | Yes | -14
VD-9001-108-DWG-071 | 2 | Louver Detail | PR-108 | Farabard | 2017-10-23 14:59 | 2017-10-25 10:54 | 2017-10-25 10:55 | Yes | 2 |  | 2017-10-25 17:16 | [6 empty] | 2017-10-25 20:00 | Yes | -14
VD-9001-201-WBK-001 | 2 | WELDING DATA BOOK | PV-201 | ATB RIVA CALZONI SpA | 2017-10-23 | 2017-11-13 16:23 | 2017-11-13 16:24 | Yes | 21 |  | 2017-11-26 16:41 | [6 empty] | 2017-11-26 19:59 | Yes | -1 | 1204-Owner-v | 2018-12-16 21:40
VD-9001-104-PCJ-002 | 1 | External communication procedure ALE / Customer | PR-104 | AIR LIQUIDE | 2017-11-06 19:59 |  |  | No | 956 | [9 empty] | No | 0
VD-9001-104-MDB-001 | 1 | Manufacturing Data Book | PR-104 | AIR LIQUIDE | 2017-11-06 20:00 | 2017-11-14 13:38 |  | No | 8 | 2017-11-28 16:43 | [7 empty] | 2017-11-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:16
VD-9001-204A-DWG-019 | 2 | Shipping Drawing for D-1001 | PV-204A | Asas Sanat Pars Inc. | 2017-10-24 12:17 | 2017-10-24 14:11 | 2017-10-24 14:12 | Yes | 0 |  | 2017-10-24 17:19 | [6 empty] | 2017-10-24 20:00 | Yes | -14
VD-9001-204A-DWG-066 | 2 | External Attachment Drawing FOR D-3003 | PV-204A | Asas Sanat Pars Inc. | 2017-10-24 12:17 | 2017-10-24 14:15 | 2017-10-24 14:16 | Yes | 0 |  | 2017-10-24 17:32 | [6 empty] | 2017-10-24 20:00 | Yes | -14
VD-9001-204A-DWG-154 | 3 | PF & LD Detail FOR D-6402 | PV-204A | Asas Sanat Pars Inc. | 2017-10-24 12:17 |  |  | No | 969 | [9 empty] | No | 0
VD-9001-204A-DWG-172 | 4 | Nozzle Detail FOR D-8301 | PV-204A | Asas Sanat Pars Inc. | 2017-10-24 | 2017-10-25 10:55 | 2017-10-25 10:55 | Yes | 1 |  | 2017-10-25 11:21 | [6 empty] | 2017-10-25 19:59 | Yes | -14
VD-9001-204C-DIS-001 | 0 | VENDOR DOCUMETN INDEX AND SCHEDULE (VDIS) | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-10-13 |  |  | No | 980 | [9 empty] | No | 0
VD-9001-204C-GAD-002 | 0 | GENERAL ARRANGEMENT DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2017-10-25 17:05 |  | No | -12 | 2017-11-12 15:38 | [7 empty] | 2017-11-12 19:59 | Yes | 0
VD-9001-204C-DWG-003 | 0 | MATERIAL LIST AND GENERAL NOTES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:39 |  | No | 58 | 2018-02-03 15:23 | [7 empty] | 2018-02-03 20:00 | Yes | 0
VD-9001-204C-DWG-004 | 0 | DETAILS DWG. With Nozzle Details | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:40 |  | No | 58 | 2018-02-17 14:39 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-204C-DWG-005 | 0 | FIREPROOFING DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-03-26 16:46 | 2018-03-26 16:46 | Yes | 126 |  |  |  | 2018-04-16 14:14 |  |  |  |  | 2018-04-16 20:00 | Yes | 7
VD-9001-204C-DWG-006 | 0 | EXTERNAL SUPPORTS DWG FOR FIREPROOFING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 |  |  | No | 942 | [9 empty] | No | 0
VD-9001-204C-DWG-008 | 0 | DEMISTER & SUPPORT DRAWING with Internals & Internal attachments | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:41 | 2018-01-17 18:42 | Yes | 58 |  | 2018-01-30 14:59 | [6 empty] | 2018-01-30 20:00 | Yes | -1 | 1204-Owner-v | 2018-05-19 07:19
VD-9001-204C-DWG-009 | 0 | NAME PLATE DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-03-26 16:45 | 2018-03-26 16:45 | Yes | 126 |  |  |  | 2018-04-15 17:31 |  |  |  |  | 2018-04-15 20:01 | Yes | 6
VD-9001-204C-DWG-010 | 0 | SHIPPING DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-03-26 16:53 | 2018-03-26 16:53 | Yes | 126 |  |  | 2018-05-09 16:21 | [5 empty] | 2018-05-09 19:59 | Yes | 30 | 1204-Owner-v | 2018-05-19 07:52
VD-9001-204C-DWG-011 | 0 | SHIPPING MARK | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 |  |  | No | 942 | [9 empty] | No | 0
VD-9001-204C-CAL-012 | 0 | MECHANICAL CODE CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2017-11-06 15:31 |  | No | 0 | 2017-11-12 15:39 | [7 empty] | 2017-11-12 19:59 | Yes | 0
VD-9001-204C-CAL-013 | 0 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2017-10-25 17:04 |  | No | -12 | 2017-11-01 15:51 | [7 empty] | 2017-11-01 20:00 | Yes | 0
VD-9001-204C-CAL-014 | 0 | NOZZLE LOAD CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2017-11-06 16:32 |  | No | 0 | 2017-11-12 15:41 | [7 empty] | 2017-11-12 19:59 | Yes | 0
VD-9001-204C-CAL-015 | 0 | LIFTING CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2017-11-06 16:36 |  | No | 0 | 2017-11-13 16:32 | [7 empty] | 2017-11-13 19:59 | Yes | 0
VD-9001-204C-CAL-016 | 0 | FEA ANALYSIS | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-06 | 2018-05-04 18:12 | 2018-05-04 18:13 | Yes | 179 |  |  |  | 2018-05-19 15:23 |  |  |  |  | 2018-05-19 19:59 | Yes | 1
VD-9001-204C-PCJ-017 | 0 | PAINTING SPECIFICATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:41 |  | No | 58 | 2018-02-04 11:03 | [7 empty] | 2018-02-04 19:59 | Yes | 0
VD-9001-204C-PCJ-018 | 0 | HYDROTEST PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:43 |  | No | 58 | 2018-01-28 10:43 | [7 empty] | 2018-01-28 20:00 | Yes | 0
VD-9001-204C-PCJ-019 | 0 | BOLT TIGHTENING PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-17 18:44 | 2018-01-17 18:45 | Yes | 58 |  | 2018-01-28 10:29 | [6 empty] | 2018-01-28 20:00 | Yes | -3 | 1204-Owner-v | 2018-12-16 21:55
VD-9001-204C-MAL-020 | 0 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-22 13:29 |  | No | 63 | 2018-02-19 17:34 | [7 empty] | 2018-02-19 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-04 15:01
VD-9001-204C-MAL-021 | 0 | SPARE PARTS LIST FOR TWO YEARS OPERATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-01-22 14:18 |  | No | 63 | 2018-02-19 17:16 | [7 empty] | 2018-02-19 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-04 15:02
VD-9001-204C-MAL-022 | 0 | SPARE PARTS LIST (SPIR FORM) | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 |  |  | No | 942 | [9 empty] | No | 0
VD-9001-204C-MNL-023 | 0 | ERECTION, OPERATION AND MAINTENANCE MANUAL | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-06-07 18:41 | 2018-06-07 18:42 | Yes | 199 |  |  | 2018-07-04 11:04 | [5 empty] | 2018-07-04 20:00 | Yes | 13 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-204C-ITP-024 | 0 | INSPECTION & TESTING PLAN | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-02-23 18:53 |  | No | 81 |  |  |  | 2018-03-07 15:15 |  |  |  |  | 2018-03-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-05-12 16:38
VD-9001-204C-PCJ-025 | 0 | N.D.E. PROCEDURES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-04-16 12:54 | 2018-04-16 13:07 | Yes | 133 |  |  | 2018-04-22 11:32 | [5 empty] | 2018-04-22 20:00 | Yes | -8
VD-9001-204C-PCJ-026 | 0 | P.M.I. PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-03-12 12:05 | 2018-03-12 12:13 | Yes | 98 |  |  |  | 2018-04-11 16:38 |  |  |  |  | 2018-04-11 20:00 | Yes | 16
VD-9001-204C-PCJ-027 | 0 | HARDNESS TEST PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-03-14 18:11 | 2018-03-14 18:19 | Yes | 100 |  |  | 2018-04-11 17:34 | [5 empty] | 2018-04-11 20:00 | Yes | 14
VD-9001-204C-PCJ-028 | 0 | FERRITE CHECK PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-03-16 13:14 | 2018-03-16 13:18 | Yes | 102 |  |  |  | 2018-04-11 17:32 |  |  |  |  | 2018-04-11 20:00 | Yes | 12
VD-9001-204C-WBK-029 | 0 | WELDING BOOK | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-04-19 14:00 | 2018-04-19 14:01 | Yes | 136 |  |  |  | 2018-04-25 16:42 |  |  |  |  | 2018-04-25 20:00 | Yes | -8
VD-9001-204C-PCJ-030 | 0 | PWHT PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-04 | 2018-04-19 13:52 | 2018-04-19 13:53 | Yes | 136 |  |  |  | 2018-04-23 10:53 |  |  |  |  | 2018-04-23 20:00 | Yes | -10
VD-9001-204C-INR-031 | 0 | CERTIFICATION DOSSIER INDEX | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-06-14 12:52 | 2018-06-14 12:53 | Yes | 174 |  |  |  | 2018-06-26 16:13 |  |  |  |  | 2018-06-26 20:01 | Yes | -2
VD-9001-204C-INR-032 | 0 | CERTIFICATION DOSSIER | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-12-22 |  |  | No | 910 | [9 empty] | No | 0
VD-9001-204C-CAL-033 | 0 | SHIPPING CALCULATION SHEETS | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-03-26 17:05 | 2018-03-26 17:06 | Yes | 126 |  |  | 2018-05-09 16:22 | [5 empty] | 2018-05-09 19:59 | Yes | 30 | 1204-Owner-v | 2018-05-19 07:49
VD-9001-204C-DWG-034 | 0 | GAGE PLATE DETAILS DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 |  |  | No | 942 | [9 empty] | No | 0
VD-9001-204C-DWG-035 | 0 | LADDER & PLATFORM S DWGS. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-20 | 2018-02-06 20:30 |  | No | 78 |  |  |  | 2018-03-14 18:36 |  |  |  |  | 2018-03-14 20:00 | Yes | 0
VD-9001-104-REQ-013 | 1 | PU-6101_HP COLUMN T-6101, LP COLUMN T-6102 LOWER PART, HP AL SEPARATOR DRUM D-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-08 19:59 | 2017-11-09 17:03 |  | No | 1 | 2017-11-15 17:16 | [7 empty] | 2017-11-15 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:24
VD-9001-104-REQ-015 | 1 | TK-6150_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-08 20:00 | 2018-03-14 16:45 | 2018-03-14 17:25 | Yes | 126 |  |  |  | 2018-05-01 14:26 |  |  |  |  | 2018-05-01 20:00 | Yes | 34
VD-9001-104-DSH-004 | 1 | EQUIPMENT DATA SHEET FOR DISTILLATION COLUMN: HP COLUMN T-6101, LP COLUMN T-6102 | PR-104 | AIR LIQUIDE | 2017-11-08 20:00 | 2017-12-05 14:14 |  | No | 27 | 2017-12-26 10:39 | [7 empty] | 2017-12-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:06
VD-9001-104-DSH-005 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-11-08 20:00 | 2018-01-03 17:09 | 2018-01-03 17:10 | Yes | 56 |  | 2018-01-16 15:34 | [6 empty] | 2018-01-16 19:59 | Yes | -1 | 1204-Owner-v | 2018-05-15 16:52
VD-9001-254-DWG-472 | 2 | FAB. DWG FOR WATER DRUM | HM-254 | AZAR AB | 2017-11-11 19:59 | 2017-10-30 14:14 | 2017-10-30 14:15 | Yes | -12 |  | 2017-11-15 10:46 | [6 empty] | 2017-11-15 19:59 | Yes | 2
VD-9001-204C-CAL-013 | 1 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-01 | 2018-01-17 18:47 |  | No | 77 | 2018-02-06 11:34 | [7 empty] | 2018-02-07 20:00 | Yes | 0
VD-9001-254-ITP-327 | 3 | CONTROL SYSTEM AND BMS FACTORY ACCEPTANCE TEST (FAT) PROCEDURE | HM-254 | AZAR AB | 2017-11-15 19:59 | 2017-12-03 14:42 | 2017-12-03 14:43 | Yes | 18 |  | 2017-12-24 10:31 | [6 empty] | 2017-12-24 19:59 | Yes | 7 | 1204-Owner-v | 2019-11-05 14:25
VD-9001-254-ITP-326 | 3 | CONTROL SYSTEM AND BMS SITE ACCEPTANCE TEST (SAT) PROCEDURE | HM-254 | AZAR AB | 2017-11-15 20:00 | 2017-12-03 14:41 | 2017-12-03 14:42 | Yes | 18 |  | 2017-12-24 10:16 | [6 empty] | 2017-12-24 19:59 | Yes | 7 | 1204-Owner-v | 2020-01-01 10:28
VD-9001-201-CAL-002 | 4 | FOUNDATION LOADS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2017-11-04 | 2017-11-07 20:35 | 2017-11-07 20:36 | Yes | 3 |  | 2017-11-08 10:25 | [6 empty] | 2017-11-08 19:59 | Yes | -13 | 1204-Owner-v | 2018-04-23 16:24
VD-9001-201-DWG-005 | 3 | SUPPORT SKIRT EXTERNAL DETAILS TAILING LUG | PV-201 | ATB RIVA CALZONI SpA | 2017-11-04 17:38 | 2017-11-07 20:35 | 2017-11-07 20:36 | Yes | 3 |  | 2017-11-08 10:23 | [6 empty] | 2017-11-08 19:59 | Yes | -13 | 1204-Owner-v | 2018-08-04 11:45
VD-9001-201-DWG-001 | 4 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2017-11-04 | 2018-01-12 19:47 | 2018-01-12 19:48 | Yes | 69 |  | 2018-02-19 15:33 | [6 empty] | 2018-02-19 20:00 | Yes | 24
VD-9001-254-LST-301 | 4 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-11-18 19:59 | 2017-12-03 14:54 |  | No | 15 | 2017-12-24 10:14 | [7 empty] | 2017-12-24 19:59 | Yes | 0
VD-9001-254-LST-302 | 4 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2017-11-18 19:59 | 2017-12-03 14:56 |  | No | 15 | 2017-12-24 10:10 | [7 empty] | 2017-12-24 19:59 | Yes | 0
VD-9001-254-LST-329 | 2 | BMS PROGRAM LIST | HM-254 | AZAR AB | 2017-11-18 19:59 | 2020-03-10 07:57 | 2020-03-10 07:58 | Yes | 843 |  |  | 2020-04-15 11:19 | [5 empty] | 2020-04-15 11:19 | Yes | 22
VD-9001-254-LST-334 | 3 | SPARE PART LIST FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2017-11-18 19:59 | 2017-12-03 15:02 |  | No | 15 | 2017-12-24 10:07 | [7 empty] | 2017-12-24 19:59 | Yes | 0
VD-9001-254-LST-362 | 4 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2017-11-18 19:59 | 2017-12-03 15:07 |  | No | 15 | 2017-12-24 10:05 | [7 empty] | 2017-12-24 19:59 | Yes | 0
VD-9001-108-MNL-057 | 4 | ISTALLATION MANUAL | PR-108 | Farabard | 2017-11-05 09:49 | 2017-11-06 11:29 | 2017-11-06 11:30 | Yes | 1 |  | 2017-11-11 14:42 | [6 empty] | 2017-11-11 19:59 | Yes | -9
VD-9001-105-DWG-302 | 1 | Steel structure drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:10 | 2017-11-07 09:47 | 2017-11-07 09:48 | Yes | 0 |  | 2017-12-20 08:52 | [6 empty] | 2017-12-20 19:59 | Yes | 29 | 1204-Owner-v | 2018-06-23 15:00
VD-9001-105-ITP-701 | 3 | Inspection and test plan for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 10:00 | 2017-11-07 10:01 | Yes | 0 |  | 2017-11-12 08:18 | [6 empty] | 2017-11-12 19:59 | Yes | -9 | 1204-Owner-v | 2020-01-01 11:04
VD-9001-105-ITP-702 | 3 | Inspection and test plan for Heater | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 11:32 | 2017-11-07 11:33 | Yes | 0 |  | 2017-11-09 10:25 | [6 empty] | 2017-11-09 19:59 | Yes | -12 | 1204-Owner-v | 2020-01-01 11:05
VD-9001-105-ITP-703 | 4 | Inspection and test plan for CMR Membrane separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 11:35 | 2017-11-07 11:36 | Yes | 0 |  | 2017-11-09 10:23 | [6 empty] | 2017-11-09 19:59 | Yes | -12 | 1204-Owner-v | 2020-01-01 11:11
VD-9001-105-ITP-705 | 3 | Inspection and test plan of piping and skid-structure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 11:43 | 2017-11-07 11:44 | Yes | 0 |  | 2017-11-09 10:21 | [6 empty] | 2017-11-09 19:59 | Yes | -12 | 1204-Owner-v | 2018-06-24 09:33
VD-9001-105-ITP-706 | 3 | Inspection and test plan of membrane modules | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 11:59 | 2017-11-07 12:00 | Yes | 0 |  | 2017-11-09 10:19 | [6 empty] | 2017-11-09 19:59 | Yes | -12 | 1204-Owner-v | 2020-01-01 11:14
VD-9001-105-ITP-707 | 3 | Inspection and test plan of instruments | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 09:13 | 2017-11-07 12:01 | 2017-11-07 12:02 | Yes | 0 |  | 2017-11-09 10:16 | [6 empty] | 2017-11-09 19:59 | Yes | -12 | 1204-Owner-v | 2020-01-01 11:18
VD-9001-105-PCJ-512 | 0 | Packing and marking procedure | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-07 | 2018-05-16 09:36 | 2018-05-16 09:36 | Yes | 190 |  |  | 2018-05-28 16:12 | [5 empty] | 2018-05-28 16:12 | Yes | -2 | 1204-Owner-v | 2018-06-24 09:36
VD-9001-108-CAL-001 | 3 | STRUCTURE CALCULATION SHEET | PR-108 | Farabard | 2017-11-21 19:59 | 2017-11-18 11:03 | 2017-11-18 11:04 | Yes | -3 |  | 2017-11-18 16:18 | [6 empty] | 2017-11-18 19:59 | Yes | -14
VD-9001-108-DWG-035 | 5 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2017-11-22 19:59 | 2017-11-16 09:15 | 2017-11-16 09:16 | Yes | -6 |  | 2017-11-18 09:46 | [6 empty] | 2017-11-18 19:59 | Yes | -12
VD-9001-108-MNL-056 | 4 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2017-11-22 19:59 | 2017-11-18 13:42 |  | No | -4 | 2017-11-18 17:06 | [7 empty] | 2017-11-18 19:59 | Yes | 0
VD-9001-740A-GAD-00085 | 1 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-11-11 14:06 | 2017-11-12 13:36 |  | No | 1 | 2017-11-14 15:39 | 2017-12-04 10:24 | [6 empty] | 2017-12-04 20:00 | Yes | 0
VD-9001-740A-GAD-00086 | 2 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-11-11 14:06 | 2017-11-12 13:38 |  | No | 1 | 2017-11-14 15:41 | 2017-12-04 10:31 | [6 empty] | 2017-12-04 20:00 | Yes | 0
VD-9001-740A-GAD-00088 | 2 | General Arrangement Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-11-11 14:06 | 2017-11-12 14:30 |  | No | 1 |  | 2017-12-04 10:29 | [6 empty] | 2017-12-04 20:00 | Yes | 0
VD-9001-740A-GAD-00353 | 2 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-11-11 14:06 | 2017-11-12 14:39 |  | No | 1 | 2017-11-14 15:36 | [7 empty] | 2017-11-14 19:59 | Yes | 0
VD-9001-104-PLC-001 | 1 | Air Liquide HSE plans | PR-104 | AIR LIQUIDE | 2017-11-25 19:59 |  |  | No | 937 | [9 empty] | No | 0
VD-9001-104-MNL-004 | 1 | Health Safety and Environment Plan for erection | PR-104 | AIR LIQUIDE | 2017-11-25 19:59 |  |  | No | 937 | [9 empty] | No | 0
VD-9001-108-DWG-029 | 6 | COOLING TOWER LAYOUT | PR-108 | Farabard | 2017-11-25 19:59 | 2017-11-11 20:24 | 2017-11-11 20:25 | Yes | -14 |  | 2017-11-12 10:19 | [6 empty] | 2017-11-12 19:59 | Yes | -13
VD-9001-104-MNL-005 | 1 | Health Safety and Environment Plan for commissioning | PR-104 | AIR LIQUIDE | 2017-11-25 19:59 |  |  | No | 937 | [9 empty] | No | 0
VD-9001-104-DSH-008 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-11-25 20:00 | 2018-02-12 12:44 |  | No | 79 | 2018-02-20 14:51 | [7 empty] | 2018-02-20 19:59 | Yes | 0
VD-9001-104-DSH-007 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-11-25 20:00 | 2018-01-03 17:42 |  | No | 39 | 2018-01-20 14:47 | [7 empty] | 2018-01-20 19:59 | Yes | 0
VD-9001-104-DPH-002 | 0 | ELECTRICAL DESIGN PHILOSOPHY | PR-104 | AIR LIQUIDE | 2017-12-01 | 2017-11-14 12:40 |  | No | -17 | 2017-11-21 17:06 | [7 empty] | 2017-11-21 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:05
VD-9001-204C-GAD-002 | 1 | GENERAL ARRANGEMENT DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-12 | 2018-01-17 18:39 |  | No | 66 | 2018-02-06 17:00 | [7 empty] | 2018-02-07 20:00 | Yes | 0
VD-9001-204C-CAL-012 | 1 | MECHANICAL CODE CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-12 | 2018-01-17 18:44 |  | No | 66 | 2018-02-04 15:06 | [7 empty] | 2018-02-04 20:00 | Yes | 0
VD-9001-204C-CAL-014 | 1 | NOZZLE LOAD CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-12 | 2018-01-17 18:45 |  | No | 66 | 2018-02-04 15:22 | [7 empty] | 2018-02-04 20:00 | Yes | 0
VD-9001-104-QCP-001 | 2 | Quality Control Plan | PR-104 | AIR LIQUIDE | 2017-11-26 19:59 | 2018-01-15 17:24 |  | No | 50 | 2018-01-22 11:12 | [7 empty] | 2018-01-22 19:59 | Yes | 0
VD-9001-253(A)-DSH-013 | 2 | PULLEY DATA SHEET for 2001 | HM-253A | FATEH SANAT KIMIA | 2017-11-13 12:26 | 2017-11-13 14:32 | 2017-11-13 14:33 | Yes | 0 |  | 2017-11-21 16:42 | [6 empty] | 2017-11-21 19:59 | Yes | -6 | 1204-Owner-v | 2018-02-03 12:40
VD-9001-253(A)-DSH-043 | 2 | PULLEY DATA SHEET for 3001 | HM-253A | FATEH SANAT KIMIA | 2017-11-13 12:26 | 2017-11-13 14:34 | 2017-11-13 14:35 | Yes | 0 |  | 2017-11-21 15:59 | [6 empty] | 2017-11-21 19:59 | Yes | -6 | 1204-Owner-v | 2018-03-12 11:19
VD-9001-253(A)-DSH-073 | 2 | PULLEY DATA SHEET for 3002 | HM-253A | FATEH SANAT KIMIA | 2017-11-13 12:27 | 2017-11-13 14:31 | 2017-11-13 14:32 | Yes | 0 |  | 2017-11-21 17:06 | [6 empty] | 2017-11-21 19:59 | Yes | -6 | 1204-Owner-v | 2018-03-12 11:20
VD-9001-204C-CAL-015 | 1 | LIFTING CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2017-11-13 | 2018-01-17 18:45 | 2018-01-17 18:46 | Yes | 65 |  | 2018-02-15 14:03 | [6 empty] | 2018-02-15 20:00 | Yes | 15 | 1204-Owner-v | 2018-12-16 21:53
VD-9001-108-DWG-016 | 8 | PIPING AND INSTRUMENT DIAGRAM | PR-108 | Farabard | 2017-11-27 19:59 | 2017-11-22 14:25 | 2017-11-22 14:26 | Yes | -5 |  | 2017-11-25 15:53 | [6 empty] | 2017-11-25 19:59 | Yes | -11
VD-9001-201-WBK-003 | 0 | WELDING DATA BOOK FOR SKIRT AND EXTERNAL ATTACHMENT | PV-201 | ATB RIVA CALZONI SpA | 2017-11-14 | 2017-11-14 14:23 |  | No | 0 |  | 2017-11-26 17:46 | [6 empty] | 2017-11-26 19:59 | Yes | 0
VD-9001-740A-GAD-00353 | 3 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-11-14 | 2017-11-25 10:59 |  | No | 11 | 2017-12-03 11:20 | [7 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-740A-GAD-00085 | 2 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-11-14 | 2017-11-25 11:04 |  | No | 11 |  | 2017-12-03 11:31 | [6 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-740A-GAD-00086 | 3 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-11-14 | 2017-12-02 13:58 |  | No | 18 |  | 2017-12-03 11:26 | [6 empty] | 2017-12-03 20:00 | Yes | 0
VD-9001-253(A)-MDB-115 | 2 | FINAL DATA BOOK INDEX | HM-253A | FATEH SANAT KIMIA | 2017-11-14 | 2017-11-25 10:40 |  | No | 11 | 2017-12-05 15:59 | [7 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-254-PCJ-465 | 2 | LEAK TEST PROCEDURE | HM-254 | AZAR AB | 2017-11-29 19:59 | 2017-12-03 13:29 |  | No | 4 | 2017-12-11 15:13 | [7 empty] | 2017-12-11 20:00 | Yes | 0
VD-9001-104-SPE-006 | 1 | Piping specifications | PR-104 | AIR LIQUIDE | 2017-11-29 19:59 | 2017-12-20 17:50 | 2017-12-20 17:51 | Yes | 21 |  | 2017-12-24 10:40 | [6 empty] | 2017-12-24 19:59 | Yes | -10 | 1204-Owner-v | 2017-12-31 12:45
VD-9001-104-REQ-013 | 2 | PU-6101_HP COLUMN T-6101, LP COLUMN T-6102 LOWER PART, HP AL SEPARATOR DRUM D-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-29 19:59 | 2017-12-04 16:58 | 2017-12-04 16:59 | Yes | 5 |  | 2017-12-18 15:14 | [6 empty] | 2017-12-18 20:00 | Yes | 0 | 1204-Owner-v | 2017-12-31 12:46
VD-9001-104-REQ-014 | 1 | LP COLUMN T-6102 UPPER PART_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-11-29 19:59 | 2017-12-06 16:31 | 2017-12-06 16:32 | Yes | 7 |  | 2017-12-18 15:27 | [6 empty] | 2017-12-18 20:00 | Yes | -2 | 1204-Owner-v | 2017-12-31 12:46
VD-9001-105-SPE-501 | 3 | Painting specification | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-11-18 | 2018-01-02 15:57 | 2018-01-02 15:58 | Yes | 45 |  | 2018-01-09 08:29 | [6 empty] | 2018-01-09 19:59 | Yes | -7
VD-9001-104-LST-001 | 1 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2017-12-02 19:59 | 2017-12-06 12:20 |  | No | 4 | 2017-12-10 17:24 | [7 empty] | 2017-12-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:15
VD-9001-108-DWG-073 | 1 | Gate Detail | PR-108 | Farabard | 2017-12-02 19:59 | 2017-11-28 10:03 | 2017-11-28 10:04 | Yes | -4 |  | 2017-11-29 09:30 | [6 empty] | 2017-11-29 20:00 | Yes | -13
VD-9001-108-MNL-056 | 5 | COOLING TOWER OPERATING&MAINTENANCE MANUAL | PR-108 | Farabard | 2017-12-02 19:59 | 2017-11-28 10:39 | 2017-11-28 10:40 | Yes | -4 |  | 2017-11-29 15:07 | [6 empty] | 2017-11-29 20:00 | Yes | -13
VD-9001-108-MNL-058 | 5 | COMMISSIONING PROCEDURE & START-UP MANUAL | PR-108 | Farabard | 2017-12-04 19:59 | 2017-11-29 11:16 | 2017-11-29 11:17 | Yes | -5 |  | 2017-11-29 15:23 | [6 empty] | 2017-11-29 20:00 | Yes | -14
VD-9001-104-REQ-008 | 1 | E-6101/E-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-04 19:59 | 2018-01-03 17:35 |  | No | 30 |  | 2018-01-17 09:37 | [6 empty] | 2018-01-17 19:59 | Yes | 0
VD-9001-204D-DIS-001 | 0 | VENDOR DOCUMENT INDEX AND SCHEDULE (VDIS) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:57 | 2017-11-22 12:57 | Yes | 27 |  | 2017-11-22 15:33 | [6 empty] | 2017-11-22 19:59 | Yes | -14 | 1204-Owner-v | 2018-04-18 15:21
VD-9001-204D-GAD-002 | 0 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:53 |  | No | 27 | 2017-12-09 17:17 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-DWG-003 | 0 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:53 |  | No | 27 | 2017-12-09 17:30 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-DWG-004 | 0 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:55 |  | No | 27 | 2017-12-09 17:22 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-DWG-005 | 0 | INTERNAL PARTS DETAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:55 |  | No | 27 |  | 2017-12-05 17:27 | [6 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-204D-DWG-006 | 0 | EXTERNAL SUPPORTS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-12-03 18:17 | 2018-12-03 18:17 | Yes | 369 |  |  |  | 2018-12-16 09:43 |  |  |  |  | 2018-12-16 09:43 | Yes | -1 | 1204-Owner-v | 2018-12-11 14:00
VD-9001-204D-DWG-007 | 0 | DRYERS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-22 12:56 |  | No | 27 | 2017-12-05 17:11 | [7 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-204D-DWG-008 | 0 | DEMISTER DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-10-09 13:15 | 2018-10-09 13:16 | Yes | 314 |  |  | 2018-10-29 08:43 | [5 empty] | 2018-10-29 08:43 | Yes | 6
VD-9001-204D-DWG-009 | 0 | NAME PLATE DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-14 10:55 | 2018-03-14 10:55 | Yes | 105 |  |  |  |  | 2018-04-18 17:59 |  |  |  | 2018-04-18 20:00 | Yes | 21
VD-9001-204D-WMP-010 | 0 | WELDING DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-13 19:22 | 2018-03-13 19:22 | Yes | 104 |  |  | 2018-04-15 17:37 | [5 empty] | 2018-04-15 20:01 | Yes | 19
VD-9001-204D-DWG-011 | 0 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-13 19:23 | 2018-03-14 10:57 | Yes | 104 |  |  |  |  | 2018-04-21 10:17 |  |  |  | 2018-04-21 20:00 | Yes | 25
VD-9001-204D-MSS-012 | 0 | MATERIAL SPECIFICATIONS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-21 14:26 |  | No | 26 | 2017-12-05 14:41 | [7 empty] | 2017-12-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-04 15:04
VD-9001-204D-CAL-013 | 0 | MECHANICAL CODE CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-21 13:28 |  | No | 26 | 2017-12-09 17:24 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-CAL-014 | 0 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-21 13:42 |  | No | 26 | 2017-12-09 17:27 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-CAL-015 | 0 | NOZZLE LOAD CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-10-26 | 2017-11-21 14:15 |  | No | 26 | 2017-12-09 17:29 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-204D-CAL-016 | 0 | LIFTING CALCULATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-13 19:26 | 2018-08-07 09:12 | Yes | 104 |  |  |  | 2018-08-08 08:28 |  |  |  |  | 2018-08-08 08:28 | Yes | 134 | 1204-Owner-v | 2018-04-24 17:01
VD-9001-204D-PCJ-017 | 0 | PAINTING SPECIFICATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-13 19:24 | 2018-06-29 18:54 | Yes | 104 |  |  |  | 2018-06-30 11:05 |  |  |  |  | 2018-06-30 20:00 | Yes | 95
VD-9001-204D-PCJ-018 | 0 | HYDROTEST PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-03-13 19:25 | 2018-03-14 10:57 | Yes | 104 |  |  |  | 2018-04-23 09:30 |  |  |  |  | 2018-04-23 20:00 | Yes | 27
VD-9001-204D-PCJ-019 | 0 | BOLT TIGHTENING PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 |  |  | No | 933 | [9 empty] | No | 0
VD-9001-204D-MAL-020 | 0 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-06 | 2017-11-27 14:40 |  | No | -9 | 2017-12-05 15:30 | [7 empty] | 2017-12-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-04 15:03
VD-9001-204D-MAL-021 | 0 | SPARE PARTS LIST FOR TWO YEARS OPERATION (SPIR FORM) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-06 | 2018-04-10 16:53 | 2018-04-10 16:53 | Yes | 125 |  |  |  | 2018-04-25 14:29 |  |  |  |  | 2018-04-25 20:00 | Yes | 1
VD-9001-204D-ITP-022 | 0 | INSPECTION & TESTING PLAN | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-17 | 2017-11-21 17:30 |  | No | 4 | 2017-11-28 09:30 | [7 empty] | 2017-11-28 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:52
VD-9001-204D-PCJ-023 | 0 | N.D.E. PROCEDURES (NDT MAP INCLUDED) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-06-22 19:08 | 2018-06-22 19:09 | Yes | 205 |  |  |  | 2018-06-30 10:30 |  |  |  |  | 2018-06-30 20:00 | Yes | -6
VD-9001-204D-PCJ-024 | 0 | HARDNESS TEST PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-04-10 12:18 | 2018-04-10 12:19 | Yes | 132 |  |  | 2018-04-18 17:14 | [5 empty] | 2018-04-18 20:00 | Yes | -6
VD-9001-204D-WBK-025 | 0 | WELDING BOOK | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-04-10 19:38 | 2018-04-10 19:38 | Yes | 132 |  |  | 2018-05-05 10:14 | [5 empty] | 2018-05-05 19:59 | Yes | 11
VD-9001-204D-PCJ-026 | 0 | PWHT PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-04-10 19:23 | 2018-04-10 19:24 | Yes | 132 |  |  |  | 2018-04-18 17:16 |  |  |  |  | 2018-04-18 20:00 | Yes | -6
VD-9001-204D-MNL-027 | 0 | INSTALLATION AND MAINTENANCE MANUAL | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-06 | 2018-03-13 19:24 | 2018-08-07 09:12 | Yes | 97 |  |  | 2018-09-03 09:49 | [5 empty] | 2018-09-03 09:49 | Yes | 160
VD-9001-204D-INR-028 | 0 | CERTIFICATION DOSSIER INDEX | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-17 | 2017-11-21 17:29 |  | No | 4 | 2017-12-05 14:10 | [7 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-204D-INR-029 | 0 | CERTIFICATION DOSSIER | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-17 |  |  | No | 945 | [9 empty] | No | 0
VD-9001-204D-DSH-030 | 0 | PROCESS/MECHANICAL DATA SHEET | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-04-06 15:07 | 2018-04-06 15:09 | Yes | 105 |  |  |  |  | 2018-04-18 17:17 |  |  |  | 2018-04-18 20:00 | Yes | -2 | 1204-Owner-v | 2018-04-17 11:29
VD-9001-204D-CAL-031 | 0 | SHIPPING SUPPORT CALCULATIONS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-11-29 | 2018-04-13 12:19 | 2018-04-13 12:22 | Yes | 135 |  |  |  |  | 2018-05-12 13:19 |  |  |  | 2018-05-12 19:59 | Yes | 15
VD-9001-204D-DWG-032 | 0 | LADDER & PLATFORM LAYOUT DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-06-28 18:36 | 2018-06-28 18:36 | Yes | 188 |  |  |  | 2018-07-18 17:50 |  |  |  |  | 2018-07-18 17:50 | Yes | 6
VD-9001-204D-DWG-033 | 0 | LADDER & PLATFORM DETAILS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-12-03 18:20 | 2018-12-03 18:20 | Yes | 346 |  |  |  | 2018-12-30 15:11 |  |  |  |  | 2018-12-30 15:11 | Yes | 13
VD-9001-204D-PCJ-034 | 0 | REPAIR PROCEDURE (IF APPLICABLE) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 |  |  | No | 910 | [9 empty] | No | 0
VD-9001-204D-PCJ-035 | 0 | PRESERVATION PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-03-13 19:25 | 2018-03-13 19:25 | Yes | 81 |  |  |  |  | 2018-04-21 09:49 |  |  |  | 2018-04-21 20:00 | Yes | 25 | 1204-Owner-v | 2018-04-18 15:39
VD-9001-204D-CAL-036 | 0 | CALCULATION FOR EXTERNAL ATTACHMENT AND CLIPS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-22 | 2018-12-21 17:02 | 2018-12-21 17:03 | Yes | 364 |  |  |  | 2018-12-29 16:12 |  |  |  |  | 2018-12-29 16:12 | Yes | -6
VD-9001-254-LST-961 | 0 | CONTROL SYSTEM POWER CONSUMPTION AND HEAT DISSIPATION | HM-254 | AZAR AB | 2017-11-21 | 2018-12-26 14:30 | 2018-12-26 14:30 | Yes | 400 |  |  |  | 2019-02-05 15:18 |  |  |  |  | 2019-02-05 15:18 | Yes | 27
VD-9001-104-DPH-002 | 1 | ELECTRICAL DESIGN PHILOSOPHY | PR-104 | AIR LIQUIDE | 2017-12-05 19:59 |  |  | No | 927 | [9 empty] | No | 0
VD-9001-201-PCJ-005 | 1 | HYDROTEST PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2017-11-25 | 2018-05-25 19:04 | 2018-05-25 19:10 | Yes | 181 |  |  |  | 2018-06-17 11:45 |  |  |  |  | 2018-06-17 11:45 | Yes | 9
VD-9001-201-PCJ-001 | 1 | HOT FORMING OF HEADS | PV-201 | ATB RIVA CALZONI SpA | 2017-11-25 | 2018-05-14 15:03 | 2018-05-14 15:04 | Yes | 170 |  |  | 2018-07-22 10:43 | [5 empty] | 2018-07-22 10:43 | Yes | 55 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-201-PCJ-002 | 1 | PWHT/ISR/DHT PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2017-11-25 | 2018-05-14 15:04 | 2018-05-14 15:09 | Yes | 170 |  |  | 2018-06-10 16:27 | [5 empty] | 2018-06-10 16:27 | Yes | 13 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-108-PFD-065 | 3 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2017-12-09 19:59 | 2017-11-29 10:57 |  | No | -10 | 2017-12-02 10:12 | [7 empty] | 2017-12-02 20:00 | Yes | 0
VD-9001-205A-DWG-032 | 4 | TOWER ATTACHMENT/SUPPORT DRAWING FOR D-2001 | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2017-11-26 15:07 | 2017-11-26 15:39 | 2017-11-26 15:40 | Yes | 0 |  |  | 2018-06-10 10:35 | [5 empty] | 2018-06-10 10:35 | Yes | 182
VD-9001-104-SPE-005 | 2 | Piping General Specification | PR-104 | AIR LIQUIDE | 2017-12-10 19:59 |  |  | No | 922 | [9 empty] | No | 0
VD-9001-204D-ITP-022 | 1 | INSPECTION & TESTING PLAN | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-12 20:00 | 2018-02-13 19:10 |  | No | 63 | 2018-02-26 08:48 | [7 empty] | 2018-02-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-05-12 16:35
VD-9001-104-MDB-001 | 2 | Manufacturing Data Book | PR-104 | AIR LIQUIDE | 2017-12-12 20:00 | 2018-01-15 13:57 | 2018-01-15 13:58 | Yes | 34 |  | 2018-01-28 15:16 | [6 empty] | 2018-01-28 20:00 | Yes | -1 | 1204-Owner-v | 2018-03-07 11:39
VD-9001-108-DWG-036 | 1 | DRIVE SHAFT ASSEMBLY | PR-108 | Farabard | 2017-11-29 12:17 | 2017-11-29 13:33 | 2017-11-29 13:34 | Yes | 0 |  | 2017-12-02 10:30 | [6 empty] | 2017-12-02 20:00 | Yes | -11
VD-9001-108-PFD-065 | 4 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2017-12-16 20:00 | 2017-12-07 08:34 |  | No | -9 | 2017-12-09 10:32 | [7 empty] | 2017-12-09 20:00 | Yes | 0
VD-9001-108-DIS-074 | 1 | VENDOR DOCUMENTS INDEX & SCHEDULE | PR-108 | Farabard | 2017-12-16 20:00 | 2017-12-04 08:59 | 2017-12-04 09:00 | Yes | -12 |  | 2017-12-05 12:09 | [6 empty] | 2017-12-05 20:00 | Yes | -13
VD-9001-201-DWG-006 | 1 | INTERNAL MISCELLANEOUS DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2017-12-03 | 2018-01-25 19:17 |  | No | 53 | 2018-02-18 17:26 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-740A-GAD-00353 | 4 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-12-03 | 2017-12-09 11:53 |  | No | 6 |  | 2017-12-10 11:43 | [6 empty] | 2017-12-10 20:00 | Yes | 0
VD-9001-740A-LST-003 | 1 | Reference/Experience list | ST-740A | Pars Tadbir Gostar | 2017-12-03 | 2017-12-11 09:07 | 2017-12-11 09:08 | Yes | 8 |  | 2018-01-24 09:38 | [6 empty] | 2018-01-24 19:58 | Yes | 28 | 1204-Owner-v | 2019-04-12 13:40
VD-9001-108-LST-051 | 4 | SPARE PARTS LIST FOR 2 YEARS OF OPERATION | PR-108 | Farabard | 2017-12-17 20:00 | 2017-12-05 14:35 | 2017-12-05 14:36 | Yes | -12 |  | 2017-12-05 15:01 | [6 empty] | 2017-12-05 20:00 | Yes | -14
VD-9001-204A-INX-001 | 1 | Fiinal Vendor Data Book Index | PV-204A | Asas Sanat Pars Inc. | 2017-12-04 | 2017-12-09 12:45 |  | No | 5 | 2017-12-11 09:01 | [7 empty] | 2017-12-11 19:59 | Yes | 0
VD-9001-108-DWG-044 | 1 | FABRICATION/ERECTION DRAWING | PR-108 | Farabard | 2017-12-04 12:16 | 2017-12-04 14:12 |  | No | 0 |  | 2017-12-05 16:54 | [6 empty] | 2017-12-05 20:00 | Yes | 0
VD-9001-105-DWG-501 | 5 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-04 14:40 | 2017-12-04 16:50 |  | No | 0 | 2017-12-20 10:36 | [7 empty] | 2017-12-20 19:59 | Yes | 0
VD-9001-105-DWG-502 | 6 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-04 14:40 | 2017-12-04 16:53 |  | No | 0 | 2017-12-20 10:24 | [7 empty] | 2017-12-20 19:59 | Yes | 0
VD-9001-105-DWG-503 | 5 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-04 14:41 | 2017-12-04 17:02 |  | No | 0 | 2017-12-20 10:19 | [7 empty] | 2017-12-20 19:59 | Yes | 0
VD-9001-105-DWG-101 | 2 | Name plate drawings of HRU Package | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-04 14:41 | 2017-12-04 17:06 | 2017-12-04 17:07 | Yes | 0 |  | 2017-12-21 11:33 | [6 empty] | 2017-12-21 19:59 | Yes | 2 | 1204-Owner-v | 2018-08-27 13:26
VD-9001-108-DBS-006 | 6 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2017-12-18 20:00 | 2017-12-11 14:26 |  | No | -7 | 2017-12-13 09:45 | [7 empty] | 2017-12-13 19:59 | Yes | 0
VD-9001-201-DWG-003 | 3 | TOP COVER & MAIN FLANGE | PV-201 | ATB RIVA CALZONI SpA | 2017-12-05 | 2018-01-19 18:41 | 2018-01-19 18:42 | Yes | 45 |  | 2018-02-19 17:11 | [6 empty] | 2018-02-19 20:00 | Yes | 17
VD-9001-253(A)-MDB-115 | 3 | FINAL DATA BOOK INDEX | HM-253A | FATEH SANAT KIMIA | 2017-12-05 | 2018-02-05 16:51 |  | No | 62 | 2018-02-13 10:38 | [7 empty] | 2018-02-13 19:59 | Yes | 0 | 1204-Owner-v | 2019-06-23 15:48
VD-9001-204D-INR-028 | 1 | CERTIFICATION DOSSIER INDEX | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-05 19:42 | 2017-12-05 19:43 |  | No | 0 | 2018-02-26 09:00 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-204D-MSS-012 | 1 | MATERIAL SPECIFICATIONS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-19 20:00 | 2018-04-13 15:22 | 2018-04-13 15:22 | Yes | 115 |  |  | 2018-06-13 13:19 | [5 empty] | 2018-06-13 20:00 | Yes | 47
VD-9001-204D-MAL-020 | 1 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-19 20:00 | 2018-04-10 16:52 | 2018-04-10 16:52 | Yes | 112 |  |  |  | 2018-04-25 14:29 |  |  |  |  | 2018-04-25 20:00 | Yes | 1
VD-9001-204D-DWG-007 | 1 | DRYERS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-19 20:00 | 2018-03-13 19:21 | 2018-03-14 10:56 | Yes | 84 |  |  | 2018-04-08 08:27 | [5 empty] | 2018-04-08 20:00 | Yes | 12
VD-9001-108-PFD-065 | 5 | PROCESS FLOW DIAGRAM | PR-108 | Farabard | 2017-12-23 20:00 | 2017-12-10 11:38 | 2017-12-10 11:39 | Yes | -13 |  | 2017-12-10 14:32 | [6 empty] | 2017-12-10 20:00 | Yes | -14
VD-9001-108-DIG-046 | 2 | CAUSE AND EFFECT DIAGRAM | PR-108 | Farabard | 2017-12-23 20:00 | 2017-12-11 10:26 |  | No | -12 | 2017-12-12 14:38 | [7 empty] | 2017-12-12 20:00 | Yes | 0
VD-9001-204D-GAD-002 | 1 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-03-13 19:10 | 2018-03-13 19:16 | Yes | 80 |  |  |  |  | 2018-04-21 17:31 |  |  |  | 2018-04-21 20:00 | Yes | 25 | 1204-Owner-v | 2018-04-25 10:36
VD-9001-204D-DWG-004 | 1 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-03-13 19:20 | 2018-03-26 15:24 | Yes | 80 |  |  |  |  | 2018-04-22 12:56 |  |  |  | 2018-04-22 20:00 | Yes | 26
VD-9001-204D-CAL-013 | 1 | MECHANICAL CODE CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-03-13 19:28 | 2018-03-14 10:58 | Yes | 80 |  |  |  | 2018-04-21 17:32 |  |  |  |  | 2018-04-21 20:00 | Yes | 25 | 1204-Owner-v | 2018-04-17 11:23
VD-9001-204D-CAL-014 | 1 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-03-13 19:27 | 2018-07-21 12:03 | Yes | 80 |  |  |  | 2018-07-22 17:39 |  |  |  |  | 2018-07-22 17:39 | Yes | 117
VD-9001-204D-CAL-015 | 1 | NOZZLE LOAD CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-08-02 18:55 | 2018-08-02 18:55 | Yes | 222 |  |  | 2018-08-06 11:09 | [5 empty] | 2018-08-06 11:09 | Yes | -10
VD-9001-204D-DWG-003 | 1 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2017-12-23 20:00 | 2018-03-13 19:17 | 2018-03-13 19:17 | Yes | 80 |  |  |  |  | 2018-04-22 14:25 |  |  |  | 2018-04-22 20:00 | Yes | 26
VD-9001-104-PFD-001 | 2 | PFD Compression and purification | PR-104 | AIR LIQUIDE | 2017-12-24 20:00 | 2018-02-09 17:45 |  | No | 47 |  |  |  | 2018-03-10 14:39 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:57
VD-9001-104-LST-001 | 2 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2017-12-24 20:00 | 2018-01-24 14:16 |  | No | 31 | 2018-02-04 10:14 | [7 empty] | 2018-02-04 19:59 | Yes | 0
VD-9001-204A-INX-001 | 2 | Fiinal Vendor Data Book Index | PV-204A | Asas Sanat Pars Inc. | 2017-12-11 | 2017-12-11 15:35 |  | No | 0 | 2017-12-13 09:09 | [7 empty] | 2017-12-13 19:59 | Yes | 0
VD-9001-254-PCJ-465 | 3 | LEAK TEST PROCEDURE | HM-254 | AZAR AB | 2017-12-25 20:00 | 2018-08-08 15:49 | 2018-08-08 15:49 | Yes | 226 |  |  | 2018-09-05 17:03 | [5 empty] | 2018-09-05 17:03 | Yes | 14
VD-9001-104-PFD-002 | 2 | PFD Cold box | PR-104 | AIR LIQUIDE | 2017-12-25 20:00 | 2018-02-09 17:45 |  | No | 46 |  |  |  | 2018-03-10 15:54 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:48
VD-9001-740A-PRC-004 | 1 | Packing and Marking Procedure | ST-740A | Pars Tadbir Gostar | 2017-12-12 09:45 | 2017-12-12 10:09 |  | No | 0 | 2018-01-24 10:00 | [7 empty] | 2018-01-24 19:59 | Yes | 0
VD-9001-740A-LST-007 | 1 | Vendor Data Book Index List | ST-740A | Pars Tadbir Gostar | 2017-12-12 09:53 | 2017-12-12 11:40 |  | No | 920 | 2018-01-23 10:34 | 2018-01-02 15:11 | [6 empty] | 2018-01-23 19:59 | Yes | 0
VD-9001-108-DBS-006 | 7 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2017-12-26 19:59 | 2017-12-13 10:59 |  | No | -13 | 2017-12-13 15:41 | [7 empty] | 2017-12-13 20:00 | Yes | 0
VD-9001-108-DIG-046 | 3 | CAUSE AND EFFECT DIAGRAM | PR-108 | Farabard | 2017-12-26 20:00 | 2017-12-16 12:57 | 2017-12-16 12:58 | Yes | -10 |  | 2017-12-17 09:17 | [6 empty] | 2017-12-17 19:59 | Yes | -13
VD-9001-104-DSH-010 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2017-12-26 20:00 | 2017-12-19 13:24 |  | No | -7 | 2017-12-28 15:05 | [7 empty] | 2017-12-28 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 08:08
VD-9001-104-DPH-001 | 1 | Instrumentation and control general requirement | PR-104 | AIR LIQUIDE | 2017-12-26 20:00 | 2018-01-15 14:16 | 2018-01-15 14:17 | Yes | 20 |  | 2018-01-28 15:05 | [6 empty] | 2018-01-28 20:00 | Yes | -1 | 1204-Owner-v | 2018-01-24 09:09
VD-9001-204A-INX-001 | 3 | Fiinal Vendor Data Book Index | PV-204A | Asas Sanat Pars Inc. | 2017-12-13 | 2017-12-16 07:58 | 2017-12-16 07:58 | Yes | 3 |  | 2017-12-23 10:24 | [6 empty] | 2017-12-23 19:59 | Yes | -7
VD-9001-104-REQ-016 | 1 | DR-6101A&B_TRS Technical Requisition Sheet Adsorber | PR-104 | AIR LIQUIDE | 2017-12-27 20:00 | 2017-12-19 13:24 |  | No | -8 | 2018-01-06 08:53 | [7 empty] | 2018-01-06 19:59 | Yes | 0
VD-9001-108-DBS-006 | 8 | PROCESS & DESIGN DATA | PR-108 | Farabard | 2017-12-27 20:00 | 2017-12-16 12:38 | 2017-12-16 12:39 | Yes | -11 |  | 2017-12-17 09:24 | [6 empty] | 2017-12-17 19:59 | Yes | -13
VD-9001-104-REQ-025 | 1 | STC-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-27 20:00 |  |  | No | 905 | [9 empty] | No | 0
VD-9001-104-REQ-022 | 1 | P-6103A / P-6103B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2017-12-27 20:00 | 2018-02-21 18:40 |  | No | 56 |  |  |  | 2018-03-17 14:37 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-24 12:25
VD-9001-251-CAL-001 | 0 | MECHANICAL CALCULATION CATALYST TUBE | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-12 14:04 |  | No | 0 | 2018-01-16 11:14 | [7 empty] | 2018-01-16 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-15 08:55
VD-9001-251-CAL-002 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 1st CONVECTION SECTION - Lower - HE-1001 | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 | 2018-05-15 14:26 | 2018-05-15 14:28 | Yes | 102 |  |  |  | 2018-05-30 15:46 |  |  |  |  | 2018-05-30 15:46 | Yes | 1
VD-9001-251-CAL-003 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 1st CONVECTION SECTION - Upper - HE1001 | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-004 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 2nd CONVECTION SECTION - HE1002 | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-005 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 3rd CONVECTION SECTION - HE1003 | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-006 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 4th CONVECTION SECTION - Upper - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-007 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 5th CONVECTION SECTION - Intermediate - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-008 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 5th CONVECTION SECTION - Lower - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-009 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 5th CONVECTION SECTION - HE1005 | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-010 | 0 | INTERMEDIATE TUBESHEETS CALCULATION 6th CONVECTION SECTION - HE1004B | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 |  |  | No | 868 | [9 empty] | No | 0
VD-9001-251-CAL-011 | 0 | MECHANICAL CALCULATION - CONVECTION COILS | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-12 14:05 |  | No | 0 | 2018-01-20 10:11 | [7 empty] | 2018-01-20 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-07 10:56
VD-9001-251-CAL-012 | 0 | MECHANICAL CALCULATION INLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-12 14:07 |  | No | 0 | 2018-01-20 11:16 | [7 empty] | 2018-01-20 19:59 | Yes | 0
VD-9001-251-CAL-013 | 0 | MECHANICAL CALCULATION OUTLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-12 14:08 |  | No | 0 | 2018-01-20 14:43 | [7 empty] | 2018-01-20 19:59 | Yes | 0
VD-9001-251-CAL-014 | 0 | MECHANICAL CALCULATION TRANSFER LINE | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 | 2018-01-12 14:08 |  | No | -25 | 2018-01-20 14:56 | [7 empty] | 2018-01-20 19:59 | Yes | 0
VD-9001-251-CAL-015 | 0 | STRUCTURAL STATICAL CALCULATONS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-05 16:53 | 2018-03-05 17:07 | Yes | 10 |  |  |  |  | 2018-03-14 16:36 |  |  |  | 2018-03-14 16:36 | Yes | -5
VD-9001-251-MTO-001 | 0 | STEELWORK MATERIAL TAKE OFF | HM-251 | KT – Kinetics Technology SpA | 2018-04-12 | 2018-06-19 16:48 | 2018-06-19 16:55 | Yes | 68 |  |  |  | 2018-06-23 14:29 |  |  |  |  | 2018-06-23 14:30 | Yes | -10
VD-9001-251-CAL-689 | 0 | LIFTING CALCULATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-251-DWG-001 | 0 | CATALYST TUBE DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-01-24 | 2018-01-19 17:56 |  | No | -5 | 2018-01-27 15:51 | [7 empty] | 2018-01-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:17
VD-9001-251-DWG-002 | 0 | INLET SYSTEM DRAWING - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-22 14:19 |  | No | -4 | 2018-02-05 15:56 | [7 empty] | 2018-02-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:09
VD-9001-251-DWG-003 | 0 | INLET SYSTEM DRAWING - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-22 14:19 |  | No | -4 | 2018-02-05 15:51 | [7 empty] | 2018-02-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:14
VD-9001-251-DWG-004 | 0 | INLET SYSTEM - MAIN HEADER DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-22 17:28 |  | No | -4 | 2018-02-06 09:13 | [7 empty] | 2018-02-06 19:59 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:25
VD-9001-251-DWG-005 | 0 | OUTLET SYSTEM - GENERAL ARRANGEMENT DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:45 |  | No | -1 | 2018-02-05 17:35 | [7 empty] | 2018-02-05 20:00 | Yes | 0
VD-9001-251-DWG-006 | 0 | OUTLET SYSTEM DETAILS DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:47 |  | No | -1 | 2018-02-05 17:34 | [7 empty] | 2018-02-05 20:00 | Yes | 0
VD-9001-251-DWG-007 | 0 | INTERMEDIATE TUBESHEETS DRAWING 1st CONVECTION SECTION - Lower - HE-1001 | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 14:26 | 2018-05-21 14:39 | Yes | 96 |  |  | 2018-05-29 17:20 | [5 empty] | 2018-05-29 17:20 | Yes | -6 | 1204-Owner-v | 2019-03-28 08:38
VD-9001-251-DWG-008 | 0 | INTERMEDIATE TUBESHEETS DRAWING 1st CONVECTION SECTION - Upper - HE1001 | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 14:44 | 2018-05-21 14:59 | Yes | 96 |  |  | 2018-05-29 17:20 | [5 empty] | 2018-05-29 17:20 | Yes | -6 | 1204-Owner-v | 2019-03-28 08:50
VD-9001-251-DWG-009 | 0 | INTERMEDIATE TUBESHEETS DRAWING 2nd CONVECTION SECTION - HE1002 | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 15:11 | 2018-05-21 15:58 | Yes | 96 |  |  | 2018-05-29 17:21 | [5 empty] | 2018-05-29 17:21 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:45
VD-9001-251-DWG-010 | 0 | INTERMEDIATE TUBESHEETS DRAWING 3rd CONVECTION SECTION - HE1003 | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 15:55 | 2018-05-21 15:59 | Yes | 96 |  |  | 2018-05-29 17:22 | [5 empty] | 2018-05-29 17:22 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-011 | 0 | INTERMEDIATE TUBESHEETS DRAWING 4th CONVECTION SECTION - Upper - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 15:59 | 2018-05-21 16:00 | Yes | 96 |  |  | 2018-05-29 17:23 | [5 empty] | 2018-05-29 17:23 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-012 | 0 | INTERMEDIATE TUBESHEETS DRAWING 5th CONVECTION SECTION - Intermediate - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 16:02 | 2018-05-21 16:07 | Yes | 96 |  |  | 2018-05-29 17:24 | [5 empty] | 2018-05-29 17:24 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-013 | 0 | INTERMEDIATE TUBESHEETS DRAWING 5th CONVECTION SECTION - Lower - HE1004A | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 16:07 | 2018-05-21 16:10 | Yes | 96 |  |  | 2018-05-29 17:26 | [5 empty] | 2018-05-29 17:26 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-014 | 0 | INTERMEDIATE TUBESHEETS DRAWING 5th CONVECTION SECTION - HE1005 | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 16:11 | 2018-05-21 16:17 | Yes | 96 |  |  | 2018-05-29 17:26 | [5 empty] | 2018-05-29 17:26 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-015 | 0 | INTERMEDIATE TUBESHEETS DRAWING 6th CONVECTION SECTION - HE1004B | HM-251 | KT – Kinetics Technology SpA | 2018-02-14 | 2018-05-21 16:18 | 2018-05-21 16:28 | Yes | 96 |  |  | 2018-05-29 17:28 | [5 empty] | 2018-05-29 17:28 | Yes | -6 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-016 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:52 |  | No | 0 | 2018-01-28 16:39 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:25
VD-9001-251-DWG-017 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:53 |  | No | 0 | 2018-01-28 17:02 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:25
VD-9001-251-DWG-018 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:54 |  | No | 0 | 2018-01-28 17:55 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:26
VD-9001-251-DWG-019 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:54 |  | No | 0 | 2018-01-28 18:14 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:26
VD-9001-251-DWG-020 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:55 |  | No | 0 | 2018-01-28 18:31 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:26
VD-9001-251-DWG-021 | 0 | CONVECTION COIL DRAWING & MANIFOLD HE-1004B | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-19 17:56 |  | No | 0 | 2018-01-28 18:47 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-04-03 17:26
VD-9001-251-DWG-022 | 0 | MAIN HEADER (TRANSFERLINE) DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-30 12:18 | 2018-03-30 12:21 | Yes | 35 |  |  |  | 2018-04-17 16:17 |  |  |  |  | 2018-04-17 16:17 | Yes | 4 | 1204-Owner-v | 2018-04-03 17:34
VD-9001-251-DWG-023 | 0 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-30 12:21 | 2018-03-30 12:24 | Yes | 35 |  |  |  | 2018-04-17 16:27 |  |  |  |  | 2018-04-17 16:27 | Yes | 4 | 1204-Owner-v | 2018-04-03 17:35
VD-9001-251-DWG-024 | 0 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-30 12:22 | 2018-03-30 12:24 | Yes | 35 |  |  |  | 2018-04-17 17:00 |  |  |  |  | 2018-04-17 17:00 | Yes | 4 | 1204-Owner-v | 2018-04-03 17:35
VD-9001-251-DWG-025 | 0 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-30 12:33 | 2018-03-30 12:33 | Yes | 35 |  |  |  | 2018-04-17 17:03 |  |  |  |  | 2018-04-17 17:03 | Yes | 4 | 1204-Owner-v | 2018-04-03 17:35
VD-9001-251-DWG-026 | 0 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-08-31 13:48 | 2018-08-31 13:53 | Yes | 189 |  |  | 2018-09-17 11:50 | [5 empty] | 2018-09-17 11:50 | Yes | 3
VD-9001-251-PPL-001 | 0 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 | 2018-01-31 20:42 |  | No | -2 | 2018-02-10 12:18 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:16
VD-9001-251-PPL-002 | 0 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 | 2018-01-31 20:43 |  | No | -2 | 2018-02-10 12:16 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:16
VD-9001-251-PPL-003 | 0 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 | 2018-01-31 20:44 |  | No | -2 | 2018-02-10 12:14 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:16
VD-9001-251-PPL-004 | 0 | REFORMER GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:49 |  | No | -1 | 2018-02-26 16:58 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:15
VD-9001-251-PPL-005 | 0 | REFORMER GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:50 |  | No | -1 | 2018-02-26 16:57 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:16
VD-9001-251-PPL-006 | 0 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:50 |  | No | -1 | 2018-02-26 16:21 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:16
VD-9001-251-PPL-007 | 0 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:51 |  | No | -1 | 2018-02-26 16:16 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:17
VD-9001-251-PPL-008 | 0 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:52 |  | No | -1 | 2018-02-26 16:04 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:17
VD-9001-251-PPL-009 | 0 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:53 |  | No | -1 | 2018-02-26 15:58 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:17
VD-9001-251-PPL-010 | 0 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-26 | 2018-01-25 18:54 |  | No | -1 | 2018-02-26 14:46 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:17
VD-9001-251-DWG-027 | 0 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-03-05 11:40 | 2018-03-05 11:56 | Yes | 17 |  |  | 2018-03-06 15:57 | [5 empty] | 2018-03-06 15:57 | Yes | -13 | 1204-Owner-v | 2018-03-07 15:34
VD-9001-251-DWG-028 | 0 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-03-05 12:17 | 2018-03-05 13:50 | Yes | 17 |  |  |  |  | 2018-03-06 15:56 |  |  |  | 2018-03-06 15:56 | Yes | -13 | 1204-Owner-v | 2018-03-07 15:19
VD-9001-251-DWG-029 | 0 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-03-05 13:58 | 2018-03-05 14:16 | Yes | 17 |  |  |  |  | 2018-03-06 15:55 |  |  |  | 2018-03-06 15:55 | Yes | -13 | 1204-Owner-v | 2018-03-07 15:19
VD-9001-251-DWG-030 | 0 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-04-20 14:39 | 2018-04-20 14:45 | Yes | 63 |  |  | 2018-04-24 17:36 | [5 empty] | 2018-04-24 17:36 | Yes | -10 | 1204-Owner-v | 2018-05-14 09:32
VD-9001-251-DWG-031 | 0 | MAIN COMPONENTS OVERALL DIMENSION | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 | 2018-10-12 11:58 | 2018-10-12 12:01 | Yes | 196 |  |  | 2018-10-21 10:04 | [5 empty] | 2018-10-21 10:04 | Yes | -5 | 1204-Owner-v | 2019-03-10 14:50
VD-9001-251-DWG-032 | 0 | GENERAL NOTES & INFORMATION | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-04-06 17:00 | 2018-04-06 17:11 | Yes | 21 |  |  |  | 2018-04-30 14:39 |  |  |  |  | 2018-04-30 14:39 | Yes | 10 | 1204-Owner-v | 2019-03-30 12:35
VD-9001-251-DWG-033 | 0 | FLOOR PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:46 |  | No | -9 | 2018-02-10 12:11 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 10:59
VD-9001-251-DWG-034 | 0 | ARCH PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:47 |  | No | -9 | 2018-02-10 12:10 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:00
VD-9001-251-DWG-035 | 0 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:51 |  | No | -9 | 2018-02-10 12:08 | [7 empty] | 2018-02-10 20:00 | Yes | 0
VD-9001-251-DWG-036 | 0 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:53 |  | No | -9 | 2018-02-10 12:07 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:00
VD-9001-251-DWG-037 | 0 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:53 |  | No | -9 | 2018-02-10 12:04 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:00
VD-9001-251-DWG-038 | 0 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:54 |  | No | -9 | 2018-02-10 11:56 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:00
VD-9001-251-DWG-039 | 0 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-09 | 2018-01-31 20:55 |  | No | -9 | 2018-02-10 11:55 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:01
VD-9001-251-DWG-040 | 0 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-15 | 2018-04-06 17:12 | 2018-04-06 17:18 | Yes | 50 |  |  | 2018-04-12 11:06 | [5 empty] | 2018-04-12 11:06 | Yes | -8
VD-9001-251-DWG-041 | 0 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-15 | 2018-04-06 17:18 | 2018-04-06 17:20 | Yes | 50 |  |  | 2018-04-12 11:06 | [5 empty] | 2018-04-12 11:06 | Yes | -8
VD-9001-251-DWG-042 | 0 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-15 | 2018-04-06 17:06 | 2018-04-06 17:10 | Yes | 50 |  |  | 2018-04-12 11:07 | [5 empty] | 2018-04-12 11:07 | Yes | -8
VD-9001-251-DWG-043 | 0 | GENERAL ARRANGEMENT STAIRS | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-01-31 20:56 |  | No | -16 | 2018-02-26 11:31 | [7 empty] | 2018-02-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:01
VD-9001-251-DWG-044 | 0 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-05-08 20:18 | 2018-05-08 20:21 | Yes | 67 |  |  | 2018-05-10 11:52 | [5 empty] | 2018-05-10 11:52 | Yes | -12
VD-9001-251-DWG-045 | 0 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-05-08 20:20 | 2018-05-08 20:23 | Yes | 67 |  |  | 2018-05-10 11:53 | [5 empty] | 2018-05-10 11:53 | Yes | -12
VD-9001-251-DWG-046 | 0 | HORIZONTAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-05-08 20:28 | 2018-05-08 20:34 | Yes | 67 |  |  | 2018-05-10 11:54 | [5 empty] | 2018-05-10 11:54 | Yes | -12
VD-9001-251-DWG-047 | 0 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-05-23 17:53 | 2018-05-23 17:54 | Yes | 75 |  |  | 2018-05-26 16:45 | [5 empty] | 2018-05-26 16:45 | Yes | -11
VD-9001-251-DWG-048 | 0 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-05-23 17:54 | 2018-05-23 17:55 | Yes | 75 |  |  | 2018-05-26 16:48 | [5 empty] | 2018-05-26 16:48 | Yes | -11
VD-9001-251-DWG-049 | 0 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-05-23 17:55 | 2018-05-23 18:05 | Yes | 75 |  |  | 2018-05-26 16:49 | [5 empty] | 2018-05-26 16:49 | Yes | -11
VD-9001-251-DWG-050 | 0 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-21 | 2018-01-31 20:57 |  | No | -21 | 2018-02-06 16:56 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:01
VD-9001-251-DWG-051 | 0 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-21 | 2018-01-31 20:57 |  | No | -21 | 2018-02-06 16:50 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:01
VD-9001-251-DWG-052 | 0 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-21 | 2018-01-31 20:58 |  | No | -21 | 2018-02-06 16:49 | [7 empty] | 2018-02-07 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:02
VD-9001-251-DWG-053 | 0 | MAIN COMBUSTION AIR DUCTS LAYOUT | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-08-31 14:12 | 2018-08-31 14:28 | Yes | 161 |  |  | 2018-09-06 11:52 | [5 empty] | 2018-09-06 11:52 | Yes | -8
VD-9001-251-DWG-054 | 0 | MAIN COMBUSTION AIR DUCTS ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-08-31 14:29 | 2018-08-31 14:29 | Yes | 161 |  |  |  | 2018-10-13 14:46 |  |  |  |  | 2018-10-13 14:46 | Yes | 29
VD-9001-251-DWG-055 | 0 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-08-31 14:29 | 2018-08-31 14:31 | Yes | 161 |  |  | 2018-09-06 11:53 | [5 empty] | 2018-09-06 11:53 | Yes | -8
VD-9001-251-DWG-056 | 0 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-08-31 14:41 | 2018-08-31 15:16 | Yes | 161 |  |  | 2018-09-06 11:54 | [5 empty] | 2018-09-06 11:54 | Yes | -8
VD-9001-251-DWG-057 | 0 | COMBUSTION AIR DUCT TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-02-21 | 2018-10-23 12:14 | 2018-10-23 12:19 | Yes | 244 |  |  | 2018-10-28 09:50 | [5 empty] | 2018-10-28 09:50 | Yes | -9
VD-9001-251-DWG-058 | 0 | COMBUSTION AIR DUCT TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-02-21 | 2018-10-23 12:28 | 2018-10-23 12:33 | Yes | 244 |  |  | 2018-10-28 09:52 | [5 empty] | 2018-10-28 09:52 | Yes | -9
VD-9001-251-DWG-059 | 0 | COLD AIR - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-07-30 13:14 | 2018-07-30 13:17 | Yes | 129 |  |  | 2018-08-06 17:36 | [5 empty] | 2018-08-06 17:36 | Yes | -7
VD-9001-251-DWG-060 | 0 | COLD AIR - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-07-30 13:17 | 2018-07-30 13:18 | Yes | 129 |  |  | 2018-08-06 17:37 | [5 empty] | 2018-08-06 17:37 | Yes | -7
VD-9001-251-DWG-061 | 0 | FLUE GAS DUCTS - Convection - APH | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-06-26 18:40 | 2018-06-26 18:40 | Yes | 102 |  |  | 2018-06-28 11:51 | [5 empty] | 2018-06-28 11:51 | Yes | -12
VD-9001-251-DWG-062 | 0 | FLUE GAS DUCTS - APH to FAN - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-06-26 18:41 | 2018-06-26 18:41 | Yes | 102 |  |  | 2018-06-28 11:52 | [5 empty] | 2018-06-28 11:52 | Yes | -12
VD-9001-251-DWG-063 | 0 | FLUE GAS DUCTS - APH to FAN - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-07-30 13:31 | 2018-07-30 13:32 | Yes | 136 |  |  | 2018-08-06 17:39 | [5 empty] | 2018-08-06 17:39 | Yes | -7
VD-9001-251-DWG-064 | 0 | FLUE GAS DUCTS - FAN to STACK | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-07-30 13:54 | 2018-07-30 13:54 | Yes | 136 |  |  | 2018-08-06 17:42 | [5 empty] | 2018-08-06 17:42 | Yes | -7
VD-9001-251-DWG-065 | 0 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-07 19:30 | 2018-03-07 19:34 | Yes | 12 |  |  | 2018-03-11 15:36 | [5 empty] | 2018-03-11 15:36 | Yes | -10
VD-9001-251-DWG-066 | 0 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-03-07 19:35 | 2018-03-07 19:38 | Yes | 12 |  |  | 2018-03-11 15:34 | [5 empty] | 2018-03-11 15:35 | Yes | -10
VD-9001-251-DWG-067 | 0 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-03-05 14:29 | 2018-03-05 14:37 | Yes | -4 |  |  |  |  | 2018-03-06 14:57 |  |  |  | 2018-03-06 14:57 | Yes | -13 | 1204-Owner-v | 2018-03-07 11:02
VD-9001-251-DWG-068 | 0 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-03-05 14:37 | 2018-03-05 14:39 | Yes | -4 |  |  |  |  | 2018-03-06 14:58 |  |  |  | 2018-03-06 14:58 | Yes | -13
VD-9001-251-DWG-069 | 0 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-03-05 14:40 | 2018-03-05 14:50 | Yes | -4 |  |  |  |  | 2018-03-06 14:59 |  |  |  | 2018-03-06 14:59 | Yes | -13
VD-9001-251-DWG-070 | 0 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-03-05 14:50 | 2018-03-05 14:54 | Yes | -4 |  |  |  |  | 2018-03-06 15:00 |  |  |  | 2018-03-06 15:00 | Yes | -13
VD-9001-251-DWG-071 | 0 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-05-30 18:33 | 2018-05-30 18:36 | Yes | 75 |  |  | 2018-06-05 14:49 | [5 empty] | 2018-06-05 14:49 | Yes | -8
VD-9001-251-DWG-072 | 0 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-05-30 18:33 | 2018-05-30 18:36 | Yes | 75 |  |  | 2018-06-05 14:50 | [5 empty] | 2018-06-05 14:50 | Yes | -8
VD-9001-251-DWG-073 | 0 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-05-30 18:33 | 2018-05-30 18:37 | Yes | 75 |  |  | 2018-06-05 14:48 | [5 empty] | 2018-06-05 14:48 | Yes | -8
VD-9001-251-DWG-074 | 0 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-02-15 15:45 |  | No | -1 | 2018-02-26 10:43 | [7 empty] | 2018-02-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 15:07
VD-9001-251-DWG-075 | 0 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-02-15 15:45 |  | No | -1 | 2018-02-26 10:54 | [7 empty] | 2018-02-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-24 11:46
VD-9001-251-DWG-076 | 0 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-02-15 15:52 |  | No | -1 | 2018-02-26 11:02 | [7 empty] | 2018-02-26 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-24 11:51
VD-9001-251-DWG-077 | 0 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-02-15 15:51 | 2018-02-15 15:52 | Yes | -1 |  | 2018-02-25 16:17 | [6 empty] | 2018-02-25 20:00 | Yes | -4 | 1204-Owner-v | 2018-03-07 11:10
VD-9001-251-DWG-078 | 0 | FLUE GAS TUNNEL | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-09-12 12:08 | 2018-09-12 12:16 | Yes | 187 |  |  | 2018-09-17 14:48 | [5 empty] | 2018-09-17 14:48 | Yes | -9
VD-9001-251-DWG-079 | 0 | STACK CONNECTION DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 | 2018-07-06 13:42 | 2018-07-06 13:43 | Yes | 98 |  |  |  | 2018-07-08 15:39 |  |  |  |  | 2018-07-08 15:39 | Yes | -12 | 1204-Owner-v | 2019-05-11 07:23
VD-9001-251-DWG-080 | 0 | STACK PLAN & PLATFORMS | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 | 2018-07-06 14:02 | 2018-07-06 14:03 | Yes | 98 |  |  | 2018-07-08 15:39 | [5 empty] | 2018-07-08 15:39 | Yes | -12 | 1204-Owner-v | 2019-05-08 10:05
VD-9001-251-SDG-001 | 0 | N.D.E. ON CAST PARTS | HM-251 | KT – Kinetics Technology SpA | 2018-02-28 | 2018-05-29 12:45 | 2018-05-29 12:47 | Yes | 90 |  |  |  | 2018-06-18 18:07 |  |  |  |  | 2018-06-18 18:07 | Yes | 6
VD-9001-251-SDG-002 | 0 | FINNING DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-02-22 | 2018-01-18 17:44 |  | No | -35 | 2018-01-24 17:45 | [7 empty] | 2018-01-24 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:18
VD-9001-251-SDG-003 | 0 | STRUCTURAL STEEL STANDARDS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-04-26 12:11 | 2018-04-26 12:28 | Yes | 55 |  |  | 2018-05-01 11:19 | [5 empty] | 2018-05-01 11:19 | Yes | -9
VD-9001-251-SDG-004 | 0 | STRUCTURAL STEEL STANDARDS FOR EXPANSION JOINTS | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 | 2018-04-26 12:29 | 2018-04-26 12:34 | Yes | 27 |  |  | 2018-04-28 16:33 | [5 empty] | 2018-04-28 16:33 | Yes | -12
VD-9001-251-SDG-005 | 0 | REFORMER TYPICAL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-04-26 12:36 | 2018-04-26 12:42 | Yes | 55 |  |  | 2018-04-28 16:56 | [5 empty] | 2018-04-28 16:56 | Yes | -12 | 1204-Owner-v | 2018-05-19 12:26
VD-9001-251-SDG-006 | 0 | REFRACTORY STANDARDS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-04-26 12:43 | 2018-04-26 12:51 | Yes | 55 |  |  | 2018-04-28 16:58 | [5 empty] | 2018-04-28 16:58 | Yes | -12 | 1204-Owner-v | 2018-05-19 12:24
VD-9001-251-DWG-081 | 0 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-10-24 12:56 | 2018-10-24 13:06 | Yes | 236 |  |  | 2018-10-28 09:59 | [5 empty] | 2018-10-28 09:59 | Yes | -10 | 1204-Owner-v | 2020-04-25 16:59
VD-9001-251-DWG-082 | 0 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2019-06-12 11:27 | 2019-06-12 11:27 | Yes | 467 |  |  |  | 2019-07-03 15:56 |  |  |  |  | 2019-07-03 15:56 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:04
VD-9001-251-DWG-083 | 0 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2019-06-12 11:27 | 2019-06-12 11:27 | Yes | 467 |  |  |  | 2019-07-03 15:57 |  |  |  |  | 2019-07-03 15:57 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:17
VD-9001-251-DWG-084 | 0 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2019-06-12 11:27 | 2019-06-12 11:27 | Yes | 467 |  |  |  | 2019-07-03 15:59 |  |  |  |  | 2019-07-03 15:59 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:17
VD-9001-251-DWG-085 | 0 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-06 | 2019-06-12 11:27 | 2019-06-12 11:27 | Yes | 463 |  |  |  | 2019-07-03 16:15 |  |  |  |  | 2019-07-03 16:15 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:18
VD-9001-251-DWG-086 | 0 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-06 | 2019-06-12 11:28 | 2019-06-12 11:28 | Yes | 463 |  |  | 2019-07-03 16:13 | [5 empty] | 2019-07-03 16:13 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:18
VD-9001-251-DWG-087 | 0 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-06 | 2019-06-12 11:28 | 2019-06-12 11:28 | Yes | 463 |  |  | 2019-07-03 16:16 | [5 empty] | 2019-07-03 16:16 | Yes | 7 | 1204-Owner-v | 2020-04-25 17:18
VD-9001-251-DWG-088 | 0 | OUTLET SYSTEM - CONTERWEIGHTS & PULLEY | HM-251 | KT – Kinetics Technology SpA | 2018-03-06 |  |  | No | 836 | [9 empty] | No | 0
VD-9001-251-PCJ-001 | 0 | ERECTION PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2018-07-20 | 2018-10-29 12:08 | 2018-10-29 12:16 | Yes | 101 |  |  |  | 2018-11-11 10:15 |  |  |  |  | 2018-11-11 10:15 | Yes | -1 | 1204-Owner-v | 2019-03-27 15:27
VD-9001-251-PCJ-002 | 0 | ERECTION PROCEDURE FOR TRANSFER LINE | HM-251 | KT – Kinetics Technology SpA | 2018-07-27 |  |  | No | 693 | [9 empty] | No | 0
VD-9001-251-DSH-023 | 0 | DATA SHEET FOR CONSTANT & VARIABLE SPRING HANGERS | HM-251 | KT – Kinetics Technology SpA | 2018-06-20 | 2020-06-06 08:17 | 2020-06-06 08:17 | Yes | 717 | [9 empty] | No | -1
VD-9001-251-CAL-016 | 0 | STRESS ANALISYS CALCULATION (INLET SYSTEM) | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2018-04-16 18:29 | 2018-04-16 18:31 | Yes | 59 |  |  |  | 2018-04-26 12:15 |  |  |  |  | 2018-04-26 12:15 | Yes | -4
VD-9001-251-CAL-017 | 0 | STRESS ANALISYS CALCULATION (OUTLET SYSTEM) | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2019-03-13 14:23 | 2019-03-13 14:23 | Yes | 390 |  |  |  | 2019-05-08 14:08 |  |  |  |  | 2019-05-08 14:08 | Yes | 42
VD-9001-251-PCJ-003 | 0 | CONVECTION MODULES ASSEMBLY PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2018-06-28 |  |  | No | 722 | [9 empty] | No | 0
VD-9001-251-DWG-089 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1001 | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 |  |  | No | 805 | [9 empty] | No | 0
VD-9001-251-DWG-090 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-091 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1003 | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-092 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-093 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-094 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-095 | 0 | CONV. MODULE STEELWORK FOR COIL BUNDLE TRANSPORT - HE-1004B | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 |  |  | No | 833 | [9 empty] | No | 0
VD-9001-251-DWG-096 | 0 | EXTERNAL DOORS COVERING DRAWINGS & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 |  |  | No | 826 | [9 empty] | No | 0
VD-9001-251-DWG-097 | 0 | EXTERNAL DOORS COVERING DRAWINGS & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 |  |  | No | 826 | [9 empty] | No | 0
VD-9001-251-DWG-098 | 0 | EXTERNAL DOORS COVERING DRAWINGS & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 |  |  | No | 826 | [9 empty] | No | 0
VD-9001-251-DWG-099 | 0 | INSTRUMENTS CONNECTION DRAWINGS | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 | 2018-04-06 17:35 | 2018-04-06 17:35 | Yes | 21 |  |  |  | 2018-04-12 11:17 |  |  |  |  | 2018-04-12 11:17 | Yes | -8
VD-9001-251-DSH-001 | 0 | DATA SHEET FOR STEAM REFORMER | HM-251 | KT – Kinetics Technology SpA | 2017-12-15 | 2017-12-22 18:53 |  | No | 7 | 2017-12-28 12:12 | [7 empty] | 2017-12-28 19:59 | Yes | 0 | 1204-Owner-v | 2018-01-03 12:49
VD-9001-251-DSH-002 | 0 | DATA SHEET ARCH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-09 19:07 |  | No | 18 | 2018-01-27 11:25 | [7 empty] | 2018-01-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:11
VD-9001-251-DSH-003 | 0 | DATA SHEET TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-09 19:08 |  | No | 18 | 2018-01-24 17:53 | [7 empty] | 2018-01-24 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:15
VD-9001-251-DSH-004 | 0 | DATA SHEET SSH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-09 19:08 |  | No | 18 | 2018-01-27 11:27 | [7 empty] | 2018-01-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-14 14:15
VD-9001-251-DSH-005 | 0 | DATA SHEET FOR FLUE GAS AIR PREHEATER (HE-1006) | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-12 12:26 |  | No | 21 | 2018-01-27 17:25 | [7 empty] | 2018-01-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:15
VD-9001-251-DSH-006 | 0 | DATA SHEET FOR AIR PREHEATER (E-4002) | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-09 19:10 |  | No | 18 | 2018-01-16 11:45 | [7 empty] | 2018-01-16 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:15
VD-9001-251-DSH-007 | 0 | DATA SHEET DAMPERS | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2020-05-30 14:05 | 2020-05-30 14:05 | Yes | 827 |  |  |  | 2020-06-14 12:41 |  |  |  |  | 2020-06-14 12:41 | Yes | 1 | 1204-Owner-v | 2020-06-01 16:18
VD-9001-251-DSH-008 | 0 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2017-12-15 | 2017-12-22 14:38 |  | No | 7 | 2017-12-31 14:32 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-251-DSH-009 | 0 | PROCESS DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2017-12-15 | 2017-12-22 14:42 |  | No | 7 | 2018-01-01 17:17 | [7 empty] | 2018-01-01 20:00 | Yes | 0
VD-9001-251-DSH-010 | 0 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2017-12-15 | 2017-12-22 14:46 |  | No | 7 | 2018-01-02 10:55 | [7 empty] | 2018-01-02 19:59 | Yes | 0
VD-9001-251-DSH-011 | 0 | PROCESS DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2017-12-15 | 2017-12-22 14:49 |  | No | 7 | 2018-01-02 10:56 | [7 empty] | 2018-01-02 19:59 | Yes | 0
VD-9001-251-PFD-001 | 0 | PROCESS FLOW DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-16 20:37 |  | No | 4 | 2018-01-28 19:02 | [7 empty] | 2018-01-28 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:13
VD-9001-251-PFD-002 | 0 | PROCESS FLOW DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 |  |  | No | 889 | [9 empty] | No | 0
VD-9001-251-PID-001 | 0 | PID - PRIMARY REFORMER RADIANT SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:25 |  | No | 11 | 2018-02-27 15:48 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:16
VD-9001-251-PID-002 | 0 | PID - PRIMARY REFORMER CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:26 |  | No | 11 | 2018-02-27 15:52 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:17
VD-9001-251-PID-003 | 0 | PID - COMBUSTION AIR FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:27 |  | No | 11 | 2018-02-27 15:57 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:17
VD-9001-251-PID-004 | 0 | PID - FLUE GAS FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:27 |  | No | 11 | 2018-02-27 16:02 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:18
VD-9001-251-PID-005 | 0 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:28 |  | No | 11 | 2018-02-27 16:09 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:18
VD-9001-251-PID-006 | 0 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:30 |  | No | 11 | 2018-02-27 16:16 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:19
VD-9001-251-PID-007 | 0 | PID - TUNNEL BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:31 |  | No | 11 | 2018-02-27 16:26 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:19
VD-9001-251-PID-008 | 0 | PID - SSH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:31 |  | No | 11 | 2018-02-27 16:23 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:15
VD-9001-251-PID-009 | 0 | PID - LOCAL PANELS | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:32 |  | No | 11 | 2018-02-27 10:32 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:15
VD-9001-251-PID-010 | 0 | PID- UTILITIES DISTRIBUTION | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-01-30 18:32 |  | No | 11 | 2018-02-27 16:29 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:15
VD-9001-251-RPT-001 | 0 | CFD MODELING REPORT | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-08-09 17:33 | 2018-08-09 17:35 | Yes | 153 |  |  |  |  | 2018-08-25 16:00 |  |  |  | 2018-08-25 16:00 | Yes | 2 | 1204-Owner-v | 2019-04-15 09:13
VD-9001-251-DIG-001 | 0 | CAUSE & EFFECT DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-09-25 11:02 | 2018-09-25 11:09 | Yes | 200 |  |  |  |  | 2018-10-24 10:22 |  |  |  | 2018-10-24 10:22 | Yes | 15
VD-9001-251-LST-001 | 0 | ALARM/TRIP SET POINTS LIST | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-09-25 13:08 | 2018-09-25 13:39 | Yes | 186 |  |  |  |  | 2018-12-08 16:35 |  |  |  | 2018-12-08 16:35 | Yes | 60
VD-9001-251-LGD-001 | 0 | OPERATING MANUAL | HM-251 | KT – Kinetics Technology SpA | 2018-07-06 | 2018-10-12 11:48 | 2018-10-12 11:50 | Yes | 98 |  |  |  |  | 2018-12-11 16:53 |  |  |  | 2018-12-11 16:53 | Yes | 46 | 1204-Owner-v | 2019-04-06 10:27
VD-9001-251-LST-002 | 0 | UTILITIES COMSUMPTION LIST | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 | 2018-06-06 14:31 | 2018-06-06 14:52 | Yes | 103 |  |  |  |  | 2018-06-10 16:47 |  |  |  | 2018-06-10 16:47 | Yes | -10 | 1204-Owner-v | 2018-08-14 17:12
VD-9001-251-CAL-018 | 0 | REFRACTORY HEAT FLOW CALCULATIONS | HM-251 | KT – Kinetics Technology SpA | 2018-02-02 | 2018-10-29 12:04 | 2018-10-29 12:08 | Yes | 269 |  |  | 2018-11-11 11:46 | [5 empty] | 2018-11-11 11:46 | Yes | -1 | 1204-Owner-v | 2020-05-14 09:31
VD-9001-251-PDS-001 | 0 | CONTROL PHILOSOFY DESCRIPTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-09-25 11:29 | 2018-09-25 12:03 | Yes | 200 |  |  |  |  | 2019-01-30 15:11 |  |  |  | 2019-01-30 15:11 | Yes | 113 | 1204-Owner-v | 2019-07-15 13:19
VD-9001-251-PDS-002 | 0 | BMS DESCRIPTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-09 | 2018-09-25 12:09 | 2018-09-25 12:27 | Yes | 200 |  |  |  |  | 2019-01-30 16:59 |  |  |  | 2019-01-30 16:59 | Yes | 113 | 1204-Owner-v | 2019-06-10 17:07
VD-9001-251-LST-003 | 0 | LINE LIST | HM-251 | KT – Kinetics Technology SpA | 2018-01-31 | 2018-02-16 11:56 |  | No | 16 | 2018-02-27 16:51 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-18 13:14
VD-9001-251-LST-004 | 0 | EQUIPMENT LIST | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-02-16 11:57 |  | No | 28 | 2018-02-27 16:48 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:11
VD-9001-251-PCJ-004 | 0 | PERFORMANCE TEST RUN PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 |  |  | No | 910 | [9 empty] | No | 0
VD-9001-251-DSH-012 | 0 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-09 19:06 |  | No | -3 | 2018-01-23 16:20 | [7 empty] | 2018-01-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:16
VD-9001-251-DSH-013 | 0 | MECHANICAL DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-09 19:04 |  | No | -3 | 2018-01-23 16:22 | [7 empty] | 2018-01-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:16
VD-9001-251-DSH-014 | 0 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-09 19:05 |  | No | -3 | 2018-01-23 16:24 | [7 empty] | 2018-01-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:16
VD-9001-251-DSH-015 | 0 | MECHANICAL DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-12 | 2018-01-09 19:06 |  | No | -3 | 2018-01-23 16:18 | [7 empty] | 2018-01-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-27 17:16
VD-9001-251-DSH-016 | 0 | PSV DATA SHEET | HM-251 | KT – Kinetics Technology SpA | 2018-02-13 | 2018-05-11 11:18 | 2018-05-11 11:29 | Yes | 87 |  |  |  |  | 2018-05-20 14:50 |  |  |  | 2018-05-20 14:50 | Yes | -5 | 1204-Owner-v | 2018-05-19 10:26
VD-9001-251-DSH-017 | 0 | Control Valves Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-02-13 | 2018-04-20 19:22 | 2018-04-20 19:26 | Yes | 66 |  |  |  |  | 2018-05-20 14:53 |  |  |  | 2018-05-20 14:53 | Yes | 16 | 1204-Owner-v | 2018-05-19 10:26
VD-9001-251-DSH-018 | 0 | ON-OFF Valves Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-02-13 | 2018-04-17 11:17 | 2018-04-17 11:30 | Yes | 63 |  |  |  |  | 2018-05-20 16:57 |  |  |  | 2018-05-20 16:57 | Yes | 19 | 1204-Owner-v | 2018-05-19 10:27
VD-9001-251-DSH-019 | 0 | Primary Flow Elements Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 | 2020-06-13 09:35 | 2020-06-13 09:35 | Yes | 848 | [9 empty] | No | -8
VD-9001-251-DSH-020 | 0 | Special Flowmeter Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-02-16 |  |  | No | 854 | [9 empty] | No | 0
VD-9001-251-DSH-021 | 0 | Pressure and Flow Transmitters Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2018-08-29 18:24 | 2018-08-29 18:24 | Yes | 180 |  |  |  |  | 2018-10-13 14:09 |  |  |  | 2018-10-13 14:09 | Yes | 31
VD-9001-251-DSH-022 | 0 | Pressure & Temperature gauge Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-03-07 | 2018-08-29 18:24 | 2018-08-29 18:24 | Yes | 175 |  |  |  |  | 2018-10-13 11:43 |  |  |  | 2018-10-13 11:43 | Yes | 31
VD-9001-251-DSH-024 | 0 | Cables Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 |  |  | No | 805 | [9 empty] | No | 0
VD-9001-251-DSH-025 | 0 | Analyzer data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-02-23 |  |  | No | 847 | [9 empty] | No | 0
VD-9001-251-DSH-026 | 0 | Thermoelements, Wells & TT Converters Data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 |  |  | No | 826 | [9 empty] | No | 0
VD-9001-251-LST-005 | 0 | Instruments List | HM-251 | KT – Kinetics Technology SpA | 2018-02-13 | 2018-03-30 13:54 | 2018-03-30 14:00 | Yes | 45 |  |  |  | 2018-04-12 11:23 |  |  |  |  | 2018-04-12 11:23 | Yes | -1 | 1204-Owner-v | 2019-03-02 11:36
VD-9001-251-LST-006 | 0 | DCS & ESD Database (I/O List) | HM-251 | KT – Kinetics Technology SpA | 2018-02-13 |  |  | No | 857 | [9 empty] | No | 0
VD-9001-251-PPL-011 | 0 | Instrument cable routing , tray & junction box layout | HM-251 | KT – Kinetics Technology SpA | 2018-04-16 | 2019-06-12 14:33 | 2019-06-12 14:33 | Yes | 422 |  |  |  | 2019-07-13 11:09 |  |  |  |  | 2019-07-13 11:09 | Yes | 17
VD-9001-251-PPL-012 | 0 | Instrument cable routing , tray & junction box layout | HM-251 | KT – Kinetics Technology SpA | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-251-PPL-013 | 0 | Instrument cable routing , tray & junction box layout | HM-251 | KT – Kinetics Technology SpA | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-251-PPL-014 | 0 | Instrument Location Layout | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-251-PPL-015 | 0 | Instrument Location Layout | HM-251 | KT – Kinetics Technology SpA | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-251-DIG-002 | 0 | Two wire loop diagram | HM-251 | KT – Kinetics Technology SpA | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-251-PPL-016 | 0 | Local Panel Layout & Wiring Diagram | HM-251 | KT – Kinetics Technology SpA | 2018-03-28 | 2019-06-12 14:34 | 2019-06-12 14:34 | Yes | 441 |  |  |  | 2019-07-23 09:34 |  |  |  |  | 2019-07-23 09:34 | Yes | 27
VD-9001-251-PPL-017 | 0 | Junction Boxes Layout & Wiring Diagram | HM-251 | KT – Kinetics Technology SpA | 2018-04-12 | 2019-06-12 14:34 | 2019-06-12 14:34 | Yes | 426 |  |  | 2019-10-22 15:59 | [5 empty] | 2019-10-22 15:59 | Yes | 118 | 1204-Owner-v | 2020-06-12 10:14
VD-9001-251-DWG-100 | 0 | Instrument Hook up's (Pneum.) | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 | 2019-06-12 14:31 | 2019-06-12 14:31 | Yes | 425 |  |  | 2019-07-03 11:29 | [5 empty] | 2019-07-03 11:29 | Yes | 7
VD-9001-251-DWG-101 | 0 | Instrument Hook up's (Mech.) | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 | 2019-06-12 14:32 | 2019-06-12 14:32 | Yes | 425 |  |  |  | 2019-07-06 15:43 |  |  |  |  | 2019-07-06 15:43 | Yes | 10
VD-9001-251-DWG-102 | 0 | Overhead electric Connection | HM-251 | KT – Kinetics Technology SpA | 2018-04-17 | 2019-06-12 14:32 | 2019-06-12 14:32 | Yes | 421 |  |  | 2019-07-03 11:41 | [5 empty] | 2019-07-03 11:41 | Yes | 7 | 1204-Owner-v | 2020-05-23 08:12
VD-9001-251-LST-007 | 0 | Cable LIST | HM-251 | KT – Kinetics Technology SpA | 2018-04-19 | 2019-06-12 14:33 | 2019-06-12 14:33 | Yes | 419 |  |  | 2020-02-08 14:37 | [5 empty] | 2020-02-08 14:37 | Yes | 227
VD-9001-251-MTO-002 | 0 | Bulk accessories Material Take Off | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-06-12 14:33 | 2019-06-12 14:33 | Yes | 408 |  |  | 2020-02-08 14:38 | [5 empty] | 2020-02-08 14:38 | Yes | 227 | 1204-Owner-v | 2019-06-15 16:33
VD-9001-251-BLD-001 | 0 | Logic Diagram | HM-251 | KT – Kinetics Technology SpA | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-251-BLD-002 | 0 | Complex Control Loops Configuration Details | HM-251 | KT – Kinetics Technology SpA | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-251-SPE-001 | 0 | General Specification for PLC | HM-251 | KT – Kinetics Technology SpA | 2018-02-28 |  |  | No | 842 | [9 empty] | No | 0
VD-9001-251-LST-008 | 0 | Electrical / Instrument Interface Table | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-251-DWG-103 | 0 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-05-11 | 2018-07-06 14:04 | 2018-07-06 14:04 | Yes | 56 |  |  |  | 2018-08-04 11:01 |  |  |  |  | 2018-08-04 11:01 | Yes | 15 | 1204-Owner-v | 2018-08-04 10:38
VD-9001-251-DWG-104 | 0 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-04-27 | 2018-07-06 14:07 | 2018-07-06 14:07 | Yes | 70 |  |  |  | 2018-08-04 11:02 |  |  |  |  | 2018-08-04 11:02 | Yes | 15
VD-9001-251-DWG-105 | 0 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-04-27 | 2018-07-06 14:08 | 2018-07-06 14:08 | Yes | 70 |  |  |  | 2018-08-04 11:03 |  |  |  |  | 2018-08-04 11:03 | Yes | 15
VD-9001-251-LST-009 | 0 | Electrical Load Summary | HM-251 | KT – Kinetics Technology SpA | 2018-03-16 |  |  | No | 826 | [9 empty] | No | 0
VD-9001-251-DSH-027 | 0 | Motor Data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-01-19 | 2018-03-05 17:48 | 2018-03-05 17:48 | Yes | 45 |  |  |  |  | 2018-03-10 17:10 |  |  |  | 2018-03-10 17:10 | Yes | -9 | 1204-Owner-v | 2018-08-06 11:53
VD-9001-251-MTO-003 | 0 | PIPING MATERIAL TAKE-OFF | HM-251 | KT – Kinetics Technology SpA | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-251-SDG-007 | 0 | PIPING ASSEMBLY STANDARD | HM-251 | KT – Kinetics Technology SpA | 2018-03-02 | 2020-05-30 14:05 | 2020-05-30 14:05 | Yes | 820 |  |  | 2020-05-31 13:58 | [5 empty] | 2020-05-31 13:58 | Yes | -13
VD-9001-251-SDG-008 | 0 | PIPING SUPPORT STANDARD | HM-251 | KT – Kinetics Technology SpA | 2018-06-22 | 2020-06-06 08:28 | 2020-06-06 08:28 | Yes | 715 |  |  | 2020-06-13 10:36 | [5 empty] | 2020-06-13 10:36 | Yes | -7
VD-9001-251-PPL-018 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:11 | 2018-04-16 18:14 | Yes | 10 |  |  |  |  | 2018-04-26 12:04 |  |  |  | 2018-04-26 12:04 | Yes | -4
VD-9001-251-PPL-019 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:15 | 2018-04-16 18:15 | Yes | 10 |  |  |  | 2018-04-26 12:07 |  |  |  |  | 2018-04-26 12:07 | Yes | -4
VD-9001-251-PPL-020 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:16 | 2018-04-16 18:21 | Yes | 10 |  |  |  | 2018-04-26 12:23 |  |  |  |  | 2018-04-26 12:23 | Yes | -4
VD-9001-251-PPL-021 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:18 | 2018-04-16 18:21 | Yes | 10 |  |  |  | 2018-04-26 12:27 |  |  |  |  | 2018-04-26 12:27 | Yes | -4
VD-9001-251-PPL-022 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:23 | 2018-04-16 18:27 | Yes | 10 |  |  |  | 2018-04-26 12:29 |  |  |  |  | 2018-04-26 12:29 | Yes | -4
VD-9001-251-PPL-023 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-04-16 18:23 | 2018-04-16 18:27 | Yes | 10 |  |  |  | 2018-04-26 12:31 |  |  |  |  | 2018-04-26 12:31 | Yes | -4
VD-9001-251-PPL-024 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-06-14 17:19 | 2018-06-14 17:21 | Yes | 69 |  |  | 2018-06-18 17:02 | [5 empty] | 2018-06-18 17:02 | Yes | -10 | 1204-Owner-v | 2018-10-09 15:27
VD-9001-251-PPL-025 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-06-14 17:19 | 2018-06-14 17:21 | Yes | 69 |  |  | 2018-06-18 17:08 | [5 empty] | 2018-06-18 17:08 | Yes | -10 | 1204-Owner-v | 2018-10-09 15:27
VD-9001-251-PPL-026 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2018-06-14 17:22 | 2018-06-14 17:22 | Yes | 69 |  |  | 2018-06-18 17:10 | [5 empty] | 2018-06-18 17:10 | Yes | -10 | 1204-Owner-v | 2018-10-09 15:27
VD-9001-251-PPL-027 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2019-03-13 14:37 | 2019-03-13 14:37 | Yes | 341 |  |  |  | 2019-04-27 11:48 |  |  |  |  | 2019-04-27 11:48 | Yes | 31
VD-9001-251-DWG-106 | 0 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-04-06 18:11 | 2018-04-06 18:14 | Yes | 14 |  |  |  |  | 2018-04-17 15:47 |  |  |  | 2018-04-17 15:47 | Yes | -3 | 1204-Owner-v | 2018-04-15 08:00
VD-9001-251-DWG-107 | 0 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-04-06 18:15 | 2018-04-06 18:20 | Yes | 14 |  |  |  | 2018-04-17 15:49 |  |  |  |  | 2018-04-17 15:49 | Yes | -3
VD-9001-251-ISO-001 | 0 | ISOMETRIC SKETCHES | HM-251 | KT – Kinetics Technology SpA | 2018-06-29 | 2019-03-13 14:27 | 2019-03-13 14:27 | Yes | 257 |  |  |  | 2019-05-08 11:44 |  |  |  |  | 2019-05-08 11:44 | Yes | 42 | 1204-Owner-v | 2019-03-27 15:31
VD-9001-251-DWG-108 | 0 | PIPING SPECIAL SUPPORT | HM-251 | KT – Kinetics Technology SpA | 2018-07-06 | 2019-03-13 14:26 | 2019-03-13 14:26 | Yes | 250 |  |  |  | 2019-06-15 11:23 |  |  |  |  | 2019-06-15 11:23 | Yes | 80 | 1204-Owner-v | 2019-04-08 09:55
VD-9001-251-DWG-109 | 0 | LOADS ON STRUCTURES AND PIPE RACK | HM-251 | KT – Kinetics Technology SpA | 2018-06-23 | 2019-03-13 14:26 | 2019-03-13 14:26 | Yes | 263 |  |  | 2019-05-22 15:18 | [5 empty] | 2019-05-22 15:18 | Yes | 56 | 1204-Owner-v | 2019-07-23 09:06
VD-9001-251-CAL-019 | 0 | PIPING LINES STRESS ANALYSIS (FOR CRITICAL LINES) | HM-251 | KT – Kinetics Technology SpA | 2018-06-08 | 2018-05-23 17:43 | 2018-05-23 17:48 | Yes | -16 |  |  |  | 2018-07-10 10:35 |  |  |  |  | 2018-07-10 10:35 | Yes | 34
VD-9001-251-MTO-004 | 0 | PAINT Material Take Off | HM-251 | KT – Kinetics Technology SpA | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-251-MTO-005 | 0 | INSULATION Material Take Off | HM-251 | KT – Kinetics Technology SpA | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-251-ORC-001 | 0 | PROJECT ORGANIZATION CHART | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-19 19:28 |  | No | 28 | 2018-01-23 15:26 | [7 empty] | 2018-01-23 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-07 11:11
VD-9001-251-PCJ-005 | 0 | PROJECT COORDINATION PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-22 18:01 | 2018-01-22 18:02 | Yes | 31 |  | 2018-02-06 11:35 | [6 empty] | 2018-02-07 20:00 | Yes | 1 | 1204-Owner-v | 2018-03-07 11:13
VD-9001-251-LST-010 | 0 | PROJECT DOCUMENTS LIST | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2017-12-19 19:56 | 2017-12-19 19:57 | Yes | -3 |  | 2017-12-21 11:30 | [6 empty] | 2017-12-21 19:59 | Yes | -12 | 1204-Owner-v | 2018-01-03 11:14
VD-9001-251-VLS-001 | 0 | SUBVENDORS LIST | HM-251 | KT – Kinetics Technology SpA | 2017-12-22 | 2018-01-10 17:53 |  | No | 19 | 2018-02-10 16:56 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-28 10:11
VD-9001-251-MDB-001 | 0 | MECHANICAL CATALOGUE (Design Final Documentation) | HM-251 | KT – Kinetics Technology SpA | 2019-05-30 |  |  | No | 386 | [9 empty] | No | 0
VD-9001-251-LST-011 | 0 | LIST OF SPARE PART | HM-251 | KT – Kinetics Technology SpA | 2018-11-30 |  |  | No | 567 | [9 empty] | No | 0
VD-9001-251-PCJ-006 | 0 | STORAGE PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2018-09-30 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-251-PCJ-007 | 0 | Suggested Pneumatic leakege test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-30 |  |  | No | 598 | [9 empty] | No | 0
VD-9001-251-ITP-001 | 0 | SHOP INSPECTION TEST PLANS | HM-251 | KT – Kinetics Technology SpA | 2018-01-20 | 2018-03-06 12:11 | 2018-03-06 12:12 | Yes | 45 |  |  |  | 2018-04-09 16:17 |  |  |  |  | 2018-04-09 16:17 | Yes | 20 | 1204-Owner-v | 2018-03-07 11:10
VD-9001-104-PFD-004 | 2 | PFD Gas utilities | PR-104 | AIR LIQUIDE | 2017-12-30 20:00 | 2018-02-09 17:45 |  | No | 41 |  |  |  | 2018-03-10 17:13 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:57
VD-9001-104-PFD-003 | 2 | PFD Liquid Nitrogen storage and vaporization | PR-104 | AIR LIQUIDE | 2017-12-30 20:00 | 2018-02-09 17:45 |  | No | 41 |  |  |  | 2018-03-10 16:36 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:57
VD-9001-104-PFD-005 | 2 | PFD Cryogenic disposal | PR-104 | AIR LIQUIDE | 2017-12-30 20:00 | 2018-02-09 17:45 |  | No | 41 |  |  |  | 2018-03-10 17:48 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:58
VD-9001-104-PFD-006 | 2 | PFD Water utilities | PR-104 | AIR LIQUIDE | 2017-12-30 20:00 | 2018-02-09 17:45 |  | No | 41 |  |  |  | 2018-03-10 18:28 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:58
VD-9001-104-PFD-007 | 2 | PFD Steam utilities | PR-104 | AIR LIQUIDE | 2017-12-30 20:00 | 2018-02-09 17:45 |  | No | 41 |  |  |  | 2018-03-10 18:37 |  |  |  |  | 2018-03-10 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:59
VD-9001-201-PCJ-012 | 1 | UT PHASED ARRAY | PV-201 | ATB RIVA CALZONI SpA | 2017-12-17 14:59 | 2017-12-18 11:16 | 2017-12-18 11:17 | Yes | 1 |  |  | 2018-04-10 15:27 | [5 empty] | 2018-04-10 15:27 | Yes | 99 | 1204-Owner-v | 2018-12-16 21:38
VD-9001-104-DSH-045 | 1 | Cryo automatic valve - EDS Equipment Data Sheet for JT globe valves | PR-104 | AIR LIQUIDE | 2017-12-31 20:00 | 2018-02-21 19:15 |  | No | 52 |  |  |  | 2018-04-12 15:37 |  |  |  |  | 2018-04-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-07-22 10:08
VD-9001-104-DSH-043 | 1 | Cryo automatic valve - EDS Equipment Data Sheet for globe valves | PR-104 | AIR LIQUIDE | 2017-12-31 20:00 | 2018-02-21 18:56 |  | No | 52 |  |  |  | 2018-04-12 15:37 |  |  |  |  | 2018-04-12 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 15:38
VD-9001-104-DSH-044 | 1 | Cryo automatic valve - EDS Equipment Data Sheet for butterfly valves | PR-104 | AIR LIQUIDE | 2018-01-01 20:00 | 2018-04-11 11:47 | 2018-04-11 11:52 | Yes | 100 |  |  |  | 2018-05-16 15:52 |  |  |  |  | 2018-05-16 20:00 | Yes | 21 | 1204-Owner-v | 2018-07-22 10:13
VD-9001-104-PFD-008 | 2 | PFD Interconnection | PR-104 | AIR LIQUIDE | 2018-01-01 20:00 | 2018-02-09 17:46 |  | No | 39 |  |  |  | 2018-03-11 15:41 |  |  |  |  | 2018-03-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-11 07:44
VD-9001-104-DCR-001 | 1 | Site data sheet | PR-104 | AIR LIQUIDE | 2018-01-02 19:59 | 2018-04-11 18:01 | 2018-04-11 18:04 | Yes | 99 |  |  |  | 2018-04-24 18:48 |  |  |  |  | 2018-04-24 20:00 | Yes | -1
VD-9001-104-REQ-018 | 1 | PU-6101_E-6108/ E-6108-D1_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-02 19:59 | 2018-01-04 13:20 |  | No | 2 |  | 2018-01-21 10:46 | [6 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-104-REQ-017 | 1 | E-6124_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-02 19:59 | 2018-01-04 13:20 |  | No | 2 | 2018-01-21 09:50 | [7 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-105-DWG-503 | 6 | CMR Membrane separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-20 | 2017-12-21 10:27 | 2017-12-21 10:28 | Yes | 1 |  | 2017-12-31 17:35 | [6 empty] | 2017-12-31 19:59 | Yes | -4 | 1204-Owner-v | 2019-01-04 21:40
VD-9001-105-DWG-502 | 7 | Heater drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-20 | 2017-12-21 10:25 | 2017-12-21 10:26 | Yes | 1 |  | 2017-12-31 17:32 | [6 empty] | 2017-12-31 19:59 | Yes | -4 | 1204-Owner-v | 2019-09-06 22:04
VD-9001-105-DWG-501 | 6 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-20 | 2017-12-21 10:07 |  | No | 1 | 2017-12-31 17:29 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-104-REQ-036 | 1 | Cryogenic Globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-03 20:00 | 2018-02-21 19:03 |  | No | 49 |  |  |  | 2018-03-12 17:07 |  |  |  |  | 2018-03-12 20:00 | Yes | 0
VD-9001-104-REQ-037 | 1 | Cryogenic Butterfly automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-03 20:00 | 2018-04-11 11:40 | 2018-04-11 11:45 | Yes | 98 |  |  |  | 2018-04-17 17:53 |  |  |  |  | 2018-04-17 20:00 | Yes | -8
VD-9001-104-REQ-038 | 1 | Cryogenic JT globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-03 20:00 | 2018-02-21 19:13 |  | No | 49 |  |  |  | 2018-03-12 17:12 |  |  |  |  | 2018-03-12 20:00 | Yes | 0
VD-9001-104-REQ-042 | 1 | Warm automatic 3-lever valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-06 19:59 | 2018-01-26 18:35 | 2018-01-26 18:36 | Yes | 20 |  | 2018-01-28 15:45 | [6 empty] | 2018-01-28 20:00 | Yes | -12
VD-9001-104-DSH-051 | 1 | Warm automatic 3-lever valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-06 19:59 | 2018-01-26 18:43 | 2018-01-26 18:44 | Yes | 20 |  | 2018-02-01 14:01 | [6 empty] | 2018-02-01 20:00 | Yes | -8 | 1204-Owner-v | 2018-03-07 15:38
VD-9001-254-MNL-325 | 2 | TECHNICAL SPECIFICATION FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2018-01-07 19:59 | 2018-08-20 10:49 | 2018-08-20 10:50 | Yes | 225 |  |  |  | 2018-10-01 15:02 |  |  |  |  | 2018-10-01 15:02 | Yes | 28
VD-9001-254-LST-362 | 5 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2018-01-07 19:59 | 2018-05-30 13:21 | 2018-05-30 13:21 | Yes | 143 |  |  | 2018-06-27 11:00 | [5 empty] | 2018-06-27 11:00 | Yes | 14
VD-9001-104-HMB-001 | 1 | Mass and enthalpy balance "for information" | PR-104 | AIR LIQUIDE | 2018-01-07 19:59 | 2018-02-16 15:28 |  | No | 40 |  |  |  | 2018-03-11 16:25 |  |  |  |  | 2018-03-11 20:00 | Yes | 0 | 1204-Owner-v | 2018-02-21 12:33
VD-9001-254-LST-334 | 4 | SPARE PART LIST FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-01-07 19:59 | 2020-03-10 08:03 | 2020-03-10 08:03 | Yes | 793 |  |  | 2020-04-15 12:02 | [5 empty] | 2020-04-15 12:02 | Yes | 22
VD-9001-254-LST-302 | 5 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2018-01-07 19:59 | 2018-01-07 14:11 |  | No | 0 | 2018-02-05 14:41 | [7 empty] | 2018-02-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-01-27 15:53
VD-9001-254-LST-301 | 5 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-01-07 19:59 | 2018-05-30 13:18 | 2018-05-30 13:18 | Yes | 143 |  |  | 2018-06-25 14:46 | [5 empty] | 2018-06-25 14:46 | Yes | 12
VD-9001-108-INX-001 | 0 | Final Data Book Index | PR-108 | Farabard | 2017-12-25 | 2017-12-31 09:35 |  | No | 6 | 2018-01-01 11:48 | [7 empty] | 2018-01-01 19:59 | Yes | 0
VD-9001-104-REQ-039 | 1 | Cryo PSV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-08 20:00 | 2018-05-04 16:45 | 2018-05-04 16:48 | Yes | 116 |  |  | 2018-05-23 17:34 | [5 empty] | 2018-05-23 19:59 | Yes | 5
VD-9001-104-DSH-046 | 1 | Cryo PSV - EDS Equipment Data Sheet (pressure) | PR-104 | AIR LIQUIDE | 2018-01-08 20:00 | 2018-05-04 17:02 | 2018-05-04 17:03 | Yes | 116 |  |  |  | 2018-06-12 15:53 |  |  |  |  | 2018-06-12 20:15 | Yes | 25 | 1204-Owner-v | 2018-07-22 10:17
VD-9001-104-DSH-047 | 1 | Cryo TSV - EDS Equipment Data Sheet (thermal) | PR-104 | AIR LIQUIDE | 2018-01-08 20:00 | 2018-05-04 17:07 | 2018-05-04 17:08 | Yes | 116 |  |  |  | 2018-06-12 16:56 |  |  |  |  | 2018-06-12 20:15 | Yes | 25 | 1204-Owner-v | 2018-07-22 10:21
VD-9001-740A-GAD-00085 | 3 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:03 | 2017-12-26 14:04 | Yes | 0 |  | 2018-01-01 16:00 | [6 empty] | 2018-01-01 19:59 | Yes | -8 | 1204-Owner-v | 2019-03-26 11:17
VD-9001-740A-GAD-00086 | 4 | General Arrangement Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:08 | 2017-12-26 14:09 | Yes | 0 |  | 2018-01-01 16:13 | [6 empty] | 2018-01-01 19:59 | Yes | -8 | 1204-Owner-v | 2019-03-26 11:17
VD-9001-740A-GAD-00088 | 3 | General Arrangement Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:11 | 2017-12-26 14:12 | Yes | 0 |  | 2018-01-01 14:23 | [6 empty] | 2018-01-01 19:59 | Yes | -8 | 1204-Owner-v | 2019-03-26 11:22
VD-9001-740A-GAD-00112 | 1 | General Arrangement Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:13 |  | No | 0 | 2017-12-31 15:34 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-GAD-00302 | 1 | General Arrangement Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:16 |  | No | 0 | 2017-12-31 15:33 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-GAD-00316 | 2 | General Arrangement Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:20 | 2017-12-26 14:21 | Yes | 0 |  | 2018-01-02 10:47 | [6 empty] | 2018-01-02 19:59 | Yes | -7 | 1204-Owner-v | 2020-04-25 09:13
VD-9001-740A-GAD-00332 | 1 | General Arrangement Drawings-STR.E | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:31 | 2017-12-26 14:32 | Yes | 0 |  | 2018-01-02 14:52 | [6 empty] | 2018-01-02 19:59 | Yes | -7 | 1204-Owner-v | 2020-04-25 09:15
VD-9001-740A-GAD-00353 | 5 | General Arrangement Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:54 | 2017-12-26 14:40 | 2017-12-26 14:41 | Yes | 0 |  | 2018-01-02 14:49 | [6 empty] | 2018-01-02 19:59 | Yes | -7 | 1204-Owner-v | 2020-04-25 09:18
VD-9001-740A-SAD-00085 | 1 | Shop Assembly Drawings-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 16:30 | 2017-12-26 16:31 | Yes | 0 |  | 2018-02-27 08:45 | [6 empty] | 2018-02-27 19:59 | Yes | 49 | 1204-Owner-v | 2019-04-12 13:54
VD-9001-740A-SAD-00086 | 1 | Shop Assembly Drawings-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 22:07 | 2017-12-26 22:08 | Yes | 0 |  | 2018-02-27 08:42 | [6 empty] | 2018-02-27 19:59 | Yes | 49 | 1204-Owner-v | 2019-03-26 11:32
VD-9001-740A-SAD-00088 | 2 | Shop Assembly Drawings-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-27 19:49 | 2017-12-27 19:50 | Yes | 1 |  | 2018-02-27 08:28 | [6 empty] | 2018-02-27 19:59 | Yes | 48 | 1204-Owner-v | 2020-05-31 14:53
VD-9001-740A-SAD-00112 | 1 | Shop Assembly Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 22:44 | 2017-12-26 22:45 | Yes | 0 |  | 2018-02-27 08:39 | [6 empty] | 2018-02-27 19:59 | Yes | 49 | 1204-Owner-v | 2019-02-16 20:23
VD-9001-740A-SAD-00302 | 1 | Shop Assembly Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 23:10 | 2017-12-26 23:11 | Yes | 0 |  | 2018-02-27 08:37 | [6 empty] | 2018-02-27 19:59 | Yes | 49
VD-9001-740A-SAD-00316 | 1 | Shop Assembly Drawings-STR.G | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 23:33 | 2017-12-26 23:34 | Yes | 0 |  | 2018-02-27 08:34 | [6 empty] | 2018-02-27 19:59 | Yes | 49
VD-9001-740A-SAD-00332 | 1 | Shop Assembly Drawings-STR.E | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:55 | 2017-12-26 23:50 | 2017-12-26 23:51 | Yes | 0 |  | 2018-02-27 08:31 | [6 empty] | 2018-02-27 19:59 | Yes | 49
VD-9001-740A-SAD-00353 | 2 | Shop Assembly Drawings-STR.F | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-27 00:31 | 2017-12-27 00:32 | Yes | 1 |  | 2018-02-27 08:07 | [6 empty] | 2018-02-27 19:59 | Yes | 48
VD-9001-740A-RPT-00085 | 1 | Reports-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:31 | 2017-12-26 15:32 | Yes | 0 |  | 2018-01-10 18:43 | [6 empty] | 2018-01-10 19:59 | Yes | 1
VD-9001-740A-RPT-00086 | 1 | Reports-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:32 | 2017-12-26 15:33 | Yes | 0 |  | 2018-01-10 18:44 | [6 empty] | 2018-01-10 19:59 | Yes | 1
VD-9001-740A-RPT-00088 | 1 | Reports-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:32 | 2017-12-26 15:33 | Yes | 0 |  | 2018-01-09 10:51 | [6 empty] | 2018-01-09 19:59 | Yes | 0
VD-9001-740A-RPT-00112 | 1 | Reports-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:33 | 2017-12-26 15:34 | Yes | 0 |  | 2018-01-09 10:37 | [6 empty] | 2018-01-09 19:59 | Yes | 0
VD-9001-740A-RPT-00302 | 1 | Reports-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:33 | 2017-12-26 15:34 | Yes | 0 |  | 2018-01-08 14:40 | [6 empty] | 2018-01-08 19:59 | Yes | -1
VD-9001-740A-RPT-00316 | 1 | Reports-STR.G | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:34 | 2017-12-26 15:35 | Yes | 0 |  | 2018-01-09 10:47 | [6 empty] | 2018-01-09 19:59 | Yes | 0
VD-9001-740A-RPT-00332 | 1 | Reports-STR.E | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:56 | 2017-12-26 15:35 | 2017-12-26 15:36 | Yes | 0 |  | 2018-01-09 10:29 | [6 empty] | 2018-01-09 19:59 | Yes | 0
VD-9001-740A-RPT-00353 | 2 | Reports-STR.F | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:35 | 2017-12-26 15:36 | Yes | 0 |  | 2018-01-09 10:23 | [6 empty] | 2018-01-09 19:59 | Yes | 0
VD-9001-740A-MOD-00085 | 5 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 14:46 |  | No | 0 | 2018-01-01 16:04 | [7 empty] | 2018-01-01 19:59 | Yes | 0
VD-9001-740A-MOD-00086 | 3 | Models-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 14:53 |  | No | 0 | 2018-01-01 16:16 | [7 empty] | 2018-01-01 19:59 | Yes | 0 | 1204-Owner-v | 2019-03-26 11:22
VD-9001-740A-MOD-00088 | 5 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:00 |  | No | 0 | 2018-01-01 14:18 | [7 empty] | 2018-01-01 19:59 | Yes | 0
VD-9001-740A-MOD-00112 | 4 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:02 |  | No | 0 | 2017-12-31 15:00 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-MOD-00302 | 5 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:08 |  | No | 0 | 2017-12-31 14:58 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-MOD-00316 | 5 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:10 |  | No | 0 | 2017-12-31 14:59 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-MOD-00332 | 6 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:14 |  | No | 0 | 2017-12-31 14:59 | [7 empty] | 2017-12-31 19:59 | Yes | 0
VD-9001-740A-MOD-00353 | 7 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2017-12-26 09:57 | 2017-12-26 15:20 |  | No | 0 | 2018-01-02 14:46 | [7 empty] | 2018-01-02 19:59 | Yes | 0
VD-9001-104-REQ-020 | 1 | E-6187_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-01-09 19:59 | 2018-02-16 13:50 | 2018-02-16 13:51 | Yes | 38 |  | 2018-02-17 15:37 | [6 empty] | 2018-02-17 20:00 | Yes | -13
VD-9001-104-DSH-004 | 2 | EQUIPMENT DATA SHEET FOR DISTILLATION COLUMN: HP COLUMN T-6101, LP COLUMN T-6102 | PR-104 | AIR LIQUIDE | 2018-01-09 19:59 | 2018-01-03 17:16 | 2018-01-03 17:17 | Yes | -6 |  | 2018-01-16 14:55 | [6 empty] | 2018-01-16 19:59 | Yes | -1 | 1204-Owner-v | 2018-01-15 12:24
VD-9001-104-DSH-012 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-09 20:00 | 2018-01-04 13:04 |  | No | -5 | 2018-01-15 17:58 | [7 empty] | 2018-01-15 19:59 | Yes | 0
VD-9001-254-PPL-318 | 3 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2018-01-10 19:59 | 2018-02-14 16:51 |  | No | 35 |  |  |  |  | 2018-03-10 14:55 |  |  |  | 2018-03-10 14:55 | Yes | 0
VD-9001-254-PPL-319 | 3 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2018-01-10 19:59 | 2018-02-14 16:56 |  | No | 35 |  |  |  |  | 2018-03-10 14:57 |  |  |  | 2018-03-10 14:57 | Yes | 0
VD-9001-251-DSH-001 | 1 | DATA SHEET FOR STEAM REFORMER | HM-251 | KT – Kinetics Technology SpA | 2017-12-28 | 2018-08-09 17:42 | 2018-08-09 17:52 | Yes | 224 |  |  |  |  | 2018-08-13 16:32 |  |  |  | 2018-08-13 16:32 | Yes | -10 | 1204-Owner-v | 2018-09-25 14:53
VD-9001-104-DSH-010 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-11 19:59 | 2018-01-03 16:55 | 2018-01-03 16:56 | Yes | -8 |  | 2018-01-07 17:50 | [6 empty] | 2018-01-07 19:59 | Yes | -10 | 1204-Owner-v | 2018-03-06 16:38
VD-9001-251-DSH-008 | 1 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2017-12-31 | 2018-08-10 14:37 | 2018-08-10 14:39 | Yes | 222 |  |  |  |  | 2018-09-04 17:07 |  |  |  | 2018-09-04 17:07 | Yes | 11 | 1204-Owner-v | 2018-08-16 11:20
VD-9001-740A-MOD-00302 | 6 | Models-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 12:59 | 2018-01-07 13:00 | Yes | 7 |  | 2018-01-08 14:43 | [6 empty] | 2018-01-08 19:59 | Yes | -13
VD-9001-740A-MOD-00332 | 7 | Models-STR.E | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 13:04 | 2018-01-07 13:05 | Yes | 7 |  | 2018-01-09 10:33 | [6 empty] | 2018-01-09 19:59 | Yes | -12
VD-9001-740A-MOD-00316 | 6 | Models-STR.G | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 13:01 | 2018-01-07 13:02 | Yes | 7 |  | 2018-01-09 10:48 | [6 empty] | 2018-01-09 19:59 | Yes | -12
VD-9001-740A-MOD-00112 | 5 | Models-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 12:54 | 2018-01-07 12:55 | Yes | 7 |  | 2018-01-09 10:39 | [6 empty] | 2018-01-09 19:59 | Yes | -12 | 1204-Owner-v | 2019-02-16 20:24
VD-9001-740A-GAD-00302 | 2 | General Arrangement Drawings-STR.B | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 15:56 | 2018-01-07 15:56 | Yes | 7 |  | 2018-01-08 14:37 | [6 empty] | 2018-01-08 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 09:13
VD-9001-740A-GAD-00112 | 2 | General Arrangement Drawings-STR.K | ST-740A | Pars Tadbir Gostar | 2017-12-31 | 2018-01-07 16:00 | 2018-01-07 16:00 | Yes | 7 |  | 2018-01-08 17:25 | [6 empty] | 2018-01-08 19:59 | Yes | -13 | 1204-Owner-v | 2020-04-25 09:10
VD-9001-105-DWG-501 | 7 | Gas-liquid separator drawings | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2017-12-31 | 2018-01-03 17:19 | 2018-01-03 17:20 | Yes | 3 |  | 2018-01-09 08:32 | [6 empty] | 2018-01-09 19:59 | Yes | -8 | 1204-Owner-v | 2019-09-06 22:04
VD-9001-108-INX-001 | 1 | Final Data Book Index | PR-108 | Farabard | 2018-01-14 19:59 | 2018-01-03 14:53 | 2018-01-03 14:54 | Yes | -11 |  | 2018-01-07 11:11 | [6 empty] | 2018-01-07 19:59 | Yes | -10
VD-9001-104-DSH-011 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-14 19:59 | 2018-01-04 13:01 |  | No | -10 | 2018-01-15 16:37 | [7 empty] | 2018-01-15 19:59 | Yes | 0
VD-9001-740A-MOD-00088 | 6 | Models-PIPE RACK ZONE 11 | ST-740A | Pars Tadbir Gostar | 2018-01-01 | 2018-01-07 12:52 | 2018-01-07 12:53 | Yes | 6 |  | 2018-01-09 10:53 | [6 empty] | 2018-01-09 19:59 | Yes | -12
VD-9001-740A-MOD-00085 | 6 | Models-STAIR FOR PIPE RACK (ZONE 1 TO 5) | ST-740A | Pars Tadbir Gostar | 2018-01-01 | 2018-01-07 12:42 | 2018-01-07 12:43 | Yes | 6 |  | 2018-01-10 18:39 | [6 empty] | 2018-01-10 19:59 | Yes | -11 | 1204-Owner-v | 2019-04-12 13:45
VD-9001-740A-MOD-00086 | 4 | Models-STAIR FOR PIPE RACK (ZONE 6 TO 9) | ST-740A | Pars Tadbir Gostar | 2018-01-01 | 2018-01-07 12:48 | 2018-01-07 12:49 | Yes | 6 |  | 2018-01-10 18:41 | [6 empty] | 2018-01-10 19:59 | Yes | -11 | 1204-Owner-v | 2019-03-26 11:21
VD-9001-251-DSH-009 | 1 | PROCESS DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-01 | 2018-08-10 14:44 | 2018-08-10 14:48 | Yes | 221 |  |  |  | 2018-09-03 16:13 |  |  |  |  | 2018-09-03 16:13 | Yes | 10 | 1204-Owner-v | 2018-08-16 11:21
VD-9001-251-DSH-010 | 1 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-02 | 2018-08-10 18:07 | 2018-08-10 18:12 | Yes | 220 |  |  |  |  | 2018-09-04 17:12 |  |  |  | 2018-09-04 17:12 | Yes | 11
VD-9001-251-DSH-011 | 1 | PROCESS DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-02 | 2018-08-10 18:12 | 2018-08-10 18:12 | Yes | 220 |  |  |  |  | 2018-09-04 17:25 |  |  |  | 2018-09-04 17:25 | Yes | 11
VD-9001-740A-MOD-00353 | 8 | Models-STR.F | ST-740A | Pars Tadbir Gostar | 2018-01-02 | 2018-01-07 13:11 | 2018-01-07 13:12 | Yes | 5 |  | 2018-01-09 10:25 | [6 empty] | 2018-01-09 19:59 | Yes | -12
VD-9001-104-PCJ-004 | 1 | Painting specification & procedure | PR-104 | AIR LIQUIDE | 2018-01-16 19:59 |  |  | No | 885 | [9 empty] | No | 0
VD-9001-254-ARP-552 | 1 | STRESS ANALYSIS OF FEED WATER LINE | HM-254 | AZAR AB | 2018-01-16 19:59 | 2018-10-06 11:38 | 2018-10-06 11:38 | Yes | 263 |  |  | 2018-10-22 11:21 | [5 empty] | 2018-10-22 11:21 | Yes | 2
VD-9001-105-WPS-701 | 3 | WPS & PQR for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-01-03 09:10 | 2018-01-10 18:22 | 2018-01-10 18:23 | Yes | 7 |  | 2018-01-27 09:25 | [6 empty] | 2018-01-27 20:00 | Yes | 3
VD-9001-104-DCR-002 | 0 | Civil and structure design criteria | PR-104 | AIR LIQUIDE | 2017-12-16 | 2018-01-05 13:26 |  | No | 20 | 2018-01-29 14:41 | [7 empty] | 2018-01-29 20:00 | Yes | 0
VD-9001-104-DSH-062 | 0 | EQUIPMENT DATA SHEET FOR VENT STRAINER DR-6101A-FT / DR-6101B-FT | PR-104 | AIR LIQUIDE | 2017-12-16 |  |  | No | 916 | [9 empty] | No | 0
VD-9001-104-REQ-016 | 2 | DR-6101A&B_TRS Technical Requisition Sheet Adsorber | PR-104 | AIR LIQUIDE | 2018-01-20 19:59 |  |  | No | 881 | [9 empty] | No | 0
VD-9001-104-LST-004 | 1 | Spare parts list for erection, precommissioning, commissiong and start-up | PR-104 | AIR LIQUIDE | 2018-01-20 19:59 |  |  | No | 881 | [9 empty] | No | 0
VD-9001-201-WBK-003 | 1 | WELDING DATA BOOK FOR SKIRT AND EXTERNAL ATTACHMENT | PV-201 | ATB RIVA CALZONI SpA | 2018-01-09 16:08 | 2018-01-09 16:27 | 2018-01-09 16:28 | Yes | 0 |  | 2018-01-29 11:48 | [6 empty] | 2018-01-29 20:00 | Yes | 6 | 1204-Owner-v | 2018-12-16 21:40
VD-9001-460A-PCJ-001 | 0 | Application procedure for coating & wrapping | PI-460A | Nia Shimi Co. | 2018-01-19 | 2018-01-11 11:17 |  | No | -8 | 2018-01-21 08:50 | [7 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-460A-ITP-001 | 0 | Inspection Test Plan | PI-460A | Nia Shimi Co. | 2018-01-19 | 2018-01-11 11:09 |  | No | -8 | 2018-01-21 08:52 | [7 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-460A-INX-001 | 0 | Final Data Book Index | PI-460A | Nia Shimi Co. | 2018-01-19 | 2018-01-14 10:51 |  | No | -5 | 2018-01-15 17:37 | [7 empty] | 2018-01-15 19:59 | Yes | 0
VD-9001-460A-PCJ-002 | 0 | Packing and Marking Procedure | PI-460A | Nia Shimi Co. | 2018-01-19 | 2018-01-11 11:28 |  | No | -8 | 2018-01-21 08:43 | [7 empty] | 2018-01-21 19:59 | Yes | 0
VD-9001-257C-DIS-001 | 0 | SUPPLIER DOCUMENT LIST (VDIS) (4137/LD) | HM-257C | Brembana & Rolle S.p.A. | 2017-11-23 |  |  | No | 939 | [9 empty] | No | 0
VD-9001-257C-INX-001 | 0 | MANUFACTURER DATA REPORT INDEX (4137/ED) | HM-257C | Brembana & Rolle S.p.A. | 2017-12-27 | 2018-03-23 14:40 | 2018-03-23 14:54 | Yes | 86 |  |  |  |  | 2018-04-22 10:06 |  |  |  | 2018-04-22 10:06 | Yes | 16
VD-9001-257C-PCJ-001 | 0 | HYDROSTATIC PROCEDURE (4137/HT) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-03-23 15:16 | 2018-03-23 15:16 | Yes | 44 |  |  |  |  | 2018-04-21 11:32 |  |  |  | 2018-04-21 11:32 | Yes | 15
VD-9001-257C-MNL-001 | 0 | INSTRUCTION OPERATING MANUAL (4137/IOM) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-05-21 13:01 | 2018-05-21 13:02 | Yes | 103 |  |  |  |  | 2018-08-05 14:34 |  |  |  | 2018-08-05 14:34 | Yes | 62
VD-9001-257C-PCJ-002 | 0 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-03-23 15:20 | 2018-03-23 15:20 | Yes | 44 |  |  |  | 2018-04-21 11:35 |  |  |  |  | 2018-04-21 11:35 | Yes | 15
VD-9001-257C-PCJ-005 | 0 | NITROGEN PURGING (4137/N) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:17 | 2018-06-04 19:17 | Yes | 117 |  |  |  |  | 2018-06-23 11:39 |  |  |  | 2018-06-23 11:39 | Yes | 5 | 1204-Owner-v | 2018-12-11 16:23
VD-9001-257C-PCJ-003 | 0 | SURFACE PREPARATION AND PAINTING PROCEDURE (4137/SP) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-07-12 14:43 | 2018-07-12 14:44 | Yes | 155 |  |  |  |  | 2018-08-05 14:30 |  |  |  | 2018-08-05 14:30 | Yes | 10
VD-9001-257C-PCJ-004 | 0 | POST WELD HEAT TREATMENT PROCEDURE (4137/PWHT) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-08-08 19:53 | 2018-08-08 19:53 | Yes | 182 |  |  | 2018-09-08 11:12 | [5 empty] | 2018-09-08 11:12 | Yes | 17
VD-9001-257C-LST-001 | 0 | COMMISSIONING & START-UP S.P.LIST (4137/SPL1) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-13 12:39 | 2018-06-13 12:39 | Yes | 126 |  |  | 2018-09-13 13:15 | [5 empty] | 2018-09-13 13:15 | Yes | 78
VD-9001-257C-LST-002 | 0 | 2 YEARS OPERATION S.P.LIST (4137/SPL2) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 |  |  | No | 863 | [9 empty] | No | 0
VD-9001-257C-FDB-001 | 0 | MANUFACTURING DATA BOOK (0641/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-05-19 11:43 | 2020-05-19 11:48 | Yes | 832 |  |  |  | 2020-06-04 12:37 |  |  |  |  | 2020-06-04 12:37 | Yes | 2
VD-9001-257C-GAD-001 | 0 | GENERAL ARRANGEMENT (4137-0364) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:18 |  | No | -13 | 2018-02-18 12:21 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-257C-DWG-001 | 0 | DETAILS DRAWING (4137-0364/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:27 |  | No | -13 | 2018-02-18 12:14 | [7 empty] | 2018-02-18 20:00 | Yes | 0 | 1204-Owner-v | 2019-07-02 08:56
VD-9001-257C-DWG-002 | 0 | DETAILS DRAWING (4137-0364/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:30 |  | No | -13 | 2018-02-18 16:00 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-257C-DWG-003 | 0 | NAME PLATE DET.DWG (4137-0364/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:09 |  | No | -7 | 2018-02-18 15:17 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-257C-DWG-004 | 0 | GASKET DETAIL DWG (4137-0364/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:32 | 2018-02-05 13:33 | Yes | -2 | 2018-02-22 16:58 | [7 empty] | 2018-02-22 20:00 | Yes | 3 | 1204-Owner-v | 2019-05-10 09:19
VD-9001-257C-ITP-001 | 0 | INSPECTION & TESTING PLAN (4137-0364/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:32 | 2018-03-09 11:43 | Yes | 58 |  |  |  | 2018-03-25 10:34 |  |  |  |  | 2018-03-25 10:34 | Yes | 2
VD-9001-257C-CAL-001 | 0 | MECHANICAL CALCULATION (4137-0364/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:24 |  | No | -13 | 2018-02-18 17:25 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-257C-DWG-005 | 0 | SHIPPING DRAWING (4137-0364/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:18 | 2018-06-04 19:18 | Yes | 117 |  |  | 2018-06-05 15:56 | [5 empty] | 2018-06-05 15:56 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:02
VD-9001-257C-DWG-006 | 0 | PAINTING PLAN (4137-0364/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:43 | 2018-05-28 14:43 | Yes | 124 |  |  |  | 2018-07-22 10:18 |  |  |  |  | 2018-07-22 10:18 | Yes | 41
VD-9001-257C-WBK-001 | 0 | WELDING BOOK (4137-0364/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-31 18:45 |  | No | 21 | 2018-02-10 11:45 | [7 empty] | 2018-02-10 20:00 | Yes | 0
VD-9001-257C-FDB-002 | 0 | MANUFACTURING DATA BOOK (0642/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-05-19 12:04 | 2020-05-19 12:15 | Yes | 832 |  |  |  | 2020-06-06 12:01 |  |  |  |  | 2020-06-06 12:01 | Yes | 4
VD-9001-257C-GAD-002 | 0 | GENERAL ARRANGEMENT (4137-0365) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:19 |  | No | -13 | 2018-02-04 09:13 | [7 empty] | 2018-02-04 19:59 | Yes | 0
VD-9001-257C-DWG-007 | 0 | DETAILS DRAWING (4137-0365/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:32 |  | No | -13 | 2018-02-04 15:44 | [7 empty] | 2018-02-04 20:00 | Yes | 0
VD-9001-257C-DWG-008 | 0 | DETAILS DRAWING (4137-0365/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:33 |  | No | -13 |  |  |  |  | 2018-03-27 10:19 |  |  |  | 2018-03-27 10:19 | Yes | 0
VD-9001-257C-DWG-009 | 0 | NAME PLATE DET.DWG (4137-0365/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:10 |  | No | -7 | 2018-02-08 16:57 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-010 | 0 | GASKET DETAIL DWG (4137-0365/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:33 | 2018-02-05 13:34 | Yes | -2 | 2018-02-22 17:02 | [7 empty] | 2018-02-22 20:00 | Yes | 3 | 1204-Owner-v | 2019-05-10 09:21
VD-9001-257C-ITP-002 | 0 | INSPECTION & TESTING PLAN (4137-0365/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:44 | 2018-03-09 11:48 | Yes | 58 |  |  |  | 2018-03-25 10:10 |  |  |  |  | 2018-03-25 10:10 | Yes | 2
VD-9001-257C-CAL-002 | 0 | MECHANICAL CALCULATION (4137-0365/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:25 |  | No | -13 | 2018-02-04 15:25 | [7 empty] | 2018-02-04 20:00 | Yes | 0
VD-9001-257C-DWG-011 | 0 | SHIPPING DRAWING (4137-0365/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:18 | 2018-06-04 19:18 | Yes | 117 |  |  | 2018-06-05 16:12 | [5 empty] | 2018-06-05 16:12 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:12
VD-9001-257C-DWG-012 | 0 | PAINTING PLAN (4137-0365/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:44 | 2018-05-28 14:44 | Yes | 124 |  |  |  | 2018-07-17 11:13 |  |  |  |  | 2018-07-17 11:13 | Yes | 36
VD-9001-257C-WBK-002 | 0 | WELDING BOOK (4137-0365/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-29 13:44 |  | No | 19 | 2018-02-10 11:48 | [7 empty] | 2018-02-10 20:00 | Yes | 0
VD-9001-257C-FDB-003 | 0 | MANUFACTURING DATA BOOK (0643/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-02-27 17:55 | 2020-02-27 17:59 | Yes | 750 |  |  |  | 2020-04-25 17:24 |  |  |  |  | 2020-04-25 17:24 | Yes | 44
VD-9001-257C-GAD-003 | 0 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:54 |  | No | -7 |  |  |  |  | 2018-03-19 17:47 |  |  |  | 2018-03-19 17:47 | Yes | 0
VD-9001-257C-DWG-013 | 0 | DETAILS DRAWING (4137-0366/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:46 |  | No | -7 |  |  |  |  | 2018-04-18 16:43 |  |  |  | 2018-04-18 16:43 | Yes | 0 | 1204-Owner-v | 2019-07-02 09:12
VD-9001-257C-DWG-014 | 0 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 14:30 |  | No | 1 |  |  |  |  | 2018-03-19 17:59 |  |  |  | 2018-03-19 17:59 | Yes | 0
VD-9001-257C-DWG-015 | 0 | NAME PLATE DET.DWG (4137-0366/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:10 |  | No | -7 |  |  |  | 2018-03-13 09:05 |  |  |  |  | 2018-03-13 09:05 | Yes | 0
VD-9001-257C-DWG-016 | 0 | GASKET DETAIL DWG (4137-0366/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:33 | 2018-02-05 13:34 | Yes | -2 |  |  |  | 2018-03-19 18:01 |  |  |  |  | 2018-03-19 18:01 | Yes | 28 | 1204-Owner-v | 2019-05-10 09:24
VD-9001-257C-ITP-003 | 0 | INSPECTION & TESTING PLAN (4137-0366/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:44 | 2018-03-09 11:48 | Yes | 58 |  |  |  | 2018-03-25 10:17 |  |  |  |  | 2018-03-25 10:17 | Yes | 2
VD-9001-257C-CAL-003 | 0 | MECHANICAL CALCULATION (4137-0366/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:55 |  | No | -7 |  |  |  |  | 2018-03-19 17:52 |  |  |  | 2018-03-19 17:52 | Yes | 0
VD-9001-257C-DWG-017 | 0 | SHIPPING DRAWING (4137-0366/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:19 | 2018-06-04 19:19 | Yes | 117 |  |  | 2018-06-05 16:10 | [5 empty] | 2018-06-05 16:10 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:13
VD-9001-257C-DWG-018 | 0 | PAINTING PLAN (4137-0366/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:44 | 2018-05-28 14:44 | Yes | 124 |  |  |  | 2018-07-22 09:57 |  |  |  |  | 2018-07-22 09:57 | Yes | 41
VD-9001-257C-WBK-003 | 0 | WELDING BOOK (4137-0366/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-31 18:52 |  | No | 21 |  |  |  | 2018-03-12 11:03 |  |  |  |  | 2018-03-12 11:03 | Yes | 0
VD-9001-257C-FDB-004 | 0 | MANUFACTURING DATA BOOK (0644/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-03-04 12:07 | 2020-03-04 12:11 | Yes | 756 |  |  |  | 2020-04-25 17:23 |  |  |  |  | 2020-04-25 17:23 | Yes | 38
VD-9001-257C-GAD-004 | 0 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:46 |  | No | -7 |  |  |  |  | 2018-03-19 16:47 |  |  |  | 2018-03-19 16:47 | Yes | 0
VD-9001-257C-DWG-019 | 0 | DETAILS DRAWING (4137-0367/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:44 |  | No | -7 |  |  |  |  | 2018-04-18 17:00 |  |  |  | 2018-04-18 17:00 | Yes | 0
VD-9001-257C-DWG-020 | 0 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 14:32 |  | No | 1 |  |  |  |  | 2018-03-19 16:51 |  |  |  | 2018-03-19 16:51 | Yes | 0
VD-9001-257C-DWG-021 | 0 | NAME PLATE DET.DWG (4137-0367/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:11 |  | No | -7 |  |  |  | 2018-03-17 09:13 |  |  |  |  | 2018-03-17 09:13 | Yes | 0
VD-9001-257C-DWG-022 | 0 | GASKET DETAIL DWG (4137-0367/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:34 | 2018-02-05 13:35 | Yes | -2 |  |  |  | 2018-03-19 17:04 |  |  |  |  | 2018-03-19 17:04 | Yes | 28 | 1204-Owner-v | 2019-05-10 09:24
VD-9001-257C-ITP-004 | 0 | INSPECTION & TESTING PLAN (4137-0367/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:49 | 2018-03-09 11:56 | Yes | 58 |  |  |  | 2018-03-25 10:19 |  |  |  |  | 2018-03-25 10:19 | Yes | 2
VD-9001-257C-CAL-004 | 0 | MECHANICAL CALCULATION (4137-0367/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 12:59 |  | No | -7 |  |  |  |  | 2018-03-19 17:21 |  |  |  | 2018-03-19 17:21 | Yes | 0
VD-9001-257C-DWG-023 | 0 | SHIPPING DRAWING (4137-0367/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:19 | 2018-06-04 19:19 | Yes | 117 |  |  |  |  | 2018-06-05 16:08 |  |  |  | 2018-06-05 16:08 | Yes | -13
VD-9001-257C-DWG-024 | 0 | PAINTING PLAN (4137-0367/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:45 | 2018-05-28 14:45 | Yes | 124 |  |  |  | 2018-07-22 09:46 |  |  |  |  | 2018-07-22 09:46 | Yes | 41
VD-9001-257C-WBK-004 | 0 | WELDING BOOK (4137-0367/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-02-02 11:50 |  | No | 23 |  |  |  | 2018-03-12 10:54 |  |  |  |  | 2018-03-12 10:54 | Yes | 0
VD-9001-257C-FDB-005 | 0 | MANUFACTURING DATA BOOK (0645/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-05-19 12:40 | 2020-05-19 12:53 | Yes | 832 |  |  |  | 2020-06-07 11:25 |  |  |  |  | 2020-06-07 11:25 | Yes | 5
VD-9001-257C-GAD-005 | 0 | GENERAL ARRANGEMENT (4137-0368) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:19 |  | No | -13 |  |  |  |  | 2018-03-17 09:29 |  |  |  | 2018-03-17 20:00 | Yes | 0
VD-9001-257C-DWG-025 | 0 | DETAILS DRAWING (4137-0368/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:33 |  | No | -13 |  |  |  |  | 2018-03-13 16:41 |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-257C-DWG-026 | 0 | DETAILS DRAWING (4137-0368/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:34 |  | No | -13 |  |  |  |  | 2018-03-13 16:59 |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-257C-DWG-027 | 0 | NAME PLATE DET.DWG (4137-0368/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:11 |  | No | -7 |  |  |  | 2018-03-13 16:19 |  |  |  |  | 2018-03-13 16:19 | Yes | 0
VD-9001-257C-ITP-005 | 0 | INSPECTION & TESTING PLAN (4137-0368/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-05-22 17:50 | 2018-05-22 17:50 | Yes | 132 |  |  |  |  | 2018-06-19 14:46 |  |  |  | 2018-06-19 14:46 | Yes | 14
VD-9001-257C-CAL-005 | 0 | MECHANICAL CALCULATION (4137-0368/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:26 |  | No | -13 |  |  |  |  | 2018-03-13 16:22 |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-257C-DWG-029 | 0 | SHIPPING DRAWING (4137-0368/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:20 | 2018-06-04 19:20 | Yes | 117 |  |  | 2018-06-05 16:04 | [5 empty] | 2018-06-05 16:04 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:15
VD-9001-257C-DWG-030 | 0 | PAINTING PLAN (4137-0368/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:45 | 2018-05-28 14:45 | Yes | 124 |  |  |  | 2018-07-22 09:50 |  |  |  |  | 2018-07-22 09:50 | Yes | 41
VD-9001-257C-WBK-005 | 0 | WELDING BOOK (4137-0368/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-06-22 18:45 | 2018-06-22 18:48 | Yes | 163 |  |  |  |  | 2018-08-04 11:53 |  |  |  | 2018-08-04 11:53 | Yes | 29
VD-9001-257C-FDB-006 | 0 | MANUFACTURING DATA BOOK (0646/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-05-19 13:14 | 2020-05-19 13:16 | Yes | 832 |  |  |  | 2020-06-07 11:42 |  |  |  |  | 2020-06-07 11:42 | Yes | 5
VD-9001-257C-GAD-006 | 0 | GENERAL ARRANGEMENT (4137-0369) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:16 |  | No | -13 | 2018-02-08 15:33 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-031 | 0 | DETAILS DRAWING (4137-0369/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:23 |  | No | -13 | 2018-02-08 15:36 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-032 | 0 | DETAILS DRAWING (4137-0369/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:23 |  | No | -13 | 2018-02-08 15:37 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-033 | 0 | NAME PLATE DET.DWG (4137-0369/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:12 |  | No | -7 | 2018-02-08 15:49 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-034 | 0 | GASKET DETAIL DWG (4137-0369/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:34 | 2018-02-05 13:35 | Yes | -2 | 2018-02-22 16:47 | [7 empty] | 2018-02-22 20:00 | Yes | 3 | 1204-Owner-v | 2019-05-10 09:24
VD-9001-257C-ITP-006 | 0 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:56 | 2018-03-09 11:59 | Yes | 58 |  |  |  | 2018-03-25 10:21 |  |  |  |  | 2018-03-25 10:21 | Yes | 2
VD-9001-257C-CAL-006 | 0 | MECHANICAL CALCULATION (4137-0369/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:13 |  | No | -13 | 2018-02-08 15:41 | [7 empty] | 2018-02-08 20:00 | Yes | 0
VD-9001-257C-DWG-035 | 0 | SHIPPING DRAWING (4137-0369/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:20 | 2018-06-04 19:20 | Yes | 117 |  |  | 2018-06-05 16:02 | [5 empty] | 2018-06-05 16:02 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:17
VD-9001-257C-DWG-036 | 0 | PAINTING PLAN (4137-0369/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:46 | 2018-05-28 14:46 | Yes | 124 |  |  |  | 2018-07-22 09:45 |  |  |  |  | 2018-07-22 09:45 | Yes | 41
VD-9001-257C-WBK-006 | 0 | WELDING BOOK (4137-0369/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-29 17:58 |  | No | 19 |  |  |  | 2018-03-12 10:47 |  |  |  |  | 2018-03-12 10:47 | Yes | 0
VD-9001-257C-FDB-007 | 0 | MANUFACTURING DATA BOOK (0647/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-02-25 14:11 | 2020-02-25 14:27 | Yes | 748 |  |  | 2020-04-25 17:38 | [5 empty] | 2020-04-25 17:38 | Yes | 46
VD-9001-257C-DWG-037 | 0 | NAME PLATE DET.DWG (4137-0370/A1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:12 |  | No | -7 | 2018-02-22 18:56 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-257C-GAD-007 | 0 | GENERAL ARRANGEMENT (4137-0370) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:17 |  | No | -13 | 2018-02-22 18:30 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-257C-DWG-038 | 0 | DETAILS DRAWING (4137-0370/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:24 |  | No | -13 | 2018-02-25 10:23 | [7 empty] | 2018-02-25 19:59 | Yes | 0
VD-9001-257C-DWG-039 | 0 | DETAILS DRAWING (4137-0370/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:24 |  | No | -13 | 2018-02-25 09:25 | [7 empty] | 2018-02-25 19:59 | Yes | 0
VD-9001-257C-DWG-040 | 0 | GASKET DETAIL DWG (4137-0370/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:41 | 2018-02-05 13:42 | Yes | -2 | 2018-02-25 09:20 | [7 empty] | 2018-02-25 19:59 | Yes | 3 | 1204-Owner-v | 2019-05-10 09:24
VD-9001-257C-ITP-007 | 0 | INSPECTION & TESTING PLAN (4137-0370/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:57 | 2018-03-09 11:59 | Yes | 58 |  |  |  | 2018-03-25 10:24 |  |  |  |  | 2018-03-25 10:24 | Yes | 2
VD-9001-257C-CAL-007 | 0 | MECHANICAL CALCULATION (4137-0370/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:14 |  | No | -13 | 2018-02-25 09:40 | [7 empty] | 2018-02-25 19:59 | Yes | 0
VD-9001-257C-DWG-041 | 0 | SHIPPING DRAWING (4137-0370/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:21 | 2018-06-04 19:21 | Yes | 117 |  |  | 2018-06-05 16:01 | [5 empty] | 2018-06-05 16:01 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:18
VD-9001-257C-DWG-042 | 0 | PAINTING PLAN (4137-0370/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:46 | 2018-05-28 14:46 | Yes | 124 |  |  |  | 2018-07-22 09:42 |  |  |  |  | 2018-07-22 09:42 | Yes | 41
VD-9001-257C-WBK-007 | 0 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-29 16:49 |  | No | 19 |  |  |  | 2018-03-12 10:43 |  |  |  |  | 2018-03-12 20:00 | Yes | 0
VD-9001-257C-FDB-008 | 0 | MANUFACTURING DATA BOOK (0648/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-02-26 17:06 | 2020-02-26 17:10 | Yes | 749 |  |  | 2020-04-25 17:39 | [5 empty] | 2020-04-25 17:39 | Yes | 45
VD-9001-257C-DWG-043 | 0 | NAME PLATE DET.DWG (4137-0370/A2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-17 17:12 |  | No | -7 | 2018-02-22 19:01 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-257C-FDB-009 | 0 | MANUFACTURING DATA BOOK (0649/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-05-19 13:46 | 2020-05-19 13:50 | Yes | 832 |  |  |  | 2020-06-08 11:22 |  |  |  |  | 2020-06-08 11:22 | Yes | 6
VD-9001-257C-GAD-008 | 0 | GENERAL ARRANGEMENT (4137-0371) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:18 |  | No | -13 |  |  |  |  | 2018-03-07 15:14 |  |  |  | 2018-03-07 20:00 | Yes | 0
VD-9001-257C-DWG-044 | 0 | DETAILS DRAWING (4137-0371/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:27 |  | No | -13 |  |  |  |  | 2018-03-07 15:05 |  |  |  | 2018-03-07 20:00 | Yes | 0
VD-9001-257C-DWG-045 | 0 | DETAILS DRAWING (4137-0371/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:28 |  | No | -13 |  |  |  |  | 2018-03-27 11:06 |  |  |  | 2018-03-27 11:06 | Yes | 0
VD-9001-257C-DWG-046 | 0 | NAME PLATE DET.DWG (4137-0371/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-15 16:01 | 2018-05-15 16:01 | Yes | 111 |  |  |  | 2018-05-17 11:36 |  |  | 2018-03-06 15:52 | 2018-03-06 15:52 | 2018-05-17 11:36 | Yes | -12
VD-9001-257C-DWG-047 | 0 | GASKET DETAIL DWG (4137-0371/G) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-05 13:42 | 2018-02-05 13:43 | Yes | -2 |  |  |  |  | 2018-03-07 15:09 |  |  |  | 2018-03-07 20:00 | Yes | 16 | 1204-Owner-v | 2019-05-10 09:24
VD-9001-257C-ITP-008 | 0 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-03-09 11:57 | 2018-03-09 11:57 | Yes | 58 |  |  |  | 2018-03-19 17:15 |  |  |  |  | 2018-03-19 17:15 | Yes | -4
VD-9001-257C-CAL-008 | 0 | MECHANICAL CALCULATION (4137-0371/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:15 |  | No | -13 |  |  |  |  | 2018-03-07 15:16 |  |  |  | 2018-03-07 20:00 | Yes | 0
VD-9001-257C-DWG-048 | 0 | SHIPPING DRAWING (4137-0371/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-04 19:21 | 2018-06-04 19:21 | Yes | 117 |  |  | 2018-06-05 15:59 | [5 empty] | 2018-06-05 15:59 | Yes | -13 | 1204-Owner-v | 2018-08-04 13:26
VD-9001-257C-DWG-049 | 0 | PAINTING PLAN (4137-0371/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-05-28 14:47 | 2018-05-28 14:47 | Yes | 124 |  |  |  |  | 2018-06-23 11:42 |  |  |  | 2018-06-23 11:42 | Yes | 12
VD-9001-257C-WBK-008 | 0 | WELDING BOOK (4137-0371/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-29 16:52 |  | No | 19 |  |  |  | 2018-03-11 14:29 |  |  |  |  | 2018-03-11 20:00 | Yes | 0
VD-9001-257C-PCJ-006 | 0 | PICKLING & PASSIVATION PROCEDURE (4137/PKP) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2019-04-02 14:08 | 2019-04-02 14:10 | Yes | 419 |  |  | 2019-05-19 10:26 | [5 empty] | 2019-05-19 10:26 | Yes | 33
VD-9001-257C-LST-003 | 0 | FIELD CONSUMABLE LIST (4137/FCL) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-06-16 11:21 | 2020-06-16 11:23 | Yes | 860 | [9 empty] | No | -11
VD-9001-257C-DWG-050 | 0 | DETAILS DRAWING (4137-0370/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-02-22 12:43 |  | No | 29 |  |  |  |  | 2018-05-08 15:44 |  |  |  | 2018-05-08 15:44 | Yes | 0
VD-9001-257C-DWG-051 | 0 | DETAILS DRAWING (4137-0371/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-02-22 12:45 |  | No | 29 |  |  |  |  | 2018-03-27 17:13 |  |  |  | 2018-03-27 17:13 | Yes | 0
VD-9001-257C-DWG-052 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0364/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:31 |  | No | -13 | 2018-02-18 10:16 | [7 empty] | 2018-02-18 19:59 | Yes | 0
VD-9001-257C-DWG-053 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0365/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:31 |  | No | -13 | 2018-02-04 15:50 | [7 empty] | 2018-02-04 20:00 | Yes | 0
VD-9001-257C-DWG-054 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0366/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 14:30 |  | No | 1 |  |  |  | 2018-03-19 17:54 |  |  |  |  | 2018-03-19 17:54 | Yes | 0
VD-9001-257C-DWG-055 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0367/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 14:31 |  | No | 1 |  |  |  | 2018-03-19 16:49 |  |  |  |  | 2018-03-19 16:49 | Yes | 0
VD-9001-257C-DWG-056 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0368/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 14:31 |  | No | -13 |  |  |  |  | 2018-03-13 17:03 |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-257C-DWG-057 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0369/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:18 |  | No | -13 |  |  |  |  | 2018-03-12 11:38 |  |  |  | 2018-03-12 11:38 | Yes | 0
VD-9001-257C-DWG-058 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0370/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:19 |  | No | -13 | 2018-02-22 19:15 | [7 empty] | 2018-02-22 20:00 | Yes | 0
VD-9001-257C-DWG-059 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4137-0371/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-11 16:22 |  | No | -13 |  |  |  |  | 2018-03-07 15:12 |  |  |  | 2018-03-07 20:00 | Yes | 0
VD-9001-257C-PCJ-007 | 0 | FIELD TEST PROCEDURE (4137/MP1) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-07 | 2020-06-12 15:10 | 2020-06-12 15:12 | Yes | 767 |  |  |  | 2020-06-15 11:33 |  |  |  |  | 2020-06-15 11:33 | Yes | -11
VD-9001-257C-PCJ-008 | 0 | WELD OVERLAY PROCEDURE (4137/WO) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 |  |  | No | 863 | [9 empty] | No | 0
VD-9001-108-DWG-044 | 2 | FABRICATION/ERECTION DRAWING | PR-108 | Farabard | 2018-01-13 15:49 | 2018-01-14 10:54 | 2018-01-14 10:49 | Yes | 1 |  | 2018-01-14 14:25 | [6 empty] | 2018-01-14 19:59 | Yes | -14
VD-9001-460A-DSH-001 | 0 | Data Sheet for Coating & Wrapping | PI-460A | Nia Shimi Co. | 2018-01-13 | 2018-01-14 10:50 |  | No | 1 | 2018-01-14 15:46 | [7 empty] | 2018-01-14 19:59 | Yes | 0
VD-9001-460A-DSH-001 | 1 | Data Sheet for Coating & Wrapping | PI-460A | Nia Shimi Co. | 2018-01-14 | 2018-01-17 15:37 | 2018-01-17 15:38 | Yes | 3 |  | 2018-01-20 08:29 | [6 empty] | 2018-01-20 19:59 | Yes | -11
VD-9001-254-DWG-330 | 2 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2018-01-28 19:59 | 2018-08-28 12:25 | 2018-08-28 12:27 | Yes | 212 |  |  |  |  | 2018-10-22 11:51 |  |  |  | 2018-10-22 11:51 | Yes | 41 | 1204-Owner-v | 2018-11-26 13:41
VD-9001-254-PPL-358 | 2 | LAYOUT & TYPICAL WIRING FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-01-28 19:59 | 2018-05-22 09:15 | 2018-05-22 09:15 | Yes | 114 |  |  | 2018-06-03 11:21 | [5 empty] | 2018-06-03 11:21 | Yes | -2 | 1204-Owner-v | 2019-05-13 09:08
VD-9001-254-DPH-345 | 2 | CONTROL SYSTEM ARCHITECTURE | HM-254 | AZAR AB | 2018-01-28 19:59 | 2018-05-12 13:41 | 2018-05-12 13:41 | Yes | 104 |  |  | 2018-06-03 11:24 | [5 empty] | 2018-06-03 11:24 | Yes | 8 | 1204-Owner-v | 2019-12-09 08:29
VD-9001-254-PPL-359 | 2 | LAYOUT & TYPICAL WIRING FOR BMS | HM-254 | AZAR AB | 2018-01-28 19:59 | 2018-05-12 13:15 | 2018-05-12 13:16 | Yes | 104 |  |  |  | 2018-06-03 11:28 |  |  |  |  | 2018-06-03 11:28 | Yes | 8
VD-9001-254-PPL-360 | 2 | LAYOUT & TYPICAL WIRING FOR LBSP | HM-254 | AZAR AB | 2018-01-28 19:59 | 2018-05-12 13:27 | 2018-05-12 13:33 | Yes | 104 |  |  | 2018-06-03 11:26 | [5 empty] | 2018-06-03 11:26 | Yes | 8
VD-9001-460A-INX-001 | 1 | Final Data Book Index | PI-460A | Nia Shimi Co. | 2018-01-15 | 2018-01-17 15:40 | 2018-01-17 15:41 | Yes | 2 |  | 2018-01-22 08:30 | [6 empty] | 2018-01-22 19:58 | Yes | -9
VD-9001-104-DSH-011 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-29 19:59 | 2018-03-26 17:33 | 2018-03-26 17:36 | Yes | 56 |  |  |  | 2018-04-10 14:38 |  |  |  |  | 2018-04-10 20:00 | Yes | 1
VD-9001-104-DSH-012 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-01-29 19:59 | 2018-02-09 18:50 |  | No | 11 | 2018-02-21 15:59 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-251-CAL-001 | 1 | MECHANICAL CALCULATION CATALYST TUBE | HM-251 | KT – Kinetics Technology SpA | 2018-01-16 | 2018-05-30 17:26 | 2018-05-30 17:27 | Yes | 134 |  |  |  |  | 2018-06-03 15:17 |  |  |  | 2018-06-03 15:17 | Yes | -10
VD-9001-251-DSH-006 | 1 | DATA SHEET FOR AIR PREHEATER (E-4002) | HM-251 | KT – Kinetics Technology SpA | 2018-01-16 | 2018-08-10 11:48 | 2018-08-10 11:49 | Yes | 206 |  |  |  |  | 2018-08-14 16:19 |  |  |  | 2018-08-14 16:20 | Yes | -10 | 1204-Owner-v | 2019-04-06 07:41
VD-9001-204B-MSS-001 | 5 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2018-01-16 14:12 | 2018-01-16 16:05 |  | No | 0 |  | 2018-01-22 09:31 | [6 empty] | 2018-01-22 19:59 | Yes | 0 | 1204-Owner-v | 2018-04-25 12:30
VD-9001-104-PPL-001 | 1 | Plot plan - Top view | PR-104 | AIR LIQUIDE | 2018-01-31 19:59 | 2018-04-06 18:23 | 2018-04-06 18:25 | Yes | 65 |  |  |  | 2018-04-24 16:31 |  |  |  |  | 2018-04-24 20:00 | Yes | 4 | 1204-Owner-v | 2018-04-07 08:25
VD-9001-104-PPL-008 | 1 | Underground Piping plot plan (Basic Design) | PR-104 | AIR LIQUIDE | 2018-01-31 19:59 |  |  | No | 870 | [9 empty] | No | 0
VD-9001-204C-MSS-036 | 0 | MATERIAL SPECIFICATION FOR FORGINGS | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-01-20 | 2018-01-22 14:52 |  | No | 2 | 2018-01-28 10:20 | [7 empty] | 2018-01-28 20:00 | Yes | 0
VD-9001-204C-MSS-037 | 0 | MATERIAL SPECIFICATION FOR PLATES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-01-20 | 2018-01-22 14:53 |  | No | 2 | 2018-01-28 10:22 | [7 empty] | 2018-01-28 20:00 | Yes | 0
VD-9001-253(A)-RPT-114 | 1 | HSE INSTRUCTION | HM-253A | FATEH SANAT KIMIA | 2018-01-20 | 2018-01-25 09:11 | 2018-01-25 09:13 | Yes | 5 |  | 2018-01-30 11:17 | [6 empty] | 2018-01-30 20:00 | Yes | -9
VD-9001-251-CAL-011 | 1 | MECHANICAL CALCULATION - CONVECTION COILS | HM-251 | KT – Kinetics Technology SpA | 2018-01-20 | 2018-05-30 17:26 | 2018-05-30 17:28 | Yes | 130 |  |  |  | 2018-06-05 13:12 |  |  |  |  | 2018-06-05 13:12 | Yes | -8
VD-9001-201-DWG-002 | 2 | WELD DETAILS - ND EXAMINATION | PV-201 | ATB RIVA CALZONI SpA | 2018-01-20 10:14 | 2018-01-23 11:59 | 2018-01-23 12:00 | Yes | 3 |  | 2018-01-29 10:43 | [6 empty] | 2018-01-29 20:00 | Yes | -8 | 1204-Owner-v | 2018-12-16 21:34
VD-9001-201-DWG-004 | 2 | TEMPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2018-01-20 10:14 | 2018-01-23 11:59 | 2018-01-23 12:00 | Yes | 3 |  | 2018-01-29 11:14 | [6 empty] | 2018-01-29 20:00 | Yes | -8 | 1204-Owner-v | 2018-12-16 21:35
VD-9001-251-CAL-012 | 1 | MECHANICAL CALCULATION INLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-20 | 2018-05-30 17:26 | 2018-05-30 17:28 | Yes | 130 |  |  |  | 2018-06-05 13:21 |  |  |  |  | 2018-06-05 13:21 | Yes | -8
VD-9001-251-CAL-013 | 1 | MECHANICAL CALCULATION OUTLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-01-20 | 2018-05-30 17:34 | 2018-05-30 17:35 | Yes | 130 |  |  |  | 2018-06-05 13:29 |  |  |  |  | 2018-06-05 13:29 | Yes | -8
VD-9001-251-CAL-014 | 1 | MECHANICAL CALCULATION TRANSFER LINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-20 | 2018-03-29 13:22 | 2018-03-29 13:30 | Yes | 68 |  |  | 2018-04-07 14:41 | [5 empty] | 2018-04-07 14:41 | Yes | -5 | 1204-Owner-v | 2018-05-14 14:49
VD-9001-104-DSH-007 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-02-03 19:59 | 2018-02-09 18:16 |  | No | 6 | 2018-02-20 12:12 | [7 empty] | 2018-02-20 19:59 | Yes | 0 | 1204-Owner-v | 2018-02-19 14:52
VD-9001-740A-PRC-004 | 2 | Packing and Marking Procedure | ST-740A | Pars Tadbir Gostar | 2018-02-03 19:59 | 2018-01-21 08:28 | 2018-01-21 08:29 | Yes | -13 |  | 2018-01-22 15:59 | [6 empty] | 2018-01-22 19:59 | Yes | -13
VD-9001-460A-PCJ-002 | 1 | Packing and Marking Procedure | PI-460A | Nia Shimi Co. | 2018-01-21 | 2018-01-27 13:50 | 2018-01-27 13:51 | Yes | 6 |  | 2018-02-07 14:25 | [6 empty] | 2018-02-07 20:00 | Yes | -3
VD-9001-460A-PCJ-001 | 1 | Application procedure for coating & wrapping | PI-460A | Nia Shimi Co. | 2018-01-21 | 2018-02-17 10:22 |  | No | 27 | 2018-02-17 11:35 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-460A-ITP-001 | 1 | Inspection Test Plan | PI-460A | Nia Shimi Co. | 2018-01-21 | 2018-01-21 15:08 |  | No | 0 | 2018-01-27 15:34 | [7 empty] | 2018-01-27 20:00 | Yes | 0
VD-9001-201B-INX-001 | 0 | MANUFACTURER DATA REPORT INDEX (4134/ED) | PV-201B | Brembana & Rolle S.p.A. | 2017-12-27 | 2018-05-14 17:42 | 2018-05-14 17:42 | Yes | 138 |  |  |  | 2018-07-04 15:39 |  |  |  |  | 2018-07-04 20:00 | Yes | 37
VD-9001-201B-PCJ-001 | 0 | HYDROSTATIC PROCEDURE (4134/HT) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-01-22 18:21 |  | No | -16 | 2018-02-25 17:36 | [7 empty] | 2018-02-25 20:00 | Yes | 0
VD-9001-201B-MNL-001 | 0 | INSTRUCTION OPERATING MANUAL (4134/IOM) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-03-25 20:14 | 2020-03-25 20:14 | Yes | 777 |  |  |  | 2020-04-27 12:51 |  |  |  |  | 2020-04-27 20:59 | Yes | 19
VD-9001-201B-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE (4134/LD) | PV-201B | Brembana & Rolle S.p.A. | 2017-12-07 |  |  | No | 925 | [9 empty] | No | 0
VD-9001-201B-PCJ-002 | 0 | MANUFACTURING & NDE PROCEDURE (4134/MP) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-01-22 18:24 |  | No | -16 |  |  |  | 2018-03-11 16:38 |  |  |  |  | 2018-03-11 20:00 | Yes | 0
VD-9001-201B-PCJ-003 | 0 | NITROGEN PURGING (4134/N) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2020-03-31 12:56 | 2020-03-31 12:58 | Yes | 783 |  |  |  | 2020-04-18 09:13 |  |  |  |  | 2020-04-18 20:59 | Yes | 4
VD-9001-201B-PCJ-004 | 0 | SURFACE PREPARATION AND PAINTING PROCEDURE (4134/SP) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-07-24 16:54 | 2018-07-24 16:54 | Yes | 167 |  |  | 2018-08-20 18:40 | [5 empty] | 2018-08-20 19:59 | Yes | 13
VD-9001-201B-PCJ-005 | 0 | POST WELD HEAT TREATMENT PROCEDURE (4134/PWHT) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-02-14 11:42 |  | No | 7 | 2018-02-25 17:25 | [7 empty] | 2018-02-25 20:00 | Yes | 0
VD-9001-201B-LST-001 | 0 | COMMISSIONING & START-UP S.P.LIST (4134/SPL1) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-08-10 19:18 | 2018-08-10 19:18 | Yes | 184 |  |  |  | 2018-11-20 17:16 |  |  |  |  | 2018-11-20 20:00 | Yes | 88
VD-9001-201B-LST-002 | 0 | 2 YEARS OPERATION S.P.LIST (4134/SPL2) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-08-10 19:19 | 2018-08-10 19:19 | Yes | 184 |  |  |  | 2018-11-20 17:10 |  |  |  |  | 2018-11-20 20:00 | Yes | 88
VD-9001-201B-FDB-001 | 0 | MANUFACTURING DATA BOOK (0636/MDB) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 |  |  | No | 863 | [9 empty] | No | 0
VD-9001-201B-GAD-001 | 0 | GENERAL ARRANGEMENT (4134/0359) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 12:55 |  | No | 1 | 2018-02-25 10:27 | [7 empty] | 2018-02-25 19:59 | Yes | 0
VD-9001-201B-DWG-001 | 0 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 12:56 |  | No | 1 |  |  |  | 2018-03-14 14:43 |  |  |  |  | 2018-03-14 20:00 | Yes | 0
VD-9001-201B-DWG-002 | 0 | DETAILS DRAWING (4134-0359/2) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 12:58 |  | No | 1 |  |  |  | 2018-03-04 17:26 |  |  |  |  | 2018-03-04 20:00 | Yes | 0
VD-9001-201B-DWG-003 | 0 | NAME PLATE DET.DWG (4134-0359/A) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 13:28 |  | No | 1 | 2018-02-26 09:52 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-201B-ITP-001 | 0 | INSPECTION & TESTING PLAN (4134-0359/ITP) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-22 18:25 |  | No | 12 | 2018-02-25 17:45 | [7 empty] | 2018-02-25 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 12:44
VD-9001-201B-CAL-001 | 0 | MECHANICAL CALCULATION (4134-0359/MC) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 13:32 |  | No | 1 | 2018-02-14 16:14 | [7 empty] | 2018-02-14 20:00 | Yes | 0
VD-9001-201B-DWG-004 | 0 | SHIPPING DRAWING (4134-0359/T) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2019-10-24 09:43 | 2019-10-24 09:45 | Yes | 624 |  |  | 2019-11-12 18:10 | [5 empty] | 2019-11-12 18:58 | Yes | 5
VD-9001-201B-DWG-005 | 0 | PAINTING PLAN (4134-0359/V) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 |  |  | No | 877 | [9 empty] | No | 0
VD-9001-201B-WBK-001 | 0 | WELDING BOOK (4134-0359/W) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-10 | 2018-01-31 12:31 |  | No | 21 | 2018-02-25 17:50 | [7 empty] | 2018-02-25 20:00 | Yes | 0
VD-9001-201B-DWG-007 | 0 | LADDER AND PLATFORM DWG (4134-0359/3) | PV-201B | Brembana & Rolle S.p.A. | 2018-04-16 | 2018-09-06 17:37 | 2018-09-06 17:37 | Yes | 143 |  |  |  | 2018-09-23 18:40 |  |  |  |  | 2018-09-23 18:59 | Yes | 3
VD-9001-201B-DWG-008 | 0 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2018-04-16 | 2018-09-06 17:37 | 2018-09-06 17:38 | Yes | 143 |  |  |  | 2018-09-24 10:47 |  |  |  |  | 2018-09-24 18:58 | Yes | 4
VD-9001-201B-DWG-009 | 0 | LADDER AND PLATFORM DWG (4134-0359/5) | PV-201B | Brembana & Rolle S.p.A. | 2018-04-16 | 2019-03-06 16:24 | 2019-03-06 16:29 | Yes | 324 |  |  |  | 2019-03-11 17:44 |  |  |  |  | 2019-03-11 20:00 | Yes | -9
VD-9001-201B-DWG-010 | 0 | TEMPLATE DWG (4134-0359/TMP) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-01-25 13:30 |  | No | -13 |  |  |  | 2018-03-12 11:52 |  |  |  |  | 2018-03-12 20:00 | Yes | 0
VD-9001-201B-CAL-002 | 0 | REFRACTORY DOME CALCULATION (4134-0359/RDC) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-08-23 18:17 | 2018-08-23 18:18 | Yes | 108 |  |  | 2018-10-29 09:56 | [5 empty] | 2018-10-29 09:56 | Yes | 53
VD-9001-201B-PCJ-006 | 0 | DRY OUT PROCEDURE (4134-0359/RDP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-06-06 19:38 | 2018-06-06 19:38 | Yes | 30 |  |  | 2018-08-28 16:39 | [5 empty] | 2018-08-28 19:58 | Yes | 69
VD-9001-201B-DWG-012 | 0 | REFRACTORY LINING REFORMER R-1004 - VERTICAL SECTIONS OF REFORMER (4134-0359/RF) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-05-14 18:02 | 2018-05-14 18:35 | Yes | 7 |  |  |  | 2018-07-04 15:21 |  |  |  |  | 2018-07-04 20:00 | Yes | 37 | 1204-Owner-v | 2019-01-29 10:14
VD-9001-201B-DWG-013 | 0 | REFRACTORY ANCHORS REFORMER R-1004 - VERTICAL SECTIONS OF REFORMER (4134-0359/RF1) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-05-14 17:46 | 2018-05-14 17:54 | Yes | 7 |  |  |  | 2018-07-04 15:59 |  |  |  |  | 2018-07-04 20:00 | Yes | 37 | 1204-Owner-v | 2019-01-29 10:19
VD-9001-201B-CAL-003 | 0 | HEAT TRANSFER CALCULATION (4134-0359/RHC) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-05-24 12:02 | 2018-05-24 12:02 | Yes | 17 |  |  | 2018-10-27 15:46 | [5 empty] | 2018-10-27 20:00 | Yes | 142
VD-9001-201B-PCJ-007 | 0 | INSTALLATION REFRACTORY PROCEDURE AT SHOP (4134-0359/RIP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-11-19 13:14 | 2018-11-19 13:14 | Yes | 196 |  |  | 2018-12-12 18:51 | [5 empty] | 2018-12-12 20:01 | Yes | 9
VD-9001-201B-PCJ-008 | 0 | INSTALLATION REFRACTORY PROCEDURE AT SITE (4134-0359/RIP-1) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-06-20 18:31 | 2018-06-20 18:31 | Yes | 44 |  |  |  | 2018-07-14 09:51 |  |  |  |  | 2018-07-14 19:59 | Yes | 10
VD-9001-201B-PCJ-009 | 0 | REFRACTORY PRECAST PROCEDURE (4134-0359/RPP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-12-11 11:01 | 2018-12-11 11:02 | Yes | 218 |  |  | 2019-01-21 17:17 | [5 empty] | 2019-01-21 19:59 | Yes | 27
VD-9001-201B-DSH-001 | 0 | MATERIAL SAFETY DATA SHEET (4134-0359/RSD) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-06-20 18:29 | 2018-06-20 18:30 | Yes | 44 |  |  | 2018-07-16 17:31 | [5 empty] | 2018-07-16 20:00 | Yes | 12
VD-9001-201B-ITP-002 | 0 | INSPECTION & TEST PLAN (REFRACTORY) (4134-0359/RTP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-11-19 13:15 | 2018-11-19 13:15 | Yes | 196 |  |  |  | 2018-12-12 09:09 |  |  |  |  | 2018-12-12 19:59 | Yes | 9 | 1204-Owner-v | 2020-01-01 12:45
VD-9001-201B-CAL-004 | 0 | FEA REPORT (4134-0359/FEA) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-07-02 18:32 | 2018-07-02 18:33 | Yes | 56 |  |  |  | 2018-11-12 18:12 |  |  |  |  | 2018-11-12 20:00 | Yes | 119
VD-9001-201B-DSH-003 | 0 | REFRACTORY DATA SHEET (4134-0359/RDS) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-05-24 12:07 | 2018-05-24 12:07 | Yes | 17 |  |  |  | 2018-07-25 18:47 |  |  |  |  | 2018-07-25 19:59 | Yes | 48 | 1204-Owner-v | 2018-05-29 11:42
VD-9001-201B-DSH-005 | 0 | THERMOCOUPLE/THERMOWELL DATA SHEET & DRAWING (4134-0359/TC) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2019-04-10 12:15 | 2019-04-10 12:15 | Yes | 338 |  |  |  | 2019-04-24 10:37 |  |  |  |  | 2019-04-24 20:59 | Yes | 0
VD-9001-201B-LST-003 | 0 | INSTRUMENT AND CABLE LIST (4134-0359/IL) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 |  |  | No | 774 | [9 empty] | No | 0
VD-9001-201B-PCJ-010 | 0 | INSTALLATION PROCEDURE FOR THERMOCOUPLE (4134-0359/IPT) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2020-03-25 20:13 | 2020-03-25 20:13 | Yes | 688 |  |  | 2020-04-29 07:48 | [5 empty] | 2020-04-29 20:58 | Yes | 21
VD-9001-201B-PCJ-011 | 0 | HARDNESS PROCEDURE (4134/PD) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-03-15 18:51 | 2018-03-15 18:52 | Yes | 36 |  |  | 2018-04-16 10:38 | [5 empty] | 2018-04-16 20:00 | Yes | 18
VD-9001-201B-PCJ-012 | 0 | PMI PROCEDURE (4134/PMI) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-03-15 18:52 | 2018-03-15 18:52 | Yes | 36 |  |  | 2018-04-16 10:14 | [5 empty] | 2018-04-16 20:00 | Yes | 18
VD-9001-201B-PCJ-013 | 0 | PACKING, MARKING & SHIPPING PROCEDURE (4134/PP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2020-03-25 20:14 | 2020-03-25 20:14 | Yes | 688 |  |  |  | 2020-05-04 15:27 |  |  |  |  | 2020-05-04 21:02 | Yes | 26
VD-9001-201B-PCJ-014 | 0 | REPAIR PROCEDURE (4134/WR) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-11-16 13:49 | 2018-11-16 13:50 | Yes | 282 |  |  | 2018-12-12 09:48 | [5 empty] | 2018-12-12 19:59 | Yes | 12
VD-9001-201B-PCJ-015 | 0 | HOT FORMING PROCEDURE FOR HEAD (4134/HFP) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-06-27 12:37 | 2018-06-27 12:37 | Yes | 140 |  |  | 2018-07-14 09:47 | [5 empty] | 2018-07-14 19:59 | Yes | 3
VD-9001-201B-PCJ-016 | 0 | DIMENSIONAL CHECK PROCEDURE (4134/DC) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-03-15 18:52 | 2018-03-15 18:53 | Yes | 36 |  |  | 2018-04-16 10:35 | [5 empty] | 2018-04-16 20:00 | Yes | 18
VD-9001-201B-DWG-015 | 0 | BILL OF MATERIAL AND GENERAL NOTES (4134-0359/BMN) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 13:30 |  | No | 1 |  |  |  | 2018-03-14 15:51 |  |  |  |  | 2018-03-14 20:00 | Yes | 0
VD-9001-201B-PCJ-017 | 0 | PICKLING AND PASSIVATION PROCEDURE (for Ni base weld seams) (4134/PKP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2020-06-12 18:51 | 2020-06-12 18:52 | Yes | 767 | [6 empty] | 2020-06-06 10:40 | 2020-06-06 10:40 |  | Yes | -20
VD-9001-201B-PCJ-019 | 0 | MANUFACTURING & NDE PROCEDURE FOR SITE (4134/MP1) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-07 | 2018-06-18 14:04 | 2018-06-18 14:05 | Yes | 42 |  |  | 2018-07-14 09:40 | [5 empty] | 2018-07-14 19:59 | Yes | 12
VD-9001-201B-CAL-005 | 0 | TRANSPORTATION SADDLE CALCULATION (4134-0359/MC1) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-26 | 2020-03-20 11:52 | 2020-03-20 11:55 | Yes | 725 |  |  |  | 2020-04-14 14:25 |  |  |  |  | 2020-04-14 21:07 | Yes | 11
VD-9001-201B-MSS-001 | 0 | MATERIAL SPECIFICATION (plate and forge) (4134/MRS) | PV-201B | Brembana & Rolle S.p.A. | 2018-01-31 | 2020-03-20 11:59 | 2020-03-20 11:59 | Yes | 779 |  |  | 2020-04-16 13:39 | [5 empty] | 2020-04-16 20:59 | Yes | 13
VD-9001-201B-DWG-017 | 0 | LIFTING STYLE DRAWING (4134-0359/LS) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-31 | 2020-03-30 12:49 | 2020-03-30 12:50 | Yes | 669 |  |  | 2020-04-12 12:45 | [5 empty] | 2020-04-12 21:02 | Yes | -1
VD-9001-401A-ITP-001 | 0 | INSPECTION AND TEST PLAN | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-01-21 | 2018-10-19 13:23 | 2018-10-19 13:23 | Yes | 271 |  |  |  | 2018-10-24 08:38 |  |  |  |  | 2018-10-24 08:38 | Yes | -9 | 1204-Owner-v | 2020-01-01 11:01
VD-9001-401A-INX-001 | 0 | FINAL DATA BOOK INDEX | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-01-21 | 2018-12-05 15:28 | 2018-12-05 15:28 | Yes | 318 |  |  |  | 2018-12-09 09:29 |  |  |  |  | 2018-12-09 09:29 | Yes | -10
VD-9001-401A-PCJ-001 | 0 | PACKING & MARKING PROCEDURE | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-01-21 | 2018-10-19 13:34 | 2018-10-19 13:34 | Yes | 271 |  |  |  | 2018-10-28 14:51 |  |  |  |  | 2018-10-28 14:51 | Yes | -5 | 1204-Owner-v | 2019-07-20 17:55
VD-9001-104-REQ-017 | 2 | E-6124_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-04 19:59 | 2018-03-26 17:24 | 2018-03-26 17:26 | Yes | 50 |  |  | 2018-03-27 11:59 | [5 empty] | 2018-03-27 21:00 | Yes | -13 | 1204-Owner-v | 2018-04-18 14:54
VD-9001-104-SPE-007 | 1 | Handrail and platform ALE standard | PR-104 | AIR LIQUIDE | 2018-02-04 19:59 |  |  | No | 866 | [9 empty] | No | 0
VD-9001-206B-PCJ-016 | 2 | HARDNESS TEST PROCEDURE | PV-206B | TASHA | 2018-01-22 09:32 | 2018-01-23 08:14 |  | No | 1 |  |  |  | 2018-05-14 14:07 |  |  |  |  | 2018-05-14 14:07 | Yes | 0
VD-9001-206B-WMP-022 | 4 | WELDING MAP&NDT TABLE | PV-206B | TASHA | 2018-01-22 09:32 | 2018-01-23 08:19 | 2018-01-23 08:20 | Yes | 1 |  | 2018-02-07 17:49 | [6 empty] | 2018-02-07 20:00 | Yes | 1
VD-9001-104-QCP-001 | 3 | Quality Control Plan | PR-104 | AIR LIQUIDE | 2018-02-05 19:59 | 2018-02-06 12:34 | 2018-02-06 12:35 | Yes | 1 |  | 2018-02-17 18:28 | [6 empty] | 2018-02-17 20:00 | Yes | -3 | 1204-Owner-v | 2018-03-13 11:41
VD-9001-104-DIG-001 | 1 | Material selection P&ID | PR-104 | AIR LIQUIDE | 2018-02-05 19:59 | 2018-04-19 19:57 | 2018-04-19 20:06 | Yes | 73 |  |  | 2018-05-21 15:55 | [5 empty] | 2018-05-21 20:00 | Yes | 18 | 1204-Owner-v | 2018-05-05 07:55
VD-9001-251-DSH-015 | 1 | MECHANICAL DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-23 | 2018-04-20 15:37 | 2018-04-20 15:41 | Yes | 87 |  |  |  |  | 2018-05-01 11:10 |  |  |  | 2018-05-01 11:10 | Yes | -3
VD-9001-251-DSH-012 | 1 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-23 | 2018-04-20 15:32 | 2018-04-20 15:35 | Yes | 87 |  |  |  | 2018-04-29 15:10 |  |  |  |  | 2018-04-29 15:10 | Yes | -5 | 1204-Owner-v | 2018-09-25 15:22
VD-9001-251-DSH-013 | 1 | MECHANICAL DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2018-01-23 | 2018-04-20 15:36 | 2018-04-20 15:37 | Yes | 87 |  |  |  | 2018-04-29 15:11 |  |  |  |  | 2018-04-29 15:11 | Yes | -5
VD-9001-251-DSH-014 | 1 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-01-23 | 2018-04-20 15:36 | 2018-04-20 15:37 | Yes | 87 |  |  |  | 2018-04-29 15:09 |  |  |  |  | 2018-04-29 15:09 | Yes | -5
VD-9001-104-PCJ-003 | 1 | Deriming procedure | PR-104 | AIR LIQUIDE | 2018-02-06 19:59 | 2018-03-08 17:39 | 2018-03-08 18:10 | Yes | 30 |  |  | 2018-03-12 11:05 | [5 empty] | 2018-03-12 11:05 | Yes | -10 | 1204-Owner-v | 2018-04-04 14:59
VD-9001-251-ORC-001 | 1 | PROJECT ORGANIZATION CHART | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 19:59 |  |  | No | 864 | [9 empty] | No | 0
VD-9001-257C-DWG-062 | 0 | EXPANSION BELLOW DETAILS DRAWING (4137-0366/EB) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-30 | 2018-05-07 19:02 | 2018-05-07 19:03 | Yes | 38 |  |  |  |  | 2018-07-22 11:10 |  |  |  | 2018-07-22 11:10 | Yes | 62
VD-9001-257C-CAL-009 | 0 | MECHANICAL CALCULATIONS FOR EXPANSION BELLOWS (4137-0366/MCS) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-30 | 2018-05-07 18:45 | 2018-05-07 18:46 | Yes | 38 |  |  |  |  | 2018-08-08 11:03 |  |  |  | 2018-08-08 11:03 | Yes | 79 | 1204-Owner-v | 2018-12-10 11:04
VD-9001-257C-DWG-063 | 0 | EXPANSION BELLOW DETAILS DRAWING (4137-0367/EB) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-30 | 2018-05-07 19:05 | 2018-05-07 19:05 | Yes | 38 |  |  |  |  | 2018-07-22 10:59 |  |  |  | 2018-07-22 10:59 | Yes | 62
VD-9001-257C-CAL-010 | 0 | MECHANICAL CALCULATIONS FOR EXPANSION BELLOWS (4137-0367/MCS) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-30 | 2018-05-07 18:53 | 2018-05-07 18:54 | Yes | 38 |  |  |  |  | 2018-08-08 15:15 |  |  |  | 2018-08-08 15:15 | Yes | 79
VD-9001-257C-DWG-064 | 0 | DETAILS DRAWING (4137-0367/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-01-24 | 2018-01-25 14:28 |  | No | 1 |  |  |  |  | 2018-03-27 17:01 |  |  |  | 2018-03-27 17:01 | Yes | 0
VD-9001-251-SDG-002 | 1 | FINNING DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-01-24 | 2018-04-18 14:23 | 2018-04-18 14:29 | Yes | 84 |  |  | 2018-04-25 19:11 | [5 empty] | 2018-04-25 19:11 | Yes | -7 | 1204-Owner-v | 2019-04-15 09:06
VD-9001-251-DSH-003 | 1 | DATA SHEET TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-01-24 | 2018-09-11 16:34 | 2018-09-11 16:38 | Yes | 230 |  |  |  | 2018-10-07 11:18 |  |  |  |  | 2018-10-07 11:18 | Yes | 12 | 1204-Owner-v | 2018-09-25 15:18
VD-9001-251-DSH-002 | 1 | DATA SHEET ARCH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-01-27 | 2018-09-11 16:25 | 2018-09-11 16:33 | Yes | 227 |  |  |  | 2018-10-07 11:17 |  |  |  |  | 2018-10-07 11:17 | Yes | 12
VD-9001-251-DSH-004 | 1 | DATA SHEET SSH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-01-27 | 2018-09-11 14:47 | 2018-09-11 16:33 | Yes | 227 |  |  |  | 2018-10-07 11:19 |  |  |  |  | 2018-10-07 11:19 | Yes | 12
VD-9001-460A-ITP-001 | 2 | Inspection Test Plan | PI-460A | Nia Shimi Co. | 2018-01-27 | 2018-01-28 11:34 |  | No | 1 | 2018-01-28 14:30 | [7 empty] | 2018-01-28 20:00 | Yes | 0
VD-9001-251-DWG-001 | 1 | CATALYST TUBE DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-01-27 | 2018-05-08 20:24 | 2018-05-08 20:27 | Yes | 101 |  |  |  | 2018-05-09 15:47 |  |  |  |  | 2018-05-09 15:47 | Yes | -13
VD-9001-301-ARP-001 | 0 | rotor response analysis syngas compressor | MC-301 | Siemens AG | 2018-06-18 | 2018-02-05 14:40 |  | No | -133 | 2018-02-13 11:32 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CAL-001 | 0 | calculation thermowells syngas train | MC-301 | Siemens AG | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-301-DIG-001 | 0 | logic diagrams syngas train | MC-301 | Siemens AG | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-301-ARP-002 | 0 | Hydrostatic Pressure Test syngas compressor | MC-301 | Siemens AG | 2018-06-18 | 2018-01-30 11:19 |  | No | -139 | 2018-01-31 09:17 | [7 empty] | 2018-01-31 19:59 | Yes | 0
VD-9001-301-DSH-001 | 0 | Material Safety Data Sheets Syngas train | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-PCJ-001 | 0 | Preservation and Storage Procedure for SYNGAS Train | MC-301 | Siemens AG | 2018-08-03 | 2018-02-03 09:49 |  | No | -181 | 2018-02-27 11:17 | [7 empty] | 2018-02-27 19:59 | Yes | 0
VD-9001-301-DSH-002 | 0 | seal gas panel SV data sheet syngas compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-CAL-002 | 0 | seal gas panel SV calculation syngas compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-DWG-001 | 0 | seal gas panel SV dim drawing syngas compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-LST-001 | 0 | Sparepart list Syngas Compressor | MC-301 | Siemens AG | 2018-11-30 |  |  | No | 567 | [9 empty] | No | 0
VD-9001-301-PCJ-002 | 0 | packing and marking procedure | MC-301 | Siemens AG | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-301-ARP-003 | 0 | rotor response analysis circulator compressor | MC-301 | Siemens AG | 2018-06-18 |  |  | No | 732 | [9 empty] | No | 0
VD-9001-301-DWG-002 | 0 | logic diagrams circulator train | MC-301 | Siemens AG | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-301-INX-001 | 0 | manufacturing data book (index) circulator train | MC-301 | Siemens AG | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-301-MDB-001 | 0 | manufacturing data book (MDB) circulator train | MC-301 | Siemens AG | 2019-02-26 |  |  | No | 479 | [9 empty] | No | 0
VD-9001-301-ITP-001 | 0 | Hydrostatic Pressure Test circulator compressor | MC-301 | Siemens AG | 2018-06-18 | 2018-01-30 11:21 |  | No | -139 | 2018-01-31 09:29 | [7 empty] | 2018-01-31 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:41
VD-9001-301-DSH-003 | 0 | seal gas panel SV data sheet circulator compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-CAL-003 | 0 | seal gas panel SV calculation circulator compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-DWG-003 | 0 | seal gas panel SV dim drawing circulator compressor | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-LST-002 | 0 | Sparepart list Circulator Compressor | MC-301 | Siemens AG | 2018-11-30 |  |  | No | 567 | [9 empty] | No | 0
VD-9001-301-WIN-001 | 0 | assembley notes (Transition piece) syngas turbine | MC-301 | Siemens AG | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-301-DBS-001 | 0 | condenser air cooled syngas turbine | MC-301 | Siemens AG | 2018-01-05 | 2018-01-28 11:23 |  | No | 23 | 2018-02-07 15:16 | [7 empty] | 2018-02-07 20:00 | Yes | 0
VD-9001-301-DSH-004 | 0 | Syngas Condenser Basic Inquiry Data for customer supply | MC-301 | Siemens AG | 2018-01-26 |  |  | No | 875 | [9 empty] | No | 0
VD-9001-301-LST-003 | 0 | Spareparts list Syngas Turbine | MC-301 | Siemens AG | 2018-11-30 |  |  | No | 567 | [9 empty] | No | 0
VD-9001-301-LST-004 | 0 | spareparts list Circulator turbine | MC-301 | Siemens AG | 2018-11-30 |  |  | No | 567 | [9 empty] | No | 0
VD-9001-301-QCP-001 | 0 | quality control plan Circulator Compressor | MC-301 | Siemens AG | 2018-01-26 | 2018-01-30 11:22 |  | No | 4 | 2018-02-27 09:00 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:42
VD-9001-301-QCP-002 | 0 | Quality Control Plan (Syngas SST Auxiliaries) | MC-301 | Siemens AG | 2018-01-26 | 2018-01-30 11:19 |  | No | 4 | 2018-02-27 08:53 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:44
VD-9001-301-QCP-003 | 0 | Quality Control Plan (Circulator SST Auxiliaries) | MC-301 | Siemens AG | 2018-01-26 | 2018-01-30 11:22 |  | No | 4 | 2018-02-27 09:06 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:44
VD-9001-301-MNL-001 | 0 | installation and operating manual (IOM) Syngas Train | MC-301 | Siemens AG | 2019-01-31 |  |  | No | 505 | [9 empty] | No | 0
VD-9001-301-MNL-002 | 0 | commissioning instructions Syngas Train | MC-301 | Siemens AG | 2019-01-31 |  |  | No | 505 | [9 empty] | No | 0
VD-9001-301-MNL-003 | 0 | installation and operating manual (IOM) Circulator Train | MC-301 | Siemens AG | 2019-01-31 |  |  | No | 505 | [9 empty] | No | 0
VD-9001-301-MNL-004 | 0 | commissioning instructions (index) Circulator Train | MC-301 | Siemens AG | 2018-10-31 |  |  | No | 597 | [9 empty] | No | 0
VD-9001-301-PCJ-003 | 0 | performance test (procedure) Syngas Compressor | MC-301 | Siemens AG | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-301-PCJ-004 | 0 | mechanical running test (procedure) Syngas Compressor | MC-301 | Siemens AG | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-301-QCP-004 | 0 | QHSE plan | MC-301 | Siemens AG | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-301-INX-002 | 0 | manufacturing data book syngas train(index) | MC-301 | Siemens AG | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-301-MDB-002 | 0 | manufacturing data book syngas train(MDB) | MC-301 | Siemens AG | 2019-02-26 |  |  | No | 479 | [9 empty] | No | 0
VD-9001-301-PCJ-005 | 0 | performance test (procedure) Circulator Compressor | MC-301 | Siemens AG | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-301-PCJ-006 | 0 | mechanical running test (procedure) Circulator Compressor | MC-301 | Siemens AG | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-301-QCP-005 | 0 | quality control plan Syngas Compressor | MC-301 | Siemens AG | 2018-01-26 | 2018-01-30 11:19 |  | No | 4 | 2018-02-26 16:03 | [7 empty] | 2018-02-26 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:45
VD-9001-301-LST-005 | 0 | lube oil list syngas train | MC-301 | Siemens AG | 2018-05-16 |  |  | No | 765 | [9 empty] | No | 0
VD-9001-301-LST-006 | 0 | customer connection list syngas train | MC-301 | Siemens AG | 2018-02-02 | 2018-01-30 11:32 |  | No | -3 | 2018-02-13 09:42 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-301-LST-007 | 0 | utility consumption list syngas train | MC-301 | Siemens AG | 2018-03-02 | 2018-01-30 11:25 |  | No | -31 | 2018-02-18 16:29 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-DWG-004 | 0 | foundation plan syngas train | MC-301 | Siemens AG | 2018-01-26 | 2018-01-28 12:47 |  | No | 2 | 2018-02-15 10:25 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-DCR-001 | 0 | foundation information syngas train | MC-301 | Siemens AG | 2018-01-26 | 2018-01-28 12:47 |  | No | 2 | 2018-02-15 10:17 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-DSH-005 | 0 | noise emission (data sheet) syngas train | MC-301 | Siemens AG | 2018-02-02 | 2018-02-05 14:40 |  | No | 3 | 2018-02-25 10:36 | [7 empty] | 2018-02-25 19:59 | Yes | 0 | 1204-Owner-v | 2019-06-17 14:22
VD-9001-301-LST-008 | 0 | lube oil list circulator train | MC-301 | Siemens AG | 2018-05-16 |  |  | No | 765 | [9 empty] | No | 0
VD-9001-301-LST-009 | 0 | customer connection list circulator train | MC-301 | Siemens AG | 2018-02-02 | 2018-01-30 11:32 |  | No | -3 | 2018-02-13 09:48 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-301-LST-010 | 0 | utility consumption list circulator train | MC-301 | Siemens AG | 2018-02-02 | 2018-01-30 11:25 |  | No | -3 | 2018-02-18 16:24 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-DWG-005 | 0 | foundation plan circulator train | MC-301 | Siemens AG | 2018-01-26 | 2018-01-28 12:50 |  | No | 2 | 2018-02-15 11:30 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-DCR-002 | 0 | foundation information circulator train | MC-301 | Siemens AG | 2018-01-26 | 2018-01-28 12:50 |  | No | 2 | 2018-02-15 11:21 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-DSH-006 | 0 | noise emission (data sheet) circulator train | MC-301 | Siemens AG | 2018-02-12 | 2018-02-05 14:40 |  | No | -7 | 2018-02-19 14:37 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-301-PID-001 | 0 | P+I Diagram Symbols syngas train | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 14:26 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-002 | 0 | P+I Diagram Machine Syngas Compressor | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 14:45 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-003 | 0 | P+I Diagram Machine Syngas Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:44 |  | No | 17 | 2018-02-13 09:11 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-301-PID-004 | 0 | P+I Diagram Seal Gas Unit (Syngas Compressor) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:44 |  | No | 17 | 2018-02-12 16:54 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-005 | 0 | P+I Diagram Oil Syngas Train | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 14:49 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-006 | 0 | P+I Diagram Oil Console Syngas and Circulator Trains | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 14:34 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-007 | 0 | P+I Diagram Process gas Syngas Compressor | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 14:39 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-008 | 0 | P+I Diagram Steam + Drainage Syngas Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:25 |  | No | 17 | 2018-02-12 15:52 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-009 | 0 | condensing system (P+I diagram; syngas turbine) | MC-301 | Siemens AG | 2018-01-11 |  |  | No | 890 | [9 empty] | No | 0
VD-9001-301-PID-010 | 0 | P+I Diagram Control Oil Syngas Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 11:26 |  | No | 17 | 2018-02-12 15:05 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-DCR-003 | 0 | final controlling element syngas (design) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DCR-004 | 0 | flow element syngas (design) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-PDS-001 | 0 | start-up description syngas train | MC-301 | Siemens AG | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-301-PDS-002 | 0 | control description syngas train | MC-301 | Siemens AG | 2018-03-02 | 2018-03-10 09:03 | 2018-03-10 09:03 | Yes | 8 | [9 empty] | No | 818 | 1204-Owner-v | 2018-03-12 08:51
VD-9001-301-DIG-002 | 0 | control diagram syngas train | MC-301 | Siemens AG | 2018-02-16 | 2018-03-14 17:32 | 2018-03-14 17:33 | Yes | 26 | [9 empty] | No | 814
VD-9001-301-LST-011 | 0 | cable list syngas train | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-DIG-003 | 0 | junction box (wiring diagram) syngas train | MC-301 | Siemens AG | 2016-06-01 | 2018-03-03 12:10 | 2018-03-04 14:24 | Yes | 641 | [9 empty] | No | 825 | 1204-Owner-v | 2018-03-12 08:46
VD-9001-301-DWG-006 | 0 | hook-up (field instruments) syngas train | MC-301 | Siemens AG | 2018-03-19 | 2018-03-03 12:10 | 2018-03-04 14:24 | Yes | -15 | [9 empty] | No | 825 | 1204-Owner-v | 2018-03-12 08:47
VD-9001-301-LST-012 | 0 | instrument list syngas train | MC-301 | Siemens AG | 2018-04-02 | 2018-03-03 12:11 | 2018-03-04 14:25 | Yes | -30 |  |  |  | 2018-06-17 14:45 |  |  |  |  | 2018-06-17 20:00 | Yes | 92 | 1204-Owner-v | 2018-03-12 08:48
VD-9001-301-DSH-007 | 0 | instrumentation syngas train (data sheet) | MC-301 | Siemens AG | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-301-CAL-004 | 0 | Ex i-analysis syngas train (calculation) | MC-301 | Siemens AG | 2016-06-01 |  |  | No | 1479 | [9 empty] | No | 0
VD-9001-301-ARP-004 | 0 | SIL and HAZOP study syngas train (summary) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-013 | 0 | list of electrical consumers syngas train | MC-301 | Siemens AG | 2018-02-16 | 2018-03-03 12:11 | 2018-03-04 14:25 | Yes | 16 | [9 empty] | No | 825
VD-9001-301-DIG-004 | 0 | installation diagram syngas train | MC-301 | Siemens AG | 2018-03-19 | 2018-04-04 08:49 | 2018-04-04 08:49 | Yes | 16 | [9 empty] | No | 793 | 1204-Owner-v | 2019-01-06 17:09
VD-9001-301-LST-014 | 0 | signal list syngas train | MC-301 | Siemens AG | 2018-03-19 | 2018-03-17 09:16 | 2018-03-17 09:16 | Yes | -2 | [9 empty] | No | 811
VD-9001-301-DIG-005 | 0 | earthing diagram syngas train | MC-301 | Siemens AG | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-301-ARP-005 | 0 | SIL and HAZOP report syngas train | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-PID-011 | 0 | P+I Diagram Symbols Circulator Train | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-13 09:36 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-301-PID-012 | 0 | P+I Diagram Machine (Circulator Compressor) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-12 16:25 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-013 | 0 | P+I Diagram Machine Circulator Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-13 09:27 | [7 empty] | 2018-02-13 19:59 | Yes | 0
VD-9001-301-PID-014 | 0 | P+I Diagram Seal gas unit (Circulator Compressor) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-13 10:49 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-PID-015 | 0 | P+I Diagram Oil Circulator Train | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-12 15:22 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-016 | 0 | P+I Diagram Process gas Circulator Compressor | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-12 16:16 | [7 empty] | 2018-02-12 20:00 | Yes | 0
VD-9001-301-PID-017 | 0 | P+I Diagram Steam + Drainage Circulator Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-13 10:56 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-PID-018 | 0 | P+I Diagram Control oil Circulator Turbine | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:41 |  | No | 17 | 2018-02-13 11:00 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-DCR-005 | 0 | final controlling element circulator train (design) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DCR-006 | 0 | flow element circulator train (design) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-PDS-003 | 0 | start-up description circulator train | MC-301 | Siemens AG | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-301-PDS-004 | 0 | control description circulator train | MC-301 | Siemens AG | 2018-03-02 | 2018-03-10 09:04 | 2018-03-10 09:04 | Yes | 8 | [9 empty] | No | 818 | 1204-Owner-v | 2018-03-12 08:52
VD-9001-301-DIG-006 | 0 | control diagram circulator train | MC-301 | Siemens AG | 2018-02-16 | 2018-03-14 17:32 | 2018-03-14 17:32 | Yes | 26 | [9 empty] | No | 814
VD-9001-301-LST-015 | 0 | cable list circulator train | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-DIG-007 | 0 | junction box circulator train (wiring diagram) | MC-301 | Siemens AG | 2016-06-01 | 2018-03-03 12:10 | 2018-03-04 14:24 | Yes | 641 | [9 empty] | No | 825
VD-9001-301-DWG-007 | 0 | hook-up circulator train (field instruments) | MC-301 | Siemens AG | 2018-03-19 | 2018-03-03 12:10 | 2018-03-04 14:25 | Yes | -15 | [9 empty] | No | 825 | 1204-Owner-v | 2018-03-12 08:53
VD-9001-301-LST-016 | 0 | instrument list circulator train | MC-301 | Siemens AG | 2018-04-02 | 2018-03-03 12:11 | 2018-03-04 14:25 | Yes | -30 |  |  |  | 2018-06-17 14:43 |  |  |  |  | 2018-06-17 20:00 | Yes | 92
VD-9001-301-DSH-008 | 0 | instrumentation circulator train (data sheet) | MC-301 | Siemens AG | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-301-CAL-005 | 0 | Ex i-analysis circulator train (calculation) | MC-301 | Siemens AG | 2016-06-01 |  |  | No | 1479 | [9 empty] | No | 0
VD-9001-301-ARP-006 | 0 | SIL and HAZOP study circulator train (summary) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-017 | 0 | list of electrical consumers circulator train | MC-301 | Siemens AG | 2018-02-16 | 2018-03-03 12:11 | 2018-03-04 14:26 | Yes | 16 | [9 empty] | No | 825
VD-9001-301-DIG-008 | 0 | installation diagram circulator train | MC-301 | Siemens AG | 2018-03-19 | 2018-04-04 08:49 | 2018-04-04 08:50 | Yes | 16 | [9 empty] | No | 793
VD-9001-301-LST-018 | 0 | signal list circulator train | MC-301 | Siemens AG | 2018-03-19 | 2018-03-17 09:16 | 2018-03-17 09:16 | Yes | -2 | [9 empty] | No | 811
VD-9001-301-DIG-009 | 0 | earthing diagram circulator train | MC-301 | Siemens AG | 2018-04-02 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-301-ARP-007 | 0 | SIL and HAZOP report circulator train | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-009 | 0 | syngas compressor (data sheet API 617) | MC-301 | Siemens AG | 2018-02-02 | 2018-01-30 11:27 |  | No | -3 | 2018-02-27 09:30 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-07-24 14:09
VD-9001-301-DSH-010 | 0 | circulator compressor (data sheet API 617) | MC-301 | Siemens AG | 2018-02-02 | 2018-01-30 11:27 |  | No | -3 | 2018-02-27 09:11 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-07-24 14:10
VD-9001-301-DWG-008 | 0 | Predicted Performance Curves Overall Syngas Compressor | MC-301 | Siemens AG | 2018-02-02 | 2018-01-28 11:24 |  | No | -5 | 2018-02-18 14:20 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-ARP-009 | 0 | torsional analysis syngas train | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-DIG-010 | 0 | Campbell diagram syngas compressor | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-ARP-010 | 0 | rotor stability analysis syngas compressor | MC-301 | Siemens AG | 2018-06-20 | 2018-02-05 14:40 |  | No | -135 | 2018-02-13 11:20 | [7 empty] | 2018-02-13 20:00 | Yes | 0 | 1204-Owner-v | 2019-12-28 09:57
VD-9001-301-DWG-009 | 0 | overall perform. curves circulator compressor (pred.) | MC-301 | Siemens AG | 2018-02-02 | 2018-01-28 11:11 |  | No | -5 | 2018-02-18 14:22 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-ARP-011 | 0 | torsional analysis circulator train | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-DIG-011 | 0 | Campbell diagram circulator compressor | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-ARP-012 | 0 | rotor stability analysis circulator compressor | MC-301 | Siemens AG | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-301-DWG-010 | 0 | syngas compressor (section) | MC-301 | Siemens AG | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-LST-019 | 0 | syngas compressor (part list) | MC-301 | Siemens AG | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-LST-020 | 0 | list of special tools syngas compressor | MC-301 | Siemens AG | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-DWG-011 | 0 | name plate syngas compressor | MC-301 | Siemens AG | 2018-04-24 | 2018-01-30 11:24 |  | No | -84 | 2018-01-31 08:56 | [7 empty] | 2018-01-31 19:59 | Yes | 0
VD-9001-301-DWG-012 | 0 | circulator compressor (section) | MC-301 | Siemens AG | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-301-LST-021 | 0 | circulator compressor (part list) | MC-301 | Siemens AG | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-301-LST-022 | 0 | list of special tools circulator compressor | MC-301 | Siemens AG | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-301-DWG-013 | 0 | name plate circulator compressor | MC-301 | Siemens AG | 2018-04-13 | 2018-01-30 11:24 |  | No | -73 | 2018-01-31 09:05 | [7 empty] | 2018-01-31 19:59 | Yes | 0
VD-9001-301-DWG-014 | 0 | oil filter (dimension drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-015 | 0 | small turbine (dimension drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-016 | 0 | small turbine (section) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-023 | 0 | small turbine (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-017 | 0 | oil purifying unit (dimension drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-024 | 0 | oil purifying unit (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-025 | 0 | oil unit (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-026 | 0 | oil cooler (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-027 | 0 | oil filter (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-CAL-006 | 0 | oil filter (calculation) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-WMP-001 | 0 | oil cooler (welding plan) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-011 | 0 | small turbine (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DWG-018 | 0 | oil unit (dimension drawing) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-PCJ-007 | 0 | oil unit (test procedure) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-012 | 0 | oil unit (API 614; data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-013 | 0 | e-heater (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-014 | 0 | oil purifying unit (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DWG-019 | 0 | lube oil rundown tank (dim. drawing) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-CAL-007 | 0 | accumulator (1; calculation) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-020 | 0 | accumulator (1; section) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-WMP-002 | 0 | accumulator (1; welding plan) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-028 | 0 | accumulator (1; parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-PID-019 | 0 | small turbine (P+I diagram) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-CAL-008 | 0 | emergency oil filter (calculation) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-021 | 0 | emergency oil filter (dimension drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-029 | 0 | emergency oil filter (parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-015 | 0 | pressure control valve (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-016 | 0 | e-motor (emergency oil pump; data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-017 | 0 | e-motor (aux. oil pump; data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-018 | 0 | main + aux. oil pump (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DWG-022 | 0 | main + aux. oil pump (dim. drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-019 | 0 | emergency oil pump (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DWG-023 | 0 | emergency oil pump (dimension drawing) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-024 | 0 | oil cooler (section) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-CAL-009 | 0 | oil cooler (heat calculation) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-CAL-010 | 0 | oil cooler (calculation) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DSH-020 | 0 | flame arrester (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DSH-021 | 0 | pressure reducing valve (data sheet) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-DWG-025 | 0 | coupling syngas train (driver; dimension drawing) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DWG-026 | 0 | coupling circulator train (driver; dimension drawing) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DWG-027 | 0 | lifting arrangement syngas compressor | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-028 | 0 | lifting arrangement circulator compressor | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-029 | 0 | syngas compressor seal gas panel(LP; supplier; dim. dwg.) | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-DWG-030 | 0 | circulator compressor seal gas panel (LP; dim. drawing);internal;purchased | MC-301 | Siemens AG | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-301-DWG-031 | 0 | syngas compressor protection strainer (1; dim. drawing) | MC-301 | Siemens AG | 2018-04-16 | 2018-03-10 09:03 | 2018-03-10 09:03 | Yes | -37 |  |  | 2018-03-15 12:09 | [5 empty] | 2018-03-15 20:00 | Yes | -9 | 1204-Owner-v | 2019-05-26 23:09
VD-9001-301-DWG-032 | 0 | circulator compressor protection strainer (1; dim. drawing) | MC-301 | Siemens AG | 2018-04-16 | 2018-03-10 09:03 | 2018-03-10 09:03 | Yes | -37 |  |  |  |  | 2018-03-18 09:57 |  |  |  | 2018-03-18 21:00 | Yes | -6
VD-9001-301-DWG-033 | 0 | control panel syngas train (1; make; dim. drawing) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:45 |  | No | 17 | 2018-02-18 16:07 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-DIG-012 | 0 | control panel syngas train (1; make; circuit diagram) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DIG-013 | 0 | control panel syngas train (1; make; terminal diagr.) | MC-301 | Siemens AG | 2018-05-16 |  |  | No | 765 | [9 empty] | No | 0
VD-9001-301-DWG-034 | 0 | control panel syngas train (1; make; arrangement pl.) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-LST-030 | 0 | control panel syngas train (1; make; parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-031 | 0 | control panel syngas train (1; make; lettering list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-035 | 0 | control panel syngas train (1; make; bit map) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-036 | 0 | control panel syngas train (1; make; HMI scr. shots) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-PCJ-008 | 0 | contr. pan. syngas train (1; make; FAT proc. hard.) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-037 | 0 | control panel circulator train (1; make; dim. drawing) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-28 12:46 |  | No | 17 | 2018-02-18 16:18 | [7 empty] | 2018-02-18 20:00 | Yes | 0
VD-9001-301-DIG-014 | 0 | control panel circulator train (1; make; circuit diagram) | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DIG-015 | 0 | control panel circulator train (1; make; terminal diagr.) | MC-301 | Siemens AG | 2018-05-16 |  |  | No | 765 | [9 empty] | No | 0
VD-9001-301-DWG-038 | 0 | control panel circulator train (1; make; arrangement pl.) | MC-301 | Siemens AG | 2018-04-16 |  |  | No | 795 | [9 empty] | No | 0
VD-9001-301-LST-032 | 0 | control panel circulator train (1; make; parts list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-LST-033 | 0 | control panel circulator train (1; make; lettering list) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-039 | 0 | control panel circulator train (1; make; bit map) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-040 | 0 | control panel circulator train (1; make; HMI scr. shots) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-PCJ-009 | 0 | contr. pan. circulator train (1; make; FAT proc. hard.) | MC-301 | Siemens AG | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-301-DWG-041 | 0 | general arrangement syngas train | MC-301 | Siemens AG | 2018-02-02 | 2018-01-28 12:48 |  | No | -5 | 2018-02-15 10:52 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-PLN-001 | 0 | piping plan syngas train | MC-301 | Siemens AG | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-301-DWG-042 | 0 | cable routing plan syngas train | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-DWG-043 | 0 | general arrangement circulator train | MC-301 | Siemens AG | 2018-02-02 | 2018-01-28 12:49 |  | No | -5 | 2018-02-15 11:17 | [7 empty] | 2018-02-15 19:59 | Yes | 0
VD-9001-301-PLN-002 | 0 | piping plan circulator train | MC-301 | Siemens AG | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-301-DWG-044 | 0 | cable routing plan circulator train | MC-301 | Siemens AG | 2018-05-02 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-301-PCJ-010 | 0 | coating procedure syngas train | MC-301 | Siemens AG | 2018-03-02 | 2018-01-28 11:11 |  | No | -33 | 2018-02-07 08:45 | [7 empty] | 2018-02-07 20:00 | Yes | 0
VD-9001-301-PCJ-011 | 0 | coating procedure circulator train | MC-301 | Siemens AG | 2018-03-02 | 2018-01-28 11:11 |  | No | -33 | 2018-02-07 08:53 | [7 empty] | 2018-02-07 20:00 | Yes | 0
VD-9001-251-DSH-005 | 1 | DATA SHEET FOR FLUE GAS AIR PREHEATER (HE-1006) | HM-251 | KT – Kinetics Technology SpA | 2018-01-27 | 2018-08-10 11:42 | 2018-08-10 11:52 | Yes | 195 |  |  |  |  | 2018-08-18 16:33 |  |  |  | 2018-08-18 16:33 | Yes | -6 | 1204-Owner-v | 2019-04-06 07:41
VD-9001-204C-MSS-036 | 1 | MATERIAL SPECIFICATION FOR FORGINGS | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-01-28 | 2018-01-31 14:42 | 2018-01-31 14:43 | Yes | 3 |  | 2018-02-07 16:25 | [6 empty] | 2018-02-07 20:00 | Yes | -7 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-204C-MSS-037 | 1 | MATERIAL SPECIFICATION FOR PLATES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-01-28 | 2018-02-05 15:17 | 2018-02-05 15:18 | Yes | 8 |  | 2018-02-07 16:22 | [6 empty] | 2018-02-07 20:00 | Yes | -12 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-204C-PCJ-018 | 1 | HYDROTEST PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-01-28 | 2018-05-08 13:28 | 2018-05-08 13:29 | Yes | 100 |  |  | 2018-05-13 16:30 | [5 empty] | 2018-05-13 20:00 | Yes | -9 | 1204-Owner-v | 2018-12-16 21:55
VD-9001-460A-ITP-001 | 3 | Inspection Test Plan | PI-460A | Nia Shimi Co. | 2018-01-28 | 2018-02-17 10:23 | 2018-01-29 13:31 | Yes | 1 |  |  | 2018-03-03 09:57 | [5 empty] | 2018-03-03 10:02 | Yes | 0
VD-9001-251-DWG-016 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:24 | 2018-04-18 16:34 | Yes | 80 |  |  |  | 2018-04-28 17:32 |  |  |  |  | 2018-04-28 17:32 | Yes | -4 | 1204-Owner-v | 2019-01-29 10:11
VD-9001-251-DWG-017 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:36 | 2018-04-18 16:49 | Yes | 80 |  |  | 2018-04-25 19:25 | [5 empty] | 2018-04-25 19:25 | Yes | -7 | 1204-Owner-v | 2019-01-28 10:39
VD-9001-251-DWG-018 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:36 | 2018-04-18 16:50 | Yes | 80 |  |  |  | 2018-04-28 17:38 |  |  |  |  | 2018-04-28 17:38 | Yes | -4
VD-9001-251-DWG-019 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:50 | 2018-04-18 16:55 | Yes | 80 |  |  |  | 2018-04-28 17:45 |  |  |  |  | 2018-04-28 17:45 | Yes | -4
VD-9001-251-DWG-020 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:52 | 2018-04-18 16:55 | Yes | 80 |  |  |  | 2018-04-28 17:55 |  |  |  |  | 2018-04-28 17:55 | Yes | -4
VD-9001-251-DWG-021 | 1 | CONVECTION COIL DRAWING & MANIFOLD HE-1004B | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-04-18 16:57 | 2018-04-18 17:02 | Yes | 80 |  |  |  | 2018-04-28 17:55 |  |  |  |  | 2018-04-28 20:00 | Yes | -4
VD-9001-251-PFD-001 | 1 | PROCESS FLOW DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2018-01-28 | 2018-08-29 14:48 | 2018-08-29 14:53 | Yes | 213 |  |  |  |  | 2019-02-18 17:33 |  |  |  | 2019-02-18 17:33 | Yes | 159 | 1204-Owner-v | 2019-07-15 13:29
VD-9001-201-PCJ-008 | 1 | PAINTING/CLEANING/DRYING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2018-01-29 | 2018-05-25 19:06 | 2018-05-25 19:06 | Yes | 116 |  |  | 2018-06-17 12:23 | [5 empty] | 2018-06-17 12:23 | Yes | 9 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-201-DWG-007 | 2 | NAMEPLATE DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2018-01-29 | 2018-04-12 19:43 | 2018-04-12 19:44 | Yes | 73 |  |  | 2018-04-22 11:36 | [5 empty] | 2018-04-22 11:36 | Yes | -4 | 1204-Owner-v | 2018-06-27 12:56
VD-9001-104-DCR-002 | 1 | Civil and structure design criteria | PR-104 | AIR LIQUIDE | 2018-02-12 20:00 | 2018-03-30 17:47 | 2018-03-30 17:49 | Yes | 46 |  |  | 2018-04-15 10:04 | [5 empty] | 2018-04-15 20:00 | Yes | 2 | 1204-Owner-v | 2019-12-10 18:02
VD-9001-257C-CAL-011 | 0 | FINITE ELEMENT ANALYSIS (4137-0366/FEA) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-01-30 12:01 |  | No | -8 |  |  |  | 2018-04-21 16:37 |  |  |  |  | 2018-04-21 16:37 | Yes | 0
VD-9001-257C-CAL-012 | 0 | FINITE ELEMENT ANALYSIS (4137-0367/FEA) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-07 | 2018-05-21 14:07 | 2018-05-21 14:07 | Yes | 103 |  |  | 2018-09-15 15:01 | [5 empty] | 2018-09-15 15:01 | Yes | 103
VD-9001-301-CSS-001 | 0 | planning notes syngas turbine (limiting and protection) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:12 |  | No | 19 | 2018-02-13 15:00 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CSS-002 | 0 | planning notes syngas turbine (piping; equipm.; found.) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:13 |  | No | 19 | 2018-02-13 15:55 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CSS-003 | 0 | planning notes syngas turbine (drains) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:13 |  | No | 19 | 2018-02-13 15:05 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CSS-004 | 0 | planning notes circulator turbine (limiting and protection) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:17 |  | No | 19 | 2018-02-13 15:52 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CSS-005 | 0 | planning notes circulator turbine (piping; equipm.; found.) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:17 |  | No | 19 | 2018-02-13 15:10 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-CSS-006 | 0 | planning notes circulator turbine (drains) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:17 |  | No | 19 | 2018-02-13 15:45 | [7 empty] | 2018-02-13 20:00 | Yes | 0
VD-9001-301-DSH-022 | 0 | syngas turbine (data sheet) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:30 |  | No | 19 | 2018-02-27 09:39 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-07-21 17:37
VD-9001-301-DSH-023 | 0 | circulator turbine (data sheet) | MC-301 | Siemens AG | 2018-01-11 | 2018-01-30 11:30 |  | No | 19 | 2018-02-27 09:51 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-07-24 14:12
VD-9001-201-DWG-008 | 1 | SHIPPING DRAWING | PV-201 | ATB RIVA CALZONI SpA | 2018-01-30 | 2018-04-16 16:24 | 2018-04-16 16:25 | Yes | 76 |  |  | 2018-06-12 16:47 | [5 empty] | 2018-06-12 16:48 | Yes | 43 | 1204-Owner-v | 2018-05-15 16:30
VD-9001-201-CAL-004 | 1 | SHIPPING SADDLES CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2018-01-30 | 2018-04-16 16:25 | 2018-04-16 16:27 | Yes | 76 |  |  | 2018-06-12 16:39 | [5 empty] | 2018-06-12 16:39 | Yes | 43 | 1204-Owner-v | 2018-12-16 21:34
VD-9001-104-LST-012 | 1 | Consumers list | PR-104 | AIR LIQUIDE | 2018-02-13 20:00 | 2018-03-12 18:20 | 2018-03-12 18:54 | Yes | 27 |  |  |  | 2018-04-16 17:43 |  |  |  |  | 2018-04-16 20:00 | Yes | 21 | 1204-Owner-v | 2018-04-07 09:53
VD-9001-104(001)-CAL-001 | 0 | Piping flexibility calculation notes 1 | PR-104-SUB | AIR LIQUIDE | 2018-04-03 |  |  | No | 808 | [9 empty] | No | 0
VD-9001-104(001)-CAL-002 | 0 | Piping flexibility calculation notes 2 | PR-104-SUB | AIR LIQUIDE | 2018-04-03 |  |  | No | 808 | [9 empty] | No | 0
VD-9001-104(001)-CAL-003 | 0 | Piping flexibility calculation notes 3 | PR-104-SUB | AIR LIQUIDE | 2018-04-03 |  |  | No | 808 | [9 empty] | No | 0
VD-9001-104(001)-PLN-001 | 0 | Area A1 - ACC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-002 | 0 | Area A2 - ACC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-003 | 0 | Area A3 - ACC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-004 | 0 | Area B1 - WCC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-005 | 0 | Area B2 - WCC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-006 | 0 | Area B3 - WCC Compressor Building Area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-007 | 0 | Area C1 - E-6108 Regeneration Heater Valve Manifold Platform | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-008 | 0 | Area C2 - E-6108 Regeneration Heater Valve Manifold Platform | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-009 | 0 | Area D1 - Pipe rack -Interconnection Tie in Valve Manifold Platform | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-010 | 0 | Area D2 - Pipe rack -Interconnection Tie in Valve Manifold Platform | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-011 | 0 | Area E1 - Air Cooled Condensers area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-PLN-012 | 0 | Area E2 - Air Cooled Condensers area | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-LST-033 | 0 | Warm part - General piping supports list | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-DWG-004 | 0 | Area A - Warm part - Special supports book + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-DWG-005 | 0 | Area B - Warm part - Special supports book + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-DWG-006 | 0 | Area C - Warm part - Special supports book + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-DWG-007 | 0 | Area D - Warm part - Special supports book + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-DWG-008 | 0 | Area E - Warm part - Special supports book + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(001)-ISO-001 | 0 | Area A - Warm part - Isometric Booklet - CS | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-ISO-002 | 0 | Area B - Warm part - Isometric Booklet - CS | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-ISO-003 | 0 | Area C - Warm part - Isometric Booklet - CS | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-ISO-004 | 0 | Area D - Warm part - Isometric Booklet - CS | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-ISO-005 | 0 | Area E - Warm part - Isometric Booklet - CS | PR-104-SUB | AIR LIQUIDE | 2018-07-03 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(001)-MAL-001 | 0 | Area A - Warm part -Bolting BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-29 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-MAL-002 | 0 | Area B - Warm part -Bolting BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-29 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-MAL-003 | 0 | Area C - Warm part -Bolting BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-29 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-MAL-004 | 0 | Area D - Warm part -Bolting BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-29 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-MAL-005 | 0 | Area E - Warm part -Bolting BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-29 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-LST-034 | 0 | All Area - Warm part - List of Reinforced pads | PR-104-SUB | AIR LIQUIDE | 2018-05-08 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104(001)-LST-035 | 0 | All Area - Warm part - List of mittered bends | PR-104-SUB | AIR LIQUIDE | 2018-05-08 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104(001)-LST-036 | 0 | All Area - Warm part - List of piping related special items (PTFE, Permali,..) | PR-104-SUB | AIR LIQUIDE | 2018-10-02 |  |  | No | 626 | [9 empty] | No | 0
VD-9001-104(003)-SKT-001 | 0 | T-6101/E-6102/T-6102 - Equipment sketch | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-02-12 17:49 |  | No | 2 | 2018-02-22 10:52 | [7 empty] | 2018-02-22 19:59 | Yes | 0
VD-9001-104(003)-DWG-001 | 0 | T-6102 - General arrangement drawing (for client) | PR-104-SUB | AIR LIQUIDE | 2018-03-03 | 2018-04-17 16:24 | 2018-04-17 17:33 | Yes | 45 |  |  |  | 2018-05-03 17:12 |  |  |  |  | 2018-05-03 19:59 | Yes | 2
VD-9001-104(003)-DWG-002 | 0 | T-6102 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-17 16:27 | 2018-04-17 17:33 | Yes | 17 |  |  | 2018-05-06 17:20 | [5 empty] | 2018-05-06 20:00 | Yes | 5 | 1204-Owner-v | 2018-05-06 15:27
VD-9001-104(003)-DWG-003 | 0 | T-6102 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-17 16:27 | 2018-04-17 19:01 | Yes | 17 |  |  | 2018-05-06 17:52 | [5 empty] | 2018-05-06 20:00 | Yes | 5
VD-9001-104(003)-DWG-004 | 0 | T-6102 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-17 16:27 | 2018-04-17 17:32 | Yes | 17 |  |  |  | 2018-05-06 17:12 |  |  |  |  | 2018-05-06 20:00 | Yes | 5
VD-9001-104(003)-DWG-005 | 0 | T-6102 - Assembly drawing Piping support | PR-104-SUB | AIR LIQUIDE | 2018-03-31 |  |  | No | 811 | [9 empty] | No | 0
VD-9001-104(003)-LST-001 | 0 | T-6102 - Parts list (for client) | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-04-17 16:28 | 2018-04-17 17:31 | Yes | 18 |  |  |  | 2018-04-26 11:46 |  |  |  |  | 2018-04-26 20:00 | Yes | -5
VD-9001-104(003)-CAL-001 | 0 | T-6102 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-26 14:21 | 2018-03-26 14:25 | Yes | -5 |  |  |  | 2018-04-26 11:26 |  |  |  |  | 2018-04-26 20:00 | Yes | 17
VD-9001-104(003)-WBK-001 | 0 | T-6102 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-03-15 | 2018-04-20 19:37 | 2018-04-20 19:38 | Yes | 36 |  |  |  | 2018-04-26 11:17 |  |  |  |  | 2018-04-26 20:00 | Yes | -8
VD-9001-104(003)-ITP-001 | 0 | T-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-02-23 18:02 |  | No | 13 |  |  |  | 2018-03-17 18:30 |  |  |  |  | 2018-03-17 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 09:43
VD-9001-104(003)-IPM-001 | 0 | T-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-03-15 | 2018-03-22 17:10 | 2018-03-22 17:15 | Yes | 7 |  |  |  | 2018-04-16 18:39 |  |  |  |  | 2018-04-16 20:00 | Yes | 11
VD-9001-104(003)-IPM-002 | 0 | T-6102 - CLEANING PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-03-22 17:10 | 2018-03-22 17:15 | Yes | 40 |  |  | 2018-04-30 09:49 | [5 empty] | 2018-04-30 20:00 | Yes | 25
VD-9001-104(003)-IPM-003 | 0 | T-6102 - FERRITEE CHECK PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-03-22 17:10 | 2018-03-22 17:15 | Yes | 40 |  |  | 2018-04-18 08:52 | [5 empty] | 2018-04-18 20:00 | Yes | 13 | 1204-Owner-v | 2019-02-02 16:47
VD-9001-104(003)-IPM-004 | 0 | T-6102 - NDE [RT+PT) PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-03-22 17:11 | 2018-03-22 17:15 | Yes | 40 |  |  | 2018-04-18 08:57 | [5 empty] | 2018-04-18 20:00 | Yes | 13
VD-9001-104(003)-IPM-005 | 0 | T-6102 - DIMENSIONAL & VISUAL CHECK PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-03-22 17:10 | 2018-03-22 17:15 | Yes | 40 |  |  | 2018-04-18 08:54 | [5 empty] | 2018-04-18 20:00 | Yes | 13
VD-9001-104(003)-IPM-006 | 0 | T-6102 - IDENTIFICATION & TRACEABILITY PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-02-10 |  |  | No | 860 | [9 empty] | No | 0
VD-9001-104(003)-DWG-006 | 0 | T-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-03-15 | 2018-04-17 16:23 | 2018-04-17 17:32 | Yes | 33 |  |  |  | 2018-05-12 11:10 |  |  |  |  | 2018-05-12 19:59 | Yes | 11
VD-9001-104(003)-MDB-001 | 0 | T-6102 - Manufacturer Data Report | PR-104-SUB | AIR LIQUIDE | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-104(003)-MDB-002 | 0 | T-6102 - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-09-11 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-104(003)-SKT-002 | 0 | T-6102 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-04-24 18:16 | 2018-04-24 18:20 | Yes | -7 |  |  |  | 2018-07-22 16:13 |  |  |  |  | 2018-07-22 20:00 | Yes | 75
VD-9001-104(003)-MTO-001 | 0 | T-6102 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-104(003)-IPM-007 | 0 | T-6102 - & T-6101 - COLUMNS ASSEMBLLY PROCEDURE | PR-104-SUB | AIR LIQUIDE | 2018-05-11 | 2018-03-22 17:15 | 2018-03-22 17:15 | Yes | -50 |  |  | 2018-04-30 09:46 | [5 empty] | 2018-04-30 20:00 | Yes | 25
VD-9001-104(002)-DWG-001 | 0 | E-6102 - Vaporizer shell - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-23 | 2018-02-01 17:47 |  | No | -22 | 2018-02-21 16:04 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(002)-DWG-002 | 0 | D-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-01-13 | 2018-02-01 17:32 |  | No | 19 | 2018-02-10 17:40 | [7 empty] | 2018-02-10 20:00 | Yes | 0
VD-9001-104(002)-DWG-003 | 0 | D-6103 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-02-01 17:22 |  | No | -9 | 2018-02-10 16:31 | [7 empty] | 2018-02-10 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-22 15:59
VD-9001-104(002)-LST-001 | 0 | D-6103 - Parts list | PR-104-SUB | AIR LIQUIDE | 2018-03-10 | 2018-03-12 16:22 | 2018-03-12 16:37 | Yes | 2 |  |  | 2018-04-10 17:40 | [5 empty] | 2018-04-10 20:00 | Yes | 15 | 1204-Owner-v | 2019-10-16 08:24
VD-9001-104(002)-CAL-001 | 0 | D-6103 - Calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-02-01 17:13 |  | No | -9 | 2018-02-27 19:08 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104(002)-WBK-001 | 0 | D-6103 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-01-31 11:33 |  | No | -10 | 2018-02-21 18:56 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(002)-ITP-001 | 0 | D-6103 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-01-31 11:33 |  | No | -10 | 2018-02-17 17:01 | [7 empty] | 2018-02-17 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 09:44
VD-9001-104(002)-IPM-001 | 0 | D-6103 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-02-24 | 2018-03-16 16:00 | 2018-03-16 16:43 | Yes | 20 |  |  |  | 2018-04-12 14:14 |  |  |  |  | 2018-04-12 20:00 | Yes | 13
VD-9001-104(002)-IPM-002 | 0 | D-6103 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-02-24 | 2018-05-22 13:34 | 2018-05-22 13:36 | Yes | 87 |  |  | 2018-06-18 09:15 | [5 empty] | 2018-06-18 20:00 | Yes | 13
VD-9001-104(002)-DWG-004 | 0 | D-6103 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-02-01 17:22 | 2018-02-01 17:23 | Yes | -65 |  | 2018-02-10 16:16 | [6 empty] | 2018-02-10 20:00 | Yes | -5 | 1204-Owner-v | 2020-01-14 10:09
VD-9001-104(002)-MDB-001 | 0 | D-6103 - Manufacturer Data Report | PR-104-SUB | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(002)-MDB-002 | 0 | D-6103 - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-12-21 |  |  | No | 546 | [9 empty] | No | 0
VD-9001-104(002)-SKT-001 | 0 | D-6103 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-11-09 | 2018-05-22 13:54 | 2018-05-22 13:59 | Yes | -171 |  |  | 2018-07-22 16:18 | [5 empty] | 2018-07-22 20:00 | Yes | 47
VD-9001-104(002)-MTO-001 | 0 | D-6103 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(002)-DWG-005 | 0 | T-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-12-21 | 2018-02-01 17:40 |  | No | -323 | 2018-02-22 11:40 | [7 empty] | 2018-02-22 19:59 | Yes | 0
VD-9001-104(002)-DWG-006 | 0 | T-6101/T-6102 - Civil work drawing / loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-01-23 | 2018-03-08 17:06 | 2018-07-08 11:56 | Yes | 44 |  |  |  | 2018-07-10 16:32 |  |  |  |  | 2018-07-10 20:00 | Yes | 110 | 1204-Owner-v | 2018-05-06 13:05
VD-9001-104(002)-DWG-007 | 0 | T-6101 - Anchoring details | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-04-10 21:14 | 2018-04-10 21:16 | Yes | 36 |  |  |  | 2018-06-30 17:26 |  |  |  |  | 2018-06-30 20:00 | Yes | 67
VD-9001-104(002)-DWG-008 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 12:31 | 2018-03-12 13:01 | Yes | 7 |  |  |  | 2018-03-18 18:14 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-009 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 12:31 | 2018-03-12 13:01 | Yes | 7 |  |  |  | 2018-03-18 18:17 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-010 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 16:38 | 2018-03-12 18:54 | Yes | 7 |  |  |  | 2018-03-18 17:43 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-011 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 16:38 | 2018-03-12 18:55 | Yes | 7 |  |  |  | 2018-03-18 17:59 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-012 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 16:38 | 2018-03-12 18:55 | Yes | 7 |  |  |  | 2018-03-18 18:03 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-013 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-20 16:10 | 2018-03-20 16:15 | Yes | 15 |  |  |  | 2018-04-15 11:11 |  |  |  |  | 2018-04-15 20:00 | Yes | 12
VD-9001-104(002)-DWG-014 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 16:39 | 2018-03-12 18:55 | Yes | 7 |  |  |  | 2018-03-18 18:05 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-015 | 0 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-03-12 16:39 | 2018-03-12 18:55 | Yes | 7 |  |  |  | 2018-03-18 18:11 |  |  |  |  | 2018-03-18 21:00 | Yes | -8
VD-9001-104(002)-DWG-016 | 0 | T-6101 - Assembly drawing Piping support | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-05-04 17:58 | 2018-05-04 19:20 | Yes | 60 |  |  | 2018-05-07 15:57 | [5 empty] | 2018-05-07 20:00 | Yes | -11
VD-9001-104(002)-LST-002 | 0 | T-6101 - Parts list | PR-104-SUB | AIR LIQUIDE | 2018-02-20 | 2018-05-28 12:43 | 2018-05-28 12:52 | Yes | 97 |  |  |  | 2018-06-09 17:03 |  |  |  |  | 2018-06-09 19:59 | Yes | -2
VD-9001-104(002)-CAL-002 | 0 | T-6101 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-04-09 | 2018-02-01 17:18 |  | No | -67 | 2018-02-19 17:32 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-104(002)-WBK-002 | 0 | T-6101 & E-6102 - Vaporizer shell - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-02-10 | 2018-01-31 11:34 |  | No | -10 | 2018-02-21 19:01 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(002)-ITP-002 | 0 | T-6101 & E-6102 - Vaporizer shell - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-09 | 2018-01-31 11:33 |  | No | -9 | 2018-02-17 16:09 | [7 empty] | 2018-02-17 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 09:43
VD-9001-104(002)-IPM-003 | 0 | T-6101 & E-6102 - Vaporizer shell - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-02-09 | 2018-03-16 16:00 | 2018-03-16 16:43 | Yes | 35 |  |  |  | 2018-04-15 15:50 |  |  |  |  | 2018-04-15 20:01 | Yes | 16
VD-9001-104(002)-DWG-017 | 0 | T-6101 & E-6102 - Vaporizer shell - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-02-09 | 2018-04-26 18:23 | 2018-08-02 11:43 | Yes | 76 |  |  |  | 2018-08-13 16:58 |  |  |  |  | 2018-08-13 19:59 | Yes | 95
VD-9001-104(002)-MDB-003 | 0 | T-6101 & E-6102 - Vaporizer shell - Manufacturer Data Report | PR-104-SUB | AIR LIQUIDE | 2018-02-23 |  |  | No | 847 | [9 empty] | No | 0
VD-9001-104(002)-MDB-004 | 0 | T-6101 & E-6102 - Vaporizer shell - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-12-16 |  |  | No | 551 | [9 empty] | No | 0
VD-9001-104(002)-SKT-002 | 0 | T-6101 & E-6102 - Vaporizer shell - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-11-09 | 2018-05-22 13:54 | 2018-05-22 13:59 | Yes | -171 |  |  | 2018-07-22 08:36 | [5 empty] | 2018-07-22 19:59 | Yes | 47
VD-9001-104(002)-MTO-002 | 0 | T-6101 & E-6102 - Vaporizer shell - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(002)-MNL-001 | 0 | T-6101 & E-6102 - Vaporizer shell - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-12-21 |  |  | No | 546 | [9 empty] | No | 0
VD-9001-104(005)-DWG-001 | 0 | E-6101/E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-10 | 2018-03-16 14:15 | 2018-03-16 14:43 | Yes | 6 |  |  |  | 2018-04-10 17:33 |  |  |  |  | 2018-04-10 20:00 | Yes | 11
VD-9001-104(005)-DWG-002 | 0 | E-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-24 | 2018-02-22 18:28 |  | No | -2 |  |  |  | 2018-03-14 08:57 |  |  |  |  | 2018-03-14 20:00 | Yes | 0
VD-9001-104(005)-DWG-003 | 0 | E-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-24 | 2018-02-22 18:28 |  | No | -2 |  |  |  | 2018-03-13 17:25 |  |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-104(005)-DWG-004 | 0 | E-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-24 | 2018-05-04 12:58 | 2018-05-04 13:46 | Yes | 10 |  |  |  | 2018-05-22 16:01 |  |  |  |  | 2018-05-22 19:59 | Yes | 4
VD-9001-104(005)-DWG-005 | 0 | E-6103 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-24 | 2018-04-27 18:01 | 2018-04-27 18:24 | Yes | 3 |  |  |  | 2018-05-29 17:12 |  |  |  |  | 2018-05-29 19:59 | Yes | 18
VD-9001-104(005)-DWG-006 | 0 | E-6101 - Support drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-19 |  |  | No | 731 | [9 empty] | No | 0
VD-9001-104(005)-DWG-007 | 0 | E-6103 - Support drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-19 |  |  | No | 731 | [9 empty] | No | 0
VD-9001-104(005)-CAL-001 | 0 | E-6101 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-04-10 | 2018-05-04 13:47 | 2018-05-04 13:58 | Yes | 24 |  |  |  | 2018-05-22 09:07 |  |  |  |  | 2018-05-22 19:59 | Yes | 4
VD-9001-104(005)-CAL-002 | 0 | E-6103 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-04-10 | 2018-04-27 18:02 | 2018-04-27 18:25 | Yes | 17 |  |  |  | 2018-05-22 09:12 |  |  |  |  | 2018-05-22 19:59 | Yes | 11
VD-9001-104(005)-WBK-001 | 0 | E-6101/E-6103 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-04-24 | 2018-05-04 13:58 | 2018-05-04 13:58 | Yes | 10 |  |  |  | 2018-06-11 11:19 |  |  |  |  | 2018-06-11 19:59 | Yes | 24
VD-9001-104(005)-ITP-001 | 0 | E-6101 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:13 | 2018-03-08 16:35 | Yes | -12 |  |  |  | 2018-04-15 15:45 |  |  |  |  | 2018-04-15 20:01 | Yes | 24 | 1204-Owner-v | 2020-01-01 09:41
VD-9001-104(005)-ITP-002 | 0 | E-6103 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:13 | 2018-03-08 16:35 | Yes | -12 |  |  |  | 2018-03-19 15:28 |  |  |  |  | 2018-03-19 21:00 | Yes | -3 | 1204-Owner-v | 2020-01-01 09:41
VD-9001-104(005)-IPM-001 | 0 | E-6101/E-6103 - Pressure / leak test procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:10 | 2018-03-08 16:35 | Yes | -12 |  |  |  | 2018-04-09 10:35 |  |  |  |  | 2018-04-09 20:00 | Yes | 18
VD-9001-104(005)-IPM-002 | 0 | E-6101/E-6103 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:09 | 2018-03-08 16:35 | Yes | -12 |  |  |  | 2018-04-11 14:29 |  |  |  |  | 2018-04-11 20:00 | Yes | 20
VD-9001-104(005)-DWG-008 | 0 | E-6101/E-6103 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-22 | 2018-05-04 12:59 | 2018-05-04 13:46 | Yes | -18 |  |  |  | 2018-05-12 14:38 |  |  |  |  | 2018-05-12 19:59 | Yes | -6
VD-9001-104(005)-MDB-001 | 0 | E-6101/E-6103 - Manufacturer Data Report | PR-104-SUB | AIR LIQUIDE | 2018-09-02 |  |  | No | 656 | [9 empty] | No | 0
VD-9001-104(005)-MDB-002 | 0 | E-6101/E-6103 - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-09-02 |  |  | No | 656 | [9 empty] | No | 0
VD-9001-104(005)-SKT-001 | 0 | E-6101 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-06-19 |  |  | No | 731 | [9 empty] | No | 0
VD-9001-104(005)-MTO-001 | 0 | E-6101/E-6103 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-02 |  |  | No | 656 | [9 empty] | No | 0
VD-9001-104(005)-MNL-001 | 0 | E-6101/E-6103 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-05-22 |  |  | No | 759 | [9 empty] | No | 0
VD-9001-104(006)-DWG-001 | 0 | E-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-10 | 2018-02-22 17:48 |  | No | -16 |  |  |  | 2018-03-13 17:13 |  |  |  |  | 2018-03-13 20:00 | Yes | 0
VD-9001-104(006)-WBK-001 | 0 | E-6102 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:11 | 2018-03-08 16:38 | Yes | -12 |  |  |  | 2018-04-09 10:15 |  |  |  |  | 2018-04-09 20:00 | Yes | 18
VD-9001-104(006)-ITP-001 | 0 | E-6102 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-07 14:39 | 2018-03-08 14:40 | Yes | -13 |  |  |  | 2018-04-09 10:45 |  |  |  |  | 2018-04-09 20:00 | Yes | 19 | 1204-Owner-v | 2020-01-01 09:37
VD-9001-104(006)-IPM-001 | 0 | E-6102 - Pressure / leak test procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-08 15:13 | 2018-03-08 16:36 | Yes | -12 |  |  |  | 2018-04-11 14:31 |  |  |  |  | 2018-04-11 20:00 | Yes | 20
VD-9001-104(006)-IPM-002 | 0 | E-6102 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-03-20 | 2018-03-20 19:15 | 2018-03-20 19:16 | Yes | 0 |  |  |  | 2018-04-12 14:18 |  |  |  |  | 2018-04-12 20:00 | Yes | 9
VD-9001-104(006)-DWG-002 | 0 | E-6102 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-22 | 2018-04-10 20:35 | 2018-04-10 20:36 | Yes | -42 |  |  |  | 2018-05-09 16:13 |  |  |  |  | 2018-05-09 19:59 | Yes | 15
VD-9001-104(006)-MDB-001 | 0 | E-6102 - Manufacturer Data Report | PR-104-SUB | AIR LIQUIDE | 2018-09-02 |  |  | No | 656 | [9 empty] | No | 0
VD-9001-104(006)-MDB-002 | 0 | E-6102 - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-09-02 |  |  | No | 656 | [9 empty] | No | 0
VD-9001-104(006)-MNL-001 | 0 | E-6102 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-05-22 |  |  | No | 759 | [9 empty] | No | 0
VD-9001-104(007)-DWG-001 | 0 | DR-6101A / DR-6101B - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-15 | 2018-02-14 18:20 |  | No | -1 | 2018-02-21 18:47 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(007)-SKT-001 | 0 | DR-6101A / DR-6101B - Filter - Equipment sketch | PR-104-SUB | AIR LIQUIDE | 2018-04-01 | 2018-02-14 18:21 |  | No | -46 | 2018-02-21 17:52 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(007)-DWG-002 | 0 | DR-6101A / DR-6101B - Civil work drawing / loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-03-15 | 2018-02-14 18:19 |  | No | -29 | 2018-02-21 17:37 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(007)-DWG-003 | 0 | DR-6101A / DR-6101B - Bottom part detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-02-14 18:20 | 2018-02-14 18:21 | Yes | -15 |  | 2018-02-21 16:18 | [6 empty] | 2018-02-21 20:00 | Yes | -7
VD-9001-104(007)-DWG-004 | 0 | DR-6101A / DR-6101B - Upper part details drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-02-14 18:20 | 2018-02-14 18:21 | Yes | -15 |  | 2018-02-21 16:22 | [6 empty] | 2018-02-21 20:00 | Yes | -7
VD-9001-104(007)-DWG-005 | 0 | DR-6101A / DR-6101B - Details drawings | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-02-14 18:20 |  | No | -15 | 2018-02-21 16:46 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(007)-LST-001 | 0 | DR-6101A / DR-6101B - Envelop parts list | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-02-14 18:20 |  | No | -15 | 2018-02-21 17:45 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104(007)-CAL-001 | 0 | DR-6101A / DR-6101B - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-03-08 14:45 | 2018-03-08 16:32 | Yes | 7 |  |  |  | 2018-04-25 14:34 |  |  |  |  | 2018-04-25 20:00 | Yes | 34
VD-9001-104(007)-CAL-002 | 0 | DR-6101A / DR-6101B - Fatigue calculation note | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-03-08 14:47 | 2018-03-08 16:32 | Yes | 7 |  |  |  | 2018-04-25 11:45 |  |  |  |  | 2018-04-25 20:00 | Yes | 34
VD-9001-104(007)-WBK-001 | 0 | DR-6101A / DR-6101B - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-02-15 | 2018-05-02 18:02 | 2018-05-02 18:04 | Yes | 76 |  |  |  | 2018-05-08 17:45 |  |  |  |  | 2018-05-08 19:59 | Yes | -8
VD-9001-104(007)-ITP-001 | 0 | DR-6101A / DR-6101B - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-15 | 2018-05-02 17:54 | 2018-05-02 18:03 | Yes | 76 |  |  |  | 2018-05-08 17:47 |  |  |  |  | 2018-05-08 19:59 | Yes | -8 | 1204-Owner-v | 2020-01-01 10:02
VD-9001-104(007)-IPM-001 | 0 | DR-6101A / DR-6101B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-05-02 18:10 | 2018-05-02 18:11 | Yes | 62 |  |  |  | 2018-05-15 10:29 |  |  |  |  | 2018-05-15 19:59 | Yes | -1
VD-9001-104(007)-IPM-002 | 0 | DR-6101A / DR-6101B - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-05-02 17:56 | 2018-05-02 18:03 | Yes | 62 |  |  | 2018-05-15 11:29 | [5 empty] | 2018-05-15 19:59 | Yes | -1
VD-9001-104(007)-DWG-006 | 0 | DR-6101A / DR-6101B - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-03-01 | 2018-02-14 18:20 | 2018-02-14 18:21 | Yes | -15 |  | 2018-02-20 15:16 | [6 empty] | 2018-02-20 19:59 | Yes | -8
VD-9001-104(007)-MDB-001 | 0 | DR-6101A / DR-6101B - Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-10-30 |  |  | No | 598 | [9 empty] | No | 0
VD-9001-104(007)-MDB-002 | 0 | DR-6101A / DR-6101B - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-10-30 |  |  | No | 598 | [9 empty] | No | 0
VD-9001-104(007)-SKT-002 | 0 | DR-6101A / DR-6101B - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-09-30 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-104(007)-MTO-001 | 0 | DR-6101A / DR-6101B - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-30 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-104(007)-LST-002 | 0 | DR-6101A / DR-6101B - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-09-30 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-104(007)-MNL-001 | 0 | DR-6101A / DR-6101B - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-30 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-104(001)-LST-032 | 0 | Tie-ins list drawing ( with Client) | PR-104-SUB | AIR LIQUIDE | 2018-03-03 | 2018-03-09 12:58 | 2018-03-09 18:02 | Yes | 6 |  |  |  | 2018-03-18 16:43 |  |  |  |  | 2018-03-18 21:00 | Yes | -5 | 1204-Owner-v | 2020-02-16 11:48
VD-9001-104(004)-IPM-001 | 0 | C-6101 / C-6102 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-03 | 2018-02-14 20:45 | 2018-02-14 20:46 | Yes | -17 |  | 2018-02-19 17:18 | [6 empty] | 2018-02-19 20:00 | Yes | -9
VD-9001-104(004)-LST-001 | 0 | ST C-6101 / C-6101 - Lubricant List | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-LST-002 | 0 | ST C-6102 / C-6102 - Lubricant List | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-PCU-001 | 0 | C-6101 / C-6102 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-02-03 | 2018-02-08 14:59 |  | No | 5 | 2018-02-27 19:40 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104(004)-MSS-001 | 0 | C-6101 / C-6102 - Motor electrical specification of lube oil pump | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-PID-001 | 0 | C-6101 / C-6102 - PID symbols summary page | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-23 12:57 |  | No | 6 |  |  |  | 2018-03-19 10:40 |  |  |  |  | 2018-03-19 21:00 | Yes | 0
VD-9001-104(004)-PID-002 | 0 | C-6101 - PID process | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:56 |  | No | -9 | 2018-02-27 19:47 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2018-09-22 10:49
VD-9001-104(004)-PID-003 | 0 | C-6101 - PID oil system | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:57 |  | No | -9 | 2018-02-27 19:36 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104(004)-PID-004 | 0 | C-6101 - PID mechanical | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:58 |  | No | -9 | 2018-02-27 19:44 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104(004)-DWG-001 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:55 |  | No | -9 | 2018-02-17 15:05 | [7 empty] | 2018-02-17 20:00 | Yes | 0 | 1204-Owner-v | 2020-03-25 16:10
VD-9001-104(004)-LST-003 | 0 | C-6101 / C-6102 - Piping connection list | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 14:59 | 2018-02-08 15:00 | Yes | -9 |  | 2018-02-27 18:54 | [6 empty] | 2018-02-27 20:00 | Yes | 5
VD-9001-104(004)-DWG-002 | 0 | C-6101 / C-6102 - Instruments and electrical arrangement Layout | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-003 | 0 | C-6101 / C-6102 - Platform and access drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-004 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Local Switch board Drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-DWG-005 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:55 |  | No | -9 | 2018-02-27 19:01 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104(004)-DWG-006 | 0 | C-6102 / ST C-6102 : Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-15 18:34 | 2018-03-15 19:16 | Yes | 26 |  |  |  | 2018-03-26 10:24 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-104(004)-DWG-007 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Anchoring details (plate,bolt, etc) | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-DIG-001 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Wiring diagram | PR-104-SUB | AIR LIQUIDE | 2018-05-12 |  |  | No | 769 | [9 empty] | No | 0
VD-9001-104(004)-DWG-008 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Junction boxes details | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-DWG-009 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Instruments hook-up drawing with BOM | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-LST-004 | 0 | C-6101 / C-6102 - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-ISO-001 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Piping drawings / isometrics | PR-104-SUB | AIR LIQUIDE | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104(004)-DWG-010 | 0 | C-6101 / C-6102 - Coupling drawing -Driver to gear | PR-104-SUB | AIR LIQUIDE | 2018-04-28 | 2018-04-27 17:06 | 2018-04-27 17:06 | Yes | -1 |  |  | 2018-05-27 10:03 | [5 empty] | 2018-05-27 19:59 | Yes | 16
VD-9001-104(004)-DWG-011 | 0 | C-6101 / C-6102 - Coupling drawing - Gear to Compressor | PR-104-SUB | AIR LIQUIDE | 2018-04-28 | 2018-04-27 17:06 | 2018-04-27 17:10 | Yes | -1 |  |  | 2018-05-27 09:39 | [5 empty] | 2018-05-27 19:59 | Yes | 16 | 1204-Owner-v | 2020-03-25 16:10
VD-9001-104(004)-DWG-012 | 0 | C-6101 / C-6102 - Oil system arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104(004)-DWG-013 | 0 | C-6101 / C-6102 - Oil pump drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-014 | 0 | C-6101 / C-6102 - Lube oil filter drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-015 | 0 | C-6101 / C-6102 - Oil cooler drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-016 | 0 | C-6101 / C-6102 - Process cooler 1 - drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-017 | 0 | C-6101 / C-6102 - Process cooler 2 - drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-018 | 0 | C-6101 / C-6102 - Process cooler 3 - drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-019 | 0 | C-6101 / C-6102 - Process cooler 4 - drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-020 | 0 | C-6101 / C-6102 - Process After-cooler - drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DWG-021 | 0 | C-6101 / C-6102 - Instruments drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DSH-001 | 0 | C-6101 / C-6102 - Process cooler 1 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-15 18:36 | 2018-03-15 19:17 | Yes | -16 |  |  |  | 2018-04-17 11:48 |  |  |  |  | 2018-04-17 20:00 | Yes | 19
VD-9001-104(004)-DSH-002 | 0 | C-6101 / C-6102 - Process cooler 2 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-15 18:36 | 2018-03-15 19:17 | Yes | -16 |  |  |  | 2018-03-26 10:13 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-104(004)-DSH-003 | 0 | C-6101 / C-6102 - Process cooler 3 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-15 18:36 | 2018-03-15 19:17 | Yes | -16 |  |  |  | 2018-03-26 11:20 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-104(004)-DSH-004 | 0 | C-6101 / C-6102 - Process cooler 4 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-15 18:36 | 2018-03-15 19:17 | Yes | -16 |  |  |  | 2018-03-26 11:23 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-104(004)-DSH-005 | 0 | C-6101 / C-6102 - Process After cooler - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-03-15 18:36 | 2018-03-15 19:17 | Yes | -16 |  |  |  | 2018-03-18 17:35 |  |  |  |  | 2018-03-18 21:00 | Yes | -11
VD-9001-104(004)-ARP-001 | 0 | ST C-6101 / C-6101 - Torsional analysis for air compressor and driver train 1 | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-05-22 11:45 | 2018-05-22 11:50 | Yes | -4 |  |  |  | 2018-05-30 17:30 |  |  |  |  | 2018-05-30 19:59 | Yes | -6
VD-9001-104(004)-ARP-002 | 0 | ST C-6102 / C-6102 - Torsional analysis for air compressor and driver train 2 | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-05-22 11:44 | 2018-05-22 11:49 | Yes | -4 |  |  | 2018-05-30 17:24 | [5 empty] | 2018-05-30 19:59 | Yes | -6
VD-9001-104(004)-ARP-003 | 0 | C-6101 / C-6102 - Lateral analysis | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-05-22 11:45 | 2018-05-22 11:50 | Yes | -4 |  |  | 2018-06-11 09:23 | [5 empty] | 2018-06-11 19:59 | Yes | 6
VD-9001-104(004)-CAL-001 | 0 | C-6101 / C-6102 - Process cooler 1 - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-002 | 0 | C-6101 / C-6102 - Process cooler 2 - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-003 | 0 | C-6101 / C-6102 - Process cooler 3 - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-004 | 0 | C-6101 / C-6102 - Process cooler 4 - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-005 | 0 | C-6101 / C-6102 - Process After cooler - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-006 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Heat emission | PR-104-SUB | AIR LIQUIDE | 2018-06-23 | 2018-03-07 16:33 | 2018-03-08 15:14 | Yes | -108 |  |  |  | 2018-04-25 11:57 |  |  |  |  | 2018-04-25 20:00 | Yes | 35
VD-9001-104(004)-WBK-001 | 0 | C-6101 / C-6102 - Process cooler 1 - welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-WBK-002 | 0 | C-6101 / C-6102 - Process cooler 2 - welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-WBK-003 | 0 | C-6101 / C-6102 - Process cooler 3 - welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-WBK-004 | 0 | C-6101 / C-6102 - Process cooler 4 - welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-WBK-005 | 0 | C-6101 / C-6102 - Process After cooler - welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CER-001 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-104(004)-ITP-001 | 0 | C-6101 / C-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-08 13:58 |  | No | -9 | 2018-02-27 19:29 | [7 empty] | 2018-02-27 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 09:43
VD-9001-104(004)-ITP-002 | 0 | C-6101 / C-6102 - Process Cooler ITP | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-IPM-002 | 0 | C-6101 / C-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-05-22 11:44 | 2018-05-22 11:49 | Yes | -4 |  |  |  |  | 2018-06-21 11:24 |  |  |  | 2018-06-21 20:00 | Yes | 16
VD-9001-104(004)-IPM-003 | 0 | C-6101 / C-6102 - Mechanical / performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-08-18 |  |  | No | 671 | [9 empty] | No | 0
VD-9001-104(004)-IPM-004 | 0 | C-6101 / C-6102 - Lube oil system tests procedure | PR-104-SUB | AIR LIQUIDE | 2018-08-18 |  |  | No | 671 | [9 empty] | No | 0
VD-9001-104(004)-IPM-005 | 0 | C-6101 / C-6102 - Prefabricated piping shop test procedure | PR-104-SUB | AIR LIQUIDE | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104(004)-IPM-006 | 0 | C-6101 / C-6102 - Shop inspection procedure - Auxiliaries | PR-104-SUB | AIR LIQUIDE | 2018-07-21 | 2018-05-24 18:05 | 2018-05-24 18:25 | Yes | -58 |  |  |  | 2018-06-19 17:31 |  |  |  |  | 2018-06-19 20:00 | Yes | 12
VD-9001-104(004)-IPM-007 | 0 | C-6101 / C-6102 - Shop inspection procedure - Compressor | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-04-20 13:02 | 2018-04-20 13:05 | Yes | -36 |  |  |  | 2018-06-03 18:03 |  |  |  |  | 2018-06-03 19:59 | Yes | 30
VD-9001-104(004)-IPM-008 | 0 | C-6101 / C-6102 - FAT Procedure for control panel | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-05-24 18:05 | 2018-05-24 18:25 | Yes | 54 |  |  |  | 2018-07-11 17:04 |  |  |  |  | 2018-07-11 20:00 | Yes | 34
VD-9001-104(004)-IPM-009 | 0 | C-6101 / C-6102 - Process Cooler shop test procedure | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-IPM-010 | 0 | C-6101 / C-6102 - Preservation procedure | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-INR-001 | 0 | C-6101 - Mechanical / Performances test report | PR-104-SUB | AIR LIQUIDE | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-104(004)-INR-002 | 0 | C-6102 - Mechanical / Performances test report | PR-104-SUB | AIR LIQUIDE | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-104(004)-DWG-022 | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-MDB-001 | 0 | C-6101 - Quality Record Book | PR-104-SUB | AIR LIQUIDE | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-104(004)-MDB-002 | 0 | C-6102 - Quality Record Book | PR-104-SUB | AIR LIQUIDE | 2019-02-15 |  |  | No | 490 | [9 empty] | No | 0
VD-9001-104(004)-MDB-003 | 0 | C-6101 / C-6102 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-01-06 |  |  | No | 895 | [9 empty] | No | 0
VD-9001-104(004)-SKT-001 | 0 | C-6101 / C-6102 - Transport and handling sketches ( included auxilaries) | PR-104-SUB | AIR LIQUIDE | 2018-12-22 |  |  | No | 545 | [9 empty] | No | 0
VD-9001-104(004)-LST-005 | 0 | C-6101 / C-6102 - Packing list | PR-104-SUB | AIR LIQUIDE | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-104(004)-LST-006 | 0 | C-6101 / C-6102 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(004)-MNL-001 | 0 | C-6101 / C-6102 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-10-13 |  |  | No | 615 | [9 empty] | No | 0
VD-9001-104(004)-IPM-011 | 0 | ST C-6101 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-04 15:15 | 2018-04-04 15:43 | Yes | 4 |  |  |  | 2018-04-23 18:01 |  |  |  |  | 2018-04-23 20:00 | Yes | 5
VD-9001-104(004)-PCU-002 | 0 | ST C-6101 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-04 15:17 | 2018-04-04 15:43 | Yes | 4 |  |  |  | 2018-04-12 14:26 |  |  |  |  | 2018-04-12 20:00 | Yes | -6
VD-9001-104(004)-DWG-023 | 0 | ST C-6101 - Gland sealing and leak-off system | PR-104-SUB | AIR LIQUIDE | 2018-04-28 | 2018-02-23 13:08 | 2018-02-23 13:09 | Yes | -64 |  |  | 2018-03-17 13:16 | [5 empty] | 2018-03-17 20:00 | Yes | 8 | 1204-Owner-v | 2019-12-09 10:20
VD-9001-104(004)-LST-007 | 0 | ST C-6101 - Allowable forces and moments | PR-104-SUB | AIR LIQUIDE | 2018-04-14 | 2018-02-07 19:01 | 2018-02-07 19:02 | Yes | -66 |  | 2018-02-13 10:58 | [6 empty] | 2018-02-13 20:00 | Yes | -8
VD-9001-104(004)-LST-008 | 0 | ST C-6101 - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-04-04 15:16 | 2018-04-04 15:43 | Yes | -52 |  |  | 2018-04-10 17:43 | [5 empty] | 2018-04-10 20:00 | Yes | -8
VD-9001-104(004)-ARP-004 | 0 | ST C-6101 - Lateral & torsional vibration analysis (turbine) | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DIG-002 | 0 | ST C-6101 - Campbell & goodman diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-23 | 2018-02-23 13:00 |  | No | -120 |  |  |  | 2018-03-14 14:48 |  |  |  |  | 2018-03-14 20:00 | Yes | 0
VD-9001-104(004)-CAL-007 | 0 | ST C-6101 - Axial Thrust Calculation | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-ITP-003 | 0 | ST C-6101/ST C-6102 - Inspection Test Plan / Quality Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-03 | 2018-02-08 13:56 |  | No | 5 | 2018-02-19 17:24 | [7 empty] | 2018-02-19 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:04
VD-9001-104(004)-IPM-012 | 0 | ST C-6101/ST C-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-23 | 2018-04-04 15:16 | 2018-04-04 15:43 | Yes | -80 |  |  |  | 2018-04-21 14:50 |  |  |  |  | 2018-04-21 20:00 | Yes | 3
VD-9001-104(004)-IPM-013 | 0 | ST C-6101/ST C-6102 - Mechanical tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-INR-003 | 0 | ST C-6101 - Mechanical test report | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-MDB-004 | 0 | ST C-6101 - Quality Record Book | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-MDB-007 | 0 | ST C-6101 - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-SKT-002 | 0 | ST C-6101 - Transport and handling sketches ( included auxilaries) | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-LST-009 | 0 | ST C-6101 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-LST-010 | 0 | ST C-6101 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-MNL-002 | 0 | ST C-6101 /ST C-6102 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-12-15 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-104(004)-IPM-014 | 0 | ST C-6102 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-04 15:16 | 2018-04-04 15:43 | Yes | 4 |  |  |  | 2018-04-23 17:19 |  |  |  |  | 2018-04-23 20:00 | Yes | 5
VD-9001-104(004)-PCU-003 | 0 | ST C-6102 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-03-31 | 2018-04-04 15:17 | 2018-04-04 15:44 | Yes | 4 |  |  |  | 2018-04-12 15:04 |  |  |  |  | 2018-04-12 20:00 | Yes | -6
VD-9001-104(004)-DWG-024 | 0 | ST C-6102 - Gland sealing and leak-off system | PR-104-SUB | AIR LIQUIDE | 2018-04-28 | 2018-02-23 13:09 | 2018-02-23 13:10 | Yes | -64 |  |  | 2018-03-17 13:13 | [5 empty] | 2018-03-17 20:00 | Yes | 8
VD-9001-104(004)-LST-011 | 0 | ST C-6102 - Allowable forces and moments | PR-104-SUB | AIR LIQUIDE | 2018-04-14 | 2018-02-07 19:01 | 2018-02-07 19:02 | Yes | -66 |  | 2018-02-13 10:54 | [6 empty] | 2018-02-13 20:00 | Yes | -8
VD-9001-104(004)-LST-012 | 0 | ST C-6102 - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-05-26 | 2018-04-04 15:16 | 2018-04-04 15:43 | Yes | -52 |  |  | 2018-04-10 17:45 | [5 empty] | 2018-04-10 20:00 | Yes | -8 | 1204-Owner-v | 2020-03-25 16:11
VD-9001-104(004)-DWG-025 | 0 | ST C-6102 - Condenser drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-04 | 2018-05-22 11:46 | 2018-05-22 11:50 | Yes | -74 |  |  |  | 2018-07-18 14:29 |  |  |  |  | 2018-07-18 19:59 | Yes | 43
VD-9001-104(004)-DWG-026 | 0 | ST C-6102 - Vacuum condenser detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-04 | 2018-05-22 11:45 | 2018-05-22 11:50 | Yes | -74 |  |  |  | 2018-06-03 17:42 |  |  |  |  | 2018-06-03 19:59 | Yes | -2
VD-9001-104(004)-DSH-006 | 0 | ST C-6102 - Condenser data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-04 | 2018-05-22 11:45 | 2018-05-22 11:50 | Yes | -74 |  |  |  | 2018-06-24 15:45 |  |  |  |  | 2018-06-24 20:00 | Yes | 19
VD-9001-104(004)-ARP-005 | 0 | ST C-6102 - Lateral & torsional vibration analysis | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-DIG-003 | 0 | ST C-6102 - Campbell & goodman diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-23 | 2018-02-23 13:01 | 2018-02-23 13:02 | Yes | -120 |  |  | 2018-03-17 13:19 | [5 empty] | 2018-03-17 20:00 | Yes | 8
VD-9001-104(004)-CAL-008 | 0 | ST C-6102 - Axial Thrust Calculation | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-CAL-009 | 0 | ST C-6102 - Condenser calculation note | PR-104-SUB | AIR LIQUIDE | 2018-08-18 |  |  | No | 671 | [9 empty] | No | 0
VD-9001-104(004)-WBK-006 | 0 | ST C-6102 - Condenser welding book | PR-104-SUB | AIR LIQUIDE | 2018-08-18 |  |  | No | 671 | [9 empty] | No | 0
VD-9001-104(004)-ITP-004 | 0 | ST C-6102 - Inspection Test Plan / Quality Plan | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-04-04 15:16 | 2018-04-04 15:43 | Yes | 46 |  |  |  | 2018-04-19 12:26 |  |  |  |  | 2018-04-19 20:00 | Yes | 1 | 1204-Owner-v | 2020-01-01 09:42
VD-9001-104(004)-IPM-015 | 0 | ST C-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-IPM-016 | 0 | ST C-6102 - Mechanical tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-23 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(004)-INR-004 | 0 | ST C-6102 - Mechanical test report | PR-104-SUB | AIR LIQUIDE | 2018-02-14 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-104(004)-MDB-005 | 0 | ST C-6102 - Quality Record Book | PR-104-SUB | AIR LIQUIDE | 2018-02-14 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-104(004)-MDB-006 | 0 | ST C-6102 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-02-14 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-104(004)-SKT-003 | 0 | ST C-6102 - Transport and handling sketches ( included auxilaries) | PR-104-SUB | AIR LIQUIDE | 2018-12-22 |  |  | No | 545 | [9 empty] | No | 0
VD-9001-104(004)-LST-013 | 0 | ST C-6102 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-02-14 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-104(004)-LST-014 | 0 | ST C-6102 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-05-26 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(004)-MNL-003 | 0 | ST C-6102 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-02-14 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-104(009)-CAL-001 | 0 | Cold box area - Access Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-CAL-002 | 0 | HP/ LP Cold box - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-02-21 | 2018-06-06 18:22 | 2018-06-06 18:26 | Yes | 105 |  |  |  | 2018-07-10 18:10 |  |  |  |  | 2018-07-10 20:00 | Yes | 20
VD-9001-104(009)-CAL-003 | 0 | Exchanger box E01 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-04-11 | 2018-06-06 18:09 | 2018-06-06 18:10 | Yes | 56 |  |  |  | 2018-07-10 14:59 |  |  |  |  | 2018-07-10 20:00 | Yes | 20
VD-9001-104(009)-CAL-004 | 0 | Exchanger box E03 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-CAL-005 | 0 | P-6103A / P-6103BA - Casing pump Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:08 | 2018-06-06 18:10 | Yes | -49 |  |  |  | 2018-07-17 10:58 |  |  |  |  | 2018-07-17 19:59 | Yes | 27
VD-9001-104(009)-CAL-006 | 0 | P-6105A / P-6105BA - Casing pump Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-CAL-007 | 0 | Interconnections - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-CAL-008 | 0 | STC-6103 / 607501T02 - Turbines Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-DWG-001 | 0 | Cold box area - Access detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-04-11 |  |  | No | 800 | [9 empty] | No | 0
VD-9001-104(009)-DWG-002 | 0 | Cold box area - Access detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:51 | 2018-06-07 17:44 | Yes | -48 |  |  |  | 2018-07-11 08:49 |  |  |  |  | 2018-07-11 19:59 | Yes | 20
VD-9001-104(009)-DWG-003 | 0 | Cold box area - Access detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:51 | 2018-06-07 17:44 | Yes | -48 |  |  |  | 2018-07-03 17:13 |  |  |  |  | 2018-07-03 20:00 | Yes | 12
VD-9001-104(009)-DWG-004 | 0 | Cold box area - Access detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-005 | 0 | Cold box area - Book - Special Pipe Supports | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-006 | 0 | HP/ LP Cold box - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-04-11 | 2018-04-04 13:10 | 2018-04-04 13:13 | Yes | -7 |  |  |  | 2018-05-09 11:03 |  |  |  |  | 2018-05-09 19:59 | Yes | 21
VD-9001-104(009)-DWG-007 | 0 | HP/ LP Cold box - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:13 | 2018-06-06 18:20 | Yes | -49 |  |  |  | 2018-06-26 11:34 |  |  |  |  | 2018-06-26 20:00 | Yes | 6
VD-9001-104(009)-DWG-008 | 0 | HP/ LP Cold box - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:14 | 2018-06-06 18:21 | Yes | -49 |  |  |  | 2018-06-26 14:46 |  |  |  |  | 2018-06-26 20:00 | Yes | 6
VD-9001-104(009)-DWG-009 | 0 | HP/ LP Cold box - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:12 | 2018-06-06 18:21 | Yes | -49 |  |  |  | 2018-06-25 16:34 |  |  |  |  | 2018-06-25 20:00 | Yes | 5
VD-9001-104(009)-DWG-010 | 0 | HP/ LP Cold box - detail drawing - plan 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:12 | 2018-06-06 18:21 | Yes | -49 |  |  |  | 2018-06-25 16:42 |  |  |  |  | 2018-06-25 20:00 | Yes | 5
VD-9001-104(009)-DWG-011 | 0 | HP/ LP Cold box - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-06 18:15 | 2018-06-06 18:21 | Yes | -49 |  |  |  | 2018-06-26 15:03 |  |  |  |  | 2018-06-26 20:00 | Yes | 6
VD-9001-104(009)-DWG-012 | 0 | Exchanger box E01 - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-06-06 18:13 | 2018-06-06 18:21 | Yes | 28 |  |  |  | 2018-06-23 14:37 |  |  |  |  | 2018-06-23 20:00 | Yes | 3
VD-9001-104(009)-DWG-013 | 0 | Exchanger box E01 - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:52 | 2018-06-07 17:44 | Yes | -48 |  |  |  | 2018-07-04 17:22 |  |  |  |  | 2018-07-04 20:00 | Yes | 13
VD-9001-104(009)-DWG-014 | 0 | Exchanger box E01 - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:52 | 2018-06-07 17:44 | Yes | -48 |  |  |  | 2018-07-04 17:34 |  |  |  |  | 2018-07-04 20:00 | Yes | 13
VD-9001-104(009)-DWG-015 | 0 | Exchanger box E01 - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:52 | 2018-06-07 17:44 | Yes | -48 |  |  |  | 2018-06-24 11:15 |  |  |  |  | 2018-06-24 20:00 | Yes | 3 | 1204-Owner-v | 2019-09-24 18:12
VD-9001-104(009)-DWG-016 | 0 | Exchanger box E01 - detail drawing - plan 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-017 | 0 | Exchanger box E01 - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-018 | 0 | Exchanger box E03 - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-05-31 18:27 | 2018-05-31 18:28 | Yes | 22 |  |  |  | 2018-06-09 17:23 |  |  |  |  | 2018-06-09 19:59 | Yes | -5
VD-9001-104(009)-DWG-019 | 0 | Exchanger box E03 - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:52 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-07-04 17:06 |  |  |  |  | 2018-07-04 20:00 | Yes | 13
VD-9001-104(009)-DWG-020 | 0 | Exchanger box E03 - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:52 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-07-03 16:52 |  |  |  |  | 2018-07-03 20:00 | Yes | 12
VD-9001-104(009)-DWG-021 | 0 | Exchanger box E03 - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:53 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-07-04 17:11 |  |  |  |  | 2018-07-04 20:00 | Yes | 13
VD-9001-104(009)-DWG-022 | 0 | Exchanger box E03 - detail drawing - plan 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:53 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-07-03 17:29 |  |  |  |  | 2018-07-03 20:00 | Yes | 12
VD-9001-104(009)-DWG-023 | 0 | Exchanger box E03 - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-024 | 0 | P-6103A / P-6103BA-B - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-05-29 16:55 | 2018-05-29 17:16 | Yes | 20 |  |  |  | 2018-06-02 16:49 |  |  |  |  | 2018-06-02 19:59 | Yes | -10
VD-9001-104(009)-DWG-025 | 0 | P-6103A / P-6103BA-B - detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:53 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-06-20 09:35 |  |  |  |  | 2018-06-20 20:00 | Yes | -1
VD-9001-104(009)-DWG-026 | 0 | P-6103A / P-6103BA-B - detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:54 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-06-20 09:22 |  |  |  |  | 2018-06-20 20:00 | Yes | -1
VD-9001-104(009)-DWG-027 | 0 | P-6103A / P-6103BA-B - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:54 | 2018-06-07 17:45 | Yes | -48 |  |  |  | 2018-06-20 09:30 |  |  |  |  | 2018-06-20 20:00 | Yes | -1
VD-9001-104(009)-DWG-028 | 0 | P-6103A / P-6103BA-B - sheeting drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(009)-DWG-029 | 0 | P-6103A / P-6103BA-B - sheeting drawing - details | PR-104-SUB | AIR LIQUIDE | 2018-07-25 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(009)-DWG-030 | 0 | P-6105A / P-6105BA-B - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-05-29 16:55 | 2018-05-29 17:16 | Yes | -57 |  |  |  | 2018-06-02 16:55 |  |  |  |  | 2018-06-02 19:59 | Yes | -10
VD-9001-104(009)-DWG-031 | 0 | P-6105A / P-6105BA-B - detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-25 | 2018-06-07 16:54 | 2018-06-07 17:46 | Yes | -48 |  |  |  | 2018-06-19 18:18 |  |  |  |  | 2018-06-19 20:01 | Yes | -2
VD-9001-104(009)-DWG-032 | 0 | P-6105A / P-6105BA-B - detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-06-07 16:55 | 2018-06-07 17:46 | Yes | 29 |  |  |  | 2018-06-19 18:06 |  |  |  |  | 2018-06-19 20:00 | Yes | -2
VD-9001-104(009)-DWG-033 | 0 | P-6105A / P-6105BA-B - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-08-08 | 2018-06-07 16:55 | 2018-06-07 17:46 | Yes | -62 |  |  |  | 2018-06-19 18:12 |  |  |  |  | 2018-06-19 20:01 | Yes | -2
VD-9001-104(009)-DWG-034 | 0 | Interconnections - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-DWG-035 | 0 | Interconnections - detail drawing - elevation and plan | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-DWG-036 | 0 | STC-6103 / 607501T02 - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-05-09 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(009)-DWG-037 | 0 | STC-6103 / 607501T02 - detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-DWG-038 | 0 | STC-6103 / 607501T02 - detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(009)-DWG-039 | 0 | STC-6103 / 607501T02 - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-08-08 |  |  | No | 681 | [9 empty] | No | 0
VD-9001-104(011)-DWG-001 | 0 | Warm automatic globe valve - Detail drawings | PR-104-SUB | AIR LIQUIDE | 2018-05-04 | 2018-04-13 16:53 | 2018-04-13 16:58 | Yes | -21 |  |  |  | 2018-05-26 11:16 |  |  |  |  | 2018-05-26 19:59 | Yes | 29
VD-9001-104(011)-DWG-002 | 0 | Warm automatic globe valve - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(011)-DWG-003 | 0 | Warm automatic globe valve - Pneumatic and electrical diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(011)-ITP-001 | 0 | Warm automatic globe valve - Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-05-22 16:30 | 2018-05-22 16:43 | Yes | 21 |  |  |  | 2018-06-18 09:33 |  |  |  |  | 2018-06-18 20:00 | Yes | 13 | 1204-Owner-v | 2020-01-01 10:00
VD-9001-104(011)-MDB-001 | 0 | Warm automatic globe valve - Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(011)-MDB-002 | 0 | Warm automatic globe valve - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(011)-MTO-001 | 0 | Cryogenic automatic globe valve - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104(011)-LST-002 | 0 | Warm automatic globe valve - Spare parts list | PR-104-SUB | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104(011)-MNL-001 | 0 | Warm automatic globe valve - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-01 | 2018-06-08 12:02 | 2018-08-02 11:44 | Yes | -30 |  |  | 2018-08-04 15:45 | [5 empty] | 2018-08-04 19:59 | Yes | 43
VD-9001-104(012)-DWG-001 | 0 | Warm automatic butterfly valve - Detail drawings | PR-104-SUB | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104(012)-DWG-002 | 0 | Warm automatic butterfly valve - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(012)-DWG-003 | 0 | Warm automatic butterfly valve - Pneumatic and electrical diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(012)-ITP-001 | 0 | Warm automatic butterfly valve - Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104(012)-MDB-001 | 0 | Warm automatic butterfly valve - Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(012)-MDB-002 | 0 | Warm automatic butterfly valve - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(012)-MTO-001 | 0 | Cryogenic automatic butterfly valve - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104(012)-LST-002 | 0 | Warm automatic butterfly valve - Spare parts list | PR-104-SUB | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104(012)-MNL-001 | 0 | Warm automatic butterfly valve - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104(010)-DWG-001 | 0 | Warm automatic 3-lever valve - Detail drawings | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-03-23 13:22 | 2018-03-23 13:44 | Yes | -39 |  |  |  | 2018-04-07 17:12 |  |  |  |  | 2018-04-07 20:00 | Yes | 1
VD-9001-104(010)-ITP-001 | 0 | Warm automatic 3-lever valve - Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-04-05 17:07 | 2018-04-05 17:09 | Yes | -26 |  |  |  | 2018-04-19 12:13 |  |  |  |  | 2018-04-19 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:00
VD-9001-104(010)-MDB-001 | 0 | Warm automatic 3-lever valve - Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(010)-MDB-002 | 0 | Warm automatic 3-lever valve - Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(010)-MTO-001 | 0 | Warm automatic 3-lever valve - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104(010)-LST-002 | 0 | Warm automatic 3-lever valve - Spare parts list | PR-104-SUB | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104(010)-MNL-001 | 0 | Warm automatic 3-lever valve - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104-PCJ-006 | 0 | INSULATION DESIGN FOR PIPING AND VESSELS | PR-104 | AIR LIQUIDE | 2017-12-15 | 2018-02-16 17:32 |  | No | 63 | 2018-02-27 18:50 | [7 empty] | 2018-02-27 20:00 | Yes | 0
VD-9001-104-CAL-001 | 0 | PSV- Cold Safety valves - Calculations | PR-104 | AIR LIQUIDE | 2017-03-01 | 2018-02-01 11:20 |  | No | 337 | 2018-02-19 16:03 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-104-CAL-002 | 0 | PSV- Warm Safety valves - Calculations | PR-104 | AIR LIQUIDE | 2017-02-05 | 2018-02-20 14:15 |  | No | 380 |  |  |  | 2018-04-05 17:31 |  |  |  |  | 2018-04-05 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-07 15:59
VD-9001-104-REQ-052 | 0 | Electrochemical Gas Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-15 | 2018-02-09 13:23 |  | No | -6 | 2018-02-19 18:29 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-104-DSH-063 | 0 | Electrochemical Gas Analysers - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-02-15 | 2018-02-09 13:49 |  | No | -6 | 2018-02-19 18:32 | [7 empty] | 2018-02-19 20:00 | Yes | 0
VD-9001-301-DWG-011 | 1 | name plate syngas compressor | MC-301 | Siemens AG | 2018-02-14 19:59 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-301-DWG-013 | 1 | name plate circulator compressor | MC-301 | Siemens AG | 2018-02-14 19:59 |  |  | No | 856 | [9 empty] | No | 0
VD-9001-301-ARP-002 | 1 | Hydrostatic Pressure Test syngas compressor | MC-301 | Siemens AG | 2018-02-14 19:59 | 2018-02-27 09:37 | 2018-02-27 09:37 | Yes | 13 |  |  | 2018-03-04 14:25 | [5 empty] | 2018-03-04 20:00 | Yes | -9 | 1204-Owner-v | 2018-08-01 09:06
VD-9001-301-ITP-001 | 1 | Hydrostatic Pressure Test circulator compressor | MC-301 | Siemens AG | 2018-02-14 20:00 | 2018-02-27 09:37 | 2018-02-27 09:37 | Yes | 13 |  |  | 2018-03-04 14:34 | [5 empty] | 2018-03-04 20:00 | Yes | -9 | 1204-Owner-v | 2018-05-12 16:53
VD-9001-104-PID-005 | 1 | Instrumentation detail diagram | PR-104 | AIR LIQUIDE | 2018-02-14 20:00 | 2018-04-12 14:59 | 2018-04-12 15:10 | Yes | 57 |  |  |  | 2018-04-21 17:48 |  |  |  |  | 2018-04-21 20:00 | Yes | -5
VD-9001-104-PID-003 | 1 | Instrumentation symbols schematic | PR-104 | AIR LIQUIDE | 2018-02-14 20:00 | 2018-04-12 14:58 | 2018-04-12 15:10 | Yes | 57 |  |  |  | 2018-07-09 12:03 |  |  |  |  | 2018-07-09 19:59 | Yes | 74 | 1204-Owner-v | 2018-04-22 09:59
VD-9001-104-PID-004 | 1 | Piping detail diagram | PR-104 | AIR LIQUIDE | 2018-02-15 20:00 | 2018-04-12 14:58 | 2018-04-12 15:10 | Yes | 56 |  |  | 2018-07-10 16:39 | [5 empty] | 2018-07-10 20:00 | Yes | 75 | 1204-Owner-v | 2018-04-22 09:59
VD-9001-104-PID-006 | 1 | P&ID LEGEND - INTERLOCK & FLUID CODES | PR-104 | AIR LIQUIDE | 2018-02-15 20:00 | 2018-04-12 14:59 | 2018-04-12 15:10 | Yes | 56 |  |  | 2018-04-21 16:36 | [5 empty] | 2018-04-21 20:00 | Yes | -5 | 1204-Owner-v | 2018-04-22 10:17
VD-9001-301-PDS-008 | 0 | stability requirements circulator turbine | MC-301 | Siemens AG | 2018-02-09 | 2018-02-03 09:51 |  | No | -6 | 2018-02-27 11:24 | [7 empty] | 2018-02-27 19:59 | Yes | 0
VD-9001-204C-DWG-003 | 1 | MATERIAL LIST AND GENERAL NOTES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-03 | 2018-03-26 15:15 | 2018-03-26 15:29 | Yes | 51 |  |  |  | 2018-04-15 16:50 |  |  |  |  | 2018-04-15 20:01 | Yes | 6 | 1204-Owner-v | 2018-05-08 09:06
VD-9001-461AP-MTC-001 | 0 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-02-07 19:54 |  | No | -2 | 2018-02-17 14:07 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-461AP-MTC-002 | 0 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-02-07 20:02 |  | No | -2 | 2018-02-17 14:08 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-461AP-MTC-003 | 0 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-02-08 13:50 |  | No | -1 | 2018-02-17 14:09 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-461AP-MTC-004 | 0 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-02-08 13:51 |  | No | -1 | 2018-02-17 14:09 | [7 empty] | 2018-02-17 20:00 | Yes | 0
VD-9001-461AP-INX-001 | 0 | FINAL DATA BOOK INDEX | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-04-18 17:28 | 2018-04-18 17:28 | Yes | 68 |  |  | 2018-04-22 14:51 | [5 empty] | 2018-04-22 14:51 | Yes | -10
VD-9001-461AP-ITP-001 | 0 | INSPECTION AND TEST PLAN | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-04-18 17:29 | 2018-04-18 17:29 | Yes | 68 |  |  | 2018-04-22 14:53 | [5 empty] | 2018-04-22 14:53 | Yes | -10
VD-9001-461AP-PCJ-001 | 0 | PACKING AND MARKING PROCEDURE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-09 | 2018-04-18 15:04 | 2018-04-18 15:05 | Yes | 68 |  |  | 2018-04-28 14:13 | [5 empty] | 2018-04-28 14:13 | Yes | -4
VD-9001-104-PID-001 | 1 | P&ID Index | PR-104 | AIR LIQUIDE | 2018-02-17 19:59 | 2018-04-12 14:58 | 2018-04-12 15:10 | Yes | 54 |  |  | 2018-04-28 15:54 | [5 empty] | 2018-04-28 20:00 | Yes | 2 | 1204-Owner-v | 2018-04-22 09:59
VD-9001-206B-DWG-011 | 6 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2018-02-17 20:00 | 2018-02-19 11:12 |  | No | 2 |  |  | 2018-06-10 10:28 | [5 empty] | 2018-06-10 10:28 | Yes | 0 | 1204-Owner-v | 2018-04-27 14:18
VD-9001-301-PCJ-012 | 0 | Preservation and Storage Procedure for Circulator Train | MC-301 | Siemens AG | 2018-02-09 |  |  | No | 861 | [9 empty] | No | 0
VD-9001-204C-PCJ-017 | 1 | PAINTING SPECIFICATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-04 | 2019-04-09 18:11 | 2019-04-09 18:12 | Yes | 429 |  |  |  | 2019-04-16 14:15 |  |  |  |  | 2019-04-16 20:59 | Yes | -7
VD-9001-204C-CAL-012 | 2 | MECHANICAL CODE CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-04 | 2018-03-26 16:57 | 2018-03-26 16:57 | Yes | 50 |  |  | 2018-04-10 10:32 | [5 empty] | 2018-04-10 20:00 | Yes | 1 | 1204-Owner-v | 2018-11-04 09:16
VD-9001-204C-CAL-014 | 2 | NOZZLE LOAD CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-04 | 2018-03-26 17:03 | 2018-03-26 17:03 | Yes | 50 |  |  | 2018-04-11 14:30 | [5 empty] | 2018-04-11 20:00 | Yes | 2 | 1204-Owner-v | 2018-12-16 21:52
VD-9001-257C-GAD-002 | 1 | GENERAL ARRANGEMENT (4137-0365) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-18 19:59 | 2018-05-14 13:43 | 2018-05-14 13:43 | Yes | 85 |  |  |  |  | 2018-08-26 15:20 |  |  |  | 2018-08-26 15:20 | Yes | 90 | 1204-Owner-v | 2018-08-04 13:29
VD-9001-104-LST-001 | 3 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2018-02-18 19:59 | 2018-03-09 13:01 | 2018-03-09 13:19 | Yes | 19 |  |  |  | 2018-03-18 15:57 |  |  |  |  | 2018-03-18 21:00 | Yes | -5 | 1204-Owner-v | 2018-03-12 15:09
VD-9001-257C-CAL-002 | 1 | MECHANICAL CALCULATION (4137-0365/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-18 20:00 | 2018-05-14 13:52 | 2018-05-14 13:52 | Yes | 85 |  |  | 2018-08-20 09:44 | [5 empty] | 2018-08-20 09:44 | Yes | 84 | 1204-Owner-v | 2018-08-19 08:54
VD-9001-257C-DWG-007 | 1 | DETAILS DRAWING (4137-0365/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-18 20:00 | 2018-05-14 14:08 | 2018-05-14 14:08 | Yes | 85 |  |  | 2018-07-21 20:04 | [5 empty] | 2018-07-21 20:04 | Yes | 54
VD-9001-257C-DWG-053 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0365/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-18 20:00 | 2018-05-14 14:03 | 2018-05-14 14:04 | Yes | 85 |  |  | 2018-07-22 10:41 | [5 empty] | 2018-07-22 10:41 | Yes | 55
VD-9001-254-DSH-566 | 2 | DATA SHEET FOR CONTROL VALVES | HM-254 | AZAR AB | 2018-02-18 20:00 |  |  | No | 852 | [9 empty] | No | 0
VD-9001-254-DSH-564 | 3 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2018-02-18 20:00 | 2018-10-27 13:30 | 2018-10-27 13:30 | Yes | 251 |  |  |  | 2018-12-23 15:45 |  |  |  |  | 2018-12-23 15:45 | Yes | 43
VD-9001-251-DWG-003 | 1 | INLET SYSTEM DRAWING - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-05 | 2018-04-18 14:44 | 2018-04-18 14:55 | Yes | 72 |  |  | 2018-04-24 17:33 | [5 empty] | 2018-04-24 17:33 | Yes | -8 | 1204-Owner-v | 2019-02-05 10:50
VD-9001-251-DWG-002 | 1 | INLET SYSTEM DRAWING - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-05 | 2018-04-18 14:32 | 2018-04-18 14:44 | Yes | 72 |  |  | 2018-04-24 17:32 | [5 empty] | 2018-04-24 17:32 | Yes | -8 | 1204-Owner-v | 2019-02-05 10:50
VD-9001-251-DWG-006 | 1 | OUTLET SYSTEM DETAILS DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-05 | 2018-04-18 16:16 | 2018-04-18 16:22 | Yes | 72 |  |  | 2018-04-26 13:03 | [5 empty] | 2018-04-26 13:03 | Yes | -6 | 1204-Owner-v | 2019-02-05 10:51
VD-9001-251-DWG-005 | 1 | OUTLET SYSTEM - GENERAL ARRANGEMENT DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-05 | 2018-04-18 15:01 | 2018-04-18 15:04 | Yes | 72 |  |  | 2018-04-26 13:08 | [5 empty] | 2018-04-26 13:08 | Yes | -6 | 1204-Owner-v | 2018-07-02 11:13
VD-9001-254-LST-340 | 4 | BMS I/O LIST | HM-254 | AZAR AB | 2018-02-19 20:00 | 2019-02-24 14:30 | 2019-02-24 14:30 | Yes | 370 |  |  | 2019-04-15 15:08 | [5 empty] | 2019-04-15 15:08 | Yes | 36 | 1204-Owner-v | 2019-12-09 08:26
VD-9001-254-LST-302 | 6 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2018-02-19 20:00 | 2018-12-16 11:01 | 2018-12-16 11:01 | Yes | 300 |  |  |  | 2019-01-02 11:02 |  |  |  |  | 2019-01-02 11:02 | Yes | 3
VD-9001-254-DWG-347 | 3 | INSTALLATION DRAWINGS & PROCEDURES FOR INSTRUMENTS | HM-254 | AZAR AB | 2018-02-19 20:00 | 2018-02-07 09:10 | 2018-02-07 09:11 | Yes | -12 |  | 2018-02-13 14:44 | [6 empty] | 2018-02-13 20:00 | Yes | -8 | 1204-Owner-v | 2018-04-09 09:44
VD-9001-251-DWG-004 | 1 | INLET SYSTEM - MAIN HEADER DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 | 2018-04-18 14:58 | 2018-04-18 15:04 | Yes | 71 |  |  | 2018-04-24 17:37 | [5 empty] | 2018-04-24 17:37 | Yes | -8 | 1204-Owner-v | 2019-02-05 10:50
VD-9001-204C-CAL-013 | 2 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-06 | 2018-03-26 17:04 | 2018-03-26 17:04 | Yes | 48 |  |  | 2018-04-11 11:57 | [5 empty] | 2018-04-11 20:00 | Yes | 2 | 1204-Owner-v | 2018-12-16 21:52
VD-9001-251-DWG-052 | 1 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 | 2018-03-30 12:38 | 2018-03-30 12:38 | Yes | 52 |  |  | 2018-04-12 10:36 | [5 empty] | 2018-04-12 10:36 | Yes | -1
VD-9001-251-DWG-051 | 1 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 | 2018-03-30 12:38 | 2018-03-30 12:38 | Yes | 52 |  |  | 2018-04-12 10:36 | [5 empty] | 2018-04-12 10:36 | Yes | -1
VD-9001-251-DWG-050 | 1 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-06 | 2018-03-30 12:34 | 2018-03-30 12:37 | Yes | 52 |  |  |  | 2018-04-09 15:04 |  |  |  |  | 2018-04-09 15:04 | Yes | -4 | 1204-Owner-v | 2018-04-15 08:02
VD-9001-204C-GAD-002 | 2 | GENERAL ARRANGEMENT DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-06 | 2018-03-26 15:11 | 2018-03-26 15:13 | Yes | 48 |  |  |  | 2018-04-15 15:37 |  |  |  |  | 2018-04-15 20:01 | Yes | 6 | 1204-Owner-v | 2018-04-25 10:35
VD-9001-254-DSH-565 | 2 | DATA SHEET FOR PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2018-02-20 19:59 | 2018-11-14 11:57 | 2018-11-14 11:58 | Yes | 267 |  |  | 2018-12-23 15:47 | [5 empty] | 2018-12-23 15:47 | Yes | 25 | 1204-Owner-v | 2019-06-15 16:48
VD-9001-254-DIG-339 | 2 | ABC & SUPERVISORY FLOW DIAGRAMS | HM-254 | AZAR AB | 2018-02-20 19:59 | 2018-02-13 11:49 | 2018-02-13 11:50 | Yes | -7 |  | 2018-02-13 14:49 | [6 empty] | 2018-02-13 20:00 | Yes | -14 | 1204-Owner-v | 2018-11-26 13:37
VD-9001-254-DIG-320 | 2 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2018-02-20 19:59 | 2019-02-24 14:29 | 2019-02-24 14:29 | Yes | 369 |  |  |  | 2019-03-10 14:29 |  |  |  |  | 2019-03-10 14:29 | Yes | 0
VD-9001-204B-MSS-001 | 6 | Material Specification for Plate and Forge | PV-204B | ABAN AIR COOLER. | 2018-02-07 15:22 | 2018-02-07 15:37 | 2018-02-07 15:38 | Yes | 0 |  | 2018-02-24 16:57 | [6 empty] | 2018-02-24 20:00 | Yes | 3 | 1204-Owner-v | 2020-04-29 08:37
VD-9001-307A-DIS-001 | 0 | Drawing / Document schedule | MC-307A | KSB GERMANY | 2018-01-12 | 2018-04-04 12:35 | 2018-04-04 12:35 | Yes | 82 |  |  |  | 2018-06-17 11:02 |  |  |  |  | 2018-06-17 20:00 | Yes | 60 | 1204-Owner-v | 2018-05-20 16:20
VD-9001-307A-VLS-001 | 0 | Sub Vendor List | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-15 11:06 | 2018-06-15 11:06 | Yes | 107 |  |  |  | 2018-07-29 10:58 |  |  |  |  | 2018-07-29 19:59 | Yes | 30
VD-9001-307A-LST-041 | 0 | Spare Parts List for Two Year Operation and Erection and Commissioning | MC-307A | KSB GERMANY | 2018-12-14 |  |  | No | 553 | [9 empty] | No | 0
VD-9001-307A-LST-042 | 0 | Lubrication List | MC-307A | KSB GERMANY | 2018-12-14 |  |  | No | 553 | [9 empty] | No | 0
VD-9001-307A-PCJ-001 | 0 | Painting Procedure | MC-307A | KSB GERMANY | 2018-12-14 | 2018-05-18 16:30 | 2018-05-18 16:38 | Yes | -210 |  |  |  | 2018-06-17 11:10 |  |  |  |  | 2018-06-17 20:00 | Yes | 16
VD-9001-307A-PCJ-002 | 0 | Packing, Lifting, Transport and Storage Procedure | MC-307A | KSB GERMANY | 2018-12-14 | 2018-05-18 16:30 | 2018-05-18 16:38 | Yes | -210 |  |  |  | 2018-07-07 14:14 |  |  |  |  | 2018-07-07 20:00 | Yes | 36
VD-9001-307A-PCJ-003 | 0 | Welding Procedure Specification (WPS) and Procedure Qualification Record (PQR) | MC-307A | KSB GERMANY | 2018-12-14 | 2018-05-18 16:32 | 2018-05-18 16:38 | Yes | -210 |  |  |  | 2018-06-17 11:14 |  |  |  |  | 2018-06-17 20:00 | Yes | 16
VD-9001-307A-WPQ-001 | 0 | Welder List Personal Certificate | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-PCJ-004 | 0 | Inspection Test Procedures (pump) | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-PCJ-005 | 0 | Hydrostatic Test Procedure | MC-307A | KSB GERMANY | 2018-08-31 | 2018-05-18 16:33 | 2018-05-18 16:38 | Yes | -105 |  |  |  | 2018-05-30 15:16 |  |  |  |  | 2018-05-30 19:59 | Yes | -2
VD-9001-307A-FBL-001 | 0 | Bill of Lading | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-LST-043 | 0 | Utility consumption list | MC-307A | KSB GERMANY | 2018-03-05 | 2018-10-24 12:37 | 2018-10-24 12:37 | Yes | 233 |  |  |  | 2018-12-02 15:09 |  |  |  |  | 2018-12-02 20:00 | Yes | 25
VD-9001-307A-CAT-001 | 0 | Cataloque and Brochure | MC-307A | KSB GERMANY | 2018-03-28 | 2018-06-15 11:00 | 2018-06-15 11:04 | Yes | 79 |  |  | 2018-06-18 14:47 | [5 empty] | 2018-06-18 20:00 | Yes | -11 | 1204-Owner-v | 2019-04-11 10:02
VD-9001-307A-LST-044 | 0 | Reference list | MC-307A | KSB GERMANY | 2018-03-28 | 2018-06-15 11:05 | 2018-06-15 11:05 | Yes | 79 |  |  | 2018-06-19 09:19 | [5 empty] | 2018-06-19 20:00 | Yes | -10
VD-9001-307A-LST-045 | 0 | Un-priced copies of sub-orders | MC-307A | KSB GERMANY | 2018-12-14 | 2018-09-07 16:56 | 2018-09-07 16:56 | Yes | -98 |  |  |  | 2018-09-15 11:19 |  |  |  |  | 2018-09-15 19:58 | Yes | -6 | 1204-Owner-v | 2018-11-06 09:14
VD-9001-307A-LST-046 | 0 | Deviation List | MC-307A | KSB GERMANY | 2018-02-16 | 2018-06-15 11:05 | 2018-06-15 11:05 | Yes | 119 |  |  |  | 2018-06-19 15:08 |  |  |  |  | 2018-06-19 20:00 | Yes | -10 | 1204-Owner-v | 2018-11-06 09:13
VD-9001-307A-LST-047 | 0 | Alarm and Trip set point list | MC-307A | KSB GERMANY | 2018-02-16 |  |  | No | 854 | [9 empty] | No | 0
VD-9001-307A-MNL-001 | 0 | Operation & Maintenance Instruction Pump | MC-307A | KSB GERMANY | 2018-02-16 |  |  | No | 854 | [9 empty] | No | 0
VD-9001-307A-MNL-002 | 0 | Operation & Maintenance Instruction Mechanical Seal | MC-307A | KSB GERMANY | 2018-01-26 |  |  | No | 875 | [9 empty] | No | 0
VD-9001-307A-MNL-003 | 0 | Operation & Maintenance Instruction Coupling | MC-307A | KSB GERMANY | 2018-12-14 |  |  | No | 553 | [9 empty] | No | 0
VD-9001-307A-MNL-004 | 0 | Operation & Maintenance Instruction Motor | MC-307A | KSB GERMANY | 2018-02-09 | 2018-04-04 10:50 | 2018-04-04 11:04 | Yes | 54 |  |  | 2018-04-16 10:36 | [5 empty] | 2018-04-16 20:00 | Yes | -2
VD-9001-307A-MNL-005 | 0 | Operation & Maintenance Instruction Gear Box | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-MNL-006 | 0 | Operation & Maintenance Instruction Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-MNL-007 | 0 | Operation & Maintenance Instruction Seal System | MC-307A | KSB GERMANY | 2018-07-31 |  |  | No | 689 | [9 empty] | No | 0
VD-9001-307A-PCJ-006 | 0 | Inspection Test Plan Procedure (Turbine) | MC-307A | KSB GERMANY | 2018-09-21 |  |  | No | 637 | [9 empty] | No | 0
VD-9001-307A-ITP-011 | 0 | Inspection Test Plan (Turbine) | MC-307A | KSB GERMANY | 2018-12-14 | 2018-05-24 18:32 | 2018-05-24 18:32 | Yes | -204 |  |  |  | 2018-06-19 09:53 |  |  |  |  | 2018-06-19 20:00 | Yes | 12 | 1204-Owner-v | 2020-01-01 10:51
VD-9001-307A-PCJ-007 | 0 | Inspection Test Plan Procedure (Motor) | MC-307A | KSB GERMANY | 2018-06-21 | 2018-04-20 10:50 | 2018-04-20 10:50 | Yes | -62 |  |  | 2018-05-01 16:06 | [5 empty] | 2018-05-01 20:00 | Yes | -3 | 1204-Owner-v | 2018-10-27 14:05
VD-9001-307A-ITP-012 | 0 | Inspection Test Plan (Motor) | MC-307A | KSB GERMANY | 2018-06-01 | 2018-04-04 10:46 | 2018-04-04 11:04 | Yes | -58 |  |  |  | 2018-04-16 14:33 |  |  |  |  | 2018-04-16 20:00 | Yes | -2
VD-9001-307A-PCJ-008 | 0 | Inspection Test Plan Procedure (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-ITP-013 | 0 | Inspection Test Plan (Seal System) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-05-24 18:33 | 2018-05-24 18:33 | Yes | 24 |  |  |  | 2018-06-19 11:07 |  |  |  |  | 2018-06-19 20:00 | Yes | 12 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-PCJ-009 | 0 | Inspection Test Plan Procedure (Mechanical Seal) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-ITP-014 | 0 | Inspection Test Plan (Mechanical Seal) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-05-24 18:33 | 2018-05-24 18:33 | Yes | 24 |  |  |  | 2018-06-17 09:07 |  |  |  |  | 2018-06-17 20:00 | Yes | 10 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-LST-048 | 0 | Instrument List | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-LST-049 | 0 | Cable List | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-LST-050 | 0 | I/O List | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-LST-051 | 0 | Electrical power consumption, heat dissipation | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-002 | 0 | Catalogue and Brochure (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-MNL-008 | 0 | Progamming Manuals (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-INC-001 | 0 | MASTER INDEX for MDR (Manufactur Data Record) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CER-001 | 0 | Certification of Conformity Pump | MC-307A | KSB GERMANY | 2018-11-16 |  |  | No | 581 | [9 empty] | No | 0
VD-9001-307A-CER-002 | 0 | Certification of Conformity Motor | MC-307A | KSB GERMANY | 2018-11-16 |  |  | No | 581 | [9 empty] | No | 0
VD-9001-307A-CER-003 | 0 | Certification of Conformity Seal System | MC-307A | KSB GERMANY | 2019-02-22 |  |  | No | 483 | [9 empty] | No | 0
VD-9001-307A-CER-004 | 0 | Certification of Conformity Turbine | MC-307A | KSB GERMANY | 2019-02-22 |  |  | No | 483 | [9 empty] | No | 0
VD-9001-307A-DSH-001 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-07-31 | 2018-02-08 14:37 |  | No | -173 | 2018-02-27 10:59 | [7 empty] | 2018-02-27 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:29
VD-9001-307A-DSH-002 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-08-24 | 2018-02-08 16:05 |  | No | -197 | 2018-02-27 10:55 | [7 empty] | 2018-02-27 19:59 | Yes | 0
VD-9001-307A-DSH-003 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-08 16:20 |  | No | -225 | 2018-02-27 10:51 | [7 empty] | 2018-02-27 19:59 | Yes | 0
VD-9001-307A-DSH-004 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-14 22:41 |  | No | -219 | 2018-02-27 10:47 | [7 empty] | 2018-02-27 19:59 | Yes | 0
VD-9001-307A-DSH-005 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:40 |  | No | -210 |  |  |  | 2018-05-01 11:44 |  |  |  |  | 2018-05-01 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-11 13:48
VD-9001-307A-DSH-006 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:41 |  | No | -210 |  |  |  | 2018-05-01 11:38 |  |  |  |  | 2018-05-01 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:29
VD-9001-307A-DSH-007 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:41 |  | No | -210 |  |  |  | 2018-05-01 11:41 |  |  |  |  | 2018-05-01 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:29
VD-9001-307A-DSH-008 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:42 |  | No | -210 |  |  |  | 2018-05-01 11:41 |  |  |  |  | 2018-05-01 19:59 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:29
VD-9001-307A-DSH-009 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:42 |  | No | -210 |  |  |  | 2018-04-25 15:15 |  |  |  |  | 2018-04-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:30
VD-9001-307A-DSH-010 | 0 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-02-23 16:42 |  | No | -210 |  |  |  | 2018-04-25 15:11 |  |  |  |  | 2018-04-25 20:00 | Yes | 0 | 1204-Owner-v | 2018-03-11 14:30
VD-9001-307A-DSH-011 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:28 | 2018-07-06 16:29 | Yes | -77 |  |  |  | 2018-07-07 10:14 |  |  |  |  | 2018-07-07 20:00 | Yes | -13 | 1204-Owner-v | 2018-10-16 13:05
VD-9001-307A-DSH-012 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:28 | 2018-07-06 16:29 | Yes | -77 |  |  |  | 2018-07-07 10:12 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-013 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:28 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 10:09 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-014 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:28 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:39 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-015 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:35 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-016 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:33 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-017 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:29 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-018 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:07 |  |  |  |  | 2018-07-07 19:59 | Yes | -13
VD-9001-307A-DSH-019 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:09 |  |  |  |  | 2018-07-07 19:59 | Yes | -13
VD-9001-307A-DSH-020 | 0 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | -77 |  |  |  | 2018-07-07 09:24 |  |  |  |  | 2018-07-07 20:00 | Yes | -13
VD-9001-307A-DSH-021 | 0 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-03-15 13:17 | 2018-03-15 13:17 | Yes | -190 |  |  |  |  | 2018-04-24 09:12 |  |  |  | 2018-04-24 20:00 | Yes | 26 | 1204-Owner-v | 2018-03-11 14:30
VD-9001-307A-DSH-022 | 0 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-08-02 13:47 | 2018-08-02 13:47 | Yes | -50 |  |  |  | 2018-09-02 10:32 |  |  |  |  | 2018-09-02 19:58 | Yes | 17 | 1204-Owner-v | 2018-06-18 09:10
VD-9001-307A-DSH-023 | 0 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-03-15 13:18 | 2018-03-15 13:19 | Yes | -190 |  |  |  |  | 2018-04-24 08:48 |  |  |  | 2018-04-24 20:00 | Yes | 26
VD-9001-307A-DSH-024 | 0 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-21 | 2018-03-15 13:18 | 2018-03-15 13:19 | Yes | -190 |  |  |  |  | 2018-04-24 09:05 |  |  |  | 2018-04-24 20:00 | Yes | 26
VD-9001-307A-DSH-025 | 0 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-03-15 13:18 | 2018-03-15 13:18 | Yes | 49 |  |  |  |  | 2018-04-24 09:33 |  |  |  | 2018-04-24 20:00 | Yes | 26
VD-9001-307A-DSH-026 | 0 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-04-04 10:45 | 2018-04-04 10:58 | Yes | 69 |  |  |  | 2018-04-16 14:29 |  |  |  |  | 2018-04-16 20:00 | Yes | -2 | 1204-Owner-v | 2018-04-21 14:14
VD-9001-307A-DSH-027 | 0 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-04-04 10:45 | 2018-04-04 11:04 | Yes | 69 |  |  |  | 2018-04-16 14:27 |  |  |  |  | 2018-04-16 20:00 | Yes | -2 | 1204-Owner-v | 2018-04-21 14:15
VD-9001-307A-DSH-028 | 0 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-03-15 17:26 | 2018-03-15 17:26 | Yes | 49 |  |  |  | 2018-04-17 17:18 |  |  |  |  | 2018-04-17 20:00 | Yes | 19 | 1204-Owner-v | 2018-04-21 14:15
VD-9001-307A-DSH-029 | 0 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-03-15 17:27 | 2018-03-15 17:27 | Yes | 49 |  |  |  | 2018-04-17 17:16 |  |  |  |  | 2018-04-17 20:00 | Yes | 19 | 1204-Owner-v | 2018-04-21 14:19
VD-9001-307A-DSH-030 | 0 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-01-25 | 2018-04-04 10:46 | 2018-04-04 11:04 | Yes | 69 |  |  |  | 2018-04-17 17:17 |  |  |  |  | 2018-04-17 20:00 | Yes | -1 | 1204-Owner-v | 2018-04-21 14:22
VD-9001-307A-DSH-031 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-01-25 |  |  | No | 876 | [9 empty] | No | 0
VD-9001-307A-DSH-032 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-01-25 |  |  | No | 876 | [9 empty] | No | 0
VD-9001-307A-DSH-033 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-01-25 |  |  | No | 876 | [9 empty] | No | 0
VD-9001-307A-DSH-034 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-01-25 |  |  | No | 876 | [9 empty] | No | 0
VD-9001-307A-DSH-035 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-036 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-037 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-038 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-039 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-040 | 0 | Instrument Data Sheet & Drawings (Pump) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-041 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-042 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-043 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-044 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DSH-045 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DSH-046 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DSH-047 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DSH-048 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DSH-049 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DSH-050 | 0 | Instrument Data Sheet & Drawings (Seal System) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DSH-051 | 0 | Instrument Data Sheet & Drawings (Turbine) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DSH-052 | 0 | Instrument Data Sheet & Drawings (Turbine) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DSH-053 | 0 | Instrument Data Sheet & Drawings (Turbine) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DSH-054 | 0 | Instrument Data Sheet & Drawings (Turbine) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DSH-055 | 0 | Instrument Data Sheet & Drawings (Turbine) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-056 | 0 | Instrument Data Sheet & Drawings (Motor) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-057 | 0 | Instrument Data Sheet & Drawings (Motor) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-058 | 0 | Instrument Data Sheet & Drawings (Motor) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-059 | 0 | Instrument Data Sheet & Drawings (Motor) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-060 | 0 | Instrument Data Sheet & Drawings (Motor) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-061 | 0 | Instrument Data Sheet & Drawings (Gear Box) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-062 | 0 | Instrument Data Sheet & Drawings (Gear Box) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-063 | 0 | Instrument Data Sheet & Drawings (Gear Box) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-064 | 0 | Instrument Data Sheet & Drawings (Gear Box) | MC-307A | KSB GERMANY | 2018-05-31 |  |  | No | 750 | [9 empty] | No | 0
VD-9001-307A-DSH-065 | 0 | Instrument Data Sheet & Drawings (Gear Box) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-066 | 0 | Instrument Data Sheet (ISA) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-067 | 0 | Instrument Data Sheet (ISA) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-068 | 0 | Instrument Data Sheet (ISA) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-069 | 0 | Instrument Data Sheet (ISA) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-070 | 0 | Instrument Data Sheet (ISA) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-071 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-072 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-20 10:48 | 2018-04-20 10:49 | Yes | -70 |  |  | 2018-05-01 15:25 | [5 empty] | 2018-05-01 20:00 | Yes | -3
VD-9001-307A-DSH-073 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DSH-074 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-20 10:48 | 2018-04-20 10:49 | Yes | -70 |  |  | 2018-05-01 15:44 | [5 empty] | 2018-05-01 20:00 | Yes | -3
VD-9001-307A-DSH-075 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-076 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-05-25 | 2018-04-20 10:48 | 2018-04-20 10:49 | Yes | -35 |  |  | 2018-05-01 15:45 | [5 empty] | 2018-05-01 20:00 | Yes | -3
VD-9001-307A-DSH-077 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-078 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-05-25 | 2018-04-20 10:48 | 2018-04-20 10:49 | Yes | -35 |  |  | 2018-05-01 15:51 | [5 empty] | 2018-05-01 20:00 | Yes | -3
VD-9001-307A-DSH-079 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-080 | 0 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-04-20 | 2018-04-20 10:49 | 2018-04-20 10:49 | Yes | 0 |  |  | 2018-05-01 15:23 | [5 empty] | 2018-05-01 20:00 | Yes | -3
VD-9001-307A-DSH-081 | 0 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-04-20 | 2018-09-21 16:37 | 2018-09-21 16:37 | Yes | 154 |  |  |  | 2018-10-03 11:22 |  |  |  |  | 2018-10-03 18:58 | Yes | -2
VD-9001-307A-DSH-082 | 0 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-04-20 | 2018-09-21 16:37 | 2018-09-21 16:37 | Yes | 154 |  |  |  | 2018-10-03 11:24 |  |  |  |  | 2018-10-03 18:58 | Yes | -2
VD-9001-307A-DSH-083 | 0 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-04-20 | 2018-09-21 16:37 | 2018-09-21 16:37 | Yes | 154 |  |  |  | 2018-10-03 11:24 |  |  |  |  | 2018-10-03 18:58 | Yes | -2
VD-9001-307A-DSH-084 | 0 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-04-20 | 2018-09-21 16:37 | 2018-09-21 16:37 | Yes | 154 |  |  |  | 2018-10-03 11:26 |  |  |  |  | 2018-10-03 18:58 | Yes | -2
VD-9001-307A-DSH-085 | 0 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-06-08 | 2018-09-21 16:37 | 2018-09-21 16:37 | Yes | 105 |  |  |  | 2018-10-03 11:27 |  |  |  |  | 2018-10-03 18:58 | Yes | -2
VD-9001-307A-PCU-001 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-06-08 | 2018-04-06 15:41 | 2018-04-06 15:42 | Yes | -63 |  |  |  | 2018-04-15 09:51 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-002 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-06-08 | 2018-04-06 15:41 | 2018-04-06 15:42 | Yes | -63 |  |  |  | 2018-04-15 09:52 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-003 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-06-08 | 2018-04-06 15:41 | 2018-04-06 15:43 | Yes | -63 |  |  |  | 2018-04-15 10:07 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-004 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-06-08 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -63 |  |  |  | 2018-04-15 10:20 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-005 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-06 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -91 |  |  |  | 2018-04-15 11:14 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-006 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-06 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -91 |  |  |  | 2018-04-15 11:19 |  |  |  |  | 2018-04-15 20:00 | Yes | -5
VD-9001-307A-PCU-007 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-06 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -91 |  |  |  | 2018-04-15 14:47 |  |  |  |  | 2018-04-15 20:01 | Yes | -5
VD-9001-307A-PCU-008 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-06 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -91 |  |  |  | 2018-04-15 14:56 |  |  |  |  | 2018-04-15 20:01 | Yes | -5
VD-9001-307A-PCU-009 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-06 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -91 |  |  |  | 2018-04-15 15:09 |  |  |  |  | 2018-04-15 20:01 | Yes | -5
VD-9001-307A-PCU-010 | 0 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-08-31 | 2018-04-06 15:42 | 2018-04-06 15:43 | Yes | -147 |  |  |  | 2018-04-15 15:18 |  |  |  |  | 2018-04-15 20:01 | Yes | -5
VD-9001-307A-PCU-011 | 0 | Motor Curves | MC-307A | KSB GERMANY | 2018-08-31 | 2018-04-04 10:43 | 2018-04-04 11:04 | Yes | -149 |  |  |  | 2018-04-17 17:15 |  |  |  |  | 2018-04-17 20:00 | Yes | -1
VD-9001-307A-PCU-012 | 0 | Motor Curves | MC-307A | KSB GERMANY | 2018-08-31 | 2018-04-04 10:44 | 2018-04-04 11:04 | Yes | -149 |  |  |  | 2018-04-17 17:15 |  |  |  |  | 2018-04-17 20:00 | Yes | -1
VD-9001-307A-PCU-013 | 0 | Motor Curves | MC-307A | KSB GERMANY | 2018-08-31 | 2018-03-15 17:29 | 2018-03-15 17:29 | Yes | -169 |  |  |  | 2018-04-17 17:14 |  |  |  |  | 2018-04-17 20:00 | Yes | 19
VD-9001-307A-PCU-014 | 0 | Motor Curves | MC-307A | KSB GERMANY | 2018-08-31 | 2018-03-15 17:30 | 2018-03-15 17:30 | Yes | -169 |  |  |  | 2018-04-17 17:13 |  |  |  |  | 2018-04-17 20:00 | Yes | 19
VD-9001-307A-PCU-015 | 0 | Motor Curves | MC-307A | KSB GERMANY | 2018-08-31 | 2018-04-04 10:44 | 2018-04-04 11:05 | Yes | -149 |  |  |  | 2018-04-17 17:13 |  |  |  |  | 2018-04-17 20:00 | Yes | -1
VD-9001-307A-PCU-016 | 0 | Turbine Performance Curves | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-PCU-017 | 0 | Turbine Performance Curves | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-PCU-018 | 0 | Turbine Performance Curves | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-PCU-019 | 0 | Turbine Performance Curves | MC-307A | KSB GERMANY | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-307A-PCU-020 | 0 | Turbine Performance Curves | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-001 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-06-08 | 2018-06-08 13:11 | 2018-06-08 13:18 | Yes | 0 |  |  |  | 2018-07-08 17:41 |  |  |  |  | 2018-07-08 20:00 | Yes | 16 | 1204-Owner-v | 2018-06-18 09:12
VD-9001-307A-DWG-002 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-06-08 | 2018-05-04 16:59 | 2018-05-04 16:59 | Yes | -35 |  |  |  | 2018-05-14 17:08 |  |  |  |  | 2018-05-14 20:00 | Yes | -4 | 1204-Owner-v | 2018-05-05 07:56
VD-9001-307A-DWG-003 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-06-08 | 2018-06-08 13:31 | 2018-06-08 13:31 | Yes | 0 |  |  |  | 2018-07-08 17:23 |  |  | 2018-04-28 15:05 | 2018-04-28 15:05 | 2018-07-08 20:00 | Yes | 16 | 1204-Owner-v | 2018-06-18 09:32
VD-9001-307A-DWG-004 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-06-08 | 2018-04-27 12:36 | 2018-04-27 12:37 | Yes | -42 |  |  |  | 2018-05-06 11:20 |  |  |  |  | 2018-05-06 20:00 | Yes | -5
VD-9001-307A-DWG-005 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-08 13:15 | 2018-06-08 13:19 | Yes | 100 |  |  |  | 2018-07-08 17:38 |  |  |  |  | 2018-07-08 20:00 | Yes | 16 | 1204-Owner-v | 2018-06-20 11:33
VD-9001-307A-DWG-006 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-04-16 13:07 | 2018-04-16 13:08 | Yes | 47 |  |  |  | 2018-06-17 14:39 |  |  |  |  | 2018-06-17 20:00 | Yes | 48 | 1204-Owner-v | 2018-10-31 16:46
VD-9001-307A-DWG-007 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-08 13:16 | 2018-06-08 13:19 | Yes | 100 |  |  |  | 2018-07-25 09:46 |  |  |  |  | 2018-07-25 19:59 | Yes | 33 | 1204-Owner-v | 2018-06-20 11:32
VD-9001-307A-DWG-008 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-04-16 13:26 | 2018-04-16 13:26 | Yes | 47 |  |  |  | 2018-06-17 14:36 |  |  |  |  | 2018-06-17 20:00 | Yes | 48 | 1204-Owner-v | 2018-10-31 16:47
VD-9001-307A-DWG-009 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-08 13:17 | 2018-06-08 13:19 | Yes | 100 |  |  |  | 2018-07-08 17:18 |  |  |  |  | 2018-07-08 20:00 | Yes | 16 | 1204-Owner-v | 2018-06-20 11:32
VD-9001-307A-DWG-010 | 0 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-08 13:18 | 2018-06-08 13:19 | Yes | 100 |  |  |  | 2018-07-08 17:27 |  |  |  |  | 2018-07-08 20:00 | Yes | 16 | 1204-Owner-v | 2018-06-20 11:33
VD-9001-307A-DWG-011 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-28 14:56 | 2018-06-28 14:57 | Yes | 120 |  |  |  | 2018-07-03 08:22 |  |  |  |  | 2018-07-03 20:00 | Yes | -9
VD-9001-307A-DWG-012 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-02-28 | 2018-06-28 14:57 | 2018-06-28 14:57 | Yes | 120 |  |  |  | 2018-07-03 08:23 |  |  |  |  | 2018-07-03 20:00 | Yes | -9
VD-9001-307A-DWG-013 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-02-28 | 2018-09-07 16:54 | 2018-09-07 16:54 | Yes | 191 |  |  |  | 2018-09-15 11:40 |  |  |  |  | 2018-09-15 19:58 | Yes | -6
VD-9001-307A-DWG-014 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-02-28 | 2018-09-07 16:54 | 2018-09-07 16:54 | Yes | 191 |  |  |  | 2018-09-15 11:41 |  |  |  |  | 2018-09-15 19:58 | Yes | -6
VD-9001-307A-DWG-015 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-03-28 | 2018-05-18 16:26 | 2018-05-18 16:27 | Yes | 51 |  |  | 2018-05-29 11:16 | [5 empty] | 2018-05-29 19:59 | Yes | -3 | 1204-Owner-v | 2020-04-23 17:38
VD-9001-307A-DWG-016 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-03-28 | 2018-05-18 16:27 | 2018-05-18 16:28 | Yes | 51 |  |  | 2018-05-29 11:16 | [5 empty] | 2018-05-29 19:59 | Yes | -3
VD-9001-307A-DWG-017 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-03-28 | 2018-05-18 16:27 | 2018-05-18 16:28 | Yes | 51 |  |  | 2018-05-29 11:27 | [5 empty] | 2018-05-29 19:59 | Yes | -3
VD-9001-307A-DWG-018 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-03-28 | 2018-05-18 16:27 | 2018-05-18 16:28 | Yes | 51 |  |  | 2018-05-29 11:27 | [5 empty] | 2018-05-29 19:59 | Yes | -3
VD-9001-307A-DWG-019 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-03-28 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-307A-DWG-020 | 0 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-021 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-022 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 | 2018-09-07 16:54 | 2018-09-07 16:54 | Yes | 140 |  |  | 2018-10-15 10:47 | [5 empty] | 2018-10-15 18:57 | Yes | 24 | 1204-Owner-v | 2020-04-23 17:39
VD-9001-307A-DWG-023 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-024 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-025 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-026 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-027 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-028 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-029 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-030 | 0 | Pipeline Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-031 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-05-11 | 2018-07-06 16:31 | 2018-07-06 16:31 | Yes | 56 |  |  |  | 2018-07-21 15:26 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:32
VD-9001-307A-DWG-032 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-06-29 | 2018-07-06 16:31 | 2018-07-06 16:31 | Yes | 7 |  |  |  | 2018-07-21 15:26 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:32
VD-9001-307A-DWG-033 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-05-11 | 2018-07-06 16:31 | 2018-07-06 16:32 | Yes | 56 |  |  |  | 2018-07-21 15:27 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:32
VD-9001-307A-DWG-034 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-06-29 | 2018-07-06 16:31 | 2018-07-06 16:32 | Yes | 7 |  |  |  | 2018-07-21 15:27 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:32
VD-9001-307A-DWG-035 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-307A-DWG-036 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-037 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-307A-DWG-038 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-039 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-05-11 | 2018-07-06 16:31 | 2018-07-06 16:32 | Yes | 56 |  |  |  | 2018-07-21 10:57 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:31
VD-9001-307A-DWG-040 | 0 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-04-30 | 2018-07-06 16:32 | 2018-07-06 16:32 | Yes | 67 |  |  |  | 2018-07-21 10:57 |  |  |  |  | 2018-07-21 19:59 | Yes | 1 | 1204-Owner-v | 2018-10-31 15:33
VD-9001-307A-DWG-041 | 0 | Coupling Drawing (Pump Side) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-042 | 0 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-11-12 16:12 | 2018-11-12 16:15 | Yes | 196 |  |  |  | 2018-11-17 15:21 |  |  |  |  | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DWG-043 | 0 | Coupling Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-044 | 0 | Coupling Drawing (Pump Side) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-045 | 0 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-11-12 16:13 | 2018-11-12 16:15 | Yes | 196 |  |  |  | 2018-11-17 15:18 |  |  |  |  | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DWG-046 | 0 | Coupling Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-047 | 0 | Coupling Drawing (Pump Side) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-048 | 0 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-11-12 16:13 | 2018-11-12 16:15 | Yes | 196 |  |  |  | 2018-11-17 15:15 |  |  |  |  | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DWG-049 | 0 | Coupling Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-050 | 0 | Coupling Drawing (Pump Side) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-051 | 0 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-11-12 16:14 | 2018-11-12 16:16 | Yes | 196 |  |  |  | 2018-11-17 15:10 |  |  |  |  | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DWG-052 | 0 | Coupling Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-053 | 0 | Coupling Drawing (Pump Side) | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-054 | 0 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-04-30 | 2018-11-12 16:14 | 2018-11-12 16:16 | Yes | 196 |  |  |  | 2018-11-17 15:02 |  |  |  |  | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DWG-055 | 0 | Coupling Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-056 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-057 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-058 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-059 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-307A-DWG-060 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-061 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-062 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-063 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-064 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-065 | 0 | Seal System Drawing | MC-307A | KSB GERMANY | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-307A-DWG-066 | 0 | Gear Box Drawing | MC-307A | KSB GERMANY | 2018-04-13 | 2018-11-12 16:17 | 2018-11-12 16:19 | Yes | 213 |  |  | 2018-11-17 14:48 | [5 empty] | 2018-11-17 20:00 | Yes | -9 | 1204-Owner-v | 2020-04-23 17:41
VD-9001-307A-DWG-067 | 0 | Gear Box Drawing | MC-307A | KSB GERMANY | 2018-04-13 | 2018-11-12 16:17 | 2018-11-12 16:19 | Yes | 213 |  |  | 2018-11-17 11:51 | [5 empty] | 2018-11-17 20:00 | Yes | -9 | 1204-Owner-v | 2020-04-23 17:42
VD-9001-307A-DWG-068 | 0 | Gear Box Drawing | MC-307A | KSB GERMANY | 2018-04-13 | 2018-11-12 16:17 | 2018-11-12 16:20 | Yes | 213 |  |  | 2018-11-17 11:29 | [5 empty] | 2018-11-17 20:00 | Yes | -9 | 1204-Owner-v | 2020-04-23 17:42
VD-9001-307A-DWG-069 | 0 | Gear Box Drawing | MC-307A | KSB GERMANY | 2018-04-13 | 2018-11-12 16:21 | 2018-11-12 16:22 | Yes | 213 |  |  | 2018-11-17 11:21 | [5 empty] | 2018-11-17 20:00 | Yes | -9 | 1204-Owner-v | 2020-04-23 17:43
VD-9001-307A-DWG-070 | 0 | Gear Box Drawing | MC-307A | KSB GERMANY | 2018-04-20 | 2018-11-12 16:19 | 2018-11-12 16:20 | Yes | 206 |  |  | 2018-11-17 11:24 | [5 empty] | 2018-11-17 20:00 | Yes | -9 | 1204-Owner-v | 2020-04-23 17:44
VD-9001-307A-DWG-071 | 0 | Motor Drawing | MC-307A | KSB GERMANY | 2018-05-25 | 2018-05-30 09:30 | 2018-05-30 09:32 | Yes | 5 |  |  | 2018-06-18 11:10 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-10-10 10:43
VD-9001-307A-DWG-072 | 0 | Motor Drawing | MC-307A | KSB GERMANY | 2018-04-20 | 2018-04-06 15:44 | 2018-04-06 15:44 | Yes | -14 |  |  |  | 2018-04-17 17:12 |  |  |  |  | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DWG-073 | 0 | Motor Drawing | MC-307A | KSB GERMANY | 2018-04-20 | 2018-06-29 12:44 | 2018-06-29 12:44 | Yes | 70 |  |  | 2018-07-02 10:53 | [5 empty] | 2018-07-02 20:00 | Yes | -11
VD-9001-307A-DWG-074 | 0 | Motor Drawing | MC-307A | KSB GERMANY | 2018-05-25 | 2018-10-04 12:50 | 2018-10-04 12:59 | Yes | 132 |  |  | 2018-10-07 15:33 | [5 empty] | 2018-10-07 18:58 | Yes | -11
VD-9001-307A-DWG-075 | 0 | Motor Drawing | MC-307A | KSB GERMANY | 2018-04-20 | 2018-04-16 13:26 | 2018-04-16 13:26 | Yes | -4 |  |  |  | 2018-04-18 10:29 |  |  |  |  | 2018-04-18 20:00 | Yes | -12
VD-9001-307A-DWG-076 | 0 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-04-20 | 2018-04-06 15:45 | 2018-04-06 15:45 | Yes | -14 |  |  |  | 2018-04-17 17:11 |  |  |  |  | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DWG-077 | 0 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-04-06 15:45 | 2018-04-06 15:45 | Yes | -49 |  |  |  | 2018-04-17 17:10 |  |  |  |  | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DWG-078 | 0 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-04-20 | 2018-06-29 12:45 | 2018-06-29 12:45 | Yes | 70 |  |  |  | 2018-07-02 11:01 |  |  |  |  | 2018-07-02 20:00 | Yes | -11
VD-9001-307A-DWG-079 | 0 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-04-20 | 2018-06-29 12:45 | 2018-06-29 12:45 | Yes | 70 |  |  |  | 2018-07-02 10:52 |  |  |  |  | 2018-07-02 20:00 | Yes | -11
VD-9001-307A-DWG-080 | 0 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-04-20 10:49 | 2018-04-20 10:49 | Yes | -35 |  |  |  | 2018-04-24 09:14 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-DWG-081 | 0 | General Arangement Drawing Turbine | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-082 | 0 | General Arangement Drawing Turbine | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-083 | 0 | General Arangement Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-084 | 0 | General Arangement Drawing Turbine | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-085 | 0 | General Arangement Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-086 | 0 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-05-04 | 2018-11-27 13:34 | 2018-11-27 13:34 | Yes | 207 |  |  |  | 2018-12-01 15:44 |  |  |  |  | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DWG-087 | 0 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-05-04 | 2018-11-27 13:35 | 2018-11-27 13:35 | Yes | 207 |  |  |  | 2018-12-01 15:42 |  |  |  |  | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DWG-088 | 0 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-05-04 | 2018-11-27 13:36 | 2018-11-27 13:36 | Yes | 207 |  |  |  | 2018-12-01 15:36 |  |  |  |  | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DWG-089 | 0 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-05-04 | 2018-11-27 13:37 | 2018-11-27 13:37 | Yes | 207 |  |  |  | 2018-12-01 15:33 |  |  |  |  | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DWG-090 | 0 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-05-04 | 2018-11-27 13:37 | 2018-11-27 13:37 | Yes | 207 |  |  |  | 2018-12-01 15:32 |  |  |  |  | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DWG-091 | 0 | Pipeline Drawing with Parts List Turbine | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-092 | 0 | Pipeline Drawing with Parts List Turbine | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-093 | 0 | Pipeline Drawing with Parts List Turbine | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-094 | 0 | Pipeline Drawing with Parts List Turbine | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-095 | 0 | Pipeline Drawing with Parts List Turbine | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-096 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-097 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-098 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-099 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DWG-100 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-101 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-102 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-103 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-104 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-105 | 0 | Nameplate Drawing Pump | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-106 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-107 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-108 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-109 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-110 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-111 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-112 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-113 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-114 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-115 | 0 | Nameplate Drawing´s (Seal System) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-116 | 0 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-06 15:45 | 2018-04-06 15:45 | Yes | -84 |  |  | 2018-04-17 09:11 | [5 empty] | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DWG-117 | 0 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-06 15:45 | 2018-04-06 15:45 | Yes | -84 |  |  | 2018-04-17 09:09 | [5 empty] | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DWG-118 | 0 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-06-29 | 2018-08-02 13:58 | 2018-08-02 13:59 | Yes | 34 |  |  | 2018-08-08 11:20 | [5 empty] | 2018-08-08 19:59 | Yes | -8
VD-9001-307A-DWG-119 | 0 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-06-29 | 2018-07-06 16:32 | 2018-07-06 16:32 | Yes | 7 |  |  | 2018-07-14 14:58 | [5 empty] | 2018-07-14 20:00 | Yes | -6
VD-9001-307A-DWG-120 | 0 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-05-25 | 2018-04-20 10:50 | 2018-04-20 10:50 | Yes | -35 |  |  |  | 2018-04-24 09:25 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-DWG-121 | 0 | Nameplate Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-122 | 0 | Nameplate Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-123 | 0 | Nameplate Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-124 | 0 | Nameplate Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-125 | 0 | Nameplate Drawing Turbine | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-126 | 0 | Local Gauge Board Drawing (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-127 | 0 | Local Gauge Board Drawing (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-128 | 0 | Local Gauge Board Drawing (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-129 | 0 | Local Gauge Board Drawing (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-130 | 0 | Local Gauge Board Drawing (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-131 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-132 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-133 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-134 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-135 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-136 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-137 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-138 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-139 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-140 | 0 | Junction Box GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-141 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-142 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-143 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-144 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-307A-DWG-145 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-146 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-147 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-148 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-149 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DWG-150 | 0 | Main control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-151 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-152 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-153 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-154 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-155 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-156 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-157 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-158 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-159 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-160 | 0 | Local control panel GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-161 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-162 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-163 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-164 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-165 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-166 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-167 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-168 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-169 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-170 | 0 | Local gauge board GAD (Control Unit) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-001 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-002 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 | 2018-09-07 16:50 | 2018-09-07 16:50 | Yes | 56 |  |  |  | 2018-10-15 09:42 |  |  |  |  | 2018-10-15 18:57 | Yes | 24 | 1204-Owner-v | 2018-10-09 15:49
VD-9001-307A-DIG-003 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-004 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 | 2018-11-12 16:02 | 2018-11-12 16:09 | Yes | 122 |  |  |  | 2018-12-11 14:26 |  |  |  |  | 2018-12-11 19:59 | Yes | 15
VD-9001-307A-DIG-005 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-006 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-007 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-008 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-009 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-010 | 0 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-011 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-012 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-013 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-014 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-015 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-016 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-017 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-018 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-019 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-020 | 0 | Seal System P&I Diagram | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-021 | 0 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-05-24 18:29 | 2018-05-24 18:31 | Yes | -50 |  |  |  | 2018-07-22 16:10 |  |  |  |  | 2018-07-22 20:00 | Yes | 45
VD-9001-307A-DIG-022 | 0 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-023 | 0 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-06-19 17:57 | 2018-06-19 17:57 | Yes | -24 |  |  |  | 2018-07-30 14:41 |  |  |  |  | 2018-07-30 19:59 | Yes | 27
VD-9001-307A-DIG-024 | 0 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-025 | 0 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-026 | 0 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-04-06 15:44 | 2018-04-06 15:44 | Yes | -98 |  |  | 2018-04-17 10:31 | [5 empty] | 2018-04-17 20:00 | Yes | -3 | 1204-Owner-v | 2018-08-01 07:42
VD-9001-307A-DIG-027 | 0 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-04-06 15:44 | 2018-04-06 15:44 | Yes | -98 |  |  | 2018-04-17 10:29 | [5 empty] | 2018-04-17 20:00 | Yes | -3
VD-9001-307A-DIG-028 | 0 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-06-29 12:43 | 2018-06-29 12:43 | Yes | -14 |  |  | 2018-07-02 10:57 | [5 empty] | 2018-07-02 20:00 | Yes | -11
VD-9001-307A-DIG-029 | 0 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-07-13 | 2018-06-29 12:44 | 2018-06-29 12:44 | Yes | -14 |  |  | 2018-07-02 10:50 | [5 empty] | 2018-07-02 20:00 | Yes | -11 | 1204-Owner-v | 2018-10-10 10:26
VD-9001-307A-DIG-030 | 0 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-06-01 | 2018-04-20 10:48 | 2018-04-20 10:48 | Yes | -42 |  |  |  | 2018-04-24 09:26 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-DIG-031 | 0 | Wiring Diagram Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-032 | 0 | Wiring Diagram Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-033 | 0 | Wiring Diagram Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-034 | 0 | Wiring Diagram Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-035 | 0 | Wiring Diagram Turbine | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-036 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-037 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-038 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-039 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-307A-DIG-040 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-041 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-042 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-043 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-044 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-045 | 0 | Control Wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-046 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-047 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-048 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-049 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-307A-DIG-050 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-051 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-052 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-053 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-054 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-055 | 0 | Electrical Connection and all junction boxes diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DIG-056 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DIG-057 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DIG-058 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DIG-059 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-307A-DIG-060 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-061 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-062 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-063 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-064 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-065 | 0 | Interconnection block diagrams (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-066 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-067 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-068 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-069 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-070 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-071 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-072 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-073 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-074 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DIG-075 | 0 | Loop wiring diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-076 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-077 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-078 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-079 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-080 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-081 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-082 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-083 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-084 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-DIG-085 | 0 | Logic diagram (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-001 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-002 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-003 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-004 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-005 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-006 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-007 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-008 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-009 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-010 | 0 | Bill of Material (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-011 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-012 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-013 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-014 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-015 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-016 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-017 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-018 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-019 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-020 | 0 | Valve List (Data Sheet´s & Drawing) (Seal System) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-021 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-022 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-023 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-024 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-025 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-026 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-027 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-028 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-029 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-030 | 0 | Termination list for Input/Outputs (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-031 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-032 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-033 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-034 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-035 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-036 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-037 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-038 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-039 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-040 | 0 | Modbus list (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-001 | 0 | Calculation Data for Control Valves | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-002 | 0 | Calculation Data for Control Valves | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-003 | 0 | Calculation Data for Control Valves | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-004 | 0 | Calculation Data for Control Valves | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-005 | 0 | Calculation Data for Control Valves | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-006 | 0 | Safty Valves calculations | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-007 | 0 | Safty Valves calculations | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-008 | 0 | Safty Valves calculations | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-009 | 0 | Safty Valves calculations | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAL-010 | 0 | Safty Valves calculations | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-ITP-001 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-03-15 17:28 | 2018-03-15 17:28 | Yes | -106 |  |  |  | 2018-04-08 15:25 |  |  |  |  | 2018-04-08 20:00 | Yes | 10 | 1204-Owner-v | 2018-09-12 12:36
VD-9001-307A-ITP-002 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-03-15 17:28 | 2018-03-15 17:28 | Yes | -106 |  |  |  | 2018-04-08 15:15 |  |  |  |  | 2018-04-08 20:00 | Yes | 10
VD-9001-307A-ITP-003 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-03-15 17:28 | 2018-03-15 17:28 | Yes | -106 |  |  |  | 2018-04-08 15:13 |  |  |  |  | 2018-04-08 20:00 | Yes | 10
VD-9001-307A-ITP-004 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-03-15 17:28 | 2018-03-15 17:28 | Yes | -106 |  |  |  | 2018-04-08 15:09 |  |  |  |  | 2018-04-08 20:00 | Yes | 10
VD-9001-307A-ITP-005 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-27 13:14 | 2018-04-27 13:14 | Yes | -63 |  |  |  | 2018-04-30 09:24 |  |  |  |  | 2018-04-30 19:59 | Yes | -11 | 1204-Owner-v | 2018-12-02 11:03
VD-9001-307A-ITP-006 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-27 13:15 | 2018-04-27 13:24 | Yes | -63 |  |  |  | 2018-04-30 09:29 |  |  |  |  | 2018-04-30 20:00 | Yes | -11
VD-9001-307A-ITP-007 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-27 13:15 | 2018-04-27 13:24 | Yes | -63 |  |  |  | 2018-04-30 09:30 |  |  |  |  | 2018-04-30 20:00 | Yes | -11
VD-9001-307A-ITP-008 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-04-27 13:15 | 2018-04-27 13:24 | Yes | -63 |  |  |  | 2018-04-30 09:35 |  |  |  |  | 2018-04-30 20:00 | Yes | -11
VD-9001-307A-ITP-009 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-29 | 2018-06-19 17:58 | 2018-06-19 17:58 | Yes | -10 |  |  |  | 2018-06-30 11:05 |  |  |  |  | 2018-06-30 20:00 | Yes | -3 | 1204-Owner-v | 2020-01-01 10:50
VD-9001-307A-ITP-010 | 0 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-11-09 | 2018-06-19 17:58 | 2018-06-19 17:58 | Yes | -143 |  |  |  | 2018-06-30 11:08 |  |  |  |  | 2018-06-30 20:00 | Yes | -3 | 1204-Owner-v | 2020-01-01 10:50
VD-9001-307A-INX-002 | 0 | MDR Index for P-2002 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-003 | 0 | MDR Index for P-2002 B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-004 | 0 | MDR Index for P-2003 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-005 | 0 | MDR Index for P-2003 B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-006 | 0 | MDR Index for P-4001 A/B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-007 | 0 | MDR Index for P-4001 C | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-008 | 0 | MDR Index for P-4002 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-009 | 0 | MDR Index for P-4002 B/C | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-010 | 0 | MDR Index for P-6301 A/B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-INX-011 | 0 | MDR Index for P-6301 C/D/E/F | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-001 | 0 | MDR for P-2002 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-002 | 0 | MDR for P-2002 B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-003 | 0 | MDR for P-2003 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-004 | 0 | MDR for P-2003 B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-005 | 0 | MDR for P-4001 A/B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-006 | 0 | MDR for P-4001 C | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-007 | 0 | MDR for P-4002 A | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-008 | 0 | MDR for P-P-4002 B/C | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-009 | 0 | MDR for P-6301 A/B | MC-307A | KSB GERMANY | 2018-11-09 |  |  | No | 588 | [9 empty] | No | 0
VD-9001-307A-MDB-010 | 0 | MDR for P-6301 C/D/E/F | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-001 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-002 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-003 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-004 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-005 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-006 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-007 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-008 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-009 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-SPE-010 | 0 | Functional design specification for hardware & software (Control Unit) | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-301-PCJ-010 | 1 | coating procedure syngas train | MC-301 | Siemens AG | 2018-02-21 20:00 | 2018-03-10 09:07 | 2018-03-10 09:07 | Yes | 17 |  |  |  | 2018-03-11 15:13 |  |  |  |  | 2018-03-11 20:00 | Yes | -13
VD-9001-301-PCJ-011 | 1 | coating procedure circulator train | MC-301 | Siemens AG | 2018-02-21 20:00 | 2018-03-10 09:07 | 2018-03-10 09:08 | Yes | 17 |  |  |  | 2018-04-08 10:48 |  |  |  |  | 2018-04-08 20:00 | Yes | 15
VD-9001-301-DBS-001 | 1 | condenser air cooled syngas turbine | MC-301 | Siemens AG | 2018-02-21 20:00 | 2018-02-27 09:33 | 2018-02-27 09:33 | Yes | 6 |  |  |  | 2018-03-12 16:34 |  |  |  |  | 2018-03-12 20:00 | Yes | -1
VD-9001-257C-GAD-006 | 1 | GENERAL ARRANGEMENT (4137-0369) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 13:45 | 2018-05-14 13:45 | Yes | 81 |  |  |  |  | 2018-08-05 16:55 |  |  |  | 2018-08-05 16:55 | Yes | 69 | 1204-Owner-v | 2018-08-04 14:03
VD-9001-257C-DWG-031 | 1 | DETAILS DRAWING (4137-0369/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 14:13 | 2018-05-14 14:13 | Yes | 81 |  |  | 2018-07-21 19:57 | [5 empty] | 2018-07-21 19:57 | Yes | 54 | 1204-Owner-v | 2019-01-30 14:20
VD-9001-257C-DWG-032 | 1 | DETAILS DRAWING (4137-0369/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 14:15 | 2018-05-14 14:15 | Yes | 81 |  |  |  |  | 2018-11-28 17:21 |  |  |  | 2018-11-28 17:21 | Yes | 184
VD-9001-257C-CAL-006 | 1 | MECHANICAL CALCULATION (4137-0369/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 13:54 | 2018-05-14 13:55 | Yes | 81 |  |  | 2018-08-21 11:51 | [5 empty] | 2018-08-21 11:51 | Yes | 85 | 1204-Owner-v | 2018-08-19 08:54
VD-9001-257C-DWG-033 | 1 | NAME PLATE DET.DWG (4137-0369/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 14:15 | 2018-05-14 14:15 | Yes | 81 |  |  |  |  | 2018-07-21 19:53 |  |  |  | 2018-07-21 19:53 | Yes | 54
VD-9001-257C-DWG-009 | 1 | NAME PLATE DET.DWG (4137-0365/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-22 20:00 | 2018-05-14 14:09 | 2018-05-14 14:10 | Yes | 81 |  |  | 2018-05-29 14:28 | [5 empty] | 2018-05-29 14:28 | Yes | 1
VD-9001-251-DWG-039 | 1 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-03-13 18:58 | 2018-03-13 19:00 | Yes | 31 |  |  | 2018-04-07 14:27 | [5 empty] | 2018-04-07 14:27 | Yes | 11
VD-9001-251-DWG-038 | 1 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-03-13 18:48 | 2018-03-13 18:57 | Yes | 31 |  |  | 2018-04-07 14:26 | [5 empty] | 2018-04-07 14:26 | Yes | 11
VD-9001-251-DWG-037 | 1 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-03-13 18:39 | 2018-03-13 18:47 | Yes | 31 |  |  | 2018-04-07 14:25 | [5 empty] | 2018-04-07 14:25 | Yes | 11
VD-9001-251-DWG-036 | 1 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-03-13 18:24 | 2018-03-13 18:38 | Yes | 31 |  |  | 2018-04-07 14:23 | [5 empty] | 2018-04-07 14:23 | Yes | 11
VD-9001-251-DWG-035 | 1 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-03-13 18:18 | 2018-03-13 18:38 | Yes | 31 |  |  | 2018-04-07 14:24 | [5 empty] | 2018-04-07 14:24 | Yes | 11
VD-9001-251-DWG-034 | 1 | ARCH PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-06-07 17:34 | 2018-06-07 17:41 | Yes | 117 |  |  | 2018-06-13 15:27 | [5 empty] | 2018-06-13 15:27 | Yes | -8 | 1204-Owner-v | 2019-03-10 14:50
VD-9001-251-DWG-033 | 1 | FLOOR PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-06-07 17:32 | 2018-06-07 17:41 | Yes | 117 |  |  | 2018-06-13 15:28 | [5 empty] | 2018-06-13 15:28 | Yes | -8 | 1204-Owner-v | 2019-03-10 14:50
VD-9001-251-PPL-003 | 1 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-04-23 19:04 | 2018-04-23 19:06 | Yes | 72 |  |  |  | 2018-04-28 18:23 |  |  |  |  | 2018-04-28 18:23 | Yes | -9
VD-9001-251-PPL-002 | 1 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-04-23 19:01 | 2018-04-23 19:03 | Yes | 72 |  |  |  | 2018-04-28 18:19 |  |  |  |  | 2018-04-28 18:19 | Yes | -9
VD-9001-251-PPL-001 | 1 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 | 2018-04-23 19:00 | 2018-04-23 19:00 | Yes | 72 |  |  |  | 2018-04-28 18:12 |  |  |  |  | 2018-04-28 18:12 | Yes | -9 | 1204-Owner-v | 2018-04-25 10:13
VD-9001-251-VLS-001 | 1 | SUBVENDORS LIST | HM-251 | KT – Kinetics Technology SpA | 2018-02-10 |  |  | No | 860 | [9 empty] | No | 0
VD-9001-104-REQ-018 | 2 | PU-6101_E-6108/ E-6108-D1_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-10 17:26 | 2018-02-13 12:43 | 2018-02-13 12:44 | Yes | 3 |  | 2018-02-13 17:22 | [6 empty] | 2018-02-13 20:00 | Yes | -14
VD-9001-257C-WBK-001 | 1 | WELDING BOOK (4137-0364/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-24 20:00 | 2018-06-22 17:43 | 2018-06-22 17:44 | Yes | 118 |  |  | 2018-07-12 17:00 | [5 empty] | 2018-07-12 17:00 | Yes | 6
VD-9001-257C-WBK-002 | 1 | WELDING BOOK (4137-0365/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-02-24 20:00 | 2018-06-22 17:56 | 2018-06-22 17:56 | Yes | 118 |  |  |  |  | 2018-06-28 15:54 |  |  |  | 2018-06-28 15:54 | Yes | -8
VD-9001-104-PCJ-001 | 1 | Particular specification for equipment labeling, packaging, marking and storage administrative procedure for supplier orders | PR-104 | AIR LIQUIDE | 2018-02-24 20:00 | 2018-03-08 17:38 | 2018-03-08 18:10 | Yes | 12 |  |  | 2018-03-12 08:58 | [5 empty] | 2018-03-12 20:00 | Yes | -10 | 1204-Owner-v | 2018-04-04 14:58
VD-9001-104(002)-DWG-003 | 1 | D-6103 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-24 20:00 | 2018-06-06 19:21 | 2018-06-06 19:27 | Yes | 102 |  |  | 2018-06-18 14:32 | [5 empty] | 2018-06-18 20:00 | Yes | -2
VD-9001-104(002)-DWG-002 | 1 | D-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-24 20:00 | 2018-06-06 19:21 | 2018-08-02 11:43 | Yes | 102 |  |  |  | 2018-08-12 15:20 |  |  |  |  | 2018-08-12 20:00 | Yes | 53
VD-9001-104-REQ-019 | 1 | FT-6101/FT-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-24 20:00 | 2018-04-24 19:07 | 2018-04-24 19:08 | Yes | 59 |  |  |  | 2018-05-23 17:27 |  |  |  |  | 2018-05-23 19:59 | Yes | 15
VD-9001-301-PID-001 | 1 | P+I Diagram Symbols syngas train | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 11:59 | 2018-03-04 14:26 | Yes | 6 |  |  | 2018-05-28 10:56 | [5 empty] | 2018-05-28 19:59 | Yes | 72 | 1204-Owner-v | 2018-04-17 13:14
VD-9001-301-PID-006 | 1 | P+I Diagram Oil Console Syngas and Circulator Trains | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:00 | 2018-03-04 14:27 | Yes | 5 |  |  |  |  | 2018-05-28 11:43 |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-007 | 1 | P+I Diagram Process gas Syngas Compressor | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:00 | 2018-03-04 14:27 | Yes | 5 |  |  |  | 2018-05-28 11:15 |  |  |  |  | 2018-05-28 19:59 | Yes | 72 | 1204-Owner-v | 2018-04-17 14:04
VD-9001-301-PID-002 | 1 | P+I Diagram Machine Syngas Compressor | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 11:59 | 2018-03-04 14:27 | Yes | 5 |  |  |  | 2018-05-28 11:05 |  |  |  |  | 2018-05-28 19:59 | Yes | 72 | 1204-Owner-v | 2018-04-17 14:07
VD-9001-301-PID-005 | 1 | P+I Diagram Oil Syngas Train | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:00 | 2018-03-04 14:27 | Yes | 5 |  |  |  | 2018-06-30 09:55 |  |  |  |  | 2018-06-30 20:00 | Yes | 105
VD-9001-301-PID-010 | 1 | P+I Diagram Control Oil Syngas Turbine | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:03 | 2018-03-04 14:28 | Yes | 5 |  |  |  |  | 2018-05-28 11:36 |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-015 | 1 | P+I Diagram Oil Circulator Train | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:04 | 2018-03-04 14:29 | Yes | 5 |  |  |  | 2018-06-18 11:26 |  |  |  |  | 2018-06-18 20:00 | Yes | 93
VD-9001-301-PID-008 | 1 | P+I Diagram Steam + Drainage Syngas Turbine | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:20 | 2018-03-04 14:23 | Yes | 5 |  |  |  | 2018-06-18 11:35 |  |  |  |  | 2018-06-18 20:00 | Yes | 93
VD-9001-301-PID-016 | 1 | P+I Diagram Process gas Circulator Compressor | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:04 | 2018-03-04 14:29 | Yes | 5 |  |  |  | 2018-05-28 11:20 |  |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-012 | 1 | P+I Diagram Machine (Circulator Compressor) | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 12:04 | 2018-03-04 14:28 | Yes | 5 |  |  |  | 2018-05-28 11:22 |  |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-004 | 1 | P+I Diagram Seal Gas Unit (Syngas Compressor) | MC-301 | Siemens AG | 2018-02-26 20:00 | 2018-03-03 11:59 | 2018-03-04 14:27 | Yes | 6 | [9 empty] | No | 825 | 1204-Owner-v | 2018-04-17 14:03
VD-9001-253(A)-MDB-115 | 4 | FINAL DATA BOOK INDEX | HM-253A | FATEH SANAT KIMIA | 2018-02-13 | 2018-02-19 09:06 | 2018-02-19 09:07 | Yes | 6 |  | 2018-02-26 09:45 | [6 empty] | 2018-02-26 19:59 | Yes | -7 | 1204-Owner-v | 2018-10-01 15:46
VD-9001-301-PID-003 | 1 | P+I Diagram Machine Syngas Turbine | MC-301 | Siemens AG | 2018-02-27 19:59 | 2018-03-03 11:59 | 2018-03-04 14:27 | Yes | 4 |  |  |  | 2018-05-28 11:00 |  |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-013 | 1 | P+I Diagram Machine Circulator Turbine | MC-301 | Siemens AG | 2018-02-27 19:59 | 2018-03-03 12:04 | 2018-03-04 14:28 | Yes | 4 |  |  |  | 2018-05-28 11:07 |  |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-011 | 1 | P+I Diagram Symbols Circulator Train | MC-301 | Siemens AG | 2018-02-27 19:59 | 2018-03-03 12:03 | 2018-03-04 14:28 | Yes | 5 |  |  | 2018-05-28 10:56 | [5 empty] | 2018-05-28 19:59 | Yes | 72
VD-9001-301-LST-006 | 1 | customer connection list syngas train | MC-301 | Siemens AG | 2018-02-27 19:59 | 2018-04-04 08:46 | 2018-04-04 08:46 | Yes | 36 |  |  |  | 2018-04-25 15:24 |  |  |  |  | 2018-04-25 20:00 | Yes | 7
VD-9001-301-LST-009 | 1 | customer connection list circulator train | MC-301 | Siemens AG | 2018-02-27 19:59 | 2018-04-04 08:46 | 2018-04-04 08:46 | Yes | 36 |  |  |  | 2018-04-25 15:23 |  |  |  |  | 2018-04-25 20:00 | Yes | 7
VD-9001-104-REQ-041 | 1 | Warm automatic butterfly valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-27 19:59 |  |  | No | 843 | [9 empty] | No | 0
VD-9001-254-DIG-336 | 2 | BMS LOGIC DIAGRAM | HM-254 | AZAR AB | 2018-02-27 19:59 | 2018-06-20 19:00 | 2018-06-20 19:00 | Yes | 113 |  |  | 2018-07-28 10:05 | [5 empty] | 2018-07-28 10:05 | Yes | 24 | 1204-Owner-v | 2018-11-26 13:37
VD-9001-104-REQ-040 | 1 | Warm automatic globe valve - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-27 20:00 |  |  | No | 843 | [9 empty] | No | 0
VD-9001-254-ISO-519 | 1 | ISOMETRIC DRAWING FOR COOLING WATER RETURN FROM F.D. FAN TURBINE(BOILER 5) | HM-254 | AZAR AB | 2018-02-27 20:00 | 2018-09-18 14:56 | 2018-09-18 14:56 | Yes | 203 |  |  | 2018-10-17 11:33 | [5 empty] | 2018-10-17 11:33 | Yes | 15 | 1204-Owner-v | 2019-05-14 16:11
VD-9001-254-ISO-520 | 1 | ISOMETRIC DRAWING FOR COOLING WATER RETURN FROM F.D. FAN TURBINE(BOILER 6) | HM-254 | AZAR AB | 2018-02-27 20:00 | 2018-09-18 14:56 | 2018-09-18 14:56 | Yes | 203 |  |  | 2018-10-17 11:31 | [5 empty] | 2018-10-17 11:31 | Yes | 15 | 1204-Owner-v | 2019-05-14 16:11
VD-9001-104-REQ-029 | 1 | Gas Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-27 20:00 |  |  | No | 843 | [9 empty] | No | 0
VD-9001-301-PID-014 | 1 | P+I Diagram Seal gas unit (Circulator Compressor) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-03-03 12:04 | 2018-03-04 14:29 | Yes | 5 | [9 empty] | No | 825
VD-9001-301-PID-017 | 1 | P+I Diagram Steam + Drainage Circulator Turbine | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-03-03 12:20 | 2018-03-04 14:23 | Yes | 4 |  |  |  |  | 2018-05-28 14:39 |  |  |  | 2018-05-28 19:59 | Yes | 72
VD-9001-301-PID-018 | 1 | P+I Diagram Control oil Circulator Turbine | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-03-03 12:04 | 2018-03-04 14:29 | Yes | 4 |  |  |  | 2018-06-18 11:13 |  |  |  |  | 2018-06-18 20:00 | Yes | 93
VD-9001-301-ARP-010 | 1 | rotor stability analysis syngas compressor | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-03-03 12:16 | 2018-03-04 14:23 | Yes | 5 |  |  | 2018-03-06 10:39 | [5 empty] | 2018-03-06 20:00 | Yes | -11
VD-9001-301-ARP-001 | 1 | rotor response analysis syngas compressor | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-03-03 12:15 | 2018-03-04 14:23 | Yes | 5 |  |  | 2018-03-10 09:39 | [5 empty] | 2018-03-10 20:00 | Yes | -7
VD-9001-301-CSS-001 | 1 | planning notes syngas turbine (limiting and protection) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:45 | 2018-02-21 10:46 | Yes | -6 |  |  | 2018-03-04 09:27 | [5 empty] | 2018-03-04 20:00 | Yes | -3 | 1204-Owner-v | 2018-04-04 14:16
VD-9001-301-CSS-003 | 1 | planning notes syngas turbine (drains) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:46 | 2018-02-21 10:47 | Yes | -6 |  |  | 2018-03-03 16:51 | [5 empty] | 2018-03-03 20:00 | Yes | -4
VD-9001-301-CSS-005 | 1 | planning notes circulator turbine (piping; equipm.; found.) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:46 | 2018-02-21 10:47 | Yes | -6 |  |  | 2018-03-03 16:24 | [5 empty] | 2018-03-03 20:00 | Yes | -4
VD-9001-301-CSS-006 | 1 | planning notes circulator turbine (drains) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:46 | 2018-02-21 10:47 | Yes | -6 |  |  | 2018-03-03 16:22 | [5 empty] | 2018-03-03 20:00 | Yes | -4
VD-9001-301-CSS-004 | 1 | planning notes circulator turbine (limiting and protection) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:46 | 2018-02-21 10:47 | Yes | -6 |  |  | 2018-03-17 10:27 | [5 empty] | 2018-03-17 20:00 | Yes | 10
VD-9001-301-CSS-002 | 1 | planning notes syngas turbine (piping; equipm.; found.) | MC-301 | Siemens AG | 2018-02-27 20:00 | 2018-02-21 10:46 | 2018-02-21 10:47 | Yes | -6 |  |  | 2018-03-04 09:10 | [5 empty] | 2018-03-04 20:00 | Yes | -3
VD-9001-201B-CAL-001 | 1 | MECHANICAL CALCULATION (4134-0359/MC) | PV-201B | Brembana & Rolle S.p.A. | 2018-02-28 20:00 | 2020-03-23 19:30 | 2020-03-23 19:30 | Yes | 754 |  |  |  | 2020-04-20 14:34 |  |  |  |  | 2020-04-20 21:00 | Yes | 14
VD-9001-204B-PCJ-006 | 4 | Hydrostatic and Air Leak Test Procedure | PV-204B | ABAN AIR COOLER. | 2018-02-15 11:40 | 2018-02-24 12:34 | 2018-02-24 12:34 | Yes | 9 |  |  | 2018-03-10 17:08 | [5 empty] | 2018-03-10 17:08 | Yes | 0 | 1204-Owner-v | 2018-12-23 16:21
VD-9001-104-LST-014 | 0 | GENERAL INPUT AND OUTPOUT LIST for instrumentation & electrical equipment | PR-104 | AIR LIQUIDE | 2018-04-01 | 2018-02-16 15:28 |  | No | -44 | 2018-02-21 17:01 | [7 empty] | 2018-02-21 20:00 | Yes | 0
VD-9001-104-DCR-003 | 0 | External loads for pressure vessel nozzles design | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-301-DCR-001 | 1 | foundation information syngas train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-14 14:51 | 2018-03-14 14:51 | Yes | 13 | [9 empty] | No | 814 | 1204-Owner-v | 2018-05-05 09:55
VD-9001-301-DWG-004 | 1 | foundation plan syngas train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-14 14:52 | 2018-03-14 14:52 | Yes | 13 |  |  |  | 2018-04-08 11:07 |  |  |  |  | 2018-04-08 20:00 | Yes | 11 | 1204-Owner-v | 2018-05-05 10:00
VD-9001-301-DWG-041 | 1 | general arrangement syngas train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-12 15:22 | 2018-03-12 15:22 | Yes | 11 |  |  |  | 2018-04-10 10:28 |  |  |  |  | 2018-04-10 20:00 | Yes | 15 | 1204-Owner-v | 2018-05-07 12:46
VD-9001-301-DWG-043 | 1 | general arrangement circulator train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-12 15:20 | 2018-03-12 15:21 | Yes | 11 |  |  |  | 2018-04-10 10:37 |  |  |  |  | 2018-04-10 20:00 | Yes | 15 | 1204-Owner-v | 2018-04-04 14:23
VD-9001-301-DCR-002 | 1 | foundation information circulator train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-14 14:48 | 2018-03-14 14:48 | Yes | 13 | [9 empty] | No | 814 | 1204-Owner-v | 2018-05-05 11:12
VD-9001-301-DWG-005 | 1 | foundation plan circulator train | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-14 14:49 | 2018-03-14 14:49 | Yes | 13 |  |  |  | 2018-04-08 15:41 |  |  |  |  | 2018-04-08 20:00 | Yes | 11 | 1204-Owner-v | 2018-05-21 11:28
VD-9001-301-QCP-005 | 1 | quality control plan Syngas Compressor | MC-301 | Siemens AG | 2018-03-01 19:59 | 2018-03-10 09:04 | 2018-03-10 09:04 | Yes | 9 |  |  | 2018-05-20 08:58 | [5 empty] | 2018-05-20 19:59 | Yes | 57 | 1204-Owner-v | 2018-04-04 14:22
VD-9001-460A-PCJ-001 | 2 | Application procedure for coating & wrapping | PI-460A | Nia Shimi Co. | 2018-02-17 | 2018-03-04 14:12 | 2018-03-04 14:12 | Yes | 15 |  |  | 2018-03-04 14:27 |  |  |  | 2018-03-04 08:33 | 2018-03-04 08:33 | 2018-03-04 14:29 | Yes | -14
VD-9001-461AP-MTC-001 | 1 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-17 | 2018-04-16 13:07 | 2018-04-16 13:36 | Yes | 58 |  |  | 2018-04-16 14:25 | [5 empty] | 2018-04-16 14:25 | Yes | -14
VD-9001-461AP-MTC-002 | 1 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-17 | 2018-04-13 20:23 | 2018-04-13 20:23 | Yes | 55 |  |  | 2018-04-14 10:44 | [5 empty] | 2018-04-14 10:44 | Yes | -13
VD-9001-461AP-MTC-003 | 1 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-17 | 2018-04-13 20:24 | 2018-04-13 20:24 | Yes | 55 |  |  | 2018-04-14 10:33 | [5 empty] | 2018-04-14 10:33 | Yes | -13
VD-9001-461AP-MTC-004 | 1 | MATERIAL TEST CERTIFICATE | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-02-17 | 2018-04-13 20:25 | 2018-04-13 20:25 | Yes | 55 |  |  | 2018-04-14 10:25 | [5 empty] | 2018-04-14 10:26 | Yes | -13
VD-9001-204C-DWG-004 | 1 | DETAILS DWG. With Nozzle Details | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-17 | 2018-03-26 15:32 | 2018-03-26 15:32 | Yes | 37 |  |  |  | 2018-04-22 11:29 |  |  |  |  | 2018-04-22 20:00 | Yes | 13
VD-9001-104(004)-DWG-001 | 1 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-03 20:00 |  |  | No | 839 | [9 empty] | No | 0
VD-9001-104-PPL-006 | 1 | Electrical main cable routing Basic Design - Plot plan top view | PR-104 | AIR LIQUIDE | 2018-03-03 20:00 |  |  | No | 839 | [9 empty] | No | 0
VD-9001-104(002)-ITP-002 | 1 | T-6101 & E-6102 - Vaporizer shell - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-03-03 20:00 |  |  | No | 839 | [9 empty] | No | 0
VD-9001-104(002)-ITP-001 | 1 | D-6103 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-03-03 20:00 |  |  | No | 839 | [9 empty] | No | 0
VD-9001-204B-PCJ-012 | 0 | Production Test plate Procedure | PV-204B | ABAN AIR COOLER. | 2018-04-01 | 2018-02-27 15:32 | 2018-02-27 15:32 | Yes | -33 |  |  |  |  | 2018-03-14 16:44 |  |  |  | 2018-03-14 16:44 | Yes | 1
VD-9001-204B-PCJ-013 | 0 | Ferrite Checking Procedure | PV-204B | ABAN AIR COOLER. | 2018-04-01 | 2018-03-10 13:54 | 2018-03-10 13:54 | Yes | -22 |  |  |  |  | 2018-03-14 18:03 |  |  |  | 2018-03-14 18:03 | Yes | -10 | 1204-Owner-v | 2018-04-04 13:56
VD-9001-204B-DIS-001 | 3 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2018-02-18 14:49 | 2018-02-19 10:25 |  | No | 1 | 2018-02-19 11:23 | [7 empty] | 2018-02-19 19:59 | Yes | 0
VD-9001-201-DWG-006 | 2 | INTERNAL MISCELLANEOUS DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2018-02-18 | 2018-03-27 13:44 | 2018-04-03 11:51 | Yes | 37 |  |  |  | 2018-04-17 11:27 |  |  |  |  | 2018-04-17 11:27 | Yes | 7
VD-9001-254-SOI-956 | 1 | ITP FOR BURNER | HM-254 | AZAR AB | 2018-03-04 19:59 |  |  | No | 838 | [9 empty] | No | 0
VD-9001-257C-DWG-052 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0364/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 19:59 | 2018-05-14 14:03 | 2018-05-14 14:03 | Yes | 71 |  |  | 2018-07-22 10:45 | [5 empty] | 2018-07-22 10:45 | Yes | 55
VD-9001-254-ISO-518 | 1 | ISOMETRIC DRAWING FOR COOLING WATER SUPPLY FOR F.D. FAN TURBINE(BOILER 6) | HM-254 | AZAR AB | 2018-03-04 20:00 | 2018-09-18 07:57 | 2018-09-18 07:57 | Yes | 198 |  |  | 2018-10-17 11:35 | [5 empty] | 2018-10-17 11:35 | Yes | 15 | 1204-Owner-v | 2019-05-14 16:10
VD-9001-254-ISO-517 | 1 | ISOMETRIC DRAWING FOR COOLING WATER SUPPLY FOR F.D. FAN TURBINE (BOILER 5) | HM-254 | AZAR AB | 2018-03-04 20:00 | 2018-09-18 07:56 | 2018-09-18 07:56 | Yes | 198 |  |  | 2018-10-17 11:37 | [5 empty] | 2018-10-17 11:37 | Yes | 15 | 1204-Owner-v | 2019-05-14 16:09
VD-9001-257C-DWG-001 | 1 | DETAILS DRAWING (4137-0364/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 20:00 | 2018-05-14 14:00 | 2018-05-14 14:00 | Yes | 71 |  |  | 2018-07-21 20:16 | [5 empty] | 2018-07-21 20:16 | Yes | 54 | 1204-Owner-v | 2019-01-30 14:12
VD-9001-257C-GAD-001 | 1 | GENERAL ARRANGEMENT (4137-0364) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 20:00 | 2018-05-14 13:42 | 2018-05-14 13:42 | Yes | 71 |  |  |  |  | 2018-08-15 12:00 |  |  |  | 2018-08-15 12:00 | Yes | 79 | 1204-Owner-v | 2018-08-04 13:05
VD-9001-301-DWG-008 | 1 | Predicted Performance Curves Overall Syngas Compressor | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-02-27 09:34 | 2018-02-27 09:34 | Yes | -5 |  |  |  | 2018-04-23 09:15 |  |  |  |  | 2018-04-23 20:00 | Yes | 41
VD-9001-301-DWG-009 | 1 | overall perform. curves circulator compressor (pred.) | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-02-27 09:34 | 2018-02-27 09:34 | Yes | -5 |  |  |  | 2018-04-23 09:17 |  |  |  |  | 2018-04-23 20:00 | Yes | 41
VD-9001-254-SOI-955 | 1 | ITP FOR F.D.FAN & DRIVERS | HM-254 | AZAR AB | 2018-03-04 20:00 | 2019-01-06 14:25 | 2019-01-06 14:25 | Yes | 308 |  |  | 2019-02-05 09:49 | [5 empty] | 2019-02-05 09:49 | Yes | 16
VD-9001-257C-DWG-003 | 1 | NAME PLATE DET.DWG (4137-0364/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 20:00 | 2018-05-14 14:02 | 2018-05-14 14:02 | Yes | 71 |  |  | 2018-05-30 09:30 | [5 empty] | 2018-05-30 09:30 | Yes | 2
VD-9001-257C-DWG-002 | 1 | DETAILS DRAWING (4137-0364/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 20:00 | 2018-05-14 14:01 | 2018-05-14 14:01 | Yes | 71 |  |  |  |  | 2018-08-13 16:39 |  |  |  | 2018-08-13 16:39 | Yes | 77 | 1204-Owner-v | 2019-07-02 09:04
VD-9001-301-DWG-033 | 1 | control panel syngas train (1; make; dim. drawing) | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-03-03 12:19 | 2018-03-04 14:22 | Yes | 0 | [9 empty] | No | 825 | 1204-Owner-v | 2018-03-12 08:52
VD-9001-301-DWG-037 | 1 | control panel circulator train (1; make; dim. drawing) | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-03-03 12:19 | 2018-03-04 14:22 | Yes | 0 | [9 empty] | No | 825 | 1204-Owner-v | 2018-05-15 16:59
VD-9001-301-LST-010 | 1 | utility consumption list circulator train | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-03-17 09:14 | 2018-03-17 09:14 | Yes | 13 |  |  |  | 2018-04-10 08:55 |  |  |  |  | 2018-04-10 20:00 | Yes | 10
VD-9001-301-LST-007 | 1 | utility consumption list syngas train | MC-301 | Siemens AG | 2018-03-04 20:00 | 2018-03-17 09:14 | 2018-03-17 09:14 | Yes | 13 |  |  |  | 2018-04-10 10:25 |  |  |  |  | 2018-04-10 20:00 | Yes | 10
VD-9001-257C-CAL-001 | 1 | MECHANICAL CALCULATION (4137-0364/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-04 20:00 | 2018-05-14 13:49 | 2018-05-14 13:49 | Yes | 71 |  |  | 2018-08-18 16:14 | [5 empty] | 2018-08-18 16:14 | Yes | 82 | 1204-Owner-v | 2018-08-19 08:53
VD-9001-104-DSH-050 | 1 | Warm automatic butterfly valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-04 20:00 |  |  | No | 838 | [9 empty] | No | 0
VD-9001-204B-ITP-001 | 2 | Inspection & Test Plan | PV-204B | ABAN AIR COOLER. | 2018-02-19 | 2018-02-24 12:34 | 2018-02-24 12:35 | Yes | 5 |  |  |  |  | 2018-03-10 11:56 |  |  |  | 2018-03-10 20:00 | Yes | 0
VD-9001-204B-DIS-001 | 4 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2018-02-19 | 2018-02-19 12:15 | 2018-02-19 12:16 | Yes | 0 |  | 2018-02-19 14:28 | [6 empty] | 2018-02-19 20:00 | Yes | -14 | 1204-Owner-v | 2018-11-17 11:58
VD-9001-461AF-INX-001 | 0 | FINAL DATA BOOK INDEX | PI-461AF | Van Leeuwen | 2018-04-01 | 2018-03-20 17:33 | 2018-03-20 17:37 | Yes | -12 |  |  |  | 2018-04-18 10:40 |  |  |  |  | 2018-04-18 10:40 | Yes | 15
VD-9001-461AF-PCJ-001 | 0 | PACKING AND MARKING AND PRESERVATION PROCEDURE | PI-461AF | Van Leeuwen | 2018-04-01 | 2018-03-20 17:42 | 2018-03-20 17:42 | Yes | -12 |  |  |  | 2018-04-30 11:26 |  |  |  |  | 2018-04-30 11:26 | Yes | 27
VD-9001-461AF-ITP-001 | 0 | INSPECTION TEST PLAN | PI-461AF | Van Leeuwen | 2018-04-01 | 2018-03-20 17:40 | 2018-03-20 17:41 | Yes | -12 |  |  |  | 2018-04-18 10:10 |  |  |  |  | 2018-04-18 10:10 | Yes | 15
VD-9001-461AF-CER-001 | 0 | MATERIAL CERTIFICATE | PI-461AF | Van Leeuwen | 2018-04-01 | 2018-02-23 17:13 |  | No | -37 | 2018-02-26 08:55 | [7 empty] | 2018-02-26 19:59 | Yes | 0
VD-9001-464A-DWG-001 | 1 | General Drawings (Sectional/ Assembly/ BOM) | PI-464A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2018-02-19 16:08 | 2018-02-21 10:28 | 2018-02-21 10:27 | Yes | 2 |  | 2018-02-21 11:22 | [6 empty] | 2018-02-21 19:59 | Yes | -14
VD-9001-204C-MAL-021 | 1 | SPARE PARTS LIST FOR TWO YEARS OPERATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-19 | 2018-06-18 15:10 | 2018-06-18 15:13 | Yes | 119 |  |  |  | 2018-07-10 17:37 |  |  |  |  | 2018-07-10 20:00 | Yes | 8
VD-9001-204C-MAL-020 | 1 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-02-19 | 2018-06-18 15:02 | 2018-06-18 15:02 | Yes | 119 |  |  |  | 2018-07-10 17:36 |  |  |  |  | 2018-07-10 20:00 | Yes | 8
VD-9001-301-DSH-006 | 1 | noise emission (data sheet) circulator train | MC-301 | Siemens AG | 2018-03-05 20:00 | 2018-03-10 09:02 | 2018-03-10 09:03 | Yes | 5 |  |  | 2018-03-10 14:50 | [5 empty] | 2018-03-10 20:00 | Yes | -14 | 1204-Owner-v | 2018-05-16 08:41
VD-9001-104-CAL-001 | 1 | PSV- Cold Safety valves - Calculations | PR-104 | AIR LIQUIDE | 2018-03-05 20:00 |  |  | No | 837 | [9 empty] | No | 0
VD-9001-104-REQ-010 | 1 | E-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-05 20:00 |  |  | No | 837 | [9 empty] | No | 0
VD-9001-104(004)-ITP-003 | 1 | ST C-6101/ST C-6102 - Inspection Test Plan / Quality Plan | PR-104-SUB | AIR LIQUIDE | 2018-03-05 20:00 | 2018-04-04 13:54 | 2018-04-04 14:12 | Yes | 30 |  |  |  | 2018-04-19 12:22 |  |  |  |  | 2018-04-19 20:00 | Yes | 1 | 1204-Owner-v | 2020-01-01 09:42
VD-9001-104(002)-CAL-002 | 1 | T-6101 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-03-05 20:00 | 2018-05-22 14:05 | 2018-05-22 14:08 | Yes | 78 |  |  |  | 2018-06-09 11:53 |  |  |  |  | 2018-06-09 19:59 | Yes | 4
VD-9001-104-REQ-030 | 1 | Moisture Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-05 20:00 | 2018-05-04 17:21 | 2018-05-04 17:23 | Yes | 60 |  |  | 2018-05-23 17:36 | [5 empty] | 2018-05-23 19:59 | Yes | 5
VD-9001-104-REQ-052 | 1 | Electrochemical Gas Analysers - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-05 20:00 | 2018-05-22 14:11 | 2018-05-22 14:15 | Yes | 78 |  |  | 2018-07-10 16:47 | [5 empty] | 2018-07-10 20:00 | Yes | 35
VD-9001-104-DSH-063 | 1 | Electrochemical Gas Analysers - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-05 20:00 | 2018-05-22 16:07 | 2018-05-22 16:12 | Yes | 78 |  |  |  | 2018-07-16 16:19 |  |  |  |  | 2018-07-16 20:00 | Yes | 41
VD-9001-104-DSH-008 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-06 19:59 | 2018-05-03 14:04 | 2018-05-03 14:09 | Yes | 58 |  |  | 2018-05-16 11:33 | [5 empty] | 2018-05-16 20:00 | Yes | -1
VD-9001-104-KPL-001 | 2 | Plot plan - Key plan | PR-104 | AIR LIQUIDE | 2018-03-06 19:59 |  |  | No | 836 | [9 empty] | No | 0
VD-9001-201-CAL-001 | 2 | PRESSURE PARTS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2018-02-21 | 2018-05-14 15:00 | 2018-05-14 15:00 | Yes | 82 |  |  |  | 2018-07-03 15:17 |  |  |  |  | 2018-07-03 15:17 | Yes | 36
VD-9001-104-LST-011 | 1 | Instrumentation list | PR-104 | AIR LIQUIDE | 2018-03-07 19:59 | 2018-05-31 14:25 | 2018-05-31 14:30 | Yes | 85 |  |  |  | 2018-07-17 11:40 |  |  |  |  | 2018-07-17 19:59 | Yes | 33
VD-9001-104-DSH-019 | 1 | EDS Equipment data sheet - PBUC | PR-104 | AIR LIQUIDE | 2018-03-07 19:59 | 2018-06-08 17:05 | 2018-06-08 17:12 | Yes | 93 |  |  |  | 2018-06-21 10:56 |  |  |  |  | 2018-06-21 20:00 | Yes | -1
VD-9001-104-DSH-020 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-07 19:59 | 2018-06-08 17:06 | 2018-06-08 17:13 | Yes | 93 |  |  |  | 2018-07-18 16:16 |  |  |  |  | 2018-07-18 19:59 | Yes | 26
VD-9001-104-DSH-012 | 3 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-07 20:00 | 2018-03-19 19:20 | 2018-03-19 19:44 | Yes | 12 |  |  |  | 2018-04-05 16:23 |  |  |  |  | 2018-04-05 20:00 | Yes | 3
VD-9001-104(002)-DWG-001 | 1 | E-6102 - Vaporizer shell - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-05-31 16:23 | 2018-08-02 11:43 | Yes | 85 |  |  |  | 2018-08-12 14:52 |  |  |  |  | 2018-08-12 20:00 | Yes | 59
VD-9001-104(007)-DWG-005 | 1 | DR-6101A / DR-6101B - Details drawings | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-11 17:21 | 2018-04-11 17:36 | Yes | 35 |  |  | 2018-05-07 15:32 | [5 empty] | 2018-05-07 20:00 | Yes | 12
VD-9001-104-LST-014 | 1 | GENERAL INPUT AND OUTPOUT LIST for instrumentation & electrical equipment | PR-104 | AIR LIQUIDE | 2018-03-07 20:00 | 2018-05-31 14:25 | 2018-05-31 14:30 | Yes | 85 |  |  |  | 2018-07-16 17:26 |  |  |  |  | 2018-07-16 20:00 | Yes | 32
VD-9001-104(007)-DWG-002 | 1 | DR-6101A / DR-6101B - Civil work drawing / loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-13 16:04 | 2018-04-13 16:10 | Yes | 37 |  |  | 2018-04-15 15:53 | [5 empty] | 2018-04-15 20:01 | Yes | -12 | 1204-Owner-v | 2018-06-17 16:31
VD-9001-104(007)-LST-001 | 1 | DR-6101A / DR-6101B - Envelop parts list | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-13 15:19 | 2018-04-13 15:24 | Yes | 37 |  |  |  | 2018-05-03 16:34 |  |  |  |  | 2018-05-03 19:59 | Yes | 6
VD-9001-104(007)-SKT-001 | 1 | DR-6101A / DR-6101B - Filter - Equipment sketch | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-11 17:20 | 2018-04-11 17:36 | Yes | 35 |  |  |  | 2018-05-13 10:07 |  |  |  |  | 2018-05-13 19:59 | Yes | 18
VD-9001-104(007)-DWG-001 | 1 | DR-6101A / DR-6101B - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-11 17:21 | 2018-04-11 17:36 | Yes | 35 |  |  |  | 2018-05-07 12:14 |  |  |  |  | 2018-05-07 12:14 | Yes | 12
VD-9001-104(002)-WBK-001 | 1 | D-6103 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-04-06 18:16 | 2018-04-06 18:16 | Yes | 30 |  |  |  | 2018-04-26 11:07 |  |  |  |  | 2018-04-26 20:00 | Yes | 6
VD-9001-104(002)-WBK-002 | 1 | T-6101 & E-6102 - Vaporizer shell - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-03-07 20:00 | 2018-03-26 16:53 | 2018-03-26 17:08 | Yes | 19 |  |  |  | 2018-04-24 16:38 |  |  |  |  | 2018-04-24 20:00 | Yes | 15
VD-9001-104-REQ-021 | 1 | C-6101 / C-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-07 20:00 |  |  | No | 835 | [9 empty] | No | 0
VD-9001-104(003)-SKT-001 | 1 | T-6101/E-6102/T-6102 - Equipment sketch | PR-104-SUB | AIR LIQUIDE | 2018-03-08 19:59 | 2018-04-24 16:46 | 2018-04-24 16:53 | Yes | 47 |  |  | 2018-05-27 11:14 | [5 empty] | 2018-05-27 19:59 | Yes | 19 | 1204-Owner-v | 2020-04-15 12:18
VD-9001-104(002)-DWG-005 | 1 | T-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-08 19:59 | 2018-04-26 18:22 | 2018-04-26 18:28 | Yes | 49 |  |  |  | 2018-07-14 14:33 |  |  |  |  | 2018-07-14 20:00 | Yes | 65 | 1204-Owner-v | 2018-05-05 07:58
VD-9001-104-DSH-022 | 1 | Gas Analysers - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-08 20:00 |  |  | No | 834 | [9 empty] | No | 0
VD-9001-104-DSH-061 | 1 | Moisture Analysers_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-08 20:00 | 2018-05-04 17:35 | 2018-05-04 17:35 | Yes | 57 |  |  |  | 2018-05-31 09:31 |  |  |  |  | 2018-05-31 19:59 | Yes | 13 | 1204-Owner-v | 2018-05-15 17:07
VD-9001-104-DSH-018 | 1 | EDS Equipment Data Sheet for ACC | PR-104 | AIR LIQUIDE | 2018-03-08 20:00 | 2018-05-04 16:58 | 2018-05-04 17:16 | Yes | 57 |  |  |  | 2018-06-20 18:14 |  |  |  |  | 2018-06-20 20:00 | Yes | 33
VD-9001-104-DSH-049 | 1 | Warm automatic globe valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-03-08 20:00 |  |  | No | 834 | [9 empty] | No | 0
VD-9001-257C-GAD-007 | 1 | GENERAL ARRANGEMENT (4137-0370) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-08 20:00 | 2018-05-14 13:47 | 2018-05-14 13:47 | Yes | 67 |  |  |  |  | 2018-11-05 10:37 |  |  |  | 2018-11-05 10:37 | Yes | 161 | 1204-Owner-v | 2018-08-04 14:06
VD-9001-257C-DWG-037 | 1 | NAME PLATE DET.DWG (4137-0370/A1) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-08 20:00 | 2018-05-14 14:21 | 2018-05-14 14:21 | Yes | 67 |  |  |  |  | 2018-07-21 19:52 |  |  |  | 2018-07-21 19:52 | Yes | 54
VD-9001-257C-DWG-043 | 1 | NAME PLATE DET.DWG (4137-0370/A2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-08 20:00 | 2018-05-14 14:21 | 2018-05-14 14:21 | Yes | 67 |  |  |  | 2018-07-21 19:51 |  |  |  |  | 2018-07-21 19:51 | Yes | 54
VD-9001-257C-DWG-058 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0370/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-08 20:00 | 2018-05-14 14:06 | 2018-05-14 14:07 | Yes | 67 |  |  |  |  | 2018-05-31 14:49 |  |  |  | 2018-05-31 14:49 | Yes | 3
VD-9001-104-REQ-008 | 2 | E-6101/E-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-02-24 09:31 | 2018-03-14 16:36 | 2018-03-14 17:25 | Yes | 18 |  |  | 2018-03-18 16:02 | [5 empty] | 2018-03-18 21:00 | Yes | -10
VD-9001-104-REQ-009 | 1 | E-6101/E-6103_TRS Technical Requisition Sheet for transition joints | PR-104 | AIR LIQUIDE | 2018-02-24 09:31 | 2018-03-14 16:36 | 2018-03-14 17:25 | Yes | 18 |  |  | 2018-03-18 16:55 | [5 empty] | 2018-03-18 21:00 | Yes | -10
VD-9001-257C-DWG-039 | 1 | DETAILS DRAWING (4137-0370/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-11 19:59 | 2018-05-14 14:17 | 2018-05-14 14:17 | Yes | 64 |  |  | 2018-11-06 11:32 | [5 empty] | 2018-11-06 11:32 | Yes | 162
VD-9001-257C-CAL-007 | 1 | MECHANICAL CALCULATION (4137-0370/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-11 19:59 | 2018-05-14 13:56 | 2018-05-14 13:56 | Yes | 64 |  |  | 2018-08-22 12:45 | [5 empty] | 2018-08-22 12:45 | Yes | 86 | 1204-Owner-v | 2018-08-19 08:55
VD-9001-257C-DWG-038 | 1 | DETAILS DRAWING (4137-0370/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-11 19:59 | 2018-05-14 14:16 | 2018-05-14 14:17 | Yes | 64 |  |  |  |  | 2018-07-21 19:39 |  |  |  | 2018-07-21 19:39 | Yes | 54
VD-9001-201B-GAD-001 | 1 | GENERAL ARRANGEMENT (4134/0359) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-11 19:59 | 2018-04-19 17:31 | 2018-04-19 17:31 | Yes | 39 |  |  |  | 2018-06-12 11:36 |  |  |  |  | 2018-06-12 11:36 | Yes | 40 | 1204-Owner-v | 2018-05-15 16:37
VD-9001-301-DSH-005 | 1 | noise emission (data sheet) syngas train | MC-301 | Siemens AG | 2018-03-11 19:59 | 2018-03-10 09:02 | 2018-03-10 09:02 | Yes | -1 |  |  | 2018-03-10 14:53 | [5 empty] | 2018-03-10 20:00 | Yes | -14 | 1204-Owner-v | 2018-05-15 17:03
VD-9001-201B-PCJ-005 | 1 | POST WELD HEAT TREATMENT PROCEDURE (4134/PWHT) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-11 20:00 | 2018-05-09 16:26 | 2018-05-09 16:27 | Yes | 59 |  |  | 2018-06-24 18:20 | [5 empty] | 2018-06-24 20:00 | Yes | 32
VD-9001-201B-PCJ-001 | 1 | HYDROSTATIC PROCEDURE (4134/HT) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-11 20:00 | 2018-03-15 18:42 | 2018-03-15 18:42 | Yes | 4 |  |  | 2018-04-16 10:07 | [5 empty] | 2018-04-16 20:00 | Yes | 18 | 1204-Owner-v | 2018-04-30 11:22
VD-9001-201B-ITP-001 | 1 | INSPECTION & TESTING PLAN (4134-0359/ITP) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-11 20:00 | 2018-03-05 13:41 | 2018-03-05 13:48 | Yes | -6 |  |  | 2018-03-11 10:59 | [5 empty] | 2018-03-11 20:00 | Yes | -8 | 1204-Owner-v | 2018-05-12 16:58
VD-9001-201B-WBK-001 | 1 | WELDING BOOK (4134-0359/W) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-11 20:00 | 2018-03-12 18:41 | 2018-03-12 18:53 | Yes | 1 |  |  | 2018-03-26 09:18 | [5 empty] | 2018-03-26 21:00 | Yes | 0
VD-9001-204B-PQR-002 | 3 | Procedure Qualification Record (PQR) For C.S | PV-204B | ABAN AIR COOLER. | 2018-02-26 | 2018-05-20 13:56 | 2018-05-20 14:02 | Yes | 83 |  |  |  |  | 2018-07-30 16:07 |  |  |  | 2018-07-30 16:07 | Yes | 57
VD-9001-204B-PQR-001 | 3 | Procedure Qualification Record (PQR) For S.S | PV-204B | ABAN AIR COOLER. | 2018-02-26 | 2018-05-20 14:05 | 2018-05-20 14:06 | Yes | 83 |  |  |  |  | 2018-07-30 16:00 |  |  |  | 2018-07-30 16:00 | Yes | 57
VD-9001-204B-WPS-002 | 3 | Welding Procedure Specification (WPS) For C.S | PV-204B | ABAN AIR COOLER. | 2018-02-26 | 2018-05-21 09:56 | 2018-05-21 09:57 | Yes | 84 |  |  | 2018-07-30 11:14 |  |  |  | 2018-05-21 09:13 | 2018-05-21 09:13 | 2018-07-30 11:14 | Yes | 56
VD-9001-204B-WPS-001 | 3 | Welding Procedure Specification (WPS) For S.S | PV-204B | ABAN AIR COOLER. | 2018-02-26 | 2018-05-20 12:44 | 2018-05-20 12:45 | Yes | 83 |  |  |  | 2018-06-19 09:09 |  |  |  |  | 2018-06-19 09:09 | Yes | 16
VD-9001-104-DSH-007 | 3 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-02-26 12:11 | 2018-06-08 14:49 | 2018-06-08 14:51 | Yes | 102 |  |  | 2018-06-18 15:59 | [5 empty] | 2018-06-18 20:01 | Yes | -4
VD-9001-251-PPL-009 | 1 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-26 | 2018-05-30 18:38 | 2018-05-30 18:43 | Yes | 93 |  |  | 2018-06-04 12:10 | [5 empty] | 2018-06-04 12:10 | Yes | -9 | 1204-Owner-v | 2018-07-11 10:50
VD-9001-104(005)-WBK-003 | 0 | Piping - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-104(005)-DWG-009 | 0 | E-6103 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-22 | 2018-04-27 18:01 | 2018-04-27 18:24 | Yes | -25 |  |  |  | 2018-05-09 15:31 |  |  |  |  | 2018-05-09 19:59 | Yes | -2
VD-9001-104(007)-IPM-003 | 0 | DR-6101A / DR-6101B - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-03-01 |  |  | No | 841 | [9 empty] | No | 0
VD-9001-104(011)-DWG-004 | 0 | Detail drawings for JT globe valves | PR-104-SUB | AIR LIQUIDE | 2018-05-04 |  |  | No | 777 | [9 empty] | No | 0
VD-9001-104(011)-DWG-005 | 0 | Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(011)-DWG-006 | 0 | Pneumatic and electrical diagram for JT globe valves | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(011)-CAL-001 | 0 | Calculation sheet for JT globe valves ( included noise calculation) | PR-104-SUB | AIR LIQUIDE | 2018-06-01 | 2018-05-03 12:49 | 2018-05-03 12:53 | Yes | -29 |  |  |  | 2018-05-27 15:20 |  |  |  |  | 2018-05-27 19:59 | Yes | 10
VD-9001-104(011)-ITP-002 | 0 | Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-05-03 12:49 | 2018-05-03 12:54 | Yes | 2 |  |  |  | 2018-05-16 17:05 |  |  |  |  | 2018-05-16 20:00 | Yes | -1 | 1204-Owner-v | 2018-05-12 16:48
VD-9001-104(011)-MDB-003 | 0 | Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(011)-MDB-004 | 0 | Final Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-104(011)-MTO-002 | 0 | Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-01 |  |  | No | 657 | [9 empty] | No | 0
VD-9001-104(011)-LST-004 | 0 | Spare parts list for JT globe valves | PR-104-SUB | AIR LIQUIDE | 2018-07-01 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-104(011)-MNL-001 | 0 | Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-01 | 2018-06-08 11:48 | 2018-06-08 12:18 | Yes | -85 |  |  | 2018-07-17 15:18 | [5 empty] | 2018-07-17 20:00 | Yes | 25 | 1204-Owner-v | 2019-02-02 17:00
VD-9001-104(012)-CAL-001 | 0 | Calculation sheet for globe valves ( included noise calculation) | PR-104-SUB | AIR LIQUIDE | 2018-06-01 |  |  | No | 749 | [9 empty] | No | 0
VD-9001-104(011)-IPM-001 | 0 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-05-22 16:38 | 2018-05-22 16:43 | Yes | 21 |  |  |  | 2018-06-18 14:52 |  |  |  |  | 2018-06-18 20:00 | Yes | 13
VD-9001-104(012)-IPM-001 | 0 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-01 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-104(011)-IPM-002 | 0 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-05-03 12:49 | 2018-05-03 12:54 | Yes | 2 |  |  | 2018-05-16 17:01 | [5 empty] | 2018-05-16 20:00 | Yes | -1
VD-9001-104(010)-IPM-001 | 0 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-04-05 17:07 | 2018-04-05 17:09 | Yes | -26 |  |  |  | 2018-04-21 15:59 |  |  |  |  | 2018-04-21 20:00 | Yes | 2
VD-9001-104(010)-WBK-001 | 0 | Welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-01 | 2018-04-05 17:08 | 2018-04-05 17:09 | Yes | -57 |  |  |  | 2018-04-24 16:15 |  |  |  |  | 2018-04-24 20:00 | Yes | 5
VD-9001-104(001)-PPL-002 | 0 | Plot plan - North Isometric view | PR-104-SUB | AIR LIQUIDE | 2018-07-05 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(001)-PPL-003 | 0 | Plot plan - South Isometric view | PR-104-SUB | AIR LIQUIDE | 2018-07-05 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(001)-PPL-004 | 0 | Plot plan - Elevation view | PR-104-SUB | AIR LIQUIDE | 2018-07-05 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(001)-DWG-001 | 0 | Simple Equipment Slabs book - Inputs for civil work guide drawings | PR-104-SUB | AIR LIQUIDE | 2018-03-09 | 2018-03-08 14:50 | 2018-03-08 16:34 | Yes | -1 |  |  |  | 2018-03-12 16:47 |  |  |  |  | 2018-03-12 20:00 | Yes | -10 | 1204-Owner-v | 2018-04-28 11:25
VD-9001-104(001)-DWG-002 | 0 | AREA D1 - O2 Blockhaus, Common Silencer | PR-104-SUB | AIR LIQUIDE | 2018-03-22 | 2018-05-04 15:16 | 2018-05-04 15:18 | Yes | 43 |  |  |  | 2018-05-15 10:53 |  |  |  |  | 2018-05-15 19:59 | Yes | -3
VD-9001-104(001)-DWG-003 | 0 | Area A / B - Machine Hall | PR-104-SUB | AIR LIQUIDE | 2018-04-27 | 2018-04-30 17:10 | 2018-04-30 17:13 | Yes | 3 |  |  |  | 2018-05-23 09:57 |  |  |  |  | 2018-05-23 19:59 | Yes | 9
VD-9001-104(001)-ISO-006 | 0 | Area A - Warm part - Isometric Booklet - SS | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-ISO-007 | 0 | Area B - Warm part - Isometric Booklet - SS | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-ISO-008 | 0 | Area C - Warm part - Isometric Booklet - SS | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-ISO-009 | 0 | Area D - Warm part - Isometric Booklet - SS | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-ISO-010 | 0 | Area E - Warm part - Isometric Booklet - SS | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-DWG-008 | 0 | AREA A - Warm part - Standard Support Booklet + BOM | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-DWG-009 | 0 | AREA B - Warm part - Standard Support Booklet + BOQ | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-DWG-010 | 0 | AREA C - Warm part - Standard Support Booklet + BOQ | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-DWG-011 | 0 | AREA D - Warm part - Standard Support Booklet + BOQ | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(001)-DWG-012 | 0 | AREA E - Warm part - Standard Support Booklet + BOQ | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(004)-PID-005 | 0 | C-6101 -PID Cooling water | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-21 19:24 | 2018-03-21 19:31 | Yes | 32 |  |  |  | 2018-04-16 18:35 |  |  |  |  | 2018-04-16 20:00 | Yes | 12
VD-9001-104(004)-PID-006 | 0 | C-6102 -PID process | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-15 18:34 | 2018-03-15 19:16 | Yes | 26 |  |  |  | 2018-04-16 17:24 |  |  |  |  | 2018-04-16 20:00 | Yes | 18
VD-9001-104(004)-PID-007 | 0 | C-6102 -PID oil system | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-15 18:34 | 2018-03-15 19:17 | Yes | 26 |  |  |  | 2018-04-16 10:10 |  |  |  |  | 2018-04-16 20:00 | Yes | 18
VD-9001-104(004)-PID-008 | 0 | C-6102 PID Vibration & temperature moniotoring system | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-15 18:35 | 2018-03-15 19:17 | Yes | 26 |  |  |  | 2018-04-15 11:40 |  |  |  |  | 2018-04-15 20:00 | Yes | 17
VD-9001-104(004)-PID-009 | 0 | C-6102 -PID Cooling water | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-03-15 18:35 | 2018-03-15 19:17 | Yes | 26 |  |  |  | 2018-04-16 16:08 |  |  |  |  | 2018-04-16 20:00 | Yes | 18
VD-9001-104(004)-PID-010 | 0 | ST C-6101 -PID turbine | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-27 11:09 | 2018-02-27 11:09 | Yes | 10 |  |  |  | 2018-03-19 17:05 |  |  |  |  | 2018-03-19 21:00 | Yes | 6
VD-9001-104(004)-PID-011 | 0 | ST-C-6102 -PID turbine | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-27 11:09 | 2018-02-27 11:09 | Yes | 10 |  |  |  | 2018-03-19 16:53 |  |  |  |  | 2018-03-19 21:00 | Yes | 6
VD-9001-104(004)-PID-012 | 0 | ST-C-6102 -PID condensing system | PR-104-SUB | AIR LIQUIDE | 2018-02-17 | 2018-02-27 11:09 | 2018-02-27 11:09 | Yes | 10 |  |  |  | 2018-03-27 18:02 |  |  |  |  | 2018-03-27 21:00 | Yes | 14
VD-9001-104(008)-PID-001 | 0 | AE-6187 - PID symbols summary page | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-02-27 12:31 | 2018-02-27 12:31 | Yes | -1 |  |  |  | 2018-03-19 10:49 |  |  |  |  | 2018-03-19 21:00 | Yes | 6
VD-9001-104(008)-PID-002 | 0 | AE-6187 - PID process ACC | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-02-27 12:31 | 2018-02-27 12:31 | Yes | -1 |  |  |  | 2018-03-19 13:05 |  |  |  |  | 2018-03-19 21:00 | Yes | 6
VD-9001-104(008)-PID-003 | 0 | AE-6187 - PID Condensate System | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-02-27 12:32 | 2018-02-27 12:32 | Yes | -1 |  |  |  | 2018-04-05 12:10 |  |  |  |  | 2018-04-05 20:00 | Yes | 23
VD-9001-104(008)-PID-004 | 0 | AE-6187 - PID Steam duct | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-02-27 12:32 | 2018-02-27 12:32 | Yes | -1 |  |  |  | 2018-04-05 11:59 |  |  |  |  | 2018-04-05 20:00 | Yes | 23
VD-9001-104(008)-PID-005 | 0 | AE-6187 - PID Steam Jet Air Ejector | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-02-27 12:32 | 2018-02-27 12:32 | Yes | -1 |  |  |  | 2018-03-19 16:07 |  |  |  |  | 2018-03-19 21:00 | Yes | 6
VD-9001-104(008)-DWG-001 | 0 | AE-6187 – General Arrangement Drawing – Front View | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-08 15:07 | 2018-03-08 16:38 | Yes | 8 |  |  |  | 2018-03-14 16:12 |  |  |  |  | 2018-03-14 20:00 | Yes | -8
VD-9001-104(008)-DWG-002 | 0 | AE-6187 - General Arrangement Drawing – Side View | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-08 15:07 | 2018-03-08 16:38 | Yes | 8 |  |  |  | 2018-03-14 16:41 |  |  |  |  | 2018-03-14 20:00 | Yes | -8
VD-9001-104(008)-DWG-003 | 0 | AE-6187 - General Arrangement Drawing – Top View | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-08 15:07 | 2018-03-08 16:39 | Yes | 8 |  |  |  | 2018-03-14 16:54 |  |  |  |  | 2018-03-14 20:00 | Yes | -8
VD-9001-104(008)-DWG-004 | 0 | AE-6187 - General Arrangement Drawing – Main Structure Walkway Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-08 15:07 | 2018-03-08 16:39 | Yes | 8 |  |  |  | 2018-03-19 10:20 |  |  |  |  | 2018-03-19 21:00 | Yes | -3
VD-9001-104(008)-DWG-005 | 0 | AE-6187 - Civil work drawing– Anchorage Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-08 15:07 | 2018-03-08 16:39 | Yes | 8 |  |  |  | 2018-03-12 16:36 |  |  |  |  | 2018-03-12 20:00 | Yes | -10
VD-9001-104(008)-DWG-006 | 0 | AE-6187 – Civil work drawing - Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-15 14:31 | 2018-03-15 15:58 | Yes | 15 |  |  |  | 2018-03-26 10:45 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-104(008)-DWG-007 | 0 | AE-6187 – Civil work drawing - Anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-02-28 | 2018-03-15 14:31 | 2018-03-15 15:58 | Yes | 15 |  |  |  | 2018-03-26 10:37 |  |  |  |  | 2018-03-26 21:00 | Yes | -3
VD-9001-204D-ITP-022 | 2 | INSPECTION & TESTING PLAN | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-03-12 19:59 | 2018-03-14 12:30 | 2018-03-14 12:32 | Yes | 2 |  |  | 2018-04-04 10:23 | [5 empty] | 2018-04-04 20:00 | Yes | 7 | 1204-Owner-v | 2018-04-04 15:03
VD-9001-461AF-CER-001 | 1 | MATERIAL CERTIFICATE | PI-461AF | Van Leeuwen | 2018-03-12 19:59 | 2018-06-21 17:06 | 2018-06-21 17:09 | Yes | 101 |  |  | 2018-06-23 08:46 | [5 empty] | 2018-06-23 08:47 | Yes | -12
VD-9001-204D-INR-028 | 2 | CERTIFICATION DOSSIER INDEX | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-03-12 19:59 | 2018-02-27 14:13 | 2018-02-27 14:13 | Yes | -13 |  |  |  | 2018-04-18 17:47 |  |  |  |  | 2018-04-18 20:00 | Yes | 36
VD-9001-201B-DWG-003 | 1 | NAME PLATE DET.DWG (4134-0359/A) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-12 19:59 | 2018-04-19 17:34 | 2018-04-19 17:34 | Yes | 38 |  |  |  | 2018-05-09 16:17 |  |  |  |  | 2018-05-09 19:59 | Yes | 6
VD-9001-251-DWG-074 | 1 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 19:59 | 2018-03-30 12:39 | 2018-03-30 12:42 | Yes | 18 |  |  | 2018-04-09 14:46 | [5 empty] | 2018-04-09 14:46 | Yes | -4 | 1204-Owner-v | 2018-05-19 12:21
VD-9001-251-DWG-075 | 1 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 19:59 | 2018-03-30 12:43 | 2018-03-30 12:50 | Yes | 18 |  |  |  | 2018-04-09 14:54 |  |  |  |  | 2018-04-09 14:54 | Yes | -4
VD-9001-251-DWG-076 | 1 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 19:59 | 2018-03-30 12:52 | 2018-03-30 12:56 | Yes | 18 |  |  |  | 2018-04-09 14:56 |  |  |  |  | 2018-04-09 14:56 | Yes | -4
VD-9001-251-DWG-043 | 1 | GENERAL ARRANGEMENT STAIRS | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 19:59 | 2018-06-07 17:41 | 2018-06-07 17:46 | Yes | 87 |  |  | 2018-06-18 17:55 | [5 empty] | 2018-06-18 17:55 | Yes | -3 | 1204-Owner-v | 2019-03-02 11:27
VD-9001-251-PPL-010 | 1 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:43 | Yes | 79 |  |  | 2018-06-04 12:11 | [5 empty] | 2018-06-04 12:11 | Yes | -9 | 1204-Owner-v | 2018-07-11 10:49
VD-9001-251-PPL-008 | 1 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:42 | Yes | 79 |  |  | 2018-06-04 12:10 | [5 empty] | 2018-06-04 12:10 | Yes | -9 | 1204-Owner-v | 2018-10-09 15:27
VD-9001-251-PPL-007 | 1 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:42 | Yes | 79 |  |  | 2018-06-04 12:09 | [5 empty] | 2018-06-04 12:09 | Yes | -9 | 1204-Owner-v | 2018-10-09 15:27
VD-9001-251-PPL-006 | 1 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:42 | Yes | 79 |  |  | 2018-06-04 11:57 | [5 empty] | 2018-06-04 11:57 | Yes | -9 | 1204-Owner-v | 2018-07-11 10:40
VD-9001-251-PPL-005 | 1 | REFORMER GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:41 | Yes | 79 |  |  | 2018-06-10 16:55 | [5 empty] | 2018-06-10 16:55 | Yes | -3 | 1204-Owner-v | 2018-07-11 10:40
VD-9001-251-PPL-004 | 1 | REFORMER GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-03-12 20:00 | 2018-05-30 18:38 | 2018-05-30 18:41 | Yes | 79 |  |  | 2018-06-10 16:53 | [5 empty] | 2018-06-10 16:53 | Yes | -3 | 1204-Owner-v | 2018-07-11 10:39
VD-9001-251-PID-009 | 1 | PID - LOCAL PANELS | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-13 17:08 | 2018-06-13 17:22 | Yes | 106 |  |  |  |  | 2018-07-23 15:58 |  |  |  | 2018-07-23 15:58 | Yes | 26
VD-9001-251-PID-001 | 1 | PID - PRIMARY REFORMER RADIANT SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-12 17:08 | 2018-06-12 17:30 | Yes | 105 |  |  |  |  | 2018-07-07 14:09 |  |  |  | 2018-07-07 14:09 | Yes | 11 | 1204-Owner-v | 2018-06-19 12:41
VD-9001-251-PID-002 | 1 | PID - PRIMARY REFORMER CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-12 17:08 | 2018-06-12 17:30 | Yes | 105 |  |  |  | 2018-07-07 14:13 |  |  |  |  | 2018-07-07 14:13 | Yes | 11 | 1204-Owner-v | 2019-06-10 12:39
VD-9001-251-PID-003 | 1 | PID - COMBUSTION AIR FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-12 17:17 | 2018-06-12 17:30 | Yes | 105 |  |  |  |  | 2018-07-07 14:15 |  |  |  | 2018-07-07 14:15 | Yes | 11
VD-9001-251-PID-004 | 1 | PID - FLUE GAS FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-12 17:21 | 2018-06-12 17:30 | Yes | 105 |  |  |  |  | 2018-07-07 14:17 |  |  |  | 2018-07-07 14:17 | Yes | 11
VD-9001-251-PID-005 | 1 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-12 17:24 | 2018-06-12 17:30 | Yes | 105 |  |  |  |  | 2018-07-07 14:18 |  |  |  | 2018-07-07 14:18 | Yes | 11
VD-9001-251-PID-006 | 1 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-13 17:00 | 2018-06-13 17:22 | Yes | 106 |  |  |  | 2018-07-07 14:21 |  |  |  |  | 2018-07-07 14:21 | Yes | 10
VD-9001-251-PID-008 | 1 | PID - SSH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-13 17:12 | 2018-06-13 17:22 | Yes | 106 |  |  |  |  | 2018-07-07 14:24 |  |  |  | 2018-07-07 14:24 | Yes | 10
VD-9001-251-PID-007 | 1 | PID - TUNNEL BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-13 17:00 | 2018-06-13 17:22 | Yes | 106 |  |  |  | 2018-07-07 14:23 |  |  |  |  | 2018-07-07 14:23 | Yes | 10
VD-9001-251-PID-010 | 1 | PID- UTILITIES DISTRIBUTION | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-06-13 17:21 | 2018-06-13 17:22 | Yes | 106 |  |  |  | 2018-07-07 14:25 |  |  |  |  | 2018-07-07 14:25 | Yes | 10
VD-9001-251-LST-004 | 1 | EQUIPMENT LIST | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-08-29 15:07 | 2018-08-29 15:26 | Yes | 183 |  |  |  |  | 2018-09-04 16:51 |  |  |  | 2018-09-04 16:51 | Yes | -8 | 1204-Owner-v | 2019-03-02 11:35
VD-9001-251-LST-003 | 1 | LINE LIST | HM-251 | KT – Kinetics Technology SpA | 2018-02-27 | 2018-08-23 13:27 | 2018-08-23 13:36 | Yes | 177 |  |  |  |  | 2018-09-09 17:32 |  |  |  | 2018-09-09 17:32 | Yes | 3 | 1204-Owner-v | 2019-04-06 10:27
VD-9001-301-QCP-002 | 1 | Quality Control Plan (Syngas SST Auxiliaries) | MC-301 | Siemens AG | 2018-03-13 19:59 | 2018-03-03 12:23 | 2018-03-04 14:21 | Yes | -10 |  |  |  | 2018-05-26 09:37 |  |  |  |  | 2018-05-26 19:59 | Yes | 70 | 1204-Owner-v | 2020-01-01 10:44
VD-9001-301-QCP-001 | 1 | quality control plan Circulator Compressor | MC-301 | Siemens AG | 2018-03-13 19:59 | 2018-03-12 15:20 | 2018-03-12 15:20 | Yes | -1 |  |  | 2018-05-26 09:33 | [5 empty] | 2018-05-26 19:59 | Yes | 61 | 1204-Owner-v | 2020-01-01 10:43
VD-9001-301-QCP-003 | 1 | Quality Control Plan (Circulator SST Auxiliaries) | MC-301 | Siemens AG | 2018-03-13 19:59 | 2018-03-03 12:24 | 2018-03-04 14:21 | Yes | -9 |  |  | 2018-05-26 09:42 | [5 empty] | 2018-05-26 19:59 | Yes | 70 | 1204-Owner-v | 2020-01-01 10:44
VD-9001-301-DSH-010 | 1 | circulator compressor (data sheet API 617) | MC-301 | Siemens AG | 2018-03-13 19:59 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-301-DSH-009 | 1 | syngas compressor (data sheet API 617) | MC-301 | Siemens AG | 2018-03-13 19:59 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-301-DSH-022 | 1 | syngas turbine (data sheet) | MC-301 | Siemens AG | 2018-03-13 19:59 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-301-DSH-023 | 1 | circulator turbine (data sheet) | MC-301 | Siemens AG | 2018-03-13 19:59 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-307A-DSH-004 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-03-13 19:59 | 2018-09-07 16:51 | 2018-09-07 16:51 | Yes | 178 |  |  |  | 2018-10-15 15:32 |  |  |  |  | 2018-10-15 18:58 | Yes | 24 | 1204-Owner-v | 2018-10-16 12:32
VD-9001-307A-DSH-003 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-03-13 19:59 | 2018-09-07 16:51 | 2018-09-07 16:51 | Yes | 178 |  |  |  | 2018-10-15 15:39 |  |  |  |  | 2018-10-15 18:58 | Yes | 24 | 1204-Owner-v | 2018-10-16 12:32
VD-9001-307A-DSH-002 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-03-13 19:59 | 2018-09-07 16:51 | 2018-09-07 16:51 | Yes | 178 |  |  |  | 2018-10-15 15:23 |  |  |  |  | 2018-10-15 18:58 | Yes | 24 | 1204-Owner-v | 2018-10-16 12:31
VD-9001-307A-DSH-001 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-03-13 19:59 | 2018-09-07 16:50 | 2018-09-07 16:51 | Yes | 178 |  |  |  | 2018-10-15 15:43 |  |  |  |  | 2018-10-15 18:59 | Yes | 24 | 1204-Owner-v | 2018-10-16 12:31
VD-9001-301-PCJ-001 | 1 | Preservation and Storage Procedure for SYNGAS Train | MC-301 | Siemens AG | 2018-03-13 19:59 | 2018-03-03 12:22 | 2018-03-04 14:22 | Yes | -9 |  |  | 2018-03-10 08:36 | [5 empty] | 2018-03-10 20:00 | Yes | -7 | 1204-Owner-v | 2018-04-04 14:22
VD-9001-301-PDS-008 | 1 | stability requirements circulator turbine | MC-301 | Siemens AG | 2018-03-13 19:59 | 2018-03-03 12:13 | 2018-03-04 14:24 | Yes | -9 |  |  | 2018-03-04 16:28 | [5 empty] | 2018-03-04 20:00 | Yes | -13
VD-9001-104-PCJ-006 | 1 | INSULATION DESIGN FOR PIPING AND VESSELS | PR-104 | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-104(004)-DWG-005 | 1 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-104(002)-CAL-001 | 1 | D-6103 - Calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 | 2018-06-06 19:24 | 2018-06-06 19:27 | Yes | 85 |  |  |  | 2018-06-23 14:44 |  |  |  |  | 2018-06-23 20:00 | Yes | 3
VD-9001-104(004)-ITP-001 | 1 | C-6101 / C-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 | 2018-04-04 14:10 | 2018-04-04 14:12 | Yes | 22 |  |  |  | 2018-04-18 16:18 |  |  |  |  | 2018-04-18 20:00 | Yes | 0 | 1204-Owner-v | 2020-01-01 09:48
VD-9001-104(004)-PID-003 | 1 | C-6101 - PID oil system | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-104(004)-PCU-001 | 1 | C-6101 / C-6102 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-104(004)-PID-004 | 1 | C-6101 - PID mechanical | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-104(004)-PID-002 | 1 | C-6101 - PID process | PR-104-SUB | AIR LIQUIDE | 2018-03-13 20:00 |  |  | No | 829 | [9 empty] | No | 0
VD-9001-201B-DWG-002 | 1 | DETAILS DRAWING (4134-0359/2) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-18 20:00 | 2018-04-19 17:33 | 2018-04-19 17:33 | Yes | 32 |  |  | 2018-04-29 09:52 | [5 empty] | 2018-04-29 19:59 | Yes | -4 | 1204-Owner-v | 2020-05-18 09:54
VD-9001-251-DWG-067 | 1 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-06-07 17:44 | 2018-06-07 17:46 | Yes | 79 |  |  | 2018-06-14 11:41 | [5 empty] | 2018-06-14 11:41 | Yes | -7 | 1204-Owner-v | 2019-03-02 11:28
VD-9001-251-DWG-068 | 1 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-06-07 17:46 | 2018-06-07 17:47 | Yes | 79 |  |  | 2018-06-14 11:41 | [5 empty] | 2018-06-14 11:41 | Yes | -7
VD-9001-251-DWG-069 | 1 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-06-07 17:48 | 2018-06-07 17:48 | Yes | 79 |  |  | 2018-06-14 11:42 | [5 empty] | 2018-06-14 11:42 | Yes | -7
VD-9001-251-DWG-070 | 1 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-06-07 17:49 | 2018-06-07 17:49 | Yes | 79 |  |  | 2018-06-14 11:43 | [5 empty] | 2018-06-14 11:43 | Yes | -7
VD-9001-251-DWG-029 | 1 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-04-20 14:45 | 2018-04-20 14:45 | Yes | 31 |  |  |  | 2018-04-26 13:23 |  |  |  |  | 2018-04-26 13:23 | Yes | -8
VD-9001-251-DWG-028 | 1 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-03-20 | 2018-04-20 14:30 | 2018-04-20 14:39 | Yes | 31 |  |  |  | 2018-04-26 13:22 |  |  |  |  | 2018-04-26 13:22 | Yes | -8 | 1204-Owner-v | 2018-04-25 10:11
VD-9001-201B-PCJ-020 | 0 | TOFD PROCEDURE (4134/TOFD) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-05 | 2018-03-06 17:30 | 2018-03-06 17:35 | Yes | 1 |  |  |  | 2018-03-26 09:54 |  |  |  |  | 2018-03-26 21:00 | Yes | 6
VD-9001-201B-PCJ-021 | 0 | PHASED ARRAY PROCEDURE (4134/PHA) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-05 | 2018-03-28 11:48 | 2018-03-28 11:55 | Yes | 23 |  |  |  | 2018-04-29 09:46 |  |  |  |  | 2018-04-29 19:59 | Yes | 18
VD-9001-301-QCP-006 | 0 | quality control plan syngas turbine | MC-301 | Siemens AG | 2018-01-26 | 2018-03-06 18:10 | 2018-03-06 18:10 | Yes | 39 |  |  |  | 2018-05-27 08:49 |  |  |  |  | 2018-05-27 19:59 | Yes | 68 | 1204-Owner-v | 2020-01-01 10:45
VD-9001-301-QCP-007 | 0 | quality control plan circulator turbine | MC-301 | Siemens AG | 2018-01-26 | 2018-03-06 18:10 | 2018-03-06 18:10 | Yes | 39 |  |  |  | 2018-05-27 09:39 |  |  |  |  | 2018-05-27 19:59 | Yes | 68 | 1204-Owner-v | 2020-01-01 10:46
VD-9001-104(008)-IPM-001 | 0 | AE-6187 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-23 | 2018-03-30 14:01 | 2018-03-30 14:03 | Yes | -54 |  |  |  | 2018-05-01 10:04 |  |  |  |  | 2018-05-01 19:59 | Yes | 18
VD-9001-104(008)-LST-001 | 0 | AE-6187 - Lubricants List | PR-104-SUB | AIR LIQUIDE | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-104(008)-IPM-002 | 0 | AE-6187 - Protection specification - Expansion Bellow | PR-104-SUB | AIR LIQUIDE | 2018-10-06 |  |  | No | 622 | [9 empty] | No | 0
VD-9001-104(008)-IPM-003 | 0 | AE-6187 - Protection specification - Manifold | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-004 | 0 | AE-6187 - Protection specification - Steam Duct | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-005 | 0 | AE-6187 - Protection specification - Piping | PR-104-SUB | AIR LIQUIDE | 2018-11-23 |  |  | No | 574 | [9 empty] | No | 0
VD-9001-104(008)-IPM-006 | 0 | AE-6187 - Protection specification - Steel structure | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-007 | 0 | AE-6187 - Protection specification - Tanks | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-008 | 0 | AE-6187 - Protection specification - Vacuum Unit | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-009 | 0 | AE-6187 - Protection specification - Manual Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-010 | 0 | AE-6187 - Protection specification - Control Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-011 | 0 | AE-6187 - Protection specification - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-23 |  |  | No | 758 | [9 empty] | No | 0
VD-9001-104(008)-PCU-001 | 0 | AE-6187 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-04-11 | 2018-03-30 14:02 | 2018-03-30 14:02 | Yes | -12 |  |  |  | 2018-04-16 18:24 |  |  |  |  | 2018-04-16 20:00 | Yes | 3
VD-9001-104(008)-DSH-001 | 0 | AE-6187-CM01 - EDS Equipment data sheet of Fan Motors | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-05-22 13:23 | 2018-05-22 13:25 | Yes | -15 |  |  |  | 2018-06-13 09:52 |  |  |  |  | 2018-06-13 20:00 | Yes | 8
VD-9001-104(008)-PPL-001 | 0 | AE-6187 - Instruments and electrical arrangement | PR-104-SUB | AIR LIQUIDE | 2018-05-23 |  |  | No | 758 | [9 empty] | No | 0
VD-9001-104(008)-DWG-008 | 0 | AE-6187 - Water washing & cleaning system assembly drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-04 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-DWG-009 | 0 | J-6188 - Inter Condenser & Ejector & Vacuum Unit- drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-05-22 13:23 | 2018-05-22 13:25 | Yes | -15 |  |  |  | 2018-06-18 11:55 |  |  |  |  | 2018-06-18 20:00 | Yes | 13
VD-9001-104(008)-DWG-010 | 0 | D-6188 - Condensate tank drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-04 18:29 | 2018-04-04 18:31 | Yes | -35 |  |  |  | 2018-04-21 16:27 |  |  |  |  | 2018-04-21 20:00 | Yes | 3
VD-9001-104(008)-DWG-011 | 0 | D-6187 - Steam Duct & Drain pot detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:05 | 2018-04-13 13:48 | Yes | -26 |  |  |  | 2018-05-03 13:26 |  |  |  |  | 2018-05-03 19:59 | Yes | 6
VD-9001-104(008)-DWG-012 | 0 | AE-6187 - Flash box drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(008)-DWG-013 | 0 | D-6188 - Condensate tank - detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-04 18:29 | 2018-04-04 18:31 | Yes | -35 |  |  |  | 2018-04-21 16:04 |  |  |  |  | 2018-04-21 20:00 | Yes | 3
VD-9001-104(008)-LST-002 | 0 | AE-6187 - Equipment list | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:06 | 2018-04-13 13:56 | Yes | -26 |  |  |  | 2018-04-17 18:14 |  |  |  |  | 2018-04-17 20:00 | Yes | -10 | 1204-Owner-v | 2020-04-23 16:29
VD-9001-104(008)-DWG-014 | 0 | AE-6187 - Emmergency stop & Local control panel | PR-104-SUB | AIR LIQUIDE | 2018-05-23 |  |  | No | 758 | [9 empty] | No | 0
VD-9001-104(008)-DWG-015 | 0 | AE-6187 - Junction boxes drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-05-31 13:29 | 2018-05-31 13:37 | Yes | -34 |  |  |  | 2018-07-03 16:46 |  |  |  |  | 2018-07-03 20:00 | Yes | 19
VD-9001-104(008)-DWG-016 | 0 | AE-6187 - Instruments hook-up drawing with BOM | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-05-31 13:29 | 2018-05-31 13:35 | Yes | -34 |  |  |  | 2018-07-12 12:46 |  |  |  |  | 2018-07-12 20:00 | Yes | 28
VD-9001-104(008)-DSH-002 | 0 | AE-6187 - Safety valves data sheet & drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:04 | 2018-04-13 13:32 | Yes | -26 |  |  |  | 2018-04-23 09:17 |  |  |  |  | 2018-04-23 20:00 | Yes | -4
VD-9001-104(008)-DSH-003 | 0 | AE-6187-CM01 - Rupture disk data sheet | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:05 | 2018-04-13 13:32 | Yes | -26 |  |  |  | 2018-05-12 17:33 |  |  |  |  | 2018-05-12 20:00 | Yes | 15
VD-9001-104(008)-DWG-017 | 0 | AE-6187 - Structural steel drawing (included Platform access , Stairs and walkways) | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-018 | 0 | AE-6187 - Fan & Drive assembly drawing with Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-019 | 0 | AE-6187-CM01 - Motor & Name plate &Terminal box arrangement drawings | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-05-22 13:22 | 2018-05-22 13:26 | Yes | 13 |  |  |  | 2018-07-14 08:38 |  |  |  |  | 2018-07-14 19:59 | Yes | 39
VD-9001-104(008)--ISO-001 | 0 | AE-6187 - Piping drawings / isometrics | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-DWG-020 | 0 | AE-6187 - Piping supports drawings | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-LST-003 | 0 | AE-6187 - Piping List | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-06-05 17:11 | 2018-08-02 11:43 | Yes | -29 |  |  |  | 2018-08-13 15:17 |  |  |  |  | 2018-08-13 19:59 | Yes | 55
VD-9001-104(008)-LST-004 | 0 | AE-6187 - Piping Accessories list | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-06-05 17:11 | 2018-08-02 11:43 | Yes | -29 |  |  |  | 2018-08-13 15:28 |  |  |  |  | 2018-08-13 19:59 | Yes | 55
VD-9001-104(008)-DWG-021 | 0 | AE-6187 - Piping items drawing book (included Manual Valves , strainers, filters, etc) | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-022 | 0 | AE-6187 - Control valves drawing book | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-023 | 0 | AE-6187 - NDC Manifold | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-04-30 19:54 | 2018-04-30 19:55 | Yes | -37 |  |  |  | 2018-05-13 17:16 |  |  |  |  | 2018-05-13 20:00 | Yes | -1
VD-9001-104(008)-DWG-024 | 0 | AE-6187 - Manifold drawings 1/2 | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-04-30 19:54 | 2018-04-30 19:55 | Yes | -37 |  |  |  | 2018-05-14 09:41 |  |  |  |  | 2018-05-14 19:59 | Yes | 0
VD-9001-104(008)-DWG-025 | 0 | AE-6187 - Manifold drawings 2/2 | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-04-30 19:54 | 2018-04-30 19:55 | Yes | -37 |  |  |  | 2018-05-14 08:48 |  |  |  |  | 2018-05-14 19:59 | Yes | 0
VD-9001-104(008)-LST-005 | 0 | AE-6187 - Instrument cables list ( Power and control), Wiring diagram, instruments tubing list and material BOM | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-05-31 13:26 | 2018-05-31 13:35 | Yes | -34 |  |  |  | 2018-07-03 16:15 |  |  |  |  | 2018-07-03 20:00 | Yes | 19
VD-9001-104(008)-LST-006 | 0 | AE-6187 - Instruments list | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-04-24 17:24 | 2018-04-24 17:32 | Yes | -43 |  |  |  | 2018-05-22 10:23 |  |  |  |  | 2018-05-22 19:59 | Yes | 14 | 1204-Owner-v | 2019-10-16 08:26
VD-9001-104(008)-DSH-004 | 0 | AE-6187 - Instruments data sheet | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-05-31 13:28 | 2018-05-31 13:34 | Yes | -34 |  |  |  | 2018-07-22 15:38 |  |  |  |  | 2018-07-22 19:59 | Yes | 38 | 1204-Owner-v | 2018-07-22 10:03
VD-9001-104(008)-DSH-005 | 0 | AE-6187 - Fan data sheet & Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-23 | 2018-04-24 17:28 | 2018-04-24 17:31 | Yes | -29 |  |  |  | 2018-05-09 14:54 |  |  |  |  | 2018-05-09 19:59 | Yes | 1
VD-9001-104(008)-DSH-006 | 0 | J-6188 - Inter Condense & Ejector & Vacuum Unit- data sheet | PR-104-SUB | AIR LIQUIDE | 2018-06-06 | 2018-05-22 13:23 | 2018-05-22 13:26 | Yes | -15 |  |  |  | 2018-06-24 17:21 |  |  |  |  | 2018-06-24 20:00 | Yes | 19
VD-9001-104(008)-CAL-001 | 0 | AE-6187 - Calculation notes ( Calculation for seimic , etc for overall package) | PR-104-SUB | AIR LIQUIDE | 2018-05-23 |  |  | No | 758 | [9 empty] | No | 0
VD-9001-104(008)-CAL-002 | 0 | D-6188 - Condensate tank - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-04 18:29 | 2018-04-04 18:31 | Yes | -35 |  |  |  | 2018-04-25 16:31 |  |  |  |  | 2018-04-25 20:00 | Yes | 7
VD-9001-104(008)-WBK-001 | 0 | AE-6187 - Welding book - Expansion Bellow | PR-104-SUB | AIR LIQUIDE | 2018-10-06 |  |  | No | 622 | [9 empty] | No | 0
VD-9001-104(008)-WBK-002 | 0 | AE-6187 - Welding book - Manifold | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-WBK-003 | 0 | AE-6187 - Welding book - Steam Duct | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-WBK-004 | 0 | AE-6187 - Welding book - Piping | PR-104-SUB | AIR LIQUIDE | 2018-11-23 |  |  | No | 574 | [9 empty] | No | 0
VD-9001-104(008)-WBK-005 | 0 | AE-6187 - Welding book - Steel structure | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-WBK-006 | 0 | AE-6187 - Welding book - Tanks | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-WBK-007 | 0 | AE-6187 - Welding book - Vacuum Unit | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-WBK-008 | 0 | AE-6187 - Welding book - Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-WBK-009 | 0 | AE-6187 - Welding book - Control Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-WBK-010 | 0 | AE-6187 - Welding book - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-09 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(008)-CER-001 | 0 | AE-6187 - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2018-12-19 |  |  | No | 548 | [9 empty] | No | 0
VD-9001-104(008)-ITP-001 | 0 | AE-6187 - Inspection and Test Plan - General | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:06 | 2018-04-13 13:38 | Yes | -26 |  |  |  | 2018-04-21 14:32 |  |  |  |  | 2018-04-21 20:00 | Yes | -6 | 1204-Owner-v | 2020-01-01 10:02
VD-9001-104(008)-ITP-002 | 0 | AE-6187 - Inspection and Test Plan - Expansion Bellow | PR-104-SUB | AIR LIQUIDE | 2018-10-06 |  |  | No | 622 | [9 empty] | No | 0
VD-9001-104(008)-ITP-003 | 0 | AE-6187 - Inspection and Test Plan - Manifold | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-ITP-004 | 0 | AE-6187 - Inspection and Test Plan - Steam Duct | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-ITP-005 | 0 | AE-6187 - Inspection and Test Plan - Piping | PR-104-SUB | AIR LIQUIDE | 2018-11-23 |  |  | No | 574 | [9 empty] | No | 0
VD-9001-104(008)-ITP-006 | 0 | AE-6187 - Inspection and Test Plan - Steel structure | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-ITP-007 | 0 | AE-6187 - Inspection and Test Plan - Tanks | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-ITP-008 | 0 | AE-6187 - Inspection and Test Plan - Vacuum Unit | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-ITP-009 | 0 | AE-6187 - Inspection and Test Plan - Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-ITP-010 | 0 | AE-6187 - Inspection and Test Plan - Control Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-ITP-011 | 0 | AE-6187 - Inspection and Test Plan - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:06 | 2018-04-13 13:39 | Yes | -26 |  |  |  | 2018-04-22 16:12 |  |  |  |  | 2018-04-22 20:00 | Yes | -5 | 1204-Owner-v | 2020-01-01 10:01
VD-9001-104(008)-IPM-012 | 0 | AE-6187 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-09 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(008)-IPM-013 | 0 | AE-6187 - Mechanical / performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-014 | 0 | AE-6187 - Non Destructive Examination Procedures - Expansion Bellow | PR-104-SUB | AIR LIQUIDE | 2018-10-06 |  |  | No | 622 | [9 empty] | No | 0
VD-9001-104(008)-IPM-015 | 0 | AE-6187 - Non Destructive Examination Procedures - Manifold | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-016 | 0 | AE-6187 - Non Destructive Examination Procedures - Steam Duct | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-017 | 0 | AE-6187 - Non Destructive Examination Procedures - Piping | PR-104-SUB | AIR LIQUIDE | 2018-11-23 |  |  | No | 574 | [9 empty] | No | 0
VD-9001-104(008)-IPM-018 | 0 | AE-6187 - Non Destructive Examination Procedures - Steel structure | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-019 | 0 | AE-6187 - Non Destructive Examination Procedures - Tanks | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-020 | 0 | AE-6187 - Non Destructive Examination Procedures - Vacuum Unit | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(008)-IPM-021 | 0 | AE-6187 - Non Destructive Examination Procedures - Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-022 | 0 | AE-6187 - Non Destructive Examination Procedures - Control Valves | PR-104-SUB | AIR LIQUIDE | 2018-09-05 |  |  | No | 653 | [9 empty] | No | 0
VD-9001-104(008)-IPM-024 | 0 | AE-6187 - Non Destructive Examination Procedures - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:05 | 2018-04-13 13:28 | Yes | -26 |  |  |  | 2018-04-22 16:23 |  |  |  |  | 2018-04-22 20:00 | Yes | -5
VD-9001-104(008)-MDB-001 | 0 | AE-6187 - Quality Record Books | PR-104-SUB | AIR LIQUIDE | 2019-02-13 |  |  | No | 492 | [9 empty] | No | 0
VD-9001-104(008)-MDB-002 | 0 | AE-6187 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-12-19 |  |  | No | 548 | [9 empty] | No | 0
VD-9001-104(008)-SKT-001 | 0 | AE-6187 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-07-04 | 2018-05-25 18:45 | 2018-05-25 18:46 | Yes | -40 |  |  | 2018-07-22 09:54 | [5 empty] | 2018-07-22 19:59 | Yes | 44
VD-9001-104(008)-MTO-001 | 0 | AE-6187 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-12-19 |  |  | No | 548 | [9 empty] | No | 0
VD-9001-104(008)-LST-007 | 0 | AE-6187 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-07-04 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-MNL-001 | 0 | AE-6187 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-026 | 0 | AE-6187 - Installation drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-04 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-DSH-007 | 0 | P-6187A/B - EDS Equipment Data Sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-PCU-002 | 0 | P-6187A/B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:06 | 2018-04-13 13:24 | Yes | -26 |  |  |  | 2018-05-12 16:27 |  |  |  |  | 2018-05-12 20:00 | Yes | 15
VD-9001-104(008)-DSH-009 | 0 | M P-6187A&B - EDS Equipment data sheet of Motor | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-DWG-027 | 0 | P-6187A/B - General arrangement drawing ( included Motor & Name plate &Terminal box arrangement drawingsand Sectional drawings with Part List) | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-WBK-011 | 0 | P-6187A/B & P-6188A/B - Welding book - Pumps | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-ITP-012 | 0 | P-6187A/B & P-6188A/B - Inspection and Test Plan - Pumps | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-IPM-025 | 0 | P-6187A/B - Tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-IPM-027 | 0 | P-6187A/B & P-6188A/B - Non Destructive Examination Procedures - Pumps | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(008)-DSH-008 | 0 | P-6188A/B - EDS Equipment Data Sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-PCU-003 | 0 | P-6188A/B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-13 13:17 | 2018-04-13 13:24 | Yes | -26 |  |  |  | 2018-05-12 16:45 |  |  |  |  | 2018-05-12 20:00 | Yes | 15
VD-9001-104(008)-DSH-010 | 0 | M P-6188A/B - EDS Equipment data sheet of Motor | PR-104-SUB | AIR LIQUIDE | 2018-06-06 |  |  | No | 744 | [9 empty] | No | 0
VD-9001-104(008)-DWG-028 | 0 | P-6188A/B - General arrangement drawing ( included Motor & Name plates &Terminal box arrangement drawings and Sectional drawings with Part List) | PR-104-SUB | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(008)-IPM-026 | 0 | P-6188A/B - Tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-08-29 |  |  | No | 660 | [9 empty] | No | 0
VD-9001-104(005)-DWG-010 | 0 | E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-10 | 2018-03-07 19:15 | 2018-03-08 11:22 | Yes | -3 |  |  |  | 2018-03-14 09:24 |  |  |  |  | 2018-03-14 20:00 | Yes | -7
VD-9001-257C-DWG-044 | 1 | DETAILS DRAWING (4137-0371/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-17 | 2018-05-14 14:23 | 2018-05-14 14:23 | Yes | 58 |  |  |  |  | 2018-07-21 19:38 |  |  |  | 2018-07-21 19:38 | Yes | 54
VD-9001-257C-DWG-059 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0371/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-17 | 2018-05-14 14:08 | 2018-05-14 14:08 | Yes | 58 |  |  | 2018-05-31 14:42 | [5 empty] | 2018-05-31 14:42 | Yes | 3
VD-9001-257C-GAD-008 | 1 | GENERAL ARRANGEMENT (4137-0371) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-17 | 2018-05-14 13:48 | 2018-05-14 13:48 | Yes | 58 |  |  |  |  | 2018-11-04 16:27 |  |  |  | 2018-11-04 16:27 | Yes | 160 | 1204-Owner-v | 2018-08-04 14:10
VD-9001-204C-ITP-024 | 1 | INSPECTION & TESTING PLAN | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-03-17 | 2018-03-13 14:34 | 2018-03-13 14:34 | Yes | -4 |  |  | 2018-03-26 00:56 | [5 empty] | 2018-03-26 21:00 | Yes | -1 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-257C-CAL-008 | 1 | MECHANICAL CALCULATION (4137-0371/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-17 | 2018-05-14 13:58 | 2018-05-14 13:58 | Yes | 58 |  |  | 2018-08-23 11:48 | [5 empty] | 2018-08-23 11:48 | Yes | 87 | 1204-Owner-v | 2018-08-19 08:55
VD-9001-104-PDS-001 | 1 | Process description | PR-104 | AIR LIQUIDE | 2018-03-17 |  |  | No | 825 | [9 empty] | No | 0
VD-9001-254-PPL-318 | 4 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2018-03-12 | 2018-05-30 13:35 | 2018-05-30 13:36 | Yes | 79 |  |  |  | 2018-06-27 10:56 |  |  |  |  | 2018-06-27 10:56 | Yes | 14 | 1204-Owner-v | 2018-06-12 14:02
VD-9001-254-PPL-319 | 4 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2018-03-13 | 2018-05-14 15:11 | 2018-05-14 15:17 | Yes | 62 |  |  |  | 2018-06-03 11:20 |  |  |  |  | 2018-06-03 11:20 | Yes | 6
VD-9001-251-DSH-027 | 1 | Motor Data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-03-18 |  |  | No | 824 | [9 empty] | No | 0
VD-9001-204B-WMP-002 | 3 | Welding & NDT Map D-1003 | PV-204B | ABAN AIR COOLER. | 2018-03-15 | 2018-05-20 13:06 | 2018-05-20 13:07 | Yes | 66 |  |  |  | 2018-07-04 18:54 |  |  |  |  | 2018-07-04 18:54 | Yes | 31 | 1204-Owner-v | 2019-01-20 11:38
VD-9001-204B-WMP-003 | 3 | Welding & NDT Map D-3006 | PV-204B | ABAN AIR COOLER. | 2018-03-15 | 2018-05-20 13:01 | 2018-05-20 13:01 | Yes | 66 |  |  |  | 2018-07-04 18:58 |  |  |  |  | 2018-07-04 18:58 | Yes | 31 | 1204-Owner-v | 2019-01-20 11:41
VD-9001-204B-WMP-004 | 3 | Welding & NDT Map D-3007 | PV-204B | ABAN AIR COOLER. | 2018-03-15 | 2018-05-20 12:49 | 2018-05-20 12:50 | Yes | 66 |  |  |  | 2018-07-04 19:00 |  |  |  |  | 2018-07-04 19:00 | Yes | 31 | 1204-Owner-v | 2019-01-20 11:41
VD-9001-204B-WMP-001 | 3 | Welding & NDT Map D-1002 | PV-204B | ABAN AIR COOLER. | 2018-03-15 | 2018-05-20 13:11 | 2018-05-20 13:13 | Yes | 66 |  |  |  | 2018-07-04 18:52 |  |  |  |  | 2018-07-04 18:52 | Yes | 31 | 1204-Owner-v | 2019-01-20 11:38
VD-9001-204B-ITP-001 | 3 | Inspection & Test Plan | PV-204B | ABAN AIR COOLER. | 2018-03-17 | 2018-06-25 13:51 | 2018-06-25 13:52 | Yes | 100 |  |  | 2018-06-30 09:20 | [5 empty] | 2018-06-30 09:20 | Yes | -9 | 1204-Owner-v | 2018-11-20 16:14
VD-9001-104-PFD-001 | 3 | PFD Compression and purification | PR-104 | AIR LIQUIDE | 2018-03-31 |  |  | No | 811 | [9 empty] | No | 0
VD-9001-104-PFD-002 | 3 | PFD Cold box | PR-104 | AIR LIQUIDE | 2018-03-31 |  |  | No | 811 | [9 empty] | No | 0
VD-9001-104-PFD-003 | 3 | PFD Liquid Nitrogen storage and vaporization | PR-104 | AIR LIQUIDE | 2018-03-31 |  |  | No | 811 | [9 empty] | No | 0
VD-9001-104-PFD-004 | 3 | PFD Gas utilities | PR-104 | AIR LIQUIDE | 2018-03-17 |  |  | No | 825 | [9 empty] | No | 0
VD-9001-104-PFD-005 | 3 | PFD Cryogenic disposal | PR-104 | AIR LIQUIDE | 2018-03-17 |  |  | No | 825 | [9 empty] | No | 0
VD-9001-104-PFD-006 | 3 | PFD Water utilities | PR-104 | AIR LIQUIDE | 2018-03-17 |  |  | No | 825 | [9 empty] | No | 0
VD-9001-104-PFD-007 | 3 | PFD Steam utilities | PR-104 | AIR LIQUIDE | 2018-03-17 |  |  | No | 825 | [9 empty] | No | 0
VD-9001-254-ISO-504 | 1 | ISOMETRIC DWG. FOR SPRAY WATER LINE (BOILER 6) | HM-254 | AZAR AB | 2018-03-13 | 2019-06-17 15:55 | 2019-06-17 15:55 | Yes | 461 |  |  | 2019-07-08 10:17 | [5 empty] | 2019-07-08 10:17 | Yes | 7
VD-9001-254-ISO-516 | 1 | BOILER FEED WATER LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2018-03-14 | 2018-09-30 15:30 | 2018-09-30 15:30 | Yes | 200 |  |  |  | 2018-10-17 15:53 |  |  |  |  | 2018-10-17 15:53 | Yes | 3
VD-9001-254-ISO-515 | 1 | BOILER FEED WATER LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2018-03-14 | 2018-09-30 15:30 | 2018-09-30 15:30 | Yes | 200 |  |  |  | 2018-10-17 15:51 |  |  |  |  | 2018-10-17 15:51 | Yes | 3
VD-9001-254-ISO-502 | 1 | ISOMETRIC DWG. FOR SPRAY WATER LINE (BOILER 5) | HM-254 | AZAR AB | 2018-03-14 | 2019-06-17 15:53 | 2019-06-17 15:54 | Yes | 460 |  |  | 2019-07-08 10:15 | [5 empty] | 2019-07-08 10:15 | Yes | 7
VD-9001-257C-WBK-008 | 1 | WELDING BOOK (4137-0371/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-18 | 2018-06-25 12:56 | 2018-06-25 13:02 | Yes | 99 |  |  |  |  | 2018-08-04 11:43 |  |  |  | 2018-08-04 11:43 | Yes | 26
VD-9001-301-PCJ-010 | 2 | coating procedure syngas train | MC-301 | Siemens AG | 2018-03-18 |  |  | No | 824 | [9 empty] | No | 0
VD-9001-104-PFD-008 | 3 | PFD Interconnection | PR-104 | AIR LIQUIDE | 2018-03-18 |  |  | No | 824 | [9 empty] | No | 0
VD-9001-104-HMB-001 | 2 | Mass and enthalpy balance "for information" | PR-104 | AIR LIQUIDE | 2018-03-18 |  |  | No | 824 | [9 empty] | No | 0
VD-9001-201B-PCJ-002 | 1 | MANUFACTURING & NDE PROCEDURE (4134/MP) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-18 | 2018-03-15 18:51 | 2018-03-15 18:52 | Yes | -3 |  |  | 2018-04-16 10:26 | [5 empty] | 2018-04-16 20:00 | Yes | 18
VD-9001-104-STR-002 | 1 | Control strategy | PR-104 | AIR LIQUIDE | 2018-03-18 | 2018-05-03 13:09 | 2018-05-03 13:11 | Yes | 46 |  |  |  | 2018-07-30 14:59 |  |  |  |  | 2018-07-30 19:59 | Yes | 74
VD-9001-257C-WBK-006 | 1 | WELDING BOOK (4137-0369/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-19 | 2018-06-22 19:22 | 2018-06-22 19:27 | Yes | 95 |  |  |  |  | 2018-06-28 15:31 |  |  |  | 2018-06-28 15:31 | Yes | -8
VD-9001-257C-WBK-004 | 1 | WELDING BOOK (4137-0367/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-19 | 2018-06-22 19:27 | 2018-06-22 19:27 | Yes | 95 |  |  |  |  | 2018-06-28 15:44 |  |  |  | 2018-06-28 15:44 | Yes | -8
VD-9001-257C-WBK-003 | 1 | WELDING BOOK (4137-0366/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-19 | 2018-06-22 18:04 | 2018-06-22 18:15 | Yes | 95 |  |  |  |  | 2018-06-28 15:56 |  |  |  | 2018-06-28 15:56 | Yes | -8
VD-9001-257C-DWG-057 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0369/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-19 | 2018-05-14 14:05 | 2018-05-14 14:05 | Yes | 56 |  |  |  |  | 2018-05-31 15:02 |  |  |  | 2018-05-31 15:02 | Yes | 3
VD-9001-257C-WBK-007 | 1 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 20:00 | 2018-06-25 12:38 | 2018-06-25 12:47 | Yes | 91 |  |  |  |  | 2018-08-04 11:50 |  |  |  | 2018-08-04 11:50 | Yes | 26
VD-9001-201B-DWG-010 | 1 | TEMPLATE DWG (4134-0359/TMP) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-26 20:00 | 2018-04-19 17:34 | 2018-04-19 17:35 | Yes | 24 |  |  | 2018-04-29 09:49 | [5 empty] | 2018-04-29 19:59 | Yes | -4 | 1204-Owner-v | 2018-07-28 13:44
VD-9001-104-DSH-054 | 1 | Warm TSV - EDS Equipment Data Sheet (thermal) | PR-104 | AIR LIQUIDE | 2018-03-26 20:00 |  |  | No | 816 | [9 empty] | No | 0
VD-9001-104-LST-002 | 1 | Utilities consumption | PR-104 | AIR LIQUIDE | 2018-03-26 20:00 |  |  | No | 816 | [9 empty] | No | 0
VD-9001-301-DBS-001 | 2 | condenser air cooled syngas turbine | MC-301 | Siemens AG | 2018-03-26 20:00 |  |  | No | 816 | [9 empty] | No | 0
VD-9001-104(008)-DWG-005 | 1 | AE-6187 - Civil work drawing– Anchorage Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-03-26 20:00 | 2018-04-23 15:04 | 2018-04-23 15:14 | Yes | 28 |  |  |  | 2018-05-06 16:11 |  |  |  |  | 2018-05-06 20:00 | Yes | -1
VD-9001-104(001)-DWG-001 | 1 | Simple Equipment Slabs book - Inputs for civil work guide drawings | PR-104-SUB | AIR LIQUIDE | 2018-03-26 20:00 |  |  | No | 816 | [9 empty] | No | 0
VD-9001-104-REQ-036 | 2 | Cryogenic Globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-26 20:00 | 2018-04-10 14:27 | 2018-04-10 14:32 | Yes | 15 |  |  |  | 2018-04-17 17:54 |  |  |  |  | 2018-04-17 20:00 | Yes | -7
VD-9001-104-REQ-038 | 2 | Cryogenic JT globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-26 20:00 | 2018-04-10 14:27 | 2018-04-10 14:32 | Yes | 15 |  |  |  | 2018-04-17 17:51 |  |  |  |  | 2018-04-17 20:00 | Yes | -7
VD-9001-257C-DWG-015 | 1 | NAME PLATE DET.DWG (4137-0366/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-20 | 2018-05-21 13:55 | 2018-05-21 13:55 | Yes | 62 |  |  |  |  | 2018-07-09 12:18 |  |  |  | 2018-07-09 12:18 | Yes | 35
VD-9001-257C-DWG-027 | 1 | NAME PLATE DET.DWG (4137-0368/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-20 | 2018-05-14 14:12 | 2018-05-14 14:13 | Yes | 55 |  |  |  | 2018-07-08 15:29 |  |  |  |  | 2018-07-08 15:29 | Yes | 41
VD-9001-104-PID-034 | 1 | PID UTILITIES TIE-INS WASTE WATER PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:20 | 2018-04-19 19:54 | Yes | 23 |  |  |  | 2018-07-08 14:38 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104-PID-017 | 1 | PID Subcooler | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:16 | 2018-04-19 19:52 | Yes | 23 |  |  |  | 2018-06-30 15:53 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:16
VD-9001-104-PID-016 | 1 | PID Main Heat Exchanger | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:16 | 2018-04-19 19:51 | Yes | 23 |  |  |  | 2018-06-30 15:36 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:16
VD-9001-104-PID-022 | 1 | PID HP Column / Main Vaporizer | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:17 | 2018-04-19 19:53 | Yes | 23 |  |  |  | 2018-07-04 16:51 |  |  |  |  | 2018-07-04 20:00 | Yes | 62 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-023 | 1 | PID LP Column / Pure Nitrogen Column | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:17 | 2018-04-19 19:53 | Yes | 23 |  |  |  | 2018-07-03 15:49 |  |  |  |  | 2018-07-03 20:00 | Yes | 61 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-007 | 1 | PID AIR FILTER & MAC 1 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-19 19:14 | 2018-04-19 19:50 | Yes | 23 |  |  |  | 2018-07-07 11:12 |  |  |  |  | 2018-07-07 20:00 | Yes | 65 | 1204-Owner-v | 2018-04-22 10:17
VD-9001-257C-CAL-005 | 1 | MECHANICAL CALCULATION (4137-0368/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-27 20:00 | 2018-05-14 13:53 | 2018-05-14 13:53 | Yes | 48 |  |  | 2018-09-17 10:05 | [5 empty] | 2018-09-17 10:05 | Yes | 112 | 1204-Owner-v | 2018-08-19 08:54
VD-9001-257C-DWG-025 | 1 | DETAILS DRAWING (4137-0368/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-27 20:00 | 2018-05-14 14:11 | 2018-05-14 14:11 | Yes | 48 |  |  | 2018-07-21 19:19 | [5 empty] | 2018-07-21 19:19 | Yes | 54
VD-9001-257C-DWG-026 | 1 | DETAILS DRAWING (4137-0368/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-27 20:00 | 2018-05-14 14:12 | 2018-05-14 14:12 | Yes | 48 |  |  | 2018-07-22 09:40 | [5 empty] | 2018-07-22 09:40 | Yes | 55
VD-9001-257C-DWG-056 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0368/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-27 20:00 | 2018-05-14 14:04 | 2018-05-14 14:04 | Yes | 48 |  |  | 2018-07-22 10:15 | [5 empty] | 2018-07-22 10:15 | Yes | 55
VD-9001-104(006)-DWG-001 | 1 | E-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-10 20:35 | 2018-04-10 20:36 | Yes | 14 |  |  |  | 2018-05-19 10:25 |  |  |  |  | 2018-05-19 19:59 | Yes | 25
VD-9001-104(005)-DWG-003 | 1 | E-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-27 20:00 | 2018-04-11 17:42 | 2018-04-11 17:47 | Yes | 15 |  |  |  | 2018-05-19 16:26 |  |  |  |  | 2018-05-19 19:59 | Yes | 24
VD-9001-204D-DWG-037 | 0 | STEAM DRUM D-2003 / INSULATION SUPPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-03-16 | 2018-03-14 11:26 | 2018-03-14 11:26 | Yes | -2 |  |  |  | 2018-04-21 11:07 |  |  |  |  | 2018-04-21 20:00 | Yes | 24
VD-9001-251-CAL-015 | 1 | STRUCTURAL STATICAL CALCULATONS | HM-251 | KT – Kinetics Technology SpA | 2018-03-21 | 2018-04-24 12:01 | 2018-04-24 12:09 | Yes | 34 |  |  | 2018-05-01 10:18 | [5 empty] | 2018-05-01 10:18 | Yes | -7
VD-9001-204B-PCJ-012 | 1 | Production Test plate Procedure | PV-204B | ABAN AIR COOLER. | 2018-03-19 | 2018-06-23 16:39 | 2018-06-23 16:43 | Yes | 96 |  |  | 2018-06-27 16:42 | [5 empty] | 2018-06-27 16:42 | Yes | -10 | 1204-Owner-v | 2020-04-29 08:42
VD-9001-204B-PCJ-013 | 1 | Ferrite Checking Procedure | PV-204B | ABAN AIR COOLER. | 2018-03-19 | 2018-06-23 16:46 | 2018-06-23 16:47 | Yes | 96 |  |  | 2018-06-27 16:47 | [5 empty] | 2018-06-27 16:47 | Yes | -10 | 1204-Owner-v | 2020-04-29 08:43
VD-9001-104(005)-DWG-002 | 1 | E-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-11 17:42 | 2018-04-11 17:46 | Yes | 14 |  |  |  | 2018-05-20 14:21 |  |  |  |  | 2018-05-20 19:59 | Yes | 25
VD-9001-104(005)-DWG-010 | 1 | E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-11 17:42 | 2018-04-11 17:47 | Yes | 14 |  |  |  | 2018-05-19 15:22 |  |  |  |  | 2018-05-19 19:59 | Yes | 24
VD-9001-104-PID-008 | 1 | PID AIR FILTER & MAC 2 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:15 | 2018-04-19 19:50 | Yes | 22 |  |  |  | 2018-07-07 11:40 |  |  |  |  | 2018-07-07 20:00 | Yes | 65 | 1204-Owner-v | 2018-04-22 10:18
VD-9001-104-PID-012 | 1 | PID Booster turbine air interface with cold booster | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:15 | 2018-04-19 19:51 | Yes | 22 |  |  |  | 2018-06-28 12:04 |  |  |  |  | 2018-06-28 20:00 | Yes | 56 | 1204-Owner-v | 2018-04-22 10:35
VD-9001-104-PID-024 | 1 | PID Liquid Nitrogen Storage | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:18 | 2018-04-19 19:53 | Yes | 22 |  |  |  | 2018-06-03 11:35 |  |  |  |  | 2018-06-03 19:59 | Yes | 31 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-025 | 1 | PID Liquid Nitrogen Vaporizer | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:18 | 2018-04-19 19:53 | Yes | 22 |  |  |  | 2018-07-07 15:38 |  |  |  |  | 2018-07-07 20:00 | Yes | 65 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-201B-DWG-001 | 1 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-28 20:00 | 2018-04-19 17:31 | 2018-04-19 17:32 | Yes | 22 |  |  |  | 2018-06-12 17:26 |  |  |  |  | 2018-06-12 20:15 | Yes | 40
VD-9001-104(004)-DIG-002 | 1 | ST C-6101 - Campbell & goodman diagram | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 |  |  | No | 814 | [9 empty] | No | 0
VD-9001-104-PID-038 | 1 | PID Service Nitrogen | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:21 | 2018-04-19 19:55 | Yes | 22 |  |  |  | 2018-07-10 15:56 |  |  |  |  | 2018-07-10 20:00 | Yes | 68 | 1204-Owner-v | 2018-04-30 16:19
VD-9001-104-PID-032 | 1 | PID Tie-ins | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:19 | 2018-04-19 19:54 | Yes | 22 |  |  |  | 2018-06-30 16:18 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-201B-DWG-015 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4134-0359/BMN) | PV-201B | Brembana & Rolle S.p.A. | 2018-03-28 20:00 | 2018-04-19 17:36 | 2018-04-19 17:36 | Yes | 22 |  |  |  | 2018-06-13 10:13 |  |  |  |  | 2018-06-13 20:00 | Yes | 41
VD-9001-104(008)-DWG-001 | 1 | AE-6187 – General Arrangement Drawing – Front View | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-23 15:04 | 2018-04-23 15:14 | Yes | 26 |  |  |  | 2018-05-06 16:40 |  |  |  |  | 2018-05-06 20:00 | Yes | -1
VD-9001-104(008)-DWG-002 | 1 | AE-6187 - General Arrangement Drawing – Side View | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-23 15:04 | 2018-04-23 15:14 | Yes | 26 |  |  |  | 2018-05-06 14:56 |  |  |  |  | 2018-05-06 20:00 | Yes | -1
VD-9001-104(008)-DWG-003 | 1 | AE-6187 - General Arrangement Drawing – Top View | PR-104-SUB | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-23 15:05 | 2018-04-23 15:14 | Yes | 26 |  |  |  | 2018-05-06 16:38 |  |  |  |  | 2018-05-06 20:00 | Yes | -1
VD-9001-104-PID-018 | 1 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:16 | 2018-04-19 19:52 | Yes | 22 |  |  |  | 2018-07-08 17:31 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:16
VD-9001-104-PID-019 | 1 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-03-28 20:00 | 2018-04-19 19:16 | 2018-04-19 19:52 | Yes | 22 |  |  |  | 2018-07-08 17:37 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:16
VD-9001-204C-DWG-035 | 1 | LADDER & PLATFORM S DWGS. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-03-28 20:00 | 2018-05-10 14:37 | 2018-05-10 14:37 | Yes | 43 |  |  |  | 2018-05-14 09:43 |  |  |  |  | 2018-05-14 19:59 | Yes | -10
VD-9001-257C-DWG-021 | 1 | NAME PLATE DET.DWG (4137-0367/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-24 | 2018-05-21 14:15 | 2018-05-21 14:15 | Yes | 58 |  |  |  |  | 2018-07-09 12:01 |  |  |  | 2018-07-09 12:01 | Yes | 35
VD-9001-257C-GAD-005 | 1 | GENERAL ARRANGEMENT (4137-0368) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-31 20:00 | 2018-05-14 13:46 | 2018-05-14 13:46 | Yes | 44 |  |  |  |  | 2018-08-18 14:33 |  |  |  | 2018-08-18 14:33 | Yes | 82 | 1204-Owner-v | 2018-08-04 14:00
VD-9001-104-PID-011 | 1 | PID Reactivation Heater | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:15 | 2018-04-19 19:51 | Yes | 26 |  |  |  | 2018-07-07 09:23 |  |  |  |  | 2018-07-07 20:00 | Yes | 65 | 1204-Owner-v | 2018-04-22 10:35
VD-9001-104-PID-013 | 1 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:15 | 2018-04-19 19:51 | Yes | 26 |  |  |  | 2018-06-30 11:41 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:15
VD-9001-104-PID-035 | 1 | PID UTILITIES TIE-INS OIL PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:20 | 2018-04-19 19:54 | Yes | 26 |  |  |  | 2018-07-08 14:45 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104-REQ-022 | 2 | P-6103A / P-6103B_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-03-24 |  |  | No | 818 | [9 empty] | No | 0
VD-9001-104-PID-037 | 1 | PID Instrument Air System | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:20 | 2018-04-19 19:55 | Yes | 26 |  |  |  | 2018-07-03 11:31 |  |  |  |  | 2018-07-03 20:00 | Yes | 61 | 1204-Owner-v | 2018-04-30 16:19
VD-9001-104-PID-039 | 1 | PID Steam | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:21 | 2018-04-19 19:55 | Yes | 26 |  |  |  | 2018-07-03 11:48 |  |  |  |  | 2018-07-03 20:00 | Yes | 61 | 1204-Owner-v | 2018-04-30 16:19
VD-9001-104-PID-030 | 1 | PID Gaseous Oxygen Production | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:19 | 2018-04-19 19:54 | Yes | 26 |  |  |  | 2018-07-08 10:34 |  |  |  |  | 2018-07-08 19:59 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104-PID-031 | 1 | PID Gaseous Nitrogen Production | PR-104 | AIR LIQUIDE | 2018-03-24 | 2018-04-19 19:19 | 2018-04-19 19:54 | Yes | 26 |  |  |  | 2018-06-30 16:55 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104(003)-ITP-001 | 1 | T-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-03-24 | 2018-04-24 18:16 | 2018-04-24 18:19 | Yes | 31 |  |  |  | 2018-05-01 10:14 |  |  |  |  | 2018-05-01 19:59 | Yes | -7 | 1204-Owner-v | 2018-08-04 10:02
VD-9001-204D-DWG-005 | 1 | INTERNAL PARTS DETAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-03-18 10:53 | 2018-03-19 15:03 | 2018-03-19 15:04 | Yes | 1 |  |  | 2018-04-21 11:41 | [5 empty] | 2018-04-21 20:00 | Yes | 19
VD-9001-104(004)-DWG-027 | 0 | General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-02-09 | 2018-04-20 19:20 | 2018-04-20 19:26 | Yes | 70 |  |  |  | 2018-07-04 14:39 |  |  |  |  | 2018-07-04 20:00 | Yes | 61 | 1204-Owner-v | 2018-08-04 10:14
VD-9001-104(004)-DWG-028 | 0 | Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-02-09 | 2018-04-20 19:20 | 2018-04-20 19:26 | Yes | 70 |  |  |  | 2018-04-30 11:13 |  |  |  |  | 2018-04-30 20:00 | Yes | -4
VD-9001-104(005)-DWG-011 | 0 | E-6101/E-6103 - Civil work guide drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-03-29 | 2018-04-04 12:34 | 2018-04-04 12:40 | Yes | 6 |  |  |  | 2018-04-15 15:27 |  |  |  |  | 2018-04-15 20:01 | Yes | -3
VD-9001-104(005)-ITP-003 | 0 | E-6101/E-6103 - Aluminium piping Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-03-05 | 2018-05-23 18:41 | 2018-05-23 18:45 | Yes | 79 |  |  |  | 2018-06-20 09:10 |  |  |  |  | 2018-06-20 20:00 | Yes | 14 | 1204-Owner-v | 2020-01-01 09:41
VD-9001-104(013)-IPM-001 | 0 | P-6103A / P-6103B - Painting specification (Motor only) | PR-104-SUB | AIR LIQUIDE | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-104(013)-DSH-001 | 0 | P-6103A / P-6103B - EDS Equipment data sheet of Motor (SPECIFIC TO CLIENT FORM) | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-04-20 18:58 | 2018-04-20 19:01 | Yes | 21 |  |  |  | 2018-05-28 15:47 |  |  |  |  | 2018-05-28 19:59 | Yes | 24
VD-9001-104(013)-DWG-001 | 0 | P-6103A / P-6103B - General arrangement drawing (motor&pump) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-20 18:26 | 2018-04-20 18:58 | Yes | 7 |  |  |  | 2018-05-16 16:17 |  |  |  |  | 2018-05-16 20:00 | Yes | 12 | 1204-Owner-v | 2018-08-13 10:03
VD-9001-104(013)-DWG-002 | 0 | P-6103A / P-6103B - Terminal box arrangement ( Including the wiring diagram) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-20 18:26 | 2018-04-20 18:58 | Yes | 7 |  |  |  | 2018-05-23 14:26 |  |  |  |  | 2018-05-23 19:59 | Yes | 19
VD-9001-104(013)-DWG-003 | 0 | P-6103A / P-6103B - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-DSH-002 | 0 | P-6103A / P-6103B - Instruments Data sheet ( according customer template ) | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-CER-001 | 0 | P-6103A / P-6103B - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2018-09-17 |  |  | No | 641 | [9 empty] | No | 0
VD-9001-104(013)-DWG-004 | 0 | P-6103A / P-6103B - Name plate (motor&pump& casing) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-104(013)-MDB-003 | 0 | P-6103A / P-6103B - Quality record book | PR-104-SUB | AIR LIQUIDE | 2018-09-24 |  |  | No | 634 | [9 empty] | No | 0
VD-9001-104(013)-MDB-004 | 0 | P-6103A / P-6103B - vendor data book | PR-104-SUB | AIR LIQUIDE | 2018-08-27 |  |  | No | 662 | [9 empty] | No | 0
VD-9001-104(013)-DWG-005 | 0 | P-6103A / P-6103B - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-104(013)-LST-001 | 0 | P-6103A / P-6103B - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-24 |  |  | No | 634 | [9 empty] | No | 0
VD-9001-104(013)-LST-002 | 0 | P-6103A / P-6103B - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-MNL-001 | 0 | P-6103A / P-6103B - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-24 |  |  | No | 634 | [9 empty] | No | 0
VD-9001-104(013)-IPM-002 | 0 | P-6105A / P-6105B - Painting specification (Motor only) | PR-104-SUB | AIR LIQUIDE | 2018-03-30 |  |  | No | 812 | [9 empty] | No | 0
VD-9001-104(013)-PCU-001 | 0 | P-6105A / P-6105B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-03-09 | 2018-04-05 14:07 | 2018-04-05 14:09 | Yes | 27 |  |  |  | 2018-05-12 15:49 |  |  |  |  | 2018-05-12 20:00 | Yes | 23
VD-9001-104(013)-DSH-003 | 0 | P-6105A / P-6105B - EDS Equipment data sheet of Motor (SPECIFIC TO CLIENT FORM) | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-05-03 19:28 | 2018-05-03 19:31 | Yes | 34 |  |  |  | 2018-05-28 15:54 |  |  |  |  | 2018-05-28 19:59 | Yes | 11
VD-9001-104(013)-DWG-006 | 0 | P-6105A / P-6105B - General arrangement drawing (motor&pump) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-20 18:26 | 2018-04-20 18:58 | Yes | 7 |  |  |  | 2018-05-13 14:42 |  |  |  |  | 2018-05-13 19:59 | Yes | 9
VD-9001-104(013)-DWG-007 | 0 | P-6105A / P-6105B - Terminal box arrangement ( Including the wiring diagram) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-20 18:27 | 2018-04-20 18:58 | Yes | 7 |  |  |  | 2018-05-27 10:40 |  |  |  |  | 2018-05-27 19:59 | Yes | 23
VD-9001-104(013)-DWG-008 | 0 | P-6105A / P-6105B - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-DSH-004 | 0 | P-6105A / P-6105B - Instruments Data sheet ( according customer template ) | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-CER-002 | 0 | P-6105A / P-6105B - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2018-09-17 |  |  | No | 641 | [9 empty] | No | 0
VD-9001-104(013)-IPM-003 | 0 | P-6105A / P-6105B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-04-20 18:27 | 2018-04-20 18:59 | Yes | 21 |  |  |  | 2018-04-24 17:01 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-104(013)-IPM-004 | 0 | P-6105A / P-6105B - Run test & Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-04-20 18:27 | 2018-04-20 18:59 | Yes | 21 |  |  |  | 2018-05-28 15:31 |  |  |  |  | 2018-05-28 19:59 | Yes | 24
VD-9001-104(013)-DWG-009 | 0 | P-6105A / P-6105B - Name plate (motor&pump& casing) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-104(013)-MDB-001 | 0 | P-6105A / P-6105B - Quality record book | PR-104-SUB | AIR LIQUIDE | 2018-09-24 |  |  | No | 634 | [9 empty] | No | 0
VD-9001-104(013)-MDB-002 | 0 | P-6105A / P-6105B - vendor data book | PR-104-SUB | AIR LIQUIDE | 2018-08-27 |  |  | No | 662 | [9 empty] | No | 0
VD-9001-104(013)-DWG-010 | 0 | P-6105A / P-6105B - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-104(013)-LST-003 | 0 | P-6105A / P-6105B - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(013)-MNL-002 | 0 | P-6105A / P-6105B - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-24 |  |  | No | 634 | [9 empty] | No | 0
VD-9001-104(004)-DWG-029 | 0 | ST C-6101 - Governor System - Outline drawing & Connection diagram | PR-104-SUB | AIR LIQUIDE | 2018-07-27 |  |  | No | 693 | [9 empty] | No | 0
VD-9001-104(014)-DSH-001 | 0 | E-6108 - EDS Equipment Data Sheet | PR-104-SUB | AIR LIQUIDE | 2018-04-14 |  |  | No | 797 | [9 empty] | No | 0
VD-9001-104(014)-IPM-001 | 0 | E-6108 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-01 | 2018-04-30 18:15 | 2018-04-30 18:21 | Yes | -1 |  |  |  | 2018-05-14 14:58 |  |  |  |  | 2018-05-14 19:59 | Yes | 0
VD-9001-104(014)-DWG-001 | 0 | E-6108/E-6108-D1 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-03-29 | 2018-04-03 15:03 | 2018-04-03 15:04 | Yes | 5 |  |  |  | 2018-04-24 19:13 |  |  |  |  | 2018-04-24 20:00 | Yes | 7
VD-9001-104(014)-DWG-002 | 0 | E-6108/E-6108-D1 - Load on structure and anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-05-02 | 2018-04-23 14:04 | 2018-04-23 14:25 | Yes | -9 |  |  |  | 2018-04-25 11:22 |  |  |  |  | 2018-04-25 20:00 | Yes | -12
VD-9001-104(014)-DWG-003 | 0 | E-6108 - Vessel detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-04-23 14:04 | 2018-04-23 14:26 | Yes | -17 |  |  |  | 2018-05-06 09:33 |  |  |  |  | 2018-05-06 19:59 | Yes | -1
VD-9001-104(014)-DWG-004 | 0 | E-6108 - Bundle detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-04-23 14:06 | 2018-04-23 14:26 | Yes | -17 |  |  | 2018-05-07 15:25 | [5 empty] | 2018-05-07 20:00 | Yes | 0 | 1204-Owner-v | 2019-02-02 16:50
VD-9001-104(014)-DWG-005 | 0 | E-6108 D1 - Detail drawing equipment and piping | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-04-23 14:05 | 2018-04-23 14:26 | Yes | -17 |  |  |  | 2018-06-02 16:43 |  |  |  |  | 2018-06-02 19:59 | Yes | 26
VD-9001-104(014)-DWG-006 | 0 | E-6108 - Expansion joint drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-05-22 11:46 | 2018-05-22 11:51 | Yes | 12 |  |  | 2018-05-30 16:37 | [5 empty] | 2018-05-30 19:59 | Yes | -6
VD-9001-104(014)-CAL-001 | 0 | E-6108/E-6108-D1 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-04-30 18:13 | 2018-04-30 18:14 | Yes | -10 |  |  |  | 2018-05-28 15:06 |  |  |  |  | 2018-05-28 19:59 | Yes | 14
VD-9001-104(014)-WBK-001 | 0 | E-6108/E-6108-D1 - Equipment and piping Welding book vessel and piping | PR-104-SUB | AIR LIQUIDE | 2018-04-26 | 2018-05-28 14:14 | 2018-05-28 14:15 | Yes | 32 |  |  |  | 2018-06-25 16:18 |  |  |  |  | 2018-06-25 20:00 | Yes | 14
VD-9001-104(014)-IPM-002 | 0 | E-6108/E-6108-D1 - Equipment and piping Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-26 | 2018-05-23 18:10 | 2018-05-23 18:12 | Yes | 27 |  |  |  | 2018-06-20 10:36 |  |  |  |  | 2018-06-20 20:00 | Yes | 14
VD-9001-104(014)-IPM-003 | 0 | E-6108/E-6108-D1 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-04-26 | 2018-05-23 18:15 | 2018-05-23 18:16 | Yes | 27 |  |  | 2018-06-20 09:40 | [5 empty] | 2018-06-20 20:00 | Yes | 14
VD-9001-104(014)-ITP-001 | 0 | E-6108/E-6108-D1 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-04-12 | 2018-04-05 18:36 | 2018-04-05 18:40 | Yes | -7 |  |  |  | 2018-04-21 14:58 |  |  |  |  | 2018-04-21 20:00 | Yes | 2 | 1204-Owner-v | 2020-01-01 09:58
VD-9001-104(014)-DWG-007 | 0 | E-6108/E-6108-D1 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-04-26 | 2018-04-17 14:39 | 2018-04-17 14:47 | Yes | -9 |  |  |  | 2018-05-09 16:31 |  |  |  |  | 2018-05-09 19:59 | Yes | 8
VD-9001-104(014)-MDB-001 | 0 | E-6108/E-6108-D1 - Quality data record book | PR-104-SUB | AIR LIQUIDE | 2018-09-08 |  |  | No | 650 | [9 empty] | No | 0
VD-9001-104(014)-MDB-002 | 0 | E-6108/E-6108-D1 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-09-26 |  |  | No | 632 | [9 empty] | No | 0
VD-9001-104(014)-SKT-001 | 0 | E-6108/E-6108-D1 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-05-10 | 2018-04-30 18:22 | 2018-04-30 18:22 | Yes | -10 |  |  | 2018-05-13 11:38 | [5 empty] | 2018-05-13 19:59 | Yes | -1
VD-9001-104(014)-LST-001 | 0 | E-6108/E-6108-D1 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-08 |  |  | No | 650 | [9 empty] | No | 0
VD-9001-104(014)-MNL-001 | 0 | E-6108/E-6108-D1 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-07-05 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-301-DWG-032 | 1 | circulator compressor protection strainer (1; dim. drawing) | MC-301 | Siemens AG | 2018-04-01 21:00 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-PID-033 | 1 | PID Cooling Water Distribution | PR-104 | AIR LIQUIDE | 2018-04-01 21:00 | 2018-04-19 19:20 | 2018-04-19 19:54 | Yes | 18 |  |  |  | 2018-07-02 09:21 |  |  |  |  | 2018-07-02 20:00 | Yes | 60 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104-PID-029 | 1 | PID Air interface | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:19 | 2018-04-19 19:53 | Yes | 12 |  |  |  | 2018-07-08 14:32 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:18
VD-9001-104-PID-020 | 1 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:18 | 2018-04-19 19:52 | Yes | 12 |  |  |  | 2018-07-09 11:30 |  |  |  |  | 2018-07-09 19:59 | Yes | 67 | 1204-Owner-v | 2018-04-30 16:16
VD-9001-104-PID-026 | 1 | PID Cryogenic Disposal Purges | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:18 | 2018-04-19 19:53 | Yes | 12 |  |  |  | 2018-07-07 17:23 |  |  |  |  | 2018-07-07 20:00 | Yes | 65 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-009 | 1 | PID ACC INTEGRATION | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:15 | 2018-04-19 19:50 | Yes | 12 |  |  |  | 2018-06-28 11:32 |  |  |  |  | 2018-06-28 20:00 | Yes | 56 | 1204-Owner-v | 2018-04-22 10:35
VD-9001-104-PID-021 | 1 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:17 | 2018-04-19 19:52 | Yes | 12 |  |  |  | 2018-07-09 11:24 |  |  |  |  | 2018-07-09 19:59 | Yes | 67 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-014 | 1 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:19 | 2018-04-19 19:51 | Yes | 12 |  |  |  | 2018-06-30 10:02 |  |  |  |  | 2018-06-30 20:00 | Yes | 58 | 1204-Owner-v | 2018-04-30 16:15
VD-9001-104-PID-010 | 1 | PID Air Purification Vessel | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:15 | 2018-04-19 19:51 | Yes | 12 |  |  |  | 2018-06-28 09:23 |  |  |  |  | 2018-06-28 20:00 | Yes | 56 | 1204-Owner-v | 2018-04-22 10:35
VD-9001-104-PID-036 | 1 | PID Derime | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:20 | 2018-04-19 19:54 | Yes | 12 |  |  |  | 2018-07-03 14:53 |  |  |  |  | 2018-07-03 20:00 | Yes | 61 | 1204-Owner-v | 2018-04-30 16:19
VD-9001-104-PID-040 | 1 | PID Utilities tie-in | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-04-19 19:21 | 2018-04-19 19:55 | Yes | 12 |  |  |  | 2018-07-08 16:01 |  |  |  |  | 2018-07-08 20:00 | Yes | 66 | 1204-Owner-v | 2018-04-30 16:19
VD-9001-104-LST-001 | 4 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2018-04-07 | 2018-06-08 14:31 | 2018-06-08 14:36 | Yes | 62 |  |  |  | 2018-07-03 16:03 |  |  |  |  | 2018-07-03 20:00 | Yes | 11
VD-9001-104-REQ-034 | 1 | Temperature - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104-REQ-044 | 1 | Warm PSV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(001)-LST-032 | 1 | Tie-ins list drawing ( with Client) | PR-104-SUB | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(004)-DSH-005 | 1 | C-6101 / C-6102 - Process After cooler - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-04-07 |  |  | No | 804 | [9 empty] | No | 0
VD-9001-104(002)-DWG-010 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:22 | 2018-04-26 18:29 | Yes | 19 |  |  |  | 2018-05-06 11:47 |  |  |  |  | 2018-05-06 20:00 | Yes | -4
VD-9001-104(002)-DWG-011 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:22 | 2018-04-26 18:29 | Yes | 19 |  |  |  | 2018-05-06 10:58 |  |  |  |  | 2018-05-06 20:00 | Yes | -4
VD-9001-104(002)-DWG-012 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:22 | 2018-04-26 18:29 | Yes | 19 |  |  | 2018-05-06 09:38 | [5 empty] | 2018-05-06 19:59 | Yes | -4 | 1204-Owner-v | 2018-09-09 13:38
VD-9001-104(002)-DWG-014 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:23 | 2018-04-26 18:30 | Yes | 19 |  |  |  | 2018-05-06 09:56 |  |  |  |  | 2018-05-06 19:59 | Yes | -4
VD-9001-104(002)-DWG-015 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:23 | 2018-04-26 18:30 | Yes | 19 |  |  | 2018-05-06 09:41 | [5 empty] | 2018-05-06 19:59 | Yes | -4
VD-9001-104(002)-DWG-008 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:21 | 2018-04-26 18:29 | Yes | 19 |  |  |  | 2018-05-06 11:59 |  |  |  |  | 2018-05-06 20:00 | Yes | -4
VD-9001-104(002)-DWG-009 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-26 18:22 | 2018-04-26 18:29 | Yes | 19 |  |  |  | 2018-05-06 11:53 |  |  |  |  | 2018-05-06 20:00 | Yes | -4
VD-9001-740A-MOD-00083 | 0 | Models-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-06 13:17 | 2018-05-06 13:17 | Yes | 48 |  |  |  |  | 2018-05-10 12:04 |  | 2018-05-05 14:11 | 2018-05-05 14:11 | 2018-05-10 12:04 | Yes | -10
VD-9001-740A-GAD-00083 | 0 | General Arrangement Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-05 13:19 | 2018-05-05 13:20 | Yes | 47 |  |  |  |  | 2018-05-10 12:01 |  |  |  | 2018-05-10 12:01 | Yes | -9
VD-9001-740A-SAD-00083 | 0 | Shop Assembly Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:38 | 2018-05-29 08:40 | Yes | 71 |  |  |  | 2018-06-07 12:19 |  |  |  |  | 2018-06-07 12:19 | Yes | -5
VD-9001-740A-SPD-00083 | 0 | Single Part Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:43 | 2018-05-29 08:43 | Yes | 71 |  |  |  | 2018-06-07 12:42 |  |  |  |  | 2018-06-07 12:42 | Yes | -5
VD-9001-740A-RPT-00083 | 0 | Reports-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:36 | 2018-05-29 08:36 | Yes | 71 |  |  | 2018-06-07 12:02 | [5 empty] | 2018-06-07 12:02 | Yes | -5
VD-9001-740A-MOD-00084 | 0 | Models-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-06 13:18 | 2018-05-06 13:18 | Yes | 48 |  |  |  |  | 2018-05-10 12:02 |  | 2018-05-05 14:13 | 2018-05-05 14:13 | 2018-05-10 12:02 | Yes | -10
VD-9001-740A-GAD-00084 | 0 | General Arrangement Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-06 13:19 | 2018-05-06 13:19 | Yes | 48 |  |  |  |  | 2018-05-10 11:58 |  |  |  | 2018-05-10 11:58 | Yes | -10
VD-9001-740A-SAD-00084 | 0 | Shop Assembly Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:42 | 2018-05-29 08:42 | Yes | 71 |  |  |  | 2018-06-07 12:20 |  |  |  |  | 2018-06-07 12:20 | Yes | -5
VD-9001-740A-SPD-00084 | 0 | Single Part Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:44 | 2018-05-29 08:44 | Yes | 71 |  |  |  | 2018-06-07 12:42 |  |  |  |  | 2018-06-07 12:42 | Yes | -5
VD-9001-740A-RPT-00084 | 0 | Reports-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-03-19 | 2018-05-29 08:36 | 2018-05-29 08:36 | Yes | 71 |  |  | 2018-06-07 12:01 | [5 empty] | 2018-06-07 12:01 | Yes | -5
VD-9001-257C-GAD-004 | 1 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 14:11 | 2018-05-21 14:11 | Yes | 56 |  |  |  |  | 2018-08-15 11:46 |  |  |  | 2018-08-15 11:46 | Yes | 72 | 1204-Owner-v | 2018-08-04 13:57
VD-9001-257C-DWG-055 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0367/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 14:11 | 2018-05-21 14:11 | Yes | 56 |  |  | 2018-05-31 12:17 | [5 empty] | 2018-05-31 12:17 | Yes | -4
VD-9001-257C-DWG-020 | 1 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 14:13 | 2018-05-21 14:14 | Yes | 56 |  |  |  |  | 2018-10-10 17:49 |  |  |  | 2018-10-10 17:49 | Yes | 128
VD-9001-257C-ITP-008 | 1 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-22 17:52 | 2018-05-22 17:53 | Yes | 57 |  |  |  |  | 2018-06-17 11:03 |  |  |  | 2018-06-17 11:03 | Yes | 12
VD-9001-257C-CAL-004 | 1 | MECHANICAL CALCULATION (4137-0367/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 14:09 | 2018-05-21 14:10 | Yes | 56 |  |  |  |  | 2018-09-11 10:42 |  |  |  | 2018-09-11 10:42 | Yes | 99 | 1204-Owner-v | 2018-08-19 08:54
VD-9001-257C-GAD-003 | 1 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 13:52 | 2018-05-21 13:52 | Yes | 56 |  |  |  |  | 2018-08-15 11:13 |  |  |  | 2018-08-15 11:13 | Yes | 72 | 1204-Owner-v | 2018-08-04 13:55
VD-9001-257C-CAL-003 | 1 | MECHANICAL CALCULATION (4137-0366/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 13:25 | 2018-05-21 13:25 | Yes | 56 |  |  |  |  | 2018-09-11 10:40 |  |  |  | 2018-09-11 10:40 | Yes | 99 | 1204-Owner-v | 2018-08-19 08:54
VD-9001-257C-DWG-054 | 1 | BILL OF MATERIAL AND GENERAL NOTES (4137-0366/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 13:56 | 2018-05-21 13:56 | Yes | 56 |  |  | 2018-05-31 13:03 | [5 empty] | 2018-05-31 13:03 | Yes | -4
VD-9001-257C-DWG-014 | 1 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-03-26 | 2018-05-21 13:54 | 2018-05-21 13:54 | Yes | 56 |  |  |  |  | 2018-07-21 19:49 |  |  |  | 2018-07-21 19:49 | Yes | 47
VD-9001-104-ORC-001 | 1 | Project Organization Chart | PR-104 | AIR LIQUIDE | 2018-03-19 19:14 | 2018-03-20 15:29 | 2018-03-20 15:39 | Yes | 1 |  |  | 2018-03-26 11:15 | [5 empty] | 2018-03-26 21:00 | Yes | -8 | 1204-Owner-v | 2018-04-09 17:02
VD-9001-104(008)-DWG-004 | 1 | AE-6187 - General Arrangement Drawing – Main Structure Walkway Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-04-02 21:00 | 2018-04-23 15:05 | 2018-04-23 15:14 | Yes | 21 |  |  | 2018-05-06 16:23 | [5 empty] | 2018-05-06 20:00 | Yes | -1
VD-9001-104(004)-PID-001 | 1 | C-6101 / C-6102 - PID symbols summary page | PR-104-SUB | AIR LIQUIDE | 2018-04-02 21:00 |  |  | No | 809 | [9 empty] | No | 0
VD-9001-104(008)-PID-001 | 1 | AE-6187 - PID symbols summary page | PR-104-SUB | AIR LIQUIDE | 2018-04-02 21:00 | 2018-04-24 17:06 | 2018-04-24 17:18 | Yes | 22 |  |  |  | 2018-05-08 11:53 |  |  |  |  | 2018-05-08 19:59 | Yes | 0
VD-9001-104(008)-PID-002 | 1 | AE-6187 - PID process ACC | PR-104-SUB | AIR LIQUIDE | 2018-04-02 21:00 | 2018-04-24 17:06 | 2018-04-24 17:18 | Yes | 22 |  |  |  | 2018-05-09 14:44 |  |  |  |  | 2018-05-09 19:59 | Yes | 1
VD-9001-104(005)-ITP-002 | 1 | E-6103 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-04-02 21:00 | 2018-04-10 20:55 | 2018-04-10 20:58 | Yes | 8 |  |  | 2018-04-24 18:52 | [5 empty] | 2018-04-24 20:00 | Yes | 0 | 1204-Owner-v | 2018-05-12 16:47
VD-9001-104(008)-PID-005 | 1 | AE-6187 - PID Steam Jet Air Ejector | PR-104-SUB | AIR LIQUIDE | 2018-03-30 | 2018-04-24 17:07 | 2018-04-24 17:20 | Yes | 25 |  |  |  | 2018-05-08 17:33 |  |  |  |  | 2018-05-08 19:59 | Yes | 0
VD-9001-104(004)-PID-011 | 1 | ST-C-6102 -PID turbine | PR-104-SUB | AIR LIQUIDE | 2018-04-14 |  |  | No | 797 | [9 empty] | No | 0
VD-9001-104(004)-PID-010 | 1 | ST C-6101 -PID turbine | PR-104-SUB | AIR LIQUIDE | 2018-04-14 |  |  | No | 797 | [9 empty] | No | 0
VD-9001-257C-ITP-002 | 1 | INSPECTION & TESTING PLAN (4137-0365/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-14 | 2018-05-22 17:49 | 2018-05-22 17:49 | Yes | 38 |  |  |  |  | 2018-06-17 11:26 |  |  |  | 2018-06-17 11:26 | Yes | 12
VD-9001-257C-ITP-003 | 1 | INSPECTION & TESTING PLAN (4137-0366/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-08 | 2018-05-22 17:48 | 2018-05-22 17:49 | Yes | 44 |  |  |  |  | 2018-06-17 11:24 |  |  |  | 2018-06-17 11:24 | Yes | 12
VD-9001-257C-ITP-004 | 1 | INSPECTION & TESTING PLAN (4137-0367/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-08 | 2018-05-22 17:50 | 2018-05-22 17:50 | Yes | 44 |  |  |  |  | 2018-06-17 11:22 |  |  |  | 2018-06-17 11:22 | Yes | 12
VD-9001-257C-ITP-006 | 1 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-08 | 2018-05-22 17:51 | 2018-05-22 17:51 | Yes | 44 |  |  |  |  | 2018-06-17 11:07 |  |  |  | 2018-06-17 11:07 | Yes | 12
VD-9001-257C-ITP-007 | 1 | INSPECTION & TESTING PLAN (4137-0370/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-08 | 2018-05-22 17:52 | 2018-05-22 17:52 | Yes | 44 |  |  |  |  | 2018-06-17 11:05 |  |  |  | 2018-06-17 11:05 | Yes | 12
VD-9001-257C-ITP-001 | 1 | INSPECTION & TESTING PLAN (4137-0364/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-08 | 2018-05-22 17:34 | 2018-05-22 17:35 | Yes | 44 |  |  |  |  | 2018-06-05 15:27 |  |  |  | 2018-06-05 15:27 | Yes | 0
VD-9001-202F-ITP-003 | 1 | Waste Heat Boiler - Inspection & Test Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-08 | 2018-04-06 15:50 | 2018-04-06 21:22 | Yes | -2 |  |  | 2018-04-22 10:10 | [5 empty] | 2018-04-22 10:10 | Yes | 2 | 1204-Owner-v | 2018-05-12 16:59
VD-9001-202F-WBK-001 | 1 | Waste Heat Boiler - Welding Book (WPS & PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-08 | 2018-04-10 20:42 | 2018-04-10 20:46 | Yes | 2 |  |  |  | 2018-05-06 10:28 |  |  |  |  | 2018-05-06 10:28 | Yes | 12
VD-9001-201B-PCJ-020 | 1 | TOFD PROCEDURE (4134/TOFD) | PV-201B | Brembana & Rolle S.p.A. | 2018-04-09 21:00 | 2018-05-28 16:59 | 2018-05-28 17:01 | Yes | 49 |  |  | 2018-06-24 11:10 | [5 empty] | 2018-06-24 20:00 | Yes | 13
VD-9001-104(004)-DSH-002 | 1 | C-6101 / C-6102 - Process cooler 2 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 |  |  | No | 802 | [9 empty] | No | 0
VD-9001-104(004)-DWG-006 | 1 | C-6102 / ST C-6102 : Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 |  |  | No | 802 | [9 empty] | No | 0
VD-9001-104(008)-DWG-007 | 1 | AE-6187 – Civil work drawing - Anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 | 2018-05-22 13:23 | 2018-05-22 13:26 | Yes | 43 |  |  |  | 2018-05-29 09:04 |  |  |  |  | 2018-05-29 19:59 | Yes | -7
VD-9001-104(008)-DWG-006 | 1 | AE-6187 – Civil work drawing - Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 | 2018-05-22 13:23 | 2018-05-22 13:26 | Yes | 43 |  |  |  | 2018-05-29 08:13 |  |  |  |  | 2018-05-29 19:59 | Yes | -7
VD-9001-104(004)-DSH-003 | 1 | C-6101 / C-6102 - Process cooler 3 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 |  |  | No | 802 | [9 empty] | No | 0
VD-9001-104(004)-DSH-004 | 1 | C-6101 / C-6102 - Process cooler 4 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-04-09 21:00 |  |  | No | 802 | [9 empty] | No | 0
VD-9001-257C-DWG-008 | 1 | DETAILS DRAWING (4137-0365/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-10 | 2018-05-14 14:09 | 2018-05-14 14:09 | Yes | 34 |  |  |  |  | 2018-10-02 11:48 |  |  |  | 2018-10-02 11:48 | Yes | 127
VD-9001-257C-DWG-045 | 1 | DETAILS DRAWING (4137-0371/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-10 | 2018-05-14 14:24 | 2018-05-14 14:24 | Yes | 34 |  |  |  |  | 2018-06-05 15:45 |  |  |  | 2018-06-05 15:45 | Yes | 8
VD-9001-257C-DWG-064 | 1 | DETAILS DRAWING (4137-0367/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-03 | 2018-05-21 14:15 | 2018-05-21 14:15 | Yes | 48 |  |  |  |  | 2018-06-14 14:21 |  |  |  | 2018-06-14 14:21 | Yes | 10
VD-9001-257C-DWG-051 | 1 | DETAILS DRAWING (4137-0371/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-03 | 2018-05-14 14:25 | 2018-05-14 14:25 | Yes | 41 |  |  |  |  | 2018-07-08 16:41 |  |  |  | 2018-07-08 16:41 | Yes | 41
VD-9001-104-EQL-001 | 1 | Main equipment list | PR-104 | AIR LIQUIDE | 2018-04-10 21:00 | 2018-06-07 18:48 | 2018-06-07 18:54 | Yes | 58 |  |  |  | 2018-06-20 14:33 |  |  |  |  | 2018-06-20 20:00 | Yes | -1 | 1204-Owner-v | 2019-02-16 20:07
VD-9001-104(004)-PID-012 | 1 | ST-C-6102 -PID condensing system | PR-104-SUB | AIR LIQUIDE | 2018-04-10 |  |  | No | 801 | [9 empty] | No | 0
VD-9001-254-DWG-907 | 2 | FOUNDATION OF CASING | HM-254 | AZAR AB | 2018-04-10 |  |  | No | 801 | [9 empty] | No | 0
VD-9001-202F-DWG-004 | 1 | Steam Superheater - Manholes/ Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-11 | 2018-08-24 17:00 | 2018-08-24 17:01 | Yes | 135 |  |  |  |  | 2018-09-08 11:39 |  |  |  | 2018-09-08 11:39 | Yes | 1 | 1204-Owner-v | 2018-11-27 17:24
VD-9001-202F-DWG-002 | 1 | Steam Superheater - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-11 | 2018-08-10 18:15 | 2018-08-10 18:15 | Yes | 121 |  |  |  |  | 2018-08-18 14:30 |  |  |  | 2018-08-18 14:30 | Yes | -6 | 1204-Owner-v | 2019-02-25 14:47
VD-9001-301-DWG-055 | 0 | Local Operator Panel Dimensional Drawing Syngas Turbine | MC-301 | Siemens AG | 2018-04-03 | 2018-04-04 09:00 | 2018-04-04 09:00 | Yes | 1 | [9 empty] | No | 793 | 1204-Owner-v | 2018-05-15 16:57
VD-9001-301-DWG-056 | 0 | Local Operator Panel Dimensional Drawing Circulator Turbine | MC-301 | Siemens AG | 2018-04-03 | 2018-04-04 09:02 | 2018-04-04 09:02 | Yes | 1 | [9 empty] | No | 793 | 1204-Owner-v | 2018-05-15 16:59
VD-9001-104-REQ-018 | 3 | PU-6101_E-6108/ E-6108-D1_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-03 17:23 | 2018-04-09 16:50 | 2018-04-09 16:52 | Yes | 6 |  |  | 2018-04-15 11:21 | [5 empty] | 2018-04-15 20:00 | Yes | -8
VD-9001-104-DSH-051 | 2 | Warm automatic 3-lever valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-04 09:16 | 2018-04-04 12:19 | 2018-04-04 12:20 | Yes | 0 |  |  |  | 2018-05-21 14:43 |  |  |  |  | 2018-05-21 19:59 | Yes | 33 | 1204-Owner-v | 2018-07-30 10:14
VD-9001-251-DWG-077 | 1 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-04 10:05 | 2018-04-04 11:52 | 2018-04-04 13:01 | Yes | 0 |  |  |  | 2018-04-09 14:57 |  |  |  |  | 2018-04-09 14:57 | Yes | -9
VD-9001-204C-DWG-038 | 0 | WELDING MAP DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-04 | 2018-04-05 12:22 | 2018-04-05 12:26 | Yes | 1 |  |  |  | 2018-06-19 14:46 |  |  |  |  | 2018-06-19 20:00 | Yes | 61
VD-9001-104(008)-PID-004 | 1 | AE-6187 - PID Steam duct | PR-104-SUB | AIR LIQUIDE | 2018-04-20 | 2018-04-24 17:07 | 2018-04-24 17:19 | Yes | 4 |  |  |  | 2018-05-08 17:35 |  |  |  |  | 2018-05-08 19:59 | Yes | 0
VD-9001-104(008)-PID-003 | 1 | AE-6187 - PID Condensate System | PR-104-SUB | AIR LIQUIDE | 2018-04-20 | 2018-04-24 17:07 | 2018-04-24 17:19 | Yes | 4 |  |  |  | 2018-05-08 17:34 |  |  |  |  | 2018-05-08 19:59 | Yes | 0
VD-9001-104-DSH-012 | 4 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-20 | 2018-06-08 13:55 | 2018-08-02 11:42 | Yes | 49 |  |  |  | 2018-08-14 11:08 |  |  |  |  | 2018-08-14 19:59 | Yes | 53
VD-9001-104-CAL-002 | 1 | PSV- Warm Safety valves - Calculations | PR-104 | AIR LIQUIDE | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-251-DWG-110 | 0 | plan and platforms – convection details | HM-251 | KT – Kinetics Technology SpA | 2018-04-07 | 2018-04-09 12:17 | 2018-04-09 12:29 | Yes | 2 |  |  | 2018-04-16 11:53 | [5 empty] | 2018-04-16 11:53 | Yes | -7
VD-9001-202F-PPL-006 | 1 | Steam Drum - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-21 | 2018-04-10 20:58 | 2018-04-10 20:58 | Yes | -11 |  |  |  |  | 2018-05-17 16:30 |  |  |  | 2018-05-17 16:30 | Yes | 23 | 1204-Owner-v | 2018-05-26 16:27
VD-9001-104(010)-DWG-001 | 1 | Warm automatic 3-lever valve - Detail drawings | PR-104-SUB | AIR LIQUIDE | 2018-04-15 |  |  | No | 796 | [9 empty] | No | 0
VD-9001-301-PCJ-011 | 2 | coating procedure circulator train | MC-301 | Siemens AG | 2018-04-17 |  |  | No | 794 | [9 empty] | No | 0
VD-9001-301-DWG-004 | 2 | foundation plan syngas train | MC-301 | Siemens AG | 2018-04-17 |  |  | No | 794 | [9 empty] | No | 0
VD-9001-307A-ITP-004 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-04-22 | 2018-09-21 16:42 | 2018-09-21 16:42 | Yes | 152 |  |  | 2018-10-09 08:58 | [5 empty] | 2018-10-09 18:57 | Yes | 4 | 1204-Owner-v | 2018-10-13 14:31
VD-9001-307A-ITP-003 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-04-22 | 2018-09-21 16:42 | 2018-09-21 16:42 | Yes | 152 |  |  | 2018-10-09 09:01 | [5 empty] | 2018-10-09 18:57 | Yes | 4 | 1204-Owner-v | 2018-10-20 15:05
VD-9001-307A-ITP-002 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-04-22 | 2018-09-21 16:41 | 2018-09-21 16:42 | Yes | 152 |  |  |  | 2018-10-08 15:53 |  |  |  |  | 2018-10-08 18:59 | Yes | 3 | 1204-Owner-v | 2018-10-20 15:05
VD-9001-307A-ITP-001 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-04-22 | 2018-09-21 16:41 | 2018-09-21 16:42 | Yes | 152 |  |  |  | 2018-10-08 08:18 |  |  |  |  | 2018-10-08 18:57 | Yes | 3 | 1204-Owner-v | 2018-10-20 15:04
VD-9001-301-DWG-005 | 2 | foundation plan circulator train | MC-301 | Siemens AG | 2018-04-22 |  |  | No | 789 | [9 empty] | No | 0
VD-9001-251-DWG-075 | 2 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-04-12 | 2018-06-07 17:51 | 2018-06-07 17:51 | Yes | 56 |  |  | 2018-06-13 14:41 | [5 empty] | 2018-06-13 14:41 | Yes | -8
VD-9001-251-DWG-076 | 2 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-12 | 2018-06-07 17:58 | 2018-06-07 17:58 | Yes | 56 |  |  | 2018-06-13 14:42 | [5 empty] | 2018-06-13 14:42 | Yes | -8
VD-9001-251-DWG-077 | 2 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-12 | 2018-06-07 18:01 | 2018-06-07 18:02 | Yes | 56 |  |  | 2018-06-13 14:43 | [5 empty] | 2018-06-13 14:43 | Yes | -8
VD-9001-251-DWG-050 | 2 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 | 2018-06-13 19:09 | 2018-06-13 19:17 | Yes | 61 |  |  |  | 2018-06-18 17:33 |  |  |  |  | 2018-06-18 17:33 | Yes | -9
VD-9001-251-ITP-001 | 1 | SHOP INSPECTION TEST PLANS | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 |  |  | No | 798 | [9 empty] | No | 0
VD-9001-202F-PPL-003 | 1 | Layout Plan for Steel Structure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-23 |  |  | No | 788 | [9 empty] | No | 0
VD-9001-202F-PPL-004 | 1 | Steam Superheater - General Arrangement | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-23 | 2018-08-13 16:18 | 2018-08-13 16:18 | Yes | 112 |  |  |  |  | 2018-09-08 09:57 |  |  |  | 2018-09-08 09:57 | Yes | 12 | 1204-Owner-v | 2018-11-28 08:43
VD-9001-104(006)-WBK-001 | 1 | E-6102 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-04-23 20:00 | 2018-04-30 15:32 | 2018-04-30 15:37 | Yes | 7 |  |  | 2018-05-19 17:22 | [5 empty] | 2018-05-19 19:59 | Yes | 5
VD-9001-104(005)-IPM-001 | 1 | E-6101/E-6103 - Pressure / leak test procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-23 20:00 | 2018-04-27 18:00 | 2018-04-27 18:23 | Yes | 4 |  |  | 2018-05-01 10:17 | [5 empty] | 2018-05-01 19:59 | Yes | -10
VD-9001-104(006)-ITP-001 | 1 | E-6102 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-04-23 20:00 |  |  | No | 788 | [9 empty] | No | 0
VD-9001-104-PID-027 | 1 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-04-23 20:00 | 2018-04-19 19:18 | 2018-04-19 19:53 | Yes | -4 |  |  |  | 2018-07-10 14:30 |  |  |  |  | 2018-07-10 20:00 | Yes | 68 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-104-PID-028 | 1 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-04-23 20:00 | 2018-04-19 19:18 | 2018-04-19 19:53 | Yes | -4 |  |  |  | 2018-07-10 11:45 |  |  |  |  | 2018-07-10 20:00 | Yes | 68 | 1204-Owner-v | 2018-04-30 16:17
VD-9001-301-LST-010 | 2 | utility consumption list circulator train | MC-301 | Siemens AG | 2018-04-24 20:00 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-LST-007 | 2 | utility consumption list syngas train | MC-301 | Siemens AG | 2018-04-24 20:00 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-DWG-041 | 2 | general arrangement syngas train | MC-301 | Siemens AG | 2018-04-24 20:00 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-301-DWG-043 | 2 | general arrangement circulator train | MC-301 | Siemens AG | 2018-04-24 20:00 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-104-DSH-011 | 3 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-04-24 20:00 | 2018-06-01 17:47 | 2018-06-01 17:51 | Yes | 38 |  |  |  | 2018-07-12 12:39 |  |  |  |  | 2018-07-12 19:59 | Yes | 27
VD-9001-104(005)-DWG-001 | 1 | E-6101/E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-24 20:00 | 2018-05-25 19:05 | 2018-05-25 19:09 | Yes | 31 |  |  |  | 2018-06-11 14:23 |  |  |  |  | 2018-06-11 19:59 | Yes | 3
VD-9001-104(005)-IPM-002 | 1 | E-6101/E-6103 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-04-25 20:00 | 2018-04-27 17:59 | 2018-04-27 18:24 | Yes | 2 |  |  | 2018-05-06 17:55 | [5 empty] | 2018-05-06 20:00 | Yes | -5
VD-9001-104(006)-IPM-001 | 1 | E-6102 - Pressure / leak test procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-25 20:00 | 2018-05-22 12:30 | 2018-05-22 12:32 | Yes | 27 |  |  | 2018-06-18 08:56 | [5 empty] | 2018-06-18 20:00 | Yes | 13
VD-9001-104-SLD-001 | 1 | LV One line diagram | PR-104 | AIR LIQUIDE | 2018-04-25 20:00 |  |  | No | 786 | [9 empty] | No | 0
VD-9001-204C-PCJ-026 | 1 | P.M.I. PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-25 20:00 | 2018-04-13 13:20 | 2018-04-13 13:25 | Yes | -12 |  |  | 2018-04-18 17:56 | [5 empty] | 2018-04-18 20:00 | Yes | -9
VD-9001-204C-PCJ-028 | 1 | FERRITE CHECK PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-25 20:00 | 2018-05-18 14:22 | 2018-05-18 14:23 | Yes | 23 |  |  |  | 2018-06-17 16:44 |  |  |  |  | 2018-06-17 20:00 | Yes | 16
VD-9001-251-DWG-099 | 1 | INSTRUMENTS CONNECTION DRAWINGS | HM-251 | KT – Kinetics Technology SpA | 2018-04-17 | 2018-10-10 11:59 | 2018-10-10 12:03 | Yes | 176 |  |  | 2018-10-24 10:25 | [5 empty] | 2018-10-24 10:25 | Yes | 0
VD-9001-104(007)-DWG-003 | 1 | DR-6101A / DR-6101B - Bottom part detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-12 12:33 | 2018-04-12 16:28 | 2018-04-12 16:35 | Yes | 0 |  |  |  | 2018-05-06 08:52 |  |  |  |  | 2018-05-06 19:59 | Yes | 10
VD-9001-104(007)-DWG-004 | 1 | DR-6101A / DR-6101B - Upper part details drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-12 12:33 | 2018-04-12 16:28 | 2018-04-12 16:35 | Yes | 0 |  |  | 2018-05-06 09:02 | [5 empty] | 2018-05-06 19:59 | Yes | 10
VD-9001-104(002)-IPM-001 | 1 | D-6103 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-26 20:00 |  |  | No | 785 | [9 empty] | No | 0
VD-9001-104(006)-IPM-002 | 1 | E-6102 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-04-26 20:00 |  |  | No | 785 | [9 empty] | No | 0
VD-9001-104(004)-PCU-002 | 1 | ST C-6101 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-04-26 20:00 |  |  | No | 785 | [9 empty] | No | 0
VD-9001-104(004)-PCU-003 | 1 | ST C-6102 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-04-26 20:00 |  |  | No | 785 | [9 empty] | No | 0
VD-9001-104-DSH-043 | 2 | Cryo automatic valve - EDS Equipment Data Sheet for globe valves | PR-104 | AIR LIQUIDE | 2018-04-26 20:00 | 2018-04-16 14:55 | 2018-04-16 14:56 | Yes | -10 |  |  |  | 2018-05-21 15:53 |  |  |  |  | 2018-05-21 19:59 | Yes | 21 | 1204-Owner-v | 2018-07-22 10:17
VD-9001-104-DSH-045 | 2 | Cryo automatic valve - EDS Equipment Data Sheet for JT globe valves | PR-104 | AIR LIQUIDE | 2018-04-26 20:00 |  |  | No | 785 | [9 empty] | No | 0
VD-9001-104(011)-CAL-002 | 0 | Cryogenic Globe automatic valves - Calculation sheet for globe valves ( included noise calculation) | PR-104-SUB | AIR LIQUIDE | 2018-06-01 | 2018-05-03 12:50 | 2018-05-03 12:53 | Yes | -29 |  |  |  | 2018-06-14 11:03 |  |  |  |  | 2018-06-14 20:00 | Yes | 28
VD-9001-104(004)-DSH-XXX | 0 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Speed reduction gear datasheet | PR-104-SUB | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104(016)-IPM-001 | 0 | C-6103/TEX-6103 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(017)-LST-001 | 0 | FT-6101 / FT-6102 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-20 |  |  | No | 638 | [9 empty] | No | 0
VD-9001-104(016)-PCU-001 | 0 | C-6103/TEX-6103 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-IPM-002 | 0 | C-6103/TEX-6103 - Motor electrical specification of lube oil pump | PR-104-SUB | AIR LIQUIDE | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-104(017)-DSH-001 | 0 | FT-6101 / FT-6102 - Noise acoustic Datasheet | PR-104-SUB | AIR LIQUIDE | 2018-04-25 | 2018-04-30 21:01 | 2018-04-30 21:08 | Yes | 5 |  |  |  | 2018-05-15 11:25 |  |  |  |  | 2018-05-15 19:59 | Yes | 1
VD-9001-104(016)-LST-002 | 0 | C-6103/TEX-6103 - Piping connection list & Allowable forces and moments | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(017)-DWG-003 | 0 | FT-6101 / FT-6102 - Anchoring details | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-30 21:01 | 2018-04-30 21:08 | Yes | -9 |  |  |  | 2018-05-15 17:23 |  |  |  |  | 2018-05-15 20:00 | Yes | 1
VD-9001-104(017)-DWG-004 | 0 | FT-6101 / FT-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-04-25 | 2018-04-30 21:02 | 2018-04-30 21:09 | Yes | 5 |  |  |  | 2018-05-13 11:28 |  |  |  |  | 2018-05-13 19:59 | Yes | -1
VD-9001-104(016)-DWG-005 | 0 | C-6103/TEX-6103 - Wiring diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(016)-LST-003 | 0 | C-6103/TEX-6103 - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-08-17 |  |  | No | 672 | [9 empty] | No | 0
VD-9001-104(017)-DSH-002 | 0 | FT-6101 / FT-6102 - Filter elements detail dwg. And datasheet | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-30 20:50 | 2018-04-30 20:56 | Yes | -9 |  |  |  |  | 2018-05-13 10:42 |  |  |  | 2018-05-13 19:59 | Yes | -1 | 1204-Owner-v | 2019-08-01 21:43
VD-9001-104(016)-DSH-003 | 0 | C-6103/TEX-6103 - Lube oil filter drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DSH-004 | 0 | C-6103/TEX-6103 - Oil cooler drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DWG-006 | 0 | C-6103/TEX-6103 - Bladder accumulator assembly drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DSH-005 | 0 | C-6103/TEX-6103 - Instruments Data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-104(016)-ARP-001 | 0 | C-6103/TEX-6103 - Lateral analysis | PR-104-SUB | AIR LIQUIDE | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-104(016)-CER-001 | 0 | C-6103/TEX-6103 - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2019-03-30 |  |  | No | 447 | [9 empty] | No | 0
VD-9001-104(016)-IPM-003 | 0 | C-6103/TEX-6103 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-27 | 2018-05-02 13:28 | 2018-05-02 13:59 | Yes | 5 |  |  |  | 2018-05-15 15:10 |  |  |  |  | 2018-05-15 19:59 | Yes | -1
VD-9001-104(016)-IPM-004 | 0 | C-6103/TEX-6103 - Mechanical / Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-27 | 2018-05-22 16:49 | 2018-05-22 16:53 | Yes | 25 |  |  |  | 2018-06-24 11:25 |  |  |  |  | 2018-06-24 20:00 | Yes | 19
VD-9001-104(016)-IPM-005 | 0 | C-6103/TEX-6103 - Shop inspection test procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-27 |  |  | No | 784 | [9 empty] | No | 0
VD-9001-104(016)-INR-001 | 0 | C-6103/TEX-6103 - Mechanical / Performances test report | PR-104-SUB | AIR LIQUIDE | 2019-03-15 |  |  | No | 462 | [9 empty] | No | 0
VD-9001-104(016)-DWG-007 | 0 | C-6103/TEX-6103 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-05-02 13:27 | 2018-05-02 13:59 | Yes | 19 |  |  |  | 2018-05-30 16:59 |  |  |  |  | 2018-05-30 19:59 | Yes | 14
VD-9001-104(017)-MDB-001 | 0 | FT-6101 / FT-6102 - Quality Record Book (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-09-12 |  |  | No | 646 | [9 empty] | No | 0
VD-9001-104(017)-MDB-002 | 0 | FT-6101 / FT-6102 - Vendor Data Book (VDB) | PR-104-SUB | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104(017)-SKT-001 | 0 | FT-6101 / FT-6102 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-07-18 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-104(016)-LST-004 | 0 | C-6103/TEX-6103 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2019-03-02 |  |  | No | 475 | [9 empty] | No | 0
VD-9001-104(017)-MNL-001 | 0 | FT-6101 / FT-6102 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-09-23 |  |  | No | 635 | [9 empty] | No | 0
VD-9001-104(016)-IPM-006 | 0 | C-6104/TEX-6104 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-11 |  |  | No | 770 | [9 empty] | No | 0
VD-9001-104(016)-LST-005 | 0 | C-6104/TEX-6104 - Lubricants list | PR-104-SUB | AIR LIQUIDE | 2018-06-22 |  |  | No | 728 | [9 empty] | No | 0
VD-9001-104(016)-PCU-002 | 0 | C-6104/TEX-6104 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-IPM-007 | 0 | C-6104/TEX-6104 - Motor electrical specification of lube oil pump | PR-104-SUB | AIR LIQUIDE | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-104(016)-DSH-010 | 0 | C-6104/TEX-6104 - EDS Equipment data sheet of oil mist fan motor | PR-104-SUB | AIR LIQUIDE | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-104(016)-DWG-008 | 0 | C-6104/TEX-6104 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-16 19:31 | 2018-04-16 19:39 | Yes | 3 |  |  |  | 2018-05-15 17:08 |  |  |  |  | 2018-05-15 20:00 | Yes | 15
VD-9001-104(016)-LST-006 | 0 | C-6104/TEX-6104 - Piping connection list & Allowable forces and moments | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DWG-009 | 0 | C-6104/TEX-6104 - Civil work drawing / Foundation plan | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-16 19:05 | 2018-04-16 19:39 | Yes | 3 |  |  |  | 2018-04-30 11:14 |  |  |  |  | 2018-04-30 20:00 | Yes | 0
VD-9001-104(016)-DWG-010 | 0 | C-6104/TEX-6104 - Anchoring details (plate,bolt, etc) | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-05-22 16:48 | 2018-05-22 16:54 | Yes | 39 |  |  |  | 2018-06-02 16:37 |  |  |  |  | 2018-06-02 19:59 | Yes | -3
VD-9001-104(016)-DWG-011 | 0 | C-6104/TEX-6104 - Local Panel details | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(016)-DWG-012 | 0 | C-6104/TEX-6104 - Wiring diagram | PR-104-SUB | AIR LIQUIDE | 2018-06-08 |  |  | No | 742 | [9 empty] | No | 0
VD-9001-104(016)-LST-007 | 0 | C-6104/TEX-6104 - Sectional drawings with Part List | PR-104-SUB | AIR LIQUIDE | 2018-08-17 |  |  | No | 672 | [9 empty] | No | 0
VD-9001-104(016)-DSH-006 | 0 | C-6104/TEX-6104 - Oil pump drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DSH-007 | 0 | C-6104/TEX-6104 - Lube oil filter drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DSH-008 | 0 | C-6104/TEX-6104 - Oil cooler drawing & data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DWG-013 | 0 | C-6104/TEX-6104 - Bladder accumulator assembly drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-03 |  |  | No | 686 | [9 empty] | No | 0
VD-9001-104(016)-DSH-011 | 0 | C-6104/TEX-6104 - Instruments Data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-104(016)-ARP-002 | 0 | C-6104/TEX-6104 - Lateral analysis | PR-104-SUB | AIR LIQUIDE | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-104(016)-CER-002 | 0 | C-6104/TEX-6104 - Instruments calibration certificates | PR-104-SUB | AIR LIQUIDE | 2019-04-01 |  |  | No | 445 | [9 empty] | No | 0
VD-9001-104(016)-ITP-002 | 0 | C-6104/TEX-6104 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-04-16 19:05 | 2018-04-16 19:39 | Yes | 3 |  |  |  | 2018-04-24 17:15 |  |  |  |  | 2018-04-24 20:00 | Yes | -6 | 1204-Owner-v | 2020-01-01 09:57
VD-9001-104(016)-IPM-008 | 0 | C-6104/TEX-6104 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-27 | 2018-05-02 13:28 | 2018-05-02 13:59 | Yes | 5 |  |  |  | 2018-05-15 14:50 |  |  |  |  | 2018-05-15 19:59 | Yes | -1
VD-9001-104(016)-IPM-009 | 0 | C-6104/TEX-6104 - Mechanical / Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-27 | 2018-05-22 16:49 | 2018-05-22 16:54 | Yes | 25 |  |  |  | 2018-06-25 14:49 |  |  |  |  | 2018-06-25 20:00 | Yes | 20
VD-9001-104(016)-IPM-010 | 0 | C-6104/TEX-6104 - Shop Inspection test procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-27 |  |  | No | 784 | [9 empty] | No | 0
VD-9001-104(016)-INR-002 | 0 | C-6104/TEX-6104 - Mechanical / Performances test report | PR-104-SUB | AIR LIQUIDE | 2019-03-15 |  |  | No | 462 | [9 empty] | No | 0
VD-9001-104(016)-DWG-014 | 0 | C-6104/TEX-6104 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-04-13 | 2018-05-02 13:28 | 2018-05-02 13:59 | Yes | 19 |  |  |  | 2018-05-30 17:02 |  |  |  |  | 2018-05-30 19:59 | Yes | 14
VD-9001-104(016)-MDB-003 | 0 | C-6104/TEX-6104 - Quality record book (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-04-27 |  |  | No | 784 | [9 empty] | No | 0
VD-9001-104(016)-MDB-004 | 0 | C-6104/TEX-6104 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2019-02-16 |  |  | No | 489 | [9 empty] | No | 0
VD-9001-104(016)-SKT-002 | 0 | C-6104/TEX-6104 - Transport and handling sketches ( included auxilaries) | PR-104-SUB | AIR LIQUIDE | 2018-08-17 |  |  | No | 672 | [9 empty] | No | 0
VD-9001-104(016)-LST-008 | 0 | C-6104/TEX-6104 - Spare parts & special tools list | PR-104-SUB | AIR LIQUIDE | 2019-03-02 |  |  | No | 475 | [9 empty] | No | 0
VD-9001-104(016)-MNL-002 | 0 | C-6104/TEX-6104 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-07-06 |  |  | No | 714 | [9 empty] | No | 0
VD-9001-104(017)-CAL-001 | 0 | FT-6101 / FT-6102 - Implosion & Explosion doors design calculations | PR-104-SUB | AIR LIQUIDE | 2018-04-25 |  |  | No | 786 | [9 empty] | No | 0
VD-9001-104(017)-WBK-001 | 0 | FT-6101 / FT-6102 - Manifold Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-23 |  |  | No | 758 | [9 empty] | No | 0
VD-9001-104(013)-PCU-002 | 0 | P-6103A / P-6103B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-03-09 | 2018-04-16 14:01 | 2018-04-16 14:41 | Yes | 38 |  |  |  | 2018-05-20 10:41 |  |  |  |  | 2018-05-20 19:59 | Yes | 20
VD-9001-104(014)-IPM-004 | 0 | E-6124 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-06-02 |  |  | No | 748 | [9 empty] | No | 0
VD-9001-104(014)-DWG-008 | 0 | E-6124 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-28 | 2018-04-17 14:39 | 2018-04-17 14:47 | Yes | -11 |  |  |  | 2018-05-22 11:59 |  |  |  |  | 2018-05-22 19:59 | Yes | 21 | 1204-Owner-v | 2018-08-01 15:12
VD-9001-104(014)-DWG-009 | 0 | E-6124 - Civil work drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-05-05 | 2018-04-23 14:05 | 2018-04-23 14:26 | Yes | -12 |  |  |  | 2018-04-25 14:44 |  |  |  |  | 2018-04-25 20:00 | Yes | -12
VD-9001-104(014)-DWG-010 | 0 | E-6124 - Vessel details drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 | 2018-06-01 17:05 | 2018-06-01 17:10 | Yes | -1 |  |  |  | 2018-06-09 09:58 |  |  |  |  | 2018-06-09 19:59 | Yes | -6
VD-9001-104(014)-DWG-011 | 0 | E-6124 - Bundle details drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 | 2018-06-01 17:24 | 2018-06-01 18:10 | Yes | -1 |  |  |  | 2018-06-11 09:35 |  |  |  |  | 2018-06-11 19:59 | Yes | -4
VD-9001-104(014)-LST-002 | 0 | E-6124 - Parts list | PR-104-SUB | AIR LIQUIDE | 2018-06-02 | 2018-05-28 14:03 | 2018-05-28 14:14 | Yes | -5 |  |  |  | 2018-06-10 09:52 |  |  |  |  | 2018-06-10 19:59 | Yes | -1
VD-9001-104(014)-CAL-002 | 0 | E-6124 - Calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-05-05 | 2018-04-30 18:09 | 2018-04-30 18:14 | Yes | -5 |  |  |  | 2018-05-28 15:21 |  |  |  |  | 2018-05-28 19:59 | Yes | 14
VD-9001-104(014)-WBK-002 | 0 | E-6124 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-19 | 2018-05-31 12:39 | 2018-05-31 12:46 | Yes | 12 |  |  |  | 2018-06-25 15:15 |  |  |  |  | 2018-06-25 20:00 | Yes | 11
VD-9001-104(014)-ITP-002 | 0 | E-6124 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-05 | 2018-05-04 19:21 | 2018-05-04 19:26 | Yes | -1 |  |  |  | 2018-05-16 17:11 |  |  |  |  | 2018-05-16 20:00 | Yes | -2 | 1204-Owner-v | 2018-05-12 16:44
VD-9001-104(014)-IPM-005 | 0 | E-6124 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-19 | 2018-05-23 18:11 | 2018-05-23 18:12 | Yes | 4 |  |  | 2018-06-23 15:12 | [5 empty] | 2018-06-23 20:00 | Yes | 17
VD-9001-104(014)-IPM-006 | 0 | E-6124 - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-05-19 | 2018-05-23 18:15 | 2018-05-23 18:16 | Yes | 4 |  |  | 2018-06-20 09:43 | [5 empty] | 2018-06-20 20:00 | Yes | 14
VD-9001-104(014)-DWG-012 | 0 | E-6124 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-05 | 2018-04-23 14:05 | 2018-04-23 14:27 | Yes | -12 |  |  |  | 2018-05-09 16:47 |  |  |  |  | 2018-05-09 20:00 | Yes | 2
VD-9001-104(014)-MDB-003 | 0 | E-6124 - Manufacturer Data Report (QRB) | PR-104-SUB | AIR LIQUIDE | 2018-09-18 |  |  | No | 640 | [9 empty] | No | 0
VD-9001-104(014)-MDB-004 | 0 | E-6124 - Vendor Data Book | PR-104-SUB | AIR LIQUIDE | 2018-08-07 |  |  | No | 682 | [9 empty] | No | 0
VD-9001-104(014)-SKT-002 | 0 | E-6124 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-07-28 |  |  | No | 692 | [9 empty] | No | 0
VD-9001-104(014)-LST-003 | 0 | E-6124 - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-09-18 |  |  | No | 640 | [9 empty] | No | 0
VD-9001-104(014)-MNL-002 | 0 | E-6124 - Installation, Operation and Maintenance manual* | PR-104-SUB | AIR LIQUIDE | 2018-10-02 |  |  | No | 626 | [9 empty] | No | 0
VD-9001-104(013)-IPM-005 | 0 | P-6103A / P-6103B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-20 18:27 | 2018-04-20 18:59 | Yes | 13 |  |  |  | 2018-04-25 15:13 |  |  |  |  | 2018-04-25 20:00 | Yes | -9
VD-9001-104(013)-IPM-006 | 0 | P-6103A / P-6103B - Run test & Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-07 | 2018-04-20 18:27 | 2018-04-20 18:59 | Yes | 13 |  |  |  | 2018-05-19 17:58 |  |  |  |  | 2018-05-19 19:59 | Yes | 15
VD-9001-104(013)-LST-004 | 0 | P-6105A / P-6105B - Packing list | PR-104-SUB | AIR LIQUIDE | 2018-10-01 |  |  | No | 627 | [9 empty] | No | 0
VD-9001-202F-BOQ-001 | 1 | Steam Superheater - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 11:42 | 2018-04-18 18:40 | 2018-04-18 18:43 | Yes | 3 |  |  | 2018-04-25 15:27 | [5 empty] | 2018-04-25 15:27 | Yes | -7 | 1204-Owner-v | 2018-07-22 17:10
VD-9001-201-DWG-001 | 5 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2018-04-15 11:49 | 2018-04-16 16:21 | 2018-04-16 16:23 | Yes | 1 |  |  |  | 2018-08-11 16:04 |  |  |  |  | 2018-08-11 16:04 | Yes | 103 | 1204-Owner-v | 2018-08-04 11:45
VD-9001-201-PCJ-011 | 1 | UT EXAMINATION OF WELDS | PV-201 | ATB RIVA CALZONI SpA | 2018-04-15 11:49 | 2018-04-16 11:22 | 2018-04-16 12:07 | Yes | 1 |  |  | 2018-05-09 15:54 | [5 empty] | 2018-05-09 15:54 | Yes | 9
VD-9001-104-PID-002 | 1 | Piping symbols schematic | PR-104 | AIR LIQUIDE | 2018-04-15 12:29 | 2018-04-16 15:09 | 2018-04-16 15:11 | Yes | 1 |  |  | 2018-04-28 15:50 | [5 empty] | 2018-04-28 20:00 | Yes | -2 | 1204-Owner-v | 2018-04-22 09:59
VD-9001-202F-DWG-011 | 1 | Waste Heat Boiler - Manholes / Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-15 17:19 | 2018-04-18 18:35 | 2018-04-18 18:39 | Yes | 3 |  |  | 2018-05-09 17:00 | [5 empty] | 2018-05-09 17:00 | Yes | 7
VD-9001-307A-PCU-001 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:51 | 2018-04-20 10:52 | Yes | -9 |  |  |  | 2018-04-24 15:27 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-002 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:51 | 2018-04-20 10:52 | Yes | -9 |  |  |  | 2018-04-24 15:23 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-003 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:51 | 2018-04-20 10:52 | Yes | -9 |  |  |  | 2018-04-24 11:17 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-004 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 11:10 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-104(002)-DWG-013 | 1 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-29 20:00 | 2018-04-26 18:23 | 2018-04-26 18:29 | Yes | -3 |  |  |  | 2018-05-06 10:11 |  |  |  |  | 2018-05-06 20:00 | Yes | -4
VD-9001-307A-PCU-005 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 10:25 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-006 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 10:15 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-104(004)-PID-008 | 1 | C-6102 PID Vibration & temperature moniotoring system | PR-104-SUB | AIR LIQUIDE | 2018-04-29 20:00 |  |  | No | 782 | [9 empty] | No | 0
VD-9001-307A-PCU-007 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 10:10 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-008 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 09:59 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-009 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 09:46 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-307A-PCU-010 | 1 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-04-29 20:00 | 2018-04-20 10:52 | 2018-04-20 10:53 | Yes | -9 |  |  |  | 2018-04-24 09:42 |  |  |  |  | 2018-04-24 20:00 | Yes | -10
VD-9001-104(005)-DWG-011 | 1 | E-6101/E-6103 - Civil work guide drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-04-29 20:00 |  |  | No | 782 | [9 empty] | No | 0
VD-9001-204C-GAD-002 | 3 | GENERAL ARRANGEMENT DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-29 20:00 | 2018-07-16 21:03 | 2018-07-16 21:08 | Yes | 78 |  |  | 2018-08-13 15:19 | [5 empty] | 2018-08-13 19:59 | Yes | 14 | 1204-Owner-v | 2019-04-06 14:32
VD-9001-104(005)-ITP-001 | 1 | E-6101 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-04-29 20:00 | 2018-05-22 12:17 | 2018-05-22 12:20 | Yes | 23 |  |  | 2018-06-18 08:43 | [5 empty] | 2018-06-18 20:00 | Yes | 13 | 1204-Owner-v | 2018-08-04 10:20
VD-9001-104(002)-IPM-003 | 1 | T-6101 & E-6102 - Vaporizer shell - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-29 20:00 |  |  | No | 782 | [9 empty] | No | 0
VD-9001-204C-DWG-003 | 2 | MATERIAL LIST AND GENERAL NOTES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-29 20:00 | 2018-07-16 21:09 | 2018-07-16 21:09 | Yes | 78 |  |  |  | 2018-07-23 17:20 |  |  |  |  | 2018-07-23 20:00 | Yes | -7
VD-9001-204C-DWG-009 | 1 | NAME PLATE DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-29 20:00 | 2018-07-16 21:24 | 2018-07-16 21:24 | Yes | 78 |  |  | 2018-07-18 10:00 | [5 empty] | 2018-07-18 19:59 | Yes | -12 | 1204-Owner-v | 2018-12-16 21:53
VD-9001-307A-PCJ-020 | 0 | Hardness Test Procedure - common | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCJ-021 | 0 | Painting Procedure (Turbine) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCJ-022 | 0 | Painting Procedure (Seal System) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-BOL-001 | 0 | Bill of Lading | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCJ-017 | 0 | Balancing procedure for rotor, impeller, shaft and etc. | MC-307A | KSB GERMANY | 2018-04-20 | 2018-04-27 13:25 | 2018-04-27 13:25 | Yes | 7 |  |  | 2018-05-01 16:01 | [5 empty] | 2018-05-01 20:00 | Yes | -10
VD-9001-307A-DSH-104 | 0 | ARC valve datasheet | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DSH-105 | 0 | Condensate Pump (Data Sheet Pump) FOR P-4005A | MC-307A | KSB GERMANY | 2018-06-29 | 2018-09-10 12:54 | 2018-09-10 12:54 | Yes | 73 |  |  |  | 2018-09-26 09:59 |  |  |  |  | 2018-09-26 18:58 | Yes | 2
VD-9001-307A-DSH-106 | 0 | Condensate Pump (Data Sheet Pump) FOR P-4005B | MC-307A | KSB GERMANY | 2018-06-29 | 2018-09-10 12:54 | 2018-09-10 12:54 | Yes | 73 |  |  |  | 2018-09-26 09:59 |  |  |  |  | 2018-09-26 18:58 | Yes | 2 | 1204-Owner-v | 2018-10-31 16:10
VD-9001-307A-PCU-032 | 0 | Condensate Pump Performance Curve) FOR P-4005A | MC-307A | KSB GERMANY | 2018-06-29 | 2018-09-10 12:55 | 2018-09-10 12:55 | Yes | 73 |  |  |  | 2018-09-26 10:06 |  |  |  |  | 2018-09-26 18:58 | Yes | 2
VD-9001-307A-PCU-033 | 0 | Condensate Pump (Performance Curve) FOR P-4005B | MC-307A | KSB GERMANY | 2018-06-29 | 2018-09-10 12:55 | 2018-09-10 12:55 | Yes | 73 |  |  |  | 2018-09-26 10:07 |  |  |  |  | 2018-09-26 18:58 | Yes | 2
VD-9001-307A-DWG-200 | 0 | Condensate Pump (Nameplate Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-201 | 0 | Condensate Pump (Nameplate Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-202 | 0 | Condensate Pump (General Arrangement Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-203 | 0 | Condensate Pump (General Arrangement Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-099 | 0 | Condensate Pump (P&I Diagram) FOR P-4005A | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DIG-100 | 0 | Condensate Pump (P&I Diagram) FOR P-4005B | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-204 | 0 | Condensate Pump (Cross Sectional Drawing incl. BOM) FOR P-4005A | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-DWG-205 | 0 | Condensate Pump (Cross Sectional Drawing incl. BOM) FOR P-4005B | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-ITP-015 | 0 | Condensate Pump (Inspection & Test Plan) FOR P-4005A | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-ITP-016 | 0 | Condensate Pump (Inspection & Test Plan) FOR P-4005B | MC-307A | KSB GERMANY | 2018-07-13 |  |  | No | 707 | [9 empty] | No | 0
VD-9001-307A-CER-006 | 0 | Condensate Pump (Certificate of Conformity) FOR P-4005A | MC-307A | KSB GERMANY | 2018-09-21 |  |  | No | 637 | [9 empty] | No | 0
VD-9001-307A-CER-007 | 0 | Condensate Pump (Certificate of Conformity) FOR P-4005B | MC-307A | KSB GERMANY | 2018-09-21 |  |  | No | 637 | [9 empty] | No | 0
VD-9001-307A-DWG-206 | 0 | Condensate Pump (Mechanical Seal Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-207 | 0 | Condensate Pump (Mechanical Seal Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-208 | 0 | Condensate Pump (Coupling Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-209 | 0 | Condensate Pump (Coupling Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DSH-107 | 0 | Condensate Pump (Data Sheet Motor) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DSH-108 | 0 | Condensate Pump (Data Sheet Motor) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-PCU-034 | 0 | Condensate Pump (Motor Curve) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-PCU-035 | 0 | Condensate Pump (Motor Curve) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-210 | 0 | Condensate Pump (Motor Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-211 | 0 | Condensate Pump (Motor Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-212 | 0 | Condensate Pump (Wiring Diagram) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-213 | 0 | Condensate Pump (Wiring Diagram) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-214 | 0 | Condensate Pump (Terminal Box Drawing) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-DWG-215 | 0 | Condensate Pump (Terminal Box Drawing) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-ITP-017 | 0 | Condensate Pump (Inspection Test Plan Motor) FOR P-4005A | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-ITP-018 | 0 | Condensate Pump (Inspection Test Plan Motor) FOR P-4005B | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-MDB-011 | 0 | Condensate Pump (MDR) FOR P-4005A | MC-307A | KSB GERMANY | 2019-02-22 |  |  | No | 483 | [9 empty] | No | 0
VD-9001-307A-MDB-012 | 0 | Condensate Pump (MDR) FOR P-4005B | MC-307A | KSB GERMANY | 2019-02-22 |  |  | No | 483 | [9 empty] | No | 0
VD-9001-307A-DSH-086 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-09-29 10:46 |  |  |  |  | 2018-09-29 18:58 | Yes | -6
VD-9001-307A-DSH-087 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-10-03 08:57 |  |  |  |  | 2018-10-03 18:57 | Yes | -2
VD-9001-307A-DSH-088 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-09-29 11:02 |  |  |  |  | 2018-09-29 18:58 | Yes | -6
VD-9001-307A-DSH-089 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-09-29 10:44 |  |  |  |  | 2018-09-29 18:58 | Yes | -6
VD-9001-307A-DSH-090 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-09-29 10:53 |  |  |  |  | 2018-09-29 18:58 | Yes | -6
VD-9001-307A-DSH-091 | 0 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:38 | 2018-09-21 16:38 | Yes | 119 |  |  |  | 2018-09-29 10:58 |  |  |  |  | 2018-09-29 18:58 | Yes | -6
VD-9001-307A-DWG-171 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:45 | 2018-05-16 08:45 |  | Yes | 0
VD-9001-307A-DWG-172 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:44 | 2018-05-16 08:44 |  | Yes | 0
VD-9001-307A-DWG-173 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:43 | 2018-05-16 08:43 |  | Yes | 0
VD-9001-307A-DWG-174 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:42 | 2018-05-16 08:42 |  | Yes | 0
VD-9001-307A-DWG-175 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:41 | 2018-05-16 08:41 |  | Yes | 0
VD-9001-307A-DWG-176 | 0 | Lube oil unit (Drawings) | MC-307A | KSB GERMANY | 2018-04-16 |  | 2018-04-18 13:35 | Yes | 795 | [6 empty] | 2018-05-16 08:39 | 2018-05-16 08:39 |  | Yes | 0
VD-9001-307A-DIG-087 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-05-24 18:31 | 2018-05-24 18:31 | Yes | -1 |  |  |  | 2018-07-22 15:55 |  |  |  |  | 2018-07-22 20:00 | Yes | 45
VD-9001-307A-DIG-088 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-089 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-090 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-091 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-092 | 0 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-092 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-093 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-094 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-095 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-096 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-097 | 0 | Lube oil unit (Instrument Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-177 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-178 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-179 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-180 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-181 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-182 | 0 | Lube oil unit (Instrument GAD) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-098 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:39 | 2018-09-21 16:40 | Yes | 119 |  |  |  |  | 2018-09-24 15:12 |  |  |  | 2018-09-24 18:58 | Yes | -11
VD-9001-307A-DSH-099 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:39 | 2018-09-21 16:40 | Yes | 119 |  |  |  |  | 2018-09-24 15:11 |  |  |  | 2018-09-24 18:58 | Yes | -11 | 1204-Owner-v | 2018-10-02 12:54
VD-9001-307A-DSH-100 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DSH-101 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:39 | 2018-09-21 16:40 | Yes | 119 |  |  |  |  | 2018-09-24 15:08 |  |  |  | 2018-09-24 18:58 | Yes | -11 | 1204-Owner-v | 2018-10-02 12:57
VD-9001-307A-DSH-102 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:39 | 2018-09-21 16:40 | Yes | 119 |  |  |  |  | 2018-09-24 15:06 |  |  |  | 2018-09-24 18:58 | Yes | -11 | 1204-Owner-v | 2018-10-02 12:59
VD-9001-307A-DSH-103 | 0 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-05-25 | 2018-09-21 16:39 | 2018-09-21 16:40 | Yes | 119 |  |  |  | 2018-09-24 15:03 | 2018-09-24 15:04 |  |  |  | 2018-09-24 18:58 | Yes | -11
VD-9001-307A-PCU-026 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCU-027 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCU-028 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCU-029 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCU-030 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCU-031 | 0 | Lube oil unit (Motor Curve) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-183 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-184 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-185 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-186 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-187 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-188 | 0 | Lube oil unit (Motor Drawing & Terminal Box DWG) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-093 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-094 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-095 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-096 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-097 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DIG-098 | 0 | Lube oil unit (Motor Wiring Diagram) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-189 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-190 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-191 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-192 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-193 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-194 | 0 | Lube oil unit (Nameplate) | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-DWG-195 | 0 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-07-27 | 2018-11-22 15:47 | 2018-11-22 15:48 | Yes | 118 |  |  |  | 2018-11-27 09:23 |  |  |  |  | 2018-11-27 19:59 | Yes | -9
VD-9001-307A-DWG-196 | 0 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-07-27 | 2018-11-22 15:47 | 2018-11-22 15:48 | Yes | 118 |  |  |  | 2018-11-27 09:22 |  |  |  |  | 2018-11-27 19:59 | Yes | -9
VD-9001-307A-DWG-197 | 0 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-07-27 | 2018-11-22 15:48 | 2018-11-22 15:48 | Yes | 118 |  |  |  | 2018-11-27 09:24 |  |  |  |  | 2018-11-27 20:00 | Yes | -9
VD-9001-307A-DWG-198 | 0 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-07-27 | 2018-11-22 15:48 | 2018-11-22 15:48 | Yes | 118 |  |  |  | 2018-11-27 09:25 |  |  |  |  | 2018-11-27 20:00 | Yes | -9
VD-9001-307A-DWG-199 | 0 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-07-27 | 2018-11-22 15:48 | 2018-11-22 15:48 | Yes | 118 |  |  |  | 2018-11-27 09:27 |  |  |  |  | 2018-11-27 20:00 | Yes | -9
VD-9001-307A-CAT-003 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-004 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-005 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-006 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-007 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-008 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-009 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-010 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-011 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-CAT-012 | 0 | Catalogue and brochures total Unit | MC-307A | KSB GERMANY | 2018-09-28 |  |  | No | 630 | [9 empty] | No | 0
VD-9001-307A-LST-052 | 0 | Detailed packing list | MC-307A | KSB GERMANY | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-307A-LST-053 | 0 | Master packing list | MC-307A | KSB GERMANY | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-307A-LST-054 | 0 | Filled SPIR list | MC-307A | KSB GERMANY | 2018-11-28 | 2018-10-24 12:38 | 2018-10-24 12:38 | Yes | -35 |  |  |  | 2018-11-05 08:40 |  |  |  |  | 2018-11-05 20:00 | Yes | -2 | 1204-Owner-v | 2019-02-16 10:34
VD-9001-307A-DPR-001 | 0 | 3D Model of package (Main Components) | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-PCJ-010 | 0 | Start up and shutdown sequence for Turbine Driven Pumps | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-DIG-086 | 0 | Cause and effect diagram | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-ARP-001 | 0 | Torsional analysis | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-ARP-002 | 0 | Lateral analysis | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-ARP-003 | 0 | Torsional report for whole train | MC-307A | KSB GERMANY | 2018-10-12 |  |  | No | 616 | [9 empty] | No | 0
VD-9001-307A-PCJ-011 | 0 | Performance test procedure | MC-307A | KSB GERMANY | 2018-05-18 |  |  | No | 763 | [9 empty] | No | 0
VD-9001-307A-PCJ-012 | 0 | Shopacceptance test procedure | MC-307A | KSB GERMANY | 2018-05-18 | 2018-05-18 16:35 | 2018-05-18 16:39 | Yes | 0 |  |  |  | 2018-06-17 14:07 |  |  |  |  | 2018-06-17 20:00 | Yes | 16
VD-9001-307A-PCJ-013 | 0 | Run test Porcedure | MC-307A | KSB GERMANY | 2018-05-18 |  |  | No | 763 | [9 empty] | No | 0
VD-9001-307A-PCJ-014 | 0 | Heat treatmant Procedure | MC-307A | KSB GERMANY | 2018-05-18 | 2018-05-18 16:35 | 2018-05-18 16:39 | Yes | 0 |  |  |  |  | 2018-06-17 14:13 |  |  |  | 2018-06-17 20:00 | Yes | 16
VD-9001-307A-PCJ-015 | 0 | Long term preservation procedure | MC-307A | KSB GERMANY | 2018-05-18 | 2018-05-18 16:35 | 2018-05-18 16:39 | Yes | 0 |  |  |  | 2018-06-19 10:57 |  |  |  |  | 2018-06-19 20:00 | Yes | 18
VD-9001-307A-PCJ-016 | 0 | Rotor Balance report (pump and turbine) | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-PCJ-018 | 0 | Mechanical run test procedure for pump and turbines | MC-307A | KSB GERMANY | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-307A-PCJ-019 | 0 | Electrical motors routine test procedure | MC-307A | KSB GERMANY | 2018-05-18 |  |  | No | 763 | [9 empty] | No | 0
VD-9001-307A-SPE-011 | 0 | Control system description, Operating principles, Functional design specification | MC-307A | KSB GERMANY | 2018-08-24 |  |  | No | 665 | [9 empty] | No | 0
VD-9001-307A-CER-005 | 0 | Ex. Certificate of conformity for all Ex. Type electrical equipment | MC-307A | KSB GERMANY | 2018-09-21 |  |  | No | 637 | [9 empty] | No | 0
VD-9001-307A-PCU-021 | 0 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-06-22 | 2018-06-14 14:37 | 2018-06-14 14:41 | Yes | -8 |  |  |  | 2018-07-02 09:25 |  |  |  |  | 2018-07-02 20:00 | Yes | 4
VD-9001-307A-PCU-022 | 0 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-06-22 | 2018-06-14 14:37 | 2018-06-14 14:41 | Yes | -8 |  |  |  | 2018-07-02 09:49 |  |  |  |  | 2018-07-02 20:00 | Yes | 4
VD-9001-307A-PCU-023 | 0 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-06-22 | 2018-09-28 13:28 | 2018-09-28 13:29 | Yes | 98 |  |  |  | 2018-10-07 15:28 |  |  |  |  | 2018-10-07 18:58 | Yes | -5
VD-9001-307A-PCU-024 | 0 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-06-22 | 2018-06-14 14:37 | 2018-06-14 14:41 | Yes | -8 |  |  |  | 2018-06-30 09:26 |  |  |  |  | 2018-06-30 20:00 | Yes | 2
VD-9001-307A-PCU-025 | 0 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-06-22 | 2018-06-14 14:37 | 2018-06-14 14:41 | Yes | -8 |  |  |  | 2018-06-30 09:29 |  |  |  |  | 2018-06-30 20:00 | Yes | 2
VD-9001-307A-DWG-216 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 | 2018-09-07 16:55 | 2018-09-07 16:55 | Yes | 70 |  |  |  | 2018-09-29 10:37 |  |  |  |  | 2018-09-29 18:58 | Yes | 8
VD-9001-307A-DWG-217 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-218 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-219 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-220 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-221 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-222 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-223 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-224 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-DWG-225 | 0 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-06-29 |  |  | No | 721 | [9 empty] | No | 0
VD-9001-307A-PCJ-023 | 0 | Painting Procedure ( Motor ) | MC-307A | KSB GERMANY | 2018-04-20 |  |  | No | 791 | [9 empty] | No | 0
VD-9001-104(004)-PID-007 | 1 | C-6102 -PID oil system | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-204C-DWG-005 | 1 | FIREPROOFING DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-04-30 20:00 | 2018-07-16 21:21 | 2018-07-16 21:21 | Yes | 77 |  |  |  | 2018-07-18 14:38 |  |  |  |  | 2018-07-18 19:59 | Yes | -12
VD-9001-307A-DSH-027 | 1 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-04-30 20:00 | 2018-05-29 10:50 | 2018-05-29 10:54 | Yes | 29 |  |  |  | 2018-06-17 15:01 |  |  |  |  | 2018-06-17 20:00 | Yes | 5
VD-9001-307A-DSH-026 | 1 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-04-30 20:00 | 2018-05-29 10:50 | 2018-05-29 10:54 | Yes | 29 |  |  |  | 2018-06-17 15:03 |  |  |  |  | 2018-06-17 20:00 | Yes | 5
VD-9001-307A-ITP-012 | 1 | Inspection Test Plan (Motor) | MC-307A | KSB GERMANY | 2018-04-30 20:00 | 2018-05-24 18:32 | 2018-05-24 18:32 | Yes | 24 |  |  | 2018-06-30 09:38 | [5 empty] | 2018-06-30 20:00 | Yes | 23 | 1204-Owner-v | 2018-10-13 09:50
VD-9001-104(004)-PID-009 | 1 | C-6102 -PID Cooling water | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-104(004)-PID-006 | 1 | C-6102 -PID process | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-104-LST-012 | 2 | Consumers list | PR-104 | AIR LIQUIDE | 2018-04-30 20:00 | 2018-06-07 18:33 | 2018-06-07 18:36 | Yes | 38 |  |  |  | 2018-07-15 17:31 |  |  |  |  | 2018-07-15 20:00 | Yes | 24
VD-9001-104(008)-PCU-001 | 1 | AE-6187 - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-104(004)-PID-005 | 1 | C-6101 -PID Cooling water | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-104(003)-IPM-001 | 1 | T-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-04-30 20:00 | 2018-05-22 13:13 | 2018-05-22 13:14 | Yes | 22 |  |  |  | 2018-06-18 09:09 |  |  |  |  | 2018-06-18 20:00 | Yes | 13
VD-9001-201-DWG-006 | 3 | INTERNAL MISCELLANEOUS DETAILS | PV-201 | ATB RIVA CALZONI SpA | 2018-04-24 | 2018-04-17 13:53 | 2018-04-17 13:56 | Yes | -7 |  |  | 2018-06-09 16:52 | [5 empty] | 2018-06-09 16:52 | Yes | 39 | 1204-Owner-v | 2019-09-05 11:42
VD-9001-251-DWG-106 | 1 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-04-24 | 2018-05-23 17:11 | 2018-05-23 17:13 | Yes | 29 |  |  |  |  | 2018-06-12 10:04 |  |  |  | 2018-06-12 10:04 | Yes | 6
VD-9001-251-DWG-107 | 1 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-04-24 | 2018-05-23 17:24 | 2018-05-23 17:35 | Yes | 29 |  |  |  |  | 2018-06-12 10:07 |  |  |  | 2018-06-12 10:07 | Yes | 6
VD-9001-251-DWG-022 | 1 | MAIN HEADER (TRANSFERLINE) DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-04-27 | 2019-06-12 10:59 | 2019-06-12 10:59 | Yes | 411 |  |  | 2019-07-03 15:29 | [5 empty] | 2019-07-03 15:29 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-023 | 1 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-27 | 2019-06-12 11:00 | 2019-06-12 11:00 | Yes | 411 |  |  |  | 2019-07-03 15:47 |  |  |  |  | 2019-07-03 15:47 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-024 | 1 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-26 | 2019-06-12 11:00 | 2019-06-12 11:00 | Yes | 412 |  |  | 2019-07-03 15:50 | [5 empty] | 2019-07-03 15:50 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-025 | 1 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-27 | 2018-08-31 13:26 | 2018-08-31 13:30 | Yes | 126 |  |  | 2018-09-17 11:49 | [5 empty] | 2018-09-17 11:49 | Yes | 3
VD-9001-254-DWG-456 | 2 | ERECTION DWG. FOR NAME PLATE OF BOILER | HM-254 | AZAR AB | 2018-04-22 | 2018-12-25 15:45 | 2018-12-25 15:46 | Yes | 247 |  |  | 2019-01-02 10:56 | [5 empty] | 2019-01-02 10:56 | Yes | -6
VD-9001-104-REQ-045 | 1 | PCV - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-05-01 20:00 |  | 2018-05-31 14:58 | Yes | 780 | [6 empty] | 2018-06-02 09:02 | 2018-06-02 09:02 |  | Yes | 0
VD-9001-104(004)-DSH-001 | 1 | C-6101 / C-6102 - Process cooler 1 - data sheet | PR-104-SUB | AIR LIQUIDE | 2018-05-01 20:00 |  |  | No | 780 | [9 empty] | No | 0
VD-9001-307A-DWG-077 | 1 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-30 09:30 | 2018-05-30 09:33 | Yes | 29 |  |  | 2018-06-18 10:52 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-10-27 13:07
VD-9001-307A-DWG-076 | 1 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-30 09:30 | 2018-05-30 09:32 | Yes | 29 |  |  | 2018-06-18 10:54 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-10-27 13:06
VD-9001-307A-DWG-072 | 1 | Motor Drawing | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-30 09:30 | 2018-05-30 09:32 | Yes | 29 |  |  | 2018-06-18 11:01 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-06-18 09:52
VD-9001-307A-PCU-014 | 1 | Motor Curves | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 11:05 | 2018-05-29 11:09 | Yes | 28 |  |  | 2018-06-18 10:38 | [5 empty] | 2018-06-18 20:00 | Yes | 6
VD-9001-307A-PCU-015 | 1 | Motor Curves | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 11:07 | 2018-05-29 11:09 | Yes | 28 |  |  | 2018-06-18 10:35 | [5 empty] | 2018-06-18 20:00 | Yes | 6
VD-9001-307A-PCU-013 | 1 | Motor Curves | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 11:04 | 2018-05-29 11:08 | Yes | 28 |  |  | 2018-06-18 10:41 | [5 empty] | 2018-06-18 20:00 | Yes | 6
VD-9001-307A-PCU-012 | 1 | Motor Curves | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 11:03 | 2018-05-29 11:08 | Yes | 28 |  |  | 2018-06-18 10:47 | [5 empty] | 2018-06-18 20:00 | Yes | 6
VD-9001-307A-PCU-011 | 1 | Motor Curves | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 11:02 | 2018-05-29 11:08 | Yes | 28 |  |  | 2018-06-18 10:48 | [5 empty] | 2018-06-18 20:00 | Yes | 6
VD-9001-307A-DSH-029 | 1 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 10:52 | 2018-05-29 10:55 | Yes | 28 |  |  |  | 2018-06-17 14:57 |  |  |  |  | 2018-06-17 20:00 | Yes | 5
VD-9001-307A-DSH-030 | 1 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 10:53 | 2018-05-29 10:55 | Yes | 28 |  |  |  | 2018-06-17 14:51 |  |  |  |  | 2018-06-17 20:00 | Yes | 5
VD-9001-307A-DSH-028 | 1 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-05-01 20:00 | 2018-05-29 10:51 | 2018-05-29 10:55 | Yes | 28 |  |  |  | 2018-06-17 15:00 |  |  |  |  | 2018-06-17 20:00 | Yes | 5
VD-9001-104-REQ-038 | 3 | Cryogenic JT globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-104-REQ-037 | 2 | Cryogenic Butterfly automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-104-REQ-036 | 3 | Cryogenic Globe automatic valves - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-104(008)-LST-002 | 1 | AE-6187 - Equipment list | PR-104-SUB | AIR LIQUIDE | 2018-04-24 |  |  | No | 787 | [9 empty] | No | 0
VD-9001-461AF-ITP-001 | 1 | INSPECTION TEST PLAN | PI-461AF | Van Leeuwen | 2018-05-02 10:10 | 2018-08-16 12:02 | 2018-08-16 12:05 | Yes | 106 |  |  | 2018-08-18 08:30 | [5 empty] | 2018-08-18 08:30 | Yes | -12
VD-9001-461AF-INX-001 | 1 | FINAL DATA BOOK INDEX | PI-461AF | Van Leeuwen | 2018-05-02 10:40 | 2018-06-01 16:57 | 2018-06-01 16:58 | Yes | 30 |  |  |  | 2018-06-11 14:22 |  |  |  |  | 2018-06-11 14:23 | Yes | -4
VD-9001-104(017)-DWG-001 | 0 | FT-6101 / FT-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-25 | 2018-04-30 21:02 | 2018-04-30 21:08 | Yes | 5 |  |  |  | 2018-05-19 11:43 |  |  |  |  | 2018-05-19 19:59 | Yes | 5
VD-9001-104(017)-DWG-002 | 0 | FT-6101 / FT-6102 - Civil work drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-05-09 | 2018-04-30 20:50 | 2018-04-30 20:56 | Yes | -9 |  |  |  | 2018-05-16 17:46 |  |  |  |  | 2018-05-16 20:00 | Yes | 2
VD-9001-104(017)-ITP-001 | 0 | FT-6101 / FT-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-04-25 | 2018-04-30 21:02 | 2018-04-30 21:09 | Yes | 5 |  |  |  | 2018-05-14 08:38 |  |  |  |  | 2018-05-14 19:59 | Yes | 0 | 1204-Owner-v | 2018-05-12 16:45
VD-9001-201-PCJ-003 | 1 | BOLT TIGHTENING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2018-04-23 | 2018-05-25 19:02 | 2018-05-25 19:02 | Yes | 32 |  |  | 2018-05-27 15:35 | [5 empty] | 2018-05-27 15:35 | Yes | -12 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-201-PCJ-004 | 1 | DOUBLE CONE INSTALLATION PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2018-04-23 | 2018-05-25 19:03 | 2018-05-25 19:03 | Yes | 32 |  |  | 2018-06-19 16:30 | [5 empty] | 2018-06-19 16:30 | Yes | 11 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-206B-INX-023 | 1 | FINAL VENDOR DATA BOOK INDEX | PV-206B | TASHA | 2018-04-25 | 2018-09-02 14:05 | 2018-09-02 14:05 | Yes | 130 |  |  | 2018-09-24 14:45 | [5 empty] | 2018-09-24 14:45 | Yes | 8
VD-9001-257C-DWG-013 | 1 | DETAILS DRAWING (4137-0366/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-02 | 2018-05-21 13:53 | 2018-05-21 13:53 | Yes | 19 |  |  | 2018-07-21 20:24 | [5 empty] | 2018-07-21 20:24 | Yes | 47 | 1204-Owner-v | 2018-07-08 14:18
VD-9001-257C-DWG-019 | 1 | DETAILS DRAWING (4137-0367/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-30 | 2018-05-21 14:13 | 2018-05-21 14:13 | Yes | 21 |  |  | 2018-07-21 20:27 | [5 empty] | 2018-07-21 20:27 | Yes | 47 | 1204-Owner-v | 2018-12-10 10:58
VD-9001-202F-PCJ-007 | 1 | Waste Heat Boiler - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-25 | 2018-04-26 20:09 | 2018-04-26 20:14 | Yes | 1 |  |  | 2018-05-12 11:11 | [5 empty] | 2018-05-12 11:11 | Yes | 2 | 1204-Owner-v | 2020-04-29 09:58
VD-9001-202F-PCJ-010 | 1 | Waste Heat Boiler - Procedure for Magnetic Particle Examination (MT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-25 | 2018-04-26 20:18 | 2018-04-26 20:21 | Yes | 1 |  |  | 2018-05-12 11:22 | [5 empty] | 2018-05-12 11:22 | Yes | 2 | 1204-Owner-v | 2020-04-29 10:01
VD-9001-202F-PCJ-013 | 1 | Waste Heat Boiler - Positive Material Identification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-25 | 2018-04-26 20:34 | 2018-04-26 21:35 | Yes | 1 |  |  | 2018-05-12 11:24 | [5 empty] | 2018-05-12 11:24 | Yes | 2 | 1204-Owner-v | 2020-04-29 10:03
VD-9001-202F-PCJ-020 | 1 | Waste Heat Boiler - Procedure for Leak Testing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-25 | 2018-04-27 14:40 | 2018-04-27 15:36 | Yes | 2 |  |  | 2018-05-12 12:01 | [5 empty] | 2018-05-12 12:01 | Yes | 1 | 1204-Owner-v | 2019-01-21 13:56
VD-9001-202F-PCJ-022 | 1 | Waste Heat Boiler - Procedure for Liquid Penetrant Examination (PT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-28 | 2018-04-27 16:11 | 2018-04-27 16:57 | Yes | -1 |  |  | 2018-05-12 14:44 | [5 empty] | 2018-05-12 14:44 | Yes | 1 | 1204-Owner-v | 2020-04-29 10:10
VD-9001-202F-PCJ-024 | 1 | Waste Heat Boiler - Procedure for Visual Examination (VT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-28 | 2018-04-27 15:55 | 2018-04-27 16:10 | Yes | -1 |  |  | 2018-05-12 14:30 | [5 empty] | 2018-05-12 14:30 | Yes | 1 | 1204-Owner-v | 2020-04-29 10:11
VD-9001-202F-PCJ-021 | 1 | Waste Heat Boiler - Procedure for Radiographic Examination of Welds (RT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-28 | 2018-04-27 15:37 | 2018-04-27 15:52 | Yes | -1 |  |  | 2018-05-12 14:20 | [5 empty] | 2018-05-12 14:20 | Yes | 1 | 1204-Owner-v | 2020-04-29 10:09
VD-9001-202F-PCJ-014 | 1 | Waste Heat Boiler - Production Weld Test Coupons Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 | 2018-04-26 21:36 | 2018-04-26 21:54 | Yes | -4 |  |  | 2018-05-12 11:30 | [5 empty] | 2018-05-12 11:30 | Yes | 2
VD-9001-202F-PCJ-012 | 1 | Waste Heat Boiler - TOFD Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-28 | 2018-04-26 20:16 | 2018-04-26 20:17 | Yes | -2 |  |  | 2018-05-12 11:13 | [5 empty] | 2018-05-12 11:13 | Yes | 2 | 1204-Owner-v | 2019-05-11 08:44
VD-9001-202F-PCJ-023 | 1 | Waste Heat Boiler - Procedure for Ultrasonic Testing of Welds (UT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-30 | 2018-04-27 15:55 | 2018-04-27 16:09 | Yes | -3 |  |  | 2018-05-12 14:23 | [5 empty] | 2018-05-12 14:23 | Yes | 1 | 1204-Owner-v | 2020-04-29 10:10
VD-9001-202F-INX-004 | 1 | Waste Heat Boiler - Quality Record Book Index | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-04-25 | 2018-04-26 22:15 | 2018-04-26 22:17 | Yes | 1 |  |  | 2018-05-17 12:09 | [5 empty] | 2018-05-17 12:09 | Yes | 7 | 1204-Owner-v | 2020-04-29 09:30
VD-9001-104-REQ-033 | 1 | Flowmeter - TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-05-02 20:00 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-307A-DWG-075 | 1 | Motor Drawing | MC-307A | KSB GERMANY | 2018-05-02 20:00 | 2018-05-30 09:30 | 2018-05-30 09:32 | Yes | 28 |  |  | 2018-06-18 10:55 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-06-18 10:03
VD-9001-104(004)-ITP-001 | 2 | C-6101 / C-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-02 20:00 |  |  | No | 779 | [9 empty] | No | 0
VD-9001-204D-PCJ-026 | 1 | PWHT PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-02 20:00 | 2018-05-08 13:06 | 2018-05-08 13:09 | Yes | 6 |  |  | 2018-05-14 16:06 | [5 empty] | 2018-05-14 20:00 | Yes | -8
VD-9001-204D-DSH-030 | 1 | PROCESS/MECHANICAL DATA SHEET | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-02 20:00 | 2018-07-02 17:05 | 2018-07-02 17:07 | Yes | 61 |  |  |  | 2018-07-22 17:40 |  |  |  |  | 2018-07-22 17:40 | Yes | 6
VD-9001-204D-INR-028 | 3 | CERTIFICATION DOSSIER INDEX | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-02 20:00 | 2018-04-19 18:56 | 2018-04-19 18:56 | Yes | -13 |  |  | 2018-04-21 09:16 | [5 empty] | 2018-04-21 20:00 | Yes | -12
VD-9001-204D-DWG-009 | 1 | NAME PLATE DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-02 20:00 | 2018-06-12 16:49 | 2018-06-12 16:49 | Yes | 41 |  |  |  | 2018-07-17 12:12 |  |  |  |  | 2018-07-17 12:12 | Yes | 21
VD-9001-104-REQ-053 | 0 | S-6101Common Silencer - TRS Technical Requisition Sheet PU-6101_S-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-054 | 0 | Manual Butterfly valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-055 | 0 | Special Butterfly valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-056 | 0 | Globe valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-057 | 0 | Gate valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-058 | 0 | Manual Ball valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-059 | 0 | Duo Check valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-REQ-060 | 0 | Piston check valves - TRS Technical Requisition Sheet PU-6101 | PR-104 | AIR LIQUIDE | 2018-04-01 |  |  | No | 810 | [9 empty] | No | 0
VD-9001-104-LST-015 | 0 | List of Elements Important for Safety (EIS) PU-6101 | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104-PPL-009 | 0 | Preliminary Layout for Control Room PU-6101 | PR-104 | AIR LIQUIDE | 2018-08-01 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-104(010)-ITP-001 | 1 | Warm automatic 3-lever valve - Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-03 20:00 |  |  | No | 778 | [9 empty] | No | 0
VD-9001-104(004)-ITP-003 | 2 | ST C-6101/ST C-6102 - Inspection Test Plan / Quality Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-03 20:00 |  |  | No | 778 | [9 empty] | No | 0
VD-9001-104(004)-ITP-004 | 1 | ST C-6102 - Inspection Test Plan / Quality Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-03 20:00 |  |  | No | 778 | [9 empty] | No | 0
VD-9001-257C-PCJ-001 | 1 | HYDROSTATIC PROCEDURE (4137/HT) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-28 | 2018-06-05 14:06 | 2018-06-05 14:07 | Yes | 38 |  |  | 2018-07-17 11:00 | [5 empty] | 2018-07-17 11:00 | Yes | 28 | 1204-Owner-v | 2019-10-05 15:21
VD-9001-257C-PCJ-002 | 1 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-28 | 2018-06-05 15:16 | 2018-06-05 16:08 | Yes | 38 |  |  | 2018-07-17 11:03 | [5 empty] | 2018-07-17 11:03 | Yes | 28 | 1204-Owner-v | 2019-01-30 16:51
VD-9001-251-DWG-027 | 1 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-04-21 12:18 | 2018-04-23 11:17 | 2018-04-23 11:31 | Yes | 2 |  |  |  | 2018-04-26 12:58 |  |  |  |  | 2018-04-26 12:58 | Yes | -11 | 1204-Owner-v | 2018-04-24 16:47
VD-9001-257C-CAL-011 | 1 | FINITE ELEMENT ANALYSIS (4137-0366/FEA) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-30 | 2018-05-21 14:04 | 2018-05-21 14:04 | Yes | 21 |  |  | 2018-09-15 14:58 | [5 empty] | 2018-09-15 14:58 | Yes | 103 | 1204-Owner-v | 2020-05-26 17:15
VD-9001-204D-PCJ-035 | 1 | PRESERVATION PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-05 20:00 | 2018-08-02 18:53 | 2018-08-02 18:53 | Yes | 89 |  |  | 2018-09-15 09:30 | [5 empty] | 2018-09-15 09:30 | Yes | 30 | 1204-Owner-v | 2019-04-06 14:47
VD-9001-204D-DWG-011 | 1 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-05 20:00 | 2018-06-12 16:53 | 2018-06-12 16:53 | Yes | 38 |  |  |  | 2018-07-21 09:59 |  |  |  |  | 2018-07-21 09:59 | Yes | 25
VD-9001-204D-DWG-037 | 1 | STEAM DRUM D-2003 / INSULATION SUPPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-05 20:00 | 2018-06-12 16:52 | 2018-06-12 16:54 | Yes | 38 |  |  | 2018-07-17 14:40 | [5 empty] | 2018-07-17 14:40 | Yes | 21 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-104(008)-ITP-001 | 1 | AE-6187 - Inspection and Test Plan - General | PR-104-SUB | AIR LIQUIDE | 2018-05-05 20:00 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-104(004)-IPM-012 | 1 | ST C-6101/ST C-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-05 20:00 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-104(014)-ITP-001 | 1 | E-6108/E-6108-D1 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-05 20:00 | 2018-05-28 14:05 | 2018-05-28 14:14 | Yes | 23 |  |  | 2018-06-18 09:12 | [5 empty] | 2018-06-18 20:00 | Yes | 7 | 1204-Owner-v | 2020-01-01 09:58
VD-9001-104(010)-IPM-001 | 1 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-28 |  |  | No | 783 | [9 empty] | No | 0
VD-9001-104(008)-DWG-013 | 1 | D-6188 - Condensate tank - detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-28 |  |  | No | 783 | [9 empty] | No | 0
VD-9001-104(008)-DWG-010 | 1 | D-6188 - Condensate tank drawing | PR-104-SUB | AIR LIQUIDE | 2018-04-28 |  |  | No | 783 | [9 empty] | No | 0
VD-9001-204D-GAD-002 | 2 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-04-28 | 2018-06-12 15:14 | 2018-06-12 15:15 | Yes | 45 |  |  |  | 2018-07-22 17:59 |  |  |  |  | 2018-07-22 17:59 | Yes | 26
VD-9001-204D-CAL-013 | 2 | MECHANICAL CODE CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-04-28 | 2018-06-29 19:00 | 2018-06-29 19:01 | Yes | 62 |  |  |  |  | 2018-06-30 14:49 |  |  |  | 2018-06-30 20:00 | Yes | -13
VD-9001-104-PID-005 | 2 | Instrumentation detail diagram | PR-104 | AIR LIQUIDE | 2018-04-28 |  |  | No | 783 | [9 empty] | No | 0
VD-9001-257C-INX-001 | 1 | MANUFACTURER DATA REPORT INDEX (4137/ED) | HM-257C | Brembana & Rolle S.p.A. | 2018-04-30 | 2018-06-05 13:54 | 2018-06-05 13:57 | Yes | 36 |  |  |  |  | 2018-07-17 11:09 |  |  |  | 2018-07-17 11:09 | Yes | 28
VD-9001-204C-DWG-004 | 2 | DETAILS DWG. With Nozzle Details | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-06 20:00 | 2018-07-16 21:10 | 2018-07-16 21:16 | Yes | 71 |  |  |  | 2018-07-24 10:33 |  |  |  |  | 2018-07-24 19:59 | Yes | -6 | 1204-Owner-v | 2019-01-20 15:41
VD-9001-204D-DWG-004 | 2 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-06 20:00 | 2018-06-12 16:46 | 2018-06-12 16:46 | Yes | 37 |  |  |  | 2018-07-22 17:40 |  |  |  |  | 2018-07-22 17:40 | Yes | 26
VD-9001-204D-DWG-003 | 2 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-06 20:00 | 2018-06-12 15:23 | 2018-06-12 16:54 | Yes | 37 |  |  |  | 2018-07-22 17:41 |  |  |  |  | 2018-07-22 17:41 | Yes | 26
VD-9001-104-DSH-033 | 1 | Flowmeter - EDS Equipment Data Sheet (flow orifice) | PR-104 | AIR LIQUIDE | 2018-05-06 20:00 |  |  | No | 775 | [9 empty] | No | 0
VD-9001-104(008)-ITP-011 | 1 | AE-6187 - Inspection and Test Plan - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-06 20:00 |  |  | No | 775 | [9 empty] | No | 0
VD-9001-104(008)-IPM-024 | 1 | AE-6187 - Non Destructive Examination Procedures - Bundles | PR-104-SUB | AIR LIQUIDE | 2018-05-06 20:00 |  |  | No | 775 | [9 empty] | No | 0
VD-9001-401A-DWG-001 | 0 | DRAWINGS | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-04-25 | 2018-10-19 13:22 | 2018-10-19 13:22 | Yes | 177 |  |  |  | 2018-10-20 09:24 |  |  |  |  | 2018-10-20 09:24 | Yes | -13
VD-9001-401A-WPS-001 | 0 | WELDING PROCEDURE SPECIFICATION | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-04-25 | 2018-10-19 13:32 | 2018-10-19 13:32 | Yes | 177 |  |  | 2018-10-23 15:56 | [5 empty] | 2018-10-23 15:56 | Yes | -10
VD-9001-202F-PPL-001 | 1 | Arrangement and Piping Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-02 | 2018-06-15 15:53 | 2018-06-15 15:55 | Yes | 44 |  |  |  |  | 2018-08-04 11:24 |  |  |  | 2018-08-04 11:24 | Yes | 36
VD-9001-301-DWG-008 | 2 | Predicted Performance Curves Overall Syngas Compressor | MC-301 | Siemens AG | 2018-05-07 20:00 |  |  | No | 774 | [9 empty] | No | 0
VD-9001-104(008)-DSH-002 | 1 | AE-6187 - Safety valves data sheet & drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-07 20:00 |  |  | No | 774 | [9 empty] | No | 0
VD-9001-301-DWG-009 | 2 | overall perform. curves circulator compressor (pred.) | MC-301 | Siemens AG | 2018-05-07 20:00 |  |  | No | 774 | [9 empty] | No | 0
VD-9001-204D-PCJ-018 | 1 | HYDROTEST PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-07 20:00 | 2018-06-29 18:53 | 2018-06-29 18:53 | Yes | 53 |  |  |  | 2018-07-17 10:29 |  |  |  |  | 2018-07-17 10:29 | Yes | 4
VD-9001-204C-PCJ-030 | 1 | PWHT PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-07 20:00 | 2018-05-22 14:20 | 2018-05-22 14:21 | Yes | 15 |  |  | 2018-06-17 16:38 | [5 empty] | 2018-06-17 20:00 | Yes | 12 | 1204-Owner-v | 2018-12-16 21:55
VD-9001-104(004)-IPM-014 | 1 | ST C-6102 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-104(004)-IPM-011 | 1 | ST C-6101 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-04-30 |  |  | No | 781 | [9 empty] | No | 0
VD-9001-254-DWG-463 | 1 | LOADING DATA & FOUNDATION OF BOILER 1/2 | HM-254 | AZAR AB | 2018-04-24 10:02 | 2018-12-12 07:46 | 2018-12-12 07:46 | Yes | 232 |  |  | 2018-12-17 10:56 | [5 empty] | 2018-12-17 10:56 | Yes | -9
VD-9001-307A-DSH-023 | 1 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-09-20 14:41 | 2018-09-20 14:41 | Yes | 135 |  |  |  | 2018-10-15 09:03 |  |  |  |  | 2018-10-15 18:57 | Yes | 11 | 1204-Owner-v | 2018-10-17 15:48
VD-9001-307A-DSH-024 | 1 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-08-02 13:48 | 2018-08-02 13:48 | Yes | 86 |  |  |  | 2018-09-01 15:07 |  |  |  |  | 2018-09-01 19:59 | Yes | 16
VD-9001-307A-DSH-021 | 1 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-08-02 13:43 | 2018-08-02 13:47 | Yes | 86 |  |  |  | 2018-09-01 15:09 |  |  |  |  | 2018-09-01 19:59 | Yes | 16
VD-9001-307A-DWG-080 | 1 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-05-30 09:31 | 2018-05-30 09:33 | Yes | 22 |  |  | 2018-06-18 10:51 | [5 empty] | 2018-06-18 20:00 | Yes | 5 | 1204-Owner-v | 2018-10-27 13:07
VD-9001-307A-DWG-120 | 1 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-04-27 13:14 | 2018-04-27 13:14 | Yes | -11 |  |  | 2018-05-01 15:53 | [5 empty] | 2018-05-01 20:00 | Yes | -10
VD-9001-307A-DIG-030 | 1 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-04-27 12:30 | 2018-04-27 12:30 | Yes | -11 |  |  | 2018-05-01 15:52 | [5 empty] | 2018-05-01 20:00 | Yes | -10
VD-9001-307A-DSH-025 | 1 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-07-06 16:29 | 2018-07-06 16:30 | Yes | 59 |  |  |  | 2018-07-22 15:14 |  |  |  |  | 2018-07-22 19:59 | Yes | 2
VD-9001-307A-PCU-010 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:24 | 2018-06-08 13:24 | Yes | 31 |  |  |  | 2018-07-02 09:20 |  |  |  |  | 2018-07-02 20:00 | Yes | 10
VD-9001-307A-PCU-009 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:24 | 2018-06-08 13:24 | Yes | 31 |  |  |  | 2018-07-02 08:54 |  |  |  |  | 2018-07-02 20:00 | Yes | 10
VD-9001-307A-PCU-008 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-307A-PCU-007 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-307A-PCU-006 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-307A-PCU-005 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-307A-PCU-004 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:24 | 2018-06-08 13:24 | Yes | 31 |  |  | 2018-07-02 11:18 | [5 empty] | 2018-07-02 20:00 | Yes | 10
VD-9001-307A-PCU-003 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:23 | 2018-06-08 13:24 | Yes | 31 |  |  | 2018-07-02 11:13 | [5 empty] | 2018-07-02 20:00 | Yes | 10
VD-9001-307A-PCU-002 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:23 | 2018-06-08 13:24 | Yes | 31 |  |  | 2018-07-02 10:39 | [5 empty] | 2018-07-02 20:00 | Yes | 10
VD-9001-307A-PCU-001 | 2 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-05-08 20:00 | 2018-06-08 13:23 | 2018-06-08 13:24 | Yes | 31 |  |  | 2018-07-02 10:09 | [5 empty] | 2018-07-02 20:00 | Yes | 10
VD-9001-104(010)-WBK-001 | 1 | Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104-PPL-001 | 2 | Plot plan - Top view | PR-104 | AIR LIQUIDE | 2018-05-08 20:00 | 2018-05-22 11:25 | 2018-05-22 11:27 | Yes | 14 |  |  |  | 2018-07-24 11:33 |  |  |  |  | 2018-07-24 19:59 | Yes | 49 | 1204-Owner-v | 2018-07-31 10:16
VD-9001-104(002)-WBK-002 | 2 | T-6101 & E-6102 - Vaporizer shell - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104(013)-IPM-003 | 1 | P-6105A / P-6105B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104(016)-ITP-002 | 1 | C-6104/TEX-6104 - Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104-DCR-001 | 2 | Site data sheet | PR-104 | AIR LIQUIDE | 2018-05-08 20:00 | 2018-06-08 11:02 | 2018-06-08 11:21 | Yes | 31 |  |  |  | 2018-06-24 09:32 |  |  |  |  | 2018-06-24 20:00 | Yes | 2
VD-9001-104(014)-DWG-001 | 1 | E-6108/E-6108-D1 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-08 20:00 |  |  | No | 773 | [9 empty] | No | 0
VD-9001-104(005)-CAL-003 | 0 | E-6101 - Support Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-10 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-104(005)-CAL-004 | 0 | E-6103 - Support Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-10 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-104(003)-DWG-007 | 0 | T-6102 - Nozzle book | PR-104-SUB | AIR LIQUIDE | 2018-05-25 | 2018-04-26 19:23 | 2018-05-28 12:30 | Yes | -29 |  |  |  | 2018-06-09 11:32 |  |  |  |  | 2018-06-09 19:59 | Yes | 30
VD-9001-104(002)-DWG-018 | 0 | T-6101 - Assembly drawing Piping support | PR-104-SUB | AIR LIQUIDE | 2018-05-25 |  |  | No | 756 | [9 empty] | No | 0
VD-9001-104(017)-DIG-001 | 0 | FT-6101 / FT-6102 -Cabinet wiring diagrams | PR-104-SUB | AIR LIQUIDE | 2018-05-30 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-104(014)-DWG-002 | 1 | E-6108/E-6108-D1 - Load on structure and anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(007)-CAL-002 | 1 | DR-6101A / DR-6101B - Fatigue calculation note | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 | 2018-05-25 16:02 | 2018-05-25 16:43 | Yes | 16 |  |  |  | 2018-06-09 11:59 |  |  |  |  | 2018-06-09 19:59 | Yes | 1
VD-9001-104(004)-CAL-006 | 1 | C-6101 / C-6102 - ST C-6101 / ST C-6102 - Heat emission | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-204D-MAL-020 | 2 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-09 20:00 | 2018-05-03 12:32 | 2018-05-03 12:33 | Yes | -6 |  |  | 2018-07-18 15:26 | [5 empty] | 2018-07-18 15:26 | Yes | 62
VD-9001-204D-MAL-021 | 1 | SPARE PARTS LIST FOR TWO YEARS OPERATION (SPIR FORM) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-09 20:00 | 2018-05-03 12:34 | 2018-05-03 12:36 | Yes | -6 |  |  |  | 2018-07-18 15:28 |  |  |  |  | 2018-07-18 15:28 | Yes | 62
VD-9001-104(007)-CAL-001 | 1 | DR-6101A / DR-6101B - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 | 2018-05-25 15:57 | 2018-05-25 16:43 | Yes | 16 |  |  |  | 2018-06-21 11:21 |  |  |  |  | 2018-06-21 20:00 | Yes | 13
VD-9001-104(014)-DWG-009 | 1 | E-6124 - Civil work drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 | 2018-06-01 17:04 | 2018-06-01 17:10 | Yes | 23 |  |  |  | 2018-06-09 09:49 |  |  |  |  | 2018-06-09 19:59 | Yes | -6 | 1204-Owner-v | 2018-08-01 15:12
VD-9001-307A-DSH-010 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-09 20:00 | 2018-09-07 16:51 | 2018-09-07 16:52 | Yes | 121 |  |  |  | 2018-10-15 10:41 |  |  |  |  | 2018-10-15 18:57 | Yes | 24 | 1204-Owner-v | 2018-10-16 13:02
VD-9001-104(013)-IPM-005 | 1 | P-6103A / P-6103B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-307A-DSH-009 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-09 20:00 | 2018-09-07 16:51 | 2018-09-07 16:52 | Yes | 121 |  |  |  | 2018-10-15 10:41 |  |  |  |  | 2018-10-15 18:57 | Yes | 24 | 1204-Owner-v | 2018-10-16 13:01
VD-9001-301-LST-009 | 2 | customer connection list circulator train | MC-301 | Siemens AG | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-301-LST-006 | 2 | customer connection list syngas train | MC-301 | Siemens AG | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104-LST-007 | 1 | Line list | PR-104 | AIR LIQUIDE | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-104(008)-CAL-002 | 1 | D-6188 - Condensate tank - calculation note | PR-104-SUB | AIR LIQUIDE | 2018-05-09 20:00 |  |  | No | 772 | [9 empty] | No | 0
VD-9001-204C-WBK-029 | 1 | WELDING BOOK | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-09 20:00 | 2018-08-29 17:07 | 2018-12-08 11:16 | Yes | 213 |  |  | 2018-12-15 10:37 | [5 empty] | 2018-12-15 19:59 | Yes | 94 | 1204-Owner-v | 2018-12-16 21:58
VD-9001-251-PPL-018 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:31 | 2019-03-13 14:31 | Yes | 317 |  |  | 2019-04-27 16:36 | [5 empty] | 2019-04-27 16:36 | Yes | 31 | 1204-Owner-v | 2019-04-08 07:16
VD-9001-251-PPL-019 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:31 | 2019-03-13 14:33 | Yes | 317 |  |  | 2019-04-27 16:38 | [5 empty] | 2019-04-27 16:38 | Yes | 31 | 1204-Owner-v | 2020-06-12 10:14
VD-9001-251-CAL-016 | 1 | STRESS ANALISYS CALCULATION (INLET SYSTEM) | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2018-06-15 11:44 | 2018-06-15 11:45 | Yes | 46 |  |  |  | 2018-07-10 10:17 |  |  |  |  | 2018-07-10 10:17 | Yes | 11
VD-9001-251-PPL-020 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:34 | 2019-03-13 14:34 | Yes | 317 |  |  |  | 2019-04-27 16:41 |  |  |  |  | 2019-04-27 16:41 | Yes | 31
VD-9001-251-PPL-021 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:34 | 2019-03-13 14:34 | Yes | 317 |  |  | 2019-04-27 16:42 | [5 empty] | 2019-04-27 16:42 | Yes | 31 | 1204-Owner-v | 2020-06-12 10:15
VD-9001-251-PPL-022 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:34 | 2019-03-13 14:34 | Yes | 317 |  |  |  | 2019-04-27 16:45 |  |  |  |  | 2019-04-27 16:45 | Yes | 31
VD-9001-251-PPL-023 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2019-03-13 14:34 | 2019-03-13 14:34 | Yes | 317 |  |  |  | 2019-04-27 16:49 |  |  |  |  | 2019-04-27 16:49 | Yes | 31
VD-9001-251-DWG-027 | 2 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-04-30 | 2018-06-07 17:23 | 2018-06-07 17:40 | Yes | 38 |  |  | 2018-06-18 17:14 | [5 empty] | 2018-06-18 17:14 | Yes | -3
VD-9001-251-DWG-028 | 2 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-05-01 | 2018-06-07 17:28 | 2018-06-07 17:41 | Yes | 37 |  |  |  | 2018-06-18 17:18 |  |  |  |  | 2018-06-18 17:18 | Yes | -3 | 1204-Owner-v | 2018-07-04 17:55
VD-9001-251-DWG-029 | 2 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-05-01 | 2018-06-07 17:32 | 2018-06-07 17:41 | Yes | 37 |  |  | 2018-06-18 17:21 | [5 empty] | 2018-06-18 17:21 | Yes | -3 | 1204-Owner-v | 2018-10-17 10:46
VD-9001-104(002)-WBK-001 | 2 | D-6103 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-10 20:00 |  |  | No | 771 | [9 empty] | No | 0
VD-9001-104(003)-WBK-001 | 1 | T-6102 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-10 20:00 | 2018-05-30 13:46 | 2018-05-30 13:48 | Yes | 20 |  |  | 2018-06-12 17:07 | [5 empty] | 2018-06-12 20:15 | Yes | -1 | 1204-Owner-v | 2019-02-02 16:50
VD-9001-104(003)-CAL-001 | 1 | T-6102 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-05-10 20:00 | 2018-05-30 13:46 | 2018-05-30 13:47 | Yes | 20 |  |  |  | 2018-06-21 11:03 |  |  |  |  | 2018-06-21 20:00 | Yes | 8
VD-9001-104(003)-LST-001 | 1 | T-6102 - Parts list (for client) | PR-104-SUB | AIR LIQUIDE | 2018-05-10 20:00 | 2018-05-30 13:42 | 2018-05-30 13:47 | Yes | 20 |  |  |  | 2018-06-09 17:09 |  |  |  |  | 2018-06-09 19:59 | Yes | -4
VD-9001-104-REQ-008 | 3 | E-6101/E-6103_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-04-28 09:23 | 2018-05-03 17:09 | 2018-05-03 17:14 | Yes | 5 |  |  | 2018-05-12 14:54 | [5 empty] | 2018-05-12 20:00 | Yes | -5 | 1204-Owner-v | 2018-05-14 09:40
VD-9001-104-REQ-009 | 2 | E-6101/E-6103_TRS Technical Requisition Sheet for transition joints | PR-104 | AIR LIQUIDE | 2018-04-28 09:23 | 2018-05-03 17:09 | 2018-05-03 17:14 | Yes | 5 |  |  | 2018-05-12 14:44 | [5 empty] | 2018-05-12 20:00 | Yes | -5
VD-9001-104-SPE-006 | 2 | Piping specifications | PR-104 | AIR LIQUIDE | 2018-04-28 11:27 | 2018-05-03 17:09 | 2018-05-03 17:14 | Yes | 5 |  |  | 2018-05-07 15:38 | [5 empty] | 2018-05-07 20:00 | Yes | -10 | 1204-Owner-v | 2019-02-25 08:34
VD-9001-251-DWG-016 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2019-06-12 10:57 | 2019-06-12 10:57 | Yes | 403 |  |  | 2019-07-06 15:02 | [5 empty] | 2019-07-06 15:02 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:48
VD-9001-251-DWG-018 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-04 12:44 | 2018-09-04 12:51 | Yes | 122 |  |  | 2018-09-08 18:47 | [5 empty] | 2018-09-08 18:47 | Yes | -10
VD-9001-251-DWG-019 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-04 12:54 | 2018-09-04 13:14 | Yes | 122 |  |  | 2018-09-08 18:48 | [5 empty] | 2018-09-08 18:48 | Yes | -10
VD-9001-251-DWG-020 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-04 13:03 | 2018-09-04 13:13 | Yes | 122 |  |  |  | 2018-09-08 18:49 |  |  |  |  | 2018-09-08 18:49 | Yes | -10
VD-9001-251-PPL-001 | 2 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-17 16:39 | 2018-09-17 16:51 | Yes | 135 |  |  | 2018-09-25 11:27 | [5 empty] | 2018-09-25 11:27 | Yes | -6 | 1204-Owner-v | 2018-10-09 15:26
VD-9001-251-PPL-002 | 2 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-17 16:44 | 2018-09-17 16:51 | Yes | 135 |  |  | 2018-09-25 11:29 | [5 empty] | 2018-09-25 11:29 | Yes | -6 | 1204-Owner-v | 2018-10-09 15:26
VD-9001-251-PPL-003 | 2 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-17 16:50 | 2018-09-17 16:51 | Yes | 135 |  |  | 2018-09-25 11:31 | [5 empty] | 2018-09-25 11:31 | Yes | -6 | 1204-Owner-v | 2018-10-09 15:26
VD-9001-251-DWG-021 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1004B | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 | 2018-09-04 12:42 | 2018-09-04 12:43 | Yes | 122 |  |  |  | 2018-09-08 18:49 |  |  |  |  | 2018-09-08 18:49 | Yes | -10
VD-9001-251-DSH-014 | 2 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-251-DSH-012 | 2 | MECHANICAL DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-251-DSH-013 | 2 | MECHANICAL DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2018-05-05 |  |  | No | 776 | [9 empty] | No | 0
VD-9001-201B-PCJ-021 | 1 | PHASED ARRAY PROCEDURE (4134/PHA) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-13 19:59 | 2018-10-22 17:22 | 2018-10-22 17:22 | Yes | 162 |  |  | 2018-11-07 12:41 | [5 empty] | 2018-11-07 20:00 | Yes | 2
VD-9001-461AF-PCJ-001 | 1 | PACKING AND MARKING AND PRESERVATION PROCEDURE | PI-461AF | Van Leeuwen | 2018-05-14 11:26 | 2018-08-28 13:09 | 2018-08-28 13:10 | Yes | 106 |  |  | 2018-09-01 16:23 | [5 empty] | 2018-09-01 16:23 | Yes | -10
VD-9001-251-DWG-032 | 1 | GENERAL NOTES & INFORMATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-06 | 2019-06-12 11:02 | 2019-06-12 11:02 | Yes | 432 |  |  |  | 2019-07-08 16:31 |  |  |  |  | 2019-07-08 16:31 | Yes | 12 | 1204-Owner-v | 2020-04-25 16:51
VD-9001-307A-ITP-005 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-05-14 19:59 | 2018-05-30 15:40 | 2018-05-30 15:40 | Yes | 16 |  |  | 2018-06-19 11:40 | [5 empty] | 2018-06-19 20:00 | Yes | 6 | 1204-Owner-v | 2018-10-20 15:05
VD-9001-307A-ITP-006 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-05-14 19:59 | 2018-05-30 15:40 | 2018-05-30 15:40 | Yes | 16 |  |  | 2018-06-19 11:44 | [5 empty] | 2018-06-19 20:00 | Yes | 6 | 1204-Owner-v | 2018-10-20 15:05
VD-9001-307A-ITP-007 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-05-14 19:59 | 2018-05-30 15:40 | 2018-05-30 15:40 | Yes | 16 |  |  | 2018-06-19 11:48 | [5 empty] | 2018-06-19 20:00 | Yes | 6 | 1204-Owner-v | 2018-10-20 15:06
VD-9001-307A-ITP-008 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-05-14 19:59 | 2018-05-30 15:40 | 2018-05-30 15:40 | Yes | 16 |  |  | 2018-06-19 11:50 | [5 empty] | 2018-06-19 20:00 | Yes | 6 | 1204-Owner-v | 2018-09-12 15:27
VD-9001-104(004)-DWG-028 | 1 | Civil work guide drawing / foundation plan with anchoring location | PR-104-SUB | AIR LIQUIDE | 2018-05-14 19:59 |  |  | No | 767 | [9 empty] | No | 0
VD-9001-104(016)-DWG-009 | 1 | C-6104/TEX-6104 - Civil work drawing / Foundation plan | PR-104-SUB | AIR LIQUIDE | 2018-05-14 19:59 |  |  | No | 767 | [9 empty] | No | 0
VD-9001-251-DSH-015 | 2 | MECHANICAL DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-05-07 |  |  | No | 774 | [9 empty] | No | 0
VD-9001-202F-PCJ-009 | 1 | Waste Heat Boiler - Tube-to tubesheet Mock-Up Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-08 | 2018-06-13 22:11 | 2018-06-13 22:16 | Yes | 36 |  |  | 2018-07-08 17:55 | [5 empty] | 2018-07-08 17:55 | Yes | 11 | 1204-Owner-v | 2019-01-21 14:07
VD-9001-202F-PCJ-011 | 1 | Waste Heat Boiler - Nitrogen Fiiling Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-08 | 2018-06-13 22:02 | 2018-06-13 22:02 | Yes | 36 |  |  | 2018-07-08 17:51 | [5 empty] | 2018-07-08 17:51 | Yes | 11 | 1204-Owner-v | 2019-02-25 15:38
VD-9001-104(008)-IPM-001 | 1 | AE-6187 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-15 19:59 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-104(003)-ITP-001 | 2 | T-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-15 19:59 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-104-REQ-012 | 1 | E-6151_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-05-15 19:59 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-307A-DSH-006 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-15 19:59 | 2018-05-30 15:39 | 2018-05-30 15:39 | Yes | 15 |  |  |  |  | 2018-06-17 09:25 |  |  |  | 2018-06-17 20:00 | Yes | 4 | 1204-Owner-v | 2018-10-16 13:06
VD-9001-307A-DSH-008 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-15 19:59 | 2018-05-30 15:39 | 2018-05-30 15:39 | Yes | 15 |  |  |  |  | 2018-06-17 09:11 |  |  |  | 2018-06-17 20:00 | Yes | 4 | 1204-Owner-v | 2018-10-16 12:40
VD-9001-307A-DSH-007 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-15 19:59 | 2018-05-30 15:39 | 2018-05-30 15:39 | Yes | 15 |  |  |  |  | 2018-06-17 09:23 |  |  |  | 2018-06-17 20:00 | Yes | 4 | 1204-Owner-v | 2018-10-17 14:00
VD-9001-307A-DSH-005 | 1 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-05-15 19:59 | 2018-05-30 15:39 | 2018-05-30 15:39 | Yes | 15 |  |  |  |  | 2018-06-17 09:30 |  |  |  | 2018-06-17 20:00 | Yes | 4 | 1204-Owner-v | 2018-10-17 14:52
VD-9001-104-REQ-015 | 2 | TK-6150_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-05-15 19:59 | 2018-06-08 17:05 | 2018-06-08 17:13 | Yes | 24 |  |  |  | 2018-06-18 15:53 |  |  |  |  | 2018-06-18 20:01 | Yes | -4
VD-9001-104-DSH-053 | 1 | Warm PSV - EDS Equipment Data Sheet (pressure) | PR-104 | AIR LIQUIDE | 2018-05-17 19:59 |  |  | No | 764 | [9 empty] | No | 0
VD-9001-104-RPT-001 | 1 | Hazop study report | PR-104 | AIR LIQUIDE | 2018-05-17 19:59 | 2018-05-22 12:49 | 2018-05-22 12:51 | Yes | 5 |  |  | 2018-07-10 16:55 | [5 empty] | 2018-07-10 20:00 | Yes | 35 | 1204-Owner-v | 2019-06-10 10:26
VD-9001-104(008)-DWG-011 | 1 | D-6187 - Steam Duct & Drain pot detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-17 19:59 |  |  | No | 764 | [9 empty] | No | 0
VD-9001-104(007)-LST-001 | 2 | DR-6101A / DR-6101B - Envelop parts list | PR-104-SUB | AIR LIQUIDE | 2018-05-17 19:59 | 2018-05-25 15:07 | 2018-05-25 15:14 | Yes | 8 |  |  | 2018-06-03 18:09 | [5 empty] | 2018-06-03 19:59 | Yes | -5
VD-9001-104(003)-DWG-001 | 1 | T-6102 - General arrangement drawing (for client) | PR-104-SUB | AIR LIQUIDE | 2018-05-17 19:59 | 2018-06-05 13:54 | 2018-06-05 14:00 | Yes | 19 |  |  |  | 2018-07-21 10:32 |  |  |  |  | 2018-07-21 19:59 | Yes | 32
VD-9001-204C-DWG-039 | 0 | TEMPLATE DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-06 | 2018-05-07 15:01 | 2018-05-07 15:02 | Yes | 1 |  |  | 2018-05-14 11:10 | [5 empty] | 2018-05-14 19:59 | Yes | -7
VD-9001-104(007)-DWG-006 | 1 | DR-6101A / DR-6101B - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-05 09:34 | 2018-05-29 17:45 | 2018-05-29 17:47 | Yes | 24 |  |  |  | 2018-06-10 17:12 |  |  |  |  | 2018-06-10 19:59 | Yes | -2
VD-9001-202F-WBK-001 | 2 | Waste Heat Boiler - Welding Book (WPS & PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-13 | 2018-06-13 21:25 | 2018-06-13 21:27 | Yes | 31 |  |  | 2018-07-08 16:45 | [5 empty] | 2018-07-08 16:45 | Yes | 11 | 1204-Owner-v | 2020-04-29 10:25
VD-9001-254-ISO-531 | 1 | ISOMETRIC DWG. FOR INTERMITTENT BLOW DOWN (BOILER 5) | HM-254 | AZAR AB | 2018-05-13 | 2018-09-24 07:46 | 2018-09-24 07:46 | Yes | 134 |  |  | 2018-10-17 16:01 | [5 empty] | 2018-10-17 16:01 | Yes | 9 | 1204-Owner-v | 2019-05-14 16:15
VD-9001-254-ISO-532 | 1 | ISOMETRIC DWG. FOR INTERMITTENT BLOW DOWN (BOILER 6) | HM-254 | AZAR AB | 2018-05-13 | 2018-09-24 07:46 | 2018-09-24 07:46 | Yes | 134 |  |  | 2018-10-17 16:03 | [5 empty] | 2018-10-17 16:03 | Yes | 9 | 1204-Owner-v | 2019-05-14 16:16
VD-9001-104(007)-DWG-003 | 2 | DR-6101A / DR-6101B - Bottom part detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 19:59 | 2018-05-25 15:05 | 2018-05-25 15:14 | Yes | 5 |  |  |  | 2018-06-09 17:15 |  |  |  |  | 2018-06-09 19:59 | Yes | 1 | 1204-Owner-v | 2018-08-01 09:47
VD-9001-104(014)-DWG-003 | 1 | E-6108 - Vessel detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 19:59 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(002)-DWG-014 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 19:59 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(002)-DWG-013 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 19:59 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(002)-DWG-011 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 19:59 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-307A-DWG-004 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-05-20 19:59 | 2018-09-21 16:41 | 2018-09-21 16:41 | Yes | 124 |  |  |  | 2018-10-10 10:41 |  |  |  |  | 2018-10-10 18:58 | Yes | 5 | 1204-Owner-v | 2018-10-31 16:27
VD-9001-104(002)-DWG-010 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(002)-DWG-009 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(002)-DWG-008 | 2 | T-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(008)-DWG-002 | 2 | AE-6187 - General Arrangement Drawing – Side View | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(008)-DWG-005 | 2 | AE-6187 - Civil work drawing– Anchorage Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-05-20 | 2018-05-31 13:24 | 2018-05-31 13:34 | Yes | 11 |  |  |  | 2018-06-20 14:37 |  |  |  |  | 2018-06-20 20:00 | Yes | 6 | 1204-Owner-v | 2018-07-31 10:55
VD-9001-104(008)-DWG-003 | 2 | AE-6187 - General Arrangement Drawing – Top View | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(008)-DWG-001 | 2 | AE-6187 – General Arrangement Drawing – Front View | PR-104-SUB | AIR LIQUIDE | 2018-05-20 |  |  | No | 761 | [9 empty] | No | 0
VD-9001-104(003)-DWG-004 | 1 | T-6102 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-20 | 2018-05-30 13:42 | 2018-05-30 13:47 | Yes | 10 |  |  | 2018-06-11 09:05 | [5 empty] | 2018-06-11 19:59 | Yes | -2
VD-9001-104(007)-DWG-001 | 2 | DR-6101A / DR-6101B - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-21 | 2018-05-25 15:05 | 2018-05-25 15:14 | Yes | 4 |  |  |  | 2018-07-11 14:40 |  |  |  |  | 2018-07-11 20:00 | Yes | 33 | 1204-Owner-v | 2018-08-01 09:47
VD-9001-257C-DWG-050 | 1 | DETAILS DRAWING (4137-0370/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-15 | 2018-05-14 14:20 | 2018-05-14 14:20 | Yes | -1 |  |  |  |  | 2018-07-08 16:43 |  |  |  | 2018-07-08 16:43 | Yes | 41
VD-9001-104(008)-PID-001 | 2 | AE-6187 - PID symbols summary page | PR-104-SUB | AIR LIQUIDE | 2018-05-22 19:59 |  |  | No | 759 | [9 empty] | No | 0
VD-9001-104(008)-PID-005 | 2 | AE-6187 - PID Steam Jet Air Ejector | PR-104-SUB | AIR LIQUIDE | 2018-05-15 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-104(008)-PID-003 | 2 | AE-6187 - PID Condensate System | PR-104-SUB | AIR LIQUIDE | 2018-05-15 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-104(008)-PID-004 | 2 | AE-6187 - PID Steam duct | PR-104-SUB | AIR LIQUIDE | 2018-05-15 |  |  | No | 766 | [9 empty] | No | 0
VD-9001-104(007)-WBK-001 | 1 | DR-6101A / DR-6101B - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-05-15 | 2018-05-25 15:18 | 2018-05-25 15:18 | Yes | 10 |  |  | 2018-06-12 17:04 | [5 empty] | 2018-06-12 20:15 | Yes | 4
VD-9001-104(007)-ITP-001 | 1 | DR-6101A / DR-6101B - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-15 | 2018-05-25 15:06 | 2018-05-25 15:14 | Yes | 10 |  |  | 2018-06-19 17:23 | [5 empty] | 2018-06-19 20:00 | Yes | 11 | 1204-Owner-v | 2020-01-01 10:02
VD-9001-204C-DWG-040 | 0 | ERECTION ASSEMBLY | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 14:12 | 2018-05-10 14:13 | Yes | 0 |  |  |  | 2018-05-22 15:05 |  |  |  |  | 2018-05-22 19:59 | Yes | -2 | 1204-Owner-v | 2018-05-19 07:20
VD-9001-204C-DWG-041 | 0 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 14:04 | 2018-05-10 14:05 | Yes | 0 |  |  |  | 2018-05-22 15:07 |  |  |  |  | 2018-05-22 19:59 | Yes | -2 | 1204-Owner-v | 2018-05-19 07:45
VD-9001-204C-DWG-042 | 0 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:56 | 2018-05-10 13:57 | Yes | 0 |  |  |  | 2018-05-22 15:08 |  |  |  |  | 2018-05-22 19:59 | Yes | -2
VD-9001-204C-DWG-043 | 0 | HANDRAILS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:43 | 2018-05-10 13:44 | Yes | 0 |  |  |  | 2018-05-22 15:11 |  |  |  |  | 2018-05-22 19:59 | Yes | -2
VD-9001-204C-DWG-044 | 0 | LADDER DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:26 | 2018-05-10 13:34 | Yes | 0 |  |  |  | 2018-06-24 16:37 |  |  |  |  | 2018-06-24 20:00 | Yes | 31
VD-9001-204C-DWG-045 | 0 | LADDER DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:20 | 2018-05-10 13:20 | Yes | 0 |  |  |  | 2018-06-24 16:37 |  |  |  |  | 2018-06-24 20:00 | Yes | 31 | 1204-Owner-v | 2019-05-11 07:47
VD-9001-204C-DWG-046 | 0 | GRATINGS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:12 | 2018-05-10 13:13 | Yes | 0 |  |  | 2018-06-24 16:38 | [5 empty] | 2018-06-24 20:00 | Yes | 31
VD-9001-204C-DWG-047 | 0 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 13:04 | 2018-05-10 13:05 | Yes | 0 |  |  |  | 2018-06-19 15:43 |  |  |  |  | 2018-06-19 20:00 | Yes | 26
VD-9001-204C-CAL-034 | 0 | PLATFORM AND LADDERS CALCULATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-10 | 2018-05-10 12:41 | 2018-05-10 12:59 | Yes | 0 |  |  | 2018-05-20 10:24 | [5 empty] | 2018-05-20 19:59 | Yes | -4 | 1204-Owner-v | 2018-12-16 21:56
VD-9001-251-DWG-001 | 2 | CATALYST TUBE DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-05-16 | 2018-09-04 13:14 | 2018-09-04 13:17 | Yes | 111 |  |  | 2018-09-08 11:47 | [5 empty] | 2018-09-08 11:47 | Yes | -10 | 1204-Owner-v | 2019-02-05 10:50
VD-9001-202F-PPL-005 | 2 | Waste Heat Boiler - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-23 | 2018-07-05 19:37 | 2018-07-05 19:37 | Yes | 43 |  |  |  |  | 2018-08-12 14:53 |  |  |  | 2018-08-12 14:53 | Yes | 24 | 1204-Owner-v | 2018-10-16 17:01
VD-9001-104(009)-DWG-006 | 1 | HP/ LP Cold box - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-05-23 19:59 | 2018-05-29 16:56 | 2018-05-29 17:16 | Yes | 6 |  |  |  | 2018-06-10 09:35 |  |  |  |  | 2018-06-10 19:59 | Yes | -2
VD-9001-104(008)-PID-002 | 2 | AE-6187 - PID process ACC | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-104(008)-DSH-005 | 1 | AE-6187 - Fan data sheet & Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-104(005)-DWG-009 | 1 | E-6103 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-104(006)-DWG-002 | 1 | E-6102 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-21 | 2018-05-25 18:05 | 2018-05-25 18:08 | Yes | 4 |  |  |  | 2018-06-10 16:42 |  |  |  |  | 2018-06-10 19:59 | Yes | 2
VD-9001-201B-DWG-003 | 2 | NAME PLATE DET.DWG (4134-0359/A) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-21 | 2019-01-23 13:03 | 2019-01-23 13:05 | Yes | 247 |  |  | 2019-02-03 17:01 | [5 empty] | 2019-02-03 20:00 | Yes | -3
VD-9001-104(014)-DWG-007 | 1 | E-6108/E-6108-D1 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-104(014)-DWG-012 | 1 | E-6124 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-740A-GAD-00084 | 1 | General Arrangement Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-05-13 | 2018-05-13 10:59 | 2018-05-13 10:59 | Yes | 0 |  |  |  |  | 2018-05-19 11:10 |  |  |  | 2018-05-19 11:10 | Yes | -8
VD-9001-740A-GAD-00083 | 1 | General Arrangement Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-05-13 | 2018-05-13 10:57 | 2018-05-13 10:57 | Yes | 0 |  |  |  |  | 2018-05-19 11:12 |  |  |  | 2018-05-19 11:12 | Yes | -8
VD-9001-740A-MOD-00084 | 1 | Models-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-05-13 | 2018-05-13 11:00 | 2018-05-13 11:00 | Yes | 0 |  |  |  |  | 2018-05-14 11:37 |  |  |  | 2018-05-14 11:37 | Yes | -13
VD-9001-740A-MOD-00083 | 1 | Models-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-05-13 | 2018-05-13 10:59 | 2018-05-13 10:59 | Yes | 0 |  |  |  |  | 2018-05-14 11:39 |  |  |  | 2018-05-14 11:39 | Yes | -13
VD-9001-201B-DWG-018 | 0 | REFRACTORY LINING REFORMER R-1004 - HORIZONTAL SECTIONS AND VIEWS (4134-0359/RF2) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-05-24 12:08 | 2018-05-24 12:09 | Yes | 6 |  |  | 2018-10-28 18:11 | [5 empty] | 2018-10-28 20:00 | Yes | 143 | 1204-Owner-v | 2019-01-29 09:12
VD-9001-201B-DWG-019 | 0 | REFRACTORY ANCHORS REFORMER R-1004 - HORIZONTAL SECTIONS AND VIEWS (4134-0359/RF3) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-05-24 12:09 | 2018-05-24 12:09 | Yes | 6 |  |  | 2018-10-28 17:59 | [5 empty] | 2018-10-28 20:00 | Yes | 143 | 1204-Owner-v | 2019-01-29 09:13
VD-9001-201B-DWG-020 | 0 | REFRACTORY LINING REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF4) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-05-24 12:10 | 2018-05-24 12:10 | Yes | 6 |  |  |  | 2018-09-03 11:01 |  |  |  |  | 2018-09-03 19:58 | Yes | 88 | 1204-Owner-v | 2019-01-29 10:20
VD-9001-201B-DWG-021 | 0 | REFRACTORY ANCHORS REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF5) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-05-24 12:11 | 2018-05-24 12:11 | Yes | 6 |  |  |  | 2018-08-28 16:29 |  |  |  |  | 2018-08-28 19:58 | Yes | 82 | 1204-Owner-v | 2019-01-29 10:27
VD-9001-201B-DWG-022 | 0 | REFRACTORY LINING REFORMER R-1004 - DOME BRICKS (4134-0359/RF6) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-11-08 18:43 | 2018-11-08 18:44 | Yes | 174 |  |  | 2018-12-05 17:49 | [5 empty] | 2018-12-05 20:00 | Yes | 13 | 1204-Owner-v | 2019-01-29 14:53
VD-9001-201B-DWG-023 | 0 | REFRACTORY STUDS REFORMER R-1004 (4134-0359/RF7) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-11-08 18:48 | 2018-11-08 18:48 | Yes | 174 |  |  | 2018-11-11 17:06 |  |  |  | 2018-10-28 15:48 | 2018-10-28 15:48 | 2018-11-11 20:00 | Yes | -11 | 1204-Owner-v | 2019-01-29 14:53
VD-9001-201B-LST-005 | 0 | BILL OF MATERIALS R-1004 (4134-0359/RBOM) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2018-05-28 17:14 | 2018-05-28 17:16 | Yes | 10 |  |  | 2018-11-21 15:59 | [5 empty] | 2018-11-21 20:00 | Yes | 163 | 1204-Owner-v | 2019-01-29 14:53
VD-9001-201B-LST-004 | 0 | SPARE PARTS LIST (4134-0359/RSPL) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-11 | 2018-06-06 19:38 | 2018-06-06 19:39 | Yes | -5 |  |  | 2018-11-21 15:57 | [5 empty] | 2018-11-21 20:00 | Yes | 154
VD-9001-201B-CAL-006 | 0 | REFRACTORY DOME SUPPORT CALCULATION ( 4134-0359/RDSC) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-18 | 2019-08-08 11:13 | 2019-08-08 11:14 | Yes | 447 |  |  |  | 2019-08-17 16:22 |  |  |  |  | 2019-08-17 20:00 | Yes | -5
VD-9001-201B-PCJ-022 | 0 | REFRACTORY SHIPPING & STORAGE INSTRUCTIONS R-1004 (4134-0359/PMS) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-11 | 2018-06-22 11:15 | 2018-06-22 11:16 | Yes | 11 |  |  | 2018-07-04 10:18 | [5 empty] | 2018-07-04 20:00 | Yes | -2 | 1204-Owner-v | 2019-01-29 15:00
VD-9001-201B-FDB-002 | 0 | MANUFACTURER DATA BOOK R-1004 (4134-0359/RMDB) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-11 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-201B-INX-002 | 0 | INDEX OF MANUFACTURER DATA BOOK R-1004 (4134-0359/RMDB Ind) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-11 | 2018-06-20 11:34 | 2018-06-20 11:35 | Yes | 9 |  |  |  | 2018-07-04 14:53 |  |  |  |  | 2018-07-04 20:00 | Yes | 0
VD-9001-104(003)-DWG-006 | 1 | T-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 | 2018-06-05 13:54 | 2018-06-05 14:00 | Yes | 10 |  |  |  | 2018-06-14 11:09 |  |  |  |  | 2018-06-14 20:00 | Yes | -5
VD-9001-204D-CAL-031 | 1 | SHIPPING SUPPORT CALCULATIONS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-05-26 19:59 | 2018-07-07 10:07 | 2018-07-07 10:07 | Yes | 42 |  |  |  | 2018-07-21 09:54 |  |  | 2018-07-04 17:29 | 2018-07-04 17:29 | 2018-07-21 09:54 | Yes | 0
VD-9001-104(005)-DWG-008 | 1 | E-6101/E-6103 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(013)-PCU-001 | 1 | P-6105A / P-6105B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(008)-PCU-002 | 1 | P-6187A/B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(008)-PCU-003 | 1 | P-6188A/B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(008)-DSH-003 | 1 | AE-6187-CM01 - Rupture disk data sheet | PR-104-SUB | AIR LIQUIDE | 2018-05-26 19:59 |  |  | No | 755 | [9 empty] | No | 0
VD-9001-104(007)-SKT-001 | 2 | DR-6101A / DR-6101B - Filter - Equipment sketch | PR-104-SUB | AIR LIQUIDE | 2018-05-27 19:59 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-104(017)-DSH-002 | 1 | FT-6101 / FT-6102 - Filter elements detail dwg. And datasheet | PR-104-SUB | AIR LIQUIDE | 2018-05-27 19:59 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-104(017)-DWG-004 | 1 | FT-6101 / FT-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-05-27 19:59 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-104(013)-DWG-006 | 1 | P-6105A / P-6105B - General arrangement drawing (motor&pump) | PR-104-SUB | AIR LIQUIDE | 2018-05-27 19:59 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-104(008)-DWG-023 | 1 | AE-6187 - NDC Manifold | PR-104-SUB | AIR LIQUIDE | 2018-05-27 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-740A-MOD-00084 | 2 | Models-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-05-17 | 2018-05-17 11:26 | 2018-05-17 11:26 | Yes | 0 |  |  |  |  | 2018-05-19 10:47 |  |  |  | 2018-05-19 10:47 | Yes | -12
VD-9001-740A-MOD-00083 | 2 | Models-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-05-17 | 2018-05-17 11:24 | 2018-05-17 11:25 | Yes | 0 |  |  |  |  | 2018-05-19 10:49 |  |  |  | 2018-05-19 10:49 | Yes | -12
VD-9001-206B-PCJ-016 | 3 | HARDNESS TEST PROCEDURE | PV-206B | TASHA | 2018-05-31 | 2018-10-06 10:12 | 2018-10-06 10:12 | Yes | 128 |  |  | 2018-11-11 09:31 | [5 empty] | 2018-11-11 09:31 | Yes | 22
VD-9001-104(017)-ITP-001 | 1 | FT-6101 / FT-6102 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-28 19:59 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-104(008)-DWG-025 | 1 | AE-6187 - Manifold drawings 2/2 | PR-104-SUB | AIR LIQUIDE | 2018-05-28 19:59 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-104(008)-DWG-024 | 1 | AE-6187 - Manifold drawings 1/2 | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-204C-DWG-035 | 2 | LADDER & PLATFORM S DWGS. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-05-21 | 2018-07-23 17:08 | 2018-07-23 17:08 | Yes | 63 |  |  |  | 2018-08-07 11:39 |  |  |  |  | 2018-08-07 19:59 | Yes | 1
VD-9001-104(014)-IPM-001 | 1 | E-6108 - Painting specification & procedure | PR-104-SUB | AIR LIQUIDE | 2018-05-21 |  |  | No | 760 | [9 empty] | No | 0
VD-9001-104-DSH-034 | 1 | Flowmeter - EDS Equipment Data Sheet (pitot) | PR-104 | AIR LIQUIDE | 2018-05-14 |  |  | No | 767 | [9 empty] | No | 0
VD-9001-307A-DWG-002 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-05-16 | 2018-09-07 16:53 | 2018-09-07 16:53 | Yes | 114 |  |  |  | 2018-10-10 10:25 |  |  |  |  | 2018-10-10 18:57 | Yes | 19 | 1204-Owner-v | 2018-10-02 13:02
VD-9001-251-LST-010 | 1 | PROJECT DOCUMENTS LIST | HM-251 | KT – Kinetics Technology SpA | 2018-05-15 09:35 | 2018-05-15 13:51 | 2018-05-15 14:21 | Yes | 0 |  |  |  | 2019-02-20 17:27 |  |  |  |  | 2019-02-20 17:27 | Yes | 267 | 1204-Owner-v | 2018-10-09 15:21
VD-9001-104(007)-IPM-001 | 1 | DR-6101A / DR-6101B - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(001)-DWG-002 | 1 | AREA D1 - O2 Blockhaus, Common Silencer | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(017)-DSH-001 | 1 | FT-6101 / FT-6102 - Noise acoustic Datasheet | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(016)-IPM-008 | 1 | C-6104/TEX-6104 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(016)-IPM-003 | 1 | C-6103/TEX-6103 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(016)-DWG-008 | 1 | C-6104/TEX-6104 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-104(017)-DWG-003 | 1 | FT-6101 / FT-6102 - Anchoring details | PR-104-SUB | AIR LIQUIDE | 2018-05-29 19:59 |  |  | No | 752 | [9 empty] | No | 0
VD-9001-257C-DWG-065 | 0 | DETAILS DRAWING (4137-0366/3) E-2001A | HM-257C | Brembana & Rolle S.p.A. | 2018-05-25 | 2018-05-21 14:01 | 2018-05-21 14:01 | Yes | -4 |  |  |  |  | 2018-05-31 13:00 |  |  |  | 2018-05-31 13:00 | Yes | -4
VD-9001-257C-DWG-066 | 0 | DETAILS DRAWING (4137-0367/4) E-2001B | HM-257C | Brembana & Rolle S.p.A. | 2018-05-25 | 2018-05-21 14:16 | 2018-05-21 14:16 | Yes | -4 |  |  |  |  | 2018-07-08 16:35 |  |  |  | 2018-07-08 16:35 | Yes | 34
VD-9001-104-DSH-044 | 2 | Cryo automatic valve - EDS Equipment Data Sheet for butterfly valves | PR-104 | AIR LIQUIDE | 2018-05-30 19:59 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-104(013)-DWG-001 | 1 | P-6103A / P-6103B - General arrangement drawing (motor&pump) | PR-104-SUB | AIR LIQUIDE | 2018-05-30 19:59 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-104(011)-ITP-002 | 1 | Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-30 19:59 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-104(014)-ITP-002 | 1 | E-6124 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-05-30 19:59 | 2018-05-31 12:25 | 2018-05-31 12:26 | Yes | 1 |  |  |  | 2018-06-21 11:34 |  |  |  |  | 2018-06-21 20:00 | Yes | 7 | 1204-Owner-v | 2020-01-01 09:57
VD-9001-104(017)-DWG-002 | 1 | FT-6101 / FT-6102 - Civil work drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-05-30 19:59 |  |  | No | 751 | [9 empty] | No | 0
VD-9001-202F-PCJ-002 | 1 | Steam Superheater - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-31 | 2018-07-05 19:32 | 2018-07-05 19:32 | Yes | 35 |  |  |  |  | 2018-07-15 15:05 |  |  |  | 2018-07-15 15:05 | Yes | -4
VD-9001-202F-PCJ-003 | 1 | Steam Superheater - Procedure for Hydrostatic Test Pressure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-24 | 2018-07-05 19:33 | 2018-07-05 19:33 | Yes | 42 |  |  |  |  | 2018-07-16 10:10 |  |  |  | 2018-07-16 10:10 | Yes | -3
VD-9001-202F-PCJ-006 | 1 | Steam Superheater - Positive Material Identification Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-24 | 2018-07-05 19:35 | 2018-07-05 19:35 | Yes | 42 |  |  | 2018-07-15 15:08 | [5 empty] | 2018-07-15 15:08 | Yes | -4 | 1204-Owner-v | 2020-04-29 09:56
VD-9001-257C-PCJ-009 | 0 | PHASED ARRAY PROCEDURE (4137/PHA) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-25 | 2018-05-28 14:43 | 2018-05-28 14:43 | Yes | 3 |  |  |  |  | 2018-07-17 11:05 |  |  |  | 2018-07-17 11:05 | Yes | 36
VD-9001-257C-PCJ-010 | 0 | TOFD PROCEDURE (4137/TOFD) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-25 | 2018-05-17 12:14 | 2018-05-17 12:16 | Yes | -8 |  |  | 2018-06-14 14:09 | [5 empty] | 2018-06-14 14:09 | Yes | 14
VD-9001-257C-DWG-046 | 1 | NAME PLATE DET.DWG (4137-0371/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-05-24 | 2018-05-17 11:40 | 2018-05-17 11:40 | Yes | -7 |  |  | 2018-05-28 11:09 | [5 empty] | 2018-05-28 11:09 | Yes | -3
VD-9001-202F-PPL-006 | 2 | Steam Drum - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-05-24 | 2018-07-07 00:05 | 2018-07-07 00:05 | Yes | 44 |  |  |  |  | 2018-08-12 16:10 |  |  |  | 2018-08-12 16:10 | Yes | 22 | 1204-Owner-v | 2019-01-09 11:06
VD-9001-105-DWG-301 | 4 | Piping general arrangement and tie-point list | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-05-19 09:18 | 2018-05-21 09:35 | 2018-05-21 09:40 | Yes | 2 |  |  | 2018-05-22 18:30 |  |  |  | 2018-05-20 10:06 | 2018-05-20 10:06 | 2018-05-22 18:30 | Yes | -13 | 1204-Owner-v | 2018-06-23 14:49
VD-9001-105-PID-101 | 5 | P & I diagram of hydrogen recovery unit (P&ID) | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-05-19 09:19 | 2018-05-21 09:41 | 2018-05-21 09:41 | Yes | 2 |  |  | 2018-05-22 14:22 |  |  |  | 2018-05-20 10:03 | 2018-05-20 10:03 | 2018-05-22 14:22 | Yes | -13 | 1204-Owner-v | 2018-06-24 13:31
VD-9001-740A-MOD-00084 | 3 | Models-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-05-26 | 2018-05-29 08:35 | 2018-05-29 08:35 | Yes | 3 |  |  |  | 2018-08-09 12:26 |  |  |  |  | 2018-08-09 12:26 | Yes | 58
VD-9001-740A-MOD-00083 | 3 | Models-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-05-26 | 2018-05-29 08:33 | 2018-05-29 08:33 | Yes | 3 |  |  |  | 2018-08-09 12:30 |  |  |  |  | 2018-08-09 12:30 | Yes | 58
VD-9001-740A-GAD-00084 | 2 | General Arrangement Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-05-26 | 2018-05-30 13:02 | 2018-05-30 13:03 | Yes | 4 |  |  |  | 2018-06-07 12:12 |  |  |  |  | 2018-06-07 12:12 | Yes | -6
VD-9001-740A-GAD-00083 | 2 | General Arrangement Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-05-26 | 2018-05-30 13:01 | 2018-05-30 13:01 | Yes | 4 |  |  |  | 2018-06-07 12:11 |  |  |  |  | 2018-06-07 12:11 | Yes | -6
VD-9001-404A-DWG-001 | 0 | Drawing | PI-404A | KVC CO., LTD. | 2018-05-15 | 2018-05-21 05:41 | 2018-05-21 05:47 | Yes | 6 |  |  |  | 2018-05-21 11:28 |  |  |  |  | 2018-05-21 11:30 | Yes | -14
VD-9001-404A-WPS-001 | 0 | Welding Procedure Specification | PI-404A | KVC CO., LTD. | 2018-05-18 | 2018-05-23 11:03 | 2018-05-23 11:03 | Yes | 5 |  |  | 2018-06-11 14:27 | [5 empty] | 2018-06-11 14:29 | Yes | 5 | 1204-Owner-v | 2019-02-02 16:39
VD-9001-404A-PQR-001 | 0 | Procedure Qualification Record | PI-404A | KVC CO., LTD. | 2018-05-18 |  |  | No | 763 | [9 empty] | No | 0
VD-9001-404A-ITP-001 | 0 | Test and Inspection Plan | PI-404A | KVC CO., LTD. | 2018-05-15 | 2018-05-23 06:09 | 2018-05-23 06:10 | Yes | 8 |  |  |  | 2018-06-11 11:22 |  |  |  |  | 2018-06-11 11:23 | Yes | 5 | 1204-Owner-v | 2020-01-01 11:01
VD-9001-404A-SRN-001 | 0 | Shipping Release Note | PI-404A | KVC CO., LTD. | 2018-10-10 | 2018-09-13 10:09 | 2018-09-13 10:09 | Yes | -27 |  |  | 2018-10-09 09:03 | [5 empty] | 2018-10-09 09:03 | Yes | 12
VD-9001-404A-MDB-001 | 0 | Manufacturing Data Book | PI-404A | KVC CO., LTD. | 2018-10-15 | 2018-09-23 09:28 | 2018-09-23 09:28 | Yes | -22 |  |  | 2018-10-10 11:26 | [5 empty] | 2018-10-10 11:33 | Yes | 3 | 1204-Owner-v | 2019-01-04 20:25
VD-9001-404A-DIS-001 | 0 | Vendor Documents Index & Schedule | PI-404A | KVC CO., LTD. | 2018-05-14 | 2018-05-21 05:42 | 2018-05-21 05:47 | Yes | 7 |  |  |  | 2018-06-11 11:30 |  |  |  |  | 2018-06-11 11:30 | Yes | 7 | 1204-Owner-v | 2019-06-17 16:03
VD-9001-404A-PCJ-001 | 0 | Hydrostatic Test Procedures | PI-404A | KVC CO., LTD. | 2018-05-18 | 2018-05-21 05:43 | 2018-05-21 05:48 | Yes | 3 |  |  |  | 2018-06-11 14:35 |  |  |  |  | 2018-06-11 14:35 | Yes | 7
VD-9001-404A-PCJ-002 | 0 | NDT Procedure | PI-404A | KVC CO., LTD. | 2018-05-18 | 2018-06-21 10:42 | 2018-06-21 10:42 | Yes | 34 |  |  | 2018-06-26 15:50 | [5 empty] | 2018-06-26 15:50 | Yes | -9 | 1204-Owner-v | 2019-02-02 14:19
VD-9001-404A-PCJ-003 | 0 | Painting Procedure | PI-404A | KVC CO., LTD. | 2018-05-18 | 2018-06-15 10:46 | 2018-06-15 10:47 | Yes | 28 |  |  |  | 2018-06-25 09:05 |  |  |  |  | 2018-06-25 09:05 | Yes | -4
VD-9001-104(006)-DWG-001 | 2 | E-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 |  |  | No | 748 | [9 empty] | No | 0
VD-9001-104(017)-DWG-001 | 1 | FT-6101 / FT-6102 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 |  |  | No | 748 | [9 empty] | No | 0
VD-9001-104(005)-DWG-010 | 2 | E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 | 2018-05-22 12:15 | 2018-05-22 12:20 | Yes | -11 |  |  |  | 2018-06-03 16:49 |  |  |  |  | 2018-06-03 19:59 | Yes | -2 | 1204-Owner-v | 2019-09-24 18:11
VD-9001-204C-CAL-016 | 1 | FEA ANALYSIS | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-06-02 | 2018-06-28 17:14 | 2018-06-28 17:15 | Yes | 26 |  |  | 2018-07-08 10:44 | [5 empty] | 2018-07-08 20:00 | Yes | -4 | 1204-Owner-v | 2018-12-16 21:53
VD-9001-104(005)-DWG-003 | 2 | E-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-02 | 2018-05-22 12:15 | 2018-05-22 12:20 | Yes | -11 |  |  |  | 2018-06-03 17:05 |  |  |  |  | 2018-06-03 19:59 | Yes | -2
VD-9001-104(013)-IPM-006 | 1 | P-6103A / P-6103B - Run test & Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-02 |  |  | No | 748 | [9 empty] | No | 0
VD-9001-251-DSH-016 | 1 | PSV DATA SHEET | HM-251 | KT – Kinetics Technology SpA | 2018-05-27 |  |  | No | 754 | [9 empty] | No | 0
VD-9001-251-DSH-017 | 1 | Control Valves Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-05-28 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-251-DSH-018 | 1 | ON-OFF Valves Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-05-28 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-104(013)-PCU-002 | 1 | P-6103A / P-6103B - Performances curves | PR-104-SUB | AIR LIQUIDE | 2018-06-03 19:59 |  |  | No | 747 | [9 empty] | No | 0
VD-9001-104(005)-DWG-002 | 2 | E-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-05-30 | 2018-05-22 12:04 | 2018-05-22 12:19 | Yes | -8 |  |  |  | 2018-06-03 15:42 |  |  |  |  | 2018-06-03 19:59 | Yes | -2
VD-9001-254-DSH-224 | 2 | DATA SHEET FOR LOCAL CONTROL STATION | HM-254 | AZAR AB | 2018-05-26 | 2018-08-29 16:31 | 2018-08-29 16:32 | Yes | 95 |  |  |  | 2018-10-01 15:00 |  |  |  |  | 2018-10-01 15:00 | Yes | 19
VD-9001-254-ISO-530 | 1 | ISOMETRIC DWG. FOR CONTINOUS BLOW DOWN (BOILER 6) | HM-254 | AZAR AB | 2018-05-26 | 2018-09-24 07:45 | 2018-09-24 07:45 | Yes | 121 |  |  | 2018-10-17 15:59 | [5 empty] | 2018-10-17 15:59 | Yes | 9 | 1204-Owner-v | 2019-05-14 16:14
VD-9001-254-ISO-529 | 1 | ISOMETRIC DWG. FOR CONTINOUS BLOW DOWN (BOILER 5) | HM-254 | AZAR AB | 2018-05-26 | 2018-09-24 07:44 | 2018-09-24 07:44 | Yes | 121 |  |  | 2018-10-17 15:57 | [5 empty] | 2018-10-17 15:57 | Yes | 9 | 1204-Owner-v | 2019-02-17 17:08
VD-9001-404A-DWG-001 | 1 | Drawing | PI-404A | KVC CO., LTD. | 2018-06-04 11:30 | 2018-06-08 11:03 | 2018-06-08 11:03 | Yes | 4 |  |  |  | 2018-06-10 09:28 |  |  |  |  | 2018-06-10 09:28 | Yes | -12
VD-9001-104-DSH-051 | 3 | Warm automatic 3-lever valve - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-05-28 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-104-DSH-043 | 3 | Cryo automatic valve - EDS Equipment Data Sheet for globe valves | PR-104 | AIR LIQUIDE | 2018-05-28 |  |  | No | 753 | [9 empty] | No | 0
VD-9001-104(005)-CAL-001 | 1 | E-6101 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(005)-CAL-002 | 1 | E-6103 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(008)-LST-006 | 1 | AE-6187 - Instruments list | PR-104-SUB | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104(014)-DWG-008 | 1 | E-6124 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-204C-DWG-040 | 1 | ERECTION ASSEMBLY | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-06-05 19:59 | 2018-07-23 17:01 | 2018-07-23 17:02 | Yes | 48 |  |  | 2018-08-08 11:32 | [5 empty] | 2018-08-08 19:59 | Yes | 2 | 1204-Owner-v | 2019-04-06 14:32
VD-9001-204C-DWG-041 | 1 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-06-05 19:59 | 2018-07-23 17:04 | 2018-07-23 17:04 | Yes | 48 |  |  | 2018-08-06 10:30 | [5 empty] | 2018-08-06 19:59 | Yes | 0
VD-9001-204C-DWG-043 | 1 | HANDRAILS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-06-05 19:59 | 2018-07-23 12:48 | 2018-07-23 12:49 | Yes | 48 |  |  | 2018-08-06 10:17 | [5 empty] | 2018-08-06 19:59 | Yes | 0
VD-9001-104(005)-DWG-004 | 1 | E-6101 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104-LST-003 | 1 | Effluent list | PR-104 | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104-DSH-014 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104-DSH-015 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-05 19:59 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-201B-ITP-001 | 2 | INSPECTION & TESTING PLAN (4134-0359/ITP) | PV-201B | Brembana & Rolle S.p.A. | 2018-05-23 10:32 | 2018-05-23 11:41 | 2018-05-23 11:42 | Yes | 0 |  |  |  | 2018-06-09 15:24 |  |  |  |  | 2018-06-09 19:59 | Yes | 3 | 1204-Owner-v | 2020-01-01 12:44
VD-9001-201-PCJ-006 | 1 | NITROGEN PRESSURIZING PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2018-05-30 | 2018-07-17 19:45 | 2018-07-17 19:45 | Yes | 48 |  |  | 2018-07-22 11:19 | [5 empty] | 2018-07-22 11:19 | Yes | -9 | 1204-Owner-v | 2018-09-22 10:48
VD-9001-104(001)-DWG-003 | 1 | Area A / B - Machine Hall | PR-104-SUB | AIR LIQUIDE | 2018-06-06 19:59 |  |  | No | 744 | [9 empty] | No | 0
VD-9001-104(013)-DWG-002 | 1 | P-6103A / P-6103B - Terminal box arrangement ( Including the wiring diagram) | PR-104-SUB | AIR LIQUIDE | 2018-06-06 19:59 |  |  | No | 744 | [9 empty] | No | 0
VD-9001-104-DSH-038 | 1 | Warm Temperature - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-06 19:59 |  |  | No | 744 | [9 empty] | No | 0
VD-9001-104-REQ-019 | 2 | FT-6101/FT-6102_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-06-06 19:59 |  |  | No | 744 | [9 empty] | No | 0
VD-9001-251-CAL-020 | 0 | LIFTING CALCULATION | HM-251 | KT – Kinetics Technology SpA | 2018-04-13 | 2019-04-13 14:47 | 2019-04-13 14:47 | Yes | 365 |  |  |  | 2019-04-13 16:40 |  |  |  |  | 2019-04-13 16:41 | Yes | -14
VD-9001-251-DWG-111 | 0 | COMBUSTION AIR DUCTS STEELWORK SUPPORT | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-26 18:42 | 2018-06-26 18:42 | Yes | 95 |  |  | 2018-07-03 09:58 | [5 empty] | 2018-07-03 09:58 | Yes | -7
VD-9001-251-DWG-112 | 0 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-07 18:04 | 2018-06-07 18:04 | Yes | 76 |  |  |  | 2018-06-18 09:53 |  |  |  |  | 2018-06-18 09:53 | Yes | -3
VD-9001-251-DWG-113 | 0 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-07 18:05 | 2018-06-07 18:05 | Yes | 76 |  |  |  | 2018-06-18 09:52 |  |  |  |  | 2018-06-18 09:52 | Yes | -3
VD-9001-251-DWG-114 | 0 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-05-28 13:53 | 2018-05-28 13:57 | Yes | 66 |  |  | 2018-06-02 16:29 | [5 empty] | 2018-06-02 16:29 | Yes | -9
VD-9001-251-DWG-115 | 0 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-26 18:42 | 2018-06-26 18:42 | Yes | 95 |  |  | 2018-06-27 16:47 | [5 empty] | 2018-06-27 16:47 | Yes | -13
VD-9001-251-DWG-116 | 0 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-26 18:43 | 2018-06-26 18:43 | Yes | 95 |  |  | 2018-06-27 16:52 | [5 empty] | 2018-06-27 16:52 | Yes | -13
VD-9001-251-DWG-117 | 0 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-26 18:43 | 2018-06-26 18:43 | Yes | 95 |  |  | 2018-06-27 16:52 | [5 empty] | 2018-06-27 16:52 | Yes | -13
VD-9001-251-DWG-118 | 0 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-26 18:44 | 2018-06-26 18:44 | Yes | 95 |  |  | 2018-06-27 16:53 | [5 empty] | 2018-06-27 16:53 | Yes | -13
VD-9001-251-DWG-119 | 0 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-05-30 18:33 | 2018-05-30 18:37 | Yes | 68 |  |  | 2018-06-05 14:55 | [5 empty] | 2018-06-05 14:55 | Yes | -8 | 1204-Owner-v | 2018-07-11 09:57
VD-9001-251-DWG-120 | 0 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-03-23 | 2018-06-13 19:12 | 2018-06-13 19:17 | Yes | 82 |  |  | 2018-06-18 09:44 | [5 empty] | 2018-06-18 09:44 | Yes | -9
VD-9001-301-QCP-002 | 2 | Quality Control Plan (Syngas SST Auxiliaries) | MC-301 | Siemens AG | 2018-06-09 19:59 |  |  | No | 741 | [9 empty] | No | 0
VD-9001-104(011)-DWG-001 | 1 | Warm automatic globe valve - Detail drawings | PR-104-SUB | AIR LIQUIDE | 2018-06-09 19:59 |  |  | No | 741 | [9 empty] | No | 0
VD-9001-301-QCP-006 | 1 | quality control plan syngas turbine | MC-301 | Siemens AG | 2018-06-10 19:59 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-301-QCP-007 | 1 | quality control plan circulator turbine | MC-301 | Siemens AG | 2018-06-10 19:59 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-104(013)-DWG-007 | 1 | P-6105A / P-6105B - Terminal box arrangement ( Including the wiring diagram) | PR-104-SUB | AIR LIQUIDE | 2018-06-10 19:59 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-104(011)-CAL-001 | 1 | Calculation sheet for JT globe valves ( included noise calculation) | PR-104-SUB | AIR LIQUIDE | 2018-06-10 19:59 |  |  | No | 740 | [9 empty] | No | 0
VD-9001-104-DSH-055 | 1 | PCV - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-10 19:59 |  | 2018-05-31 14:59 | Yes | 740 | [6 empty] | 2018-06-02 09:05 | 2018-06-02 09:05 |  | Yes | 0
VD-9001-301-PID-003 | 2 | P+I Diagram Machine Syngas Turbine | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-002 | 2 | P+I Diagram Machine Syngas Compressor | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-013 | 2 | P+I Diagram Machine Circulator Turbine | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-007 | 2 | P+I Diagram Process gas Syngas Compressor | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-016 | 2 | P+I Diagram Process gas Circulator Compressor | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-012 | 2 | P+I Diagram Machine (Circulator Compressor) | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-010 | 2 | P+I Diagram Control Oil Syngas Turbine | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-006 | 2 | P+I Diagram Oil Console Syngas and Circulator Trains | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-301-PID-017 | 2 | P+I Diagram Steam + Drainage Circulator Turbine | MC-301 | Siemens AG | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(014)-CAL-001 | 1 | E-6108/E-6108-D1 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(014)-CAL-002 | 1 | E-6124 - Calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(013)-IPM-004 | 1 | P-6105A / P-6105B - Run test & Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(013)-DSH-001 | 1 | P-6103A / P-6103B - EDS Equipment data sheet of Motor (SPECIFIC TO CLIENT FORM) | PR-104-SUB | AIR LIQUIDE | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(013)-DSH-003 | 1 | P-6105A / P-6105B - EDS Equipment data sheet of Motor (SPECIFIC TO CLIENT FORM) | PR-104-SUB | AIR LIQUIDE | 2018-06-11 19:59 |  |  | No | 739 | [9 empty] | No | 0
VD-9001-104(007)-IPM-002 | 1 | DR-6101A / DR-6101B - Shop test Procedure and condition of test | PR-104-SUB | AIR LIQUIDE | 2018-05-29 09:03 | 2018-05-31 13:51 | 2018-05-31 13:52 | Yes | 2 |  |  | 2018-06-21 11:30 | [5 empty] | 2018-06-21 20:00 | Yes | 7
VD-9001-104(008)-DWG-006 | 2 | AE-6187 – Civil work drawing - Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-06-12 19:59 | 2018-05-31 13:25 | 2018-05-31 13:34 | Yes | -12 |  |  |  | 2018-06-20 14:42 |  |  |  |  | 2018-06-20 20:00 | Yes | 6
VD-9001-104(008)-DWG-007 | 2 | AE-6187 – Civil work drawing - Anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-06-12 19:59 | 2018-05-31 13:25 | 2018-05-31 13:37 | Yes | -12 |  |  |  | 2018-06-20 14:47 |  |  |  |  | 2018-06-20 20:00 | Yes | 6 | 1204-Owner-v | 2018-07-31 14:16
VD-9001-104(005)-DWG-005 | 1 | E-6103 - Detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-104-DSH-001 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-05 |  |  | No | 745 | [9 empty] | No | 0
VD-9001-251-CAL-002 | 1 | INTERMEDIATE TUBESHEETS CALCULATION 1st CONVECTION SECTION - Lower - HE-1001 | HM-251 | KT – Kinetics Technology SpA | 2018-06-06 | 2018-08-29 18:10 | 2018-08-29 18:14 | Yes | 84 |  |  | 2018-09-09 11:13 | [5 empty] | 2018-09-09 11:13 | Yes | -3 | 1204-Owner-v | 2020-05-30 13:59
VD-9001-307A-PCJ-005 | 1 | Hydrostatic Test Procedure | MC-307A | KSB GERMANY | 2018-06-13 19:59 | 2018-09-25 17:01 | 2018-09-25 17:04 | Yes | 104 |  |  |  | 2018-09-30 11:00 |  |  |  |  | 2018-09-30 18:58 | Yes | -9
VD-9001-104(016)-DWG-007 | 1 | C-6103/TEX-6103 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-06-13 19:59 |  |  | No | 737 | [9 empty] | No | 0
VD-9001-104(016)-DWG-014 | 1 | C-6104/TEX-6104 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-06-13 19:59 |  |  | No | 737 | [9 empty] | No | 0
VD-9001-104(004)-ARP-001 | 1 | ST C-6101 / C-6101 - Torsional analysis for air compressor and driver train 1 | PR-104-SUB | AIR LIQUIDE | 2018-06-13 19:59 |  |  | No | 737 | [9 empty] | No | 0
VD-9001-251-DWG-040 | 1 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-05-31 12:39 | 2018-05-31 13:27 | 2018-05-31 13:29 | Yes | 0 |  |  | 2018-06-13 14:50 | [5 empty] | 2018-06-13 14:50 | Yes | -1
VD-9001-251-DWG-041 | 1 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-05-31 12:39 | 2018-05-31 13:27 | 2018-05-31 13:29 | Yes | 0 |  |  | 2018-06-13 14:50 | [5 empty] | 2018-06-13 14:50 | Yes | -1
VD-9001-251-DWG-042 | 1 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-05-31 12:39 | 2018-05-31 13:27 | 2018-05-31 13:29 | Yes | 0 |  |  | 2018-06-13 14:51 | [5 empty] | 2018-06-13 14:51 | Yes | -1
VD-9001-251-DWG-110 | 1 | plan and platforms – convection details | HM-251 | KT – Kinetics Technology SpA | 2018-05-31 12:40 | 2018-05-31 13:27 | 2018-05-31 13:30 | Yes | 0 |  |  | 2018-06-13 15:38 | [5 empty] | 2018-06-13 15:38 | Yes | -1 | 1204-Owner-v | 2018-07-11 09:44
VD-9001-257C-DWG-065 | 1 | DETAILS DRAWING (4137-0366/3) E-2001A | HM-257C | Brembana & Rolle S.p.A. | 2018-06-07 | 2018-10-11 16:52 | 2018-10-11 16:52 | Yes | 126 |  |  | 2018-10-13 11:00 | [5 empty] | 2018-10-13 11:00 | Yes | -12
VD-9001-257C-DWG-058 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0370/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-07 | 2018-10-11 17:53 | 2018-10-11 17:53 | Yes | 126 |  |  | 2018-10-23 15:03 | [5 empty] | 2018-10-23 15:03 | Yes | -2
VD-9001-257C-DWG-057 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0369/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-07 | 2018-10-11 16:59 | 2018-10-11 16:59 | Yes | 126 |  |  | 2018-10-13 18:04 | [5 empty] | 2018-10-13 18:04 | Yes | -12
VD-9001-104-DSH-061 | 2 | Moisture Analysers_EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-14 19:59 |  |  | No | 736 | [9 empty] | No | 0
VD-9001-202F-DWG-010 | 2 | Waste Heat Boiler - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-16 | 2018-09-18 13:43 | 2018-09-18 13:43 | Yes | 94 |  |  |  |  | 2018-10-02 11:58 |  |  |  | 2018-10-02 11:58 | Yes | 0 | 1204-Owner-v | 2018-12-18 10:10
VD-9001-104-DSH-032 | 1 | Flowmeter - EDS Equipment Data Sheet (diaphragm FE) | PR-104 | AIR LIQUIDE | 2018-06-16 19:59 |  |  | No | 734 | [9 empty] | No | 0
VD-9001-104(016)-DWG-010 | 1 | C-6104/TEX-6104 - Anchoring details (plate,bolt, etc) | PR-104-SUB | AIR LIQUIDE | 2018-06-16 19:59 |  |  | No | 734 | [9 empty] | No | 0
VD-9001-104(014)-DWG-005 | 1 | E-6108 D1 - Detail drawing equipment and piping | PR-104-SUB | AIR LIQUIDE | 2018-06-16 19:59 |  |  | No | 734 | [9 empty] | No | 0
VD-9001-104(009)-DWG-024 | 1 | P-6103A / P-6103BA-B - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-06-16 19:59 |  |  | No | 734 | [9 empty] | No | 0
VD-9001-104(009)-DWG-030 | 1 | P-6105A / P-6105BA-B - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-06-16 19:59 |  |  | No | 734 | [9 empty] | No | 0
VD-9001-254-PPL-319 | 5 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2018-06-10 | 2018-12-16 10:53 | 2018-12-16 10:53 | Yes | 189 |  |  |  | 2019-01-12 10:19 |  |  |  |  | 2019-01-12 10:19 | Yes | 13 | 1204-Owner-v | 2018-12-23 11:13
VD-9001-254-PPL-359 | 3 | LAYOUT & TYPICAL WIRING FOR BMS | HM-254 | AZAR AB | 2018-06-10 | 2018-06-10 11:39 | 2018-06-10 11:39 | Yes | 0 |  |  | 2018-06-27 10:58 | [5 empty] | 2018-06-27 10:58 | Yes | 3
VD-9001-254-LST-216 | 6 | ELECTERICAL LOAD LIST | HM-254 | AZAR AB | 2018-06-10 | 2018-07-01 12:49 | 2018-07-01 12:49 | Yes | 21 |  |  | 2018-07-28 09:59 | [5 empty] | 2018-07-28 09:59 | Yes | 13 | 1204-Owner-v | 2018-09-09 10:30
VD-9001-251-CAL-001 | 2 | MECHANICAL CALCULATION CATALYST TUBE | HM-251 | KT – Kinetics Technology SpA | 2018-06-08 | 2018-08-29 17:58 | 2018-08-29 18:14 | Yes | 82 |  |  | 2018-09-22 11:28 | [5 empty] | 2018-09-22 11:28 | Yes | 10 | 1204-Owner-v | 2019-04-08 22:00
VD-9001-104-PID-024 | 2 | PID Liquid Nitrogen Storage | PR-104 | AIR LIQUIDE | 2018-06-17 19:59 |  |  | No | 733 | [9 empty] | No | 0
VD-9001-104-DSH-003 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-17 19:59 |  |  | No | 733 | [9 empty] | No | 0
VD-9001-104-DSH-002 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-17 19:59 |  |  | No | 733 | [9 empty] | No | 0
VD-9001-104(005)-DWG-002 | 3 | E-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-17 19:59 |  |  | No | 733 | [9 empty] | No | 0
VD-9001-104(005)-DWG-010 | 3 | E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-12 |  |  | No | 738 | [9 empty] | No | 0
VD-9001-104(005)-DWG-003 | 3 | E-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-12 |  |  | No | 738 | [9 empty] | No | 0
VD-9001-104(004)-DWG-026 | 1 | ST C-6102 - Vacuum condenser detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-12 |  |  | No | 738 | [9 empty] | No | 0
VD-9001-104(004)-IPM-007 | 1 | C-6101 / C-6102 - Shop inspection procedure - Compressor | PR-104-SUB | AIR LIQUIDE | 2018-06-12 |  |  | No | 738 | [9 empty] | No | 0
VD-9001-251-CAL-011 | 2 | MECHANICAL CALCULATION - CONVECTION COILS | HM-251 | KT – Kinetics Technology SpA | 2018-06-12 | 2018-08-29 18:12 | 2018-08-29 18:14 | Yes | 78 |  |  | 2018-09-09 11:26 | [5 empty] | 2018-09-09 11:26 | Yes | -3 | 1204-Owner-v | 2019-05-30 14:04
VD-9001-251-CAL-012 | 2 | MECHANICAL CALCULATION INLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-06-12 | 2018-08-29 18:13 | 2018-08-29 18:14 | Yes | 78 |  |  | 2018-09-09 11:27 | [5 empty] | 2018-09-09 11:28 | Yes | -3
VD-9001-251-CAL-013 | 2 | MECHANICAL CALCULATION OUTLET SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-06-12 | 2018-08-29 18:14 | 2018-08-29 18:14 | Yes | 78 |  |  | 2018-09-22 11:30 | 2018-09-02 16:32 |  |  |  |  | 2018-09-22 11:30 | Yes | 10 | 1204-Owner-v | 2019-04-29 17:11
VD-9001-257C-ITP-001 | 2 | INSPECTION & TESTING PLAN (4137-0364/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-12 | 2018-07-10 18:37 | 2018-07-10 18:37 | Yes | 28 |  |  | 2018-07-21 09:39 | [5 empty] | 2018-07-21 09:39 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:40
VD-9001-257C-DWG-045 | 2 | DETAILS DRAWING (4137-0371/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-19 | 2018-10-11 17:55 | 2018-10-11 17:55 | Yes | 114 |  |  | 2018-11-03 16:59 | [5 empty] | 2018-11-03 16:59 | Yes | 9
VD-9001-257C-DWG-023 | 1 | SHIPPING DRAWING (4137-0367/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-19 | 2018-10-11 16:57 | 2018-10-11 16:57 | Yes | 114 |  |  | 2018-10-13 16:33 | [5 empty] | 2018-10-13 16:33 | Yes | -12 | 1204-Owner-v | 2019-04-22 10:17
VD-9001-740A-GAD-00083 | 3 | General Arrangement Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 09:58 | 2018-06-24 09:58 | Yes | 10 |  |  |  | 2018-07-16 14:03 |  |  |  |  | 2018-07-16 14:03 | Yes | 8
VD-9001-740A-GAD-00084 | 3 | General Arrangement Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 09:59 | 2018-06-24 09:59 | Yes | 10 |  |  |  | 2018-07-16 14:03 |  |  |  |  | 2018-07-16 14:03 | Yes | 8
VD-9001-740A-SAD-00083 | 1 | Shop Assembly Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 10:02 | 2018-06-24 10:02 | Yes | 10 |  |  |  | 2018-07-16 14:04 |  |  |  |  | 2018-07-16 14:04 | Yes | 8
VD-9001-740A-SAD-00084 | 1 | Shop Assembly Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 10:04 | 2018-06-24 10:04 | Yes | 10 |  |  |  | 2018-07-16 14:04 |  |  |  |  | 2018-07-16 14:04 | Yes | 8
VD-9001-740A-SPD-00083 | 1 | Single Part Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 10:05 | 2018-06-24 10:05 | Yes | 10 |  |  |  | 2018-07-16 14:00 |  |  |  |  | 2018-07-16 14:00 | Yes | 8
VD-9001-740A-SPD-00084 | 1 | Single Part Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-06-14 | 2018-06-24 10:06 | 2018-06-24 10:06 | Yes | 10 |  |  |  | 2018-07-16 13:59 |  |  |  |  | 2018-07-16 13:59 | Yes | 8
VD-9001-251-DWG-030 | 1 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 14:49 | 2018-06-11 14:59 | Yes | 2 |  |  |  | 2018-06-18 10:03 |  |  |  |  | 2018-06-18 10:03 | Yes | -7
VD-9001-251-DWG-035 | 2 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 14:52 | 2018-06-11 14:55 | Yes | 2 |  |  | 2018-06-13 17:06 | [5 empty] | 2018-06-13 17:06 | Yes | -12
VD-9001-251-DWG-036 | 2 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 14:53 | 2018-06-11 14:53 | Yes | 2 |  |  | 2018-06-13 17:07 | [5 empty] | 2018-06-13 17:07 | Yes | -12
VD-9001-251-DWG-037 | 2 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 14:56 | 2018-06-11 14:58 | Yes | 2 |  |  | 2018-06-13 17:08 | [5 empty] | 2018-06-13 17:08 | Yes | -12 | 1204-Owner-v | 2019-03-10 14:51
VD-9001-251-DWG-038 | 2 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 14:58 | 2018-06-11 14:59 | Yes | 2 |  |  | 2018-06-13 17:08 | [5 empty] | 2018-06-13 17:08 | Yes | -12
VD-9001-251-DWG-039 | 2 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 15:00 | 2018-06-11 15:07 | Yes | 2 |  |  | 2018-06-13 17:09 | [5 empty] | 2018-06-13 17:09 | Yes | -12
VD-9001-251-DWG-074 | 2 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-06-09 14:14 | 2018-06-11 15:04 | 2018-06-11 15:08 | Yes | 2 |  |  | 2018-06-18 18:01 | [5 empty] | 2018-06-18 18:01 | Yes | -7
VD-9001-104(014)-DWG-009 | 2 | E-6124 - Civil work drawing / Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(014)-DWG-010 | 1 | E-6124 - Vessel details drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(003)-DWG-007 | 1 | T-6102 - Nozzle book | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(002)-CAL-002 | 2 | T-6101 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(007)-CAL-002 | 2 | DR-6101A / DR-6101B - Fatigue calculation note | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-201B-ITP-001 | 3 | INSPECTION & TESTING PLAN (4134-0359/ITP) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-23 19:59 | 2018-06-15 13:06 | 2018-06-15 13:06 | Yes | -8 |  |  | 2018-07-04 10:22 | [5 empty] | 2018-07-04 20:00 | Yes | 5 | 1204-Owner-v | 2020-01-01 12:44
VD-9001-104(002)-LST-002 | 1 | T-6101 - Parts list | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(003)-LST-001 | 2 | T-6102 - Parts list (for client) | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(007)-DWG-003 | 3 | DR-6101A / DR-6101B - Bottom part detail drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-104(009)-DWG-018 | 1 | Exchanger box E03 - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-06-23 19:59 |  |  | No | 727 | [9 empty] | No | 0
VD-9001-404A-DWG-001 | 2 | Drawing | PI-404A | KVC CO., LTD. | 2018-06-24 09:28 | 2018-06-11 08:50 | 2018-06-11 08:51 | Yes | -13 |  |  | 2018-06-11 11:16 | [5 empty] | 2018-06-11 11:17 | Yes | -14 | 1204-Owner-v | 2019-02-02 14:15
VD-9001-251-LST-002 | 1 | UTILITIES COMSUMPTION LIST | HM-251 | KT – Kinetics Technology SpA | 2018-06-17 | 2018-09-18 16:14 | 2018-09-18 16:16 | Yes | 93 |  |  |  |  | 2018-10-14 17:53 |  |  |  | 2018-10-14 17:53 | Yes | 12
VD-9001-104(009)-DWG-006 | 2 | HP/ LP Cold box - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-06-24 19:59 |  |  | No | 726 | [9 empty] | No | 0
VD-9001-104(014)-LST-002 | 1 | E-6124 - Parts list | PR-104-SUB | AIR LIQUIDE | 2018-06-24 19:59 |  |  | No | 726 | [9 empty] | No | 0
VD-9001-104(006)-DWG-002 | 2 | E-6102 - Name plates | PR-104-SUB | AIR LIQUIDE | 2018-06-24 19:59 |  |  | No | 726 | [9 empty] | No | 0
VD-9001-104(007)-DWG-006 | 2 | DR-6101A / DR-6101B - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-06-24 19:59 |  |  | No | 726 | [9 empty] | No | 0
VD-9001-104-DSH-037 | 1 | Cryo Temperature - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-24 19:59 |  |  | No | 726 | [9 empty] | No | 0
VD-9001-404A-ITP-001 | 1 | Test and Inspection Plan | PI-404A | KVC CO., LTD. | 2018-06-25 11:23 | 2018-06-11 13:24 | 2018-06-11 13:25 | Yes | -14 |  |  | 2018-06-11 17:12 | [5 empty] | 2018-06-11 17:13 | Yes | -14
VD-9001-404A-DIS-001 | 1 | Vendor Documents Index & Schedule | PI-404A | KVC CO., LTD. | 2018-06-25 11:30 | 2018-06-11 13:24 | 2018-06-11 13:24 | Yes | -14 |  |  | 2018-06-11 14:11 | [5 empty] | 2018-06-11 14:12 | Yes | -14 | 1204-Owner-v | 2019-01-04 21:10
VD-9001-202F-WPS-001 | 1 | Steam Superheater - Welding Procedure Specification (WPS) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-18 |  |  | No | 732 | [9 empty] | No | 0
VD-9001-202F-PQR-001 | 1 | Steam Superheater - Procedure Qualification Record (PQR) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-18 |  |  | No | 732 | [9 empty] | No | 0
VD-9001-461AF-INX-001 | 2 | FINAL DATA BOOK INDEX | PI-461AF | Van Leeuwen | 2018-06-25 14:23 | 2018-06-13 17:30 | 2018-06-13 17:37 | Yes | -12 |  |  | 2018-06-14 11:52 | [5 empty] | 2018-06-14 11:52 | Yes | -13
VD-9001-404A-PCJ-001 | 1 | Hydrostatic Test Procedures | PI-404A | KVC CO., LTD. | 2018-06-25 14:35 | 2018-06-14 10:11 | 2018-06-14 10:11 | Yes | -11 |  |  | 2018-06-24 08:50 | [5 empty] | 2018-06-24 08:50 | Yes | -4 | 1204-Owner-v | 2019-02-02 14:18
VD-9001-254-DSH-218 | 2 | DATA SHEET FOR MOTORS FOR FORCED DRAFT FANS | HM-254 | AZAR AB | 2018-06-18 | 2018-09-01 13:18 | 2018-09-01 13:18 | Yes | 75 |  |  |  | 2018-09-05 17:09 |  |  |  |  | 2018-09-05 17:09 | Yes | -10 | 1204-Owner-v | 2018-12-02 09:23
VD-9001-254-DSH-225 | 2 | DATA SHEET FOR CABLES AND WIRES | HM-254 | AZAR AB | 2018-06-18 | 2018-08-26 15:20 | 2018-08-26 15:20 | Yes | 69 |  |  | 2018-09-05 17:05 | [5 empty] | 2018-09-05 17:05 | Yes | -4
VD-9001-401A-MTC-001 | 0 | MATERIAL TEST CERTIFICATE | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-06-11 | 2018-10-30 13:31 | 2018-10-30 13:37 | Yes | 141 |  |  |  | 2018-11-03 16:22 |  |  |  |  | 2018-11-03 16:22 | Yes | -10
VD-9001-104(014)-DWG-011 | 1 | E-6124 - Bundle details drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-104(005)-WBK-001 | 1 | E-6101/E-6103 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-104(005)-DWG-001 | 2 | E-6101/E-6103 - Battery General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-104-DSH-017 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-104-DSH-016 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-104-DSH-009 | 1 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-06-25 19:59 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-251-DWG-106 | 2 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-06-19 | 2019-03-13 14:24 | 2019-03-13 14:24 | Yes | 267 |  |  |  | 2019-04-27 14:37 |  |  |  |  | 2019-04-27 14:37 | Yes | 31 | 1204-Owner-v | 2019-04-08 09:42
VD-9001-251-DWG-107 | 2 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-06-19 | 2019-03-13 14:24 | 2019-03-13 14:25 | Yes | 267 |  |  |  | 2019-04-27 17:01 |  |  |  |  | 2019-04-27 17:01 | Yes | 31 | 1204-Owner-v | 2019-04-08 09:42
VD-9001-202F-PCJ-005 | 1 | Steam Superheater - NDE Procedures (RT, UT,VT,MT, PT) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-19 | 2018-08-03 21:58 | 2018-08-03 22:10 | Yes | 45 |  |  | 2018-08-22 10:49 | [5 empty] | 2018-08-22 10:49 | Yes | 5 | 1204-Owner-v | 2020-04-29 09:55
VD-9001-202F-PPL-007 | 0 | Layout - Cut-Free System Boiler | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-12 | 2018-06-12 14:49 | 2018-06-12 14:50 | Yes | 0 |  |  |  |  | 2018-06-23 11:32 |  |  |  | 2018-06-23 11:32 | Yes | -3
VD-9001-202F-PPL-008 | 0 | Layout - Cut-Free System Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-12 | 2018-06-12 14:57 | 2018-06-12 14:57 | Yes | 0 |  |  |  |  | 2018-06-19 16:12 |  |  |  | 2018-06-19 16:12 | Yes | -7
VD-9001-201B-GAD-001 | 2 | GENERAL ARRANGEMENT (4134/0359) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-14 | 2018-06-27 11:29 | 2018-06-27 11:29 | Yes | 13 |  |  |  | 2018-10-22 16:18 |  |  |  |  | 2018-10-22 18:57 | Yes | 103 | 1204-Owner-v | 2018-07-08 10:39
VD-9001-104-DSH-046 | 2 | Cryo PSV - EDS Equipment Data Sheet (pressure) | PR-104 | AIR LIQUIDE | 2018-06-26 20:15 |  |  | No | 724 | [9 empty] | No | 0
VD-9001-104-DSH-047 | 2 | Cryo TSV - EDS Equipment Data Sheet (thermal) | PR-104 | AIR LIQUIDE | 2018-06-26 20:15 |  |  | No | 724 | [9 empty] | No | 0
VD-9001-201B-DWG-001 | 2 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-26 20:15 | 2018-06-27 11:23 | 2018-06-27 11:23 | Yes | 1 |  |  |  | 2018-10-17 11:53 |  |  |  |  | 2018-10-17 18:57 | Yes | 98
VD-9001-204D-WMP-010 | 1 | WELDING DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-06-13 09:40 | 2018-06-13 12:23 | 2018-06-13 12:23 | Yes | 0 |  |  |  |  | 2018-06-30 10:59 |  |  |  | 2018-06-30 20:00 | Yes | 3
VD-9001-204D-DWG-005 | 2 | INTERNAL PARTS DETAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-06-13 09:40 | 2018-06-13 11:58 | 2018-06-13 11:58 | Yes | 0 |  |  |  | 2018-07-17 14:33 |  |  |  |  | 2018-07-17 14:33 | Yes | 20
VD-9001-204D-DWG-007 | 2 | DRYERS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-06-13 09:40 | 2018-06-13 12:12 | 2018-06-13 12:12 | Yes | 0 |  |  | 2018-07-17 13:44 | [5 empty] | 2018-07-17 13:44 | Yes | 20
VD-9001-105-DIG-201 | 5 | Wiring diagram of J.B. | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-06-13 12:59 | 2018-06-14 13:26 | 2018-06-14 13:27 | Yes | 1 |  |  | 2018-07-02 09:37 | [5 empty] | 2018-07-02 09:37 | Yes | 4
VD-9001-104(008)-DSH-001 | 1 | AE-6187-CM01 - EDS Equipment data sheet of Fan Motors | PR-104-SUB | AIR LIQUIDE | 2018-06-27 20:00 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-201B-DWG-015 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4134-0359/BMN) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-27 20:00 | 2018-06-27 11:25 | 2018-06-27 11:27 | Yes | 0 |  |  | 2018-07-14 11:30 | [5 empty] | 2018-07-14 20:00 | Yes | 3 | 1204-Owner-v | 2019-04-22 09:11
VD-9001-251-CAL-015 | 2 | STRUCTURAL STATICAL CALCULATONS | HM-251 | KT – Kinetics Technology SpA | 2018-06-14 11:40 | 2018-06-14 17:12 | 2018-06-14 17:20 | Yes | 0 |  |  | 2018-06-25 09:40 | [5 empty] | 2018-06-25 09:40 | Yes | -3
VD-9001-251-DWG-051 | 2 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-06-14 11:40 | 2018-06-14 17:18 | 2018-06-14 17:20 | Yes | 0 |  |  | 2018-06-18 17:35 | [5 empty] | 2018-06-18 17:35 | Yes | -10
VD-9001-251-DWG-052 | 2 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-06-14 11:40 | 2018-06-14 17:18 | 2018-06-14 17:20 | Yes | 0 |  |  | 2018-06-18 17:37 | [5 empty] | 2018-06-18 17:37 | Yes | -10
VD-9001-257C-DWG-064 | 2 | DETAILS DRAWING (4137-0367/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-21 | 2018-10-11 16:55 | 2018-10-11 16:55 | Yes | 112 |  |  | 2018-11-10 15:39 | [5 empty] | 2018-11-10 15:39 | Yes | 16
VD-9001-104(011)-CAL-002 | 1 | Cryogenic Globe automatic valves - Calculation sheet for globe valves ( included noise calculation) | PR-104-SUB | AIR LIQUIDE | 2018-06-28 20:00 |  |  | No | 722 | [9 empty] | No | 0
VD-9001-104(003)-DWG-006 | 2 | T-6102 - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-06-28 20:00 |  |  | No | 722 | [9 empty] | No | 0
VD-9001-257C-ITP-008 | 2 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:41 | 2018-07-10 18:42 | Yes | 16 |  |  | 2018-07-21 09:05 | [5 empty] | 2018-07-21 09:05 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-257C-ITP-007 | 2 | INSPECTION & TESTING PLAN (4137-0370/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:41 | 2018-07-10 18:41 | Yes | 16 |  |  | 2018-07-21 09:07 | [5 empty] | 2018-07-21 09:07 | Yes | -3 | 1204-Owner-v | 2020-01-01 10:35
VD-9001-257C-ITP-006 | 2 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:40 | 2018-07-10 18:40 | Yes | 16 |  |  | 2018-07-21 09:12 | [5 empty] | 2018-07-21 09:12 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-201B-DWG-024 | 0 | INTERNAL DETAILS DRAWING R-1004 (4134-0359/H) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-18 | 2018-06-20 11:27 | 2018-06-20 11:27 | Yes | 2 |  |  | 2018-10-28 14:49 | [5 empty] | 2018-10-28 20:00 | Yes | 116
VD-9001-257C-ITP-004 | 2 | INSPECTION & TESTING PLAN (4137-0367/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:39 | 2018-07-10 18:40 | Yes | 16 |  |  | 2018-07-21 09:22 | [5 empty] | 2018-07-21 09:22 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-257C-ITP-003 | 2 | INSPECTION & TESTING PLAN (4137-0366/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:39 | 2018-07-10 18:39 | Yes | 16 |  |  | 2018-07-21 09:25 | [5 empty] | 2018-07-21 09:25 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:41
VD-9001-257C-ITP-002 | 2 | INSPECTION & TESTING PLAN (4137-0365/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-24 | 2018-07-10 18:38 | 2018-07-10 18:38 | Yes | 16 |  |  | 2018-07-21 09:33 | [5 empty] | 2018-07-21 09:33 | Yes | -3 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-201-PCJ-005 | 2 | HYDROTEST PROCEDURE | PV-201 | ATB RIVA CALZONI SpA | 2018-06-24 | 2018-06-26 17:53 | 2018-06-26 17:54 | Yes | 2 |  |  | 2018-07-22 10:36 | [5 empty] | 2018-07-22 10:36 | Yes | 12 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-202F-ITP-002 | 1 | Steam Superheater - Inspection Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-24 | 2018-07-05 19:30 | 2018-07-05 19:30 | Yes | 11 |  |  | 2018-07-15 15:10 | [5 empty] | 2018-07-15 15:10 | Yes | -4 | 1204-Owner-v | 2020-01-01 12:46
VD-9001-307A-ITP-014 | 1 | Inspection Test Plan (Mechanical Seal) | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-11 16:35 | 2018-07-11 16:35 | Yes | 10 |  |  | 2018-08-06 09:43 | [5 empty] | 2018-08-06 19:59 | Yes | 12 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-DSH-008 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DSH-007 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DSH-006 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DSH-005 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DIS-001 | 1 | Drawing / Document schedule | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  | 2018-10-05 16:21 | Yes | 719 | [6 empty] | 2018-10-07 11:59 | 2018-10-07 11:59 |  | Yes | 0
VD-9001-307A-PCJ-001 | 1 | Painting Procedure | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-09-25 17:01 | 2018-09-25 17:03 | Yes | 86 |  |  |  | 2018-10-13 08:45 |  |  |  |  | 2018-10-13 18:57 | Yes | 4
VD-9001-307A-PCJ-003 | 1 | Welding Procedure Specification (WPS) and Procedure Qualification Record (PQR) | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-09-07 16:59 | 2018-09-07 17:00 | Yes | 68 |  |  | 2018-09-15 10:52 | [5 empty] | 2018-09-15 19:58 | Yes | -6
VD-9001-307A-PCJ-012 | 1 | Shopacceptance test procedure | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-PCJ-014 | 1 | Heat treatmant Procedure | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DWG-008 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DWG-006 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-301-LST-016 | 1 | instrument list circulator train | MC-301 | Siemens AG | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-301-LST-012 | 1 | instrument list syngas train | MC-301 | Siemens AG | 2018-07-01 20:00 |  |  | No | 719 | [9 empty] | No | 0
VD-9001-307A-DSH-030 | 2 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-09 13:13 | 2018-07-09 13:14 | Yes | 8 |  |  |  | 2018-07-14 14:43 |  |  |  |  | 2018-07-14 20:00 | Yes | -9
VD-9001-307A-DSH-029 | 2 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-09 13:13 | 2018-07-09 13:13 | Yes | 8 |  |  |  | 2018-07-14 14:46 |  |  |  |  | 2018-07-14 20:00 | Yes | -9
VD-9001-307A-DSH-028 | 2 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-09 13:12 | 2018-07-09 13:13 | Yes | 8 |  |  |  | 2018-07-14 14:51 |  |  |  |  | 2018-07-14 20:00 | Yes | -9
VD-9001-307A-DSH-027 | 2 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-09 13:12 | 2018-07-09 13:13 | Yes | 8 |  |  |  | 2018-07-14 14:53 |  |  |  |  | 2018-07-14 20:00 | Yes | -9
VD-9001-307A-DSH-026 | 2 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-01 20:00 | 2018-07-09 13:12 | 2018-07-09 13:13 | Yes | 8 |  |  |  | 2018-07-14 14:55 |  |  |  |  | 2018-07-14 20:00 | Yes | -9
VD-9001-204C-PCJ-028 | 2 | FERRITE CHECK PROCEDURE | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-01 20:00 | 2018-07-16 12:07 | 2018-07-16 12:08 | Yes | 15 |  |  | 2018-08-07 11:30 | [5 empty] | 2018-08-07 19:59 | Yes | 8 | 1204-Owner-v | 2018-12-16 21:55
VD-9001-251-DWG-113 | 1 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-06-25 | 2018-06-25 17:59 | 2018-06-25 17:59 | Yes | 0 |  |  | 2018-06-26 16:28 | [5 empty] | 2018-06-26 16:28 | Yes | -13 | 1204-Owner-v | 2018-07-08 12:03
VD-9001-251-DWG-112 | 1 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-06-25 | 2018-06-25 17:56 | 2018-06-25 17:56 | Yes | 0 |  |  |  | 2018-06-26 16:24 |  |  |  |  | 2018-06-26 16:24 | Yes | -13 | 1204-Owner-v | 2018-07-10 14:25
VD-9001-251-DWG-030 | 2 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-06-25 | 2018-06-25 17:53 | 2018-06-25 17:54 | Yes | 0 |  |  |  | 2018-06-26 16:21 |  |  |  |  | 2018-06-26 16:21 | Yes | -13 | 1204-Owner-v | 2018-07-16 15:43
VD-9001-251-DWG-028 | 3 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-06-21 | 2018-06-25 17:49 | 2018-06-25 17:49 | Yes | 4 |  |  | 2018-06-28 10:54 | [5 empty] | 2018-06-28 10:54 | Yes | -11
VD-9001-251-DWG-050 | 3 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-06-20 | 2018-10-12 11:54 | 2018-10-12 11:57 | Yes | 114 |  |  | 2018-10-27 14:55 | [5 empty] | 2018-10-27 14:55 | Yes | 1 | 1204-Owner-v | 2019-04-06 10:54
VD-9001-251-SDG-001 | 1 | N.D.E. ON CAST PARTS | HM-251 | KT – Kinetics Technology SpA | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-104(003)-IPM-001 | 2 | T-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-07-02 20:00 |  |  | No | 718 | [9 empty] | No | 0
VD-9001-104(011)-ITP-001 | 1 | Warm automatic globe valve - Inspection Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-07-02 20:00 |  |  | No | 718 | [9 empty] | No | 0
VD-9001-301-PID-018 | 2 | P+I Diagram Control oil Circulator Turbine | MC-301 | Siemens AG | 2018-06-27 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-301-PID-015 | 2 | P+I Diagram Oil Circulator Train | MC-301 | Siemens AG | 2018-06-27 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-301-PID-008 | 2 | P+I Diagram Steam + Drainage Syngas Turbine | MC-301 | Siemens AG | 2018-06-27 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-104(008)-DWG-009 | 1 | J-6188 - Inter Condenser & Ejector & Vacuum Unit- drawing | PR-104-SUB | AIR LIQUIDE | 2018-06-27 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-104(011)-IPM-001 | 1 | Inspection Test Procedure | PR-104-SUB | AIR LIQUIDE | 2018-06-27 |  |  | No | 723 | [9 empty] | No | 0
VD-9001-104-REQ-015 | 3 | TK-6150_TRS Technical Requisition Sheet | PR-104 | AIR LIQUIDE | 2018-06-25 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-204B-WPS-001 | 4 | Welding Procedure Specification (WPS) For S.S | PV-204B | ABAN AIR COOLER. | 2018-06-26 | 2018-06-25 13:50 | 2018-06-25 13:51 | Yes | -1 |  |  | 2018-06-30 09:17 | [5 empty] | 2018-06-30 09:18 | Yes | -9 | 1204-Owner-v | 2019-02-02 13:36
VD-9001-257C-ITP-005 | 1 | INSPECTION & TESTING PLAN (4137-0368/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-26 | 2018-07-10 18:40 | 2018-07-10 18:45 | Yes | 14 |  |  | 2018-07-19 17:48 | [5 empty] | 2018-07-19 17:48 | Yes | -5 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-202F-PPL-008 | 1 | Layout - Cut-Free System Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-20 | 2018-06-21 14:53 | 2018-06-21 14:55 | Yes | 1 |  |  |  |  | 2018-07-02 09:04 |  |  |  | 2018-07-02 09:04 | Yes | -3
VD-9001-307A-ITP-011 | 1 | Inspection Test Plan (Turbine) | MC-307A | KSB GERMANY | 2018-07-03 20:00 | 2018-08-02 13:51 | 2018-08-02 14:00 | Yes | 30 |  |  |  | 2018-09-01 09:52 |  |  |  |  | 2018-09-01 19:58 | Yes | 16 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-PCJ-015 | 1 | Long term preservation procedure | MC-307A | KSB GERMANY | 2018-07-03 20:00 | 2018-09-25 17:03 | 2018-09-25 17:04 | Yes | 84 |  |  |  | 2018-10-08 09:23 | 2018-10-08 09:22 |  |  |  | 2018-10-08 18:58 | Yes | -1
VD-9001-307A-ITP-013 | 1 | Inspection Test Plan (Seal System) | MC-307A | KSB GERMANY | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-204C-DWG-038 | 1 | WELDING MAP DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-03 20:00 | 2018-07-16 21:24 | 2018-07-16 21:26 | Yes | 13 |  |  | 2018-08-07 11:33 | [5 empty] | 2018-08-07 19:59 | Yes | 8 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-307A-LST-046 | 1 | Deviation List | MC-307A | KSB GERMANY | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-204C-DWG-047 | 1 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-03 20:00 | 2018-07-23 12:53 | 2018-07-23 12:53 | Yes | 20 |  |  |  | 2018-08-06 10:57 |  |  |  |  | 2018-08-06 19:59 | Yes | 0
VD-9001-104(004)-IPM-006 | 1 | C-6101 / C-6102 - Shop inspection procedure - Auxiliaries | PR-104-SUB | AIR LIQUIDE | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(009)-DWG-032 | 1 | P-6105A / P-6105BA-B - detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(009)-DWG-033 | 1 | P-6105A / P-6105BA-B - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-104(009)-DWG-031 | 1 | P-6105A / P-6105BA-B - detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-03 20:00 |  |  | No | 717 | [9 empty] | No | 0
VD-9001-307A-ITP-005 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-20 14:55 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-307A-ITP-006 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-20 14:56 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-307A-ITP-007 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-20 14:56 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-307A-ITP-008 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-06-20 14:56 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-104(005)-ITP-003 | 1 | E-6101/E-6103 - Aluminium piping Inspection Test Plan / quality plan | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(009)-DWG-026 | 1 | P-6103A / P-6103BA-B - detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(009)-DWG-027 | 1 | P-6103A / P-6103BA-B - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(009)-DWG-025 | 1 | P-6103A / P-6103BA-B - detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(014)-IPM-002 | 1 | E-6108/E-6108-D1 - Equipment and piping Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104-EQL-001 | 2 | Main equipment list | PR-104 | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-DWG-005 | 3 | AE-6187 - Civil work drawing– Anchorage Arrangement | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-DWG-006 | 3 | AE-6187 – Civil work drawing - Loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104(008)-DWG-007 | 3 | AE-6187 – Civil work drawing - Anchorage details | PR-104-SUB | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104-DSH-018 | 2 | EDS Equipment Data Sheet for ACC | PR-104 | AIR LIQUIDE | 2018-07-04 20:00 |  |  | No | 716 | [9 empty] | No | 0
VD-9001-104-DSH-019 | 2 | EDS Equipment data sheet - PBUC | PR-104 | AIR LIQUIDE | 2018-07-05 20:00 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(003)-CAL-001 | 2 | T-6102 - Column calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-07-05 20:00 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(007)-CAL-001 | 2 | DR-6101A / DR-6101B - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-05 20:00 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(004)-IPM-002 | 1 | C-6101 / C-6102 - Hydrostatic / Pneumatic tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-07-05 20:00 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-104(014)-ITP-002 | 2 | E-6124 - Inspection and Test Plan | PR-104-SUB | AIR LIQUIDE | 2018-07-05 20:00 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-202F-PPL-007 | 1 | Layout - Cut-Free System Boiler | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-24 | 2018-06-25 15:52 | 2018-06-25 15:52 | Yes | 1 |  |  |  |  | 2018-06-28 15:52 |  |  |  | 2018-06-28 15:52 | Yes | -11
VD-9001-202F-ISO-027 | 0 | Superheated Steam Pipe (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:52 | 2018-06-25 17:52 | Yes | 2 |  |  |  |  | 2018-07-19 12:43 |  |  |  | 2018-07-19 12:43 | Yes | 10
VD-9001-202F-ISO-028 | 0 | Superheated Steam Pipe (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:58 | 2018-06-25 17:58 | Yes | 2 |  |  |  |  | 2018-07-19 12:40 |  |  |  | 2018-07-19 12:40 | Yes | 10
VD-9001-202F-ISO-029 | 0 | Boiler Feed Water Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:59 | 2018-06-25 17:59 | Yes | 2 |  |  |  |  | 2018-07-19 12:17 |  |  |  | 2018-07-19 12:17 | Yes | 10
VD-9001-202F-ISO-030 | 0 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 18:03 | 2018-06-25 18:03 | Yes | 2 |  |  |  |  | 2018-07-19 12:12 |  |  |  | 2018-07-19 12:12 | Yes | 10
VD-9001-202F-ISO-031 | 0 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 18:04 | 2018-06-25 18:04 | Yes | 2 |  |  |  |  | 2018-07-19 12:08 |  |  |  | 2018-07-19 12:08 | Yes | 10
VD-9001-202F-ISO-003 | 0 | Isometric - Riser R1A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:07 | 2018-06-25 17:07 | Yes | 2 |  |  |  |  | 2018-07-17 10:41 |  |  |  | 2018-07-17 10:41 | Yes | 8 | 1204-Owner-v | 2019-05-11 08:31
VD-9001-202F-ISO-004 | 0 | Isometric - Riser R2A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:08 | 2018-06-25 17:09 | Yes | 2 |  |  |  |  | 2018-07-19 17:46 |  |  |  | 2018-07-19 17:46 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-005 | 0 | Isometric - Riser R3A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:12 | 2018-06-25 17:12 | Yes | 2 |  |  |  |  | 2018-07-19 17:44 |  |  |  | 2018-07-19 17:44 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-006 | 0 | Isometric - Riser R4A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:13 | 2018-06-25 17:13 | Yes | 2 |  |  |  |  | 2018-07-19 17:43 |  |  |  | 2018-07-19 17:43 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-007 | 0 | Isometric - Riser R5A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:14 | 2018-06-25 17:14 | Yes | 2 |  |  |  |  | 2018-07-19 17:42 |  |  |  | 2018-07-19 17:42 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-008 | 0 | Isometric - Riser R6A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:19 | 2018-06-25 17:19 | Yes | 2 |  |  |  |  | 2018-07-19 17:40 |  |  |  | 2018-07-19 17:40 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-009 | 0 | Isometric - Downcomer D1A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:20 | 2018-06-25 17:20 | Yes | 2 |  |  |  |  | 2018-07-19 17:39 |  |  |  | 2018-07-19 17:39 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-010 | 0 | Isometric - Downcomer D2A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:26 | 2018-06-25 17:26 | Yes | 2 |  |  |  |  | 2018-07-19 17:38 |  |  |  | 2018-07-19 17:38 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-011 | 0 | Isometric - Downcomer D3A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:27 | 2018-06-25 17:27 | Yes | 2 |  |  |  |  | 2018-07-19 17:35 |  |  |  | 2018-07-19 17:35 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-012 | 0 | Isometric - Downcomer D4A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:28 | 2018-06-25 17:29 | Yes | 2 |  |  |  |  | 2018-07-19 17:34 |  |  |  | 2018-07-19 17:34 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:39
VD-9001-202F-ISO-013 | 0 | Isometric - Downcomer D5A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:30 | 2018-06-25 17:30 | Yes | 2 |  |  |  |  | 2018-07-19 17:30 |  |  |  | 2018-07-19 17:30 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-014 | 0 | Isometric - Downcomer D6A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:31 | 2018-06-25 17:31 | Yes | 2 |  |  |  |  | 2018-07-19 17:29 |  |  |  | 2018-07-19 17:29 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-015 | 0 | Isometric - Riser R1B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:32 | 2018-06-25 17:32 | Yes | 2 |  |  |  |  | 2018-07-19 17:27 |  |  |  | 2018-07-19 17:27 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-016 | 0 | Isometric - Riser R2B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:33 | 2018-06-25 17:33 | Yes | 2 |  |  |  |  | 2018-07-19 17:24 |  |  |  | 2018-07-19 17:24 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-017 | 0 | Isometric - Riser R3B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:34 | 2018-06-25 17:34 | Yes | 2 |  |  |  |  | 2018-07-19 17:22 |  |  |  | 2018-07-19 17:22 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-018 | 0 | Isometric - Riser R4B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:36 | 2018-06-25 17:37 | Yes | 2 |  |  |  |  | 2018-07-19 17:21 |  |  |  | 2018-07-19 17:21 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-019 | 0 | Isometric - Riser R5B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:38 | 2018-06-25 17:39 | Yes | 2 |  |  |  |  | 2018-07-19 17:13 |  |  |  | 2018-07-19 17:13 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-020 | 0 | Isometric - Riser R6B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:39 | 2018-06-25 17:39 | Yes | 2 |  |  |  |  | 2018-07-19 17:10 |  |  |  | 2018-07-19 17:10 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:40
VD-9001-202F-ISO-021 | 0 | Isometric - Downcomer D1B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:40 | 2018-06-25 17:45 | Yes | 2 |  |  |  |  | 2018-07-19 16:57 |  |  |  | 2018-07-19 16:57 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:41
VD-9001-202F-ISO-022 | 0 | Isometric - Downcomer D2B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:46 | 2018-06-25 17:46 | Yes | 2 |  |  |  |  | 2018-07-19 16:53 |  |  |  | 2018-07-19 16:53 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:42
VD-9001-202F-ISO-023 | 0 | Isometric - Downcomer D3B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:47 | 2018-06-25 17:47 | Yes | 2 |  |  |  |  | 2018-07-19 15:37 |  |  |  | 2018-07-19 15:37 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:41
VD-9001-202F-ISO-024 | 0 | Isometric - Downcomer D4B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:48 | 2018-06-25 17:48 | Yes | 2 |  |  |  |  | 2018-07-19 14:58 |  |  |  | 2018-07-19 14:58 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:41
VD-9001-202F-ISO-025 | 0 | Isometric - Downcomer D5B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:49 | 2018-06-25 17:50 | Yes | 2 |  |  |  |  | 2018-07-19 14:55 |  |  |  | 2018-07-19 14:55 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:41
VD-9001-202F-ISO-026 | 0 | Isometric - Downcomer D6B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-23 | 2018-06-25 17:51 | 2018-06-25 17:51 | Yes | 2 |  |  |  |  | 2018-07-19 13:14 |  |  |  | 2018-07-19 13:14 | Yes | 10 | 1204-Owner-v | 2019-05-11 08:42
VD-9001-257C-PCJ-005 | 1 | NITROGEN PURGING (4137/N) | HM-257C | Brembana & Rolle S.p.A. | 2018-06-30 | 2019-01-09 17:36 | 2019-01-09 17:36 | Yes | 193 |  |  |  |  | 2019-01-13 15:40 |  |  |  | 2019-01-13 15:40 | Yes | -10
VD-9001-251-MTO-001 | 1 | STEELWORK MATERIAL TAKE OFF | HM-251 | KT – Kinetics Technology SpA | 2018-06-30 | 2018-08-31 12:54 | 2018-08-31 13:13 | Yes | 62 |  |  |  | 2018-09-02 16:40 |  |  |  |  | 2018-09-02 16:40 | Yes | -12 | 1204-Owner-v | 2019-03-30 12:43
VD-9001-104(009)-DWG-012 | 1 | Exchanger box E01 - detail drawing - anchors | PR-104-SUB | AIR LIQUIDE | 2018-07-07 20:00 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104(002)-CAL-001 | 2 | D-6103 - Calculation notes | PR-104-SUB | AIR LIQUIDE | 2018-07-07 20:00 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104-DCR-001 | 3 | Site data sheet | PR-104 | AIR LIQUIDE | 2018-07-08 20:00 |  |  | No | 712 | [9 empty] | No | 0
VD-9001-104(009)-DWG-015 | 1 | Exchanger box E01 - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-08 20:00 |  |  | No | 712 | [9 empty] | No | 0
VD-9001-104(016)-IPM-004 | 1 | C-6103/TEX-6103 - Mechanical / Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-07-02 |  |  | No | 718 | [9 empty] | No | 0
VD-9001-104(004)-DSH-006 | 1 | ST C-6102 - Condenser data sheet | PR-104-SUB | AIR LIQUIDE | 2018-07-02 |  |  | No | 718 | [9 empty] | No | 0
VD-9001-204C-DWG-045 | 1 | LADDER DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-02 | 2019-05-29 10:44 | 2019-05-29 10:44 | Yes | 331 |  |  | 2019-05-29 15:13 | [5 empty] | 2019-05-29 20:59 | Yes | -14
VD-9001-104(008)-DSH-006 | 1 | J-6188 - Inter Condense & Ejector & Vacuum Unit- data sheet | PR-104-SUB | AIR LIQUIDE | 2018-07-02 |  |  | No | 718 | [9 empty] | No | 0
VD-9001-404A-PCJ-003 | 1 | Painting Procedure | PI-404A | KVC CO., LTD. | 2018-07-09 09:05 | 2018-07-02 06:03 | 2018-07-02 06:03 | Yes | -7 |  |  | 2018-07-04 08:38 | [5 empty] | 2018-07-04 08:38 | Yes | -12 | 1204-Owner-v | 2019-02-02 16:38
VD-9001-254-MNL-322 | 1 | OPERATION MANUAL FOR OPERATER STATIONS | HM-254 | AZAR AB | 2018-06-29 | 2019-03-18 10:52 | 2019-03-18 10:53 | Yes | 262 |  |  | 2019-04-15 15:14 | [5 empty] | 2019-04-15 15:14 | Yes | 14 | 1204-Owner-v | 2020-04-20 12:47
VD-9001-251-DWG-027 | 3 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-06-25 17:37 | 2018-06-25 19:41 | 2018-06-25 19:41 | Yes | 0 |  |  |  | 2018-06-28 10:49 |  |  |  |  | 2018-06-28 10:49 | Yes | -11 | 1204-Owner-v | 2018-06-30 10:20
VD-9001-251-DWG-029 | 3 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-06-25 17:38 | 2018-06-25 19:44 | 2018-06-25 19:44 | Yes | 0 |  |  | 2018-06-28 10:57 | [5 empty] | 2018-06-28 10:57 | Yes | -11 | 1204-Owner-v | 2019-03-28 00:18
VD-9001-202F-PPL-002 | 1 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-02 | 2018-06-25 18:09 | 2018-06-25 18:09 | Yes | -7 |  |  |  |  | 2018-06-28 15:48 |  |  |  | 2018-06-28 15:48 | Yes | -11
VD-9001-104(016)-IPM-009 | 1 | C-6104/TEX-6104 - Mechanical / Performance tests procedures | PR-104-SUB | AIR LIQUIDE | 2018-07-09 20:00 |  |  | No | 711 | [9 empty] | No | 0
VD-9001-104(014)-WBK-002 | 1 | E-6124 - Welding book | PR-104-SUB | AIR LIQUIDE | 2018-07-09 20:00 |  |  | No | 711 | [9 empty] | No | 0
VD-9001-104(014)-WBK-001 | 1 | E-6108/E-6108-D1 - Equipment and piping Welding book vessel and piping | PR-104-SUB | AIR LIQUIDE | 2018-07-09 20:00 |  |  | No | 711 | [9 empty] | No | 0
VD-9001-104(009)-DWG-009 | 1 | HP/ LP Cold box - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-09 20:00 |  |  | No | 711 | [9 empty] | No | 0
VD-9001-104(009)-DWG-010 | 1 | HP/ LP Cold box - detail drawing - plan 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-09 20:00 |  |  | No | 711 | [9 empty] | No | 0
VD-9001-251-DWG-030 | 3 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-06-28 | 2019-06-12 11:02 | 2019-06-12 11:02 | Yes | 349 |  |  | 2019-07-21 11:11 | [5 empty] | 2019-07-21 11:11 | Yes | 25 | 1204-Owner-v | 2020-04-25 16:50
VD-9001-251-DWG-112 | 2 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-06-28 | 2019-06-12 11:29 | 2019-06-12 11:29 | Yes | 349 |  |  | 2019-07-21 10:40 | [5 empty] | 2019-07-21 10:40 | Yes | 25 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-104(009)-DWG-007 | 1 | HP/ LP Cold box - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-10 20:00 |  |  | No | 710 | [9 empty] | No | 0
VD-9001-104(009)-DWG-008 | 1 | HP/ LP Cold box - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-10 20:00 |  |  | No | 710 | [9 empty] | No | 0
VD-9001-104(009)-DWG-011 | 1 | HP/ LP Cold box - detail drawing - joints | PR-104-SUB | AIR LIQUIDE | 2018-07-10 20:00 |  |  | No | 710 | [9 empty] | No | 0
VD-9001-204C-INR-031 | 1 | CERTIFICATION DOSSIER INDEX | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-10 20:00 | 2018-06-28 18:26 | 2018-06-28 18:26 | Yes | -12 |  |  | 2018-07-15 10:03 | [5 empty] | 2018-07-15 20:00 | Yes | 3
VD-9001-202F-CAL-008 | 0 | Waste Heat Boiler - Support Calculation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-27 | 2018-06-27 22:21 | 2018-06-27 22:21 | Yes | 0 |  |  | 2018-09-30 15:08 | [5 empty] | 2018-09-30 15:08 | Yes | 81 | 1204-Owner-v | 2019-05-11 08:36
VD-9001-202F-CAL-009 | 0 | Waste Heat Boiler - Nozzle Load Calculation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-27 | 2018-06-27 22:26 | 2018-06-27 22:26 | Yes | 0 |  |  | 2018-09-30 15:11 | [5 empty] | 2018-09-30 15:11 | Yes | 81 | 1204-Owner-v | 2019-05-11 08:42
VD-9001-254-PPL-318 | 5 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2018-06-30 | 2018-12-16 08:57 | 2018-12-16 10:53 | Yes | 169 |  |  |  | 2019-01-12 10:21 |  |  |  |  | 2019-01-12 10:21 | Yes | 13 | 1204-Owner-v | 2018-12-23 11:13
VD-9001-251-DWG-129 | 0 | Foundation base plate details (sh.7) | HM-251 | KT – Kinetics Technology SpA | 2018-06-27 | 2018-06-27 13:13 | 2018-06-27 13:17 | Yes | 0 |  |  | 2018-06-28 11:25 | [5 empty] | 2018-06-28 11:25 | Yes | -13
VD-9001-251-DWG-130 | 0 | Foundation base plate details (sh.8) | HM-251 | KT – Kinetics Technology SpA | 2018-06-27 | 2018-06-27 13:15 | 2018-06-27 13:18 | Yes | 0 |  |  | 2018-06-28 11:25 | [5 empty] | 2018-06-28 11:25 | Yes | -13
VD-9001-251-DWG-121 | 0 | STEELWORK SUPPORT AL. A – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-06-27 | 2018-06-27 13:09 | 2018-06-27 13:12 | Yes | 0 |  |  | 2018-06-28 11:23 | [5 empty] | 2018-06-28 11:23 | Yes | -13
VD-9001-201B-DWG-002 | 2 | DETAILS DRAWING (4134-0359/2) | PV-201B | Brembana & Rolle S.p.A. | 2018-06-27 14:33 | 2018-06-27 14:56 | 2018-06-27 14:56 | Yes | 0 |  |  | 2018-07-25 19:21 | [5 empty] | 2018-07-25 19:59 | Yes | 14 | 1204-Owner-v | 2018-09-16 15:34
VD-9001-202F-BOQ-004 | 2 | Waste Heat Boiler - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-27 14:56 | 2018-06-27 22:32 | 2018-06-27 22:33 | Yes | 0 |  |  | 2018-07-08 15:15 | [5 empty] | 2018-07-08 15:15 | Yes | -3 | 1204-Owner-v | 2018-12-17 15:25
VD-9001-202F-PCJ-014 | 2 | Waste Heat Boiler - Production Weld Test Coupons Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-27 14:56 | 2018-06-27 22:34 | 2018-06-27 22:35 | Yes | 0 |  |  | 2018-07-15 15:03 | [5 empty] | 2018-07-15 15:03 | Yes | 4 | 1204-Owner-v | 2020-04-29 10:06
VD-9001-202F-CAL-003 | 1 | Waste Heat Boiler - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-06-27 14:57 | 2018-06-27 22:29 | 2018-06-27 22:29 | Yes | 0 |  |  | 2018-07-22 11:59 | [5 empty] | 2018-07-22 11:59 | Yes | 11 | 1204-Owner-v | 2019-05-11 08:36
VD-9001-251-DWG-027 | 4 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-07-05 | 2018-07-25 12:11 | 2018-07-25 13:29 | Yes | 20 |  |  | 2018-08-04 11:41 | [5 empty] | 2018-08-04 11:41 | Yes | -4
VD-9001-257C-WBK-006 | 2 | WELDING BOOK (4137-0369/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-05 | 2018-09-18 12:48 | 2018-09-18 12:52 | Yes | 75 |  |  | 2018-10-13 15:09 | [5 empty] | 2018-10-13 15:09 | Yes | 11
VD-9001-257C-WBK-004 | 2 | WELDING BOOK (4137-0367/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-05 | 2018-11-21 12:02 | 2018-11-21 12:06 | Yes | 139 |  |  | 2018-12-10 17:01 | [5 empty] | 2018-12-10 17:01 | Yes | 5
VD-9001-202F-PCJ-019 | 1 | Instructions on painting & conservation | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-05 |  |  | No | 715 | [9 empty] | No | 0
VD-9001-202F-PPL-002 | 2 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-05 | 2018-07-09 17:28 | 2018-07-09 17:29 | Yes | 4 |  |  |  |  | 2018-07-12 16:10 |  |  |  | 2018-07-12 16:11 | Yes | -11 | 1204-Owner-v | 2018-07-17 11:12
VD-9001-202F-PPL-007 | 2 | Layout - Cut-Free System Boiler | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-05 | 2018-07-05 16:49 | 2018-07-05 16:50 | Yes | 0 |  |  |  |  | 2018-07-12 16:20 |  |  |  | 2018-07-12 16:20 | Yes | -7
VD-9001-257C-WBK-002 | 2 | WELDING BOOK (4137-0365/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-05 | 2018-09-18 12:17 | 2018-09-18 12:27 | Yes | 75 |  |  |  |  | 2018-10-13 11:34 |  |  |  | 2018-10-13 11:34 | Yes | 11
VD-9001-257C-WBK-003 | 2 | WELDING BOOK (4137-0366/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-05 | 2018-08-09 11:01 | 2018-08-09 11:01 | Yes | 35 |  |  | 2018-08-28 10:57 | [5 empty] | 2018-08-28 10:57 | Yes | 5
VD-9001-104-PID-010 | 2 | PID Air Purification Vessel | PR-104 | AIR LIQUIDE | 2018-07-12 20:00 |  |  | No | 708 | [9 empty] | No | 0
VD-9001-104-PID-009 | 2 | PID ACC INTEGRATION | PR-104 | AIR LIQUIDE | 2018-07-12 20:00 |  |  | No | 708 | [9 empty] | No | 0
VD-9001-104-PID-012 | 2 | PID Booster turbine air interface with cold booster | PR-104 | AIR LIQUIDE | 2018-07-12 20:00 |  |  | No | 708 | [9 empty] | No | 0
VD-9001-307A-PCU-024 | 1 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-07-14 20:00 | 2018-09-20 15:14 | 2018-09-20 15:14 | Yes | 68 |  |  |  | 2018-10-03 16:24 |  |  |  |  | 2018-10-03 18:58 | Yes | -1
VD-9001-307A-PCU-025 | 1 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-07-14 20:00 | 2018-09-20 15:14 | 2018-09-20 15:14 | Yes | 68 |  |  |  | 2018-10-03 16:23 |  |  |  |  | 2018-10-03 18:58 | Yes | -1
VD-9001-301-PID-005 | 2 | P+I Diagram Oil Syngas Train | MC-301 | Siemens AG | 2018-07-14 20:00 |  |  | No | 706 | [9 empty] | No | 0
VD-9001-104-PID-014 | 2 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-07-14 20:00 |  |  | No | 706 | [9 empty] | No | 0
VD-9001-204D-PCJ-023 | 1 | N.D.E. PROCEDURES (NDT MAP INCLUDED) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-14 20:00 |  |  | No | 706 | [9 empty] | No | 0
VD-9001-204D-WMP-010 | 2 | WELDING DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-14 20:00 | 2018-10-09 13:28 | 2018-10-09 13:28 | Yes | 87 |  |  | 2018-11-03 15:17 | [5 empty] | 2018-11-03 15:17 | Yes | 11
VD-9001-204D-PCJ-017 | 1 | PAINTING SPECIFICATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-14 20:00 | 2018-07-02 17:16 | 2018-07-02 17:17 | Yes | -12 |  |  |  | 2018-08-06 08:47 |  |  |  |  | 2018-08-06 08:47 | Yes | 21
VD-9001-307A-ITP-009 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-07-14 20:00 | 2018-09-21 16:42 | 2018-09-21 16:42 | Yes | 69 |  |  |  | 2018-10-08 17:30 |  |  |  |  | 2018-10-08 18:59 | Yes | 3 | 1204-Owner-v | 2018-10-20 15:08
VD-9001-307A-ITP-010 | 1 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-07-14 20:00 | 2018-09-21 16:42 | 2018-09-21 16:42 | Yes | 69 |  |  |  | 2018-10-08 17:29 |  |  |  |  | 2018-10-08 18:59 | Yes | 3 | 1204-Owner-v | 2018-10-20 15:08
VD-9001-104-PID-013 | 2 | PID Air Expansion Turbine process | PR-104 | AIR LIQUIDE | 2018-07-14 20:00 |  |  | No | 706 | [9 empty] | No | 0
VD-9001-204D-CAL-013 | 3 | MECHANICAL CODE CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-14 20:00 | 2018-07-03 17:14 | 2018-07-03 17:15 | Yes | -11 |  |  |  |  | 2018-07-10 08:47 |  |  |  | 2018-07-10 08:47 | Yes | -7
VD-9001-104-PID-016 | 2 | PID Main Heat Exchanger | PR-104 | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104-PID-017 | 2 | PID Subcooler | PR-104 | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104-PID-032 | 2 | PID Tie-ins | PR-104 | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104-PID-031 | 2 | PID Gaseous Nitrogen Production | PR-104 | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104(002)-DWG-007 | 1 | T-6101 - Anchoring details | PR-104-SUB | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-104-STR-001 | 1 | Project management plan | PR-104 | AIR LIQUIDE | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-202F-PPL-008 | 2 | Layout - Cut-Free System Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-09 | 2018-07-05 18:18 | 2018-07-05 18:20 | Yes | -4 |  |  |  |  | 2018-07-12 16:58 |  |  |  | 2018-07-12 16:58 | Yes | -7
VD-9001-204C-DWG-048 | 0 | INTERNAL PIPE DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-02 | 2018-07-02 17:54 | 2018-07-02 17:54 | Yes | 0 |  |  | 2018-07-04 11:11 | [5 empty] | 2018-07-04 20:00 | Yes | -12
VD-9001-307A-PCU-009 | 3 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-16 20:00 |  |  | No | 704 | [9 empty] | No | 0
VD-9001-307A-PCU-010 | 3 | Pump Performance Curve | MC-307A | KSB GERMANY | 2018-07-16 20:00 |  |  | No | 704 | [9 empty] | No | 0
VD-9001-104-PID-033 | 2 | PID Cooling Water Distribution | PR-104 | AIR LIQUIDE | 2018-07-16 20:00 |  |  | No | 704 | [9 empty] | No | 0
VD-9001-307A-PCU-021 | 1 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-07-16 20:00 | 2018-09-20 15:14 | 2018-09-20 15:14 | Yes | 66 |  |  | 2018-10-07 10:00 | [5 empty] | 2018-10-07 18:57 | Yes | 3
VD-9001-307A-PCU-022 | 1 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-07-16 20:00 | 2018-09-20 15:14 | 2018-09-20 15:14 | Yes | 66 |  |  |  | 2018-10-03 17:17 |  |  |  |  | 2018-10-03 18:58 | Yes | -1
VD-9001-307A-DWG-079 | 1 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-07-16 20:00 |  |  | No | 704 | [9 empty] | No | 0
VD-9001-307A-DWG-078 | 1 | Terminal Box Drawing (Motor) | MC-307A | KSB GERMANY | 2018-07-16 20:00 |  |  | No | 704 | [9 empty] | No | 0
VD-9001-206B-DWG-021 | 2 | SHIPPING DRAWING-T-1001 | PV-206B | TASHA | 2018-07-03 11:20 | 2018-07-05 10:52 | 2018-08-11 10:22 | Yes | 2 |  |  | 2018-08-11 11:50 | [5 empty] | 2018-08-11 11:50 | Yes | 23 | 1204-Owner-v | 2018-07-10 15:19
VD-9001-307A-PCU-011 | 2 | Motor Curves | MC-307A | KSB GERMANY | 2018-07-03 12:09 | 2018-07-04 17:02 | 2018-07-04 17:06 | Yes | 1 |  |  | 2018-07-14 15:10 | [5 empty] | 2018-07-14 20:00 | Yes | -4
VD-9001-307A-PCU-012 | 2 | Motor Curves | MC-307A | KSB GERMANY | 2018-07-03 12:09 | 2018-07-04 17:03 | 2018-07-04 17:06 | Yes | 1 |  |  | 2018-07-14 15:07 | [5 empty] | 2018-07-14 20:00 | Yes | -4
VD-9001-307A-PCU-013 | 2 | Motor Curves | MC-307A | KSB GERMANY | 2018-07-03 12:09 | 2018-07-04 17:03 | 2018-07-04 17:06 | Yes | 1 |  |  | 2018-07-14 15:04 | [5 empty] | 2018-07-14 20:00 | Yes | -4
VD-9001-307A-PCU-014 | 2 | Motor Curves | MC-307A | KSB GERMANY | 2018-07-03 12:10 | 2018-07-04 17:04 | 2018-07-04 17:06 | Yes | 1 |  |  | 2018-07-14 15:02 | [5 empty] | 2018-07-14 20:00 | Yes | -4
VD-9001-307A-PCU-015 | 2 | Motor Curves | MC-307A | KSB GERMANY | 2018-07-03 12:10 | 2018-07-04 17:05 | 2018-07-04 17:06 | Yes | 1 |  |  | 2018-07-14 15:00 | [5 empty] | 2018-07-14 20:00 | Yes | -4
VD-9001-404A-INX-001 | 0 | FINAL DATA BOOK INDEX | PI-404A | KVC CO., LTD. | 2018-07-03 | 2018-07-04 04:49 | 2018-07-04 04:49 | Yes | 1 |  |  |  | 2018-07-11 17:08 |  |  |  |  | 2018-07-11 17:08 | Yes | -7
VD-9001-201-CAL-001 | 3 | PRESSURE PARTS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2018-07-10 | 2018-08-27 20:03 | 2018-08-27 20:04 | Yes | 48 |  |  |  | 2018-09-04 15:54 |  |  |  |  | 2018-09-04 15:54 | Yes | -6
VD-9001-307A-DWG-011 | 1 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-07-17 20:00 | 2018-09-07 16:53 | 2018-09-07 16:53 | Yes | 52 |  |  |  | 2018-09-16 09:11 |  |  |  |  | 2018-09-16 19:58 | Yes | -5
VD-9001-307A-DWG-012 | 1 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-07-17 20:00 | 2018-09-07 16:53 | 2018-09-07 16:53 | Yes | 52 |  |  |  | 2018-09-16 09:12 |  |  |  |  | 2018-09-16 19:58 | Yes | -5
VD-9001-104-PID-037 | 2 | PID Instrument Air System | PR-104 | AIR LIQUIDE | 2018-07-10 |  |  | No | 710 | [9 empty] | No | 0
VD-9001-104-PID-039 | 2 | PID Steam | PR-104 | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104-PID-036 | 2 | PID Derime | PR-104 | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104-PID-023 | 2 | PID LP Column / Pure Nitrogen Column | PR-104 | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104-LST-001 | 5 | Piping tie-in list (with client) | PR-104 | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104(008)-LST-005 | 1 | AE-6187 - Instrument cables list ( Power and control), Wiring diagram, instruments tubing list and material BOM | PR-104-SUB | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104(008)-DWG-015 | 1 | AE-6187 - Junction boxes drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104(009)-DWG-020 | 1 | Exchanger box E03 - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104(009)-DWG-003 | 1 | Cold box area - Access detail drawing - plan | PR-104-SUB | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-104(009)-DWG-022 | 1 | Exchanger box E03 - detail drawing - plan 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-201B-CAL-007 | 0 | FEA REPORT (skirt to shell junction) (4134-0359/FEA1) | PV-201B | Brembana & Rolle S.p.A. | 2018-07-04 | 2018-08-10 19:22 | 2018-08-10 19:23 | Yes | 37 |  |  | 2018-10-29 09:57 | [5 empty] | 2018-10-29 09:57 | Yes | 66
VD-9001-204B-WMP-001 | 4 | Welding & NDT Map D-1002 | PV-204B | ABAN AIR COOLER. | 2018-07-11 | 2018-08-01 14:35 | 2018-08-01 14:35 | Yes | 21 |  |  | 2018-08-23 08:57 | [5 empty] | 2018-08-23 08:57 | Yes | 8 | 1204-Owner-v | 2019-02-02 13:45
VD-9001-204B-WMP-002 | 4 | Welding & NDT Map D-1003 | PV-204B | ABAN AIR COOLER. | 2018-07-11 | 2018-08-01 14:41 | 2018-08-01 14:41 | Yes | 21 |  |  | 2018-08-23 08:55 | [5 empty] | 2018-08-23 08:55 | Yes | 8 | 1204-Owner-v | 2019-02-16 09:38
VD-9001-204B-WMP-003 | 4 | Welding & NDT Map D-3006 | PV-204B | ABAN AIR COOLER. | 2018-07-11 | 2018-08-01 14:49 | 2018-08-01 14:49 | Yes | 21 |  |  | 2018-08-23 08:53 | [5 empty] | 2018-08-23 19:58 | Yes | 8 | 1204-Owner-v | 2019-02-16 09:39
VD-9001-204B-WMP-004 | 4 | Welding & NDT Map D-3007 | PV-204B | ABAN AIR COOLER. | 2018-07-11 | 2018-08-01 14:54 | 2018-08-01 14:54 | Yes | 21 |  |  | 2018-08-23 08:50 | [5 empty] | 2018-08-23 19:58 | Yes | 8 | 1204-Owner-v | 2019-02-16 09:39
VD-9001-104(004)-DWG-027 | 1 | General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-201B-INX-002 | 1 | INDEX OF MANUFACTURER DATA BOOK R-1004 (4134-0359/RMDB Ind) | PV-201B | Brembana & Rolle S.p.A. | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-201B-DWG-012 | 1 | REFRACTORY LINING REFORMER R-1004 - VERTICAL SECTIONS OF REFORMER (4134-0359/RF) | PV-201B | Brembana & Rolle S.p.A. | 2018-07-18 20:00 | 2018-11-08 18:42 | 2018-11-08 18:42 | Yes | 113 |  |  | 2018-11-11 16:16 | [5 empty] | 2018-11-11 20:00 | Yes | -11 | 1204-Owner-v | 2019-01-29 09:55
VD-9001-201B-INX-001 | 1 | MANUFACTURER DATA REPORT INDEX (4134/ED) | PV-201B | Brembana & Rolle S.p.A. | 2018-07-18 20:00 | 2018-07-05 13:36 | 2018-07-05 13:36 | Yes | -13 |  |  | 2018-10-28 18:32 | [5 empty] | 2018-10-28 20:00 | Yes | 101
VD-9001-201B-DWG-013 | 1 | REFRACTORY ANCHORS REFORMER R-1004 - VERTICAL SECTIONS OF REFORMER (4134-0359/RF1) | PV-201B | Brembana & Rolle S.p.A. | 2018-07-18 20:00 | 2018-11-08 18:43 | 2018-11-08 18:43 | Yes | 113 |  |  | 2018-11-11 18:14 | [5 empty] | 2018-11-11 20:01 | Yes | -11 | 1204-Owner-v | 2019-01-29 15:01
VD-9001-104-PID-022 | 2 | PID HP Column / Main Vaporizer | PR-104 | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-104(009)-DWG-019 | 1 | Exchanger box E03 - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-104(009)-DWG-021 | 1 | Exchanger box E03 - detail drawing - plan 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-104(009)-DWG-013 | 1 | Exchanger box E01 - detail drawing - elevation 1 | PR-104-SUB | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-104(009)-DWG-014 | 1 | Exchanger box E01 - detail drawing - elevation 2 | PR-104-SUB | AIR LIQUIDE | 2018-07-18 20:00 |  |  | No | 702 | [9 empty] | No | 0
VD-9001-251-DWG-122 | 0 | STEELWORK SUPPORT AL. 12 – GENERAL ARRANGEMENT | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 | 2018-07-09 18:07 | 2018-07-09 18:07 | Yes | 2 |  |  | 2018-07-14 11:11 | [5 empty] | 2018-07-14 11:11 | Yes | -9 | 1204-Owner-v | 2018-07-11 09:57
VD-9001-251-DWG-123 | 0 | STEELWORK SUPPORT AL. 12 – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 | 2018-07-09 18:07 | 2018-07-09 18:07 | Yes | 2 |  |  | 2018-07-12 11:54 | [5 empty] | 2018-07-12 11:54 | Yes | -11
VD-9001-251-DWG-126 | 0 | STACK PLAN & PLATFORMS | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 | 2018-07-09 18:09 | 2018-07-09 18:09 | Yes | 2 |  |  | 2018-07-14 11:14 | [5 empty] | 2018-07-14 11:14 | Yes | -9 | 1204-Owner-v | 2019-05-08 10:05
VD-9001-251-DWG-131 | 0 | POWER SUPPLY DISTRIBUTION ID FAN REMOTE I/O PANEL | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 | 2018-07-09 18:04 | 2018-07-09 18:04 | Yes | 2 |  |  |  | 2018-08-04 11:04 |  |  |  |  | 2018-08-04 11:04 | Yes | 12 | 1204-Owner-v | 2018-09-11 15:25
VD-9001-251-BLD-003 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS TYPICAL FOR FLUE GAS AND WASTE GAS PRESSURE TRIPS 2 OUT 3 | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-BLD-004 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS TYPICAL FOR REFORMER BOX FLUE GAS PRESSURE TRIPS AND CONTROL 2 OUT 3 | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-BLD-005 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS TYPICAL FOR COMB. AIR, FLUE GAS AND WASTE GAS FLOW TRIPS IN PLC LOGICS | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-BLD-006 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS ARCH BURNERS COMBUSTION MODULE REPRESENTATION IN P&ID | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-BLD-007 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS POST BURNERS COMBUSTION MODULE REPRESENTATION IN P&ID | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-BLD-008 | 0 | COMPLEX CONTROL LOOPS CONFIGURATION DETAILS TUNNEL BURNERS COMBUSTION MODULE REPRESENTATION IN P&ID | HM-251 | KT – Kinetics Technology SpA | 2018-07-07 |  |  | No | 713 | [9 empty] | No | 0
VD-9001-251-PID-001 | 2 | PID - PRIMARY REFORMER RADIANT SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 16:58 | 2018-08-29 17:32 | Yes | 47 |  |  |  |  | 2018-12-04 14:56 |  |  |  | 2018-12-04 14:56 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:43
VD-9001-251-PID-002 | 2 | PID - PRIMARY REFORMER CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:02 | 2018-08-29 17:32 | Yes | 47 |  |  |  |  | 2018-12-04 14:57 |  |  |  | 2018-12-04 14:57 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:43
VD-9001-251-PID-003 | 2 | PID - COMBUSTION AIR FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:08 | 2018-08-29 17:32 | Yes | 47 |  |  |  |  | 2018-12-04 14:58 |  |  |  | 2018-12-04 14:58 | Yes | 83 | 1204-Owner-v | 2019-04-08 11:36
VD-9001-251-PID-004 | 2 | PID - FLUE GAS FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:17 | 2018-08-29 17:32 | Yes | 47 |  |  |  |  | 2018-12-04 15:00 |  |  |  | 2018-12-04 15:00 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:43
VD-9001-251-PID-005 | 2 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:20 | 2018-08-29 17:32 | Yes | 47 |  |  |  |  | 2018-12-04 15:02 |  |  |  | 2018-12-04 15:02 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:40
VD-9001-251-PID-006 | 2 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:22 | 2018-08-29 17:33 | Yes | 47 |  |  |  |  | 2018-12-04 15:03 |  |  |  | 2018-12-04 15:03 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:42
VD-9001-251-PID-007 | 2 | PID - TUNNEL BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:24 | 2018-08-29 17:33 | Yes | 47 |  |  |  |  | 2018-12-04 15:04 |  |  |  | 2018-12-04 15:04 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:42
VD-9001-251-PID-008 | 2 | PID - SSH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:26 | 2018-08-29 17:33 | Yes | 47 |  |  |  |  | 2018-12-04 15:05 |  |  |  | 2018-12-04 15:05 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:42
VD-9001-251-PID-010 | 2 | PID- UTILITIES DISTRIBUTION | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2018-08-29 17:30 | 2018-08-29 17:33 | Yes | 47 |  |  |  |  | 2018-12-04 15:06 |  |  |  | 2018-12-04 15:06 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:42
VD-9001-254-LST-220 | 2 | WIRING LIST AND CABLE ROUTH ( POWER ) | HM-254 | AZAR AB | 2018-07-11 | 2018-10-01 09:15 | 2018-10-01 09:15 | Yes | 82 |  |  |  | 2018-10-22 12:03 |  |  |  |  | 2018-10-22 12:03 | Yes | 7 | 1204-Owner-v | 2018-10-08 16:42
VD-9001-307A-DSH-018 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-019 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104-PID-011 | 2 | PID Reactivation Heater | PR-104 | AIR LIQUIDE | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-020 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-017 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-016 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-015 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-014 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-013 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-012 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-DSH-011 | 1 | Seal System Data Sheet | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104-PID-007 | 2 | PID AIR FILTER & MAC 1 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104-PID-008 | 2 | PID AIR FILTER & MAC 2 INTEGRATION | PR-104 | AIR LIQUIDE | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-307A-PCJ-002 | 1 | Packing, Lifting, Transport and Storage Procedure | MC-307A | KSB GERMANY | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104-PID-025 | 2 | PID Liquid Nitrogen Vaporizer | PR-104 | AIR LIQUIDE | 2018-07-21 19:59 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-104-PID-026 | 2 | PID Cryogenic Disposal Purges | PR-104 | AIR LIQUIDE | 2018-07-15 |  |  | No | 705 | [9 empty] | No | 0
VD-9001-257C-DWG-027 | 2 | NAME PLATE DET.DWG (4137-0368/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-15 | 2018-10-11 16:58 | 2018-10-11 16:58 | Yes | 88 |  |  | 2018-10-13 16:41 | [5 empty] | 2018-10-13 16:41 | Yes | -12
VD-9001-251-DWG-079 | 1 | STACK CONNECTION DETAIL | HM-251 | KT – Kinetics Technology SpA | 2018-07-13 | 2019-06-12 11:26 | 2019-06-12 11:26 | Yes | 334 |  |  | 2019-07-06 15:25 | [5 empty] | 2019-07-06 15:25 | Yes | 10 | 1204-Owner-v | 2019-07-23 09:22
VD-9001-257C-DWG-066 | 1 | DETAILS DRAWING (4137-0367/4) E-2001B | HM-257C | Brembana & Rolle S.p.A. | 2018-07-15 | 2018-10-11 16:55 | 2018-10-11 16:55 | Yes | 88 |  |  | 2018-12-16 16:06 | [5 empty] | 2018-12-16 16:06 | Yes | 52 | 1204-Owner-v | 2018-12-10 10:59
VD-9001-257C-DWG-051 | 2 | DETAILS DRAWING (4137-0371/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-15 | 2018-10-11 17:55 | 2018-10-11 17:55 | Yes | 88 |  |  | 2018-11-03 10:58 | [5 empty] | 2018-11-03 10:58 | Yes | 9 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-257C-DWG-050 | 2 | DETAILS DRAWING (4137-0370/3) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-15 | 2018-10-11 17:25 | 2018-10-15 13:20 | Yes | 92 |  |  | 2018-11-06 16:58 | [5 empty] | 2018-11-06 16:58 | Yes | 12 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-104-PID-030 | 2 | PID Gaseous Oxygen Production | PR-104 | AIR LIQUIDE | 2018-07-22 19:59 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-029 | 2 | PID Air interface | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-034 | 2 | PID UTILITIES TIE-INS WASTE WATER PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-035 | 2 | PID UTILITIES TIE-INS OIL PIT & LIFTING PUMPS | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-040 | 2 | PID Utilities tie-in | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-307A-DWG-009 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-22 | 2018-09-28 12:21 | 2018-09-28 12:23 | Yes | 68 |  |  |  | 2018-10-10 10:19 |  |  |  |  | 2018-10-10 18:57 | Yes | -2 | 1204-Owner-v | 2018-10-31 10:38
VD-9001-307A-DWG-003 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-22 | 2018-09-27 15:55 | 2018-09-28 12:17 | Yes | 67 |  |  |  | 2018-10-10 10:46 |  |  |  |  | 2018-10-10 18:58 | Yes | -1 | 1204-Owner-v | 2018-10-31 16:25
VD-9001-307A-DWG-010 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-018 | 2 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-104-PID-019 | 2 | PID HP Liquid Oxygen Pump | PR-104 | AIR LIQUIDE | 2018-07-22 |  |  | No | 698 | [9 empty] | No | 0
VD-9001-307A-DWG-005 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-22 | 2018-09-28 13:07 | 2018-09-28 13:18 | Yes | 68 |  |  |  | 2018-10-10 10:38 |  |  |  |  | 2018-10-10 18:57 | Yes | -2 | 1204-Owner-v | 2018-10-31 16:32
VD-9001-307A-DWG-001 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-07-22 | 2018-09-25 11:07 | 2018-09-25 11:07 | Yes | 65 |  |  |  | 2018-10-10 10:20 |  |  |  |  | 2018-10-10 18:57 | Yes | 1 | 1204-Owner-v | 2018-10-02 13:00
VD-9001-257C-DWG-021 | 2 | NAME PLATE DET.DWG (4137-0367/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-16 | 2018-10-15 12:31 | 2018-10-15 12:32 | Yes | 91 |  |  | 2018-10-15 16:47 | [5 empty] | 2018-10-15 16:47 | Yes | -14
VD-9001-257C-DWG-015 | 2 | NAME PLATE DET.DWG (4137-0366/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-16 | 2018-10-11 16:53 | 2018-10-11 16:53 | Yes | 87 |  |  | 2018-10-13 11:07 | [5 empty] | 2018-10-13 11:07 | Yes | -12
VD-9001-104-PID-021 | 2 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-07-23 19:59 |  |  | No | 697 | [9 empty] | No | 0
VD-9001-104-PID-020 | 2 | PID Liquid Nitrogen Pump | PR-104 | AIR LIQUIDE | 2018-07-23 19:59 |  |  | No | 697 | [9 empty] | No | 0
VD-9001-104-PID-003 | 2 | Instrumentation symbols schematic | PR-104 | AIR LIQUIDE | 2018-07-23 19:59 |  |  | No | 697 | [9 empty] | No | 0
VD-9001-204D-CAL-013 | 4 | MECHANICAL CODE CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-11 |  |  | No | 709 | [9 empty] | No | 0
VD-9001-251-CAL-016 | 2 | STRESS ANALISYS CALCULATION (INLET SYSTEM) | HM-251 | KT – Kinetics Technology SpA | 2018-07-17 | 2019-03-13 14:22 | 2019-03-13 14:22 | Yes | 239 |  |  | 2019-05-08 14:06 | [5 empty] | 2019-05-08 14:06 | Yes | 42 | 1204-Owner-v | 2020-06-13 07:58
VD-9001-251-CAL-019 | 1 | PIPING LINES STRESS ANALYSIS (FOR CRITICAL LINES) | HM-251 | KT – Kinetics Technology SpA | 2018-07-17 | 2019-03-13 14:23 | 2019-03-13 14:23 | Yes | 239 |  |  | 2019-05-08 14:10 | [5 empty] | 2019-05-08 14:10 | Yes | 42 | 1204-Owner-v | 2020-06-13 08:08
VD-9001-202F-DWG-009 | 2 | Waste Heat Boiler - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-10 15:35 | 2018-07-10 16:08 | 2018-07-10 16:18 | Yes | 0 |  |  | 2018-07-21 19:04 | [5 empty] | 2018-07-21 19:04 | Yes | -3 | 1204-Owner-v | 2019-01-21 13:26
VD-9001-202F-DWG-011 | 2 | Waste Heat Boiler - Manholes / Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-10 15:35 | 2018-07-10 16:19 | 2018-07-10 16:19 | Yes | 0 |  |  | 2018-07-21 19:16 | [5 empty] | 2018-07-21 19:16 | Yes | -3 | 1204-Owner-v | 2019-01-21 13:29
VD-9001-104-PID-028 | 2 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-104-PID-027 | 2 | PID Air Expansion Turbine Mechanical & Lube Oil System | PR-104 | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-104(009)-CAL-003 | 1 | Exchanger box E01 - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-104-PID-038 | 2 | PID Service Nitrogen | PR-104 | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-104(002)-DWG-006 | 1 | T-6101/T-6102 - Civil work drawing / loads on foundations | PR-104-SUB | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-204C-MAL-020 | 2 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-24 19:59 | 2018-11-08 11:06 | 2018-11-08 11:06 | Yes | 107 |  |  | 2018-11-13 09:39 | [5 empty] | 2018-11-13 20:00 | Yes | -9 | 1204-Owner-v | 2019-05-11 07:48
VD-9001-204C-MAL-021 | 2 | SPARE PARTS LIST FOR TWO YEARS OPERATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-24 19:59 | 2018-11-08 11:08 | 2018-11-08 11:09 | Yes | 107 |  |  | 2018-11-13 09:38 | [5 empty] | 2018-11-13 20:00 | Yes | -9 | 1204-Owner-v | 2019-05-11 07:48
VD-9001-104(009)-CAL-002 | 1 | HP/ LP Cold box - Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-24 19:59 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-404A-INX-001 | 1 | FINAL DATA BOOK INDEX | PI-404A | KVC CO., LTD. | 2018-07-25 17:08 | 2018-07-18 12:07 | 2018-07-18 12:07 | Yes | -7 |  |  |  | 2018-07-22 17:26 |  |  |  |  | 2018-07-22 17:26 | Yes | -10
VD-9001-104(009)-DWG-002 | 1 | Cold box area - Access detail drawing - elevation | PR-104-SUB | AIR LIQUIDE | 2018-07-25 19:59 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(007)-DWG-001 | 3 | DR-6101A / DR-6101B - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-25 19:59 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-104(004)-IPM-008 | 1 | C-6101 / C-6102 - FAT Procedure for control panel | PR-104-SUB | AIR LIQUIDE | 2018-07-25 19:59 |  |  | No | 695 | [9 empty] | No | 0
VD-9001-202F-PPL-002 | 3 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-19 | 2018-07-20 13:05 | 2018-07-20 13:06 | Yes | 1 |  |  |  | 2018-07-24 15:23 |  |  |  |  | 2018-07-24 15:25 | Yes | -10
VD-9001-202F-PPL-007 | 3 | Layout - Cut-Free System Boiler | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-19 | 2018-07-20 13:00 | 2018-07-20 13:00 | Yes | 1 |  |  |  | 2018-07-24 15:43 |  |  |  |  | 2018-07-24 15:43 | Yes | -10
VD-9001-202F-PPL-008 | 3 | Layout - Cut-Free System Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-19 | 2018-07-20 13:03 | 2018-07-20 13:03 | Yes | 1 |  |  |  | 2018-07-24 15:46 |  |  |  |  | 2018-07-24 15:46 | Yes | -10 | 1204-Owner-v | 2019-05-11 08:47
VD-9001-104-DSH-011 | 4 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-07-26 19:59 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-104(008)-DWG-016 | 1 | AE-6187 - Instruments hook-up drawing with BOM | PR-104-SUB | AIR LIQUIDE | 2018-07-26 19:59 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-104(008)-DWG-019 | 1 | AE-6187-CM01 - Motor & Name plate &Terminal box arrangement drawings | PR-104-SUB | AIR LIQUIDE | 2018-07-28 19:59 |  |  | No | 692 | [9 empty] | No | 0
VD-9001-104(002)-DWG-005 | 2 | T-6101 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-07-28 19:59 |  |  | No | 692 | [9 empty] | No | 0
VD-9001-307A-DSH-030 | 3 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-28 19:59 | 2018-08-27 13:25 | 2018-08-27 13:26 | Yes | 30 |  |  | 2018-08-29 16:45 | [5 empty] | 2018-08-29 19:59 | Yes | -12 | 1204-Owner-v | 2018-10-02 12:47
VD-9001-307A-DSH-029 | 3 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-28 19:59 | 2018-08-27 13:25 | 2018-08-27 13:26 | Yes | 30 |  |  | 2018-08-29 16:48 | [5 empty] | 2018-08-29 19:59 | Yes | -12 | 1204-Owner-v | 2018-10-02 12:45
VD-9001-307A-DSH-028 | 3 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-28 19:59 | 2018-08-27 13:25 | 2018-08-27 13:26 | Yes | 30 |  |  | 2018-08-29 16:49 | [5 empty] | 2018-08-29 19:59 | Yes | -12 | 1204-Owner-v | 2018-10-02 11:55
VD-9001-307A-DSH-027 | 3 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-28 19:59 | 2018-08-27 13:25 | 2018-08-27 13:26 | Yes | 30 |  |  | 2018-08-29 16:51 | [5 empty] | 2018-08-29 19:59 | Yes | -12 | 1204-Owner-v | 2018-10-02 11:53
VD-9001-307A-DSH-026 | 3 | Motor Data Sheet | MC-307A | KSB GERMANY | 2018-07-28 19:59 | 2018-08-27 13:25 | 2018-08-27 13:26 | Yes | 30 |  |  | 2018-08-29 16:53 | [5 empty] | 2018-08-29 19:59 | Yes | -12 | 1204-Owner-v | 2018-10-02 11:50
VD-9001-202F-PCJ-002 | 2 | Steam Superheater - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-22 | 2018-08-09 18:24 | 2018-08-09 18:43 | Yes | 18 |  |  |  |  | 2018-08-22 10:46 |  |  |  | 2018-08-22 10:46 | Yes | -1
VD-9001-104-LST-012 | 3 | Consumers list | PR-104 | AIR LIQUIDE | 2018-07-29 19:59 |  |  | No | 691 | [9 empty] | No | 0
VD-9001-202F-PCJ-003 | 2 | Steam Superheater - Procedure for Hydrostatic Test Pressure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-23 | 2018-08-09 18:24 | 2018-08-09 18:42 | Yes | 17 |  |  | 2018-08-26 08:51 | [5 empty] | 2018-08-26 08:51 | Yes | 3 | 1204-Owner-v | 2019-01-21 13:28
VD-9001-740A-SPD-00084 | 2 | Single Part Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:44 | 2018-07-29 10:44 | Yes | 6 |  |  | 2018-08-09 12:52 | [5 empty] | 2018-08-09 12:52 | Yes | -3
VD-9001-740A-SPD-00083 | 2 | Single Part Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:42 | 2018-07-29 10:42 | Yes | 6 |  |  | 2018-08-09 12:51 | [5 empty] | 2018-08-09 12:51 | Yes | -3
VD-9001-740A-GAD-00084 | 4 | General Arrangement Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:30 | 2018-07-29 10:30 | Yes | 6 |  |  | 2018-08-09 12:52 | [5 empty] | 2018-08-09 12:52 | Yes | -3 | 1204-Owner-v | 2020-04-25 09:09
VD-9001-740A-GAD-00083 | 4 | General Arrangement Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:29 | 2018-07-29 10:29 | Yes | 6 |  |  | 2018-08-09 12:53 | [5 empty] | 2018-08-09 12:53 | Yes | -3 | 1204-Owner-v | 2020-04-25 09:08
VD-9001-740A-SAD-00083 | 2 | Shop Assembly Drawings-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:36 | 2018-07-29 10:36 | Yes | 6 |  |  | 2018-08-09 12:50 | [5 empty] | 2018-08-09 12:50 | Yes | -3
VD-9001-740A-SAD-00084 | 2 | Shop Assembly Drawings-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-07-23 | 2018-07-29 10:39 | 2018-07-29 10:39 | Yes | 6 |  |  | 2018-08-09 12:51 | [5 empty] | 2018-08-09 12:51 | Yes | -3
VD-9001-104-DSH-063 | 2 | Electrochemical Gas Analysers - EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-07-30 20:00 |  |  | No | 690 | [9 empty] | No | 0
VD-9001-104-LST-014 | 2 | GENERAL INPUT AND OUTPOUT LIST for instrumentation & electrical equipment | PR-104 | AIR LIQUIDE | 2018-07-30 20:00 |  |  | No | 690 | [9 empty] | No | 0
VD-9001-204D-PCJ-018 | 2 | HYDROTEST PROCEDURE | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-19 | 2018-08-30 17:22 | 2018-08-30 17:23 | Yes | 42 |  |  | 2018-09-05 10:41 | [5 empty] | 2018-09-05 10:41 | Yes | -8
VD-9001-202F-ISO-003 | 1 | Isometric - Riser R1A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-24 |  |  | No | 696 | [9 empty] | No | 0
VD-9001-257C-PCJ-009 | 1 | PHASED ARRAY PROCEDURE (4137/PHA) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-24 | 2019-02-04 19:06 | 2019-02-04 19:06 | Yes | 195 |  |  | 2019-02-17 16:38 | [5 empty] | 2019-02-17 16:38 | Yes | -1 | 1204-Owner-v | 2019-05-10 09:14
VD-9001-257C-INX-001 | 2 | MANUFACTURER DATA REPORT INDEX (4137/ED) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-24 | 2018-10-29 12:58 | 2018-10-29 12:58 | Yes | 97 |  |  | 2018-11-07 11:43 | [5 empty] | 2018-11-07 11:43 | Yes | -5 | 1204-Owner-v | 2019-05-10 09:42
VD-9001-204D-DWG-009 | 2 | NAME PLATE DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-19 | 2019-03-07 18:12 | 2019-03-07 18:13 | Yes | 231 |  |  |  | 2019-03-12 11:12 |  |  |  |  | 2019-03-12 11:12 | Yes | -9
VD-9001-201A-PCJ-072 | 0 | SHIPPING, MARKING AND PURGING PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-201A-PCJ-073 | 0 | FABRICATION PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 12:05 | 2018-11-12 12:05 | Yes | 20 |  |  |  | 2018-12-03 10:05 |  |  |  |  | 2018-12-03 10:05 | Yes | 7
VD-9001-201A-LST-074 | 0 | PACKING LIST | PV-201A | FATEH SANAT KIMIA | 2019-10-10 |  |  | No | 253 | [9 empty] | No | 0
VD-9001-201A-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | PV-201A | FATEH SANAT KIMIA | 2018-06-26 | 2018-09-08 11:11 | 2018-09-08 11:11 | Yes | 74 |  |  | 2018-11-20 17:03 | [5 empty] | 2018-11-20 17:03 | Yes | 59 | 1204-Owner-v | 2018-10-01 14:35
VD-9001-201A-DWG-002 | 0 | GENERAL ASSEMBLY- R1001 | PV-201A | FATEH SANAT KIMIA | 2018-07-17 | 2018-07-22 09:18 | 2018-07-22 09:18 | Yes | 5 |  |  |  | 2018-09-03 12:56 |  |  |  |  | 2018-09-03 12:56 | Yes | 29
VD-9001-201A-DWG-003 | 0 | NOZZLE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-10-06 08:40 | 2018-10-06 08:40 | Yes | 55 |  |  |  | 2018-11-14 16:31 |  |  |  |  | 2018-11-14 16:31 | Yes | 25
VD-9001-201A-DWG-005 | 0 | NAME PLATE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:34 | 2019-03-09 08:34 | Yes | 209 |  |  |  | 2019-03-11 11:57 |  |  |  |  | 2019-03-11 11:57 | Yes | -12
VD-9001-201A-DWG-006 | 0 | EXTERNAL ATTACHMENT DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:30 | 2019-03-09 08:30 | Yes | 209 |  |  |  | 2019-06-03 11:09 |  |  |  |  | 2019-06-03 11:09 | Yes | 72
VD-9001-201A-DWG-007 | 0 | TEMPLATE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-12-12 15:22 | 2018-12-12 15:23 | Yes | 122 |  |  | 2018-12-17 13:23 | [5 empty] | 2018-12-17 13:23 | Yes | -9 | 1204-Owner-v | 2019-01-05 12:44
VD-9001-201A-DWG-008 | 0 | SHIPPING AND LIFTING STYLE DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:39 | 2019-03-09 08:39 | Yes | 209 |  |  |  | 2019-05-20 12:33 |  |  |  |  | 2019-05-20 12:33 | Yes | 58 | 1204-Owner-v | 2019-12-15 13:27
VD-9001-201A-DWG-009 | 0 | LADDER & PLATFORM DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-10 12:41 | 2019-03-10 12:41 | Yes | 210 |  |  |  | 2019-04-24 15:15 |  |  |  |  | 2019-04-24 15:15 | Yes | 31
VD-9001-201A-DWG-010 | 0 | TOP DAVIT DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-201A-WMP-011 | 0 | WELDING & NDT MAP - R-1001 | PV-201A | FATEH SANAT KIMIA | 2018-10-13 | 2019-05-12 10:44 | 2019-05-12 10:44 | Yes | 211 |  |  |  | 2019-06-02 12:11 |  |  |  |  | 2019-06-02 12:11 | Yes | 7
VD-9001-201A-CAL-012 | 0 | CALCULATION BOOK - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-07-22 09:04 | 2018-07-22 09:04 | Yes | -21 |  |  |  | 2018-08-28 15:48 |  |  |  |  | 2018-08-28 15:48 | Yes | 23
VD-9001-201A-ANL-013 | 0 | F.E.A. FOR SKIRT - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-10-06 08:37 | 2018-10-06 08:37 | Yes | 55 |  |  |  | 2018-11-18 15:54 |  |  |  |  | 2018-11-18 15:54 | Yes | 29
VD-9001-201A-ANL-014 | 0 | F.E.A. FOR NOZZLES - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-09-30 12:49 | 2018-09-30 12:49 | Yes | 49 |  |  |  | 2018-11-14 16:43 |  |  |  |  | 2018-11-14 16:43 | Yes | 31
VD-9001-201A-CAL-015 | 0 | SHIPPING CALCULATION - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-10-13 |  |  | No | 615 | [9 empty] | No | 0
VD-9001-201A-VDR-016 | 0 | FINAL VENDOR DATA BOOK - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-10-10 |  |  | No | 253 | [9 empty] | No | 0
VD-9001-201A-DWG-020 | 0 | GENERAL ASSEMBLY - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-07-22 09:19 | 2018-07-22 09:19 | Yes | -21 |  |  |  | 2018-09-03 12:56 |  |  |  |  | 2018-09-03 12:56 | Yes | 29 | 1204-Owner-v | 2018-08-09 11:21
VD-9001-201A-DWG-021 | 0 | NOZZLE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-10-07 15:08 | 2018-10-07 15:08 | Yes | 56 |  |  |  | 2018-11-14 16:35 |  |  |  |  | 2018-11-14 16:35 | Yes | 24
VD-9001-201A-DWG-023 | 0 | NAME PLATE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:37 | 2019-03-09 08:37 | Yes | 209 |  |  |  | 2019-03-11 11:58 |  |  |  |  | 2019-03-11 11:58 | Yes | -12
VD-9001-201A-DWG-024 | 0 | EXTERNAL ATTACHMENT DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:31 | 2019-03-09 08:32 | Yes | 209 |  |  |  | 2019-06-03 11:10 |  |  |  |  | 2019-06-03 11:10 | Yes | 72
VD-9001-201A-DWG-025 | 0 | TEMPLATE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-12-17 11:28 | 2018-12-17 11:28 | Yes | 127 |  |  | 2018-12-17 13:24 | [5 empty] | 2018-12-17 13:24 | Yes | -14 | 1204-Owner-v | 2019-01-05 12:46
VD-9001-201A-DWG-026 | 0 | SHIPPING AND LIFTING STYLE DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-09 08:41 | 2019-03-09 08:41 | Yes | 209 |  |  |  | 2019-05-20 12:33 |  |  |  |  | 2019-05-20 12:33 | Yes | 58 | 1204-Owner-v | 2019-12-15 13:29
VD-9001-201A-DWG-027 | 0 | LADDER & PLATFORM DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2019-03-12 08:13 | 2019-03-12 08:13 | Yes | 212 |  |  |  | 2019-04-24 15:14 |  |  |  |  | 2019-04-24 15:14 | Yes | 29
VD-9001-201A-DWG-028 | 0 | TOP DAVIT DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-201A-WMP-029 | 0 | WELDING & NDT MAP - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-10-13 | 2019-05-12 10:57 | 2019-05-12 10:57 | Yes | 211 |  |  |  | 2019-06-02 12:11 |  |  |  |  | 2019-06-02 12:11 | Yes | 7
VD-9001-201A-CAL-030 | 0 | CALCULATION BOOK - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-07-22 09:14 | 2018-07-22 09:14 | Yes | -21 |  |  |  | 2018-08-28 15:48 |  |  |  |  | 2018-08-28 15:48 | Yes | 23
VD-9001-201A-ANL-031 | 0 | F.E.A. FOR SKIRT - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-10-06 08:30 | 2018-10-06 08:30 | Yes | 55 |  |  |  | 2018-11-18 15:55 |  |  |  |  | 2018-11-18 15:55 | Yes | 29
VD-9001-201A-ANL-032 | 0 | F.E.A. FOR NOZZLES - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-10-01 16:25 | 2018-10-01 16:25 | Yes | 50 |  |  |  | 2018-11-14 16:45 |  |  |  |  | 2018-11-14 16:45 | Yes | 30
VD-9001-201A-CAL-033 | 0 | SHIPPING CALCULATION - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-10-13 |  |  | No | 615 | [9 empty] | No | 0
VD-9001-201A-VDR-034 | 0 | FINAL VENDOR DATA BOOK - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-10-10 |  |  | No | 253 | [9 empty] | No | 0
VD-9001-201A-DWG-038 | 0 | GENERAL ASSEMBLY - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-07-22 09:20 | 2018-07-22 09:20 | Yes | -21 |  |  |  | 2018-09-04 11:39 |  |  |  |  | 2018-09-04 11:39 | Yes | 30
VD-9001-201A-DWG-039 | 0 | NOZZLE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2018-10-22 14:35 | 2018-10-22 14:35 | Yes | 62 |  |  |  | 2018-12-26 09:54 |  |  | 2018-09-23 17:49 | 2018-09-23 17:49 | 2018-12-26 09:54 | Yes | 51 | 1204-Owner-v | 2019-01-05 12:48
VD-9001-201A-DWG-040 | 0 | INTERNAL DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2019-03-09 09:15 | 2019-03-09 09:15 | Yes | 200 |  |  |  | 2019-06-03 16:36 |  |  |  |  | 2019-06-03 16:36 | Yes | 72
VD-9001-201A-DWG-041 | 0 | NAME PLATE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2019-03-09 09:12 | 2019-03-09 09:12 | Yes | 200 |  |  |  | 2019-03-11 11:59 |  |  |  |  | 2019-03-11 11:59 | Yes | -12
VD-9001-201A-DWG-042 | 0 | EXTERNAL ATTACHMENT DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2019-03-09 09:09 | 2019-03-09 09:09 | Yes | 200 |  |  |  | 2019-06-03 11:11 |  |  |  |  | 2019-06-03 11:11 | Yes | 72
VD-9001-201A-DWG-043 | 0 | TEMPLATE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2019-03-05 15:59 | 2019-03-05 15:59 | Yes | 196 |  |  | 2019-03-06 17:24 | [5 empty] | 2019-03-06 17:24 | Yes | -13 | 1204-Owner-v | 2019-05-09 08:23
VD-9001-201A-DWG-044 | 0 | SHIPPING AND LIFTING STYLE DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2019-03-09 09:13 | 2019-03-09 09:13 | Yes | 200 |  |  |  | 2019-05-20 12:32 |  |  |  |  | 2019-05-20 12:32 | Yes | 58 | 1204-Owner-v | 2019-12-15 13:31
VD-9001-201A-DWG-045 | 0 | LADDER & PLATFORM DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 |  |  | No | 668 | [9 empty] | No | 0
VD-9001-201A-DWG-046 | 0 | TOP DAVIT DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 |  |  | No | 668 | [9 empty] | No | 0
VD-9001-201A-WMP-047 | 0 | WELDING & NDT MAP - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2019-05-12 10:58 | 2019-05-12 10:58 | Yes | 201 |  |  |  | 2019-06-02 12:20 |  |  |  |  | 2019-06-02 12:20 | Yes | 7
VD-9001-201A-CAL-048 | 0 | CALCULATION BOOK - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-12 | 2018-07-22 09:17 | 2018-07-22 09:17 | Yes | -21 |  |  |  | 2018-09-01 15:15 |  |  |  |  | 2018-09-01 15:15 | Yes | 27
VD-9001-201A-ANL-049 | 0 | F.E.A. FOR SKIRT - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2018-09-18 09:33 | 2018-09-18 09:33 | Yes | 28 |  |  |  | 2018-12-16 17:45 |  |  |  |  | 2018-12-16 17:45 | Yes | 75
VD-9001-201A-ANL-050 | 0 | F.E.A. FOR NOZZLES - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2018-10-21 08:54 | 2018-10-21 08:54 | Yes | 61 |  |  |  | 2018-12-16 17:46 |  |  | 2018-09-23 17:41 | 2018-09-23 17:41 | 2018-12-16 17:46 | Yes | 42
VD-9001-201A-CAL-051 | 0 | SHIPPING CALCULATION - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-201A-VDR-052 | 0 | FINAL VENDOR DATA BOOK - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-10-10 |  |  | No | 253 | [9 empty] | No | 0
VD-9001-201A-WBK-053 | 0 | WELDING DOCUMENT (WELDING MAP, WPS, PQR) - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2019-05-12 11:06 | 2019-05-12 11:06 | Yes | 201 |  |  |  | 2019-06-02 12:27 |  |  |  |  | 2019-06-02 12:27 | Yes | 7
VD-9001-201A-PCJ-054 | 0 | PWHT PROCEDURE - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-201A-PCJ-058 | 0 | NDE PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:56 | 2018-11-12 11:57 | Yes | 20 |  |  |  | 2018-12-02 17:04 |  |  |  |  | 2018-12-02 17:04 | Yes | 6
VD-9001-201A-PCJ-059 | 0 | PICKLING & PASSIVATION PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:57 | 2018-11-12 11:57 | Yes | 20 |  |  |  | 2018-12-02 17:07 |  |  |  |  | 2018-12-02 17:07 | Yes | 6
VD-9001-201A-PCJ-060 | 0 | HYDROSTATIC TEST PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:58 | 2018-11-12 11:58 | Yes | 20 |  |  | 2018-12-02 17:15 | [5 empty] | 2018-12-02 17:15 | Yes | 6
VD-9001-201A-PCJ-061 | 0 | PAINTING PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:58 | 2018-11-12 11:58 | Yes | 20 |  |  |  | 2018-12-26 10:30 |  |  |  |  | 2018-12-26 10:30 | Yes | 30
VD-9001-201A-PCJ-062 | 0 | PMI & FERRITE CHECK PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:59 | 2018-11-12 11:59 | Yes | 20 |  |  |  | 2018-12-02 17:30 |  |  |  |  | 2018-12-02 17:30 | Yes | 6
VD-9001-201A-PCJ-063 | 0 | HARDNESS TEST PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 11:59 | 2018-11-12 11:59 | Yes | 20 |  |  |  | 2018-12-02 17:37 |  |  |  |  | 2018-12-02 17:37 | Yes | 6
VD-9001-201A-WBK-064 | 0 | WELDING DOCUMENT (WELDING MAP, WPS, PQR) - R-1001 &R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2019-05-12 11:02 | 2019-05-12 11:02 | Yes | 201 |  |  |  | 2019-06-02 12:23 |  |  |  |  | 2019-06-02 12:23 | Yes | 7
VD-9001-201A-QCP-065 | 0 | QUALITY CONTROL PLAN (QCP) | PV-201A | FATEH SANAT KIMIA | 2018-08-21 | 2018-11-03 16:30 | 2018-11-03 16:31 | Yes | 74 |  |  |  | 2018-12-26 09:59 |  |  |  |  | 2018-12-26 09:59 | Yes | 39
VD-9001-201A-PCJ-066 | 0 | WELDER QUALIFICATION RECORDS | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 12:04 | 2018-11-12 12:04 | Yes | 20 |  |  | 2018-12-03 10:00 | [5 empty] | 2018-12-03 10:00 | Yes | 7
VD-9001-201A-PCJ-067 | 0 | PWHT PROCEDURE - R-1001 &R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-10-23 | 2018-11-12 12:05 | 2018-11-12 12:05 | Yes | 20 |  |  |  | 2018-12-03 10:16 |  |  |  |  | 2018-12-03 10:16 | Yes | 7
VD-9001-201A-VLS-068 | 0 | SUB-VENDOR LIST | PV-201A | FATEH SANAT KIMIA | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-201A-LST-070 | 0 | SPARE PART FORCOMMISSIONING & 2 YEARS | PV-201A | FATEH SANAT KIMIA | 2018-10-23 |  | 2020-04-22 10:03 | Yes | 605 | [6 empty] | 2020-04-28 17:54 | 2020-04-28 17:54 |  | Yes | 0
VD-9001-201A-MPR-071 | 0 | MONTHLY PROGRESS REPORT | PV-201A | FATEH SANAT KIMIA | 2018-10-23 |  |  | No | 605 | [9 empty] | No | 0
VD-9001-204D-DWG-005 | 3 | INTERNAL PARTS DETAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-19 | 2018-10-09 13:00 | 2018-10-09 13:03 | Yes | 82 |  |  |  | 2018-10-29 10:00 |  |  |  |  | 2018-10-29 10:00 | Yes | 6
VD-9001-104(009)-CAL-005 | 1 | P-6103A / P-6103BA - Casing pump Calculation note | PR-104-SUB | AIR LIQUIDE | 2018-07-31 19:59 |  |  | No | 689 | [9 empty] | No | 0
VD-9001-104-LST-011 | 2 | Instrumentation list | PR-104 | AIR LIQUIDE | 2018-07-31 19:59 |  |  | No | 689 | [9 empty] | No | 0
VD-9001-105-RPT-701 | 1 | QC records for Gas-liquid separator | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-07-23 | 2018-07-31 11:45 | 2018-07-31 12:30 | Yes | 8 |  |  | 2018-08-26 09:08 | [5 empty] | 2018-08-26 09:08 | Yes | 12
VD-9001-204D-MAL-021 | 2 | SPARE PARTS LIST FOR TWO YEARS OPERATION (SPIR FORM) | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-20 | 2018-08-02 18:51 | 2018-08-02 18:51 | Yes | 13 |  |  | 2018-08-05 08:56 | [5 empty] | 2018-08-05 08:56 | Yes | -11 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-204D-DWG-032 | 1 | LADDER & PLATFORM LAYOUT DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-20 | 2018-09-27 18:02 | 2018-09-27 18:02 | Yes | 69 |  |  |  | 2018-10-02 11:43 |  |  |  |  | 2018-10-02 11:43 | Yes | -9
VD-9001-104(004)-DWG-025 | 1 | ST C-6102 - Condenser drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-01 19:59 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-204C-DWG-005 | 2 | FIREPROOFING DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-08-01 19:59 | 2018-07-26 11:51 | 2018-07-26 11:52 | Yes | -6 |  |  | 2018-08-11 09:42 | [5 empty] | 2018-08-11 19:59 | Yes | 2 | 1204-Owner-v | 2018-12-16 21:53
VD-9001-104-DSH-020 | 2 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-08-01 19:59 |  |  | No | 688 | [9 empty] | No | 0
VD-9001-202F-ISO-031 | 1 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 | 2018-07-27 21:24 | 2018-07-27 21:34 | Yes | 1 |  |  |  |  | 2018-08-12 11:53 |  |  |  | 2018-08-12 11:53 | Yes | 2 | 1204-Owner-v | 2019-05-11 08:42
VD-9001-202F-ISO-030 | 1 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 | 2018-07-27 21:20 | 2018-07-27 21:21 | Yes | 1 |  |  |  |  | 2018-08-12 11:55 |  |  |  | 2018-08-12 11:55 | Yes | 2 | 1204-Owner-v | 2019-05-11 08:42
VD-9001-202F-ISO-029 | 1 | Boiler Feed Water Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 | 2018-07-27 21:35 | 2018-07-27 21:36 | Yes | 1 |  |  | 2018-08-12 11:56 | [5 empty] | 2018-08-12 11:56 | Yes | 2 | 1204-Owner-v | 2019-03-04 16:05
VD-9001-202F-ISO-028 | 1 | Superheated Steam Pipe (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 | 2018-07-27 21:07 | 2018-07-27 21:07 | Yes | 1 |  |  | 2018-08-12 11:57 | [5 empty] | 2018-08-12 11:57 | Yes | 2 | 1204-Owner-v | 2019-01-21 13:27
VD-9001-202F-ISO-027 | 1 | Superheated Steam Pipe (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 | 2018-07-27 20:58 | 2018-07-27 20:58 | Yes | 1 |  |  | 2018-08-12 11:59 | [5 empty] | 2018-08-12 11:59 | Yes | 2 | 1204-Owner-v | 2019-01-21 13:27
VD-9001-202F-ISO-026 | 1 | Isometric - Downcomer D6B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-025 | 1 | Isometric - Downcomer D5B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-024 | 1 | Isometric - Downcomer D4B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-023 | 1 | Isometric - Downcomer D3B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-022 | 1 | Isometric - Downcomer D2B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-021 | 1 | Isometric - Downcomer D1B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-020 | 1 | Isometric - Riser R6B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-019 | 1 | Isometric - Riser R5B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-018 | 1 | Isometric - Riser R4B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-017 | 1 | Isometric - Riser R3B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-016 | 1 | Isometric - Riser R2B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-015 | 1 | Isometric - Riser R1B (Train B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-014 | 1 | Isometric - Downcomer D6A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-013 | 1 | Isometric - Downcomer D5A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-012 | 1 | Isometric - Downcomer D4A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-011 | 1 | Isometric - Downcomer D3A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-010 | 1 | Isometric - Downcomer D2A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-009 | 1 | Isometric - Downcomer D1A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-008 | 1 | Isometric - Riser R6A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-007 | 1 | Isometric - Riser R5A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-006 | 1 | Isometric - Riser R4A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-005 | 1 | Isometric - Riser R3A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-202F-ISO-004 | 1 | Isometric - Riser R2A (Train A) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-26 |  |  | No | 694 | [9 empty] | No | 0
VD-9001-204D-CAL-031 | 2 | SHIPPING SUPPORT CALCULATIONS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-23 | 2018-08-02 18:59 | 2018-08-02 18:59 | Yes | 10 |  |  | 2018-08-05 15:20 | [5 empty] | 2018-08-05 15:20 | Yes | -11
VD-9001-204D-DWG-011 | 2 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-22 | 2018-09-11 14:49 | 2018-09-11 14:49 | Yes | 51 |  |  |  | 2018-11-12 14:32 |  |  |  |  | 2018-11-12 14:32 | Yes | 48 | 1204-Owner-v | 2018-09-24 09:37
VD-9001-204C-DWG-039 | 1 | TEMPLATE DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-21 11:57 | 2018-07-23 13:26 | 2018-07-23 13:26 | Yes | 2 |  |  | 2018-08-11 10:24 | [5 empty] | 2018-08-11 19:59 | Yes | 5 | 1204-Owner-v | 2019-05-09 08:23
VD-9001-204C-DWG-048 | 1 | INTERNAL PIPE DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-07-21 11:58 | 2018-07-23 13:24 | 2018-07-23 13:25 | Yes | 2 |  |  | 2018-08-08 11:43 | [5 empty] | 2018-08-08 19:59 | Yes | 2 | 1204-Owner-v | 2018-12-16 21:54
VD-9001-108-DWG-035 | 6 | FAN PACKAGE ASSEMBLY | PR-108 | Farabard | 2018-07-21 14:29 | 2018-08-05 10:24 | 2018-08-05 10:24 | Yes | 15 |  |  | 2018-08-05 11:06 |  |  |  | 2018-07-28 15:20 | 2018-07-28 15:20 | 2018-08-05 19:59 | Yes | -14
VD-9001-202F-DWG-016 | 1 | Steam Drum - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-28 |  |  | No | 692 | [9 empty] | No | 0
VD-9001-202F-DWG-018 | 1 | Steam Drum - Saddle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-28 |  |  | No | 692 | [9 empty] | No | 0
VD-9001-257C-DWG-044 | 2 | DETAILS DRAWING (4137-0371/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 17:54 | 2018-10-11 17:54 | Yes | 75 |  |  |  |  | 2018-11-03 10:07 |  |  |  | 2018-11-03 10:07 | Yes | 9
VD-9001-257C-DWG-038 | 2 | DETAILS DRAWING (4137-0370/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 17:50 | 2018-10-11 17:51 | Yes | 75 |  |  |  |  | 2018-11-24 10:11 |  |  |  | 2018-11-24 10:11 | Yes | 30
VD-9001-257C-DWG-014 | 2 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 16:52 | 2018-10-11 16:52 | Yes | 75 |  |  | 2018-11-10 17:32 | [5 empty] | 2018-11-10 17:32 | Yes | 16
VD-9001-257C-DWG-043 | 2 | NAME PLATE DET.DWG (4137-0370/A2) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 17:52 | 2018-10-11 17:52 | Yes | 75 |  |  | 2018-10-13 18:08 | [5 empty] | 2018-10-13 18:08 | Yes | -12
VD-9001-257C-DWG-037 | 2 | NAME PLATE DET.DWG (4137-0370/A1) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 17:23 | 2018-10-11 17:23 | Yes | 75 |  |  | 2018-10-13 18:06 | [5 empty] | 2018-10-13 18:06 | Yes | -12
VD-9001-257C-DWG-033 | 2 | NAME PLATE DET.DWG (4137-0369/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-28 | 2018-10-11 16:58 | 2018-10-11 16:58 | Yes | 75 |  |  | 2018-10-13 18:01 | [5 empty] | 2018-10-13 18:01 | Yes | -12
VD-9001-104(003)-DWG-001 | 2 | T-6102 - General arrangement drawing (for client) | PR-104-SUB | AIR LIQUIDE | 2018-08-04 19:59 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-039 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 19:59 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-040 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 19:59 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-031 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-032 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-033 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-307A-DWG-034 | 1 | Mechanical Seal Drawing | MC-307A | KSB GERMANY | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-104-VLS-001 | 1 | SUB SUPPLIER LIST | PR-104 | AIR LIQUIDE | 2018-08-04 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-257C-DWG-063 | 1 | EXPANSION BELLOW DETAILS DRAWING (4137-0367/EB) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-29 | 2018-10-11 16:57 | 2018-10-11 16:57 | Yes | 74 |  |  | 2018-10-13 15:56 | [5 empty] | 2018-10-13 15:56 | Yes | -12
VD-9001-257C-DWG-062 | 1 | EXPANSION BELLOW DETAILS DRAWING (4137-0366/EB) | HM-257C | Brembana & Rolle S.p.A. | 2018-07-29 | 2018-10-11 16:53 | 2018-10-11 16:53 | Yes | 74 |  |  | 2018-10-13 15:29 | [5 empty] | 2018-10-13 15:29 | Yes | -12
VD-9001-745-ITP-001 | 0 | Inspection and Test Plan | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:17 | 2018-07-29 10:17 | Yes | -14 | [9 empty] | No | 677 | 1204-Owner-v | 2020-01-01 13:00
VD-9001-745-PRC-001 | 0 | NDE Procedures (UT,MT,PT,RT) | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:18 | 2018-07-29 10:18 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-PRC-002 | 0 | Welding Documents (WPS and PQR) | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:23 | 2018-07-29 10:23 | Yes | -14 | [9 empty] | No | 677
VD-9001-PL-PLN-001 | 0 | Project Overall Plan | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-LST-001 | 0 | Vendor Print Index Schedule | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-LST-002 | 0 | Sub-Supplier List | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:22 | 2018-07-29 10:22 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-SAD-00776 | 0 | Shop Assembly Drawings-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-SPD-00776 | 0 | Single Part Drawings-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-RPT-00776 | 0 | Reports-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-FRM-007 | 0 | Welding Map | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:24 | 2018-07-29 10:24 | Yes | -14 | [9 empty] | No | 677 | 1204-Owner-v | 2018-08-01 08:00
VD-9001-745-PRC-005 | 0 | Surface Preparation and Painting Procedure/HDG Procedure | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:21 | 2018-07-29 10:21 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-LST-007 | 0 | Vendor Data Book Index List | ST-745 | Pars Tadbir Gostar | 2018-08-12 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-745-MOD-00776 | 0 | Models-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-08-19 10:28 | 2018-08-19 10:28 | Yes | 7 |  |  | 2018-08-28 11:30 |  |  |  | 2018-08-18 11:34 | 2018-08-18 11:35 | 2018-08-28 11:30 | Yes | -5 | 1204-Owner-v | 2019-05-01 18:17
VD-9001-745-GAD-00776 | 0 | General Arrangement Drawings-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-08-19 10:29 | 2018-08-19 10:29 | Yes | 7 |  |  |  | 2018-08-28 11:26 |  |  | 2018-08-18 15:31 | 2018-08-18 15:31 | 2018-08-28 11:27 | Yes | -5 | 1204-Owner-v | 2019-02-28 23:02
VD-9001-745-LST-003 | 0 | Reference/Experience list | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:21 | 2018-07-29 10:21 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-PRC-004 | 0 | Packing and Marking Procedure | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:20 | 2018-07-29 10:20 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-FRM-008 | 0 | Welder Performance Qualification Certificates | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:25 | 2018-07-29 10:26 | Yes | -14 | [9 empty] | No | 677
VD-9001-745-FRM-009 | 0 | NDE Operator Certificates | ST-745 | Pars Tadbir Gostar | 2018-08-12 | 2018-07-29 10:18 | 2018-07-29 10:18 | Yes | -14 | [9 empty] | No | 677
VD-9001-404A-INX-001 | 2 | FINAL DATA BOOK INDEX | PI-404A | KVC CO., LTD. | 2018-08-05 17:26 | 2018-07-24 09:59 | 2018-07-24 09:59 | Yes | -12 |  |  | 2018-07-24 17:12 | [5 empty] | 2018-07-24 17:12 | Yes | -14 | 1204-Owner-v | 2019-02-02 14:10
VD-9001-204D-CAL-014 | 2 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-24 | 2018-08-02 18:57 | 2018-08-02 18:57 | Yes | 9 |  |  |  |  | 2018-08-06 08:43 |  |  |  | 2018-08-06 08:43 | Yes | -10
VD-9001-204D-DSH-030 | 2 | PROCESS/MECHANICAL DATA SHEET | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-24 | 2018-10-09 13:40 | 2018-10-09 13:40 | Yes | 77 |  |  | 2018-10-29 08:50 | [5 empty] | 2018-10-29 08:50 | Yes | 6 | 1204-Owner-v | 2018-12-16 21:56
VD-9001-204D-DWG-004 | 3 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-24 | 2018-10-09 12:58 | 2018-10-09 12:58 | Yes | 77 |  |  | 2018-10-29 14:18 | [5 empty] | 2018-10-29 14:18 | Yes | 6 | 1204-Owner-v | 2018-11-04 09:20
VD-9001-204D-DWG-003 | 3 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-24 | 2018-10-09 12:55 | 2018-10-09 12:55 | Yes | 77 |  |  |  | 2018-11-03 14:06 |  |  |  |  | 2018-11-03 14:06 | Yes | 11
VD-9001-204D-GAD-002 | 3 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-07-24 | 2018-08-02 18:43 | 2018-08-02 18:45 | Yes | 9 |  |  |  | 2018-09-03 10:42 |  |  |  |  | 2018-09-03 10:42 | Yes | 18
VD-9001-307A-DSH-025 | 2 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-08-05 19:59 | 2018-09-20 14:42 | 2018-09-20 14:42 | Yes | 46 |  |  |  | 2018-10-15 10:07 |  |  |  |  | 2018-10-15 18:57 | Yes | 11 | 1204-Owner-v | 2018-10-16 13:29
VD-9001-104(008)-DSH-004 | 1 | AE-6187 - Instruments data sheet | PR-104-SUB | AIR LIQUIDE | 2018-08-05 19:59 |  |  | No | 684 | [9 empty] | No | 0
VD-9001-307A-DIG-087 | 1 | Lube oil unit (P&ID) | MC-307A | KSB GERMANY | 2018-08-05 19:59 |  |  | No | 684 | [9 empty] | No | 0
VD-9001-307A-DIG-021 | 1 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-08-05 19:59 | 2018-09-20 14:36 | 2018-09-20 14:41 | Yes | 46 |  |  |  | 2018-10-15 11:02 |  |  |  |  | 2018-10-15 18:57 | Yes | 11 | 1204-Owner-v | 2018-10-09 15:58
VD-9001-104(003)-SKT-002 | 1 | T-6102 - Transport and handling sketches | PR-104-SUB | AIR LIQUIDE | 2018-08-05 19:59 |  |  | No | 684 | [9 empty] | No | 0
VD-9001-604-PCJ-002 | 0 | Paint Procedures | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-28 14:31 | 2018-07-28 14:31 | Yes | 38 | [9 empty] | No | 678
VD-9001-604-MSS-001 | 0 | Handling Procedure | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-08-13 15:54 | 2018-08-13 15:54 | Yes | 54 | [9 empty] | No | 662
VD-9001-604-PCJ-003 | 0 | Storage Procedure | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-28 15:16 | 2018-07-28 15:17 | Yes | 38 | [9 empty] | No | 678 | 1204-Owner-v | 2018-11-19 12:24
VD-9001-604-MCI-001 | 0 | lifting Procedure | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-28 13:02 | 2018-07-28 13:03 | Yes | 38 | [9 empty] | No | 678
VD-9001-604-MNL-001 | 0 | Quality manual | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-28 15:14 | 2018-07-28 15:14 | Yes | 38 | [9 empty] | No | 678
VD-9001-604-WPS-001 | 0 | Welding procedures | IN-604 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-604-PCJ-004 | 0 | Packing & Marking Procedure | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-28 13:50 | 2018-07-28 13:51 | Yes | 38 | [9 empty] | No | 678
VD-9001-604-DSH-001 | 0 | CVDS ( On Off Data sheet) | IN-604 | Nihon KOSO CO. | 2018-06-25 |  |  | No | 725 | [9 empty] | No | 0
VD-9001-604-CAT-001 | 0 | Catalogue | IN-604 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-604-GAD-001 | 0 | GAD | IN-604 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-604-DWG-001 | 0 | Name plate drawings | IN-604 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-604-MNL-002 | 0 | IOM (Installation and operation Manual) | IN-604 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-604-LST-001 | 0 | Spare Parts list | IN-604 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-604-CAT-002 | 0 | Catalogue for the accessories | IN-604 | Nihon KOSO CO. | 2018-09-25 |  |  | No | 633 | [9 empty] | No | 0
VD-9001-604-LST-002 | 0 | Packing List | IN-604 | Nihon KOSO CO. | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-604-LOC-001 | 0 | Letter of Conformity | IN-604 | Nihon KOSO CO. | 2018-06-20 | 2018-07-24 12:18 | 2018-07-24 12:18 | Yes | 34 | [9 empty] | No | 682
VD-9001-604-FAS-001 | 0 | Manufacturing schedule | IN-604 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-604-RPT-001 | 0 | Monthly Report | IN-604 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-604-IPM-001 | 0 | Inspection & test plan | IN-604 | Nihon KOSO CO. | 2018-06-30 | 2018-07-28 12:43 | 2018-07-28 12:43 | Yes | 28 | [9 empty] | No | 678
VD-9001-604-PCJ-001 | 0 | test procedure | IN-604 | Nihon KOSO CO. | 2018-06-30 | 2018-07-28 11:28 | 2018-07-28 11:28 | Yes | 28 | [9 empty] | No | 678
VD-9001-605-MSS-001 | 0 | Handling Procedure | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-08-13 15:47 | 2018-08-13 15:49 | Yes | 54 | [9 empty] | No | 662
VD-9001-605-PCJ-003 | 0 | Storage Procedure | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-08-15 11:21 | 2018-08-15 11:22 | Yes | 56 | [9 empty] | No | 660 | 1204-Owner-v | 2019-01-06 17:11
VD-9001-605-MCI-001 | 0 | lifting Procedure | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-07-25 10:08 | 2018-07-25 10:09 | Yes | 35 | [9 empty] | No | 681 | 1204-Owner-v | 2020-05-05 14:43
VD-9001-605-MNL-001 | 0 | Quality manual | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-07-25 10:30 | 2018-07-25 10:31 | Yes | 35 | [9 empty] | No | 681
VD-9001-605-WPS-001 | 0 | Welding procedures | IN-605 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-605-PCJ-004 | 0 | Packing & Marking Procedure | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-07-25 10:10 | 2018-07-25 10:10 | Yes | 35 | [9 empty] | No | 681
VD-9001-605-LOC-001 | 0 | Letter of Conformity | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-07-24 10:26 | 2018-07-24 10:26 | Yes | 34 | [9 empty] | No | 682
VD-9001-605-FAS-001 | 0 | Manufacturing schedule | IN-605 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-605-RPT-001 | 0 | Monthly Report | IN-605 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-605-IPM-001 | 0 | Inspection & test plan | IN-605 | Nihon KOSO CO. | 2018-06-30 | 2018-07-24 09:52 | 2018-07-24 09:53 | Yes | 24 | [9 empty] | No | 682
VD-9001-605-PCJ-001 | 0 | test procedure | IN-605 | Nihon KOSO CO. | 2018-06-30 | 2018-07-24 12:54 | 2018-07-24 12:54 | Yes | 24 | [9 empty] | No | 682
VD-9001-605-PCJ-002 | 0 | Paint Procedures | IN-605 | Nihon KOSO CO. | 2018-06-20 | 2018-07-25 10:18 | 2018-07-25 10:18 | Yes | 35 | [9 empty] | No | 681
VD-9001-605-DSH-001 | 0 | CVDS ( Control valve Data sheet) | IN-605 | Nihon KOSO CO. | 2018-06-25 | 2018-08-15 11:09 | 2018-08-15 11:09 | Yes | 51 | [9 empty] | No | 660 | 1204-Owner-v | 2020-02-08 12:49
VD-9001-605-PCU-001 | 0 | CV curve | IN-605 | Nihon KOSO CO. | 2018-06-20 |  |  | No | 730 | [9 empty] | No | 0
VD-9001-605-CAT-001 | 0 | Catalogue | IN-605 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-605-GAD-001 | 0 | GAD | IN-605 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-605-DWG-001 | 0 | Name plate drawings | IN-605 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-605-MNL-002 | 0 | IOM (Installation and operation Manual) | IN-605 | Nihon KOSO CO. | 2018-06-30 |  |  | No | 720 | [9 empty] | No | 0
VD-9001-605-LST-001 | 0 | Spare Parts list | IN-605 | Nihon KOSO CO. | 2018-07-20 |  |  | No | 700 | [9 empty] | No | 0
VD-9001-605-CAT-002 | 0 | Catalogue for the accessories | IN-605 | Nihon KOSO CO. | 2018-09-25 |  |  | No | 633 | [9 empty] | No | 0
VD-9001-605-LST-002 | 0 | Packing List | IN-605 | Nihon KOSO CO. | 2019-01-01 |  |  | No | 535 | [9 empty] | No | 0
VD-9001-206B-PCJ-015 | 6 | PAINTING PROCEDURE | PV-206B | TASHA | 2018-07-23 15:44 | 2018-07-25 08:31 | 2018-07-25 08:31 | Yes | 2 |  |  | 2018-08-29 11:06 | [5 empty] | 2018-08-29 11:06 | Yes | 21 | 1204-Owner-v | 2019-02-13 16:12
VD-9001-251-PID-009 | 2 | PID - LOCAL PANELS | HM-251 | KT – Kinetics Technology SpA | 2018-07-30 | 2018-08-29 17:26 | 2018-08-29 17:33 | Yes | 30 |  |  |  |  | 2018-12-04 15:06 |  |  |  | 2018-12-04 15:06 | Yes | 83 | 1204-Owner-v | 2019-04-08 10:42
VD-9001-204C-DWG-003 | 3 | MATERIAL LIST AND GENERAL NOTES | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-08-06 19:59 | 2018-09-10 19:15 | 2018-09-10 19:15 | Yes | 35 |  |  | 2018-09-23 11:00 | [5 empty] | 2018-09-23 18:58 | Yes | -1 | 1204-Owner-v | 2018-11-04 09:17
VD-9001-231B-PCJ-002 | 0 | WPS&PQR | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-09-11 16:09 | 2018-09-11 16:09 | Yes | 52 |  |  |  | 2018-10-13 15:59 |  |  |  |  | 2018-10-13 18:58 | Yes | 18
VD-9001-231B-PCJ-003 | 0 | Painting procedure | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-10-13 08:34 | 2018-10-13 08:34 | Yes | 84 |  |  |  | 2018-10-14 10:27 |  |  |  |  | 2018-10-14 10:27 | Yes | -13
VD-9001-231B-PCJ-004 | 0 | Liquid penetrant Test Procedure | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-09-11 16:07 | 2018-09-11 16:07 | Yes | 52 |  |  | 2018-10-10 11:17 | [5 empty] | 2018-10-10 11:17 | Yes | 15
VD-9001-231B-PCJ-005 | 0 | Packing&Marking&Shipping procedure | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-10-13 08:35 | 2018-10-13 08:35 | Yes | 84 |  |  | 2019-01-21 15:34 | [5 empty] | 2019-01-21 15:34 | Yes | 86
VD-9001-231B-PCJ-006 | 0 | Visual and dimensional inspection procedure | PV-231B | Fars Ghaleb | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-231B-PCJ-007 | 0 | Fabrication procedure | PV-231B | Fars Ghaleb | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-231B-LST-001 | 0 | SPIR FORMS | PV-231B | Fars Ghaleb | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-231B-WPQ-001 | 0 | Welder performance Qualification report | PV-231B | Fars Ghaleb | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-231B-FDB-001 | 0 | Final Data BOOK | PV-231B | Fars Ghaleb | 2018-07-21 |  |  | No | 699 | [9 empty] | No | 0
VD-9001-231B-DWG-001 | 0 | Ladder and platform drawing for Deaerator DA-4001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-12-03 11:11 | 2018-12-03 11:11 | Yes | 135 |  |  | 2018-12-04 11:09 | [5 empty] | 2018-12-04 11:09 | Yes | -13 | 1204-Owner-v | 2018-12-22 09:11
VD-9001-231B-DWG-002 | 0 | Ladder and platform drawing for D-1002 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-12-31 11:48 | 2018-12-31 11:48 | Yes | 163 |  |  | 2019-01-02 11:19 | [5 empty] | 2019-01-02 11:19 | Yes | -12 | 1204-Owner-v | 2019-01-03 10:39
VD-9001-231B-DWG-003 | 0 | Ladder and platform drawing for D-1003 | PV-231B | Fars Ghaleb | 2018-07-21 | 2019-01-06 14:13 | 2019-01-06 14:13 | Yes | 169 |  |  | 2019-01-13 11:44 | [5 empty] | 2019-01-13 20:00 | Yes | -7 | 1204-Owner-v | 2019-04-09 13:32
VD-9001-231B-DWG-004 | 0 | Ladder and platform drawing for D-3006 | PV-231B | Fars Ghaleb | 2018-07-21 | 2019-01-07 15:51 | 2019-01-07 15:54 | Yes | 170 |  |  | 2019-01-13 11:42 | [5 empty] | 2019-01-13 19:59 | Yes | -8 | 1204-Owner-v | 2019-04-09 13:32
VD-9001-231B-DWG-005 | 0 | Ladder and platform drawing for D-3007 | PV-231B | Fars Ghaleb | 2018-07-21 | 2019-01-13 11:45 | 2019-01-13 11:45 | Yes | 176 |  |  | 2019-01-15 09:41 | [5 empty] | 2019-01-15 09:41 | Yes | -12 | 1204-Owner-v | 2019-04-09 13:31
VD-9001-231B-DWG-006 | 0 | Ladder and platform drawing FOR SATURATOR COLUMN T-1001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-09-24 09:40 | 2018-09-24 09:42 | Yes | 65 |  |  |  | 2018-09-26 14:53 |  |  |  |  | 2018-09-26 14:53 | Yes | -12
VD-9001-231B-DWG-007 | 0 | Ladder and platform drawing FOR SATURATOR COLUMN T-2001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-09-08 09:33 | 2018-09-08 09:33 | Yes | 49 |  |  | 2018-09-08 12:10 |  |  |  | 2018-08-13 15:53 | 2018-08-13 15:53 | 2018-09-08 12:10 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:04
VD-9001-231B-DWG-008 | 0 | Ladder and platform drawing FOR SATURATOR COLUMN T-4001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-09-29 15:28 | 2018-09-29 15:28 | Yes | 70 |  |  |  |  | 2018-10-03 11:21 |  | 2018-08-13 15:52 | 2018-08-13 15:52 | 2018-10-03 11:21 | Yes | -10
VD-9001-231B-DWG-009 | 0 | Ladder and platform Arrangment D-1001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-04 10:47 | 2018-11-04 10:47 | Yes | 106 |  |  | 2018-11-04 15:57 | [5 empty] | 2018-11-04 15:57 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:09
VD-9001-231B-DWG-0010 | 0 | Ladder and platform Detail D-1001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-04 10:46 | 2018-11-04 10:46 | Yes | 106 |  |  | 2018-11-04 16:02 | [5 empty] | 2018-11-04 16:02 | Yes | -14 | 1204-Owner-v | 2018-11-26 13:56
VD-9001-231B-DWG-0011 | 0 | Ladder and platform Arrangment D-2002 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-04 16:32 | 2018-11-04 16:33 | Yes | 106 |  |  | 2018-11-05 11:38 | [5 empty] | 2018-11-05 11:38 | Yes | -13 | 1204-Owner-v | 2018-11-26 13:57
VD-9001-231B-DWG-0012 | 0 | Ladder and platform Detail D-2002 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-04 16:35 | 2018-11-04 16:35 | Yes | 106 |  |  | 2018-11-05 11:23 | [5 empty] | 2018-11-05 11:23 | Yes | -13 | 1204-Owner-v | 2018-11-26 13:58
VD-9001-231B-DWG-0013 | 0 | Ladder and platform Arrangment D-3001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-05 14:58 | 2018-11-05 14:58 | Yes | 107 |  |  | 2018-11-06 09:21 | [5 empty] | 2018-11-06 09:21 | Yes | -13 | 1204-Owner-v | 2018-11-26 13:59
VD-9001-231B-DWG-0014 | 0 | Ladder and platform Detail D-3001 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-05 14:59 | 2018-11-05 14:59 | Yes | 107 |  |  | 2018-11-06 09:23 | [5 empty] | 2018-11-06 09:23 | Yes | -13 | 1204-Owner-v | 2018-11-26 13:59
VD-9001-231B-DWG-0015 | 0 | Ladder and platform Arrangment D-3003 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-06 11:50 | 2018-11-06 11:50 | Yes | 108 |  |  | 2018-11-06 15:50 | [5 empty] | 2018-11-06 15:50 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:00
VD-9001-231B-DWG-0016 | 0 | Ladder and platform Detail D-3003 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-06 11:51 | 2018-11-06 11:51 | Yes | 108 |  |  | 2018-11-06 15:51 | [5 empty] | 2018-11-06 15:51 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:01
VD-9001-231B-DWG-0017 | 0 | Ladder and platform Arrangment D-3004 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-06 11:59 | 2018-11-06 11:59 | Yes | 108 |  |  | 2018-11-06 15:52 | [5 empty] | 2018-11-06 15:52 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:02
VD-9001-231B-DWG-0018 | 0 | Ladder and platform Detail D-3004 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-06 12:00 | 2018-11-06 12:00 | Yes | 108 |  |  | 2018-11-06 15:52 | [5 empty] | 2018-11-06 15:52 | Yes | -14 | 1204-Owner-v | 2018-11-26 13:55
VD-9001-231B-DWG-0019 | 0 | Ladder and platform Arrangment D-4002 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-10 12:37 | 2018-11-10 12:37 | Yes | 112 |  |  | 2018-11-11 17:00 | [5 empty] | 2018-11-11 17:00 | Yes | -13
VD-9001-231B-DWG-0020 | 0 | Ladder and platform Detail D-4002 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-10 12:38 | 2018-11-10 12:38 | Yes | 112 |  |  | 2018-11-11 17:01 | [5 empty] | 2018-11-11 17:01 | Yes | -13
VD-9001-231B-DWG-0021 | 0 | Ladder and platform Arrangment D-4003 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-10 12:39 | 2018-11-10 12:39 | Yes | 112 |  |  | 2018-11-11 17:02 | [5 empty] | 2018-11-11 17:02 | Yes | -13
VD-9001-231B-DWG-0022 | 0 | Ladder and platform Detail D-4003 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-10 12:40 | 2018-11-10 12:40 | Yes | 112 |  |  | 2018-11-11 17:03 | [5 empty] | 2018-11-11 17:03 | Yes | -13
VD-9001-231B-DWG-0023 | 0 | Ladder and platform Arrangment D-4004 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-11 10:08 | 2018-11-11 10:08 | Yes | 113 |  |  | 2018-11-11 17:07 | [5 empty] | 2018-11-11 17:07 | Yes | -14 | 1204-Owner-v | 2019-01-03 10:39
VD-9001-231B-DWG-0024 | 0 | Ladder and platform Detail D-4004 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-11 10:09 | 2018-11-11 10:09 | Yes | 113 |  |  |  | 2018-11-11 17:08 |  |  |  |  | 2018-11-11 17:08 | Yes | -14
VD-9001-231B-DWG-0025 | 0 | Ladder and platform Arrangment D-6201 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-12 14:05 | 2018-11-12 14:05 | Yes | 114 |  |  |  |  | 2018-11-13 15:01 |  |  |  | 2018-11-13 15:01 | Yes | -13
VD-9001-231B-DWG-0026 | 0 | Ladder and platform Detail D-6201 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-12 14:06 | 2018-11-12 14:06 | Yes | 114 |  |  |  |  | 2018-11-13 15:02 |  |  |  | 2018-11-13 15:02 | Yes | -13
VD-9001-231B-DWG-0027 | 0 | Ladder and platform Arrangment D-6202 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-12 14:08 | 2018-11-12 14:08 | Yes | 114 |  |  |  |  | 2018-11-13 15:03 |  |  |  | 2018-11-13 15:03 | Yes | -13
VD-9001-231B-DWG-0028 | 0 | Ladder and platform Detail D-6202 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-12 14:12 | 2018-11-12 14:10 | Yes | 114 |  |  |  |  | 2018-11-13 15:04 |  |  |  | 2018-11-13 15:04 | Yes | -13
VD-9001-231B-DWG-0029 | 0 | Ladder and platform Arrangment D-6402 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-19 12:56 | 2018-11-19 12:56 | Yes | 121 |  |  |  |  | 2018-11-26 11:13 |  |  |  | 2018-11-26 11:13 | Yes | -7
VD-9001-231B-DWG-0030 | 0 | Ladder and platform Detail D-6402 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-11-19 13:01 | 2018-11-19 13:01 | Yes | 121 |  |  |  |  | 2018-11-26 11:15 |  |  |  | 2018-11-26 11:15 | Yes | -7
VD-9001-231B-DWG-0031 | 0 | Ladder and platform Arrangment D-8301 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-12-05 14:08 | 2018-12-05 14:08 | Yes | 137 |  |  | 2018-12-10 11:06 | [5 empty] | 2018-12-10 11:06 | Yes | -9 | 1204-Owner-v | 2018-12-22 09:16
VD-9001-231B-DWG-0032 | 0 | Ladder and platform Detail D-8301 | PV-231B | Fars Ghaleb | 2018-07-21 | 2018-12-05 14:10 | 2018-12-05 14:10 | Yes | 137 |  |  | 2018-12-10 11:05 | [5 empty] | 2018-12-10 11:05 | Yes | -9 | 1204-Owner-v | 2018-12-22 09:16
VD-9001-202F-PPL-002 | 4 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-07 15:25 | 2018-07-27 20:44 | 2018-07-27 20:44 | Yes | -11 |  |  | 2018-08-04 10:49 | [5 empty] | 2018-08-04 10:49 | Yes | -6
VD-9001-202F-PPL-007 | 4 | Layout - Cut-Free System Boiler | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-31 | 2018-07-27 20:46 | 2018-07-27 20:46 | Yes | -4 |  |  | 2018-08-12 14:54 | [5 empty] | 2018-08-12 14:54 | Yes | 2 | 1204-Owner-v | 2019-01-21 14:02
VD-9001-202F-PPL-008 | 4 | Layout - Cut-Free System Piping | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-07-31 |  |  | No | 689 | [9 empty] | No | 0
VD-9001-204C-DWG-004 | 3 | DETAILS DWG. With Nozzle Details | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-08-07 19:59 | 2018-09-10 19:21 | 2018-09-10 19:21 | Yes | 34 |  |  | 2018-10-07 10:25 | [5 empty] | 2018-10-07 18:58 | Yes | 13 | 1204-Owner-v | 2018-11-04 09:18
VD-9001-104-PPL-001 | 3 | Plot plan - Top view | PR-104 | AIR LIQUIDE | 2018-08-07 19:59 |  |  | No | 682 | [9 empty] | No | 0
VD-9001-108-LST-068 | 0 | ALARM AND SET POINT LIST | PR-108 | Farabard | 2018-07-25 | 2018-07-26 09:25 | 2018-07-26 09:26 | Yes | 1 |  |  | 2018-07-28 11:43 | [5 empty] | 2018-07-28 11:43 | Yes | -12
VD-9001-251-DWG-035 | 3 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:16 | 2018-07-25 18:15 | 2018-07-25 18:18 | Yes | 0 |  |  | 2018-08-04 12:32 | [5 empty] | 2018-08-04 12:32 | Yes | -4 | 1204-Owner-v | 2019-03-02 11:26
VD-9001-251-DWG-036 | 3 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:16 | 2018-07-25 18:20 | 2018-07-25 18:25 | Yes | 0 |  |  | 2018-08-04 12:32 | [5 empty] | 2018-08-04 12:32 | Yes | -4 | 1204-Owner-v | 2019-03-10 14:50
VD-9001-251-DWG-040 | 2 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:16 | 2018-07-25 18:27 | 2018-07-25 18:30 | Yes | 0 |  |  | 2018-08-04 12:33 | [5 empty] | 2018-08-04 12:33 | Yes | -4
VD-9001-251-DWG-042 | 2 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:16 | 2018-07-25 18:49 | 2018-07-25 18:51 | Yes | 0 |  |  | 2018-08-04 12:33 | [5 empty] | 2018-08-04 12:33 | Yes | -4
VD-9001-251-DWG-110 | 2 | plan and platforms – convection details | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:17 | 2018-07-25 18:32 | 2018-07-25 18:35 | Yes | 0 |  |  | 2018-08-04 12:34 | [5 empty] | 2018-08-04 12:34 | Yes | -4
VD-9001-251-DWG-028 | 4 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:17 | 2018-07-25 18:13 | 2018-07-25 18:15 | Yes | 0 |  |  | 2018-07-28 10:02 | [5 empty] | 2018-07-28 10:02 | Yes | -11
VD-9001-251-DWG-113 | 2 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:17 | 2018-07-25 18:36 | 2018-07-25 18:41 | Yes | 0 |  |  | 2018-07-28 09:59 | [5 empty] | 2018-07-28 09:59 | Yes | -11 | 1204-Owner-v | 2019-05-08 14:40
VD-9001-251-DWG-129 | 1 | Foundation base plate details (sh.7) | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:17 | 2018-07-25 18:41 | 2018-07-25 18:42 | Yes | 0 |  |  | 2018-07-28 10:00 | [5 empty] | 2018-07-28 10:00 | Yes | -11 | 1204-Owner-v | 2018-09-11 15:49
VD-9001-251-DWG-130 | 1 | Foundation base plate details (sh.8) | HM-251 | KT – Kinetics Technology SpA | 2018-07-25 16:17 | 2018-07-25 18:45 | 2018-07-25 18:48 | Yes | 0 |  |  | 2018-07-28 10:00 | [5 empty] | 2018-07-28 10:00 | Yes | -11 | 1204-Owner-v | 2018-09-11 15:43
VD-9001-307A-DWG-007 | 1 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-08-08 19:59 | 2018-09-28 12:20 | 2018-09-28 12:23 | Yes | 51 |  |  |  | 2018-10-10 10:37 |  |  |  |  | 2018-10-10 18:57 | Yes | -2 | 1204-Owner-v | 2018-10-31 16:49
VD-9001-201B-DSH-003 | 1 | REFRACTORY DATA SHEET (4134-0359/RDS) | PV-201B | Brembana & Rolle S.p.A. | 2018-08-08 19:59 | 2019-02-25 14:49 | 2019-02-25 14:49 | Yes | 201 |  |  |  | 2019-03-03 18:05 |  |  |  |  | 2019-03-03 20:00 | Yes | -8
VD-9001-307A-VLS-001 | 1 | Sub Vendor List | MC-307A | KSB GERMANY | 2018-08-12 19:59 |  |  | No | 677 | [9 empty] | No | 0
VD-9001-204B-PQR-001 | 4 | Procedure Qualification Record (PQR) For S.S | PV-204B | ABAN AIR COOLER. | 2018-08-06 | 2018-08-01 14:15 | 2018-08-01 14:16 | Yes | -5 |  |  | 2018-08-23 09:02 | [5 empty] | 2018-08-23 09:02 | Yes | 8 | 1204-Owner-v | 2020-04-29 08:45
VD-9001-204B-PQR-002 | 4 | Procedure Qualification Record (PQR) For C.S | PV-204B | ABAN AIR COOLER. | 2018-08-06 | 2018-08-01 14:25 | 2018-08-01 14:25 | Yes | -5 |  |  | 2018-08-23 09:07 | [5 empty] | 2018-08-23 09:07 | Yes | 8 | 1204-Owner-v | 2019-02-02 13:48
VD-9001-251-DWG-124 | 0 | GENERAL ARRANGEMENT ALIGNMENTS “R-S” | HM-251 | KT – Kinetics Technology SpA | 2018-07-30 | 2018-07-30 19:36 | 2018-07-30 19:38 | Yes | 0 |  |  | 2018-08-06 17:46 | [5 empty] | 2018-08-06 17:46 | Yes | -7
VD-9001-251-DWG-125 | 0 | GENERAL ARRANGEMENT ALIGNMENTS “17-18-19” | HM-251 | KT – Kinetics Technology SpA | 2018-07-30 | 2018-07-30 19:45 | 2018-07-30 19:48 | Yes | 0 |  |  | 2018-08-06 17:47 | [5 empty] | 2018-08-06 17:47 | Yes | -7
VD-9001-251-DWG-127 | 0 | FAN AND FROM FAN TO STACK - DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-07-30 | 2018-07-30 19:44 | 2018-07-30 19:45 | Yes | 0 |  |  | 2018-08-07 09:36 | [5 empty] | 2018-08-07 09:36 | Yes | -6 | 1204-Owner-v | 2018-10-09 15:20
VD-9001-251-DWG-132 | 0 | PLANS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-07-30 | 2018-07-30 19:40 | 2018-07-30 19:43 | Yes | 0 |  |  | 2018-08-07 09:36 | [5 empty] | 2018-08-07 09:36 | Yes | -6
VD-9001-204B-WPS-002 | 4 | Welding Procedure Specification (WPS) For C.S | PV-204B | ABAN AIR COOLER. | 2018-07-30 16:56 | 2018-08-01 14:08 | 2018-08-01 14:08 | Yes | 2 |  |  | 2018-08-23 09:00 | [5 empty] | 2018-08-23 09:00 | Yes | 8 | 1204-Owner-v | 2019-02-02 11:45
VD-9001-307A-DIG-023 | 1 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-08-06 | 2018-09-21 16:36 | 2018-09-21 16:36 | Yes | 46 |  |  |  | 2018-10-15 16:09 |  |  |  |  | 2018-10-15 18:59 | Yes | 10 | 1204-Owner-v | 2018-10-31 15:40
VD-9001-104-STR-002 | 2 | Control strategy | PR-104 | AIR LIQUIDE | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-201-PCJ-011 | 2 | UT EXAMINATION OF WELDS | PV-201 | ATB RIVA CALZONI SpA | 2018-07-31 16:54 | 2018-08-01 14:48 | 2018-08-01 15:00 | Yes | 1 |  |  | 2018-08-21 14:41 | [5 empty] | 2018-08-21 14:41 | Yes | 6 | 1204-Owner-v | 2018-12-16 21:38
VD-9001-307A-DWG-071 | 1 | Motor Drawing | MC-307A | KSB GERMANY | 2018-08-04 09:26 | 2018-08-08 16:02 | 2018-08-08 16:02 | Yes | 4 |  |  | 2018-08-12 08:44 | [5 empty] | 2018-08-12 19:59 | Yes | -10 | 1204-Owner-v | 2018-10-10 10:37
VD-9001-307A-DWG-073 | 1 | Motor Drawing | MC-307A | KSB GERMANY | 2018-08-04 09:26 | 2018-08-08 16:02 | 2018-08-08 16:03 | Yes | 4 |  |  | 2018-08-12 08:42 | [5 empty] | 2018-08-12 19:59 | Yes | -10
VD-9001-307A-DWG-116 | 1 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-08-04 09:26 | 2018-08-08 16:04 | 2018-08-08 16:04 | Yes | 4 |  |  | 2018-08-12 08:40 | [5 empty] | 2018-08-12 19:59 | Yes | -10
VD-9001-307A-DWG-117 | 1 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-08-04 09:26 |  |  | No | 685 | [9 empty] | No | 0
VD-9001-202F-DWG-032 | 0 | Fitting Device - Multi-Ball Bearings / Spring Supports | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-04 | 2018-08-24 16:29 | 2018-08-24 16:29 | Yes | 20 |  |  |  |  | 2018-10-10 11:09 |  |  |  | 2018-10-10 11:09 | Yes | 33 | 1204-Owner-v | 2019-02-25 15:36
VD-9001-204D-MAL-020 | 3 | SPARE PARTS LIST FOR COMMISSIONING & START-UP | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-08-04 10:23 | 2018-08-06 14:21 | 2018-08-06 14:21 | Yes | 2 |  |  | 2018-08-06 14:31 | [5 empty] | 2018-08-06 14:31 | Yes | -14 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-251-DWG-103 | 1 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-08-13 | 2019-10-05 11:02 | 2019-10-05 11:02 | Yes | 418 |  |  |  | 2019-10-22 16:04 |  |  |  |  | 2019-10-22 16:04 | Yes | 3
VD-9001-251-DWG-104 | 1 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-251-DWG-105 | 1 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2018-08-13 | 2019-10-05 11:02 | 2019-10-05 11:02 | Yes | 418 |  |  |  | 2019-10-26 14:36 |  |  |  |  | 2019-10-26 14:36 | Yes | 7
VD-9001-251-DWG-131 | 1 | POWER SUPPLY DISTRIBUTION ID FAN REMOTE I/O PANEL | HM-251 | KT – Kinetics Technology SpA | 2018-08-13 | 2019-10-05 11:03 | 2019-10-05 11:03 | Yes | 418 |  |  |  | 2019-10-26 14:37 |  |  |  |  | 2019-10-26 14:37 | Yes | 7 | 1204-Owner-v | 2020-04-25 18:34
VD-9001-202F-PPL-001 | 2 | Arrangement and Piping Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-11 | 2018-08-21 15:22 | 2018-08-21 15:22 | Yes | 10 |  |  | 2018-09-05 11:00 | [5 empty] | 2018-09-05 11:00 | Yes | 1 | 1204-Owner-v | 2018-12-17 15:25
VD-9001-257C-WBK-008 | 2 | WELDING BOOK (4137-0371/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-11 | 2019-04-02 13:14 | 2019-04-02 13:28 | Yes | 234 |  |  | 2019-04-21 10:33 | [5 empty] | 2019-04-21 10:33 | Yes | 5
VD-9001-257C-WBK-007 | 2 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-11 | 2018-09-18 13:23 | 2018-09-18 13:25 | Yes | 38 |  |  |  |  | 2018-10-13 11:14 |  |  |  | 2018-10-13 11:14 | Yes | 11
VD-9001-257C-WBK-005 | 1 | WELDING BOOK (4137-0368/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-11 | 2018-09-18 12:34 | 2018-09-18 12:35 | Yes | 38 |  |  | 2018-10-13 15:12 | [5 empty] | 2018-10-13 15:12 | Yes | 11
VD-9001-257C-PCJ-003 | 1 | SURFACE PREPARATION AND PAINTING PROCEDURE (4137/SP) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-12 | 2018-08-28 12:37 | 2018-08-28 12:38 | Yes | 16 |  |  | 2018-09-12 15:48 | [5 empty] | 2018-09-12 15:49 | Yes | 1
VD-9001-257B-VDR-045 | 0 | FINAL VENDOR DATABOOK FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-046 | 0 | FINAL VENDOR DATABOOK FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-PCJ-047 | 0 | PMI PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:19 | 2018-12-18 13:19 | Yes | 134 |  |  |  |  | 2019-01-12 11:45 |  |  |  | 2019-01-12 11:45 | Yes | 11
VD-9001-257B-PCJ-048 | 0 | FERRITE CHECK PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:20 | 2018-12-18 13:20 | Yes | 134 |  |  |  |  | 2019-01-12 11:44 |  |  |  | 2019-01-12 11:44 | Yes | 11
VD-9001-257B-PCJ-049 | 0 | HARDNESS TEST PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:20 | 2018-12-18 13:20 | Yes | 134 |  |  |  |  | 2019-01-06 11:59 |  |  |  | 2019-01-06 11:59 | Yes | 5
VD-9001-257B-PCJ-050 | 0 | PICKLING AND PASSIVATION PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:21 | 2018-12-18 13:21 | Yes | 134 |  |  |  |  | 2019-01-06 11:36 |  |  |  | 2019-01-06 11:37 | Yes | 5
VD-9001-257B-PCJ-026 | 0 | PACKING & SHIPPING PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-PCJ-053 | 0 | WELDER QUALIFICATION RECORD | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2020-05-12 14:22 | 2020-05-12 14:22 | Yes | 645 |  |  | 2020-05-25 10:56 | [5 empty] | 2020-05-25 10:56 | Yes | -1
VD-9001-257B-LST-027 | 0 | SPARE PART LIST FOR 2 YEARS | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-12-15 12:06 | 2019-12-15 12:07 | Yes | 496 |  |  |  | 2020-01-04 10:21 |  |  |  |  | 2020-01-04 10:21 | Yes | 6
VD-9001-257B-DWG-002 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-11-05 16:20 | 2018-11-05 16:20 | Yes | 91 |  |  |  |  | 2018-12-10 16:40 |  |  |  | 2018-12-10 16:40 | Yes | 21
VD-9001-257B-DWG-003 | 0 | BUNDLE DETAIL FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-11-05 16:21 | 2018-11-05 16:21 | Yes | 91 |  |  |  |  | 2018-12-06 12:42 |  |  |  | 2018-12-06 12:43 | Yes | 17
VD-9001-257B-CAL-004 | 0 | CALCULATION BOOK FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-08 16:41 | 2018-08-11 08:46 | Yes | 2 |  |  |  |  | 2018-10-14 09:46 |  |  |  | 2018-10-14 09:46 | Yes | 53
VD-9001-257B-DWG-005 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-30 09:12 | 2018-09-30 09:13 | Yes | 55 |  |  |  |  | 2018-10-23 11:19 |  |  |  | 2018-10-23 11:19 | Yes | 9 | 1204-Owner-v | 2019-01-05 12:33
VD-9001-257B-DWG-006 | 0 | BUNDLE DETAIL FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-30 09:09 | 2018-09-30 09:11 | Yes | 55 |  |  |  |  | 2018-10-23 11:20 |  |  |  | 2018-10-23 11:20 | Yes | 9
VD-9001-257B-CAL-007 | 0 | CALCULATION BOOK FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-11 08:44 | 2018-08-11 08:47 | Yes | 5 |  |  |  |  | 2018-10-14 16:38 |  |  |  | 2018-10-14 16:38 | Yes | 50
VD-9001-257B-DWG-008 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-30 14:25 | 2018-09-30 14:30 | Yes | 55 |  |  |  |  | 2018-10-29 17:13 |  |  |  | 2018-10-29 17:13 | Yes | 15
VD-9001-257B-DWG-009 | 0 | BUNDLE DETAIL FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-30 14:26 | 2018-09-30 14:26 | Yes | 55 |  |  |  |  | 2018-10-29 17:20 |  |  |  | 2018-10-29 17:20 | Yes | 15
VD-9001-257B-CAL-010 | 0 | CALCULATION BOOK FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-11 09:38 | 2018-08-11 10:11 | Yes | 5 |  |  |  |  | 2018-09-30 15:42 |  |  |  | 2018-09-30 15:42 | Yes | 36
VD-9001-257B-DWG-011 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-23 13:37 | 2018-10-23 13:38 | Yes | 78 |  |  |  |  | 2018-12-31 10:53 |  |  |  | 2018-12-31 10:53 | Yes | 55 | 1204-Owner-v | 2019-01-05 12:35
VD-9001-257B-DWG-012 | 0 | BUNDLE DETAIL FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-23 13:39 | 2018-10-23 13:39 | Yes | 78 |  |  | 2018-12-16 18:44 | [5 empty] | 2018-12-16 18:44 | Yes | 40
VD-9001-257B-CAL-013 | 0 | CALCULATION BOOK FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-26 11:00 | 2018-09-26 11:01 | Yes | 51 |  |  |  |  | 2018-10-15 18:18 |  |  |  | 2018-10-15 18:18 | Yes | 5
VD-9001-257B-DWG-014 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-16 15:12 | 2018-10-16 15:12 | Yes | 71 |  |  |  |  | 2018-12-30 10:56 |  |  |  | 2018-12-30 10:56 | Yes | 61 | 1204-Owner-v | 2019-01-05 12:38
VD-9001-257B-DWG-015 | 0 | BUNDLE DETAIL FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-16 15:14 | 2018-10-16 15:15 | Yes | 71 |  |  | 2018-12-16 18:06 | [5 empty] | 2018-12-16 18:06 | Yes | 47
VD-9001-257B-CAL-016 | 0 | CALCULATION BOOK FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-11 10:11 | 2018-08-11 10:12 | Yes | 5 |  |  |  |  | 2018-10-14 17:38 |  |  |  | 2018-10-14 17:38 | Yes | 50
VD-9001-257B-DWG-017 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-10 11:52 | 2018-10-10 11:53 | Yes | 65 |  |  |  |  | 2018-12-16 19:12 |  |  |  | 2018-12-16 19:12 | Yes | 53 | 1204-Owner-v | 2019-01-05 12:38
VD-9001-257B-DWG-018 | 0 | BUNDLE DETAIL FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-10-09 16:57 | 2018-10-09 16:58 | Yes | 64 |  |  | 2018-12-16 17:20 | [5 empty] | 2018-12-16 17:20 | Yes | 54
VD-9001-257B-CAL-019 | 0 | CALCULATION BOOK FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-11 10:39 | 2018-08-11 10:47 | Yes | 5 |  |  |  |  | 2018-10-15 18:08 |  |  |  | 2018-10-15 18:08 | Yes | 51
VD-9001-257B-DWG-020 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-29 11:48 | 2018-09-29 11:48 | Yes | 54 |  |  |  |  | 2018-10-23 10:30 |  |  |  | 2018-10-23 10:30 | Yes | 10
VD-9001-257B-DWG-021 | 0 | BUNDLE DETAIL FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-09-29 11:49 | 2018-09-29 11:49 | Yes | 54 |  |  |  |  | 2018-10-23 10:31 |  |  |  | 2018-10-23 10:31 | Yes | 10
VD-9001-257B-CAL-022 | 0 | CALCULATION BOOK FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-14 11:46 | 2018-08-14 11:53 | Yes | 8 |  |  |  |  | 2018-09-30 15:39 |  |  |  | 2018-09-30 15:39 | Yes | 33
VD-9001-257B-DWG-023 | 0 | GENERAL ARRANGEMENT DRAWING FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-28 15:47 | 2018-09-01 10:57 | Yes | 22 |  |  |  |  | 2018-10-22 14:32 |  |  |  | 2018-10-22 14:32 | Yes | 41
VD-9001-257B-DWG-024 | 0 | BUNDLE DETAIL FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-28 14:49 | 2018-08-28 14:50 | Yes | 22 |  |  |  |  | 2018-10-22 14:39 |  |  |  | 2018-10-22 14:39 | Yes | 41
VD-9001-257B-CAL-025 | 0 | CALCULATION BOOK FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-08-14 16:05 | 2018-08-14 16:11 | Yes | 8 |  |  |  |  | 2018-09-30 15:37 |  |  |  | 2018-09-30 15:37 | Yes | 33
VD-9001-257B-LST-026 | 0 | SPARE PART LIST FOR COMMISSIONING | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-028 | 0 | FINAL VENDOR DATABOOK INDEX | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-MPR-029 | 0 | MONTHLY PROGRESS REPORT | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-PCJ-030 | 0 | PAINTING PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-01-06 12:17 | 2019-01-06 12:18 | Yes | 153 |  |  |  |  | 2019-02-12 11:14 |  |  |  | 2019-02-12 11:14 | Yes | 23
VD-9001-257B-PCJ-031 | 0 | P.W.H.T. PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:17 | 2018-12-18 13:17 | Yes | 134 |  |  |  |  | 2019-01-02 18:14 |  |  |  | 2019-01-02 18:14 | Yes | 1
VD-9001-257B-PCJ-032 | 0 | NDT PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 14:28 | 2018-12-18 14:29 | Yes | 134 |  |  | 2019-01-02 18:12 | [5 empty] | 2019-01-02 18:12 | Yes | 1
VD-9001-257B-PCJ-033 | 0 | HYDROSTATIC TEST PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-12-18 13:18 | 2018-12-18 13:18 | Yes | 134 |  |  |  |  | 2019-01-12 11:47 |  |  |  | 2019-01-12 11:47 | Yes | 11
VD-9001-257B-NPL-034 | 0 | WELDING DOCUMENT (WPS,PQR) | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-01-26 17:13 | 2019-01-27 08:21 | Yes | 173 |  |  |  |  | 2019-02-17 16:42 |  |  |  | 2019-02-17 16:42 | Yes | 8
VD-9001-257B-ITP-035 | 0 | INSPECTION AND TEST PLAN | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2018-11-24 14:21 | 2018-11-24 14:21 | Yes | 110 |  |  |  |  | 2018-12-10 16:59 |  |  |  | 2018-12-10 16:59 | Yes | 2 | 1204-Owner-v | 2020-01-01 10:38
VD-9001-257B-PCJ-036 | 0 | FABRICATION PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-01-26 16:02 | 2019-01-26 16:06 | Yes | 173 |  |  | 2019-02-06 14:39 | [5 empty] | 2019-02-06 14:39 | Yes | -3
VD-9001-257B-PCJ-037 | 0 | TUBE EXPAND PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-12-11 14:15 | 2019-12-11 14:16 | Yes | 492 |  |  |  | 2020-01-12 09:20 |  |  |  |  | 2020-01-12 09:20 | Yes | 18
VD-9001-257B-WMP-038 | 0 | WELDING AND NDT MAP | HM-257B | FATEH SANAT KIMIA | 2018-08-06 | 2019-01-26 16:08 | 2019-01-26 16:09 | Yes | 173 |  |  |  |  | 2019-02-06 14:38 |  |  |  | 2019-02-06 14:38 | Yes | -3
VD-9001-257B-VDR-039 | 0 | FINAL VENDOR DATABOOK FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-040 | 0 | FINAL VENDOR DATABOOK FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-041 | 0 | FINAL VENDOR DATABOOK FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-042 | 0 | FINAL VENDOR DATABOOK FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-043 | 0 | FINAL VENDOR DATABOOK FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-257B-VDR-044 | 0 | FINAL VENDOR DATABOOK FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-08-06 |  |  | No | 683 | [9 empty] | No | 0
VD-9001-461AP-MDB-001 | 0 | Manufacturing Final Data Book | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-08-06 | 2018-08-17 14:15 | 2018-08-17 14:16 | Yes | 11 |  |  |  | 2018-08-26 17:19 |  |  |  |  | 2018-08-26 17:19 | Yes | -5
VD-9001-257C-GAD-006 | 2 | GENERAL ARRANGEMENT (4137-0369) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-12 | 2018-10-11 16:49 | 2018-10-11 16:49 | Yes | 60 |  |  |  |  | 2018-11-28 15:43 |  |  |  | 2018-11-28 15:43 | Yes | 34
VD-9001-204D-CAL-014 | 3 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-08-08 | 2018-09-06 16:59 | 2018-09-06 16:59 | Yes | 29 |  |  |  | 2018-09-30 17:14 |  |  |  |  | 2018-09-30 17:14 | Yes | 10
VD-9001-204D-PCJ-017 | 2 | PAINTING SPECIFICATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-08-08 | 2018-08-30 17:44 | 2018-08-30 17:44 | Yes | 22 |  |  | 2018-09-05 10:46 | [5 empty] | 2018-09-05 10:46 | Yes | -8
VD-9001-204D-DWG-034 | 0 | VICO-TEX MIST ELIMINATORS FOR STEAM DRUM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-08-06 | 2018-08-06 14:47 | 2018-08-06 14:47 | Yes | 0 |  |  | 2018-08-13 15:14 | [5 empty] | 2018-08-13 15:14 | Yes | -7 | 1204-Owner-v | 2019-05-11 08:00
VD-9001-254-DSH-134 | 3 | DATA SHEET FOR BURNER | HM-254 | AZAR AB | 2018-08-10 | 2018-08-26 09:36 | 2018-08-26 09:37 | Yes | 16 |  |  |  | 2018-12-08 09:30 |  |  |  |  | 2018-12-08 09:30 | Yes | 90 | 1204-Owner-v | 2019-07-06 16:19
VD-9001-204C-DWG-035 | 3 | LADDER & PLATFORM S DWGS. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-08-21 19:59 | 2018-09-17 17:43 | 2018-09-17 17:43 | Yes | 27 |  |  | 2018-09-25 17:05 | [5 empty] | 2018-09-25 18:58 | Yes | -6
VD-9001-204D-CAL-016 | 1 | LIFTING CALCULATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-08-10 | 2018-08-30 17:25 | 2018-08-30 17:25 | Yes | 20 |  |  |  | 2018-09-08 10:42 |  |  |  |  | 2018-09-08 10:42 | Yes | -5
VD-9001-251-DWG-044 | 1 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-08-08 10:12 | 2018-08-08 16:31 | 2018-08-08 16:37 | Yes | 0 |  |  | 2018-08-11 10:58 | [5 empty] | 2018-08-11 10:58 | Yes | -11
VD-9001-251-DWG-045 | 1 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-08-08 10:13 | 2018-08-08 16:32 | 2018-08-08 16:37 | Yes | 0 |  |  | 2018-08-11 10:59 | [5 empty] | 2018-08-11 10:59 | Yes | -11
VD-9001-251-DWG-046 | 1 | HORIZONTAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-08-08 10:13 | 2018-08-08 16:34 | 2018-08-08 16:37 | Yes | 0 |  |  | 2018-08-11 11:00 | [5 empty] | 2018-08-11 11:00 | Yes | -11
VD-9001-257C-CAL-009 | 1 | MECHANICAL CALCULATIONS FOR EXPANSION BELLOWS (4137-0366/MCS) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-15 | 2019-02-22 12:10 | 2019-02-22 12:11 | Yes | 191 |  |  | 2020-05-16 12:32 |  | 2019-02-24 09:56 |  |  |  | 2020-05-16 12:32 | Yes | 435
VD-9001-257C-CAL-010 | 1 | MECHANICAL CALCULATIONS FOR EXPANSION BELLOWS (4137-0367/MCS) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-15 | 2019-02-22 12:12 | 2019-02-22 12:13 | Yes | 191 |  |  | 2020-05-16 12:34 |  | 2019-02-24 09:57 |  |  |  | 2020-05-16 12:34 | Yes | 435
VD-9001-257C-PCJ-011 | 0 | LOCAL POST-WELD HEAT TREATMENT PROCEDURE(4137/LPWHT) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-09 | 2018-08-09 11:48 | 2018-08-09 11:55 | Yes | 0 |  |  | 2018-09-08 11:06 | [5 empty] | 2018-09-08 11:06 | Yes | 16
VD-9001-740A-MOD-00084 | 4 | Models-PIPE RACK ZONE 3 | ST-740A | Pars Tadbir Gostar | 2018-08-16 | 2018-08-12 09:08 | 2018-08-12 09:08 | Yes | -4 |  |  | 2018-08-15 08:56 | [5 empty] | 2018-08-15 08:56 | Yes | -11
VD-9001-740A-MOD-00083 | 4 | Models-PIPE RACK ZONE 8 | ST-740A | Pars Tadbir Gostar | 2018-08-16 | 2018-08-12 09:07 | 2018-08-12 09:07 | Yes | -4 |  |  | 2018-08-15 08:55 | [5 empty] | 2018-08-15 08:55 | Yes | -11
VD-9001-253(A)-DWG-002 | 9 | GENERAL ARRANGEMENT for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2018-08-11 14:34 | 2018-08-11 15:51 | 2018-08-11 15:51 | Yes | 0 |  |  | 2018-08-14 09:32 | [5 empty] | 2018-08-14 19:59 | Yes | -11 | 1204-Owner-v | 2018-08-14 17:16
VD-9001-253(A)-DWG-032 | 7 | GENERAL ARRANGEMENT for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2018-08-11 14:35 | 2018-08-11 15:52 | 2018-08-11 16:00 | Yes | 0 |  |  | 2018-08-14 09:20 | [5 empty] | 2018-08-14 19:59 | Yes | -11 | 1204-Owner-v | 2018-08-14 17:32
VD-9001-253(A)-DWG-062 | 8 | GENERAL ARRANGEMENT for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2018-08-11 14:35 | 2018-08-11 16:03 | 2018-08-11 16:24 | Yes | 0 |  |  | 2018-08-14 09:14 | [5 empty] | 2018-08-14 19:59 | Yes | -11 | 1204-Owner-v | 2018-08-14 17:48
VD-9001-201-DWG-001 | 6 | ASSEMBLY AND NOTES | PV-201 | ATB RIVA CALZONI SpA | 2018-08-18 | 2018-09-21 19:49 | 2018-09-21 19:50 | Yes | 34 |  |  | 2018-09-26 15:59 | [5 empty] | 2018-09-26 15:59 | Yes | -9 | 1204-Owner-v | 2018-10-09 10:24
VD-9001-461AF-LST-001 | 0 | Item List | PI-461AF | Van Leeuwen | 2018-08-11 | 2018-08-16 11:38 | 2018-08-16 11:40 | Yes | 5 |  |  |  | 2018-08-18 09:12 |  |  |  |  | 2018-08-18 09:13 | Yes | -12
VD-9001-461AF-PCJ-002 | 0 | Preservation Procedure | PI-461AF | Van Leeuwen | 2018-08-11 | 2018-08-16 11:50 | 2018-08-16 11:51 | Yes | 5 |  |  |  | 2018-08-26 09:21 |  |  |  |  | 2018-08-26 09:26 | Yes | -4
VD-9001-461AF-DWG-001 | 0 | Drawings for Manufacturer Procedure | PI-461AF | Van Leeuwen | 2018-08-11 | 2018-08-16 11:45 | 2018-08-16 11:46 | Yes | 5 |  |  |  | 2018-08-18 08:49 |  |  |  |  | 2018-08-18 08:51 | Yes | -12
VD-9001-202F-ISO-031 | 2 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-ISO-030 | 2 | Equalizing Pipe (Train A/B) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-PPL-005 | 3 | Waste Heat Boiler - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-254-DSH-151 | 3 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2018-08-15 | 2018-08-18 13:03 | 2018-08-18 13:03 | Yes | 3 |  |  |  | 2018-10-22 11:24 |  |  |  |  | 2018-10-22 11:24 | Yes | 51
VD-9001-202F-PPL-006 | 3 | Steam Drum - General Arrangement Drawing | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-DWG-012 | 1 | Waste Heat Boiler - Name Plate | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-DWG-019 | 1 | Steam Drum - Internals I | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-DWG-020 | 1 | Steam Drum - Internals II | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-202F-DWG-021 | 1 | Steam Drum - Internals III | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-19 |  |  | No | 670 | [9 empty] | No | 0
VD-9001-104(002)-DWG-001 | 2 | E-6102 - Vaporizer shell - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-26 19:59 |  |  | No | 663 | [9 empty] | No | 0
VD-9001-104(002)-DWG-002 | 2 | D-6103 - General arrangement drawing | PR-104-SUB | AIR LIQUIDE | 2018-08-26 19:59 |  |  | No | 663 | [9 empty] | No | 0
VD-9001-204C-DWG-007 | 0 | EXTERNAL CLIPS DRAWING | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-08-14 |  |  | No | 675 | [9 empty] | No | 0
VD-9001-251-DSH-001 | 2 | DATA SHEET FOR STEAM REFORMER | HM-251 | KT – Kinetics Technology SpA | 2018-08-20 |  |  | No | 669 | [9 empty] | No | 0
VD-9001-257C-DWG-002 | 2 | DETAILS DRAWING (4137-0364/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-20 | 2018-10-11 16:50 | 2018-10-11 16:50 | Yes | 52 |  |  | 2018-11-17 15:06 | [5 empty] | 2018-11-17 15:06 | Yes | 23 | 1204-Owner-v | 2019-01-30 14:11
VD-9001-104(008)-LST-003 | 1 | AE-6187 - Piping List | PR-104-SUB | AIR LIQUIDE | 2018-08-27 19:59 |  |  | No | 662 | [9 empty] | No | 0
VD-9001-104(008)-LST-004 | 1 | AE-6187 - Piping Accessories list | PR-104-SUB | AIR LIQUIDE | 2018-08-27 19:59 |  |  | No | 662 | [9 empty] | No | 0
VD-9001-104(002)-DWG-017 | 1 | T-6101 & E-6102 - Vaporizer shell - Name plate | PR-104-SUB | AIR LIQUIDE | 2018-08-27 19:59 |  |  | No | 662 | [9 empty] | No | 0
VD-9001-251-DSH-006 | 2 | DATA SHEET FOR AIR PREHEATER (E-4002) | HM-251 | KT – Kinetics Technology SpA | 2018-08-21 |  |  | No | 668 | [9 empty] | No | 0
VD-9001-104-DSH-012 | 5 | EDS Equipment Data Sheet | PR-104 | AIR LIQUIDE | 2018-08-28 |  |  | No | 661 | [9 empty] | No | 0
VD-9001-231B-ITP-001 | 0 | INSPECTON AND TEST PLAN | PV-231B | Fars Ghaleb | 2018-08-19 | 2018-09-08 10:44 | 2018-09-08 10:45 | Yes | 20 |  |  |  | 2018-09-16 16:41 |  |  |  |  | 2018-09-16 16:41 | Yes | -6 | 1204-Owner-v | 2020-01-01 12:57
VD-9001-257C-GAD-003 | 2 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-22 | 2018-10-11 16:48 | 2018-10-11 16:48 | Yes | 50 |  |  |  |  | 2018-11-21 16:57 |  |  |  | 2018-11-21 16:57 | Yes | 27
VD-9001-257C-GAD-004 | 2 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-22 | 2018-10-11 16:49 | 2018-10-11 16:49 | Yes | 50 |  |  |  |  | 2019-01-14 17:07 |  |  |  | 2019-01-14 17:07 | Yes | 81
VD-9001-257C-GAD-001 | 2 | GENERAL ARRANGEMENT (4137-0364) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-22 | 2018-10-11 16:42 | 2018-10-11 16:42 | Yes | 50 |  |  | 2018-11-24 10:18 | [5 empty] | 2018-11-24 10:18 | Yes | 30 | 1204-Owner-v | 2020-02-16 10:27
VD-9001-461AF-DWG-001 | 1 | Drawings for Manufacturer Procedure | PI-461AF | Van Leeuwen | 2018-09-01 08:51 | 2018-08-28 12:37 | 2018-08-28 12:39 | Yes | -4 |  |  |  | 2018-08-28 15:05 |  |  |  |  | 2018-08-28 15:05 | Yes | -14
VD-9001-461AF-LST-001 | 1 | Item List | PI-461AF | Van Leeuwen | 2018-09-01 09:13 | 2018-08-28 13:16 | 2018-08-28 13:19 | Yes | -4 |  |  | 2018-08-28 14:27 | [5 empty] | 2018-08-28 14:33 | Yes | -14
VD-9001-202F-BOQ-010 | 0 | Part List – Bypass Flap | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-20 | 2018-08-20 14:31 | 2018-08-20 14:31 | Yes | 0 |  |  | 2018-08-21 11:53 | [5 empty] | 2018-08-21 11:53 | Yes | -13 | 1204-Owner-v | 2019-01-21 13:29
VD-9001-202F-DWG-034 | 0 | Waste Heat Boiler – Bypass Flap | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-20 | 2018-08-20 14:33 | 2018-08-20 14:33 | Yes | 0 |  |  | 2018-08-21 11:54 | [5 empty] | 2018-08-21 11:54 | Yes | -13
VD-9001-202F-DWG-002 | 2 | Steam Superheater - Nozzle | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-25 |  |  | No | 664 | [9 empty] | No | 0
VD-9001-257C-GAD-005 | 2 | GENERAL ARRANGEMENT (4137-0368) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-25 | 2018-11-05 19:26 | 2018-11-05 19:26 | Yes | 72 |  |  |  |  | 2019-01-01 14:35 |  |  |  | 2019-01-01 14:35 | Yes | 43
VD-9001-251-DSH-005 | 2 | DATA SHEET FOR FLUE GAS AIR PREHEATER (HE-1006) | HM-251 | KT – Kinetics Technology SpA | 2018-08-25 |  |  | No | 664 | [9 empty] | No | 0
VD-9001-404A-DWG-001 | 3 | Drawing | PI-404A | KVC CO., LTD. | 2018-08-20 16:44 | 2018-08-20 16:45 | 2018-08-20 16:45 | Yes | 0 |  |  | 2018-08-20 17:13 | [5 empty] | 2018-08-20 17:13 | Yes | -14 | 1204-Owner-v | 2018-12-30 09:24
VD-9001-202F-SPE-007 | 0 | Piping – Spring Hanger & Supports | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-21 | 2018-08-24 16:14 | 2018-08-24 16:18 | Yes | 3 |  |  |  |  | 2018-09-05 09:38 |  |  |  | 2018-09-05 09:38 | Yes | -2 | 1204-Owner-v | 2020-04-29 10:22
VD-9001-202F-PPL-002 | 5 | Foundation Load Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-21 17:17 | 2018-08-24 16:21 | 2018-08-24 16:21 | Yes | 3 |  |  | 2018-09-05 11:02 | [5 empty] | 2018-09-05 11:02 | Yes | -2 | 1204-Owner-v | 2018-08-26 16:17
VD-9001-202F-PCJ-002 | 3 | Steam Superheater - Hardness Test Procedure | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-29 | 2018-09-24 14:52 | 2018-09-24 14:53 | Yes | 26 |  |  | 2018-11-01 10:46 | [5 empty] | 2018-11-01 10:46 | Yes | 24 | 1204-Owner-v | 2020-04-29 09:41
VD-9001-202F-CAL-002 | 1 | Steam Superheater - Stress Calculation (Code Calculation) | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-25 12:08 | 2018-08-27 17:07 | 2018-08-27 17:08 | Yes | 2 |  |  | 2018-10-10 16:16 | [5 empty] | 2018-10-10 16:16 | Yes | 30 | 1204-Owner-v | 2018-11-27 17:07
VD-9001-202F-BOQ-001 | 2 | Steam Superheater - Part List | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-25 12:09 | 2018-08-27 17:05 | 2018-08-27 17:05 | Yes | 2 |  |  | 2018-08-28 11:05 | [5 empty] | 2018-08-28 11:05 | Yes | -13 | 1204-Owner-v | 2019-01-21 13:26
VD-9001-202F-BOQ-002 | 1 | Steam Superheater - Part List - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-08-25 12:09 | 2018-08-27 17:05 | 2018-08-27 17:06 | Yes | 2 |  |  | 2018-08-28 11:37 | [5 empty] | 2018-08-28 11:37 | Yes | -13 | 1204-Owner-v | 2019-01-21 13:25
VD-9001-251-RPT-001 | 1 | CFD MODELING REPORT | HM-251 | KT – Kinetics Technology SpA | 2018-08-31 |  |  | No | 658 | [9 empty] | No | 0
VD-9001-461AF-PCJ-002 | 1 | Preservation Procedure | PI-461AF | Van Leeuwen | 2018-09-09 09:26 | 2018-08-28 13:21 | 2018-08-28 13:21 | Yes | -12 |  |  |  | 2018-09-03 10:24 |  |  |  |  | 2018-09-03 10:25 | Yes | -8
VD-9001-257C-GAD-002 | 2 | GENERAL ARRANGEMENT (4137-0365) | HM-257C | Brembana & Rolle S.p.A. | 2018-09-02 | 2018-10-31 16:16 | 2018-10-31 16:16 | Yes | 59 |  |  |  |  | 2019-01-05 10:17 |  |  |  | 2019-01-05 10:17 | Yes | 52
VD-9001-202F-WMP-001 | 1 | Steam Superheater - Weld Map & Heat Treatment | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-02 | 2018-10-10 20:22 | 2018-10-10 20:23 | Yes | 38 |  |  | 2018-10-15 18:20 | [5 empty] | 2018-10-15 18:20 | Yes | -9 | 1204-Owner-v | 2020-04-29 10:26
VD-9001-461AP-MDB-001 | 1 | Manufacturing Final Data Book | PI-461AP | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-09-09 17:19 | 2018-09-12 19:19 | 2018-09-12 19:22 | Yes | 3 |  |  | 2018-10-08 09:56 | [5 empty] | 2018-10-08 10:01 | Yes | 12
VD-9001-206B-DWG-011 | 7 | GENERAL ARRANGMENT DRAWING -T-1001 | PV-206B | TASHA | 2018-08-27 09:02 | 2018-09-24 14:50 | 2018-09-24 14:50 | Yes | 28 |  |  | 2018-09-24 15:01 |  |  |  | 2018-09-24 14:41 | 2018-09-24 14:41 | 2018-09-24 15:01 | Yes | -14 | 1204-Owner-v | 2018-11-05 17:54
VD-9001-206B-DWG-012 | 3 | BODY & SUPPORT DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2018-08-27 09:02 | 2018-09-02 12:17 | 2018-09-02 12:18 | Yes | 6 |  |  | 2018-09-23 11:48 |  |  |  | 2018-08-29 11:03 | 2018-08-29 11:03 | 2018-09-23 11:48 | Yes | 7 | 1204-Owner-v | 2019-06-22 10:33
VD-9001-206B-DWG-021 | 3 | SHIPPING DRAWING-T-1001 | PV-206B | TASHA | 2018-08-27 09:02 | 2018-09-02 12:19 | 2018-09-02 12:19 | Yes | 6 |  |  | 2018-09-23 11:37 |  |  |  | 2018-08-29 11:05 | 2018-08-29 11:05 | 2018-09-23 11:37 | Yes | 7 | 1204-Owner-v | 2019-07-10 15:05
VD-9001-745-GAD-00776 | 1 | General Arrangement Drawings-GUARD RAIL | ST-745 | Pars Tadbir Gostar | 2018-09-11 11:27 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-257C-CAL-013 | 0 | PIPING STRESS ANALYSIS (4137-0367/PSA) | HM-257C | Brembana & Rolle S.p.A. | 2018-08-27 | 2018-08-29 12:25 | 2018-08-29 12:27 | Yes | 2 |  |  | 2018-09-30 15:30 | [5 empty] | 2018-09-30 15:30 | Yes | 18
VD-9001-461AF-DWG-001 | 2 | Drawings for Manufacturer Procedure | PI-461AF | Van Leeuwen | 2018-09-11 15:05 | 2018-08-29 10:55 | 2018-08-29 10:59 | Yes | -13 |  |  | 2018-08-29 11:12 | [5 empty] | 2018-08-29 11:12 | Yes | -14
VD-9001-201A-CAL-012 | 1 | CALCULATION BOOK - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-09-04 | 2018-10-01 09:31 | 2018-10-01 09:34 | Yes | 27 |  |  |  | 2018-11-08 14:25 |  |  | 2018-09-23 17:45 | 2018-09-23 17:45 | 2018-11-08 14:25 | Yes | 24
VD-9001-201A-CAL-030 | 1 | CALCULATION BOOK - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-09-04 | 2018-09-29 12:23 | 2018-09-29 12:23 | Yes | 25 |  |  |  | 2018-11-08 14:26 |  |  | 2018-09-23 17:47 | 2018-09-23 17:47 | 2018-11-08 14:26 | Yes | 26
VD-9001-201B-DWG-021 | 1 | REFRACTORY ANCHORS REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF5) | PV-201B | Brembana & Rolle S.p.A. | 2018-09-11 19:58 | 2019-05-20 18:51 | 2019-05-20 18:51 | Yes | 251 |  |  |  | 2019-05-30 13:08 |  |  |  |  | 2019-05-30 20:58 | Yes | -4 | 1204-Owner-v | 2019-05-23 07:21
VD-9001-204D-ITP-022 | 3 | INSPECTION & TESTING PLAN | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-09-01 09:48 | 2018-09-03 11:57 | 2018-09-03 11:57 | Yes | 2 |  |  | 2018-09-08 16:31 | [5 empty] | 2018-09-08 16:31 | Yes | -9 | 1204-Owner-v | 2019-02-17 15:27
VD-9001-105-RPT-707 | 0 | QC records for instruments | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-09-01 | 2018-09-02 13:04 | 2018-09-02 13:04 | Yes | 1 |  |  | 2018-09-08 15:08 | [5 empty] | 2018-09-08 15:08 | Yes | -8 | 1204-Owner-v | 2019-01-04 21:25
VD-9001-105-RPT-708 | 0 | QC records for miscellaneous | PR-105 | DALIAN EUROFILM INDUSTRIAL LTD. | 2018-09-01 | 2018-09-02 13:06 | 2018-09-02 13:06 | Yes | 1 |  |  | 2018-09-08 15:07 | [5 empty] | 2018-09-08 15:07 | Yes | -8
VD-9001-201A-CAL-048 | 1 | CALCULATION BOOK - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-09-08 | 2018-10-20 15:21 | 2018-10-20 15:21 | Yes | 42 |  |  |  | 2018-12-16 17:47 |  |  | 2018-09-23 17:39 | 2018-09-23 17:39 | 2018-12-16 17:47 | Yes | 43
VD-9001-204B-DWG-009 | 3 | Body Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-09-01 15:36 | 2018-09-02 13:38 | 2018-09-02 13:38 | Yes | 1 |  |  |  | 2018-09-02 16:47 |  |  |  |  | 2018-09-02 16:47 | Yes | -14 | 1204-Owner-v | 2018-12-08 10:13
VD-9001-204B-DWG-010 | 4 | Body Detail Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-09-01 15:36 | 2018-09-03 07:50 | 2018-09-03 07:57 | Yes | 2 |  |  | 2018-09-03 08:47 | [5 empty] | 2018-09-03 08:47 | Yes | -14 | 1204-Owner-v | 2018-11-05 09:23
VD-9001-204B-DWG-011 | 8 | Body Detail Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2018-09-01 15:36 | 2018-09-03 16:12 | 2018-09-03 16:13 | Yes | 2 |  |  | 2018-09-03 16:55 | [5 empty] | 2018-09-03 16:55 | Yes | -14 | 1204-Owner-v | 2018-12-02 10:10
VD-9001-204B-DWG-012 | 4 | Body Detail Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2018-09-01 15:36 | 2018-09-04 12:36 | 2018-09-04 12:35 | Yes | 3 |  |  | 2018-09-05 09:34 | [5 empty] | 2018-09-05 09:34 | Yes | -13 | 1204-Owner-v | 2018-12-02 10:10
VD-9001-307A-ITP-011 | 2 | Inspection Test Plan (Turbine) | MC-307A | KSB GERMANY | 2018-09-15 19:58 | 2018-09-21 16:43 | 2018-09-21 16:43 | Yes | 6 |  |  |  | 2018-10-14 16:37 |  |  |  |  | 2018-10-14 18:58 | Yes | 9 | 1204-Owner-v | 2018-10-13 09:50
VD-9001-307A-DSH-024 | 2 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-15 19:58 | 2018-09-20 14:42 | 2018-09-20 14:42 | Yes | 5 |  |  |  | 2018-10-15 15:12 |  |  |  |  | 2018-10-15 18:58 | Yes | 11 | 1204-Owner-v | 2018-10-17 15:48
VD-9001-307A-DSH-021 | 2 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-15 19:58 | 2018-09-20 14:41 | 2018-09-20 14:41 | Yes | 5 |  |  |  | 2018-10-15 09:10 |  |  |  |  | 2018-10-15 18:57 | Yes | 11 | 1204-Owner-v | 2018-10-09 16:03
VD-9001-251-DWG-027 | 5 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-09-02 10:03 | 2018-09-03 11:25 | 2018-09-03 11:30 | Yes | 1 |  |  | 2018-09-04 15:22 | [5 empty] | 2018-09-04 15:22 | Yes | -13 | 1204-Owner-v | 2018-09-11 15:25
VD-9001-251-DWG-028 | 5 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2018-09-02 10:03 | 2018-09-03 11:31 | 2018-09-03 11:54 | Yes | 1 |  |  | 2018-09-04 15:23 | [5 empty] | 2018-09-04 15:23 | Yes | -13 | 1204-Owner-v | 2019-05-08 14:50
VD-9001-201-DWG-003 | 4 | TOP COVER & MAIN FLANGE | PV-201 | ATB RIVA CALZONI SpA | 2018-09-02 12:00 | 2018-09-21 19:53 | 2018-09-21 19:54 | Yes | 19 |  |  | 2018-09-26 12:08 | [5 empty] | 2018-09-26 12:08 | Yes | -9 | 1204-Owner-v | 2018-12-16 21:35
VD-9001-251-MTO-001 | 2 | STEELWORK MATERIAL TAKE OFF | HM-251 | KT – Kinetics Technology SpA | 2018-09-10 | 2019-06-12 11:37 | 2019-06-12 11:37 | Yes | 275 |  |  |  |  | 2019-07-08 16:20 |  |  |  | 2019-07-08 16:20 | Yes | 12
VD-9001-204B-DWG-009 | 4 | Body Detail Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-09-03 | 2018-09-03 08:51 | 2018-09-03 08:51 | Yes | 0 |  |  | 2018-09-03 09:28 | [5 empty] | 2018-09-03 09:28 | Yes | -14 | 1204-Owner-v | 2018-11-05 09:23
VD-9001-307A-DSH-022 | 1 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-09-16 19:58 | 2018-09-20 14:41 | 2018-09-20 14:41 | Yes | 4 |  |  |  | 2018-10-15 09:35 |  |  |  |  | 2018-10-15 18:57 | Yes | 11 | 1204-Owner-v | 2018-10-17 15:48
VD-9001-461AF-PCJ-002 | 2 | Preservation Procedure | PI-461AF | Van Leeuwen | 2018-09-17 10:25 | 2018-09-04 16:05 | 2018-09-04 16:09 | Yes | -13 |  |  | 2018-09-08 14:35 | [5 empty] | 2018-09-08 14:35 | Yes | -10
VD-9001-204D-GAD-002 | 4 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-09-08 | 2018-10-09 12:47 | 2018-10-09 12:49 | Yes | 31 |  |  |  | 2018-11-12 10:16 |  |  |  |  | 2018-11-12 10:16 | Yes | 20 | 1204-Owner-v | 2018-12-11 14:01
VD-9001-201A-DWG-020 | 1 | GENERAL ASSEMBLY - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-09-10 | 2018-10-07 09:29 | 2018-10-07 09:29 | Yes | 27 |  |  |  | 2018-11-18 11:53 |  |  |  |  | 2018-11-18 11:53 | Yes | 28
VD-9001-201A-DWG-002 | 1 | GENERAL ASSEMBLY- R1001 | PV-201A | FATEH SANAT KIMIA | 2018-09-10 | 2018-10-02 14:48 | 2018-10-02 14:48 | Yes | 22 |  |  |  | 2018-11-18 11:52 |  |  |  |  | 2018-11-18 11:52 | Yes | 33
VD-9001-251-DSH-009 | 2 | PROCESS DATA SHEET FOR FLUE GAS FAN | HM-251 | KT – Kinetics Technology SpA | 2018-09-10 |  |  | No | 648 | [9 empty] | No | 0
VD-9001-201B-DWG-020 | 1 | REFRACTORY LINING REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF4) | PV-201B | Brembana & Rolle S.p.A. | 2018-09-17 19:58 | 2019-05-20 19:09 | 2019-05-20 19:09 | Yes | 245 |  |  |  | 2019-05-30 13:07 |  |  |  |  | 2019-05-30 20:58 | Yes | -4 | 1204-Owner-v | 2019-05-23 07:20
VD-9001-201A-DWG-038 | 1 | GENERAL ASSEMBLY - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-09-11 | 2018-10-20 15:28 | 2018-10-20 15:28 | Yes | 39 |  |  |  | 2018-12-16 17:48 |  |  | 2018-09-23 17:43 | 2018-09-23 17:44 | 2018-12-16 17:48 | Yes | 43 | 1204-Owner-v | 2018-12-16 11:47
VD-9001-251-SDG-004 | 1 | STRUCTURAL STEEL STANDARDS FOR EXPANSION JOINTS | HM-251 | KT – Kinetics Technology SpA | 2018-09-04 15:29 | 2018-09-04 19:12 | 2018-09-04 19:13 | Yes | 0 |  |  |  | 2018-09-08 10:23 |  |  |  |  | 2018-09-08 10:23 | Yes | -10
VD-9001-251-DWG-005 | 2 | OUTLET SYSTEM - GENERAL ARRANGEMENT DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-09-04 15:29 | 2018-09-04 19:08 | 2018-09-04 19:10 | Yes | 0 |  |  | 2018-09-22 15:57 | [5 empty] | 2018-09-22 15:57 | Yes | 4 | 1204-Owner-v | 2018-10-09 15:16
VD-9001-201-CAL-001 | 4 | PRESSURE PARTS CALCULATION | PV-201 | ATB RIVA CALZONI SpA | 2018-09-11 | 2018-09-21 19:42 | 2018-09-21 19:48 | Yes | 10 |  |  | 2018-11-17 11:29 | [5 empty] | 2018-11-17 11:29 | Yes | 43 | 1204-Owner-v | 2018-12-16 21:33
VD-9001-251-LST-004 | 2 | EQUIPMENT LIST | HM-251 | KT – Kinetics Technology SpA | 2018-09-11 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-251-DSH-008 | 2 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN | HM-251 | KT – Kinetics Technology SpA | 2018-09-11 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-251-DSH-010 | 2 | PROCESS DATA SHEET FOR COMBUSTION AIR FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-09-11 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-251-DSH-011 | 2 | PROCESS DATA SHEET FOR FLUE GAS FAN TURBINE | HM-251 | KT – Kinetics Technology SpA | 2018-09-11 |  |  | No | 647 | [9 empty] | No | 0
VD-9001-202F-SPE-007 | 1 | Piping – Spring Hanger & Supports | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-12 |  |  | No | 646 | [9 empty] | No | 0
VD-9001-254-DSH-218 | 3 | DATA SHEET FOR MOTORS FOR FORCED DRAFT FANS | HM-254 | AZAR AB | 2018-09-09 | 2018-12-17 07:57 | 2018-12-17 07:57 | Yes | 99 |  |  | 2019-01-02 10:59 | [5 empty] | 2019-01-02 10:59 | Yes | 2 | 1204-Owner-v | 2019-11-09 13:48
VD-9001-251-DWG-041 | 2 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-09-08 09:34 | 2018-09-10 12:42 | 2018-09-10 12:54 | Yes | 2 |  |  | 2018-09-17 11:31 | [5 empty] | 2018-09-17 11:31 | Yes | -7
VD-9001-251-DWG-042 | 3 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-09-08 09:34 | 2018-09-10 12:47 | 2018-09-10 12:56 | Yes | 2 |  |  | 2018-09-17 11:31 | [5 empty] | 2018-09-17 11:31 | Yes | -7
VD-9001-307A-DWG-120 | 2 | Nameplate Drawing Motor | MC-307A | KSB GERMANY | 2018-09-08 09:39 | 2018-09-10 12:55 | 2018-09-10 12:55 | Yes | 2 |  |  | 2018-09-22 08:24 | [5 empty] | 2018-09-22 18:58 | Yes | -2 | 1204-Owner-v | 2018-10-31 15:29
VD-9001-307A-DIG-030 | 2 | Wiring Diagram (Motor) | MC-307A | KSB GERMANY | 2018-09-08 09:40 | 2018-09-10 12:52 | 2018-09-10 12:52 | Yes | 2 |  |  | 2018-09-22 08:26 | [5 empty] | 2018-09-22 18:58 | Yes | -2
VD-9001-307A-DSH-072 | 1 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-09-08 09:41 | 2018-09-10 12:53 | 2018-09-10 12:53 | Yes | 2 |  |  | 2018-10-08 09:08 | [5 empty] | 2018-10-08 18:57 | Yes | 14 | 1204-Owner-v | 2018-10-02 12:51
VD-9001-307A-DSH-074 | 1 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-09-08 09:42 | 2018-09-10 12:53 | 2018-09-10 12:54 | Yes | 2 |  |  | 2018-10-08 09:27 | [5 empty] | 2018-10-08 18:58 | Yes | 14 | 1204-Owner-v | 2018-10-02 12:53
VD-9001-307A-DSH-076 | 1 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-09-08 09:43 | 2018-09-10 12:53 | 2018-09-10 12:54 | Yes | 2 |  |  | 2018-10-08 09:28 | [5 empty] | 2018-10-08 18:58 | Yes | 14
VD-9001-307A-DSH-078 | 1 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-09-08 09:43 | 2018-09-10 12:54 | 2018-09-10 12:54 | Yes | 2 |  |  | 2018-10-08 09:07 | [5 empty] | 2018-10-08 18:57 | Yes | 14
VD-9001-307A-DSH-080 | 1 | Noise Data Sheet | MC-307A | KSB GERMANY | 2018-09-08 09:43 | 2018-09-10 12:54 | 2018-09-10 12:54 | Yes | 2 |  |  | 2018-10-08 09:30 | [5 empty] | 2018-10-08 18:58 | Yes | 14
VD-9001-202F-PPL-004 | 2 | Steam Superheater - General Arrangement | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-15 |  |  | No | 643 | [9 empty] | No | 0
VD-9001-251-SDG-004 | 2 | STRUCTURAL STEEL STANDARDS FOR EXPANSION JOINTS | HM-251 | KT – Kinetics Technology SpA | 2018-09-10 | 2018-09-17 16:59 | 2018-09-17 17:04 | Yes | 7 |  |  | 2018-09-22 16:03 | [5 empty] | 2018-09-22 16:03 | Yes | -9
VD-9001-204D-CAL-016 | 2 | LIFTING CALCULATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-09-10 | 2018-09-11 14:53 | 2018-09-11 14:55 | Yes | 1 |  |  | 2018-09-17 10:01 | [5 empty] | 2018-09-17 10:01 | Yes | -8
VD-9001-202F-SPE-001 | 1 | Spring Hanger Specification | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-15 |  |  | No | 643 | [9 empty] | No | 0
VD-9001-202F-DWG-004 | 2 | Steam Superheater - Manholes/ Handholes | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-15 |  |  | No | 643 | [9 empty] | No | 0
VD-9001-251-DWG-020 | 3 | CONVECTION COIL DRAWING & MANIFOLD HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2018-09-10 | 2018-09-17 16:41 | 2018-09-17 16:42 | Yes | 7 |  |  | 2018-09-22 15:50 | [5 empty] | 2018-09-22 15:50 | Yes | -9
VD-9001-251-DWG-021 | 3 | CONVECTION COIL DRAWING & MANIFOLD HE-1004B | HM-251 | KT – Kinetics Technology SpA | 2018-09-17 | 2019-06-12 10:59 | 2019-06-12 10:59 | Yes | 268 |  |  | 2019-07-06 15:16 | [5 empty] | 2019-07-06 15:16 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-LST-003 | 2 | LINE LIST | HM-251 | KT – Kinetics Technology SpA | 2018-09-17 |  |  | No | 641 | [9 empty] | No | 0
VD-9001-204C-GAD-002 | 4 | GENERAL ARRANGEMENT DWG. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-09-11 08:36 | 2018-09-11 14:30 | 2018-09-11 14:31 | Yes | 0 |  |  | 2018-09-25 17:09 | [5 empty] | 2018-09-25 18:58 | Yes | 0 | 1204-Owner-v | 2018-09-24 09:37
VD-9001-257C-CAL-003 | 2 | MECHANICAL CALCULATION (4137-0366/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-09-18 | 2019-01-22 18:52 | 2019-01-22 18:52 | Yes | 126 |  |  |  |  | 2019-02-06 15:49 |  |  |  | 2019-02-06 15:49 | Yes | 1
VD-9001-257C-CAL-004 | 2 | MECHANICAL CALCULATION (4137-0367/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-09-18 | 2019-01-22 18:53 | 2019-01-22 18:55 | Yes | 126 |  |  |  |  | 2019-02-06 15:52 |  |  |  | 2019-02-06 15:52 | Yes | 1
VD-9001-202F-DWG-035 | 0 | Steam Drum - Internal Details IV | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-12 | 2018-09-12 14:07 | 2018-09-12 14:08 | Yes | 0 |  |  | 2018-10-09 14:13 | [5 empty] | 2018-10-09 14:13 | Yes | 13 | 1204-Owner-v | 2019-01-24 15:17
VD-9001-202F-DWG-036 | 0 | Steam Drum - Internal Details V | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-12 | 2018-09-12 14:10 | 2018-09-12 14:11 | Yes | 0 |  |  | 2018-10-09 14:28 | [5 empty] | 2018-10-09 14:28 | Yes | 13 | 1204-Owner-v | 2019-01-24 15:17
VD-9001-202F-DWG-034 | 1 | Waste Heat Boiler – Bypass Flap | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-12 16:15 | 2018-09-12 16:49 | 2018-09-12 16:49 | Yes | 0 |  |  | 2018-09-18 10:39 | [5 empty] | 2018-09-18 10:39 | Yes | -8 | 1204-Owner-v | 2019-01-24 15:05
VD-9001-204C-DWG-010 | 1 | SHIPPING DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-09-15 11:20 | 2019-02-22 17:49 | 2019-02-22 17:50 | Yes | 160 |  |  |  | 2019-03-11 14:35 |  |  | 2018-09-23 09:52 | 2018-09-23 09:52 | 2019-03-11 20:00 | Yes | 3
VD-9001-307A-LST-045 | 1 | Un-priced copies of sub-orders | MC-307A | KSB GERMANY | 2018-09-29 19:58 |  |  | No | 629 | [9 empty] | No | 0
VD-9001-307A-DWG-013 | 1 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-09-29 19:58 |  |  | No | 629 | [9 empty] | No | 0
VD-9001-307A-DWG-014 | 1 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-09-29 19:58 |  |  | No | 629 | [9 empty] | No | 0
VD-9001-231B-ITP-001 | 1 | INSPECTON AND TEST PLAN | PV-231B | Fars Ghaleb | 2018-09-23 | 2018-09-23 14:44 | 2018-09-23 14:44 | Yes | 0 |  |  |  | 2018-10-13 15:40 |  |  |  |  | 2018-10-13 18:58 | Yes | 6 | 1204-Owner-v | 2020-01-01 12:57
VD-9001-307A-DWG-011 | 2 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-09-30 19:58 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-307A-DWG-012 | 2 | Cross Sectional Drawing with Parts List (Pump) | MC-307A | KSB GERMANY | 2018-09-30 19:58 |  |  | No | 628 | [9 empty] | No | 0
VD-9001-743A-GAD-00086-001 | 0 | GRATING G.A. FOR PIPE RACK STAIRS ZONE 6 TO 9 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:47 | 2018-10-07 14:48 | Yes | 16 |  |  | 2018-11-06 11:25 | [5 empty] | 2018-11-06 11:25 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:23
VD-9001-743A-SAD-00086-001 | 0 | GRATING ASS.DWG. FOR PIPE RACK STAIRS ZONE 6 TO 9 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:49 | 2018-10-07 14:49 | Yes | 16 |  |  | 2018-11-06 11:25 | [5 empty] | 2018-11-06 11:25 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:18
VD-9001-743A-RPT-00086-001 | 0 | ASS. REPORT FOR PIPE RACK STAIRS ZONE 6 TO 9 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:51 | 2018-10-07 14:51 | Yes | 16 |  |  | 2018-11-06 11:26 | [5 empty] | 2018-11-06 11:26 | Yes | 16
VD-9001-743A-MOD-00088 | 0 | GRATING MODEL FOR PIPE RACK ZONE "11" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 12:56 | 2018-10-13 12:56 | Yes | 22 |  |  | 2018-11-06 11:27 | [5 empty] | 2018-11-06 11:27 | Yes | 10 | 1204-Owner-v | 2018-11-26 15:38
VD-9001-743A-GAD-00088-001 | 0 | GRATING G.A. FOR PIPE RACK ZONE "11" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 12:59 | 2018-10-13 12:59 | Yes | 22 |  |  | 2018-11-06 11:28 | [5 empty] | 2018-11-06 11:28 | Yes | 10 | 1204-Owner-v | 2018-11-26 15:56
VD-9001-743A-SAD-00088-001 | 0 | GRATING ASS.DWG. FOR PIPE RACK ZONE "11" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:03 | 2018-10-13 13:03 | Yes | 22 |  |  | 2018-11-06 11:29 | [5 empty] | 2018-11-06 11:29 | Yes | 10 | 1204-Owner-v | 2019-01-09 08:19
VD-9001-743A-RPT-00088-001 | 0 | ASS. REPORT FOR PIPE RACK ZONE "11" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:05 | 2018-10-13 13:05 | Yes | 22 |  |  | 2018-11-06 11:29 | [5 empty] | 2018-11-06 11:29 | Yes | 10
VD-9001-743A-MOD-10112 | 0 | GRATING MODEL FOR STRUCTURE "K" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:10 | 2018-10-13 13:10 | Yes | 22 |  |  | 2018-11-06 11:30 | [5 empty] | 2018-11-06 11:30 | Yes | 10
VD-9001-743A-GAD-10112-001 | 0 | GRATING G.A. FOR STRUCTURE "K" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:12 | 2018-10-13 13:12 | Yes | 22 |  |  | 2018-11-06 17:37 | [5 empty] | 2018-11-06 17:37 | Yes | 10 | 1204-Owner-v | 2018-11-26 15:38
VD-9001-743A-SAD-10112-001 | 0 | GRATING ASS.DWG. FOR STRUCTURE "K" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:13 | 2018-10-13 13:13 | Yes | 22 |  |  | 2018-11-06 11:35 | [5 empty] | 2018-11-06 11:35 | Yes | 10 | 1204-Owner-v | 2019-01-09 08:19
VD-9001-743A-RPT-10112-001 | 0 | ASS. REPORT FOR STRUCTURE "K" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:14 | 2018-10-13 13:14 | Yes | 22 |  |  | 2018-11-06 11:35 | [5 empty] | 2018-11-06 11:35 | Yes | 10
VD-9001-743A-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE (VDIS) | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 09:57 | 2018-10-06 09:57 | Yes | 15 |  |  | 2018-11-26 17:17 | [5 empty] | 2018-11-26 17:17 | Yes | 37 | 1204-Owner-v | 2018-11-26 15:35
VD-9001-743A-ITP-002 | 0 | Inspection & Test Plan | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-11-05 09:19 | 2018-11-05 09:19 | Yes | 45 |  |  |  | 2018-12-22 14:37 |  |  |  |  | 2018-12-22 14:37 | Yes | 33 | 1204-Owner-v | 2018-11-26 15:36
VD-9001-743A-QCP-003 | 0 | Quality Control Plan | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-24 13:13 | 2018-10-24 13:13 | Yes | 33 |  |  | 2018-11-21 11:29 | [5 empty] | 2018-11-21 11:29 | Yes | 14
VD-9001-743A-WPS-004 | 0 | WPS & PQR | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-24 13:53 | 2018-10-24 13:53 | Yes | 33 |  |  |  | 2018-11-21 11:16 |  |  |  |  | 2018-11-21 11:16 | Yes | 14
VD-9001-743A-SRN-005 | 0 | Packing, marking & Shipping Procedure | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-31 12:22 | 2018-10-31 12:22 | Yes | 40 |  |  | 2018-11-21 11:56 | [5 empty] | 2018-11-21 11:56 | Yes | 7
VD-9001-743A-SAD-TR-001 | 0 | FOR 745*280 TRADES | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 11:33 | 2018-10-06 11:35 | Yes | 15 |  |  | 2018-11-06 10:22 | [5 empty] | 2018-11-06 10:22 | Yes | 17 | 1204-Owner-v | 2019-01-09 08:20
VD-9001-743A-SAD-TR-002 | 0 | FOR 795*280 TRADES | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 11:39 | 2018-10-06 11:59 | Yes | 15 |  |  | 2018-11-06 10:23 | [5 empty] | 2018-11-06 10:23 | Yes | 17 | 1204-Owner-v | 2018-11-26 16:03
VD-9001-743A-SAD-TR-003 | 0 | FOR 995*280 TRADES | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 12:07 | 2018-10-06 12:07 | Yes | 15 |  |  | 2018-11-06 10:24 | [5 empty] | 2018-11-06 10:24 | Yes | 17 | 1204-Owner-v | 2019-01-09 08:20
VD-9001-743A-MOD-30302 | 0 | GRATING MODEL FOR STRUCTURE "B" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-13 13:59 | 2018-10-14 07:26 | Yes | 23 |  |  | 2018-11-06 11:46 | [5 empty] | 2018-11-06 11:46 | Yes | 10
VD-9001-743A-GAD-30302-001 | 0 | GRATING G.A. FOR STRUCTURE "B" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-14 07:29 | 2018-10-14 07:30 | Yes | 23 |  |  | 2018-11-06 11:49 | [5 empty] | 2018-11-06 11:49 | Yes | 9 | 1204-Owner-v | 2018-11-26 14:41
VD-9001-743A-SAD-30302-001 | 0 | GRATING ASS.DWG. FOR STRUCTURE "B" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-16 13:15 | 2018-10-16 13:15 | Yes | 25 |  |  | 2018-11-06 11:48 | [5 empty] | 2018-11-06 11:49 | Yes | 7 | 1204-Owner-v | 2018-11-26 14:42
VD-9001-743A-RPT-30302-001 | 0 | ASS. REPORT FOR STRUCTURE "B" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-14 07:31 | 2018-10-14 07:31 | Yes | 23 |  |  | 2018-11-06 11:47 | [5 empty] | 2018-11-06 11:47 | Yes | 9
VD-9001-743A-MOD-30316 | 0 | GRATING MODEL FOR STRUCTURE "G" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 10:42 | 2018-10-07 10:42 | Yes | 16 |  |  | 2018-11-06 10:15 | [5 empty] | 2018-11-06 10:15 | Yes | 16
VD-9001-743A-GAD-30316-001 | 0 | GRATING G.A. FOR STRUCTURE "G" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 12:23 | 2018-10-06 12:23 | Yes | 15 |  |  | 2018-11-06 10:26 | [5 empty] | 2018-11-06 10:26 | Yes | 17 | 1204-Owner-v | 2018-11-26 15:37
VD-9001-743A-SAD-30316-001 | 0 | GRATING ASS.DWG. FOR STRUCTURE "G" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-06 12:21 | 2018-10-06 12:21 | Yes | 15 |  |  | 2018-11-06 10:25 | [5 empty] | 2018-11-06 10:25 | Yes | 17 | 1204-Owner-v | 2019-01-09 08:19
VD-9001-743A-RPT-30316-001 | 0 | ASS. REPORT FOR STRUCTURE "G" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 10:46 | 2018-10-07 10:46 | Yes | 16 |  |  | 2018-11-06 10:27 | [5 empty] | 2018-11-06 10:27 | Yes | 16
VD-9001-743A-MOD-30332 | 0 | GRATING MODEL FOR STRUCTURE "E" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 11:18 | 2018-10-07 11:19 | Yes | 16 |  |  | 2018-11-06 10:29 | [5 empty] | 2018-11-06 10:29 | Yes | 16
VD-9001-743A-GAD-30332-001 | 0 | GRATING G.A. FOR STRUCTURE "E" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 11:22 | 2018-10-07 11:22 | Yes | 16 |  |  | 2018-11-06 10:33 | [5 empty] | 2018-11-06 10:33 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:24
VD-9001-743A-SAD-30332-001 | 0 | GRATING ASS.DWG. FOR STRUCTURE "E" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 11:25 | 2018-10-07 11:26 | Yes | 16 |  |  | 2018-11-06 11:08 | [5 empty] | 2018-11-06 11:08 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:19
VD-9001-743A-RPT-30332-001 | 0 | ASS. REPORT FOR STRUCTURE "E" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 11:28 | 2018-10-07 11:29 | Yes | 16 |  |  | 2018-11-06 11:09 | [5 empty] | 2018-11-06 11:09 | Yes | 16
VD-9001-743A-MOD-30353 | 0 | GRATING MODEL FOR STRUCTURE "F" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 12:35 | 2018-10-07 12:42 | Yes | 16 |  |  | 2018-11-06 11:10 | [5 empty] | 2018-11-06 11:10 | Yes | 16
VD-9001-743A-GAD-30353-001 | 0 | GRATING G.A. FOR STRUCTURE "F" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:12 | 2018-10-07 13:12 | Yes | 16 |  |  | 2018-11-06 11:12 | [5 empty] | 2018-11-06 11:12 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:25
VD-9001-743A-SAD-30353-001 | 0 | GRATING ASS.DWG. FOR STRUCTURE "F" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-14 13:58 | 2018-10-14 13:58 | Yes | 23 |  |  | 2018-11-06 11:48 | [5 empty] | 2018-11-06 11:48 | Yes | 9 | 1204-Owner-v | 2019-01-08 15:54
VD-9001-743A-RPT-30353-001 | 0 | ASS. REPORT FOR STRUCTURE "F" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:17 | 2018-10-07 13:17 | Yes | 16 |  |  | 2018-11-06 11:13 | [5 empty] | 2018-11-06 11:13 | Yes | 16
VD-9001-743A-MOD-71755 | 0 | GRATING MODEL FOR STAIR FOR DYKEWALL | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:28 | 2018-10-07 13:28 | Yes | 16 |  |  | 2018-11-06 11:13 | [5 empty] | 2018-11-06 11:13 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:32
VD-9001-743A-GAD-71755-001 | 0 | GRATING G.A. FOR STAIR FOR DYKEWALL | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:30 | 2018-10-07 13:30 | Yes | 16 |  |  | 2018-11-06 11:14 | [5 empty] | 2018-11-06 11:14 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:25
VD-9001-743A-SAD-71755-001 | 0 | GRATING ASS.DWG. FOR STAIR FOR DYKEWALL | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:33 | 2018-10-07 13:33 | Yes | 16 |  |  | 2018-11-06 11:15 | [5 empty] | 2018-11-06 11:15 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:19
VD-9001-743A-RPT-71755-001 | 0 | ASS. REPORT FOR STAIR FOR DYKEWALL | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:34 | 2018-10-07 13:34 | Yes | 16 |  |  | 2018-11-06 11:15 | [5 empty] | 2018-11-06 11:15 | Yes | 16
VD-9001-743A-MOD-00083 | 0 | GRATING MODEL FOR PIPE RACK ZONE "8" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:43 | 2018-10-07 13:43 | Yes | 16 |  |  | 2018-11-06 11:16 | [5 empty] | 2018-11-06 11:16 | Yes | 16 | 1204-Owner-v | 2019-03-02 11:15
VD-9001-743A-GAD-00083-001 | 0 | GRATING G.A. FOR PIPE RACK ZONE "8" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:53 | 2018-10-07 13:53 | Yes | 16 |  |  | 2018-11-06 11:16 | [5 empty] | 2018-11-06 11:16 | Yes | 16 | 1204-Owner-v | 2018-11-26 14:40
VD-9001-743A-SAD-00083-001 | 0 | GRATING ASS.DWG. FOR PIPE RACK ZONE "8" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:56 | 2018-10-07 13:56 | Yes | 16 |  |  | 2018-11-06 11:17 | [5 empty] | 2018-11-06 11:17 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:18
VD-9001-743A-RPT-00083-001 | 0 | ASS. REPORT FOR PIPE RACK ZONE "8" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 13:57 | 2018-10-07 13:57 | Yes | 16 |  |  | 2018-11-06 11:18 | [5 empty] | 2018-11-06 11:18 | Yes | 16 | 1204-Owner-v | 2019-02-16 20:26
VD-9001-743A-MOD-00084 | 0 | GRATING MODEL FOR PIPE RACK ZONE "3" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:02 | 2018-10-07 14:02 | Yes | 16 |  |  | 2018-11-06 11:19 | [5 empty] | 2018-11-06 11:19 | Yes | 16
VD-9001-743A-GAD-00084-001 | 0 | GRATING G.A. FOR PIPE RACK ZONE "3" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:04 | 2018-10-07 14:04 | Yes | 16 |  |  | 2018-11-06 11:20 | [5 empty] | 2018-11-06 11:20 | Yes | 16 | 1204-Owner-v | 2020-06-06 12:23
VD-9001-743A-SAD-00084-001 | 0 | GRATING ASS.DWG. FOR PIPE RACK ZONE "3" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:05 | 2018-10-07 14:05 | Yes | 16 |  |  | 2018-11-06 11:20 | [5 empty] | 2018-11-06 11:20 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:18
VD-9001-743A-RPT-00084-001 | 0 | ASS. REPORT FOR PIPE RACK ZONE "3" | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:08 | 2018-10-07 14:08 | Yes | 16 |  |  | 2018-11-06 11:21 | [5 empty] | 2018-11-06 11:21 | Yes | 16
VD-9001-743A-MOD-00085 | 0 | GRATING MODEL FOR PIPE RACK STAIRS ZONE 1 TO 5 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:27 | 2018-10-07 14:27 | Yes | 16 |  |  | 2018-11-06 11:21 | [5 empty] | 2018-11-06 11:21 | Yes | 16
VD-9001-743A-GAD-00085-001 | 0 | GRATING G.A. FOR PIPE RACK STAIRS ZONE 1 TO 5 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:30 | 2018-10-07 14:30 | Yes | 16 |  |  | 2018-11-06 11:23 | [5 empty] | 2018-11-06 11:23 | Yes | 16 | 1204-Owner-v | 2019-04-13 07:26
VD-9001-743A-SAD-00085-001 | 0 | GRATING ASS.DWG. FOR PIPE RACK STAIRS ZONE 1 TO 5 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:31 | 2018-10-07 14:31 | Yes | 16 |  |  | 2018-11-06 11:23 | [5 empty] | 2018-11-06 11:23 | Yes | 16 | 1204-Owner-v | 2019-01-09 08:18
VD-9001-743A-RPT-00085-001 | 0 | ASS. REPORT FOR PIPE RACK STAIRS ZONE 1 TO 5 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:33 | 2018-10-07 14:33 | Yes | 16 |  |  | 2018-11-06 11:24 | [5 empty] | 2018-11-06 11:24 | Yes | 16
VD-9001-743A-MOD-00086 | 0 | GRATING MODEL FOR PIPE RACK STAIRS ZONE 6 TO 9 | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-09-21 | 2018-10-07 14:45 | 2018-10-07 14:45 | Yes | 16 |  |  | 2018-11-06 11:24 | [5 empty] | 2018-11-06 11:24 | Yes | 16 | 1204-Owner-v | 2019-04-13 08:37
VD-9001-201B-WBK-001 | 2 | WELDING BOOK (4134-0359/W) | PV-201B | Brembana & Rolle S.p.A. | 2018-09-22 09:16 | 2018-09-24 15:35 | 2018-09-24 15:35 | Yes | 2 |  |  |  | 2018-10-27 15:59 |  |  |  |  | 2018-10-27 20:00 | Yes | 19
VD-9001-201-DWG-005 | 4 | SUPPORT SKIRT EXTERNAL DETAILS TAILING LUG | PV-201 | ATB RIVA CALZONI SpA | 2018-09-22 10:01 | 2018-09-24 17:46 | 2018-09-24 17:55 | Yes | 2 |  |  | 2018-09-26 11:48 | [5 empty] | 2018-09-26 11:48 | Yes | -12 | 1204-Owner-v | 2018-10-20 11:16
VD-9001-204C-DWG-040 | 2 | ERECTION ASSEMBLY | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-09-23 10:18 | 2018-09-24 16:06 | 2018-09-24 16:06 | Yes | 1 |  |  | 2018-09-26 17:14 | [5 empty] | 2018-09-26 18:58 | Yes | -12 | 1204-Owner-v | 2018-12-11 13:57
VD-9001-204C-DWG-041 | 2 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-09-23 10:19 | 2018-09-24 16:10 | 2018-09-24 16:13 | Yes | 1 |  |  |  | 2018-09-29 09:39 |  |  |  |  | 2018-09-29 18:58 | Yes | -9
VD-9001-204C-DWG-046 | 1 | GRATINGS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2018-09-23 10:19 | 2018-09-24 16:20 | 2018-09-24 16:21 | Yes | 1 |  |  | 2018-09-26 09:03 | [5 empty] | 2018-09-26 18:58 | Yes | -12 | 1204-Owner-v | 2019-05-11 07:48
VD-9001-201B-DWG-007 | 1 | LADDER AND PLATFORM DWG (4134-0359/3) | PV-201B | Brembana & Rolle S.p.A. | 2018-10-07 18:58 | 2018-12-19 18:37 | 2018-12-19 18:37 | Yes | 73 |  |  |  |  | 2018-12-30 10:00 |  |  |  | 2018-12-30 20:00 | Yes | -3
VD-9001-201B-DWG-008 | 1 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2018-10-08 18:58 | 2018-12-19 18:37 | 2018-12-19 18:37 | Yes | 72 |  |  |  | 2018-12-30 09:56 |  |  |  |  | 2018-12-30 20:00 | Yes | -3
VD-9001-307A-DSH-103 | 1 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-10-08 18:58 |  |  | No | 620 | [9 empty] | No | 0
VD-9001-307A-DSH-102 | 1 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-10-08 18:58 |  |  | No | 620 | [9 empty] | No | 0
VD-9001-307A-DSH-101 | 1 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-10-08 18:58 |  |  | No | 620 | [9 empty] | No | 0
VD-9001-307A-DSH-099 | 1 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-10-08 18:58 |  |  | No | 620 | [9 empty] | No | 0
VD-9001-307A-DSH-098 | 1 | Lube oil unit (Motor Datasheet) | MC-307A | KSB GERMANY | 2018-10-08 18:58 |  |  | No | 620 | [9 empty] | No | 0
VD-9001-231B-DWG-006 | 1 | Ladder and platform drawing FOR SATURATOR COLUMN T-1001 | PV-231B | Fars Ghaleb | 2018-09-19 | 2018-09-29 16:40 | 2018-09-29 16:41 | Yes | 10 |  |  | 2018-10-02 09:32 | [5 empty] | 2018-10-02 09:32 | Yes | -11 | 1204-Owner-v | 2018-12-26 14:13
VD-9001-202F-ITP-002 | 2 | Steam Superheater - Inspection Plan | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-09-26 16:27 | 2018-09-26 17:08 | 2018-09-26 17:08 | Yes | 0 |  |  | 2018-11-05 14:24 | [5 empty] | 2018-11-05 14:25 | Yes | 26 | 1204-Owner-v | 2020-01-01 12:46
VD-9001-307A-DSH-106 | 1 | Condensate Pump (Data Sheet Pump) FOR P-4005B | MC-307A | KSB GERMANY | 2018-10-10 18:58 |  |  | No | 618 | [9 empty] | No | 0
VD-9001-307A-DSH-105 | 1 | Condensate Pump (Data Sheet Pump) FOR P-4005A | MC-307A | KSB GERMANY | 2018-10-10 18:58 |  |  | No | 618 | [9 empty] | No | 0
VD-9001-307A-PCU-032 | 1 | Condensate Pump Performance Curve) FOR P-4005A | MC-307A | KSB GERMANY | 2018-10-10 18:58 |  |  | No | 618 | [9 empty] | No | 0
VD-9001-307A-PCU-033 | 1 | Condensate Pump (Performance Curve) FOR P-4005B | MC-307A | KSB GERMANY | 2018-10-10 18:58 |  |  | No | 618 | [9 empty] | No | 0
VD-9001-204D-MNL-027 | 1 | INSTALLATION AND MAINTENANCE MANUAL | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-09-29 11:22 | 2018-10-02 09:53 | 2018-10-02 09:53 | Yes | 3 |  |  | 2018-11-06 15:10 | [5 empty] | 2018-11-06 15:10 | Yes | 21
VD-9001-307A-DWG-216 | 1 | Hook up Drawing | MC-307A | KSB GERMANY | 2018-10-13 18:58 |  |  | No | 615 | [9 empty] | No | 0
VD-9001-307A-DSH-089 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-13 18:58 | 2018-11-27 13:11 | 2018-11-27 13:11 | Yes | 45 |  |  | 2018-12-01 16:51 | [5 empty] | 2018-12-01 20:01 | Yes | -10
VD-9001-307A-DSH-086 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-13 18:58 | 2018-11-27 13:10 | 2018-11-27 13:11 | Yes | 45 |  |  | 2018-12-01 17:10 | [5 empty] | 2018-12-01 20:01 | Yes | -10
VD-9001-307A-DSH-090 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-13 18:58 | 2018-11-27 13:12 | 2018-11-27 13:12 | Yes | 45 |  |  | 2018-12-01 16:41 | [5 empty] | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DSH-091 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-13 18:58 | 2018-11-27 13:12 | 2018-11-27 13:12 | Yes | 45 |  |  | 2018-12-01 16:42 | [5 empty] | 2018-12-01 20:00 | Yes | -10
VD-9001-307A-DSH-088 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-13 18:58 | 2018-11-27 13:11 | 2018-11-27 13:11 | Yes | 45 |  |  |  |  | 2018-12-01 17:04 |  |  |  | 2018-12-01 20:01 | Yes | -10
VD-9001-202F-DWG-003 | 1 | Steam Superheater - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-10-07 |  |  | No | 621 | [9 empty] | No | 0
VD-9001-257B-CAL-025 | 1 | CALCULATION BOOK FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-10-07 | 2018-10-31 15:43 | 2018-10-31 15:44 | Yes | 24 |  |  |  |  | 2018-12-31 16:47 |  |  |  | 2018-12-31 16:47 | Yes | 47
VD-9001-257B-CAL-022 | 1 | CALCULATION BOOK FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-10-07 | 2018-10-31 15:42 | 2018-10-31 15:42 | Yes | 24 |  |  |  |  | 2018-12-31 17:12 |  |  |  | 2018-12-31 17:12 | Yes | 47
VD-9001-257B-CAL-010 | 1 | CALCULATION BOOK FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-10-07 | 2018-11-11 10:19 | 2018-11-11 10:21 | Yes | 35 |  |  |  |  | 2018-12-20 11:31 |  |  |  | 2018-12-20 11:31 | Yes | 25
VD-9001-204D-CAL-014 | 4 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-02 | 2018-10-09 13:32 | 2018-10-09 13:33 | Yes | 7 |  |  |  | 2018-10-29 11:45 |  |  |  |  | 2018-10-29 11:45 | Yes | 6
VD-9001-307A-PCJ-005 | 2 | Hydrostatic Test Procedure | MC-307A | KSB GERMANY | 2018-10-14 18:58 | 2018-10-10 10:12 | 2018-10-10 10:12 | Yes | -4 |  |  |  | 2018-10-29 09:02 |  |  |  |  | 2018-10-29 20:00 | Yes | 5
VD-9001-254-DIG-300 | 3 | SYSTEM ARCITECTURE & INTERCONNECTION DIAGRAM FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-10-05 | 2018-12-03 16:08 | 2018-12-03 16:08 | Yes | 59 |  |  |  | 2018-12-23 10:07 |  |  |  |  | 2018-12-23 10:07 | Yes | 6
VD-9001-254-DSH-224 | 3 | DATA SHEET FOR LOCAL CONTROL STATION | HM-254 | AZAR AB | 2018-10-05 | 2018-10-17 13:16 | 2018-10-17 13:16 | Yes | 12 |  |  | 2018-11-14 10:06 | [5 empty] | 2018-11-14 10:06 | Yes | 14
VD-9001-254-MNL-325 | 3 | TECHNICAL SPECIFICATION FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2018-10-05 | 2018-11-20 08:27 | 2018-11-20 08:27 | Yes | 46 |  |  |  | 2018-12-23 16:34 |  |  |  |  | 2018-12-23 16:34 | Yes | 19 | 1204-Owner-v | 2018-11-26 13:49
VD-9001-254-SPE-331 | 1 | TECHNICAL SPECIFICATIONS FOR LBSP | HM-254 | AZAR AB | 2018-10-05 | 2018-11-20 08:27 | 2018-11-20 08:28 | Yes | 46 |  |  |  | 2018-12-23 16:37 |  |  |  |  | 2018-12-23 16:37 | Yes | 19 | 1204-Owner-v | 2018-11-26 13:44
VD-9001-204D-DWG-032 | 2 | LADDER & PLATFORM LAYOUT DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-04 | 2018-10-09 13:10 | 2018-10-09 13:11 | Yes | 5 |  |  |  | 2018-11-03 14:22 |  |  |  |  | 2018-11-03 14:22 | Yes | 11
VD-9001-257C-DWG-008 | 2 | DETAILS DRAWING (4137-0365/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-09 | 2018-10-31 16:17 | 2018-10-31 16:20 | Yes | 22 |  |  | 2018-12-16 17:25 | [5 empty] | 2018-12-16 17:25 | Yes | 32 | 1204-Owner-v | 2019-07-02 09:07
VD-9001-202F-DWG-010 | 3 | Waste Heat Boiler - Supports & External Attachments | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-10-09 |  |  | No | 619 | [9 empty] | No | 0
VD-9001-231B-DWG-008 | 1 | Ladder and platform drawing FOR SATURATOR COLUMN T-4001 | PV-231B | Fars Ghaleb | 2018-10-04 | 2018-10-13 08:07 | 2018-10-13 08:07 | Yes | 9 |  |  |  |  | 2018-10-20 08:59 |  |  |  | 2018-10-20 08:59 | Yes | -7
VD-9001-307A-DSH-087 | 1 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-27 13:10 | 2018-11-27 13:11 | Yes | 41 |  |  | 2018-12-01 17:07 | [5 empty] | 2018-12-01 20:01 | Yes | -10
VD-9001-307A-DSH-081 | 1 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-12 16:03 | 2018-11-12 16:04 | Yes | 26 |  |  | 2018-11-17 10:00 | [5 empty] | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DSH-082 | 1 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-12 16:04 | 2018-11-12 16:05 | Yes | 26 |  |  | 2018-11-17 10:07 | [5 empty] | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DSH-083 | 1 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-12 16:06 | 2018-11-12 16:08 | Yes | 26 |  |  | 2018-11-17 10:36 | [5 empty] | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DSH-084 | 1 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-12 16:06 | 2018-11-12 16:08 | Yes | 26 |  |  | 2018-11-17 10:42 | [5 empty] | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-DSH-085 | 1 | Gear Box Data Sheet | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-11-12 16:06 | 2018-11-12 16:08 | Yes | 26 |  |  | 2018-11-17 10:46 | [5 empty] | 2018-11-17 20:00 | Yes | -9
VD-9001-307A-PCU-025 | 2 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-10-17 15:12 | 2018-10-17 15:12 | Yes | 0 |  |  |  | 2018-11-10 09:34 |  |  |  |  | 2018-11-10 20:00 | Yes | 10
VD-9001-307A-PCU-024 | 2 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-10-17 15:12 | 2018-10-17 15:12 | Yes | 0 |  |  |  | 2018-11-10 09:33 |  |  |  |  | 2018-11-10 20:00 | Yes | 10
VD-9001-307A-PCU-022 | 2 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-10-17 18:57 | 2018-10-17 15:12 | 2018-10-17 15:12 | Yes | 0 |  |  |  | 2018-11-10 09:35 |  |  |  |  | 2018-11-10 20:00 | Yes | 10
VD-9001-257C-ITP-007 | 3 | INSPECTION & TESTING PLAN (4137-0370/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-06 14:15 | 2018-10-08 10:32 | 2018-10-08 10:32 | Yes | 2 |  |  | 2018-10-23 15:08 | [5 empty] | 2018-10-23 15:08 | Yes | 1 | 1204-Owner-v | 2018-10-27 10:43
VD-9001-251-DSH-002 | 2 | DATA SHEET ARCH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-10-14 |  |  | No | 614 | [9 empty] | No | 0
VD-9001-251-DSH-003 | 2 | DATA SHEET TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-10-14 |  |  | No | 614 | [9 empty] | No | 0
VD-9001-251-DSH-004 | 2 | DATA SHEET SSH BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-10-14 |  |  | No | 614 | [9 empty] | No | 0
VD-9001-204B-DWG-005 | 5 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-10-07 16:22 | 2018-10-08 11:01 | 2018-10-08 11:01 | Yes | 1 |  |  |  | 2018-10-09 15:57 |  |  |  |  | 2018-10-09 15:57 | Yes | -13 | 1204-Owner-v | 2018-12-22 10:06
VD-9001-204B-DWG-006 | 2 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-10-07 16:22 | 2018-10-13 13:58 | 2018-10-13 13:59 | Yes | 6 |  |  |  |  | 2018-10-14 17:46 |  |  |  | 2018-10-14 17:46 | Yes | -13
VD-9001-204B-DWG-007 | 4 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2018-10-07 16:22 | 2018-10-14 15:44 | 2018-10-14 15:44 | Yes | 7 |  |  |  | 2018-10-20 09:30 |  |  |  |  | 2018-10-20 09:30 | Yes | -8 | 1204-Owner-v | 2018-12-02 09:20
VD-9001-204B-DWG-008 | 3 | Ladder & Platform Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2018-10-07 16:22 | 2018-10-16 15:50 | 2018-10-16 15:51 | Yes | 9 |  |  | 2018-10-20 10:58 | [5 empty] | 2018-10-20 18:57 | Yes | -10 | 1204-Owner-v | 2018-12-02 09:48
VD-9001-307A-PCU-023 | 1 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-10-21 18:57 |  |  | No | 607 | [9 empty] | No | 0
VD-9001-307A-ITP-001 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-10-22 18:57 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-307A-PCJ-015 | 2 | Long term preservation procedure | MC-307A | KSB GERMANY | 2018-10-22 18:57 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-307A-ITP-002 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-10-22 18:57 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-307A-ITP-010 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-10-22 18:57 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-307A-ITP-009 | 2 | Inspection and Test Plan Pump (ITP) | MC-307A | KSB GERMANY | 2018-10-22 18:57 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-201-CAL-005 | 1 | STRESS ANALYSIS OF TOP FLANGED JOINT | PV-201 | ATB RIVA CALZONI SpA | 2018-10-16 | 2018-11-30 11:31 | 2018-11-30 11:31 | Yes | 45 |  |  | 2018-12-02 16:21 | [5 empty] | 2018-12-02 16:21 | Yes | -12 | 1204-Owner-v | 2018-12-16 21:35
VD-9001-204B-DWG-005 | 6 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-10-16 | 2018-10-10 12:51 | 2018-10-10 12:51 | Yes | -6 |  |  | 2018-10-10 15:38 | [5 empty] | 2018-10-10 15:38 | Yes | -14 | 1204-Owner-v | 2018-11-05 09:16
VD-9001-307A-DWG-074 | 1 | Motor Drawing | MC-307A | KSB GERMANY | 2018-10-09 16:35 | 2018-10-10 10:10 | 2018-10-10 10:11 | Yes | 1 |  |  | 2018-10-13 08:20 | [5 empty] | 2018-10-13 18:57 | Yes | -11
VD-9001-202F-DWG-032 | 1 | Fitting Device - Multi-Ball Bearings / Spring Supports | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-231B-DWG-006 | 2 | Ladder and platform drawing FOR SATURATOR COLUMN T-1001 | PV-231B | Fars Ghaleb | 2018-10-10 16:21 | 2018-10-13 15:17 | 2018-10-13 15:17 | Yes | 3 |  |  | 2018-10-14 10:58 | [5 empty] | 2018-10-14 10:58 | Yes | -13 | 1204-Owner-v | 2018-11-26 11:11
VD-9001-257C-DWG-020 | 2 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-17 | 2018-10-11 16:54 | 2018-10-11 16:54 | Yes | -6 |  |  |  | 2018-12-05 16:12 |  |  |  |  | 2018-12-05 16:12 | Yes | 41
VD-9001-307A-DWG-009 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-27 13:33 | 2018-11-27 13:33 | Yes | 34 |  |  |  | 2018-12-15 14:49 |  |  |  |  | 2018-12-15 19:59 | Yes | 4 | 1204-Owner-v | 2020-04-23 17:54
VD-9001-307A-DWG-001 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-27 13:17 | 2018-11-27 13:24 | Yes | 34 |  |  |  | 2018-12-16 08:39 |  |  |  |  | 2018-12-16 19:59 | Yes | 5 | 1204-Owner-v | 2020-04-23 17:48
VD-9001-307A-DWG-002 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-12 16:13 | 2018-11-16 13:32 | Yes | 19 |  |  |  | 2018-11-21 17:02 |  |  |  |  | 2018-11-21 20:00 | Yes | -5 | 1204-Owner-v | 2018-11-27 11:56
VD-9001-307A-DWG-007 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-27 13:31 | 2018-11-27 13:31 | Yes | 34 |  |  |  | 2018-12-16 08:47 |  |  |  |  | 2018-12-16 19:59 | Yes | 5 | 1204-Owner-v | 2020-04-23 17:53
VD-9001-307A-DWG-005 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-27 13:29 | 2018-11-27 13:30 | Yes | 34 |  |  |  | 2018-12-24 11:36 |  |  |  |  | 2018-12-24 20:00 | Yes | 13 | 1204-Owner-v | 2020-04-23 17:55
VD-9001-307A-DWG-004 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-12 16:14 | 2018-11-12 16:14 | Yes | 19 |  |  |  | 2018-11-21 17:01 |  |  |  |  | 2018-11-21 20:00 | Yes | -5 | 1204-Owner-v | 2018-11-27 12:14
VD-9001-307A-DWG-003 | 2 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-10-24 18:57 | 2018-11-27 13:22 | 2018-11-27 13:24 | Yes | 34 |  |  |  | 2018-12-15 14:44 |  |  |  |  | 2018-12-15 19:59 | Yes | 4 | 1204-Owner-v | 2020-04-23 17:55
VD-9001-204D-DWG-007 | 3 | DRYERS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-13 09:52 | 2018-10-15 11:32 | 2018-10-15 11:36 | Yes | 2 |  |  | 2018-10-29 08:28 | [5 empty] | 2018-10-29 08:28 | Yes | 0 | 1204-Owner-v | 2019-04-06 14:47
VD-9001-204D-DWG-037 | 2 | STEAM DRUM D-2003 / INSULATION SUPPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-13 09:52 | 2018-10-15 11:43 | 2018-10-15 11:44 | Yes | 2 |  |  | 2018-10-29 14:41 | [5 empty] | 2018-10-29 14:41 | Yes | 0 | 1204-Owner-v | 2018-11-05 08:33
VD-9001-257C-WBK-007 | 3 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-20 | 2019-04-02 13:59 | 2019-04-02 14:00 | Yes | 164 |  |  |  | 2019-04-21 10:40 |  |  |  |  | 2019-04-21 10:40 | Yes | 5
VD-9001-257C-WBK-002 | 3 | WELDING BOOK (4137-0365/W) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-20 | 2019-04-02 12:52 | 2019-04-02 12:52 | Yes | 164 |  |  | 2019-04-21 10:35 | [5 empty] | 2019-04-21 10:35 | Yes | 5
VD-9001-251-DSH-022 | 1 | Pressure & Temperature gauge Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-22 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-251-DWG-119 | 1 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:10 | 2018-10-15 11:00 | 2018-10-15 11:25 | Yes | 2 |  |  | 2018-10-21 17:07 | [5 empty] | 2018-10-21 17:07 | Yes | -8
VD-9001-251-DWG-073 | 1 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:10 | 2018-10-15 11:17 | 2018-10-15 11:26 | Yes | 2 |  |  | 2018-10-21 17:08 | [5 empty] | 2018-10-21 17:08 | Yes | -8
VD-9001-251-DWG-065 | 1 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:10 | 2018-10-15 12:23 | 2018-10-15 12:27 | Yes | 2 |  |  | 2018-11-13 11:56 | [5 empty] | 2018-11-13 11:56 | Yes | 15
VD-9001-251-DWG-066 | 1 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:10 | 2018-10-15 11:30 | 2018-10-15 11:40 | Yes | 2 |  |  |  |  | 2018-10-22 15:22 |  |  |  | 2018-10-22 15:22 | Yes | -7
VD-9001-251-DWG-051 | 3 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:11 | 2018-10-15 11:42 | 2018-10-15 12:01 | Yes | 2 |  |  | 2018-10-28 10:15 | [5 empty] | 2018-10-28 10:15 | Yes | -1
VD-9001-251-DWG-052 | 3 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:11 | 2018-10-15 12:04 | 2018-10-15 12:12 | Yes | 2 |  |  | 2018-10-28 10:12 | [5 empty] | 2018-10-28 10:12 | Yes | -1
VD-9001-251-DWG-053 | 1 | MAIN COMBUSTION AIR DUCTS LAYOUT | HM-251 | KT – Kinetics Technology SpA | 2018-10-13 12:11 | 2018-10-15 12:15 | 2018-10-15 12:22 | Yes | 2 |  |  | 2018-10-28 10:09 | [5 empty] | 2018-10-28 10:09 | Yes | -1
VD-9001-251-DSH-021 | 1 | Pressure and Flow Transmitters Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-22 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-251-DWG-054 | 1 | MAIN COMBUSTION AIR DUCTS ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-15 | 2018-10-31 17:37 | 2018-10-31 17:38 | Yes | 16 |  |  |  | 2018-12-11 17:00 |  |  |  |  | 2018-12-11 17:00 | Yes | 27
VD-9001-307A-PCJ-001 | 2 | Painting Procedure | MC-307A | KSB GERMANY | 2018-10-27 18:57 |  |  | No | 601 | [9 empty] | No | 0
VD-9001-231B-ITP-001 | 2 | INSPECTON AND TEST PLAN | PV-231B | Fars Ghaleb | 2018-10-27 18:57 | 2018-10-14 09:45 | 2018-10-14 09:46 | Yes | -13 |  |  |  | 2018-10-27 11:00 |  |  |  |  | 2018-10-27 11:00 | Yes | -1 | 1204-Owner-v | 2020-01-01 12:57
VD-9001-231B-PCJ-002 | 1 | WPS&PQR | PV-231B | Fars Ghaleb | 2018-10-27 18:57 | 2018-10-14 10:50 | 2018-10-14 10:50 | Yes | -13 |  |  | 2018-10-15 11:11 | [5 empty] | 2018-10-15 11:11 | Yes | -13
VD-9001-257B-CAL-004 | 1 | CALCULATION BOOK FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-10-21 | 2018-10-27 12:36 | 2018-10-27 12:36 | Yes | 6 |  |  |  |  | 2018-12-10 16:53 |  |  |  | 2018-12-10 16:53 | Yes | 30
VD-9001-231B-PCJ-003 | 1 | Painting procedure | PV-231B | Fars Ghaleb | 2018-10-16 | 2018-12-31 17:33 | 2018-12-31 17:33 | Yes | 76 |  |  | 2019-01-07 17:04 | [5 empty] | 2019-01-07 20:00 | Yes | -7
VD-9001-257B-CAL-007 | 1 | CALCULATION BOOK FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-10-21 | 2019-01-22 11:56 | 2019-01-22 11:56 | Yes | 93 |  |  | 2019-02-04 16:03 | [5 empty] | 2019-02-04 16:03 | Yes | -1
VD-9001-257B-CAL-016 | 1 | CALCULATION BOOK FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2018-10-21 | 2019-01-17 10:29 | 2019-01-17 10:29 | Yes | 88 |  |  | 2019-02-06 14:36 | [5 empty] | 2019-02-06 14:36 | Yes | 6
VD-9001-204B-DWG-006 | 3 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-10-16 | 2018-10-20 11:37 | 2018-10-20 11:37 | Yes | 4 |  |  |  | 2018-10-20 11:52 |  |  |  |  | 2018-10-20 11:52 | Yes | -14 | 1204-Owner-v | 2018-12-02 09:18
VD-9001-251-LST-002 | 2 | UTILITIES COMSUMPTION LIST | HM-251 | KT – Kinetics Technology SpA | 2018-10-22 |  |  | No | 606 | [9 empty] | No | 0
VD-9001-307A-ITP-011 | 3 | Inspection Test Plan (Turbine) | MC-307A | KSB GERMANY | 2018-10-28 18:58 |  |  | No | 600 | [9 empty] | No | 0
VD-9001-257C-DWG-003 | 2 | NAME PLATE DET.DWG (4137-0364/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 11:52 | 2018-10-15 11:52 | Yes | 0 |  |  | 2018-10-15 17:26 | [5 empty] | 2018-10-15 17:26 | Yes | -14
VD-9001-257C-DWG-005 | 1 | SHIPPING DRAWING (4137-0364/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 12:20 | 2018-10-15 12:20 | Yes | 0 |  |  | 2018-11-04 17:23 | [5 empty] | 2018-11-04 17:23 | Yes | 6 | 1204-Owner-v | 2019-04-22 10:14
VD-9001-257C-DWG-006 | 1 | PAINTING PLAN (4137-0364/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 12:21 | 2018-10-15 12:21 | Yes | 0 |  |  | 2018-11-04 17:25 | [5 empty] | 2018-11-04 17:25 | Yes | 6
VD-9001-257C-DWG-009 | 2 | NAME PLATE DET.DWG (4137-0365/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 12:22 | 2018-10-15 12:22 | Yes | 0 |  |  | 2018-10-15 17:21 | [5 empty] | 2018-10-15 17:21 | Yes | -14
VD-9001-257C-DWG-052 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0364/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 12:20 | 2018-10-15 12:20 | Yes | 0 |  |  | 2018-10-15 17:25 | [5 empty] | 2018-10-15 17:25 | Yes | -14
VD-9001-257C-DWG-053 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0365/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:09 | 2018-10-15 12:23 | 2018-10-15 12:23 | Yes | 0 |  |  | 2018-10-15 17:20 | [5 empty] | 2018-10-15 17:20 | Yes | -14
VD-9001-257C-DWG-054 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0366/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:25 | 2018-10-15 12:25 | Yes | 0 |  |  | 2018-10-15 17:15 | [5 empty] | 2018-10-15 17:15 | Yes | -14
VD-9001-257C-DWG-012 | 1 | PAINTING PLAN (4137-0365/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:23 | 2018-10-15 12:23 | Yes | 0 |  |  | 2018-11-04 16:33 | [5 empty] | 2018-11-04 16:33 | Yes | 6
VD-9001-257C-DWG-017 | 1 | SHIPPING DRAWING (4137-0366/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:30 | 2018-10-15 12:30 | Yes | 0 |  |  | 2018-11-05 10:39 | [5 empty] | 2018-11-05 10:39 | Yes | 7 | 1204-Owner-v | 2019-04-22 10:17
VD-9001-257C-DWG-018 | 1 | PAINTING PLAN (4137-0366/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:30 | 2018-10-15 12:31 | Yes | 0 |  |  | 2018-11-05 10:41 | [5 empty] | 2018-11-05 10:41 | Yes | 7
VD-9001-257C-DWG-055 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0367/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:33 | 2018-10-15 12:33 | Yes | 0 |  |  | 2018-10-15 16:41 | [5 empty] | 2018-10-15 16:41 | Yes | -14
VD-9001-257C-DWG-024 | 1 | PAINTING PLAN (4137-0367/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 12:34 | 2018-10-15 12:34 | Yes | 0 |  |  | 2018-11-10 15:42 | [5 empty] | 2018-11-10 15:42 | Yes | 12
VD-9001-257C-DWG-025 | 2 | DETAILS DRAWING (4137-0368/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 13:15 | 2018-10-15 13:15 | Yes | 0 |  |  | 2018-11-10 17:13 | [5 empty] | 2018-11-10 17:13 | Yes | 12 | 1204-Owner-v | 2019-01-30 14:20
VD-9001-257C-DWG-026 | 2 | DETAILS DRAWING (4137-0368/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:10 | 2018-10-15 13:16 | 2018-10-15 13:16 | Yes | 0 |  |  |  |  | 2018-11-13 09:22 |  |  |  | 2018-11-13 09:22 | Yes | 15
VD-9001-257C-DWG-029 | 1 | SHIPPING DRAWING (4137-0368/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:11 | 2018-10-15 13:17 | 2018-10-15 13:17 | Yes | 0 |  |  | 2018-11-06 16:30 | [5 empty] | 2018-11-06 16:30 | Yes | 8 | 1204-Owner-v | 2019-04-22 10:26
VD-9001-257C-DWG-030 | 1 | PAINTING PLAN (4137-0368/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:11 | 2018-10-15 13:19 | 2018-10-15 13:19 | Yes | 0 |  |  | 2018-11-05 10:43 | [5 empty] | 2018-11-05 10:43 | Yes | 7
VD-9001-257C-DWG-056 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0368/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:11 | 2018-10-15 13:16 | 2018-10-15 13:16 | Yes | 0 |  |  | 2018-10-15 16:35 | [5 empty] | 2018-10-15 16:35 | Yes | -14
VD-9001-257C-DWG-035 | 1 | SHIPPING DRAWING (4137-0369/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:19 | 2018-10-15 13:19 | Yes | 0 |  |  | 2018-11-06 16:34 | [5 empty] | 2018-11-06 16:34 | Yes | 8 | 1204-Owner-v | 2019-04-22 10:28
VD-9001-257C-DWG-036 | 1 | PAINTING PLAN (4137-0369/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:19 | 2018-10-15 13:19 | Yes | 0 |  |  | 2018-11-06 16:32 | [5 empty] | 2018-11-06 16:32 | Yes | 8
VD-9001-257C-DWG-041 | 1 | SHIPPING DRAWING (4137-0370/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:21 | 2018-10-15 13:21 | Yes | 0 |  |  | 2018-11-03 17:04 | [5 empty] | 2018-11-03 17:04 | Yes | 5 | 1204-Owner-v | 2019-04-22 10:30
VD-9001-257C-DWG-042 | 1 | PAINTING PLAN (4137-0370/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:21 | 2018-10-15 13:21 | Yes | 0 |  |  | 2018-11-03 17:02 | [5 empty] | 2018-11-03 17:02 | Yes | 5
VD-9001-257C-DWG-046 | 2 | NAME PLATE DET.DWG (4137-0371/A) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:22 | 2018-10-15 13:22 | Yes | 0 |  |  | 2018-10-15 15:34 | [5 empty] | 2018-10-15 15:34 | Yes | -14
VD-9001-257C-DWG-048 | 1 | SHIPPING DRAWING (4137-0371/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:23 | 2018-10-15 13:23 | Yes | 0 |  |  | 2018-11-01 12:02 | [5 empty] | 2018-11-01 12:02 | Yes | 3 | 1204-Owner-v | 2019-04-22 10:32
VD-9001-257C-DWG-049 | 1 | PAINTING PLAN (4137-0371/V) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:12 | 2018-10-15 13:24 | 2018-10-15 13:24 | Yes | 0 |  |  | 2018-11-01 12:56 | [5 empty] | 2018-11-01 12:56 | Yes | 3
VD-9001-257C-DWG-059 | 2 | BILL OF MATERIAL AND GENERAL NOTES (4137-0371/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-15 11:13 | 2018-10-15 13:23 | 2018-10-15 13:23 | Yes | 0 |  |  | 2018-10-15 15:21 | [5 empty] | 2018-10-15 15:21 | Yes | -14
VD-9001-257B-CAL-019 | 1 | CALCULATION BOOK FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-10-22 | 2019-02-13 10:55 | 2019-02-13 10:55 | Yes | 114 |  |  |  |  | 2019-02-20 17:14 |  |  |  | 2019-02-20 17:14 | Yes | -7
VD-9001-257B-CAL-013 | 1 | CALCULATION BOOK FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2018-10-22 | 2019-01-14 09:16 | 2019-01-14 09:15 | Yes | 84 |  |  |  |  | 2019-02-04 16:58 |  |  |  | 2019-02-04 16:58 | Yes | 7
VD-9001-307A-DSH-023 | 2 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-021 | 3 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-022 | 2 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DIG-002 | 1 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-10-29 18:57 | 2018-11-12 16:00 | 2018-11-12 16:00 | Yes | 14 |  |  |  | 2018-12-11 14:37 |  |  |  |  | 2018-12-11 19:59 | Yes | 15
VD-9001-307A-DSH-025 | 3 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-009 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-010 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-024 | 3 | Turbine Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-002 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-004 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-003 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DSH-001 | 2 | Pump Data Sheet | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-307A-DIG-023 | 2 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2018-10-29 18:57 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-665 | 0 | Heat Exchanger Costruction Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:00 | 2018-10-31 18:00 | Yes | 14 |  |  |  | 2019-01-14 10:40 |  |  |  |  | 2019-01-14 10:40 | Yes | 61 | 1204-Owner-v | 2019-04-06 10:18
VD-9001-251-DWG-666 | 0 | Gearboxes Cross Section Drawing & Assembly Drawing (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:01 | 2018-10-31 18:02 | Yes | 14 |  |  |  | 2018-11-18 14:35 |  |  |  |  | 2018-11-18 14:35 | Yes | 4 | 1204-Owner-v | 2020-02-16 11:37
VD-9001-251-DWG-667 | 0 | Gearboxes Cross Section Drawing & Assembly Drawing (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:03 | 2018-10-31 18:03 | Yes | 14 |  |  |  | 2018-12-23 09:42 |  |  |  |  | 2018-12-23 09:42 | Yes | 39
VD-9001-251-DWG-668 | 0 | Turbines Cross Section Drawing & Assembly Drawing (TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-669 | 0 | Turbines Cross Section Drawing & Assembly Drawing (TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-670 | 0 | Instrument Hook-Up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:03 | 2018-10-31 18:04 | Yes | 14 |  |  |  | 2018-11-22 11:32 |  |  |  |  | 2018-11-22 11:32 | Yes | 8
VD-9001-251-DWG-671 | 0 | Instrument Hook-Up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:03 | 2018-10-31 18:03 | Yes | 14 |  |  |  | 2018-11-22 11:30 |  |  |  |  | 2018-11-22 11:30 | Yes | 8
VD-9001-251-DWG-672 | 0 | Nameplate dwg.(LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-673 | 0 | Terminal Box with termination details dwg. (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-674 | 0 | Electric Motor Dwg. (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-675 | 0 | Nameplate dwg.(LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-676 | 0 | Terminal Box with termination details dwg. (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-677 | 0 | Electric Motor Dwg. (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-678 | 0 | Heavy and Large eqpt. Dwg. (GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-EQL-660 | 0 | Equipment List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:07 | 2018-10-31 18:07 | Yes | 14 |  |  | 2018-12-11 17:06 | [5 empty] | 2018-12-11 17:06 | Yes | 27 | 1204-Owner-v | 2019-03-02 11:32
VD-9001-251-EQL-661 | 0 | Equipment List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:08 | 2018-10-31 18:10 | Yes | 14 |  |  | 2018-12-11 17:07 | [5 empty] | 2018-12-11 17:07 | Yes | 27 | 1204-Owner-v | 2019-03-02 11:32
VD-9001-251-INR-660 | 0 | Quality Record Book (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INR-661 | 0 | Quality Record Book (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-660 | 0 | Mechanical Book Index (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-661 | 0 | Mechanical Book Index (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-662 | 0 | Inspection Book Index (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-663 | 0 | Inspection Book Index (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-ISO-660 | 0 | Piping Interconnecting dwg. (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-ISO-661 | 0 | Piping Interconnecting dwg. (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-ITP-660 | 0 | Test & Inspection Plan (LOS/GB/YTUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:10 | 2018-10-31 18:10 | Yes | 14 |  |  |  | 2018-11-17 15:48 |  |  |  |  | 2018-11-17 15:48 | Yes | 3 | 1204-Owner-v | 2020-01-01 09:34
VD-9001-251-CAL-641 | 0 | Structural Calculation notes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 15:05 | 2018-10-31 15:09 | Yes | 14 |  |  | 2018-11-12 15:43 | [5 empty] | 2018-11-12 15:43 | Yes | -2
VD-9001-251-CAL-642 | 0 | Structural Calculation notes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 15:10 | 2018-10-31 15:12 | Yes | 14 |  |  | 2018-11-12 15:44 | [5 empty] | 2018-11-12 15:44 | Yes | -2
VD-9001-251-DSH-640 | 0 | Thermal Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 15:10 | 2018-10-31 15:11 | Yes | 14 |  |  |  |  | 2019-01-08 10:17 |  |  |  | 2019-01-08 10:17 | Yes | 55
VD-9001-251-DSH-641 | 0 | Thermal Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:11 | 2018-10-31 16:15 | Yes | 14 |  |  |  |  | 2019-01-08 10:18 |  |  |  | 2019-01-08 10:18 | Yes | 55
VD-9001-251-DSH-642 | 0 | Thermal Calculation Resume | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:12 | 2018-10-31 16:16 | Yes | 14 |  |  |  |  | 2019-01-07 11:23 |  |  |  | 2019-01-07 11:23 | Yes | 54
VD-9001-251-DSH-643 | 0 | Thermal Calculation Resume | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:15 | 2018-10-31 16:17 | Yes | 14 |  |  |  |  | 2019-01-07 11:24 |  |  |  | 2019-01-07 11:24 | Yes | 54
VD-9001-251-DSH-644 | 0 | LOADS ON SUPPORT STAND | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:18 | 2018-10-31 16:20 | Yes | 14 |  |  | 2018-11-12 15:59 | [5 empty] | 2018-11-12 15:59 | Yes | -2
VD-9001-251-DSH-645 | 0 | LOADS ON SUPPORT STAND | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:18 | 2018-10-31 16:21 | Yes | 14 |  |  |  | 2018-11-12 16:01 |  |  |  |  | 2018-11-12 16:01 | Yes | -2
VD-9001-251-DSH-646 | 0 | Skin Thermocouple Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:24 | 2018-10-31 16:27 | Yes | 14 |  |  |  |  | 2019-01-05 16:28 |  |  |  | 2019-01-05 16:28 | Yes | 52
VD-9001-251-DWG-640 | 0 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:25 | 2018-10-31 16:26 | Yes | 14 |  |  |  | 2018-11-18 15:04 |  |  |  |  | 2018-11-18 15:04 | Yes | 4 | 1204-Owner-v | 2019-04-06 07:43
VD-9001-251-DWG-641 | 0 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:28 | 2018-10-31 16:32 | Yes | 14 |  |  |  | 2018-11-18 15:06 |  |  |  |  | 2018-11-18 15:06 | Yes | 4 | 1204-Owner-v | 2019-04-06 07:46
VD-9001-251-DWG-642 | 0 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:42 | 2018-10-31 16:48 | Yes | 14 |  |  |  | 2018-11-18 15:08 |  |  |  |  | 2018-11-18 15:08 | Yes | 4 | 1204-Owner-v | 2019-04-06 07:46
VD-9001-251-DWG-643 | 0 | Name Plate drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:44 | 2018-10-31 16:48 | Yes | 14 |  |  |  | 2018-11-18 15:09 |  |  |  |  | 2018-11-18 15:09 | Yes | 4
VD-9001-251-DWG-644 | 0 | Name Plate drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:49 | 2018-10-31 16:52 | Yes | 14 |  |  |  | 2018-11-18 15:10 |  |  |  |  | 2018-11-18 15:10 | Yes | 4
VD-9001-251-MBD-640 | 0 | Mechanical Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MBD-641 | 0 | Mechanical Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MBD-642 | 0 | Inspection Book (incl.test reports, material certificates) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MBD-643 | 0 | Inspection Book (incl.test reports, material certificates) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-645 | 0 | Installation start up and commissioning manuals | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-646 | 0 | Installation start up and commissioning manuals | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PCJ-640 | 0 | Surface preparation Painting Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:49 | 2018-10-31 16:50 | Yes | 14 |  |  |  | 2018-11-17 15:34 |  |  |  |  | 2018-11-17 15:34 | Yes | 3
VD-9001-251-PCJ-641 | 0 | Procedure for erection and installation of equipment | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:58 | 2018-10-31 17:00 | Yes | 14 |  |  | 2018-11-14 10:18 | [5 empty] | 2018-11-14 10:18 | Yes | 0 | 1204-Owner-v | 2019-03-02 11:42
VD-9001-251-PCJ-642 | 0 | Procedure for site assembly, levelling and welding (including WPS for site) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PCJ-643 | 0 | Hydraulic Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:53 | 2018-10-31 16:56 | Yes | 14 |  |  |  | 2018-11-17 15:37 |  |  |  |  | 2018-11-17 15:37 | Yes | 3 | 1204-Owner-v | 2019-04-06 10:30
VD-9001-251-PCJ-644 | 0 | Pneumatic Leak Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 16:57 | 2018-10-31 17:01 | Yes | 14 |  |  |  | 2018-11-17 15:41 |  |  |  |  | 2018-11-17 15:41 | Yes | 3
VD-9001-251-PCJ-645 | 0 | NDT Test Procedure (Dye Penetrant ) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:01 | 2018-10-31 17:01 | Yes | 14 |  |  | 2018-11-17 15:43 | [5 empty] | 2018-11-17 15:43 | Yes | 3
VD-9001-251-PCJ-646 | 0 | NDT Test Procedure (RX Procedure) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:07 | 2018-10-31 17:09 | Yes | 14 |  |  | 2018-11-17 15:44 | [5 empty] | 2018-11-17 15:44 | Yes | 3
VD-9001-251-QCP-640 | 0 | Quality Control Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:06 | 2018-10-31 17:07 | Yes | 14 |  |  |  | 2018-11-17 11:57 |  |  |  |  | 2018-11-17 11:57 | Yes | 3
VD-9001-251-QCP-641 | 0 | Quality Control Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:10 | 2018-10-31 17:13 | Yes | 14 |  |  |  | 2018-11-17 11:58 |  |  |  |  | 2018-11-17 11:58 | Yes | 3
VD-9001-251-QCP-642 | 0 | Site quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-WBK-640 | 0 | Welding Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:19 | 2018-10-31 17:20 | Yes | 14 |  |  |  | 2018-11-12 16:27 |  |  |  |  | 2018-11-12 16:27 | Yes | -2
VD-9001-251-WBK-641 | 0 | Welding Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:18 | 2018-10-31 17:19 | Yes | 14 |  |  |  | 2018-11-12 16:18 |  |  |  |  | 2018-11-12 16:18 | Yes | -2
VD-9001-251-LST-660 | 0 | Lubricant List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:11 | 2018-10-31 18:12 | Yes | 14 |  |  | 2018-11-18 14:13 | [5 empty] | 2018-11-18 14:13 | Yes | 4
VD-9001-251-LST-661 | 0 | Instrument List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:15 | 2018-10-31 18:16 | Yes | 14 |  |  |  | 2018-11-22 11:37 |  |  |  |  | 2018-11-22 11:37 | Yes | 8 | 1204-Owner-v | 2019-03-02 11:39
VD-9001-251-LST-662 | 0 | Instrument List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:16 | 2018-10-31 18:16 | Yes | 14 |  |  |  | 2018-11-22 11:38 |  |  |  |  | 2018-11-22 11:38 | Yes | 8 | 1204-Owner-v | 2019-03-02 11:39
VD-9001-251-LST-663 | 0 | List of Instrument and sistem cable (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-664 | 0 | List of Instrument and sistem cable (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-665 | 0 | List of JB, Cabinets and Panel (LOS/ GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-666 | 0 | List of JB, Cabinets and Panel (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-667 | 0 | List of I/O Signals & Instruments ranges, set point & set of Alarm/Trip (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-668 | 0 | List of I/O Signals & Instruments ranges, set point & set of Alarm/Trip (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-669 | 0 | List of Spare parts for erection, commissioning & start-up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-670 | 0 | List of Spare parts for erection, commissioning & start-up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-671 | 0 | Special Tools List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-672 | 0 | Preliminary Packing List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-673 | 0 | Preliminary Packing List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-674 | 0 | Packing List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-675 | 0 | Packing List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-660 | 0 | Vendor Data Book (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-661 | 0 | Vendor Data Book (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDL-660 | 0 | Document List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:17 | 2018-10-31 18:17 | Yes | 14 |  |  |  | 2018-12-11 17:04 |  |  |  |  | 2018-12-11 17:04 | Yes | 27 | 1204-Owner-v | 2019-04-06 10:09
VD-9001-251-PCU-662 | 0 | Torque vs. Speed/current/power factor curves (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PCU-663 | 0 | Torque vs. Speed/current/power factor curves (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PPL-660 | 0 | Lube Oil System General Arrangement drawing (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:27 | 2018-10-31 18:28 | Yes | 14 |  |  |  | 2018-11-22 11:43 |  |  |  |  | 2018-11-22 11:43 | Yes | 8 | 1204-Owner-v | 2019-04-06 10:34
VD-9001-251-PPL-661 | 0 | Lube Oil System General Arrangement drawing (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:30 | 2018-10-31 18:30 | Yes | 14 |  |  |  | 2018-11-22 11:40 |  |  |  |  | 2018-11-22 11:40 | Yes | 8 | 1204-Owner-v | 2019-04-06 10:35
VD-9001-251-PPL-662 | 0 | Skid Turbine & Gearbox General Arrangement drawing (GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:30 | 2018-10-31 18:30 | Yes | 14 |  |  |  | 2018-11-22 11:45 |  |  |  |  | 2018-11-22 11:45 | Yes | 8 | 1204-Owner-v | 2019-04-06 10:34
VD-9001-251-PPL-663 | 0 | Skid Turbine & Gearbox General Arrangement drawing (GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:32 | 2018-10-31 18:32 | Yes | 14 |  |  |  | 2018-11-22 11:49 |  |  |  |  | 2018-11-22 11:49 | Yes | 8 | 1204-Owner-v | 2019-04-06 10:35
VD-9001-251-UDD-660 | 0 | Utility Consumption List including Electrical Users (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:34 | 2018-10-31 18:34 | Yes | 14 |  |  |  | 2019-01-09 14:24 |  |  |  |  | 2019-01-09 14:24 | Yes | 56
VD-9001-251-UDD-661 | 0 | Utility Consumption List including Electrical Users (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:34 | 2018-10-31 18:34 | Yes | 14 |  |  |  | 2019-01-09 14:21 |  |  |  |  | 2019-01-09 14:21 | Yes | 56
VD-9001-251-WBK-660 | 0 | Welding Book ( Including WMP,WPS,PQR,WPQ) (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 19:03 | 2018-10-31 19:07 | Yes | 14 |  |  |  | 2018-11-17 16:19 |  |  |  |  | 2018-11-17 16:19 | Yes | 3
VD-9001-251-CAL-500 | 0 | MECHANICAL CALCULATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 15:48 | 2018-10-19 15:56 | Yes | 2 |  |  | 2018-10-21 17:30 | [5 empty] | 2018-10-21 17:30 | Yes | -12 | 1204-Owner-v | 2020-02-11 15:39
VD-9001-251-CAL-501 | 0 | Fea Calculations | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 15:58 | 2018-10-19 16:07 | Yes | 2 |  |  | 2018-10-21 17:36 | [5 empty] | 2018-10-21 17:36 | Yes | -12 | 1204-Owner-v | 2019-04-08 07:12
VD-9001-251-DWG-500 | 0 | Drawing Of Complete Reformer Assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:10 | 2018-10-19 16:14 | Yes | 2 |  |  |  | 2018-10-22 11:21 |  |  |  |  | 2018-10-22 11:21 | Yes | -11 | 1204-Owner-v | 2019-04-06 10:15
VD-9001-251-DWG-501 | 0 | Drawing Of Cast Tube Paralloy Item No.01 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:15 | 2018-10-19 16:16 | Yes | 2 |  |  |  | 2018-10-22 11:20 |  |  |  |  | 2018-10-22 11:20 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-502 | 0 | Drawing Of Cast Reducer Paralloy Item No.02 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:17 | 2018-10-19 16:21 | Yes | 2 |  |  |  | 2018-10-22 11:20 |  |  |  |  | 2018-10-22 11:20 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-503 | 0 | Drawing Of Catalyst Grid Paralloy Item No.03 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:22 | 2018-10-19 16:23 | Yes | 2 |  |  |  | 2018-10-22 11:19 |  |  |  |  | 2018-10-22 11:19 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-504 | 0 | Drawing Of RFWN Flange Paralloy Item No.04 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:24 | 2018-10-19 16:27 | Yes | 2 |  |  |  | 2018-10-22 10:58 |  |  |  |  | 2018-10-22 10:58 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-505 | 0 | Drawing Of RF Blind Flange Paralloy Item No. 05 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:29 | 2018-10-19 16:47 | Yes | 2 |  |  |  | 2018-10-22 10:58 |  |  |  |  | 2018-10-22 10:58 | Yes | -11 | 1204-Owner-v | 2019-03-02 11:30
VD-9001-251-DWG-506 | 0 | Drawing Of Weldolet Paralloy Item No.12 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:48 | 2018-10-19 16:54 | Yes | 2 |  |  |  | 2018-10-22 10:57 |  |  |  |  | 2018-10-22 10:57 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-507 | 0 | Drawing Of Outlet Tube Paralloy Item No. 08 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 16:55 | 2018-10-19 16:59 | Yes | 2 |  |  |  | 2018-10-22 10:56 |  |  |  |  | 2018-10-22 10:56 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:17
VD-9001-251-DWG-508 | 0 | Drawing Of Flange Rods Paralloy Item No. 09 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:00 | 2018-10-19 17:03 | Yes | 2 |  |  |  | 2018-10-22 10:55 |  |  |  |  | 2018-10-22 10:55 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-509 | 0 | Drawing Of Spiral Wound Gasket Paralloy Item No.10 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:03 | 2018-10-19 17:08 | Yes | 2 |  |  |  | 2018-10-22 10:54 |  |  |  |  | 2018-10-22 10:54 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-510 | 0 | Drawing Of Blind Flange Can Assembly Paralloy Item No. 11 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:09 | 2018-10-19 17:09 | Yes | 2 |  |  |  | 2018-10-22 10:54 |  |  |  |  | 2018-10-22 10:54 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-511 | 0 | Drawing Of Complete Manifold Assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:10 | 2018-10-19 17:10 | Yes | 2 |  |  |  | 2018-10-22 10:52 |  |  |  |  | 2018-10-22 10:52 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-512 | 0 | Drawing Of Centricast Tube Paralloy Item No.21 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:10 | 2018-10-19 17:11 | Yes | 2 |  |  |  | 2018-10-22 10:48 |  |  |  |  | 2018-10-22 10:48 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-513 | 0 | Drawing Of 4"SCH 80 Tube Paralloy Item No.22 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:11 | 2018-10-19 17:14 | Yes | 2 |  |  |  | 2018-10-22 10:46 |  |  |  |  | 2018-10-22 10:46 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:18
VD-9001-251-DWG-514 | 0 | Drawing Of Static Cast Tee Paralloy Item No.23 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:15 | 2018-10-19 17:15 | Yes | 2 |  |  |  | 2018-10-22 10:45 |  |  |  |  | 2018-10-22 10:45 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-515 | 0 | Drawing Of Static Cast End Cap Paralloy Item No.24 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:16 | 2018-10-19 17:17 | Yes | 2 |  |  |  | 2018-10-22 10:44 |  |  |  |  | 2018-10-22 10:44 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-PID-685 | 0 | Piping & Instrument diagrams | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:54 | 2018-10-30 18:55 | Yes | 13 |  |  |  | 2018-11-18 14:32 |  |  |  |  | 2018-11-18 14:32 | Yes | 5 | 1204-Owner-v | 2019-06-10 10:23
VD-9001-251-CAL-685 | 0 | Lateral critical speed analysis | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAL-686 | 0 | Torsional critical speed analysis | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAL-687 | 0 | Lateral critical speed analysis | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAL-688 | 0 | Torsional critical speed analysis | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAT-685 | 0 | Instrument documentation | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAT-686 | 0 | Instrument documentation | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CER-685 | 0 | Excerpt from Atex Dossier | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CER-686 | 0 | Excerpt from Atex Dossier | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DIG-685 | 0 | Wiring Diagram and Terminal Block | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DIG-686 | 0 | Wiring Diagram and Terminal Block | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-685 | 0 | Noise data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-687 | 0 | Actuator Datasheet and Drawing | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-688 | 0 | Instrument data sheets | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-690 | 0 | Actuator Datasheet and Drawing | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-691 | 0 | Instrument data sheets | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-685 | 0 | Cross sectional and assembly dwgs (with part list) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-686 | 0 | Detailed dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-687 | 0 | Nameplate dwg (including CE Nameplate) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-688 | 0 | Instrument hook-up dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-689 | 0 | Heavy and/or large eqpt dwgs with weight, transp. dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-690 | 0 | Cross sectional and assembly dwgs (with part list) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-691 | 0 | Detailed dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-692 | 0 | Nameplate dwg (including CE Nameplate) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-693 | 0 | Instrument hook-up dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-694 | 0 | Heavy and/or large eqpt dwgs with weight, transp. dwgs | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INR-685 | 0 | Quality Record Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INR-686 | 0 | Quality Record Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-685 | 0 | Mechanical Book Index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-686 | 0 | Inspection Book Index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-ITP-685 | 0 | Fabrication and quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:37 | 2018-10-30 18:40 | Yes | 13 |  |  |  | 2018-11-14 11:18 |  |  |  |  | 2018-11-14 11:18 | Yes | 1 | 1204-Owner-v | 2020-01-01 09:34
VD-9001-251-ITP-686 | 0 | Fabrication and quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:41 | 2018-10-30 18:43 | Yes | 13 |  |  |  | 2018-11-14 10:35 |  |  |  |  | 2018-11-14 10:35 | Yes | 1 | 1204-Owner-v | 2020-01-01 09:34
VD-9001-251-LST-686 | 0 | Completed lubricant charts | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-687 | 0 | List of instr ranges, set points & set of alarms/trips | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-688 | 0 | List of components to be erected/installed on site | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-689 | 0 | List of spare parts for erection, commiss. & start-up | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-690 | 0 | Preliminary packing list | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-691 | 0 | Packing list | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-693 | 0 | List of instr ranges, set points & set of alarms/trips | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-694 | 0 | List of components to be erected/installed on site | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-695 | 0 | List of spare parts for erection, commiss. & start-up | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-696 | 0 | Preliminary packing list | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-697 | 0 | Packing list | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-685 | 0 | Mechanical Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-686 | 0 | Mechanical Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-685 | 0 | Installation, start-up and commissioning manuals | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-686 | 0 | Installation, start-up and commissioning manuals | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-NPL-685 | 0 | NDT Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:46 | 2018-10-30 18:47 | Yes | 13 |  |  |  | 2018-11-14 10:22 |  |  |  |  | 2018-11-14 10:22 | Yes | 1
VD-9001-251-PCJ-685 | 0 | Painting specification | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:47 | 2018-10-30 18:49 | Yes | 13 |  |  |  | 2018-11-14 10:33 |  |  |  |  | 2018-11-14 10:33 | Yes | 1
VD-9001-251-PCJ-686 | 0 | Testing procedures | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:48 | 2018-10-30 18:49 | Yes | 13 |  |  |  | 2018-12-04 15:10 |  |  |  |  | 2018-12-04 15:10 | Yes | 21
VD-9001-251-PCU-685 | 0 | FAN PERFORMANCE CURVES | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:50 |  | No | 611 | [9 empty] | No | 0 | 1204-Owner-v | 2018-11-20 11:40
VD-9001-251-PCU-686 | 0 | FAN PERFORMANCE CURVES | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PPL-685 | 0 | General Arrangement dwg with Foundation Loads Fan Type 80W/A10 - 155 M DWDI | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:57 | 2018-10-30 18:58 | Yes | 13 |  |  |  | 2018-11-12 15:39 |  |  |  |  | 2018-11-12 15:39 | Yes | -1 | 1204-Owner-v | 2019-04-06 10:39
VD-9001-251-DWG-516 | 0 | Drawing Of Weldolets Paralloy Item No.25 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:18 | 2018-10-19 17:19 | Yes | 2 |  |  |  | 2018-10-22 10:44 |  |  |  |  | 2018-10-22 10:44 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-517 | 0 | Drawing Of 1" #6000 Socket Paralloy Item No.26 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:20 | 2018-10-19 17:32 | Yes | 2 |  |  |  | 2018-10-22 10:43 |  |  |  |  | 2018-10-22 10:43 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-518 | 0 | Drawing of End Plate Paralloy Item No.27 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:33 | 2018-10-19 17:40 | Yes | 2 |  |  |  | 2018-10-22 10:42 |  |  |  |  | 2018-10-22 10:42 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-519 | 0 | Drawing Of Thermowell Paralloy Item No. 28 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:40 | 2018-10-19 17:43 | Yes | 2 |  |  |  | 2018-10-22 10:42 |  |  |  |  | 2018-10-22 10:42 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-520 | 0 | Drawing Of Spacer Plates Paralloy Item No 29 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:44 | 2018-10-19 17:44 | Yes | 2 |  |  |  | 2018-10-22 10:40 |  |  |  |  | 2018-10-22 10:40 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:19
VD-9001-251-DWG-521 | 0 | Drawing Of Centrispun Cone Paralloy Item No 30 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:44 | 2018-10-19 17:46 | Yes | 2 |  |  |  | 2018-10-22 10:40 |  |  |  |  | 2018-10-22 10:40 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:20
VD-9001-251-DWG-522 | 0 | Drawing Of Liner Paralloy Item No. 31 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:46 | 2018-10-19 17:48 | Yes | 2 |  |  |  | 2018-10-22 10:38 |  |  |  |  | 2018-10-22 10:38 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:20
VD-9001-251-DWG-523 | 0 | Drawing Of Anchors Paralloy Item No. 32 | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:48 | 2018-10-19 17:51 | Yes | 2 |  |  |  | 2018-10-22 10:37 |  |  |  |  | 2018-10-22 10:37 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:20
VD-9001-251-DWG-524 | 0 | Drawing of outlet cone assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:52 | 2018-10-19 17:55 | Yes | 2 |  |  |  | 2018-10-22 10:35 |  |  |  |  | 2018-10-22 10:35 | Yes | -11 | 1204-Owner-v | 2019-04-09 07:20
VD-9001-251-FAS-500 | 0 | Paralloy Project Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-500 | 0 | Data Book Index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-NPL-531 | 0 | PMI Procedure for Forged Fittings and Olets | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:20 | 2018-10-30 17:21 | Yes | 13 |  |  |  | 2018-11-14 11:11 |  |  |  |  | 2018-11-14 11:11 | Yes | 1
VD-9001-251-NPL-532 | 0 | PMI Procedure for Seamless and Welded Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:22 | 2018-10-30 17:23 | Yes | 13 |  |  |  | 2018-11-14 11:13 |  |  |  |  | 2018-11-14 11:13 | Yes | 1
VD-9001-251-NPL-533 | 0 | PMI Procedure for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:24 | 2018-10-30 17:27 | Yes | 13 |  |  |  | 2018-11-14 10:55 |  |  |  |  | 2018-11-14 10:55 | Yes | 1
VD-9001-251-NPL-534 | 0 | PMI Procedure for Seamless Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:30 | 2018-10-30 17:33 | Yes | 13 |  |  |  | 2018-11-14 10:49 |  |  |  |  | 2018-11-14 10:49 | Yes | 1
VD-9001-251-NPL-535 | 0 | PMI Procedure for Alloy 800HT Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:34 | 2018-10-30 17:35 | Yes | 13 |  |  |  | 2018-11-14 10:51 |  |  |  |  | 2018-11-14 10:51 | Yes | 1
VD-9001-251-NPL-536 | 0 | PMI Procedure for Stainless Steel Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:39 | 2018-10-30 17:39 | Yes | 13 |  |  |  | 2018-11-14 11:14 |  |  |  |  | 2018-11-14 11:14 | Yes | 1
VD-9001-251-NPL-537 | 0 | PMI Procedure for 347H Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:41 | 2018-10-30 17:43 | Yes | 13 |  |  |  | 2018-11-14 10:40 |  |  |  |  | 2018-11-14 10:40 | Yes | 1
VD-9001-251-WPS-530 | 0 | WPS/PQR for Welded Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:46 | 2018-10-30 17:48 | Yes | 13 |  |  |  | 2018-11-17 16:51 |  |  |  |  | 2018-11-17 16:51 | Yes | 4
VD-9001-251-WPS-531 | 0 | WPS/PQR for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:55 | 2018-10-30 18:02 | Yes | 13 |  |  |  | 2018-11-17 16:49 |  |  |  |  | 2018-11-17 16:49 | Yes | 4
VD-9001-251-DSH-590 | 0 | Burner data sheet for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 13:30 | 2018-10-23 13:54 | Yes | 6 |  |  |  | 2018-11-22 11:53 |  |  |  |  | 2018-11-22 11:53 | Yes | 16 | 1204-Owner-v | 2019-03-06 19:16
VD-9001-251-DSH-591 | 0 | Burner data sheet for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 13:57 | 2018-10-23 14:51 | Yes | 6 |  |  |  |  | 2018-11-22 12:02 |  |  |  | 2018-11-22 12:02 | Yes | 16 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-592 | 0 | Burner data sheet for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 14:55 | 2018-10-23 15:05 | Yes | 6 |  |  |  |  | 2018-11-22 11:56 |  |  |  | 2018-11-22 11:56 | Yes | 16 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-593 | 0 | Burner data sheet for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:06 | 2018-10-23 15:10 | Yes | 6 |  |  |  |  | 2018-11-22 11:58 |  |  |  | 2018-11-22 11:58 | Yes | 16 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-594 | 0 | Burner data sheet for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:10 | 2018-10-23 15:13 | Yes | 6 |  |  |  |  | 2018-11-22 12:00 |  |  |  | 2018-11-22 12:00 | Yes | 16 | 1204-Owner-v | 2019-04-15 08:08
VD-9001-251-DSH-595 | 0 | Noise data sheet for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:14 | 2018-10-23 15:21 | Yes | 6 |  |  |  | 2018-11-27 16:42 |  |  |  |  | 2018-11-27 16:42 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-596 | 0 | Noise data sheet for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:21 | 2018-10-23 15:25 | Yes | 6 |  |  |  | 2018-11-27 16:43 |  |  |  |  | 2018-11-27 16:43 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-597 | 0 | Noise data sheet for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:25 | 2018-10-23 15:33 | Yes | 6 |  |  |  | 2018-11-27 16:44 |  |  |  |  | 2018-11-27 16:44 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:13
VD-9001-251-DSH-598 | 0 | Noise data sheet for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:34 | 2018-10-23 15:55 | Yes | 6 |  |  |  | 2018-11-27 16:44 |  |  |  |  | 2018-11-27 16:44 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:14
VD-9001-251-DSH-599 | 0 | Noise data sheet for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 15:55 | 2018-10-23 16:00 | Yes | 6 |  |  |  | 2018-11-27 16:45 |  |  |  |  | 2018-11-27 16:45 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:14
VD-9001-251-DSH-600 | 0 | Amplifier data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:01 | 2018-10-23 16:09 | Yes | 6 |  |  |  | 2018-11-27 16:47 |  |  |  |  | 2018-11-27 16:47 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:12
VD-9001-251-DSH-601 | 0 | UV scanner data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:10 | 2018-10-23 16:18 | Yes | 6 |  |  |  | 2018-11-27 16:48 |  |  |  |  | 2018-11-27 16:48 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:12
VD-9001-251-MDB-501 | 0 | Final Document Books (Upon Completion Of Project) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDL-500 | 0 | VENDOR DELIVERABLE LIST | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 17:56 | 2018-10-19 17:59 | Yes | 2 |  |  |  | 2018-11-03 15:55 |  |  |  |  | 2018-11-03 15:55 | Yes | 1 | 1204-Owner-v | 2019-07-20 17:35
VD-9001-251-NPL-500 | 0 | Dye Penetrant Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 18:01 | 2018-10-19 18:02 | Yes | 2 |  |  |  | 2018-10-27 11:10 |  |  |  |  | 2018-10-27 11:10 | Yes | -6
VD-9001-251-NPL-501 | 0 | RX Procedure For Welds | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-19 18:06 | 2018-10-19 18:10 | Yes | 2 |  |  |  | 2018-10-27 11:11 |  |  |  |  | 2018-10-27 11:11 | Yes | -6
VD-9001-251-NPL-502 | 0 | RX Procedurre For Castings and Forgings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 10:45 | 2018-10-23 10:54 | Yes | 6 |  |  |  | 2018-10-27 17:52 |  |  |  |  | 2018-10-27 17:52 | Yes | -10
VD-9001-251-NPL-503 | 0 | Hydrostatic Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 10:57 | 2018-10-23 11:01 | Yes | 6 |  |  |  | 2018-11-03 16:01 |  |  |  |  | 2018-11-03 16:01 | Yes | -3
VD-9001-251-NPL-504 | 0 | Pneumatic Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 11:04 | 2018-10-23 11:16 | Yes | 6 |  |  |  | 2018-11-03 16:35 |  |  |  |  | 2018-11-03 16:35 | Yes | -3
VD-9001-251-NPL-505 | 0 | PMI Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 11:20 | 2018-10-23 11:38 | Yes | 6 |  |  |  | 2018-11-03 16:37 |  |  |  |  | 2018-11-03 16:37 | Yes | -3
VD-9001-251-NPL-506 | 0 | Radiography NDE Technique Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 11:40 | 2018-10-23 12:03 | Yes | 6 |  |  |  | 2018-11-12 16:05 |  |  |  |  | 2018-11-12 16:05 | Yes | 6
VD-9001-251-NPL-507 | 0 | DYE Pen NDT Technique Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 12:04 | 2018-10-23 12:05 | Yes | 6 |  |  |  | 2018-11-12 16:08 |  |  |  |  | 2018-11-12 16:08 | Yes | 6
VD-9001-251-QCP-500 | 0 | Tube Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-QCP-501 | 0 | Static Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 12:07 | 2018-10-23 12:17 | Yes | 6 |  |  |  | 2018-11-13 14:35 |  |  |  |  | 2018-11-13 14:35 | Yes | 7
VD-9001-251-QCP-502 | 0 | Centrispun Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 12:19 | 2018-10-23 12:31 | Yes | 6 |  |  |  | 2018-11-17 16:14 |  |  |  |  | 2018-11-17 16:14 | Yes | 11
VD-9001-251-QCP-503 | 0 | Fabrication Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 12:35 | 2018-10-23 12:52 | Yes | 6 |  |  |  | 2018-11-13 14:38 |  |  |  |  | 2018-11-13 14:38 | Yes | 7
VD-9001-251-WBK-500 | 0 | Full Welding Dossier (Including Weld Maps,WPS,PQR'S) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 13:21 | 2018-10-23 13:27 | Yes | 6 |  |  |  | 2018-11-13 14:24 |  |  |  |  | 2018-11-13 14:24 | Yes | 7
VD-9001-251-CAL-530 | 0 | Drawings and Calculation Notes for Olets | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:20 | 2018-10-30 16:44 | Yes | 13 |  |  |  | 2019-01-14 10:32 |  |  |  |  | 2019-01-14 10:32 | Yes | 62
VD-9001-251-DWG-530 | 0 | Drawings for Valves | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:27 | 2018-10-30 16:45 | Yes | 13 |  |  |  | 2018-11-03 16:41 |  |  |  |  | 2018-11-03 16:41 | Yes | -10 | 1204-Owner-v | 2019-04-09 07:21
VD-9001-251-INR-530 | 0 | Inspection Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-530 | 0 | Mechanical Book Index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-531 | 0 | Inspection Book Index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-ITP-530 | 0 | Fabrication and Quality Control Plan for Low Alloy Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:36 | 2018-10-30 16:50 | Yes | 13 |  |  |  | 2018-11-17 16:46 |  |  |  |  | 2018-11-17 16:46 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:31
VD-9001-251-ITP-531 | 0 | Fabrication and Quality Control Plan for Forged Fittings and Olets | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:44 | 2018-10-30 16:50 | Yes | 13 |  |  |  | 2018-11-14 11:09 |  |  |  |  | 2018-11-14 11:09 | Yes | 1 | 1204-Owner-v | 2020-01-01 09:34
VD-9001-251-ITP-532 | 0 | Fabrication and Quality Control Plan for Seamless and Welded Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:53 | 2018-10-30 16:57 | Yes | 13 |  |  |  | 2018-11-17 16:00 |  |  |  |  | 2018-11-17 16:00 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:31
VD-9001-251-ITP-533 | 0 | Fabrication and Quality Control Plan for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 16:56 | 2018-10-30 17:00 | Yes | 13 |  |  |  | 2018-11-17 16:02 |  |  |  |  | 2018-11-17 16:02 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:31
VD-9001-251-ITP-534 | 0 | Fabrication and Quality Control Plan for Seamless Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:01 | 2018-10-30 17:02 | Yes | 13 |  |  |  | 2018-11-17 16:05 |  |  |  |  | 2018-11-17 16:05 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:31
VD-9001-251-ITP-535 | 0 | Fabrication and Quality Control Plan for Alloy 800HT Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:01 | 2018-10-30 17:02 | Yes | 13 |  |  |  | 2018-11-17 16:09 |  |  |  |  | 2018-11-17 16:09 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:30
VD-9001-251-ITP-536 | 0 | Fabrication and Quality Control Plan for Stainless Steel Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:03 | 2018-10-30 17:05 | Yes | 13 |  |  |  | 2018-11-17 11:46 |  |  |  |  | 2018-11-17 11:47 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:30
VD-9001-251-ITP-537 | 0 | Fabrication and Quality Control Plan for 347H Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:07 | 2018-10-30 17:11 | Yes | 13 |  |  |  | 2018-11-17 11:51 |  |  |  |  | 2018-11-17 11:51 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:30
VD-9001-251-ITP-538 | 0 | Fabrication and Quality Control Plan for Stock Piping | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:12 | 2018-10-30 17:13 | Yes | 13 |  |  |  | 2018-11-17 11:54 |  |  |  |  | 2018-11-17 11:54 | Yes | 4 | 1204-Owner-v | 2020-01-01 09:23
VD-9001-251-ITP-539 | 0 | Fabrication and Quality Control Plan for Valves | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDB-530 | 0 | Mechanical Book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-NPL-530 | 0 | PMI Procedure for Low Alloy Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 17:18 | 2018-10-30 17:19 | Yes | 13 |  |  |  | 2018-11-14 11:05 |  |  |  |  | 2018-11-14 11:05 | Yes | 1
VD-9001-251-DSH-602 | 0 | Ionization cable data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:19 | 2018-10-23 16:29 | Yes | 6 |  |  |  | 2018-12-08 16:44 |  |  |  |  | 2018-12-08 16:44 | Yes | 32 | 1204-Owner-v | 2019-04-15 08:12
VD-9001-251-DSH-603 | 0 | Flame scanner cable data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:30 | 2018-10-23 16:32 | Yes | 6 |  |  |  | 2018-12-08 16:44 |  |  |  |  | 2018-12-08 16:44 | Yes | 32 | 1204-Owner-v | 2019-04-15 08:12
VD-9001-251-DSH-604 | 0 | Portable igniter data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:33 | 2018-10-23 16:38 | Yes | 6 |  |  |  | 2018-11-27 16:41 |  |  |  |  | 2018-11-27 16:41 | Yes | 21 | 1204-Owner-v | 2019-04-15 08:12
VD-9001-251-DWG-590 | 0 | General arrangement drawing for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:39 | 2018-10-23 16:42 | Yes | 6 |  |  |  | 2018-10-27 14:57 |  |  |  |  | 2018-10-27 14:57 | Yes | -10 | 1204-Owner-v | 2019-03-02 11:32
VD-9001-251-DWG-591 | 0 | General arrangement drawing for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:43 | 2018-10-23 16:47 | Yes | 6 |  |  |  | 2018-10-27 14:59 |  |  |  |  | 2018-10-27 14:59 | Yes | -10
VD-9001-251-DWG-592 | 0 | General arrangement drawing for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:48 | 2018-10-23 16:55 | Yes | 6 |  |  |  | 2018-10-27 16:06 |  |  |  |  | 2018-10-27 16:06 | Yes | -10
VD-9001-251-DWG-593 | 0 | General arrangement drawing for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 16:56 | 2018-10-23 17:02 | Yes | 6 |  |  |  | 2018-10-27 16:07 |  |  |  |  | 2018-10-27 16:07 | Yes | -10
VD-9001-251-DWG-594 | 0 | General arrangement drawing for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:03 | 2018-10-23 17:09 | Yes | 6 |  |  |  | 2018-10-27 16:07 |  |  |  |  | 2018-10-27 16:07 | Yes | -10
VD-9001-251-DWG-595 | 0 | Pilot assembly for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:10 | 2018-10-23 17:15 | Yes | 6 |  |  |  | 2018-10-27 16:08 |  |  |  |  | 2018-10-27 16:08 | Yes | -10
VD-9001-251-DWG-596 | 0 | Nameplate drawing | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:16 | 2018-10-23 17:16 | Yes | 6 |  |  |  | 2018-10-27 16:09 |  |  |  |  | 2018-10-27 16:09 | Yes | -10
VD-9001-251-PPL-686 | 0 | General Arrangement dwg with Foundation Loads Fan Type 80W/A10 - 190 M DWDI | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:58 | 2018-10-30 18:58 | Yes | 13 |  |  |  | 2018-11-12 15:39 |  |  |  |  | 2018-11-12 15:39 | Yes | -1 | 1204-Owner-v | 2019-04-06 10:40
VD-9001-251-SPE-685 | 0 | Insulation specification | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-SPE-686 | 0 | Insulation specification | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-SVL-685 | 0 | SUB VENDOR LIST | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-30 18:56 | 2018-10-30 18:59 | Yes | 13 |  |  |  | 2018-11-03 15:43 |  |  |  |  | 2018-11-03 15:43 | Yes | -10 | 1204-Owner-v | 2019-02-05 11:01
VD-9001-251-UDD-685 | 0 | Utility balance | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-UDD-686 | 0 | Utility balance | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-WPS-685 | 0 | Welding book (including WKF, WPS, PQR, WQR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-WPS-686 | 0 | Welding book (including WKF, WPS, PQR, WQR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-CAL-660 | 0 | Lateral Critical speed data | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:28 | 2018-10-31 17:31 | Yes | 14 |  |  |  | 2018-11-13 14:32 |  |  |  |  | 2018-11-13 14:32 | Yes | -1
VD-9001-251-CAL-661 | 0 | Lateral Critical speed analysis (TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:28 | 2018-10-31 17:31 | Yes | 14 |  |  |  | 2018-11-13 14:29 |  |  |  |  | 2018-11-13 14:29 | Yes | -1
VD-9001-251-DIG-660 | 0 | Wiring Diagram & Terminal Block (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:30 | 2018-10-31 17:32 | Yes | 14 |  |  |  | 2018-11-12 16:14 |  |  |  |  | 2018-11-12 16:14 | Yes | -2
VD-9001-251-DWG-597 | 0 | EWD and layout for ionization panel | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:18 | 2018-10-23 17:24 | Yes | 6 |  |  |  | 2018-10-27 16:35 |  |  |  |  | 2018-10-27 16:35 | Yes | -10
VD-9001-251-DWG-598 | 0 | EWD and layout for UV scanner panel | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:26 | 2018-10-23 17:42 | Yes | 6 |  |  |  | 2018-10-27 16:37 |  |  |  |  | 2018-10-27 16:37 | Yes | -10
VD-9001-251-INR-590 | 0 | Inspection book for ARCH burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INR-591 | 0 | Inspection book for TUNNEL burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INR-592 | 0 | Inspection book for SSH burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-590 | 0 | Inspection book index for ARCH burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-591 | 0 | Inspection book index for TUNNEL burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-INX-592 | 0 | Inspection book index for SSH burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-LST-590 | 0 | Commissionign spare parts list | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:45 | 2018-10-23 17:53 | Yes | 6 |  |  |  | 2018-10-27 16:10 |  |  |  |  | 2018-10-27 16:10 | Yes | -10 | 1204-Owner-v | 2019-02-16 10:31
VD-9001-251-MDB-590 | 0 | Mechanical book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MDX-590 | 0 | Mechanical book index | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-660 | 0 | Installation, start up and commissioning manual Operation and Maintenance Manual (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-MNL-661 | 0 | Installation, start up and commissioning manual Operation and Maintenance Manual (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-NPL-660 | 0 | NDT Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:19 | 2018-10-31 18:20 | Yes | 14 |  |  |  | 2018-11-17 15:50 |  |  |  |  | 2018-11-17 15:50 | Yes | 3
VD-9001-251-PCJ-660 | 0 | Painting Procedure Only for Info (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:19 | 2018-10-31 18:20 | Yes | 14 |  |  | 2018-11-18 14:57 | [5 empty] | 2018-11-18 14:57 | Yes | 4
VD-9001-251-PCJ-661 | 0 | Control Narrative (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PCJ-662 | 0 | Control Narrative (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-PCJ-663 | 0 | Testing Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:20 | 2018-10-31 18:20 | Yes | 14 |  |  |  | 2018-11-14 11:22 |  |  |  |  | 2018-11-14 11:22 | Yes | 0
VD-9001-251-PCJ-664 | 0 | Testing Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:23 | 2018-10-31 18:24 | Yes | 14 |  |  | 2018-11-17 15:53 | [5 empty] | 2018-11-17 15:53 | Yes | 3
VD-9001-251-MNL-590 | 0 | IOMI for burners | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-NPL-590 | 0 | Leak test procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 17:54 | 2018-10-23 18:01 | Yes | 6 |  |  |  | 2018-11-13 14:42 |  |  |  |  | 2018-11-13 14:42 | Yes | 7
VD-9001-251-NPL-591 | 0 | Dye penetrant test procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:02 | 2018-10-23 18:12 | Yes | 6 |  |  |  | 2018-11-03 15:48 |  |  |  |  | 2018-11-03 15:48 | Yes | -3
VD-9001-251-NPL-592 | 0 | PMI procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:15 | 2018-10-23 18:22 | Yes | 6 |  |  |  | 2018-11-03 15:52 |  |  |  |  | 2018-11-03 15:52 | Yes | -3
VD-9001-251-PCJ-590 | 0 | Paint procedure | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:23 | 2018-10-23 18:26 | Yes | 6 |  |  |  | 2018-11-03 15:58 |  |  |  |  | 2018-11-03 15:58 | Yes | -3
VD-9001-251-PCU-590 | 0 | Performance curves for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:26 | 2018-10-23 18:29 | Yes | 6 |  |  |  |  | 2018-11-22 12:11 |  |  |  | 2018-11-22 12:11 | Yes | 16
VD-9001-251-PCU-591 | 0 | Performance curves for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:30 | 2018-10-23 18:35 | Yes | 6 |  |  |  |  | 2018-11-22 12:05 |  |  |  | 2018-11-22 12:05 | Yes | 16
VD-9001-251-PCU-592 | 0 | Performance curves for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-23 18:36 | 2018-10-23 18:36 | Yes | 6 |  |  |  |  | 2018-11-22 12:09 |  |  |  | 2018-11-22 12:09 | Yes | 16
VD-9001-251-PCU-593 | 0 | Performance curves for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-24 10:19 | 2018-10-24 10:30 | Yes | 7 |  |  |  |  | 2018-11-22 12:14 |  |  |  | 2018-11-22 12:14 | Yes | 15
VD-9001-251-PCU-594 | 0 | Performance curves for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-24 10:31 | 2018-10-24 10:36 | Yes | 7 |  |  |  |  | 2018-11-22 12:15 |  |  |  | 2018-11-22 12:16 | Yes | 15
VD-9001-251-QCP-590 | 0 | Quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-24 10:37 | 2018-10-24 10:41 | Yes | 7 |  |  |  | 2018-10-27 17:30 |  |  |  |  | 2018-10-27 17:30 | Yes | -11
VD-9001-251-WBS-590 | 0 | Welding book | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-24 10:46 | 2018-10-24 10:48 | Yes | 7 |  |  |  | 2018-10-28 09:06 |  |  |  |  | 2018-10-28 09:06 | Yes | -10
VD-9001-251-DSH-669 | 0 | Instruments Data Sheet Including Control/Safety valves data sheet (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:51 | 2018-10-31 17:51 | Yes | 14 |  |  |  |  | 2019-01-19 10:16 |  |  |  | 2019-01-19 10:16 | Yes | 66 | 1204-Owner-v | 2019-06-10 10:09
VD-9001-251-DSH-670 | 0 | Instruments Data Sheet Including Control/Safety valves data sheet (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:54 | 2018-10-31 17:56 | Yes | 14 |  |  |  |  | 2019-01-19 10:59 |  |  |  | 2019-01-19 10:59 | Yes | 66 | 1204-Owner-v | 2019-06-10 10:09
VD-9001-251-DSH-671 | 0 | Electric Motor Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-672 | 0 | Electric Motor Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-660 | 0 | Filter Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:55 | 2018-10-31 17:57 | Yes | 14 |  |  |  | 2019-01-14 10:42 |  |  |  |  | 2019-01-14 10:42 | Yes | 61
VD-9001-251-DWG-661 | 0 | Filter Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:55 | 2018-10-31 17:57 | Yes | 14 |  |  |  | 2018-12-04 15:12 |  |  |  |  | 2018-12-04 15:12 | Yes | 20
VD-9001-251-DWG-662 | 0 | Pump Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-663 | 0 | Pump Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DWG-664 | 0 | Heat Exchanger Costruction Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 18:00 | 2018-10-31 18:00 | Yes | 14 |  |  |  | 2019-02-20 17:32 |  |  |  |  | 2019-02-20 17:32 | Yes | 98 | 1204-Owner-v | 2019-04-06 10:17
VD-9001-251-DIG-661 | 0 | Wiring Diagram & Terminal Block (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:35 | 2018-10-31 17:41 | Yes | 14 |  |  |  | 2018-11-12 16:13 |  |  |  |  | 2018-11-12 16:13 | Yes | -2
VD-9001-251-DSH-660 | 0 | Noise Data Sheet (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 |  |  | No | 611 | [9 empty] | No | 0
VD-9001-251-DSH-661 | 0 | Lube Oil System Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:35 | 2018-10-31 17:42 | Yes | 14 |  |  |  | 2018-11-13 12:04 |  |  |  |  | 2018-11-13 12:04 | Yes | -1
VD-9001-251-DSH-662 | 0 | Lube Oil System Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:35 | 2018-10-31 17:42 | Yes | 14 |  |  |  | 2018-11-13 12:05 |  |  |  |  | 2018-11-13 12:05 | Yes | -1
VD-9001-251-DSH-665 | 0 | Gearbox Data Sheet (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:46 | 2018-10-31 17:47 | Yes | 14 |  |  |  | 2018-11-13 14:15 |  |  |  |  | 2018-11-13 14:15 | Yes | -1 | 1204-Owner-v | 2019-08-15 14:26
VD-9001-251-DSH-666 | 0 | Gearbox Data Sheet (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-10-17 | 2018-10-31 17:47 | 2018-10-31 17:47 | Yes | 14 |  |  |  | 2018-11-13 11:48 |  |  |  |  | 2018-11-13 11:48 | Yes | -1 | 1204-Owner-v | 2018-11-20 11:14
VD-9001-254-ISO-526 | 1 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER6) | HM-254 | AZAR AB | 2018-10-22 | 2018-12-09 08:58 | 2018-12-09 08:58 | Yes | 48 |  |  |  | 2018-12-26 09:18 |  |  |  |  | 2018-12-26 09:18 | Yes | 3
VD-9001-254-ISO-525 | 1 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER 5) | HM-254 | AZAR AB | 2018-10-22 | 2018-12-09 08:59 | 2018-12-09 08:59 | Yes | 48 |  |  |  | 2018-12-26 09:20 |  |  |  |  | 2018-12-26 09:20 | Yes | 3
VD-9001-254-ISO-515 | 2 | BOILER FEED WATER LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2018-10-23 | 2019-05-11 14:29 | 2019-05-11 14:29 | Yes | 200 |  |  | 2019-05-14 11:08 | [5 empty] | 2019-05-14 11:08 | Yes | -11 | 1204-Owner-v | 2019-05-23 08:29
VD-9001-254-ISO-516 | 2 | BOILER FEED WATER LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2018-10-23 | 2019-05-11 14:30 | 2019-05-11 14:32 | Yes | 200 |  |  | 2019-05-14 11:10 | [5 empty] | 2019-05-14 11:10 | Yes | -11 | 1204-Owner-v | 2019-05-23 08:29
VD-9001-254-DWH-548 | 4 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2018-10-17 17:04 | 2018-10-20 09:06 | 2018-10-20 09:07 | Yes | 3 |  |  |  | 2018-11-14 10:05 |  |  |  |  | 2018-11-14 10:05 | Yes | 11
VD-9001-201B-DWG-001 | 3 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2018-10-31 | 2018-11-26 11:40 | 2018-11-26 11:42 | Yes | 26 |  |  |  | 2019-01-02 18:10 |  |  |  |  | 2019-01-02 20:00 | Yes | 23
VD-9001-251-PPL-001 | 3 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 13:40 | 2018-10-18 13:44 | Yes | 0 |  |  | 2018-12-11 16:56 | [5 empty] | 2018-12-11 16:56 | Yes | 40 | 1204-Owner-v | 2019-03-28 08:58
VD-9001-251-PPL-002 | 3 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 13:45 | 2018-10-18 13:51 | Yes | 0 |  |  | 2018-12-11 16:58 | [5 empty] | 2018-12-11 16:58 | Yes | 40
VD-9001-251-PPL-003 | 3 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 13:52 | 2018-10-18 13:59 | Yes | 0 |  |  | 2018-10-22 14:21 | [5 empty] | 2018-10-22 14:21 | Yes | -10
VD-9001-251-PPL-004 | 2 | REFORMER GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 13:59 | 2018-10-18 15:00 | Yes | 0 |  |  | 2018-10-22 14:22 | [5 empty] | 2018-10-22 14:22 | Yes | -10 | 1204-Owner-v | 2019-03-28 08:58
VD-9001-251-PPL-005 | 2 | REFORMER GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 15:02 | 2018-10-18 15:02 | Yes | 0 |  |  | 2018-10-22 14:23 | [5 empty] | 2018-10-22 14:23 | Yes | -10 | 1204-Owner-v | 2019-04-06 10:51
VD-9001-251-PPL-006 | 2 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 15:03 | 2018-10-18 15:05 | Yes | 0 |  |  | 2018-10-22 14:24 | [5 empty] | 2018-10-22 14:24 | Yes | -10
VD-9001-251-PPL-007 | 2 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:42 | 2018-10-18 15:05 | 2018-10-18 15:15 | Yes | 0 |  |  | 2018-10-22 14:25 | [5 empty] | 2018-10-22 14:25 | Yes | -10
VD-9001-251-PPL-008 | 2 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:43 | 2018-10-18 15:17 | 2018-10-18 15:25 | Yes | 0 |  |  | 2018-10-22 14:25 | [5 empty] | 2018-10-22 14:25 | Yes | -10
VD-9001-251-PPL-009 | 2 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:43 | 2018-10-18 15:25 | 2018-10-18 15:29 | Yes | 0 |  |  | 2018-10-22 14:26 | [5 empty] | 2018-10-22 14:26 | Yes | -10
VD-9001-251-PPL-010 | 2 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:43 | 2018-10-18 15:29 | 2018-10-18 15:30 | Yes | 0 |  |  | 2018-10-22 14:26 | [5 empty] | 2018-10-22 14:26 | Yes | -10
VD-9001-251-SDG-004 | 3 | STRUCTURAL STEEL STANDARDS FOR EXPANSION JOINTS | HM-251 | KT – Kinetics Technology SpA | 2018-10-18 12:43 | 2018-10-18 13:38 | 2018-10-18 13:39 | Yes | 0 |  |  | 2018-10-27 16:18 | [5 empty] | 2018-10-27 16:18 | Yes | -5 | 1204-Owner-v | 2019-02-14 10:25
VD-9001-231B-DWG-008 | 2 | Ladder and platform drawing FOR SATURATOR COLUMN T-4001 | PV-231B | Fars Ghaleb | 2018-10-23 | 2018-10-24 12:32 | 2018-10-24 12:32 | Yes | 1 |  |  |  | 2018-10-29 09:45 |  |  |  |  | 2018-10-29 09:45 | Yes | -9
VD-9001-401A-DWG-001 | 1 | DRAWINGS | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-11-03 09:24 | 2018-10-23 11:59 | 2018-10-23 12:00 | Yes | -11 |  |  |  | 2018-10-23 16:12 |  |  |  |  | 2018-10-23 16:13 | Yes | -14
VD-9001-204B-DWG-007 | 5 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2018-10-23 | 2018-10-22 09:49 | 2018-10-22 09:50 | Yes | -1 |  |  | 2018-10-22 10:55 | [5 empty] | 2018-10-22 10:55 | Yes | -14 | 1204-Owner-v | 2018-12-02 09:48
VD-9001-251-DWG-055 | 1 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:25 | 2018-10-24 12:05 | 2018-10-24 12:09 | Yes | 4 |  |  | 2018-10-28 10:16 | [5 empty] | 2018-10-28 10:16 | Yes | -10
VD-9001-251-DWG-056 | 1 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:25 | 2018-10-24 12:10 | 2018-10-24 12:11 | Yes | 4 |  |  | 2018-10-27 17:41 | [5 empty] | 2018-10-27 17:41 | Yes | -11
VD-9001-251-DWG-059 | 1 | COLD AIR - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 12:16 | 2018-10-24 12:16 | Yes | 4 |  |  | 2018-10-27 17:17 | [5 empty] | 2018-10-27 17:18 | Yes | -11
VD-9001-251-DWG-060 | 1 | COLD AIR - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 12:14 | 2018-10-24 12:20 | Yes | 4 |  |  | 2018-10-28 09:56 | [5 empty] | 2018-10-28 09:56 | Yes | -10
VD-9001-251-DWG-061 | 1 | FLUE GAS DUCTS - Convection - APH | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 12:17 | 2018-10-24 12:21 | Yes | 4 |  |  | 2018-10-28 10:07 | [5 empty] | 2018-10-28 10:07 | Yes | -10
VD-9001-251-DWG-062 | 1 | FLUE GAS DUCTS - APH to FAN - PLAN | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 12:22 | 2018-10-24 12:26 | Yes | 4 |  |  | 2018-10-28 10:05 | [5 empty] | 2018-10-28 10:05 | Yes | -10
VD-9001-251-DWG-063 | 1 | FLUE GAS DUCTS - APH to FAN - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 13:00 | 2018-10-24 13:04 | Yes | 4 |  |  | 2018-10-28 10:04 | [5 empty] | 2018-10-28 10:04 | Yes | -10
VD-9001-251-DWG-064 | 1 | FLUE GAS DUCTS - FAN to STACK | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-24 13:05 | 2018-10-24 13:07 | Yes | 4 |  |  | 2018-10-28 10:02 | [5 empty] | 2018-10-28 10:02 | Yes | -10 | 1204-Owner-v | 2019-07-23 09:43
VD-9001-251-DWG-042 | 4 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:26 | 2018-10-23 10:59 | 2018-10-23 11:03 | Yes | 3 |  |  | 2018-10-27 16:46 | [5 empty] | 2018-10-27 16:46 | Yes | -10
VD-9001-251-DWG-110 | 3 | plan and platforms – convection details | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:27 | 2018-10-24 13:17 | 2019-04-13 10:21 | Yes | 175 |  |  | 2019-04-27 16:04 | [5 empty] | 2019-04-27 16:04 | Yes | 171 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-127 | 1 | FAN AND FROM FAN TO STACK - DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-20 10:27 | 2018-10-24 13:11 | 2018-10-24 13:16 | Yes | 4 |  |  | 2018-10-27 17:46 | [5 empty] | 2018-10-27 17:46 | Yes | -11
VD-9001-204B-DWG-006 | 4 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-10-21 | 2018-10-20 15:04 | 2018-10-20 15:03 | Yes | -1 |  |  | 2018-10-20 15:16 | [5 empty] | 2018-10-20 15:16 | Yes | -14 | 1204-Owner-v | 2018-11-05 09:21
VD-9001-251-DWG-524 | 1 | Drawing of outlet cone assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-523 | 1 | Drawing Of Anchors Paralloy Item No. 32 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-522 | 1 | Drawing Of Liner Paralloy Item No. 31 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-521 | 1 | Drawing Of Centrispun Cone Paralloy Item No 30 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-520 | 1 | Drawing Of Spacer Plates Paralloy Item No 29 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-519 | 1 | Drawing Of Thermowell Paralloy Item No. 28 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-518 | 1 | Drawing of End Plate Paralloy Item No.27 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-517 | 1 | Drawing Of 1" #6000 Socket Paralloy Item No.26 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-516 | 1 | Drawing Of Weldolets Paralloy Item No.25 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-515 | 1 | Drawing Of Static Cast End Cap Paralloy Item No.24 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-514 | 1 | Drawing Of Static Cast Tee Paralloy Item No.23 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-513 | 1 | Drawing Of 4"SCH 80 Tube Paralloy Item No.22 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-512 | 1 | Drawing Of Centricast Tube Paralloy Item No.21 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-511 | 1 | Drawing Of Complete Manifold Assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-510 | 1 | Drawing Of Blind Flange Can Assembly Paralloy Item No. 11 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-509 | 1 | Drawing Of Spiral Wound Gasket Paralloy Item No.10 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-508 | 1 | Drawing Of Flange Rods Paralloy Item No. 09 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-507 | 1 | Drawing Of Outlet Tube Paralloy Item No. 08 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-506 | 1 | Drawing Of Weldolet Paralloy Item No.12 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-505 | 1 | Drawing Of RF Blind Flange Paralloy Item No. 05 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-504 | 1 | Drawing Of RFWN Flange Paralloy Item No.04 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-503 | 1 | Drawing Of Catalyst Grid Paralloy Item No.03 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-502 | 1 | Drawing Of Cast Reducer Paralloy Item No.02 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-501 | 1 | Drawing Of Cast Tube Paralloy Item No.01 | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-251-DWG-500 | 1 | Drawing Of Complete Reformer Assembly | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 |  |  | No | 599 | [9 empty] | No | 0
VD-9001-254-DSH-151 | 4 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2018-10-27 | 2018-10-24 10:45 | 2018-10-24 10:45 | Yes | -3 |  |  |  | 2018-12-23 09:50 |  |  |  |  | 2018-12-23 09:50 | Yes | 46 | 1204-Owner-v | 2018-12-02 09:22
VD-9001-254-LST-554 | 2 | PIPE LINE LIST | HM-254 | AZAR AB | 2018-10-27 |  |  | No | 601 | [9 empty] | No | 0
VD-9001-254-DWG-330 | 3 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2018-10-27 | 2019-01-27 09:12 | 2019-01-27 09:12 | Yes | 92 |  |  |  | 2019-02-13 15:20 |  |  |  |  | 2019-02-13 15:20 | Yes | 3
VD-9001-254-LST-220 | 3 | WIRING LIST AND CABLE ROUTH ( POWER ) | HM-254 | AZAR AB | 2018-10-27 | 2018-12-22 13:46 | 2018-12-22 13:46 | Yes | 56 |  |  |  | 2019-02-05 14:28 |  |  |  |  | 2019-02-05 14:28 | Yes | 31 | 1204-Owner-v | 2020-04-27 19:39
VD-9001-254-LST-555 | 3 | VALVE LIST | HM-254 | AZAR AB | 2018-10-27 | 2018-12-23 15:52 | 2018-12-23 15:52 | Yes | 57 |  |  | 2019-01-12 10:27 | [5 empty] | 2019-01-12 10:27 | Yes | 6
VD-9001-257B-DWG-023 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-10-29 | 2018-11-24 09:39 | 2018-11-24 09:39 | Yes | 26 |  |  |  |  | 2019-01-15 16:11 |  |  |  | 2019-01-15 16:11 | Yes | 38 | 1204-Owner-v | 2019-01-05 12:39
VD-9001-257B-DWG-024 | 1 | BUNDLE DETAIL FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-10-29 | 2018-11-24 09:40 | 2018-11-24 09:52 | Yes | 26 |  |  |  |  | 2018-12-17 10:52 |  |  |  | 2018-12-17 10:52 | Yes | 9
VD-9001-251-DWG-066 | 2 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2018-10-29 | 2019-04-13 10:26 | 2019-04-13 10:26 | Yes | 166 |  |  |  | 2019-04-27 16:59 |  |  |  |  | 2019-04-27 16:59 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:57
VD-9001-201B-GAD-001 | 3 | GENERAL ARRANGEMENT (4134/0359) | PV-201B | Brembana & Rolle S.p.A. | 2018-11-05 18:57 | 2019-01-23 13:01 | 2019-01-23 13:01 | Yes | 79 |  |  |  | 2019-02-06 17:33 |  |  |  |  | 2019-02-06 19:59 | Yes | 0 | 1204-Owner-v | 2019-01-27 16:40
VD-9001-257B-DWG-020 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-10-30 | 2018-12-09 09:55 | 2018-12-09 09:55 | Yes | 40 |  |  |  |  | 2018-12-24 15:19 |  |  |  | 2018-12-24 15:19 | Yes | 1 | 1204-Owner-v | 2019-01-05 12:39
VD-9001-257B-DWG-021 | 1 | BUNDLE DETAIL FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-10-30 | 2018-12-09 09:56 | 2018-12-09 09:56 | Yes | 40 |  |  |  |  | 2018-12-18 11:58 |  |  |  | 2018-12-18 11:58 | Yes | -5
VD-9001-257B-DWG-005 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-10-30 | 2019-01-22 11:58 | 2019-01-22 11:58 | Yes | 84 |  |  |  | 2019-02-20 17:24 |  |  |  |  | 2019-02-20 17:24 | Yes | 15
VD-9001-257B-DWG-006 | 1 | BUNDLE DETAIL FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2018-10-30 | 2019-01-22 12:01 | 2019-01-22 12:01 | Yes | 84 |  |  | 2019-02-02 16:34 | [5 empty] | 2019-02-02 16:34 | Yes | -3
VD-9001-401A-DWG-001 | 2 | DRAWINGS | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-11-06 16:13 | 2018-10-30 17:21 | 2018-10-30 17:22 | Yes | -7 |  |  | 2018-10-31 08:43 | [5 empty] | 2018-10-31 08:43 | Yes | -13 | 1204-Owner-v | 2020-04-23 16:52
VD-9001-401A-ITP-001 | 1 | INSPECTION AND TEST PLAN | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-11-07 08:38 | 2018-10-30 16:44 | 2018-10-30 17:22 | Yes | -8 |  |  | 2018-11-03 16:37 | [5 empty] | 2018-11-03 16:37 | Yes | -10 | 1204-Owner-v | 2020-01-01 11:01
VD-9001-251-DIG-001 | 1 | CAUSE & EFFECT DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2018-10-31 |  |  | No | 597 | [9 empty] | No | 0
VD-9001-251-DWG-111 | 1 | COMBUSTION AIR DUCTS STEELWORK SUPPORT | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-24 15:27 | 2018-10-31 12:02 | Yes | 0 |  |  | 2018-11-11 09:47 | [5 empty] | 2018-11-11 09:47 | Yes | 4
VD-9001-251-DWG-121 | 1 | STEELWORK SUPPORT AL. A – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-24 15:50 | 2018-10-31 12:03 | Yes | 0 |  |  | 2018-11-11 10:56 | [5 empty] | 2018-11-11 10:56 | Yes | 4
VD-9001-251-DWG-122 | 1 | STEELWORK SUPPORT AL. 12 – GENERAL ARRANGEMENT | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-31 11:48 | 2018-10-31 16:57 | Yes | 7 |  |  | 2018-11-13 11:53 | [5 empty] | 2018-11-13 11:53 | Yes | -1
VD-9001-251-DWG-123 | 1 | STEELWORK SUPPORT AL. 12 – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-31 11:53 | 2018-10-31 11:54 | Yes | 7 |  |  | 2018-11-11 10:57 | [5 empty] | 2018-11-11 10:57 | Yes | -3
VD-9001-251-DWG-124 | 1 | GENERAL ARRANGEMENT ALIGNMENTS “R-S” | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-31 11:56 | 2018-10-31 11:57 | Yes | 7 |  |  | 2018-11-11 09:30 | [5 empty] | 2018-11-11 09:30 | Yes | -3 | 1204-Owner-v | 2019-03-02 11:29
VD-9001-251-DWG-125 | 1 | GENERAL ARRANGEMENT ALIGNMENTS “17-18-19” | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:02 | 2018-10-31 11:58 | 2018-10-31 12:02 | Yes | 7 |  |  | 2018-11-11 09:22 | [5 empty] | 2018-11-11 09:22 | Yes | -3
VD-9001-251-DWG-120 | 1 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:03 | 2018-10-31 12:05 | 2018-10-31 12:06 | Yes | 7 |  |  | 2018-11-11 10:53 | [5 empty] | 2018-11-11 10:53 | Yes | -3
VD-9001-251-DWG-132 | 1 | PLANS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2018-10-24 12:03 | 2018-10-31 12:04 | 2018-10-31 12:04 | Yes | 7 |  |  | 2018-11-11 10:04 | [5 empty] | 2018-11-11 10:04 | Yes | -3 | 1204-Owner-v | 2019-03-02 11:30
VD-9001-231B-ITP-001 | 3 | INSPECTON AND TEST PLAN | PV-231B | Fars Ghaleb | 2018-10-30 | 2018-10-27 15:07 | 2018-10-27 15:07 | Yes | -3 |  |  | 2018-10-28 17:12 | [5 empty] | 2018-10-28 17:12 | Yes | -13 | 1204-Owner-v | 2020-01-01 12:57
VD-9001-251-NPL-500 | 1 | Dye Penetrant Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-NPL-501 | 1 | RX Procedure For Welds | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-590 | 1 | General arrangement drawing for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-591 | 1 | General arrangement drawing for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-592 | 1 | General arrangement drawing for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-594 | 1 | General arrangement drawing for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-593 | 1 | General arrangement drawing for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-595 | 1 | Pilot assembly for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-596 | 1 | Nameplate drawing | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-LST-590 | 1 | Commissionign spare parts list | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-597 | 1 | EWD and layout for ionization panel | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-DWG-598 | 1 | EWD and layout for UV scanner panel | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-QCP-590 | 1 | Quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-251-NPL-502 | 1 | RX Procedurre For Castings and Forgings | HM-251 | KT – Kinetics Technology SpA | 2018-11-03 |  |  | No | 594 | [9 empty] | No | 0
VD-9001-201B-WBK-001 | 3 | WELDING BOOK (4134-0359/W) | PV-201B | Brembana & Rolle S.p.A. | 2018-11-10 20:00 | 2019-01-04 12:46 | 2019-01-04 12:49 | Yes | 55 |  |  | 2019-01-06 18:15 | [5 empty] | 2019-01-06 20:00 | Yes | -12
VD-9001-251-WBS-590 | 1 | Welding book | HM-251 | KT – Kinetics Technology SpA | 2018-11-04 |  |  | No | 593 | [9 empty] | No | 0
VD-9001-401A-PCJ-001 | 1 | PACKING & MARKING PROCEDURE | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-11-11 14:51 | 2018-10-30 15:01 | 2018-10-30 15:01 | Yes | -12 |  |  | 2018-11-03 16:30 | [5 empty] | 2018-11-03 16:31 | Yes | -10
VD-9001-231B-DWG-008 | 3 | Ladder and platform drawing FOR SATURATOR COLUMN T-4001 | PV-231B | Fars Ghaleb | 2018-10-29 | 2018-10-29 10:25 | 2018-10-29 10:25 | Yes | 0 |  |  | 2018-10-29 10:55 | [5 empty] | 2018-10-29 10:55 | Yes | -14 | 1204-Owner-v | 2018-11-26 14:09
VD-9001-204D-DWG-005 | 4 | INTERNAL PARTS DETAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-31 | 2019-03-07 18:10 | 2019-03-07 18:11 | Yes | 127 |  |  | 2019-03-12 11:27 | [5 empty] | 2019-03-12 11:27 | Yes | -9 | 1204-Owner-v | 2019-04-06 14:46
VD-9001-204D-CAL-014 | 5 | FOUNDATION LOAD AND SUPPORT CALC'S | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-10-31 | 2019-05-03 18:32 | 2019-05-03 18:35 | Yes | 184 |  |  | 2019-05-06 08:01 | [5 empty] | 2019-05-06 08:01 | Yes | -11
VD-9001-257C-PCJ-010 | 1 | TOFD PROCEDURE (4137/TOFD) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-29 17:04 | 2018-10-29 18:04 | 2018-10-29 18:23 | Yes | 0 |  |  | 2018-11-07 11:34 | [5 empty] | 2018-11-07 11:34 | Yes | -5 | 1204-Owner-v | 2019-05-10 09:17
VD-9001-257C-ITP-005 | 2 | INSPECTION & TESTING PLAN (4137-0368/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-29 17:04 | 2018-10-29 18:30 | 2018-10-29 18:30 | Yes | 0 |  |  |  |  | 2018-11-07 10:38 |  |  |  | 2018-11-07 10:38 | Yes | -5 | 1204-Owner-v | 2020-01-01 10:33
VD-9001-257C-ITP-006 | 3 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-29 17:04 | 2018-10-29 18:31 | 2018-10-29 18:31 | Yes | 0 |  |  |  |  | 2018-11-07 10:34 |  |  |  | 2018-11-07 10:34 | Yes | -5 | 1204-Owner-v | 2020-01-01 10:36
VD-9001-257C-ITP-008 | 3 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-10-29 17:04 | 2018-10-29 18:32 | 2018-10-29 18:31 | Yes | 0 |  |  |  |  | 2018-11-07 11:45 |  |  |  | 2018-11-07 11:45 | Yes | -5 | 1204-Owner-v | 2020-01-01 10:36
VD-9001-257B-DWG-008 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-11-05 | 2018-12-01 12:08 | 2018-12-01 12:20 | Yes | 26 |  |  |  |  | 2018-12-18 16:35 |  |  |  | 2018-12-18 16:35 | Yes | 3 | 1204-Owner-v | 2019-01-05 12:35
VD-9001-257B-DWG-009 | 1 | BUNDLE DETAIL FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-11-05 | 2018-12-01 10:58 | 2018-12-01 11:00 | Yes | 26 |  |  | 2018-12-16 15:32 | [5 empty] | 2018-12-16 15:32 | Yes | 1
VD-9001-307A-PCJ-005 | 3 | Hydrostatic Test Procedure | MC-307A | KSB GERMANY | 2018-11-12 20:00 |  |  | No | 585 | [9 empty] | No | 0
VD-9001-401A-MDB-001 | 0 | Manufacturing Data Book | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-10-31 | 2018-12-16 05:42 | 2018-12-16 06:06 | Yes | 46 |  |  | 2018-12-19 08:16 |  |  |  | 2018-12-09 10:34 | 2018-12-09 10:34 | 2018-12-19 08:22 | Yes | -11
VD-9001-251-DWG-135 | 0 | Convection section – steel details | HM-251 | KT – Kinetics Technology SpA | 2018-10-31 | 2018-10-31 16:55 | 2018-10-31 16:57 | Yes | 0 |  |  | 2018-11-13 11:51 | [5 empty] | 2018-11-13 11:51 | Yes | -1
VD-9001-257C-DWG-044 | 3 | DETAILS DRAWING (4137-0371/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-10 | 2019-01-09 17:48 | 2019-01-09 17:48 | Yes | 60 |  |  |  |  | 2019-01-26 18:11 |  |  |  | 2019-01-26 18:11 | Yes | 3 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-204D-DWG-003 | 4 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-05 | 2019-03-07 18:09 | 2019-03-07 18:09 | Yes | 122 |  |  | 2019-05-18 14:59 | [5 empty] | 2019-05-18 14:59 | Yes | 58 | 1204-Owner-v | 2019-05-11 07:59
VD-9001-204D-DWG-032 | 3 | LADDER & PLATFORM LAYOUT DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-05 | 2018-11-20 12:06 | 2018-11-20 12:06 | Yes | 15 |  |  |  | 2018-12-30 15:16 |  |  |  |  | 2018-12-30 15:16 | Yes | 26
VD-9001-251-SVL-685 | 1 | SUB VENDOR LIST | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-NPL-591 | 1 | Dye penetrant test procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-NPL-592 | 1 | PMI procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-MDL-500 | 1 | VENDOR DELIVERABLE LIST | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-PCJ-590 | 1 | Paint procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-NPL-503 | 1 | Hydrostatic Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-257C-DWG-007 | 2 | DETAILS DRAWING (4137-0365/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-03 16:04 | 2018-11-05 12:46 | 2018-11-05 12:46 | Yes | 2 |  |  |  |  | 2018-11-27 11:33 |  |  |  | 2018-11-27 11:33 | Yes | 8 | 1204-Owner-v | 2019-08-15 15:39
VD-9001-257C-DWG-011 | 1 | SHIPPING DRAWING (4137-0365/T) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-03 16:04 | 2018-11-05 12:48 | 2018-11-05 12:47 | Yes | 2 |  |  | 2018-11-28 15:01 | [5 empty] | 2018-11-28 15:01 | Yes | 9 | 1204-Owner-v | 2019-04-22 10:16
VD-9001-401A-MTC-001 | 1 | MATERIAL TEST CERTIFICATE | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-11-17 16:22 | 2018-11-26 15:37 | 2018-12-04 01:00 | Yes | 9 |  |  |  | 2018-12-06 09:43 |  |  |  |  | 2018-12-06 09:44 | Yes | -4
VD-9001-251-NPL-504 | 1 | Pneumatic Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-NPL-505 | 1 | PMI Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-251-DWG-530 | 1 | Drawings for Valves | HM-251 | KT – Kinetics Technology SpA | 2018-11-10 |  |  | No | 587 | [9 empty] | No | 0
VD-9001-254-PLN-558 | 1 | GENERAL PIPING ARRANGEMENT FOR BOILER 6 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2018-11-04 12:04 | 2018-11-04 15:09 | 2018-11-04 15:09 | Yes | 0 |  |  |  | 2018-11-24 10:00 |  |  |  |  | 2018-11-24 10:00 | Yes | 6
VD-9001-257C-GAD-008 | 2 | GENERAL ARRANGEMENT (4137-0371) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-11 | 2019-01-09 17:42 | 2019-01-09 17:42 | Yes | 59 |  |  | 2019-02-18 11:48 | [5 empty] | 2019-02-18 11:48 | Yes | 26 | 1204-Owner-v | 2019-05-10 09:11
VD-9001-257C-GAD-007 | 2 | GENERAL ARRANGEMENT (4137-0370) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-12 | 2019-01-09 17:41 | 2019-01-09 17:41 | Yes | 58 |  |  | 2019-02-18 17:10 | [5 empty] | 2019-02-18 17:10 | Yes | 26 | 1204-Owner-v | 2019-05-10 09:11
VD-9001-307A-LST-054 | 1 | Filled SPIR list | MC-307A | KSB GERMANY | 2018-11-19 20:00 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-257C-ITP-006 | 4 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-14 | 2018-11-27 14:32 | 2018-11-27 14:32 | Yes | 13 |  |  | 2018-12-11 17:05 | [5 empty] | 2018-12-11 17:05 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:37
VD-9001-257C-ITP-005 | 3 | INSPECTION & TESTING PLAN (4137-0368/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-14 | 2018-11-27 14:19 | 2018-11-27 14:19 | Yes | 13 |  |  | 2018-12-11 15:22 | [5 empty] | 2018-12-11 15:22 | Yes | 0 | 1204-Owner-v | 2019-04-20 09:43
VD-9001-202F-SPE-004 | 1 | Waste Heat Boiler - Specification of Bypass Actuator | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-11-14 |  |  | No | 583 | [9 empty] | No | 0
VD-9001-202F-MNL-002 | 1 | Operating Manual | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2018-11-14 |  |  | No | 583 | [9 empty] | No | 0
VD-9001-257C-ITP-008 | 4 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-14 | 2018-11-27 14:34 | 2018-11-27 14:34 | Yes | 13 |  |  | 2018-12-11 17:07 | [5 empty] | 2018-12-11 17:07 | Yes | 0 | 1204-Owner-v | 2020-01-01 10:37
VD-9001-257C-CAL-005 | 2 | MECHANICAL CALCULATION (4137-0368/MC) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-08 12:33 | 2018-11-08 18:27 | 2018-11-08 18:27 | Yes | 0 |  |  |  |  | 2019-01-01 14:37 |  |  |  | 2019-01-01 14:37 | Yes | 40
VD-9001-201A-CAL-012 | 2 | CALCULATION BOOK - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-11-15 | 2018-12-01 12:08 | 2018-12-01 12:08 | Yes | 16 |  |  | 2019-01-21 16:41 | [5 empty] | 2019-01-21 16:41 | Yes | 37
VD-9001-201A-CAL-030 | 2 | CALCULATION BOOK - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-11-15 | 2018-12-16 12:00 | 2018-12-16 12:00 | Yes | 31 |  |  | 2019-01-21 16:42 |  |  |  | 2018-12-16 11:45 | 2018-12-16 11:45 | 2019-01-21 16:42 | Yes | 22
VD-9001-307A-ITP-019 | 0 | Inspection and Test Plan Gear Box (ITP) For PT-2002A-GB1 | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:46 | 2018-11-16 15:46 | Yes | 6 |  |  |  | 2018-11-20 09:46 |  |  |  |  | 2018-11-20 19:59 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-ITP-020 | 0 | Inspection and Test Plan Pump (ITP) For PT-2003A-GB1 | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:47 | 2018-11-16 15:47 | Yes | 6 |  |  |  | 2018-11-20 11:36 |  |  |  |  | 2018-11-20 20:00 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:52
VD-9001-307A-ITP-021 | 0 | Inspection and Test Plan Pump (ITP) For PT-4001A/B-GB1 | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:47 | 2018-11-16 15:47 | Yes | 6 |  |  |  | 2018-11-20 09:49 |  |  |  |  | 2018-11-20 20:00 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:53
VD-9001-307A-ITP-022 | 0 | Inspection and Test Plan Pump (ITP) For PT-4002A-GB1 | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:47 | 2018-11-16 15:47 | Yes | 6 |  |  |  | 2018-11-20 09:51 |  |  |  |  | 2018-11-20 20:00 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:53
VD-9001-307A-ITP-023 | 0 | Inspection and Test Plan Pump (ITP) For PT-6301A/B-GB1 | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:47 | 2018-11-16 15:48 | Yes | 6 |  |  |  | 2018-11-20 09:58 |  |  |  |  | 2018-11-20 20:00 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:54
VD-9001-307A-ITP-025 | 0 | Inspection Test Plan Procedure (Gear Box) | MC-307A | KSB GERMANY | 2018-11-10 | 2018-11-16 15:47 | 2018-11-16 15:48 | Yes | 6 |  |  |  | 2018-11-20 11:12 |  |  |  |  | 2018-11-20 20:00 | Yes | -10 | 1204-Owner-v | 2020-01-01 10:54
VD-9001-231B-DWG-033 | 0 | Ladder and platform Detail D-6401 | PV-231B | Fars Ghaleb | 2018-11-10 | 2018-11-19 12:54 | 2018-11-19 12:54 | Yes | 9 |  |  |  |  | 2018-11-26 11:02 |  |  |  | 2018-11-26 11:02 | Yes | -7
VD-9001-231B-DWG-034 | 0 | Ladder and platform Arrangment D-6401 | PV-231B | Fars Ghaleb | 2018-11-10 | 2018-11-19 13:06 | 2018-11-19 13:06 | Yes | 9 |  |  |  |  | 2018-11-26 10:58 |  |  |  | 2018-11-26 10:58 | Yes | -7
VD-9001-307A-PCU-024 | 3 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-11-24 20:00 |  |  | No | 573 | [9 empty] | No | 0
VD-9001-307A-PCU-025 | 3 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-11-24 20:00 |  |  | No | 573 | [9 empty] | No | 0
VD-9001-307A-PCU-022 | 3 | Steam Consumption Curves Turbine | MC-307A | KSB GERMANY | 2018-11-24 20:00 |  |  | No | 573 | [9 empty] | No | 0
VD-9001-251-PCJ-001 | 1 | ERECTION PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 | 2019-04-13 10:40 | 2019-04-13 10:40 | Yes | 145 |  |  |  | 2019-06-09 11:31 |  |  |  |  | 2019-06-09 11:31 | Yes | 43 | 1204-Owner-v | 2019-04-23 14:13
VD-9001-231B-DWG-0024 | 1 | Ladder and platform Detail D-4004 | PV-231B | Fars Ghaleb | 2018-11-14 | 2018-11-12 14:02 | 2018-11-12 14:03 | Yes | -2 |  |  | 2018-11-13 15:00 | [5 empty] | 2018-11-13 20:00 | Yes | -13 | 1204-Owner-v | 2018-12-26 14:21
VD-9001-204D-GAD-002 | 5 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-14 | 2019-03-07 18:45 | 2019-03-07 18:46 | Yes | 113 |  |  |  | 2019-04-16 14:00 |  |  |  |  | 2019-04-16 14:00 | Yes | 26 | 1204-Owner-v | 2019-03-18 17:47
VD-9001-204D-DWG-011 | 3 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-14 | 2019-02-22 17:32 | 2019-02-22 17:33 | Yes | 100 |  |  | 2019-04-07 16:38 | [5 empty] | 2019-04-07 16:38 | Yes | 30 | 1204-Owner-v | 2019-05-11 07:57
VD-9001-251-PPL-685 | 1 | General Arrangement dwg with Foundation Loads Fan Type 80W/A10 - 155 M DWDI | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-PPL-686 | 1 | General Arrangement dwg with Foundation Loads Fan Type 80W/A10 - 190 M DWDI | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-DSH-645 | 1 | LOADS ON SUPPORT STAND | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-NPL-506 | 1 | Radiography NDE Technique Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-NPL-507 | 1 | DYE Pen NDT Technique Sheet | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-DIG-661 | 1 | Wiring Diagram & Terminal Block (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-DIG-660 | 1 | Wiring Diagram & Terminal Block (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-WBK-641 | 1 | Welding Book | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-WBK-640 | 1 | Welding Book | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-201B-CAL-004 | 1 | FEA REPORT (4134-0359/FEA) | PV-201B | Brembana & Rolle S.p.A. | 2018-11-26 20:00 | 2018-12-03 10:38 | 2018-12-03 10:38 | Yes | 7 |  |  |  | 2018-12-12 17:01 |  |  |  |  | 2018-12-12 20:00 | Yes | -5
VD-9001-257C-DWG-026 | 3 | DETAILS DRAWING (4137-0368/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-20 | 2019-01-09 17:44 | 2019-01-09 17:44 | Yes | 50 |  |  | 2019-01-16 16:47 | [5 empty] | 2019-01-16 16:47 | Yes | -7 | 1204-Owner-v | 2019-01-30 14:20
VD-9001-251-DSH-666 | 1 | Gearbox Data Sheet (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-DSH-661 | 1 | Lube Oil System Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-DSH-662 | 1 | Lube Oil System Data Sheet (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-DSH-665 | 1 | Gearbox Data Sheet (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-WBK-500 | 1 | Full Welding Dossier (Including Weld Maps,WPS,PQR'S) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-CAL-661 | 1 | Lateral Critical speed analysis (TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-CAL-660 | 1 | Lateral Critical speed data | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-QCP-501 | 1 | Static Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-QCP-503 | 1 | Fabrication Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-251-NPL-590 | 1 | Leak test procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-20 |  |  | No | 577 | [9 empty] | No | 0
VD-9001-231B-DWG-0025 | 1 | Ladder and platform Arrangment D-6201 | PV-231B | Fars Ghaleb | 2018-11-20 | 2018-12-19 11:54 | 2018-12-19 11:54 | Yes | 29 |  |  |  | 2019-01-02 11:52 |  |  |  |  | 2019-01-02 20:00 | Yes | 0
VD-9001-231B-DWG-0026 | 1 | Ladder and platform Detail D-6201 | PV-231B | Fars Ghaleb | 2018-11-15 | 2018-12-19 11:55 | 2018-12-19 11:55 | Yes | 34 |  |  |  | 2019-01-02 11:42 |  |  |  |  | 2019-01-02 20:00 | Yes | 0
VD-9001-254-DWH-548 | 5 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2018-11-19 | 2019-03-09 10:23 | 2019-03-09 10:23 | Yes | 110 |  |  | 2019-03-13 11:35 | [5 empty] | 2019-03-13 11:35 | Yes | -10 | 1204-Owner-v | 2019-12-08 13:02
VD-9001-254-DSH-219 | 3 | DATA SHEET FOR JUNCTION BOXES | HM-254 | AZAR AB | 2018-11-18 | 2018-12-12 08:07 | 2018-12-12 08:07 | Yes | 24 |  |  | 2019-01-02 11:03 | [5 empty] | 2019-01-02 11:03 | Yes | 7 | 1204-Owner-v | 2019-11-09 16:50
VD-9001-254-LST-217 | 4 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2018-11-18 | 2018-12-11 15:57 | 2018-12-11 15:57 | Yes | 23 |  |  |  | 2019-02-05 15:22 |  |  |  |  | 2019-02-05 15:22 | Yes | 42
VD-9001-251-NPL-685 | 1 | NDT Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-PCJ-685 | 1 | Painting specification | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-ITP-686 | 1 | Fabrication and quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-537 | 1 | PMI Procedure for 347H Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-534 | 1 | PMI Procedure for Seamless Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-535 | 1 | PMI Procedure for Alloy 800HT Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-533 | 1 | PMI Procedure for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-530 | 1 | PMI Procedure for Low Alloy Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-ITP-531 | 1 | Fabrication and Quality Control Plan for Forged Fittings and Olets | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-531 | 1 | PMI Procedure for Forged Fittings and Olets | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-532 | 1 | PMI Procedure for Seamless and Welded Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-NPL-536 | 1 | PMI Procedure for Stainless Steel Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-ITP-685 | 1 | Fabrication and quality control plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-251-PCJ-663 | 1 | Testing Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-254-ITP-584 | 0 | ITP FOR PISTON ACTUATED VALVES | HM-254 | AZAR AB | 2018-11-14 | 2018-11-14 12:42 | 2018-11-14 12:42 | Yes | 0 |  |  | 2018-11-24 10:03 | [5 empty] | 2018-11-24 10:03 | Yes | -4 | 1204-Owner-v | 2020-01-01 10:29
VD-9001-201A-DWG-003 | 1 | NOZZLE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-11-21 | 2018-12-06 12:48 | 2018-12-06 12:48 | Yes | 15 |  |  | 2019-01-21 16:38 | [5 empty] | 2019-01-21 16:38 | Yes | 32 | 1204-Owner-v | 2019-01-05 12:44
VD-9001-201A-DWG-021 | 1 | NOZZLE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-11-21 | 2018-12-12 15:30 | 2018-12-12 15:30 | Yes | 21 |  |  | 2019-01-21 16:39 | [5 empty] | 2019-01-21 16:39 | Yes | 26 | 1204-Owner-v | 2019-01-05 12:46
VD-9001-201A-ANL-014 | 1 | F.E.A. FOR NOZZLES - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-11-21 |  |  | No | 576 | [9 empty] | No | 0
VD-9001-201A-ANL-032 | 1 | F.E.A. FOR NOZZLES - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-11-21 | 2019-03-18 12:03 | 2019-03-18 12:03 | Yes | 117 |  |  |  | 2019-08-28 17:35 |  |  |  |  | 2019-08-28 17:35 | Yes | 149
VD-9001-251-ITP-536 | 1 | Fabrication and Quality Control Plan for Stainless Steel Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-537 | 1 | Fabrication and Quality Control Plan for 347H Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-ITP-538 | 1 | Fabrication and Quality Control Plan for Stock Piping | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-QCP-640 | 1 | Quality Control Plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-QCP-641 | 1 | Quality Control Plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-PCJ-640 | 1 | Surface preparation Painting Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-19 |  |  | No | 578 | [9 empty] | No | 0
VD-9001-251-PCJ-643 | 1 | Hydraulic Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-PCJ-644 | 1 | Pneumatic Leak Test Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-660 | 1 | Test & Inspection Plan (LOS/GB/YTUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-NPL-660 | 1 | NDT Procedure | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-532 | 1 | Fabrication and Quality Control Plan for Seamless and Welded Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-533 | 1 | Fabrication and Quality Control Plan for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-534 | 1 | Fabrication and Quality Control Plan for Seamless Butt-Weld Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-535 | 1 | Fabrication and Quality Control Plan for Alloy 800HT Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-QCP-502 | 1 | Centrispun Quality Plan | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-WBK-660 | 1 | Welding Book ( Including WMP,WPS,PQR,WPQ) (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-ITP-530 | 1 | Fabrication and Quality Control Plan for Low Alloy Seamless Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-WPS-531 | 1 | WPS/PQR for Welded Pipes | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-WPS-530 | 1 | WPS/PQR for Welded Fittings | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-307A-DWG-054 | 1 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-12-01 20:00 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-307A-DWG-051 | 1 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-12-01 20:00 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-307A-DWG-048 | 1 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-12-01 20:00 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-307A-DWG-045 | 1 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-12-01 20:00 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-307A-DWG-042 | 1 | Coupling Drawing (Turbin Side) | MC-307A | KSB GERMANY | 2018-12-01 20:00 |  |  | No | 566 | [9 empty] | No | 0
VD-9001-201A-DWG-002 | 2 | GENERAL ASSEMBLY- R1001 | PV-201A | FATEH SANAT KIMIA | 2018-11-25 | 2018-12-05 15:32 | 2018-12-05 15:33 | Yes | 10 |  |  |  | 2019-01-21 16:43 |  |  |  |  | 2019-01-21 16:43 | Yes | 33 | 1204-Owner-v | 2019-01-05 12:44
VD-9001-201A-DWG-020 | 2 | GENERAL ASSEMBLY - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-11-25 | 2018-12-12 15:27 | 2018-12-12 15:29 | Yes | 17 |  |  |  | 2019-01-21 16:44 |  |  |  |  | 2019-01-21 16:44 | Yes | 26 | 1204-Owner-v | 2019-01-05 12:46
VD-9001-251-PID-685 | 1 | Piping & Instrument diagrams | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-666 | 1 | Gearboxes Cross Section Drawing & Assembly Drawing (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-640 | 1 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-641 | 1 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-642 | 1 | General Arrangement drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-643 | 1 | Name Plate drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-251-DWG-644 | 1 | Name Plate drawing for Pre-Heaters | HM-251 | KT – Kinetics Technology SpA | 2018-11-26 |  |  | No | 571 | [9 empty] | No | 0
VD-9001-201A-ANL-013 | 1 | F.E.A. FOR SKIRT - R1001 | PV-201A | FATEH SANAT KIMIA | 2018-11-25 | 2019-04-18 12:27 | 2019-04-18 12:37 | Yes | 144 |  |  |  | 2019-08-28 17:32 |  |  |  |  | 2019-08-28 17:32 | Yes | 118 | 1204-Owner-v | 2020-05-21 15:33
VD-9001-201A-ANL-031 | 1 | F.E.A. FOR SKIRT - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-11-25 | 2019-04-20 09:31 | 2019-04-20 09:31 | Yes | 146 |  |  |  | 2019-08-28 17:31 |  |  |  |  | 2019-08-28 17:31 | Yes | 116
VD-9001-201B-PCJ-008 | 1 | INSTALLATION REFRACTORY PROCEDURE AT SITE (4134-0359/RIP-1) | PV-201B | Brembana & Rolle S.p.A. | 2018-11-20 09:11 | 2018-11-20 11:26 | 2018-11-20 11:26 | Yes | 0 |  |  | 2018-11-28 16:00 | [5 empty] | 2018-11-28 20:00 | Yes | -6
VD-9001-201-CAL-006 | 1 | STRESS ANALYSIS FOR BOTTOM HEAD | PV-201 | ATB RIVA CALZONI SpA | 2018-11-27 | 2018-11-30 11:33 | 2018-11-30 11:35 | Yes | 3 |  |  | 2018-12-02 16:41 | [5 empty] | 2018-12-02 16:41 | Yes | -12 | 1204-Owner-v | 2018-12-16 21:36
VD-9001-204B-DWG-021 | 1 | Transportation Saddle Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-11-20 15:29 | 2018-11-26 15:42 | 2018-11-26 15:42 | Yes | 6 |  |  | 2018-11-26 16:29 | [5 empty] | 2018-11-26 16:29 | Yes | -14 | 1204-Owner-v | 2019-01-13 09:14
VD-9001-204B-DWG-022 | 1 | Transportation Saddle Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-11-20 15:29 | 2018-11-27 14:31 | 2018-11-27 14:30 | Yes | 7 |  |  |  | 2018-11-28 15:18 |  |  |  |  | 2018-11-28 20:00 | Yes | -13
VD-9001-204B-DWG-023 | 1 | Transportation Saddle Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2018-11-20 15:29 | 2018-11-27 10:23 | 2018-11-27 10:24 | Yes | 7 |  |  |  | 2018-11-27 15:16 |  |  |  |  | 2018-11-27 15:16 | Yes | -14
VD-9001-204B-DWG-024 | 1 | Transportation Saddle Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2018-11-20 15:29 | 2018-11-28 10:22 | 2018-11-28 10:23 | Yes | 8 |  |  |  | 2018-11-28 15:43 |  |  |  |  | 2018-11-28 20:00 | Yes | -14
VD-9001-201-MDB-001 | 2 | MANUFACTURING DATA BOOK INDEX | PV-201 | ATB RIVA CALZONI SpA | 2018-11-27 |  |  | No | 570 | [9 empty] | No | 0
VD-9001-307A-ITP-019 | 1 | Inspection and Test Plan Gear Box (ITP) For PT-2002A-GB1 | MC-307A | KSB GERMANY | 2018-12-04 19:59 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-307A-ITP-021 | 1 | Inspection and Test Plan Pump (ITP) For PT-4001A/B-GB1 | MC-307A | KSB GERMANY | 2018-12-04 19:59 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-307A-ITP-022 | 1 | Inspection and Test Plan Pump (ITP) For PT-4002A-GB1 | MC-307A | KSB GERMANY | 2018-12-04 19:59 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-307A-ITP-023 | 1 | Inspection and Test Plan Pump (ITP) For PT-6301A/B-GB1 | MC-307A | KSB GERMANY | 2018-12-04 19:59 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-307A-ITP-025 | 1 | Inspection Test Plan Procedure (Gear Box) | MC-307A | KSB GERMANY | 2018-12-04 19:59 | 2018-12-07 15:39 | 2018-12-07 15:39 | Yes | 3 |  |  | 2018-12-10 11:24 | [5 empty] | 2018-12-10 19:59 | Yes | -11 | 1204-Owner-v | 2020-01-01 10:54
VD-9001-307A-ITP-020 | 1 | Inspection and Test Plan Pump (ITP) For PT-2003A-GB1 | MC-307A | KSB GERMANY | 2018-12-04 19:59 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-201B-LST-002 | 1 | 2 YEARS OPERATION S.P.LIST (4134/SPL2) | PV-201B | Brembana & Rolle S.p.A. | 2018-12-04 19:59 | 2019-03-21 12:19 | 2019-03-21 12:19 | Yes | 107 |  |  |  | 2019-04-10 16:22 |  |  |  |  | 2019-04-10 21:00 | Yes | 6
VD-9001-201B-LST-001 | 1 | COMMISSIONING & START-UP S.P.LIST (4134/SPL1) | PV-201B | Brembana & Rolle S.p.A. | 2018-12-04 19:59 | 2019-01-02 13:26 | 2019-01-02 13:26 | Yes | 29 |  |  |  | 2019-01-06 18:11 |  |  |  |  | 2019-01-06 20:00 | Yes | -10
VD-9001-257C-GAD-003 | 3 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-28 | 2019-01-22 18:41 | 2019-01-22 18:41 | Yes | 55 |  |  |  |  | 2019-02-19 10:32 |  |  |  | 2019-02-19 10:32 | Yes | 14 | 1204-Owner-v | 2019-03-18 16:17
VD-9001-307A-DWG-004 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-307A-DWG-002 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-251-DWG-671 | 1 | Instrument Hook-Up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DWG-670 | 1 | Instrument Hook-Up (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-LST-661 | 1 | Instrument List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-LST-662 | 1 | Instrument List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PPL-661 | 1 | Lube Oil System General Arrangement drawing (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PPL-660 | 1 | Lube Oil System General Arrangement drawing (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PPL-662 | 1 | Skid Turbine & Gearbox General Arrangement drawing (GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PPL-663 | 1 | Skid Turbine & Gearbox General Arrangement drawing (GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DSH-590 | 1 | Burner data sheet for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DSH-592 | 1 | Burner data sheet for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DSH-593 | 1 | Burner data sheet for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DSH-594 | 1 | Burner data sheet for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-DSH-591 | 1 | Burner data sheet for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PCU-591 | 1 | Performance curves for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PCU-592 | 1 | Performance curves for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PCU-590 | 1 | Performance curves for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PCU-593 | 1 | Performance curves for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-251-PCU-594 | 1 | Performance curves for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-11-29 |  |  | No | 568 | [9 empty] | No | 0
VD-9001-254-PLN-556 | 2 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-254-PLN-557 | 2 | GENERAL PIPING ARRANGEMENT FOR BOILER 5 (EL. 3800 AND UP) | HM-254 | AZAR AB | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-254-PLN-558 | 2 | GENERAL PIPING ARRANGEMENT FOR BOILER 6 (EL. 0 TO 3800) | HM-254 | AZAR AB | 2018-11-28 |  |  | No | 569 | [9 empty] | No | 0
VD-9001-257C-DWG-038 | 3 | DETAILS DRAWING (4137-0370/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-01 | 2019-01-09 17:47 | 2019-01-09 17:47 | Yes | 39 |  |  |  |  | 2019-01-26 18:08 |  |  |  | 2019-01-26 18:08 | Yes | 3 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-257C-PCJ-004 | 1 | POST WELD HEAT TREATMENT PROCEDURE (4137/PWHT) | HM-257C | Brembana & Rolle S.p.A. | 2018-11-24 10:12 | 2018-11-26 11:09 | 2018-11-26 11:13 | Yes | 2 |  |  | 2018-12-10 16:57 | [5 empty] | 2018-12-10 16:57 | Yes | 0
VD-9001-231B-DWG-034 | 1 | Ladder and platform Arrangment D-6401 | PV-231B | Fars Ghaleb | 2018-12-03 | 2018-11-27 10:32 | 2018-11-27 10:32 | Yes | -6 |  |  | 2018-11-28 15:33 | [5 empty] | 2018-11-28 15:33 | Yes | -13 | 1204-Owner-v | 2019-01-03 10:41
VD-9001-231B-DWG-033 | 1 | Ladder and platform Detail D-6401 | PV-231B | Fars Ghaleb | 2018-12-03 | 2018-11-27 10:31 | 2018-11-27 10:31 | Yes | -6 |  |  | 2018-11-28 15:34 | [5 empty] | 2018-11-28 15:34 | Yes | -13 | 1204-Owner-v | 2019-01-03 10:41
VD-9001-231B-DWG-0029 | 1 | Ladder and platform Arrangment D-6402 | PV-231B | Fars Ghaleb | 2018-12-03 | 2018-11-27 11:34 | 2018-11-27 11:34 | Yes | -6 |  |  | 2018-11-28 15:28 | [5 empty] | 2018-11-28 15:28 | Yes | -13 | 1204-Owner-v | 2019-01-03 10:39
VD-9001-231B-DWG-0030 | 1 | Ladder and platform Detail D-6402 | PV-231B | Fars Ghaleb | 2018-12-03 | 2018-11-27 11:35 | 2018-11-27 11:35 | Yes | -6 |  |  | 2018-11-28 15:31 | [5 empty] | 2018-11-28 15:31 | Yes | -13 | 1204-Owner-v | 2019-01-03 10:40
VD-9001-231B-DWG-0019 | 1 | Ladder and platform Arrangment D-4002 | PV-231B | Fars Ghaleb | 2018-11-26 11:45 | 2018-12-16 11:42 | 2018-12-16 11:42 | Yes | 20 |  |  | 2018-12-16 12:57 | [5 empty] | 2018-12-16 12:57 | Yes | -14 | 1204-Owner-v | 2019-01-03 10:38
VD-9001-231B-DWG-0020 | 1 | Ladder and platform Detail D-4002 | PV-231B | Fars Ghaleb | 2018-11-26 11:45 | 2018-12-16 11:43 | 2018-12-16 11:43 | Yes | 20 |  |  | 2018-12-16 13:00 | [5 empty] | 2018-12-16 13:00 | Yes | -14 | 1204-Owner-v | 2019-01-03 10:40
VD-9001-231B-DWG-0021 | 1 | Ladder and platform Arrangment D-4003 | PV-231B | Fars Ghaleb | 2018-11-26 11:45 | 2018-12-16 11:46 | 2018-12-16 11:46 | Yes | 20 |  |  | 2018-12-16 13:02 | [5 empty] | 2018-12-16 13:02 | Yes | -14 | 1204-Owner-v | 2019-01-03 10:40
VD-9001-231B-DWG-0022 | 1 | Ladder and platform Detail D-4003 | PV-231B | Fars Ghaleb | 2018-11-26 11:46 | 2018-12-16 11:47 | 2018-12-16 11:47 | Yes | 20 |  |  | 2018-12-16 14:50 | [5 empty] | 2018-12-16 14:50 | Yes | -14 | 1204-Owner-v | 2019-01-03 10:39
VD-9001-231B-DWG-0024 | 2 | Ladder and platform Detail D-4004 | PV-231B | Fars Ghaleb | 2018-11-26 11:46 | 2018-12-19 10:59 | 2018-12-19 10:59 | Yes | 23 |  |  | 2018-12-31 10:05 | [5 empty] | 2018-12-31 10:05 | Yes | -2 | 1204-Owner-v | 2019-01-03 10:40
VD-9001-201B-DWG-024 | 1 | INTERNAL DETAILS DRAWING R-1004 (4134-0359/H) | PV-201B | Brembana & Rolle S.p.A. | 2018-11-26 14:28 | 2018-11-26 14:38 | 2018-11-26 14:42 | Yes | 0 |  |  | 2018-12-18 11:37 | [5 empty] | 2018-12-19 09:15 | Yes | 8 | 1204-Owner-v | 2018-12-16 21:49
VD-9001-307A-DWG-226 | 0 | Surface Condenser Drawing | MC-307A | KSB GERMANY | 2018-11-27 | 2018-11-27 13:38 | 2018-11-27 13:38 | Yes | 0 |  |  |  | 2018-12-24 11:34 |  |  |  |  | 2018-12-24 20:00 | Yes | 13 | 1204-Owner-v | 2020-04-23 17:45
VD-9001-257C-DWG-007 | 3 | DETAILS DRAWING (4137-0365/1) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-04 | 2019-01-09 17:42 | 2019-01-09 17:43 | Yes | 36 |  |  | 2019-01-24 10:54 | [5 empty] | 2019-01-24 10:54 | Yes | 1 | 1204-Owner-v | 2019-01-30 14:12
VD-9001-254-LST-301 | 6 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-11-27 14:31 | 2018-12-01 15:58 | 2018-12-01 15:58 | Yes | 4 |  |  | 2018-12-26 09:22 | [5 empty] | 2018-12-26 09:22 | Yes | 11 | 1204-Owner-v | 2019-10-15 16:08
VD-9001-204B-DWG-023 | 2 | Transportation Saddle Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2018-12-04 | 2018-11-27 15:53 | 2018-11-27 15:53 | Yes | -7 |  |  | 2018-11-27 16:56 | [5 empty] | 2018-11-27 16:56 | Yes | -14 | 1204-Owner-v | 2019-01-13 09:15
VD-9001-204D-DWG-008 | 1 | DEMISTER DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-27 15:42 | 2018-11-28 12:23 | 2018-11-28 12:23 | Yes | 1 |  |  | 2018-12-15 10:21 | [5 empty] | 2018-12-15 10:21 | Yes | 3
VD-9001-251-DSH-604 | 1 | Portable igniter data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-595 | 1 | Noise data sheet for DFB-200 (ARCH CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-596 | 1 | Noise data sheet for DFB-200R (ARCH LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-597 | 1 | Noise data sheet for SF-FD-300 (TUNNEL CENTRAL) | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-598 | 1 | Noise data sheet for SF-FD-200 (TUNNEL LATERAL) | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-599 | 1 | Noise data sheet for SF-FD-300 (SSH) | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-600 | 1 | Amplifier data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-251-DSH-601 | 1 | UV scanner data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-12-04 |  |  | No | 563 | [9 empty] | No | 0
VD-9001-307A-DWG-196 | 1 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-12-11 19:59 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-307A-DWG-195 | 1 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-12-11 19:59 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-307A-DWG-197 | 1 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-12-11 19:59 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-307A-DWG-198 | 1 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-12-11 19:59 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-307A-DWG-199 | 1 | Gear Box Nameplate | MC-307A | KSB GERMANY | 2018-12-11 19:59 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-257C-GAD-006 | 3 | GENERAL ARRANGEMENT (4137-0369) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-05 | 2019-01-09 17:39 | 2019-01-09 17:39 | Yes | 35 |  |  |  |  | 2019-02-18 17:41 |  |  |  | 2019-02-18 17:41 | Yes | 26 | 1204-Owner-v | 2019-03-18 16:19
VD-9001-257C-DWG-032 | 2 | DETAILS DRAWING (4137-0369/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-05 | 2019-01-09 17:45 | 2019-01-09 17:45 | Yes | 35 |  |  | 2019-02-20 17:31 | [5 empty] | 2019-02-20 17:31 | Yes | 28 | 1204-Owner-v | 2019-01-30 14:20
VD-9001-204B-DWG-022 | 2 | Transportation Saddle Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2018-12-12 20:00 | 2018-12-01 16:03 | 2018-12-01 16:03 | Yes | -11 |  |  | 2018-12-01 16:23 | [5 empty] | 2018-12-01 20:00 | Yes | -14 | 1204-Owner-v | 2019-01-13 09:14
VD-9001-204B-DWG-024 | 2 | Transportation Saddle Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2018-12-12 20:00 | 2018-12-02 07:57 | 2018-12-02 07:57 | Yes | -10 |  |  | 2018-12-02 10:04 | [5 empty] | 2018-12-02 10:04 | Yes | -14 | 1204-Owner-v | 2019-01-13 09:14
VD-9001-204D-CAL-050 | 0 | PLATFORM STRUCTURAL ANALYSIS CALCULATION REPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:14 | 2018-12-03 18:15 | Yes | 3 |  |  |  | 2018-12-16 09:46 |  |  |  |  | 2018-12-16 09:46 | Yes | -1
VD-9001-204D-DWG-038 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:24 | 2018-12-03 18:24 | Yes | 3 |  |  |  | 2018-12-30 15:06 |  |  |  |  | 2018-12-30 15:06 | Yes | 13 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-039 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:26 | 2018-12-03 18:26 | Yes | 3 |  |  |  | 2018-12-30 15:06 |  |  |  |  | 2018-12-30 15:06 | Yes | 13
VD-9001-204D-DWG-040 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:43 | 2018-12-03 18:43 | Yes | 3 |  |  |  | 2018-12-30 15:07 |  |  |  |  | 2018-12-30 15:07 | Yes | 13 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-041 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:31 | 2018-12-03 18:31 | Yes | 3 |  |  |  | 2018-12-30 15:08 |  |  |  |  | 2018-12-30 15:08 | Yes | 13
VD-9001-204D-DWG-042 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:44 | 2018-12-03 18:44 | Yes | 3 |  |  |  | 2018-12-30 15:08 |  |  |  |  | 2018-12-30 15:08 | Yes | 13
VD-9001-204D-DWG-043 | 0 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:47 | 2018-12-03 18:47 | Yes | 3 |  |  |  | 2018-12-30 15:08 |  |  |  |  | 2018-12-30 15:08 | Yes | 13
VD-9001-204D-DWG-044 | 0 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:49 | 2018-12-03 18:49 | Yes | 3 |  |  |  | 2018-12-19 16:16 |  |  |  |  | 2018-12-19 16:16 | Yes | 2
VD-9001-204D-DWG-045 | 0 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:52 | 2018-12-03 18:53 | Yes | 3 |  |  |  | 2018-12-19 16:15 |  |  |  |  | 2018-12-19 16:15 | Yes | 2
VD-9001-204D-DWG-046 | 0 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:57 | 2018-12-03 18:58 | Yes | 3 |  |  |  | 2018-12-19 16:15 |  |  |  |  | 2018-12-19 16:15 | Yes | 2
VD-9001-204D-DWG-047 | 0 | LADDERS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 18:59 | 2018-12-03 19:00 | Yes | 3 |  |  |  | 2018-12-17 09:34 |  |  |  |  | 2018-12-17 09:34 | Yes | 0
VD-9001-204D-DWG-048 | 0 | LADDERS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 19:02 | 2018-12-03 19:02 | Yes | 3 |  |  |  | 2018-12-17 09:35 |  |  |  |  | 2018-12-17 09:35 | Yes | 0
VD-9001-204D-DWG-049 | 0 | GRATINGS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-11-30 | 2018-12-03 19:05 | 2018-12-03 19:05 | Yes | 3 |  |  |  | 2018-12-17 09:37 |  |  |  |  | 2018-12-17 09:37 | Yes | 0
VD-9001-307A-DWG-090 | 1 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-307A-DWG-089 | 1 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-307A-DWG-088 | 1 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-307A-DWG-087 | 1 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-307A-DWG-086 | 1 | Cross Sectinal Drawing Turbin inkl. BOM | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-307A-DSH-088 | 2 | Lube oil unit (Datasheet) | MC-307A | KSB GERMANY | 2018-12-15 20:00 |  |  | No | 552 | [9 empty] | No | 0
VD-9001-201A-PCJ-058 | 1 | NDE PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-12-09 | 2019-04-25 16:35 | 2019-04-25 16:35 | Yes | 137 |  |  | 2019-05-19 16:25 | [5 empty] | 2019-05-19 16:25 | Yes | 10
VD-9001-201A-PCJ-059 | 1 | PICKLING & PASSIVATION PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-12-09 | 2019-04-25 16:35 | 2019-04-25 16:35 | Yes | 137 |  |  | 2019-05-19 15:54 | [5 empty] | 2019-05-19 15:54 | Yes | 10
VD-9001-201A-PCJ-062 | 1 | PMI & FERRITE CHECK PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-12-09 | 2019-04-27 11:18 | 2019-04-27 11:18 | Yes | 139 |  |  | 2019-06-02 11:33 | [5 empty] | 2019-06-02 11:33 | Yes | 22
VD-9001-201A-PCJ-063 | 1 | HARDNESS TEST PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-12-09 | 2019-04-24 16:30 | 2019-04-24 16:30 | Yes | 136 |  |  | 2019-05-19 15:40 | [5 empty] | 2019-05-19 15:40 | Yes | 11
VD-9001-307A-LST-043 | 1 | Utility consumption list | MC-307A | KSB GERMANY | 2018-12-16 19:59 |  |  | No | 551 | [9 empty] | No | 0
VD-9001-201A-PCJ-073 | 1 | FABRICATION PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2018-12-10 | 2019-04-24 16:30 | 2019-04-24 16:30 | Yes | 135 |  |  | 2019-05-19 15:46 | [5 empty] | 2019-05-19 15:46 | Yes | 11
VD-9001-201A-PCJ-067 | 1 | PWHT PROCEDURE - R-1001 &R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2018-12-10 | 2019-11-09 13:01 | 2019-11-09 13:01 | Yes | 334 |  |  | 2019-12-09 17:06 | [5 empty] | 2019-12-09 17:06 | Yes | 16
VD-9001-251-PID-001 | 3 | PID - PRIMARY REFORMER RADIANT SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-002 | 3 | PID - PRIMARY REFORMER CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-003 | 3 | PID - COMBUSTION AIR FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-004 | 3 | PID - FLUE GAS FAN SYSTEM | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-005 | 3 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-006 | 3 | PID - ARCH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-007 | 3 | PID - TUNNEL BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-008 | 3 | PID - SSH BURNERS FIRING | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-009 | 3 | PID - LOCAL PANELS | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PID-010 | 3 | PID- UTILITIES DISTRIBUTION | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-PCJ-686 | 1 | Testing procedures | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-251-DWG-661 | 1 | Filter Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2018-12-11 |  |  | No | 556 | [9 empty] | No | 0
VD-9001-743A-WPS-004 | 1 | WPS & PQR | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-12-05 10:48 | 2018-12-05 11:12 | 2018-12-05 11:12 | Yes | 0 |  |  |  | 2018-12-05 11:49 |  |  |  |  | 2018-12-05 11:49 | Yes | -14
VD-9001-743A-WPS-004 | 2 | WPS & PQR | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-12-05 |  |  | No | 562 | [9 empty] | No | 0
VD-9001-257C-DWG-020 | 3 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-12 | 2019-01-22 18:44 | 2019-01-22 18:44 | Yes | 41 |  |  |  |  | 2019-02-18 10:10 |  |  |  | 2019-02-18 10:10 | Yes | 13 | 1204-Owner-v | 2019-01-30 14:20
VD-9001-401A-MTC-001 | 2 | MATERIAL TEST CERTIFICATE | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-12-20 09:44 | 2018-12-06 14:24 | 2018-12-06 14:32 | Yes | -14 |  |  | 2018-12-08 08:43 | [5 empty] | 2018-12-08 08:44 | Yes | -12
VD-9001-257B-DWG-003 | 1 | BUNDLE DETAIL FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-12-13 | 2019-01-02 13:50 | 2019-01-02 13:50 | Yes | 20 |  |  | 2019-01-22 16:40 | [5 empty] | 2019-01-22 16:40 | Yes | 6
VD-9001-254-DIG-333 | 1 | CONTROL SYSTEM & BMS LOOP DIAGRAM | HM-254 | AZAR AB | 2018-12-13 | 2018-12-26 16:20 | 2018-12-26 16:22 | Yes | 13 |  |  |  | 2019-01-12 10:25 |  |  |  |  | 2019-01-12 10:25 | Yes | 3 | 1204-Owner-v | 2019-11-09 15:20
VD-9001-254-DSH-134 | 4 | DATA SHEET FOR BURNER | HM-254 | AZAR AB | 2018-12-13 |  |  | No | 554 | [9 empty] | No | 0
VD-9001-108-MDB-001 | 0 | Manufacturing Data Book | PR-108 | Farabard | 2018-12-08 | 2018-12-09 09:35 | 2018-12-09 09:58 | Yes | 1 |  |  |  |  | 2018-12-25 11:25 |  |  |  | 2018-12-25 11:26 | Yes | 2
VD-9001-251-LST-001 | 1 | ALARM/TRIP SET POINTS LIST | HM-251 | KT – Kinetics Technology SpA | 2018-12-17 |  |  | No | 550 | [9 empty] | No | 0
VD-9001-251-DSH-603 | 1 | Flame scanner cable data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-12-17 |  |  | No | 550 | [9 empty] | No | 0
VD-9001-251-DSH-602 | 1 | Ionization cable data sheet | HM-251 | KT – Kinetics Technology SpA | 2018-12-17 |  |  | No | 550 | [9 empty] | No | 0
VD-9001-401A-INX-001 | 1 | FINAL DATA BOOK INDEX | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-12-23 09:29 | 2018-12-13 13:11 | 2018-12-13 13:12 | Yes | -10 |  |  |  | 2018-12-16 11:47 |  |  |  |  | 2018-12-16 11:47 | Yes | -11
VD-9001-206B-PCJ-020 | 2 | CLADING PROCEDURE | PV-206B | TASHA | 2018-12-12 | 2018-12-24 07:52 | 2018-12-24 07:52 | Yes | 12 |  |  |  | 2019-01-12 17:36 |  |  |  |  | 2019-01-12 17:36 | Yes | 5
VD-9001-257B-DWG-002 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-12-17 | 2019-01-02 13:50 | 2019-01-02 13:50 | Yes | 16 |  |  | 2019-02-18 14:57 | [5 empty] | 2019-02-18 14:57 | Yes | 33 | 1204-Owner-v | 2019-01-05 12:32
VD-9001-257B-CAL-004 | 2 | CALCULATION BOOK FOR E-1005 | HM-257B | FATEH SANAT KIMIA | 2018-12-17 | 2019-01-01 16:07 | 2019-01-01 16:07 | Yes | 15 |  |  | 2019-01-16 16:39 | [5 empty] | 2019-01-16 16:39 | Yes | 1 | 1204-Owner-v | 2019-09-29 10:19
VD-9001-257B-ITP-035 | 1 | INSPECTION AND TEST PLAN | HM-257B | FATEH SANAT KIMIA | 2018-12-17 | 2018-12-18 09:54 | 2018-12-18 09:55 | Yes | 1 |  |  |  |  | 2019-01-13 15:50 |  |  |  | 2019-01-13 15:50 | Yes | 12 | 1204-Owner-v | 2020-01-01 10:39
VD-9001-204B-DWG-001 | 6 | General Arrangment Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2018-12-11 15:30 | 2018-12-11 15:41 | 2018-12-11 15:43 | Yes | 0 |  |  | 2018-12-11 16:00 | [5 empty] | 2018-12-11 16:00 | Yes | -14 | 1204-Owner-v | 2019-01-26 10:28
VD-9001-251-LGD-001 | 1 | OPERATING MANUAL | HM-251 | KT – Kinetics Technology SpA | 2018-12-18 |  |  | No | 549 | [9 empty] | No | 0
VD-9001-251-DWG-054 | 2 | MAIN COMBUSTION AIR DUCTS ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2018-12-18 | 2019-04-13 09:30 | 2019-04-13 09:30 | Yes | 116 |  |  |  | 2019-04-27 14:39 |  |  |  |  | 2019-04-27 14:39 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:55
VD-9001-251-MDL-660 | 1 | Document List (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2018-12-18 |  |  | No | 549 | [9 empty] | No | 0
VD-9001-307A-DIG-004 | 1 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-12-25 19:59 |  |  | No | 542 | [9 empty] | No | 0
VD-9001-307A-DIG-002 | 2 | P&I Diagram Pump Unit | MC-307A | KSB GERMANY | 2018-12-25 19:59 |  |  | No | 542 | [9 empty] | No | 0
VD-9001-201B-ITP-002 | 1 | INSPECTION & TEST PLAN (REFRACTORY) (4134-0359/RTP) | PV-201B | Brembana & Rolle S.p.A. | 2018-12-26 19:59 | 2019-01-23 13:04 | 2019-01-23 13:04 | Yes | 28 |  |  | 2019-02-05 08:39 | [5 empty] | 2019-02-05 19:59 | Yes | -1 | 1204-Owner-v | 2020-01-01 12:45
VD-9001-201B-CAL-004 | 2 | FEA REPORT (4134-0359/FEA) | PV-201B | Brembana & Rolle S.p.A. | 2018-12-26 19:59 | 2019-02-12 11:11 | 2019-02-12 11:11 | Yes | 48 |  |  | 2019-02-19 10:44 | [5 empty] | 2019-02-19 19:59 | Yes | -7
VD-9001-307A-DWG-003 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-12-29 19:59 |  |  | No | 538 | [9 empty] | No | 0
VD-9001-307A-DWG-009 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-12-29 19:59 |  |  | No | 538 | [9 empty] | No | 0
VD-9001-204D-DWG-006 | 1 | EXTERNAL SUPPORTS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-20 | 2019-02-14 17:46 | 2019-02-14 17:47 | Yes | 56 |  |  | 2019-02-19 16:16 | [5 empty] | 2019-02-19 16:16 | Yes | -9 | 1204-Owner-v | 2019-05-11 07:59
VD-9001-204D-CAL-050 | 1 | PLATFORM STRUCTURAL ANALYSIS CALCULATION REPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-20 | 2019-03-18 20:13 | 2019-03-18 20:13 | Yes | 88 |  |  |  | 2019-04-08 11:57 |  |  |  |  | 2019-04-08 11:57 | Yes | 7
VD-9001-201B-CAL-008 | 0 | LADDER AND PLATFORM CALCULATION (4134-0359/MC2) | PV-201B | Brembana & Rolle S.p.A. | 2018-12-16 | 2018-12-19 18:39 | 2018-12-19 18:40 | Yes | 3 |  |  |  | 2019-01-14 17:28 |  |  |  |  | 2019-01-14 20:00 | Yes | 12
VD-9001-401A-INX-001 | 2 | FINAL DATA BOOK INDEX | PI-401A | DORIS INTERNATIONAL SRL UNIPERSONALE | 2018-12-30 11:47 | 2018-12-16 14:59 | 2018-12-16 15:00 | Yes | -14 |  |  | 2018-12-16 15:30 | [5 empty] | 2018-12-16 15:30 | Yes | -14 | 1204-Owner-v | 2020-04-21 18:05
VD-9001-201A-ANL-049 | 1 | F.E.A. FOR SKIRT - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-12-23 | 2019-03-14 10:04 | 2019-03-14 10:04 | Yes | 81 |  |  |  | 2019-08-28 17:34 |  |  |  |  | 2019-08-28 17:34 | Yes | 153
VD-9001-201A-DWG-038 | 2 | GENERAL ASSEMBLY - R1003 | PV-201A | FATEH SANAT KIMIA | 2018-12-23 | 2019-03-06 14:59 | 2019-03-06 14:59 | Yes | 73 |  |  |  | 2019-04-24 12:10 |  |  |  |  | 2019-04-24 12:10 | Yes | 35 | 1204-Owner-v | 2019-12-15 13:30
VD-9001-257B-DWG-017 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2018-12-23 | 2019-02-13 10:52 | 2019-02-13 10:52 | Yes | 52 |  |  |  |  | 2019-02-20 16:28 |  |  |  | 2019-02-20 16:28 | Yes | -7
VD-9001-307A-DWG-001 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-12-30 19:59 |  |  | No | 537 | [9 empty] | No | 0
VD-9001-307A-DWG-007 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2018-12-30 19:59 |  |  | No | 537 | [9 empty] | No | 0
VD-9001-204D-DWG-047 | 1 | LADDERS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-19 | 2019-03-07 18:39 | 2019-03-07 18:39 | Yes | 78 |  |  | 2019-04-13 09:19 | [5 empty] | 2019-04-13 09:19 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:02
VD-9001-204D-DWG-048 | 1 | LADDERS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-19 | 2019-03-07 18:41 | 2019-03-07 18:41 | Yes | 78 |  |  | 2019-04-13 09:20 | [5 empty] | 2019-04-13 09:20 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-204D-DWG-049 | 1 | GRATINGS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-19 | 2019-03-07 18:43 | 2019-03-07 18:43 | Yes | 78 |  |  |  | 2019-04-13 09:21 |  |  |  |  | 2019-04-13 09:21 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:02
VD-9001-257B-DWG-024 | 2 | BUNDLE DETAIL FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2018-12-24 | 2019-02-05 09:53 | 2019-02-05 09:53 | Yes | 43 |  |  | 2019-02-10 14:32 | [5 empty] | 2019-02-10 14:32 | Yes | -9
VD-9001-257B-DWG-021 | 2 | BUNDLE DETAIL FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-12-25 | 2019-01-28 16:28 | 2019-01-28 16:29 | Yes | 34 |  |  | 2019-02-10 14:16 | [5 empty] | 2019-02-10 14:17 | Yes | -1
VD-9001-257B-DWG-008 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-12-25 | 2019-01-07 16:06 | 2019-01-07 16:07 | Yes | 13 |  |  | 2019-02-17 17:17 | [5 empty] | 2019-02-17 17:17 | Yes | 27
VD-9001-204D-DWG-046 | 1 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-21 | 2019-03-07 18:35 | 2019-03-07 18:35 | Yes | 76 |  |  | 2019-04-13 09:19 | [5 empty] | 2019-04-13 09:19 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-045 | 1 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-21 | 2019-03-07 18:32 | 2019-03-07 18:33 | Yes | 76 |  |  | 2019-04-13 09:16 | [5 empty] | 2019-04-13 09:16 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-204D-DWG-044 | 1 | HANDRAILS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-21 | 2019-03-07 18:30 | 2019-03-07 18:30 | Yes | 76 |  |  | 2019-04-13 09:16 | [5 empty] | 2019-04-13 09:16 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-257B-CAL-010 | 2 | CALCULATION BOOK FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2018-12-27 | 2019-01-07 16:09 | 2019-01-07 16:09 | Yes | 11 |  |  |  |  | 2019-02-04 16:51 |  |  |  | 2019-02-04 16:51 | Yes | 14
VD-9001-257C-CAL-013 | 1 | PIPING STRESS ANALYSIS (4137-0367/PSA) | HM-257C | Brembana & Rolle S.p.A. | 2018-12-22 11:51 | 2019-01-02 12:35 | 2019-01-02 12:35 | Yes | 11 |  |  |  |  | 2019-01-16 09:58 |  |  |  | 2019-01-16 09:58 | Yes | 0
VD-9001-743A-ITP-002 | 1 | Inspection & Test Plan | ST-743A | TASHFA Grating Co.(Toseh Shabakehaye Fooladi Asia) | 2018-12-01 | 2018-12-22 14:55 | 2018-12-22 14:55 | Yes | 21 |  |  | 2018-12-25 14:47 | [5 empty] | 2018-12-25 14:47 | Yes | -11 | 1204-Owner-v | 2020-01-01 12:59
VD-9001-743B-GAD-231B006 | 0 | GRATING ARRANGEMENT DRAWING FOR SATURATOR COLUMN T-1001 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:15 | 2018-12-24 14:15 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-16 20:30
VD-9001-743B-GAD-231B007 | 0 | GRATING ARRANGEMENT DRAWING FOR SATURATOR COLUMN T-2001 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:17 | 2018-12-24 14:17 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B008 | 0 | GRATING ARRANGEMENT DRAWING FOR SATURATOR COLUMN T-4001 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:26 | 2018-12-24 14:33 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B010 | 0 | GRATING ARRANGEMENT DRAWING D-1001 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:22 | 2018-12-24 14:22 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0012 | 0 | GRATING ARRANGEMENT DRAWING D-2002 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:27 | 2018-12-24 14:33 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-01-01 12:59
VD-9001-743B-GAD-231B0014 | 0 | GRATING ARRANGEMENT DRAWING D-3001 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:35 | 2018-12-24 14:37 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-16 20:50
VD-9001-743B-GAD-231B0016 | 0 | GRATING ARRANGEMENT DRAWING D-3003 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:32 | 2018-12-24 14:34 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-17 07:14
VD-9001-743B-GAD-231B0018 | 0 | GRATING ARRANGEMENT DRAWING D-3004 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-24 14:35 | 2018-12-24 14:37 | Yes | 2 | [9 empty] | No | 529 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0020 | 0 | GRATING ARRANGEMENT DRAWING D-4002 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-26 12:13 | 2018-12-26 12:19 | Yes | 4 | [9 empty] | No | 527 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0022 | 0 | GRATING ARRANGEMENT DRAWING D-4003 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-26 12:15 | 2018-12-26 12:19 | Yes | 4 | [9 empty] | No | 527 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0024 | 0 | GRATING ARRANGEMENT DRAWING D-4004 | ST-743B | Arak Rail | 2018-12-22 | 2019-02-25 08:44 | 2019-02-25 08:44 | Yes | 65 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:58
VD-9001-743B-GAD-231B0026 | 0 | GRATING ARRANGEMENT DRAWING D-6201 | ST-743B | Arak Rail | 2018-12-22 | 2019-02-25 08:46 | 2019-02-25 08:46 | Yes | 65 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:58
VD-9001-743B-GAD-231B0028 | 0 | GRATING ARRANGEMENT DRAWING D-6202 | ST-743B | Arak Rail | 2018-12-22 | 2019-02-25 08:47 | 2019-02-25 08:47 | Yes | 65 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:59
VD-9001-743B-GAD-231B0030 | 0 | GRATING ARRANGEMENT DRAWING D-6402 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-26 12:16 | 2018-12-26 12:18 | Yes | 4 | [9 empty] | No | 527 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0032 | 0 | GRATING ARRANGEMENT DRAWING D-8301 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-26 12:17 | 2018-12-26 12:18 | Yes | 4 | [9 empty] | No | 527 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-743B-GAD-231B0034 | 0 | GRATING ARRANGEMENT DRAWING D-6401 | ST-743B | Arak Rail | 2018-12-22 | 2018-12-26 12:18 | 2018-12-26 12:18 | Yes | 4 | [9 empty] | No | 527 | 1204-Owner-v | 2019-02-17 07:15
VD-9001-251-DWG-667 | 1 | Gearboxes Cross Section Drawing & Assembly Drawing (GB) | HM-251 | KT – Kinetics Technology SpA | 2018-12-31 |  |  | No | 536 | [9 empty] | No | 0
VD-9001-254-PFD-111 | 4 | PROCESS FLOW DIAGRAM (PFD) | HM-254 | AZAR AB | 2018-12-28 |  |  | No | 539 | [9 empty] | No | 0
VD-9001-254-DSH-151 | 5 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2018-12-28 | 2019-01-26 10:11 | 2019-01-26 10:12 | Yes | 29 |  |  |  | 2019-02-05 14:26 |  |  |  |  | 2019-02-05 14:26 | Yes | -4 | 1204-Owner-v | 2019-11-09 11:54
VD-9001-254-DIG-300 | 4 | SYSTEM ARCITECTURE & INTERCONNECTION DIAGRAM FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2018-12-28 | 2019-03-16 09:10 | 2019-03-16 09:10 | Yes | 78 |  |  | 2019-04-15 15:11 | [5 empty] | 2019-04-15 15:11 | Yes | 16
VD-9001-254-PPL-701 | 2 | GENERAL ARRANGEMENT OF COLUMN BASE | HM-254 | AZAR AB | 2018-12-28 |  |  | No | 539 | [9 empty] | No | 0
VD-9001-254-DSH-564 | 4 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2018-12-28 | 2018-12-24 10:59 | 2018-12-24 10:59 | Yes | -4 |  |  |  | 2019-01-12 10:23 |  |  |  |  | 2019-01-12 10:23 | Yes | 5 | 1204-Owner-v | 2019-06-15 14:44
VD-9001-254-MNL-325 | 4 | TECHNICAL SPECIFICATION FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2018-12-28 | 2019-03-18 10:58 | 2019-03-18 10:58 | Yes | 80 |  |  | 2019-04-15 15:12 | [5 empty] | 2019-04-15 15:12 | Yes | 14
VD-9001-254-SPE-331 | 2 | TECHNICAL SPECIFICATIONS FOR LBSP | HM-254 | AZAR AB | 2018-12-28 | 2019-04-24 14:07 | 2019-04-24 14:07 | Yes | 117 |  |  | 2019-05-05 09:23 | [5 empty] | 2019-05-05 09:23 | Yes | -3
VD-9001-257B-DWG-020 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2018-12-31 | 2019-01-28 16:28 | 2019-01-28 16:28 | Yes | 28 |  |  |  |  | 2019-02-17 16:55 |  |  |  | 2019-02-17 16:55 | Yes | 6
VD-9001-307A-DWG-226 | 1 | Surface Condenser Drawing | MC-307A | KSB GERMANY | 2019-01-07 20:00 |  |  | No | 529 | [9 empty] | No | 0
VD-9001-307A-DWG-005 | 3 | General Arrangement Drawing | MC-307A | KSB GERMANY | 2019-01-07 20:00 |  |  | No | 529 | [9 empty] | No | 0
VD-9001-108-MDB-001 | 1 | Manufacturing Data Book | PR-108 | Farabard | 2019-01-08 11:26 | 2019-01-23 12:55 | 2019-01-24 11:16 | Yes | 15 |  |  |  |  | 2019-02-10 09:04 |  |  |  | 2019-02-10 19:59 | Yes | 4
VD-9001-254-ISO-526 | 2 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER6) | HM-254 | AZAR AB | 2018-12-31 |  |  | No | 536 | [9 empty] | No | 0
VD-9001-254-ISO-525 | 2 | ISOMETRIC DWG. FOR INSTRUMENT AIR (BOILER 5) | HM-254 | AZAR AB | 2018-12-31 |  |  | No | 536 | [9 empty] | No | 0
VD-9001-254-DSH-567 | 2 | DATA SHEET FOR PRESSURE REGULATORS | HM-254 | AZAR AB | 2018-12-31 |  |  | No | 536 | [9 empty] | No | 0
VD-9001-201A-DWG-039 | 1 | NOZZLE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-01-02 | 2019-05-08 15:44 | 2019-05-08 15:44 | Yes | 126 |  |  |  | 2019-05-15 10:42 |  |  |  |  | 2019-05-15 10:42 | Yes | -7 | 1204-Owner-v | 2020-02-03 16:04
VD-9001-201A-QCP-065 | 1 | QUALITY CONTROL PLAN (QCP) | PV-201A | FATEH SANAT KIMIA | 2019-01-02 | 2019-01-15 15:15 | 2019-01-15 15:15 | Yes | 13 |  |  | 2019-02-03 17:49 | [5 empty] | 2019-02-03 17:49 | Yes | 5 | 1204-Owner-v | 2019-03-17 12:38
VD-9001-201A-PCJ-061 | 1 | PAINTING PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2019-01-02 | 2019-04-25 16:35 | 2019-04-25 16:35 | Yes | 113 |  |  |  | 2019-05-20 11:39 |  |  |  |  | 2019-05-20 11:39 | Yes | 11
VD-9001-204D-CAL-036 | 1 | CALCULATION FOR EXTERNAL ATTACHMENT AND CLIPS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-01-10 12:19 | 2019-01-10 12:20 | Yes | 10 |  |  |  | 2019-02-19 10:31 |  |  |  |  | 2019-02-19 10:31 | Yes | 26
VD-9001-257B-DWG-014 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2019-01-06 | 2019-01-17 10:26 | 2019-01-17 10:26 | Yes | 11 |  |  |  |  | 2019-02-19 10:48 |  |  |  | 2019-02-19 10:48 | Yes | 19
VD-9001-204D-DWG-038 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 |  |  | No | 536 | [9 empty] | No | 0
VD-9001-204D-DWG-039 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:21 | 2019-03-07 18:21 | Yes | 66 |  |  |  | 2019-04-13 09:08 |  |  |  |  | 2019-04-13 09:08 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-040 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:22 | 2019-03-07 18:22 | Yes | 66 |  |  | 2019-04-13 09:10 | [5 empty] | 2019-04-13 09:10 | Yes | 23
VD-9001-204D-DWG-041 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:25 | 2019-03-07 18:25 | Yes | 66 |  |  |  | 2019-04-13 09:11 |  |  |  |  | 2019-04-13 09:11 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-042 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:28 | 2019-03-07 18:28 | Yes | 66 |  |  | 2019-04-13 09:13 | [5 empty] | 2019-04-13 09:13 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:01
VD-9001-204D-DWG-043 | 1 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:29 | 2019-03-07 18:29 | Yes | 66 |  |  | 2019-04-13 09:15 | [5 empty] | 2019-04-13 09:15 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-204D-DWG-033 | 1 | LADDER & PLATFORM DETAILS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:19 | 2019-03-07 18:19 | Yes | 66 |  |  |  | 2019-04-13 09:09 |  |  |  |  | 2019-04-13 09:09 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:00
VD-9001-204D-DWG-032 | 4 | LADDER & PLATFORM LAYOUT DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2018-12-31 | 2019-03-07 18:17 | 2019-03-07 18:17 | Yes | 66 |  |  | 2019-04-13 09:09 | [5 empty] | 2019-04-13 09:09 | Yes | 23 | 1204-Owner-v | 2019-05-11 08:00
VD-9001-201B-DWG-008 | 2 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-13 20:00 | 2019-01-23 12:55 | 2019-01-23 12:58 | Yes | 10 |  |  |  | 2019-02-03 16:38 |  |  |  |  | 2019-02-03 20:00 | Yes | -3
VD-9001-201B-DWG-007 | 2 | LADDER AND PLATFORM DWG (4134-0359/3) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-13 20:00 | 2019-01-23 12:54 | 2019-01-23 12:55 | Yes | 10 |  |  | 2019-01-29 17:55 | [5 empty] | 2019-01-29 20:01 | Yes | -8
VD-9001-257B-DWG-011 | 1 | GENERAL ARRANGEMENT DRAWING FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-01-07 | 2019-01-14 09:11 | 2019-01-14 09:11 | Yes | 7 |  |  |  |  | 2019-02-17 17:31 |  |  |  | 2019-02-17 17:31 | Yes | 20
VD-9001-257B-CAL-025 | 2 | CALCULATION BOOK FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2019-01-07 | 2019-02-05 09:34 | 2019-02-05 09:34 | Yes | 29 |  |  | 2019-02-10 16:30 | [5 empty] | 2019-02-10 16:30 | Yes | -9
VD-9001-257B-CAL-022 | 2 | CALCULATION BOOK FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2019-01-07 | 2019-01-29 08:51 | 2019-01-29 08:51 | Yes | 22 |  |  | 2019-02-10 10:19 | [5 empty] | 2019-02-10 10:19 | Yes | -2
VD-9001-257C-GAD-005 | 3 | GENERAL ARRANGEMENT (4137-0368) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-08 | 2019-01-09 17:38 | 2019-01-09 17:38 | Yes | 1 |  |  |  |  | 2019-02-20 17:51 |  |  |  | 2019-02-20 17:51 | Yes | 28 | 1204-Owner-v | 2019-03-18 16:18
VD-9001-257C-CAL-005 | 3 | MECHANICAL CALCULATION (4137-0368/MC) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-08 | 2019-06-07 13:42 | 2019-06-07 13:44 | Yes | 150 |  |  | 2019-07-17 16:32 | [5 empty] | 2019-07-17 16:32 | Yes | 26
VD-9001-254-LST-302 | 7 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2019-01-07 | 2019-03-16 09:03 | 2019-03-16 09:03 | Yes | 68 |  |  | 2019-04-22 09:50 | [5 empty] | 2019-04-22 09:50 | Yes | 23
VD-9001-201B-LST-005 | 1 | BILL OF MATERIALS R-1004 (4134-0359/RBOM) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-02 15:27 | 2019-01-02 17:05 | 2019-01-02 17:05 | Yes | 0 |  |  | 2019-01-03 08:23 | [5 empty] | 2019-01-03 20:00 | Yes | -13 | 1204-Owner-v | 2019-01-29 14:58
VD-9001-257B-PCJ-031 | 1 | P.W.H.T. PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-09 | 2019-01-06 12:15 | 2019-01-06 12:15 | Yes | -3 |  |  | 2019-01-13 15:38 | [5 empty] | 2019-01-13 15:38 | Yes | -7
VD-9001-231B-DWG-0026 | 2 | Ladder and platform Detail D-6201 | PV-231B | Fars Ghaleb | 2019-01-14 | 2019-02-17 16:52 | 2019-02-17 16:57 | Yes | 34 |  |  |  | 2019-02-20 11:03 |  |  |  |  | 2019-02-20 19:59 | Yes | -11
VD-9001-231B-DWG-0025 | 2 | Ladder and platform Arrangment D-6201 | PV-231B | Fars Ghaleb | 2019-01-14 | 2019-02-17 16:33 | 2019-02-17 16:34 | Yes | 34 |  |  |  | 2019-02-20 11:00 |  |  |  |  | 2019-02-20 19:59 | Yes | -11 | 1204-Owner-v | 2019-02-28 23:07
VD-9001-201B-DWG-001 | 4 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-14 | 2019-01-23 12:57 | 2019-01-23 12:57 | Yes | 9 |  |  |  | 2019-02-06 18:28 |  |  |  |  | 2019-02-06 19:59 | Yes | 0
VD-9001-257C-GAD-002 | 3 | GENERAL ARRANGEMENT (4137-0365) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 | 2019-01-09 17:37 | 2019-01-09 17:37 | Yes | -3 |  |  | 2019-02-20 18:01 | [5 empty] | 2019-02-20 18:01 | Yes | 28 | 1204-Owner-v | 2019-03-18 16:18
VD-9001-251-DSH-646 | 1 | Skin Thermocouple Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2019-01-19 |  |  | No | 517 | [9 empty] | No | 0
VD-9001-257B-PCJ-050 | 1 | PICKLING AND PASSIVATION PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-13 | 2019-11-24 12:30 | 2019-11-24 12:30 | Yes | 315 |  |  | 2019-12-03 10:31 | [5 empty] | 2019-12-03 10:31 | Yes | -5
VD-9001-257B-PCJ-049 | 1 | HARDNESS TEST PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-13 | 2019-01-15 11:54 | 2019-01-15 11:54 | Yes | 2 |  |  | 2019-01-26 10:46 | [5 empty] | 2019-01-26 10:46 | Yes | -3
VD-9001-201B-LST-001 | 2 | COMMISSIONING & START-UP S.P.LIST (4134/SPL1) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-20 20:00 | 2019-03-21 12:19 | 2019-03-21 12:19 | Yes | 60 |  |  |  | 2019-04-10 16:21 |  |  |  |  | 2019-04-10 21:00 | Yes | 6
VD-9001-251-DSH-642 | 1 | Thermal Calculation Resume | HM-251 | KT – Kinetics Technology SpA | 2019-01-14 |  |  | No | 522 | [9 empty] | No | 0
VD-9001-251-DSH-643 | 1 | Thermal Calculation Resume | HM-251 | KT – Kinetics Technology SpA | 2019-01-14 |  |  | No | 522 | [9 empty] | No | 0
VD-9001-251-DSH-640 | 1 | Thermal Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-251-DSH-641 | 1 | Thermal Data Sheet | HM-251 | KT – Kinetics Technology SpA | 2019-01-15 |  |  | No | 521 | [9 empty] | No | 0
VD-9001-251-UDD-661 | 1 | Utility Consumption List including Electrical Users (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-01-16 |  |  | No | 520 | [9 empty] | No | 0
VD-9001-251-UDD-660 | 1 | Utility Consumption List including Electrical Users (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-01-16 |  |  | No | 520 | [9 empty] | No | 0
VD-9001-254-DWG-215 | 1 | CONNECTION & TERMINATION DWG | HM-254 | AZAR AB | 2019-01-17 | 2019-02-06 15:27 | 2019-02-06 15:29 | Yes | 20 |  |  |  | 2019-02-19 14:16 |  |  |  |  | 2019-02-19 14:16 | Yes | -1
VD-9001-254-PPL-319 | 6 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2019-01-17 | 2019-04-07 12:49 | 2019-04-07 12:49 | Yes | 80 |  |  |  | 2019-05-19 14:30 |  |  |  |  | 2019-05-19 14:30 | Yes | 28
VD-9001-254-PPL-318 | 6 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2019-01-17 | 2019-02-05 08:04 | 2019-02-05 08:05 | Yes | 19 |  |  |  | 2019-02-19 14:24 |  |  |  |  | 2019-02-19 14:24 | Yes | 0
VD-9001-254-DSH-564 | 5 | DATA SHEET SAFETY VALVES | HM-254 | AZAR AB | 2019-01-17 |  |  | No | 519 | [9 empty] | No | 0
VD-9001-254-DIG-333 | 2 | CONTROL SYSTEM & BMS LOOP DIAGRAM | HM-254 | AZAR AB | 2019-01-17 |  |  | No | 519 | [9 empty] | No | 0
VD-9001-257B-DWG-009 | 2 | BUNDLE DETAIL FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2019-01-12 10:37 | 2019-01-12 13:55 | 2019-01-12 13:56 | Yes | 0 |  |  | 2019-02-02 11:51 | [5 empty] | 2019-02-02 11:51 | Yes | 7
VD-9001-257C-DWG-039 | 2 | DETAILS DRAWING (4137-0370/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:00 | 2019-01-14 11:44 | 2019-01-14 11:44 | Yes | 2 |  |  | 2019-02-18 15:17 | [5 empty] | 2019-02-18 15:17 | Yes | 21 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-257C-DWG-045 | 3 | DETAILS DRAWING (4137-0371/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:01 | 2019-01-14 11:48 | 2019-01-14 11:48 | Yes | 2 |  |  | 2019-01-22 11:32 | [5 empty] | 2019-01-22 11:32 | Yes | -6 | 1204-Owner-v | 2019-01-30 14:21
VD-9001-257C-DWG-052 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0364/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:01 | 2019-01-14 11:39 | 2019-01-14 11:39 | Yes | 2 |  |  | 2019-01-15 16:16 | [5 empty] | 2019-01-15 16:16 | Yes | -13 | 1204-Owner-v | 2019-02-23 10:39
VD-9001-257C-DWG-053 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0365/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:01 | 2019-01-14 11:40 | 2019-01-14 11:41 | Yes | 2 |  |  | 2019-01-15 16:20 | [5 empty] | 2019-01-15 16:20 | Yes | -13
VD-9001-257C-DWG-056 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0368/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:01 | 2019-01-14 11:41 | 2019-01-14 11:41 | Yes | 2 |  |  | 2019-01-15 17:37 | [5 empty] | 2019-01-15 17:37 | Yes | -13 | 1204-Owner-v | 2019-02-23 14:19
VD-9001-257C-DWG-057 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0369/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:01 | 2019-01-14 11:43 | 2019-01-14 11:43 | Yes | 2 |  |  | 2019-01-14 18:06 | [5 empty] | 2019-01-14 18:06 | Yes | -14 | 1204-Owner-v | 2019-02-23 14:19
VD-9001-257C-DWG-058 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0370/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:02 | 2019-01-14 11:47 | 2019-01-14 11:47 | Yes | 2 |  |  | 2019-01-14 17:59 | [5 empty] | 2019-01-14 17:59 | Yes | -14 | 1204-Owner-v | 2019-02-23 14:19
VD-9001-257C-DWG-059 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0371/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:02 | 2019-01-14 11:50 | 2019-01-14 11:50 | Yes | 2 |  |  | 2019-01-14 15:27 | [5 empty] | 2019-01-14 15:27 | Yes | -14
VD-9001-257C-GAD-001 | 3 | GENERAL ARRANGEMENT (4137-0364) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-12 11:02 | 2019-01-14 11:29 | 2019-01-14 11:31 | Yes | 2 |  |  | 2019-02-20 17:36 | [5 empty] | 2019-02-20 17:36 | Yes | 23 | 1204-Owner-v | 2019-05-10 09:10
VD-9001-257B-PCJ-048 | 1 | FERRITE CHECK PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-19 | 2019-01-15 11:53 | 2019-01-15 11:53 | Yes | -4 |  |  | 2019-01-26 10:51 | [5 empty] | 2019-01-26 10:51 | Yes | -3
VD-9001-257B-PCJ-047 | 1 | PMI PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-19 | 2019-01-15 11:51 | 2019-01-15 11:51 | Yes | -4 |  |  | 2019-01-26 10:48 | [5 empty] | 2019-01-26 10:48 | Yes | -3
VD-9001-257B-PCJ-033 | 1 | HYDROSTATIC TEST PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-01-19 | 2019-01-26 16:01 | 2019-01-26 16:01 | Yes | 7 |  |  | 2019-02-06 09:22 | [5 empty] | 2019-02-06 09:22 | Yes | -3
VD-9001-206B-PCJ-020 | 3 | CLADING PROCEDURE | PV-206B | TASHA | 2019-01-14 | 2019-01-23 15:19 | 2019-01-23 15:20 | Yes | 9 |  |  | 2019-01-26 14:48 | [5 empty] | 2019-01-26 14:49 | Yes | -11
VD-9001-257C-PCJ-005 | 2 | NITROGEN PURGING (4137/N) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-20 | 2019-01-21 18:18 | 2019-01-21 18:18 | Yes | 1 |  |  |  |  | 2019-01-26 17:58 |  |  |  | 2019-01-26 17:58 | Yes | -9
VD-9001-257B-ITP-035 | 2 | INSPECTION AND TEST PLAN | HM-257B | FATEH SANAT KIMIA | 2019-01-15 | 2019-01-15 11:50 | 2019-01-15 11:50 | Yes | 0 |  |  | 2019-01-22 09:50 | [5 empty] | 2019-01-22 09:50 | Yes | -7 | 1204-Owner-v | 2020-01-01 10:39
VD-9001-251-CAL-530 | 1 | Drawings and Calculation Notes for Olets | HM-251 | KT – Kinetics Technology SpA | 2019-01-21 |  |  | No | 515 | [9 empty] | No | 0
VD-9001-251-DWG-665 | 1 | Heat Exchanger Costruction Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2019-01-21 |  |  | No | 515 | [9 empty] | No | 0
VD-9001-251-DWG-660 | 1 | Filter Detailed Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2019-01-21 |  |  | No | 515 | [9 empty] | No | 0
VD-9001-257B-DWG-012 | 1 | BUNDLE DETAIL FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-01-14 11:47 | 2019-01-14 13:00 | 2019-01-14 13:00 | Yes | 0 |  |  | 2019-02-02 15:31 | [5 empty] | 2019-02-02 15:31 | Yes | 5
VD-9001-257C-GAD-004 | 3 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-21 | 2019-01-22 18:42 | 2019-01-22 18:42 | Yes | 1 |  |  |  |  | 2019-02-19 10:36 |  |  |  | 2019-02-19 10:36 | Yes | 14 | 1204-Owner-v | 2019-03-18 16:17
VD-9001-201B-CAL-008 | 1 | LADDER AND PLATFORM CALCULATION (4134-0359/MC2) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-28 20:00 | 2020-05-14 19:41 | 2020-05-14 19:43 | Yes | 472 |  |  |  | 2020-06-01 13:40 |  |  |  |  | 2020-06-01 20:02 | Yes | 4
VD-9001-257B-DWG-023 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2019-01-22 | 2019-02-05 09:32 | 2019-02-05 09:32 | Yes | 14 |  |  |  |  | 2019-02-18 16:54 |  |  |  | 2019-02-18 16:54 | Yes | -1
VD-9001-257C-CAL-013 | 2 | PIPING STRESS ANALYSIS (4137-0367/PSA) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 | 2019-01-22 18:55 | 2019-01-22 18:55 | Yes | -1 |  |  |  |  | 2019-02-06 15:40 |  |  |  | 2019-02-06 15:40 | Yes | 1
VD-9001-257C-PCJ-003 | 2 | SURFACE PREPARATION AND PAINTING PROCEDURE (4137/SP) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-19 09:52 | 2019-01-21 11:13 | 2019-01-21 11:13 | Yes | 2 |  |  | 2019-01-26 17:57 | [5 empty] | 2019-01-26 17:57 | Yes | -9
VD-9001-251-DSH-669 | 1 | Instruments Data Sheet Including Control/Safety valves data sheet (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-01-28 |  |  | No | 508 | [9 empty] | No | 0
VD-9001-251-DSH-670 | 1 | Instruments Data Sheet Including Control/Safety valves data sheet (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-01-28 |  |  | No | 508 | [9 empty] | No | 0
VD-9001-201A-PCJ-075 | 0 | REPAIR PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2019-01-22 | 2019-04-28 10:45 | 2019-04-28 10:45 | Yes | 96 |  |  | 2019-05-20 11:46 | [5 empty] | 2019-05-20 11:46 | Yes | 8
VD-9001-201A-PCJ-076 | 0 | PRODUCTION TEST PLATE (PTP) PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2019-01-22 | 2019-12-11 10:04 | 2019-12-11 10:05 | Yes | 323 |  |  |  | 2020-02-08 09:03 |  |  |  |  | 2020-02-08 09:03 | Yes | 45
VD-9001-201A-DWG-002 | 3 | GENERAL ASSEMBLY- R1001 | PV-201A | FATEH SANAT KIMIA | 2019-01-28 | 2019-02-12 08:47 | 2019-02-12 08:47 | Yes | 15 |  |  |  | 2019-02-19 16:15 |  |  |  |  | 2019-02-19 16:15 | Yes | -7 | 1204-Owner-v | 2019-02-16 09:17
VD-9001-201A-DWG-020 | 3 | GENERAL ASSEMBLY - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-01-28 | 2019-02-12 08:48 | 2019-02-12 08:48 | Yes | 15 |  |  |  | 2019-02-19 16:00 |  |  |  |  | 2019-02-19 16:00 | Yes | -7 | 1204-Owner-v | 2019-02-16 09:18
VD-9001-257B-DWG-015 | 1 | BUNDLE DETAIL FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2019-01-22 09:47 | 2019-01-22 11:50 | 2019-01-22 11:52 | Yes | 0 |  |  | 2019-02-03 17:01 | [5 empty] | 2019-02-03 17:01 | Yes | -2
VD-9001-257C-DWG-012 | 2 | PAINTING PLAN (4137-0365/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:33 | 2019-01-23 16:42 | 2019-01-23 16:42 | Yes | 0 |  |  | 2019-02-06 14:48 | [5 empty] | 2019-02-06 14:48 | Yes | 0
VD-9001-257C-DWG-014 | 3 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:33 | 2019-01-23 16:45 | 2019-01-23 16:46 | Yes | 0 |  |  |  |  | 2019-02-17 15:56 |  |  |  | 2019-02-17 15:56 | Yes | 11 | 1204-Owner-v | 2019-01-30 14:19
VD-9001-257C-DWG-054 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0366/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:33 | 2019-01-23 16:48 | 2019-01-23 16:48 | Yes | 0 |  |  | 2019-01-24 12:29 | [5 empty] | 2019-01-24 12:29 | Yes | -13
VD-9001-257C-DWG-055 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4137-0367/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:49 | 2019-01-23 16:50 | Yes | 0 |  |  |  |  | 2019-01-24 12:17 |  |  |  | 2019-01-24 12:17 | Yes | -13
VD-9001-257C-DWG-062 | 2 | EXPANSION BELLOW DETAILS DRAWING (4137-0366/EB) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:51 | 2019-01-23 16:51 | Yes | 0 |  |  | 2019-01-24 11:20 | [5 empty] | 2019-01-24 11:20 | Yes | -13 | 1204-Owner-v | 2019-02-14 10:22
VD-9001-257C-DWG-063 | 2 | EXPANSION BELLOW DETAILS DRAWING (4137-0367/EB) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:56 | 2019-01-23 16:56 | Yes | 0 |  |  | 2019-01-24 11:09 | [5 empty] | 2019-01-24 11:09 | Yes | -13 | 1204-Owner-v | 2019-05-10 09:26
VD-9001-257C-DWG-064 | 3 | DETAILS DRAWING (4137-0367/3) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:53 | 2019-01-23 16:53 | Yes | 0 |  |  | 2019-02-06 15:42 | [5 empty] | 2019-02-06 15:42 | Yes | 0 | 1204-Owner-v | 2019-01-30 14:22
VD-9001-257C-DWG-065 | 2 | DETAILS DRAWING (4137-0366/3) E-2001A | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:44 | 2019-01-23 16:44 | Yes | 0 |  |  | 2019-01-24 12:33 | [5 empty] | 2019-01-24 12:33 | Yes | -13 | 1204-Owner-v | 2019-01-30 14:22
VD-9001-257C-DWG-066 | 2 | DETAILS DRAWING (4137-0367/4) E-2001B | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 15:34 | 2019-01-23 16:54 | 2019-01-23 16:54 | Yes | 0 |  |  | 2019-02-03 16:42 | [5 empty] | 2019-02-03 16:42 | Yes | -3 | 1204-Owner-v | 2019-01-30 14:22
VD-9001-257C-LST-004 | 0 | MASTER & DETAILED PACKING LIST (4137/PL) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-23 | 2019-01-30 18:55 | 2019-01-30 18:55 | Yes | 7 |  |  | 2019-02-02 11:39 | [5 empty] | 2019-02-02 11:39 | Yes | -11
VD-9001-201B-DWG-015 | 3 | BILL OF MATERIAL AND GENERAL NOTES (4134-0359/BMN) | PV-201B | Brembana & Rolle S.p.A. | 2019-01-23 17:43 | 2019-01-23 18:08 | 2019-01-23 18:21 | Yes | 0 |  |  | 2019-02-16 10:21 | [5 empty] | 2019-02-16 19:59 | Yes | 10 | 1204-Owner-v | 2019-04-23 11:36
VD-9001-257C-DWG-055 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0367/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-31 | 2019-01-28 16:22 | 2019-01-28 16:22 | Yes | -3 |  |  | 2019-01-29 15:36 | [5 empty] | 2019-01-29 15:36 | Yes | -13 | 1204-Owner-v | 2019-02-23 14:19
VD-9001-108-FMT-001 | 0 | SPIR FORM | PR-108 | Farabard | 2019-01-26 | 2019-01-27 12:08 | 2019-01-27 12:08 | Yes | 1 |  |  |  |  | 2019-01-28 11:33 |  |  |  | 2019-01-28 11:34 | Yes | -13
VD-9001-257C-PCJ-005 | 3 | NITROGEN PURGING (4137/N) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-02 | 2019-06-05 17:09 | 2019-06-05 17:13 | Yes | 123 |  |  | 2019-06-19 08:58 | [5 empty] | 2019-06-19 08:58 | Yes | 0 | 1204-Owner-v | 2019-07-01 13:03
VD-9001-257C-DWG-038 | 4 | DETAILS DRAWING (4137-0370/1) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-02 | 2019-01-30 18:22 | 2019-01-30 18:22 | Yes | -3 |  |  | 2019-02-03 14:32 | [5 empty] | 2019-02-03 14:32 | Yes | -10 | 1204-Owner-v | 2020-03-07 10:06
VD-9001-257C-DWG-044 | 4 | DETAILS DRAWING (4137-0371/1) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-02 | 2019-01-30 18:22 | 2019-01-30 18:22 | Yes | -3 |  |  | 2019-02-03 14:28 | [5 empty] | 2019-02-03 14:28 | Yes | -10 | 1204-Owner-v | 2020-05-09 10:24
VD-9001-108-FMT-001 | 1 | SPIR FORM | PR-108 | Farabard | 2019-02-11 11:34 |  |  | No | 494 | [9 empty] | No | 0
VD-9001-257C-DWG-003 | 3 | NAME PLATE DET.DWG (4137-0364/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:54 | 2019-01-29 16:37 | 2019-01-29 16:37 | Yes | 0 |  |  | 2019-02-03 14:47 | [5 empty] | 2019-02-03 14:47 | Yes | -9
VD-9001-257C-DWG-008 | 3 | DETAILS DRAWING (4137-0365/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:54 | 2019-01-29 16:36 | 2019-01-29 16:36 | Yes | 0 |  |  | 2019-02-03 16:53 | [5 empty] | 2019-02-03 16:53 | Yes | -9 | 1204-Owner-v | 2019-01-30 14:13
VD-9001-257C-DWG-009 | 3 | NAME PLATE DET.DWG (4137-0365/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:55 | 2019-01-29 16:37 | 2019-01-29 16:37 | Yes | 0 |  |  | 2019-02-03 14:40 | [5 empty] | 2019-02-03 14:40 | Yes | -9
VD-9001-257C-DWG-021 | 3 | NAME PLATE DET.DWG (4137-0367/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:55 | 2019-01-29 16:36 | 2019-01-29 16:36 | Yes | 0 |  |  | 2019-02-03 14:35 | [5 empty] | 2019-02-03 14:35 | Yes | -9
VD-9001-257C-DWG-053 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0365/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:55 | 2019-01-29 16:35 | 2019-01-29 16:35 | Yes | 0 |  |  | 2019-01-30 17:59 | [5 empty] | 2019-01-30 17:59 | Yes | -13 | 1204-Owner-v | 2019-02-23 14:18
VD-9001-257C-DWG-054 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0366/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-01-29 14:56 | 2019-01-29 16:34 | 2019-01-29 16:35 | Yes | 0 |  |  | 2019-01-30 17:57 | [5 empty] | 2019-01-30 17:57 | Yes | -13 | 1204-Owner-v | 2019-02-23 10:40
VD-9001-251-PDS-001 | 1 | CONTROL PHILOSOFY DESCRIPTION | HM-251 | KT – Kinetics Technology SpA | 2019-02-08 |  |  | No | 497 | [9 empty] | No | 0
VD-9001-251-PDS-002 | 1 | BMS DESCRIPTION | HM-251 | KT – Kinetics Technology SpA | 2019-02-07 |  |  | No | 498 | [9 empty] | No | 0
VD-9001-257C-DWG-059 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0371/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-02 10:46 | 2019-02-04 12:05 | 2019-02-04 12:05 | Yes | 2 |  |  | 2019-02-04 16:06 | [5 empty] | 2019-02-04 16:06 | Yes | -14 | 1204-Owner-v | 2019-02-23 14:20
VD-9001-254-ISO-590 | 0 | ISOMETRIC DRAWING FOR ATOMIZING STEAM LINE (BOILER A) | HM-254 | AZAR AB | 2019-02-02 | 2019-03-16 15:11 | 2019-03-16 15:11 | Yes | 42 |  |  |  | 2019-03-19 10:49 |  |  |  |  | 2019-03-19 10:49 | Yes | -11
VD-9001-254-ISO-591 | 0 | ISOMETRIC DRAWING FOR ATOMIZING STEAM LINE (BOILER B) | HM-254 | AZAR AB | 2019-02-02 | 2019-03-16 15:12 | 2019-03-16 15:12 | Yes | 42 |  |  |  | 2019-03-19 10:51 |  |  |  |  | 2019-03-19 10:52 | Yes | -11
VD-9001-254-ISO-592 | 0 | ISOMETRIC DRAWING FOR SOOTBLOWER LINE (BOILER A) | HM-254 | AZAR AB | 2019-02-02 |  |  | No | 503 | [9 empty] | No | 0
VD-9001-254-ISO-593 | 0 | ISOMETRIC DRAWING FOR SOOTBLOWER LINE (BOILER B) | HM-254 | AZAR AB | 2019-02-02 |  |  | No | 503 | [9 empty] | No | 0
VD-9001-254-ISO-594 | 0 | ISOMETRIC DRAWING FOR DESUPERHEATER LINE (BOILER A) | HM-254 | AZAR AB | 2019-02-02 | 2019-02-05 10:42 | 2019-02-05 10:42 | Yes | 3 |  |  | 2019-02-19 09:26 | [5 empty] | 2019-02-19 09:26 | Yes | 0
VD-9001-254-ISO-595 | 0 | ISOMETRIC DRAWING FOR DESUPERHEATER LINE (BOILER B) | HM-254 | AZAR AB | 2019-02-02 | 2019-02-05 10:44 | 2019-02-05 10:44 | Yes | 3 |  |  | 2019-02-19 09:29 | [5 empty] | 2019-02-19 09:29 | Yes | 0
VD-9001-201B-DWG-008 | 3 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2019-02-17 19:59 | 2019-04-19 17:46 | 2019-04-19 17:46 | Yes | 61 |  |  |  | 2019-04-22 18:09 |  |  |  |  | 2019-04-22 20:59 | Yes | -11
VD-9001-257B-CAL-010 | 3 | CALCULATION BOOK FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2019-02-11 | 2019-03-03 16:49 | 2019-03-03 16:48 | Yes | 20 |  |  | 2019-03-05 10:40 | [5 empty] | 2019-03-05 10:40 | Yes | -12
VD-9001-257B-CAL-013 | 2 | CALCULATION BOOK FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-02-11 | 2019-03-04 11:35 | 2019-03-05 11:43 | Yes | 21 |  |  |  |  | 2019-03-07 10:21 |  |  |  | 2019-03-07 10:21 | Yes | -11
VD-9001-254-MNL-310 | 1 | INSTRUCTION MANUAL FOR O2 GAS ANALYZERS | HM-254 | AZAR AB | 2019-02-09 | 2019-02-05 13:54 | 2019-02-05 13:57 | Yes | -4 |  |  |  | 2019-02-13 16:14 |  |  |  |  | 2019-02-13 16:14 | Yes | -6
VD-9001-254-ISO-527 | 1 | ISOMETRIC DWG. FOR SEALING AIR LINE (BOILER 5) | HM-254 | AZAR AB | 2019-02-09 |  |  | No | 496 | [9 empty] | No | 0
VD-9001-254-ISO-528 | 1 | ISOMETRIC DWG. FOR SEALING AIR LINE (BOILER 6) | HM-254 | AZAR AB | 2019-02-09 |  |  | No | 496 | [9 empty] | No | 0
VD-9001-254-DSH-151 | 6 | DATA SHEET FOR F.D. FAN | HM-254 | AZAR AB | 2019-02-09 | 2019-04-06 11:30 | 2019-04-06 11:30 | Yes | 56 |  |  | 2019-04-30 16:00 | [5 empty] | 2019-04-30 16:00 | Yes | 10
VD-9001-254-LST-220 | 4 | WIRING LIST AND CABLE ROUTH ( POWER ) | HM-254 | AZAR AB | 2019-02-09 | 2020-05-02 13:32 | 2020-05-02 13:32 | Yes | 448 |  |  | 2020-05-12 07:44 | [5 empty] | 2020-05-12 07:44 | Yes | -4
VD-9001-254-LST-961 | 1 | CONTROL SYSTEM POWER CONSUMPTION AND HEAT DISSIPATION | HM-254 | AZAR AB | 2019-02-09 | 2019-04-24 14:13 | 2019-04-24 14:14 | Yes | 74 |  |  |  | 2019-05-21 11:33 |  |  |  |  | 2019-05-21 11:33 | Yes | 13
VD-9001-254-LST-217 | 5 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2019-02-09 | 2019-02-24 14:27 | 2019-02-24 14:27 | Yes | 15 |  |  |  | 2019-03-13 11:36 |  |  |  |  | 2019-03-13 11:36 | Yes | 3
VD-9001-254-SPE-200 | 1 | OUTLINE DRAWING & SPECIFICATION OF F.D.F MOTOR | HM-254 | AZAR AB | 2019-02-09 | 2019-02-24 14:26 | 2019-02-24 14:26 | Yes | 15 |  |  | 2019-04-15 15:06 | [5 empty] | 2019-04-15 15:06 | Yes | 36
VD-9001-108-DWG-020 | 6 | COLUMNS DEATAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-06 15:17 | 2019-02-06 15:17 | Yes | 0 |  |  |  |  | 2019-02-12 15:20 |  |  |  | 2019-02-12 15:20 | Yes | -8
VD-9001-108-DWG-021 | 8 | SHEAR WALLS DETAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-06 15:15 | 2019-02-06 15:15 | Yes | 0 |  |  | 2019-02-16 14:25 | [5 empty] | 2019-02-16 14:25 | Yes | -4
VD-9001-108-DWG-022 | 6 | MAIN BEAMS DETAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-07 09:47 | 2019-02-07 09:59 | Yes | 1 |  |  | 2019-02-16 15:45 | [5 empty] | 2019-02-16 15:45 | Yes | -5
VD-9001-108-DWG-024 | 4 | WATER DISTRIBUTION CHANNEL DETAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-06 15:10 | 2019-02-06 15:10 | Yes | 0 |  |  | 2019-02-16 10:26 | [5 empty] | 2019-02-16 10:26 | Yes | -4
VD-9001-108-DWG-025 | 5 | SUMP & ROOF SLAB DETAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-06 15:07 | 2019-02-06 15:07 | Yes | 0 |  |  | 2019-02-16 10:02 | [5 empty] | 2019-02-16 10:02 | Yes | -4
VD-9001-108-DWG-028 | 5 | STAIR CASE DETAIL | PR-108 | Farabard | 2019-02-06 11:43 | 2019-02-06 15:05 | 2019-02-06 15:05 | Yes | 0 |  |  | 2019-02-12 16:02 | [5 empty] | 2019-02-12 16:02 | Yes | -8
VD-9001-257B-WMP-038 | 1 | WELDING AND NDT MAP | HM-257B | FATEH SANAT KIMIA | 2019-02-13 | 2019-10-20 12:20 | 2019-10-20 12:20 | Yes | 249 |  |  | 2019-10-23 09:56 | [5 empty] | 2019-10-23 09:56 | Yes | -11
VD-9001-257C-CAL-013 | 3 | PIPING STRESS ANALYSIS (4137-0367/PSA) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-13 | 2019-06-07 13:49 | 2019-06-07 13:51 | Yes | 114 |  |  | 2019-07-17 16:35 | [5 empty] | 2019-07-17 16:35 | Yes | 26
VD-9001-257C-CAL-003 | 3 | MECHANICAL CALCULATION (4137-0366/MC) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-13 | 2019-06-12 17:16 | 2019-06-12 17:17 | Yes | 119 |  |  | 2019-07-17 16:39 | [5 empty] | 2019-07-17 16:39 | Yes | 21
VD-9001-257C-CAL-004 | 3 | MECHANICAL CALCULATION (4137-0367/MC) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-13 | 2019-06-07 13:40 | 2019-06-07 13:42 | Yes | 114 |  |  | 2019-07-17 16:15 | [5 empty] | 2019-07-17 16:15 | Yes | 26
VD-9001-201B-GAD-001 | 4 | GENERAL ARRANGEMENT (4134/0359) | PV-201B | Brembana & Rolle S.p.A. | 2019-02-20 19:59 | 2019-06-04 18:09 | 2019-06-04 18:38 | Yes | 104 |  |  | 2019-06-26 16:07 | [5 empty] | 2019-06-26 20:58 | Yes | 8 | 1204-Owner-v | 2019-08-06 13:42
VD-9001-201B-DWG-001 | 5 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2019-02-20 19:59 | 2019-06-04 18:05 | 2019-06-04 18:38 | Yes | 104 |  |  |  | 2019-06-11 17:49 |  |  |  |  | 2019-06-11 20:58 | Yes | -7 | 1204-Owner-v | 2020-05-18 09:31
VD-9001-108-MDB-001 | 2 | Manufacturing Data Book | PR-108 | Farabard | 2019-02-24 19:59 |  |  | No | 481 | [9 empty] | No | 0
VD-9001-257B-PCJ-030 | 1 | PAINTING PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2019-02-19 | 2019-11-03 09:35 | 2019-11-03 09:35 | Yes | 257 |  |  | 2019-11-09 09:37 | [5 empty] | 2019-11-09 09:37 | Yes | -8
VD-9001-108-DWG-020 | 7 | COLUMNS DEATAIL | PR-108 | Farabard | 2019-02-26 15:20 |  |  | No | 479 | [9 empty] | No | 0
VD-9001-257C-ITP-004 | 3 | INSPECTION & TESTING PLAN (4137-0367/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:03 | 2019-02-12 17:26 | 2019-02-12 17:26 | Yes | 0 |  |  | 2019-02-17 16:32 | [5 empty] | 2019-02-17 16:32 | Yes | -9 | 1204-Owner-v | 2020-01-01 10:36
VD-9001-257C-PCJ-002 | 2 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:03 | 2019-02-12 17:40 | 2019-02-12 17:45 | Yes | 0 |  |  | 2019-02-17 16:34 | [5 empty] | 2019-02-17 16:34 | Yes | -9
VD-9001-257C-DWG-003 | 4 | NAME PLATE DET.DWG (4137-0364/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:03 | 2019-02-12 18:31 | 2019-02-12 18:31 | Yes | 0 |  |  | 2019-02-13 18:06 | [5 empty] | 2019-02-13 18:06 | Yes | -13
VD-9001-257C-DWG-009 | 4 | NAME PLATE DET.DWG (4137-0365/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:32 | 2019-02-12 18:32 | Yes | 0 |  |  | 2019-02-13 18:04 | [5 empty] | 2019-02-13 18:04 | Yes | -13
VD-9001-257C-DWG-015 | 3 | NAME PLATE DET.DWG (4137-0366/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:32 | 2019-02-12 18:32 | Yes | 0 |  |  | 2019-02-13 18:03 | [5 empty] | 2019-02-13 18:03 | Yes | -13
VD-9001-257C-DWG-021 | 4 | NAME PLATE DET.DWG (4137-0367/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:33 | 2019-02-12 18:33 | Yes | 0 |  |  | 2019-02-13 10:16 | [5 empty] | 2019-02-13 10:16 | Yes | -13
VD-9001-257C-DWG-027 | 3 | NAME PLATE DET.DWG (4137-0368/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:34 | 2019-02-12 18:34 | Yes | 0 |  |  | 2019-02-13 15:50 | [5 empty] | 2019-02-13 15:50 | Yes | -13 | 1204-Owner-v | 2020-02-09 11:28
VD-9001-257C-DWG-033 | 3 | NAME PLATE DET.DWG (4137-0369/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:34 | 2019-02-12 18:35 | Yes | 0 |  |  | 2019-02-13 15:48 | [5 empty] | 2019-02-13 15:48 | Yes | -13 | 1204-Owner-v | 2020-02-09 11:29
VD-9001-257C-DWG-037 | 3 | NAME PLATE DET.DWG (4137-0370/A1) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:35 | 2019-02-12 18:35 | Yes | 0 |  |  | 2019-02-13 15:46 | [5 empty] | 2019-02-13 15:46 | Yes | -13 | 1204-Owner-v | 2020-02-09 11:31
VD-9001-257C-DWG-043 | 3 | NAME PLATE DET.DWG (4137-0370/A2) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:36 | 2019-02-12 18:36 | Yes | 0 |  |  | 2019-02-13 15:45 | [5 empty] | 2019-02-13 15:45 | Yes | -13 | 1204-Owner-v | 2020-02-09 11:30
VD-9001-257C-DWG-046 | 3 | NAME PLATE DET.DWG (4137-0371/A) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-12 17:04 | 2019-02-12 18:36 | 2019-02-12 18:36 | Yes | 0 |  |  | 2019-02-13 15:43 | [5 empty] | 2019-02-13 15:43 | Yes | -13 | 1204-Owner-v | 2020-02-09 11:32
VD-9001-257B-DWG-018 | 1 | BUNDLE DETAIL FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2019-02-13 15:19 | 2019-02-13 16:07 | 2019-02-13 16:07 | Yes | 0 |  |  | 2019-02-16 17:02 | [5 empty] | 2019-02-16 17:02 | Yes | -11
VD-9001-254-DWG-330 | 4 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2019-02-18 | 2019-04-07 12:44 | 2019-04-07 12:44 | Yes | 48 |  |  |  | 2019-05-07 09:18 |  |  |  |  | 2019-05-07 09:18 | Yes | 16 | 1204-Owner-v | 2019-10-15 11:23
VD-9001-257C-DWG-014 | 4 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-24 | 2019-06-07 12:34 | 2019-06-07 12:38 | Yes | 103 |  |  | 2019-08-24 15:31 | [5 empty] | 2019-08-24 15:31 | Yes | 64
VD-9001-257B-NPL-034 | 1 | WELDING DOCUMENT (WPS,PQR) | HM-257B | FATEH SANAT KIMIA | 2019-02-24 | 2019-11-24 14:14 | 2019-11-24 14:36 | Yes | 273 |  |  |  |  | 2019-12-03 10:29 |  |  |  | 2019-12-03 10:29 | Yes | -5
VD-9001-257B-DWG-020 | 3 | GENERAL ARRANGEMENT DRAWING FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2019-02-24 | 2019-03-09 11:33 | 2019-03-09 11:38 | Yes | 13 |  |  | 2019-04-30 11:39 | [5 empty] | 2019-04-30 11:39 | Yes | 38 | 1204-Owner-v | 2019-12-15 13:34
VD-9001-257B-DWG-011 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-02-24 | 2019-03-03 16:59 | 2019-03-03 16:59 | Yes | 7 |  |  |  |  | 2019-04-30 15:56 |  |  |  | 2019-04-30 15:56 | Yes | 44
VD-9001-257C-DWG-020 | 4 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-25 | 2019-06-07 12:34 | 2019-06-07 12:40 | Yes | 102 |  |  | 2019-08-24 11:52 | [5 empty] | 2019-08-24 11:52 | Yes | 64
VD-9001-257B-DWG-023 | 3 | GENERAL ARRANGEMENT DRAWING FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2019-02-25 | 2019-03-03 14:39 | 2019-03-03 14:40 | Yes | 6 |  |  | 2019-03-12 11:50 | [5 empty] | 2019-03-12 11:50 | Yes | -5 | 1204-Owner-v | 2019-07-02 08:19
VD-9001-251-PFD-001 | 2 | PROCESS FLOW DIAGRAM | HM-251 | KT – Kinetics Technology SpA | 2019-02-26 |  |  | No | 479 | [9 empty] | No | 0
VD-9001-257C-GAD-006 | 4 | GENERAL ARRANGEMENT (4137-0369) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-25 | 2019-03-19 17:15 | 2019-03-19 17:17 | Yes | 22 |  |  | 2019-05-22 09:44 | [5 empty] | 2019-05-22 09:44 | Yes | 50 | 1204-Owner-v | 2019-05-10 09:12
VD-9001-254-ISO-501 | 1 | HIGH PRESSURE STEAM LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-02-22 |  |  | No | 483 | [9 empty] | No | 0
VD-9001-254-ISO-503 | 1 | HIGH PRESSURE STEAM LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-254-ISO-507 | 1 | LP STEAM OUTLET FROM FDF TURBINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-254-ISO-508 | 1 | LP STEAM OUTLET FROM FDF TURBINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-254-ISO-512 | 1 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF MAIN STEAM SAFETY VALVE (BOILER 6) | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-254-ISO-511 | 1 | ISOMETRIC DRAWING FOR EXHAUST PIPE OF MAIN STEAM SAFETY VALVE (BOILER 5) | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-204D-CAL-036 | 2 | CALCULATION FOR EXTERNAL ATTACHMENT AND CLIPS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-02-21 | 2019-02-22 17:36 | 2019-02-22 17:36 | Yes | 1 |  |  | 2019-02-26 15:03 | [5 empty] | 2019-02-26 15:03 | Yes | -10
VD-9001-257C-GAD-003 | 4 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-26 | 2019-06-07 12:36 | 2019-06-07 12:36 | Yes | 101 |  |  | 2019-11-20 10:03 | [5 empty] | 2019-11-20 10:03 | Yes | 152 | 1204-Owner-v | 2019-07-02 08:36
VD-9001-257C-GAD-004 | 4 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-26 | 2019-06-07 12:37 | 2019-06-12 17:13 | Yes | 101 |  |  |  | 2019-08-24 11:01 |  |  |  |  | 2019-08-24 11:01 | Yes | 64 | 1204-Owner-v | 2019-07-02 08:37
VD-9001-257B-DWG-014 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2019-02-26 | 2019-03-03 14:09 | 2019-03-03 14:11 | Yes | 5 |  |  | 2019-05-06 09:55 | [5 empty] | 2019-05-06 09:55 | Yes | 50 | 1204-Owner-v | 2019-12-15 13:33
VD-9001-254-DWG-215 | 2 | CONNECTION & TERMINATION DWG | HM-254 | AZAR AB | 2019-02-23 |  |  | No | 482 | [9 empty] | No | 0
VD-9001-254-PPL-318 | 7 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2019-02-23 | 2019-03-18 10:47 | 2019-03-18 10:48 | Yes | 23 |  |  | 2019-04-22 09:52 | [5 empty] | 2019-04-22 09:52 | Yes | 21 | 1204-Owner-v | 2019-05-13 09:15
VD-9001-254-DWG-222 | 2 | CABLE TRENCH LAYOUT | HM-254 | AZAR AB | 2019-02-23 | 2019-03-17 14:25 | 2019-03-17 14:26 | Yes | 22 |  |  |  | 2019-05-05 10:51 |  |  |  |  | 2019-05-05 10:51 | Yes | 35
VD-9001-201A-DWG-020 | 4 | GENERAL ASSEMBLY - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-02-26 | 2019-04-24 14:47 | 2019-04-24 14:48 | Yes | 57 |  |  | 2019-04-27 11:04 | [5 empty] | 2019-04-27 11:04 | Yes | -11 | 1204-Owner-v | 2019-12-15 13:28
VD-9001-201A-DWG-002 | 4 | GENERAL ASSEMBLY- R1001 | PV-201A | FATEH SANAT KIMIA | 2019-02-26 | 2019-04-24 14:46 | 2019-04-24 14:47 | Yes | 57 |  |  | 2019-04-27 11:03 | [5 empty] | 2019-04-27 11:03 | Yes | -11 | 1204-Owner-v | 2019-12-15 13:25
VD-9001-257B-DWG-017 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2019-02-27 | 2019-03-12 15:54 | 2019-03-12 15:54 | Yes | 13 |  |  |  |  | 2019-05-08 12:20 |  |  |  | 2019-05-08 12:20 | Yes | 43
VD-9001-257B-CAL-019 | 2 | CALCULATION BOOK FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2019-02-27 | 2019-03-12 15:59 | 2019-03-12 15:59 | Yes | 13 |  |  | 2019-05-11 09:10 | [5 empty] | 2019-05-11 09:10 | Yes | 46
VD-9001-257B-DWG-005 | 2 | GENERAL ARRANGEMENT DRAWING FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2019-02-27 | 2019-03-13 09:25 | 2019-03-13 09:25 | Yes | 14 |  |  | 2019-04-30 11:32 | [5 empty] | 2019-04-30 11:32 | Yes | 34 | 1204-Owner-v | 2019-12-15 13:33
VD-9001-251-LST-010 | 2 | PROJECT DOCUMENTS LIST | HM-251 | KT – Kinetics Technology SpA | 2019-02-28 |  |  | No | 477 | [9 empty] | No | 0
VD-9001-251-DWG-664 | 1 | Heat Exchanger Costruction Drawing (including Nameplate dwg.) (LOS) | HM-251 | KT – Kinetics Technology SpA | 2019-02-28 |  |  | No | 477 | [9 empty] | No | 0
VD-9001-257C-GAD-005 | 4 | GENERAL ARRANGEMENT (4137-0368) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-27 | 2019-03-19 17:15 | 2019-03-19 17:17 | Yes | 20 |  |  | 2019-05-22 09:42 | [5 empty] | 2019-05-22 09:42 | Yes | 50 | 1204-Owner-v | 2019-05-10 09:11
VD-9001-231B-DWG-0025 | 3 | Ladder and platform Arrangment D-6201 | PV-231B | Fars Ghaleb | 2019-03-06 19:59 | 2019-05-13 11:03 | 2019-05-13 11:03 | Yes | 68 |  |  | 2019-05-14 09:57 |  |  |  | 2019-05-13 10:48 | 2019-05-13 10:48 | 2019-05-14 09:57 | Yes | -13
VD-9001-231B-DWG-0026 | 3 | Ladder and platform Detail D-6201 | PV-231B | Fars Ghaleb | 2019-03-06 19:59 | 2019-05-13 11:04 | 2019-05-13 11:04 | Yes | 68 |  |  | 2019-05-14 09:58 |  |  |  | 2019-05-13 10:52 | 2019-05-13 10:52 | 2019-05-14 09:58 | Yes | -13
VD-9001-257C-PCJ-002 | 3 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2019-02-23 09:51 | 2019-02-25 13:33 | 2019-02-25 13:33 | Yes | 2 |  |  |  |  | 2019-04-14 09:44 |  |  |  | 2019-04-14 09:44 | Yes | 34
VD-9001-743B-GAD-231B001 | 0 | Grating Arrangement Drawing for Dearator DA-4001 | ST-743B | Arak Rail | 2019-02-25 | 2019-02-25 08:38 | 2019-02-25 08:38 | Yes | 0 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:57
VD-9001-743B-GAD-231B002 | 0 | Grating Arrangement Drawing for D-1002 | ST-743B | Arak Rail | 2019-02-25 | 2019-02-25 08:40 | 2019-02-25 08:40 | Yes | 0 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:58
VD-9001-743B-GAD-231B003 | 0 | Grating Arrangement Drawing for D-1003 | ST-743B | Arak Rail | 2019-02-25 | 2019-02-25 08:40 | 2019-02-25 08:41 | Yes | 0 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:59
VD-9001-743B-GAD-231B004 | 0 | Grating Arrangement Drawing for D-3006 | ST-743B | Arak Rail | 2019-02-25 | 2019-02-25 08:42 | 2019-02-25 08:42 | Yes | 0 | [9 empty] | No | 466 | 1204-Owner-v | 2019-02-28 23:03
VD-9001-743B-GAD-231B005 | 0 | Grating Arrangement Drawing for D-3007 | ST-743B | Arak Rail | 2019-02-25 | 2019-02-25 08:43 | 2019-02-25 08:43 | Yes | 0 | [9 empty] | No | 466 | 1204-Owner-v | 2019-03-02 09:59
VD-9001-254-MNL-310 | 2 | INSTRUCTION MANUAL FOR O2 GAS ANALYZERS | HM-254 | AZAR AB | 2019-02-24 10:12 | 2019-02-24 10:36 | 2019-02-24 10:36 | Yes | 0 |  |  | 2019-03-13 11:32 | [5 empty] | 2019-03-13 11:32 | Yes | 3 | 1204-Owner-v | 2019-09-22 14:51
VD-9001-254-CAT-308 | 1 | OUTLINE DRAWING & SPECIFICATION SHEETS FOR O2 GAS ANALYZERS | HM-254 | AZAR AB | 2019-02-24 10:13 | 2019-02-24 10:36 | 2019-02-24 10:36 | Yes | 0 |  |  | 2019-04-15 15:04 | [5 empty] | 2019-04-15 15:04 | Yes | 36 | 1204-Owner-v | 2019-09-22 14:48
VD-9001-251-PCU-660 | 0 | Performance Curve (TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:01 | 2019-02-24 12:01 | Yes | 0 |  |  |  |  | 2020-02-09 14:04 |  |  |  | 2020-02-09 14:04 | Yes | 336
VD-9001-251-PCU-661 | 0 | Performance Curve (TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:01 | 2019-02-24 12:01 | Yes | 0 |  |  |  |  | 2020-02-09 14:03 |  |  |  | 2020-02-09 14:03 | Yes | 336
VD-9001-251-PID-661 | 0 | Piping & Instrumentation Diagram (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:02 | 2019-02-24 12:02 | Yes | 0 |  |  |  |  | 2019-06-09 15:45 |  |  |  | 2019-06-09 15:45 | Yes | 91 | 1204-Owner-v | 2019-06-10 10:24
VD-9001-251-PID-660 | 0 | Piping & Instrumentation Diagram (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:01 | 2019-02-24 12:01 | Yes | 0 |  |  |  |  | 2019-06-09 15:00 |  |  |  | 2019-06-09 15:00 | Yes | 91 | 1204-Owner-v | 2019-06-10 10:23
VD-9001-251-DSH-686 | 0 | Eqpt filled-in data sheets | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:00 | 2019-02-24 12:00 | Yes | 0 |  |  |  |  | 2020-02-09 14:08 |  |  |  | 2020-02-09 14:08 | Yes | 336
VD-9001-251-DSH-689 | 0 | Eqpt filled-in data sheets | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 12:00 | 2019-02-24 12:00 | Yes | 0 |  |  |  |  | 2020-02-09 14:07 |  |  |  | 2020-02-09 14:07 | Yes | 336
VD-9001-251-DSH-664 | 0 | Turbines Data Sheet (TUR | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 11:59 | 2019-02-24 11:59 | Yes | 0 |  |  |  |  | 2020-02-04 09:44 |  |  |  | 2020-02-04 09:44 | Yes | 331
VD-9001-251-DSH-663 | 0 | Turbines Data Sheet (TUR | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 11:59 | 2019-02-24 11:59 | Yes | 0 |  |  |  |  | 2020-02-09 14:05 |  |  |  | 2020-02-09 14:05 | Yes | 336
VD-9001-251-DSH-667 | 0 | 'Auxilliaries Data Sheets & Pump performance curve Only for Lube Oil pump, Heat Exchanger & Filter (LOS) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 11:59 | 2019-02-24 11:59 | Yes | 0 |  |  |  |  | 2020-02-09 14:09 |  |  |  | 2020-02-09 14:09 | Yes | 336 | 1204-Owner-v | 2019-04-07 14:08
VD-9001-251-DSH-668 | 0 | 'Auxilliaries Data Sheets & Pump performance curve Only for Lube Oil pump, Heat Exchanger & Filter (LOS) | HM-251 | KT – Kinetics Technology SpA | 2019-02-24 | 2019-02-24 11:59 | 2019-02-24 12:00 | Yes | 0 |  |  |  |  | 2020-02-09 14:10 |  |  |  | 2020-02-09 14:10 | Yes | 336 | 1204-Owner-v | 2019-04-07 14:08
VD-9001-201A-ANL-050 | 1 | F.E.A. FOR NOZZLES - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-02-24 14:51 | 2019-02-24 14:56 | 2019-02-24 14:56 | Yes | 0 |  |  |  | 2019-08-28 17:36 |  |  |  |  | 2019-08-28 17:36 | Yes | 171
VD-9001-201A-CAL-048 | 2 | CALCULATION BOOK - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-02-24 14:51 | 2019-02-24 14:56 | 2019-02-24 14:56 | Yes | 0 |  |  | 2019-03-11 11:23 | [5 empty] | 2019-03-11 11:23 | Yes | 1
VD-9001-201A-DWG-004 | 0 | INTERNAL DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-02-25 | 2019-02-24 14:56 | 2019-02-24 14:56 | Yes | -1 |  |  |  | 2019-02-26 11:06 |  |  |  |  | 2019-02-26 11:06 | Yes | -12
VD-9001-201A-DWG-022 | 0 | INTERNAL DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-02-25 | 2019-02-24 14:57 | 2019-02-24 14:57 | Yes | -1 |  |  |  | 2019-02-26 11:07 |  |  |  |  | 2019-02-26 11:07 | Yes | -12
VD-9001-202F-DWG-033 | 0 | Fire Proofing Steelwork | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2019-02-25 | 2019-02-24 16:09 | 2019-02-24 16:09 | Yes | -1 |  |  |  |  | 2019-03-03 16:06 |  |  |  | 2019-03-03 16:06 | Yes | -7 | 1204-Owner-v | 2019-05-11 08:38
VD-9001-201B-CAL-002 | 1 | REFRACTORY DOME CALCULATION (4134-0359/RDC) | PV-201B | Brembana & Rolle S.p.A. | 2019-02-26 09:25 | 2019-02-26 11:06 | 2019-02-26 11:06 | Yes | 0 |  |  |  | 2019-03-19 18:59 |  |  |  |  | 2019-03-19 20:59 | Yes | 7
VD-9001-201B-DWG-022 | 1 | REFRACTORY LINING REFORMER R-1004 - DOME BRICKS (4134-0359/RF6) | PV-201B | Brembana & Rolle S.p.A. | 2019-02-26 09:26 | 2019-02-26 11:12 | 2019-02-26 11:12 | Yes | 0 |  |  |  | 2019-02-27 10:39 |  |  |  |  | 2019-02-27 20:00 | Yes | -13 | 1204-Owner-v | 2019-04-22 09:17
VD-9001-201A-DWG-004 | 1 | INTERNAL DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-03-05 | 2019-03-12 11:35 | 2019-03-12 11:35 | Yes | 7 |  |  | 2019-04-23 16:25 | [5 empty] | 2019-04-23 16:25 | Yes | 28 | 1204-Owner-v | 2020-01-22 11:31
VD-9001-201A-DWG-022 | 1 | INTERNAL DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-03-05 | 2019-03-12 11:36 | 2019-03-12 11:36 | Yes | 7 |  |  | 2019-04-23 16:26 | [5 empty] | 2019-04-23 16:26 | Yes | 28
VD-9001-201B-DWG-022 | 2 | REFRACTORY LINING REFORMER R-1004 - DOME BRICKS (4134-0359/RF6) | PV-201B | Brembana & Rolle S.p.A. | 2019-03-13 20:00 | 2019-03-11 11:58 | 2019-03-11 11:58 | Yes | -2 |  |  | 2019-03-19 19:03 | [5 empty] | 2019-03-19 21:00 | Yes | -6
VD-9001-202F-DWG-033 | 1 | Fire Proofing Steelwork | PV-202F | ARVOS SCHMIDTSCHE SCHACK | 2019-03-10 |  |  | No | 467 | [9 empty] | No | 0
VD-9001-204B-DIS-001 | 5 | Vendor Print Index & Schedule | PV-204B | ABAN AIR COOLER. | 2019-03-03 16:19 | 2019-03-04 07:13 | 2019-03-04 07:13 | Yes | 1 |  |  | 2019-05-13 11:16 | [5 empty] | 2019-05-13 20:58 | Yes | 56 | 1204-Owner-v | 2019-05-28 10:23
VD-9001-201B-DSH-003 | 2 | REFRACTORY DATA SHEET (4134-0359/RDS) | PV-201B | Brembana & Rolle S.p.A. | 2019-03-17 20:00 | 2019-05-20 19:04 | 2019-05-20 19:04 | Yes | 64 |  |  | 2019-06-30 15:09 | [5 empty] | 2019-06-30 20:57 | Yes | 27 | 1204-Owner-v | 2019-05-23 07:20
VD-9001-257B-DWG-008 | 3 | GENERAL ARRANGEMENT DRAWING FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2019-03-05 09:10 | 2019-03-05 11:45 | 2019-03-05 11:46 | Yes | 0 |  |  | 2019-03-06 14:37 | [5 empty] | 2019-03-06 14:37 | Yes | -13 | 1204-Owner-v | 2019-06-16 12:47
VD-9001-257B-DWG-009 | 3 | BUNDLE DETAIL FOR E-1011 | HM-257B | FATEH SANAT KIMIA | 2019-03-05 09:10 | 2019-03-05 11:48 | 2019-03-05 11:49 | Yes | 0 |  |  | 2019-03-06 14:27 | [5 empty] | 2019-03-06 14:27 | Yes | -13
VD-9001-254-ISO-522 | 1 | FUEL GAS LINE (BOILER 6) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-03-10 |  |  | No | 467 | [9 empty] | No | 0
VD-9001-257B-DWG-012 | 2 | BUNDLE DETAIL FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-03-05 09:10 | 2019-03-05 11:53 | 2019-03-05 11:53 | Yes | 0 |  |  | 2019-03-06 11:55 | [5 empty] | 2019-03-06 11:55 | Yes | -13
VD-9001-257B-DWG-015 | 2 | BUNDLE DETAIL FOR E-2003 A/B | HM-257B | FATEH SANAT KIMIA | 2019-03-05 09:11 | 2019-03-05 11:56 | 2019-03-05 11:57 | Yes | 0 |  |  | 2019-03-06 11:51 | [5 empty] | 2019-03-06 11:51 | Yes | -13
VD-9001-257B-DWG-024 | 3 | BUNDLE DETAIL FOR E-3007 | HM-257B | FATEH SANAT KIMIA | 2019-03-05 09:11 | 2019-03-05 12:01 | 2019-03-05 12:02 | Yes | 0 |  |  | 2019-03-06 11:46 | [5 empty] | 2019-03-06 11:46 | Yes | -13
VD-9001-254-ISO-521 | 1 | FUEL GAS LINE (BOILER 5) ISOMETRIC DWG | HM-254 | AZAR AB | 2019-03-10 |  |  | No | 467 | [9 empty] | No | 0
VD-9001-204B-CAL-001 | 3 | Strength Calculation Book D-1002 | PV-204B | ABAN AIR COOLER. | 2019-03-05 15:27 | 2019-03-06 08:18 | 2019-03-06 08:19 | Yes | 1 |  |  |  | 2019-03-18 15:46 |  |  |  |  | 2019-03-18 21:00 | Yes | -2
VD-9001-204B-CAL-002 | 5 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2019-03-05 15:27 | 2019-03-06 08:19 | 2019-03-06 08:20 | Yes | 1 |  |  |  | 2019-03-18 15:52 |  |  |  |  | 2019-03-18 21:00 | Yes | -2
VD-9001-204B-CAL-004 | 4 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2019-03-05 15:27 | 2019-03-06 08:20 | 2019-03-06 08:21 | Yes | 1 |  |  |  | 2019-03-18 15:55 |  |  |  |  | 2019-03-18 21:00 | Yes | -2
VD-9001-254-ISO-524 | 1 | ISOMETRIC DWG. FOR PILOT GAS LINE ( BOILER 6) | HM-254 | AZAR AB | 2019-03-10 |  |  | No | 467 | [9 empty] | No | 0
VD-9001-254-ISO-523 | 1 | ISOMETRIC DWG. FOR PILOT GAS LINE ( BOILER 5) | HM-254 | AZAR AB | 2019-03-11 |  |  | No | 466 | [9 empty] | No | 0
VD-9001-201B-DWG-025 | 0 | LADDER AND PLATFORM DWG. (4134-0359/6) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-03-07 | 2019-03-06 16:24 | 2019-03-06 16:24 | Yes | -1 |  |  |  | 2019-03-11 17:46 |  |  |  |  | 2019-03-11 20:00 | Yes | -9
VD-9001-201B-DWG-026 | 0 | LADDER AND PLATFORM DWG. (4134-0359/7) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-03-07 | 2019-03-06 16:25 | 2019-03-06 16:29 | Yes | -1 |  |  |  | 2019-03-11 17:48 |  |  |  |  | 2019-03-11 20:00 | Yes | -9
VD-9001-201B-DWG-027 | 0 | LADDER AND PLATFORM DWG. (4134-0359/8) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-03-07 | 2019-03-06 16:29 | 2019-03-06 16:29 | Yes | -1 |  |  |  | 2019-03-11 17:42 |  |  |  |  | 2019-03-11 20:00 | Yes | -9
VD-9001-257B-CAL-013 | 3 | CALCULATION BOOK FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-03-14 | 2019-05-06 10:52 | 2019-05-06 10:53 | Yes | 53 |  |  | 2019-05-06 15:06 | [5 empty] | 2019-05-06 15:06 | Yes | -14 | 1204-Owner-v | 2019-10-02 16:12
VD-9001-257B-CAL-022 | 3 | CALCULATION BOOK FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2019-03-07 11:04 | 2019-03-09 11:30 | 2019-03-09 11:30 | Yes | 2 |  |  | 2019-04-17 17:38 | [5 empty] | 2019-04-17 17:38 | Yes | 25
VD-9001-204D-DWG-050 | 0 | ERECTION ASSEMBLY FOR PAD FOR D-2003 | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 | 2019-03-11 13:38 | 2019-03-11 13:38 | Yes | 2 |  |  | 2019-04-13 09:21 | [5 empty] | 2019-04-13 09:21 | Yes | 19 | 1204-Owner-v | 2019-04-06 14:47
VD-9001-204D-DWG-051 | 0 | HANDRAILS FOR D-2003 | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 | 2019-03-11 13:40 | 2019-03-11 13:40 | Yes | 2 |  |  | 2019-04-13 09:22 | [5 empty] | 2019-04-13 09:22 | Yes | 19 | 1204-Owner-v | 2019-05-11 08:02
VD-9001-204D-DWG-052 | 0 | HANDRAILS FOR D-2003 | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 | 2019-03-11 13:42 | 2019-03-11 13:42 | Yes | 2 |  |  | 2019-04-13 09:23 | [5 empty] | 2019-04-13 09:23 | Yes | 19 | 1204-Owner-v | 2019-05-11 08:02
VD-9001-204D-DWG-053 | 0 | SAFETY BAR FOR D-2003 | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 | 2019-03-11 13:45 | 2019-03-11 13:45 | Yes | 2 |  |  | 2019-04-13 09:25 | [5 empty] | 2019-04-13 09:25 | Yes | 19 | 1204-Owner-v | 2019-05-11 08:03
VD-9001-204D-DWG-004 | 4 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 09:53 | 2019-03-11 13:50 | 2019-03-11 13:50 | Yes | 2 |  |  |  | 2019-04-16 14:02 |  |  |  |  | 2019-04-16 14:03 | Yes | 22
VD-9001-204D-DWG-008 | 2 | DEMISTER DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-09 09:53 | 2019-03-11 13:53 | 2019-03-11 13:54 | Yes | 2 |  |  | 2019-03-12 11:41 | [5 empty] | 2019-03-12 11:41 | Yes | -13 | 1204-Owner-v | 2019-04-06 14:47
VD-9001-254-DIG-320 | 3 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2019-03-12 | 2019-03-10 14:40 | 2019-03-10 14:41 | Yes | -2 |  |  |  | 2019-03-10 16:55 |  |  |  |  | 2019-03-10 16:55 | Yes | -14
VD-9001-204B-DWG-005 | 7 | Ladder & Platform Drawing D-1002 | PV-204B | ABAN AIR COOLER. | 2019-03-10 16:43 | 2019-03-11 08:57 | 2019-03-11 08:57 | Yes | 1 |  |  | 2019-03-18 16:02 | [5 empty] | 2019-03-18 21:00 | Yes | -7 | 1204-Owner-v | 2019-03-23 15:28
VD-9001-204B-DWG-006 | 5 | Ladder & Platform Drawing D-1003 | PV-204B | ABAN AIR COOLER. | 2019-03-10 16:43 | 2019-03-11 09:13 | 2019-03-11 09:13 | Yes | 1 |  |  | 2019-03-18 16:50 | [5 empty] | 2019-03-18 21:00 | Yes | -7 | 1204-Owner-v | 2020-04-29 08:12
VD-9001-204B-DWG-007 | 6 | Ladder & Platform Drawing D-3006 | PV-204B | ABAN AIR COOLER. | 2019-03-10 16:43 | 2019-03-12 10:35 | 2019-03-12 10:37 | Yes | 2 |  |  | 2019-03-18 16:54 | [5 empty] | 2019-03-18 21:00 | Yes | -8 | 1204-Owner-v | 2020-04-29 08:13
VD-9001-204B-DWG-008 | 4 | Ladder & Platform Drawing D-3007 | PV-204B | ABAN AIR COOLER. | 2019-03-10 16:43 | 2019-03-12 15:01 | 2019-03-12 15:01 | Yes | 2 |  |  | 2019-05-12 17:20 | [5 empty] | 2019-05-12 20:58 | Yes | 47 | 1204-Owner-v | 2020-04-29 08:14
VD-9001-254-DIG-320 | 4 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2019-03-12 | 2019-03-16 08:58 | 2019-03-16 08:58 | Yes | 4 |  |  |  | 2019-04-22 09:54 |  |  |  |  | 2019-04-22 09:54 | Yes | 23
VD-9001-201A-DWG-005 | 1 | NAME PLATE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-03-18 | 2019-03-13 15:46 | 2019-03-13 15:46 | Yes | -5 |  |  |  | 2019-05-20 15:34 |  |  |  |  | 2019-05-20 15:34 | Yes | 54
VD-9001-201A-DWG-023 | 1 | NAME PLATE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-03-18 | 2019-03-13 15:47 | 2019-03-13 15:47 | Yes | -5 |  |  |  | 2019-05-20 15:35 |  |  |  |  | 2019-05-20 15:35 | Yes | 54
VD-9001-201A-DWG-041 | 1 | NAME PLATE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-03-18 | 2019-03-13 15:48 | 2019-03-13 15:48 | Yes | -5 |  |  |  | 2019-05-20 15:35 |  |  |  |  | 2019-05-20 15:35 | Yes | 54
VD-9001-204C-DWG-010 | 2 | SHIPPING DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-03-25 20:00 | 2019-04-08 18:41 | 2019-04-08 18:42 | Yes | 14 |  |  | 2019-04-09 15:15 | [5 empty] | 2019-04-09 20:59 | Yes | -13
VD-9001-201B-DWG-025 | 1 | LADDER AND PLATFORM DWG. (4134-0359/6) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-03-25 20:00 | 2019-04-19 17:48 | 2019-04-19 17:48 | Yes | 25 |  |  |  | 2019-04-22 17:14 |  |  |  |  | 2019-04-22 20:59 | Yes | -11
VD-9001-204D-DWG-009 | 3 | NAME PLATE DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-03-13 | 2019-04-17 18:07 | 2019-04-17 18:08 | Yes | 35 |  |  | 2019-04-18 07:55 | [5 empty] | 2019-04-18 07:55 | Yes | -13
VD-9001-254-LST-217 | 6 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2019-03-16 | 2019-03-18 11:11 | 2019-03-18 11:11 | Yes | 2 |  |  |  | 2019-04-22 09:55 |  |  |  |  | 2019-04-22 09:55 | Yes | 21
VD-9001-257B-DWG-006 | 2 | BUNDLE DETAIL FOR E-1006 | HM-257B | FATEH SANAT KIMIA | 2019-03-13 11:38 | 2019-03-13 16:18 | 2019-03-13 16:18 | Yes | 0 |  |  | 2019-03-14 11:56 | [5 empty] | 2019-03-14 11:56 | Yes | -13
VD-9001-257B-DWG-021 | 3 | BUNDLE DETAIL FOR E-3006 | HM-257B | FATEH SANAT KIMIA | 2019-03-13 11:38 | 2019-03-13 13:09 | 2019-03-13 13:09 | Yes | 0 |  |  | 2019-03-18 19:19 | [5 empty] | 2019-03-18 19:19 | Yes | -9
VD-9001-251-PPL-024 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-03-13 14:39 | 2019-03-13 14:42 | 2019-03-13 14:42 | Yes | 0 |  |  |  | 2019-04-27 16:51 |  |  |  |  | 2019-04-27 16:51 | Yes | 31
VD-9001-251-PPL-025 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-03-13 14:39 | 2019-03-13 14:43 | 2019-03-13 14:43 | Yes | 0 |  |  |  | 2019-04-27 16:53 |  |  |  |  | 2019-04-27 16:53 | Yes | 31
VD-9001-251-PPL-026 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-03-13 14:39 | 2019-03-13 14:43 | 2019-03-13 14:43 | Yes | 0 |  |  | 2019-04-27 16:54 | [5 empty] | 2019-04-27 16:54 | Yes | 31 | 1204-Owner-v | 2020-06-12 10:19
VD-9001-251-PPL-028 | 0 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-03-13 | 2019-03-13 14:55 | 2019-03-13 14:55 | Yes | 0 |  |  | 2019-04-27 16:55 | [5 empty] | 2019-04-27 16:55 | Yes | 31 | 1204-Owner-v | 2020-06-13 07:41
VD-9001-254-ISO-596 | 0 | ISOMERTRIC DWG. FOR FUEL OIL LINE (BOILER A) | HM-254 | AZAR AB | 2019-03-16 | 2019-03-17 15:49 | 2019-03-17 15:49 | Yes | 1 |  |  |  | 2019-04-09 09:38 |  |  |  |  | 2019-04-09 09:38 | Yes | 9
VD-9001-254-ISO-597 | 0 | ISOMERTRIC DWG. FOR FUEL OIL LINE (BOILER B) | HM-254 | AZAR AB | 2019-03-16 | 2019-03-17 15:50 | 2019-03-17 15:50 | Yes | 1 |  |  |  | 2019-04-09 09:41 |  |  |  |  | 2019-04-09 09:41 | Yes | 9
VD-9001-254-ISO-598 | 0 | ISOMETRIC DWG.FOR COOLING WATER SUPPLY FOR SAMPLING UNIT (BOILER A) | HM-254 | AZAR AB | 2019-03-16 | 2019-04-30 12:20 | 2019-04-30 12:28 | Yes | 45 |  |  |  | 2019-05-11 10:21 |  |  |  |  | 2019-05-11 10:21 | Yes | -3
VD-9001-254-ISO-599 | 0 | ISOMETRIC DWG.FOR COOLING WATER SUPPLY FOR SAMPLING UNIT (BOILER B) | HM-254 | AZAR AB | 2019-03-16 | 2019-04-30 12:28 | 2019-04-30 12:28 | Yes | 45 |  |  |  | 2019-05-11 10:17 |  |  |  |  | 2019-05-11 10:17 | Yes | -3
VD-9001-254-ISO-606 | 0 | ISOMERTIC DWG. FOR COOLING WATER RETURN FROM SMAPLING UNIT (BOILER A) | HM-254 | AZAR AB | 2019-03-16 | 2019-04-30 12:28 | 2019-04-30 12:28 | Yes | 45 |  |  |  | 2019-05-11 10:19 |  |  |  |  | 2019-05-11 10:19 | Yes | -3
VD-9001-254-ISO-607 | 0 | ISOMERTIC DWG. FOR COOLING WATER RETURN FROM SMAPLING UNIT (BOILERB) | HM-254 | AZAR AB | 2019-03-16 | 2019-04-30 12:28 | 2019-04-30 12:28 | Yes | 45 |  |  |  | 2019-05-11 10:16 |  |  |  |  | 2019-05-11 10:16 | Yes | -3
VD-9001-254-LST-301 | 7 | I/O LIST & I/O ASSIGNMENT FOR CONTROL SYSTEM | HM-254 | AZAR AB | 2019-03-16 09:50 | 2019-03-16 15:05 | 2019-03-16 15:06 | Yes | 0 |  |  | 2019-04-22 09:48 | [5 empty] | 2019-04-22 09:48 | Yes | 23 | 1204-Owner-v | 2019-12-09 08:28
VD-9001-204B-CAL-001 | 4 | Strength Calculation Book D-1002 | PV-204B | ABAN AIR COOLER. | 2019-04-01 21:00 | 2019-04-17 11:52 | 2019-04-17 11:53 | Yes | 16 |  |  | 2019-05-04 09:44 | [5 empty] | 2019-05-04 20:59 | Yes | 3 | 1204-Owner-v | 2020-04-29 07:58
VD-9001-204B-CAL-002 | 6 | Strength Calculation Book D-1003 | PV-204B | ABAN AIR COOLER. | 2019-04-01 21:00 | 2019-04-17 11:55 | 2019-04-17 11:55 | Yes | 16 |  |  | 2019-05-04 09:42 | [5 empty] | 2019-05-04 20:59 | Yes | 3 | 1204-Owner-v | 2020-04-29 07:59
VD-9001-204B-CAL-004 | 5 | Strength Calculation Book D-3007 | PV-204B | ABAN AIR COOLER. | 2019-04-01 21:00 | 2019-04-17 12:00 | 2019-04-17 12:00 | Yes | 16 |  |  | 2019-05-04 09:21 | [5 empty] | 2019-05-04 20:59 | Yes | 3 | 1204-Owner-v | 2020-04-29 08:00
VD-9001-254-ISO-590 | 1 | ISOMETRIC DRAWING FOR ATOMIZING STEAM LINE (BOILER A) | HM-254 | AZAR AB | 2019-03-24 |  |  | No | 453 | [9 empty] | No | 0
VD-9001-254-ISO-591 | 1 | ISOMETRIC DRAWING FOR ATOMIZING STEAM LINE (BOILER B) | HM-254 | AZAR AB | 2019-03-24 |  |  | No | 453 | [9 empty] | No | 0
VD-9001-201B-CAL-002 | 2 | REFRACTORY DOME CALCULATION (4134-0359/RDC) | PV-201B | Brembana & Rolle S.p.A. | 2019-04-02 20:59 | 2019-05-20 18:57 | 2019-05-20 18:57 | Yes | 48 |  |  | 2019-05-30 13:20 | [5 empty] | 2019-05-30 20:58 | Yes | -4
VD-9001-257C-DWG-056 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0368/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:20 | 2019-04-08 11:20 | 2019-04-08 11:20 | Yes | 2 |  |  | 2019-04-10 10:19 | [5 empty] | 2019-04-10 10:19 | Yes | -12 | 1204-Owner-v | 2019-05-10 09:26
VD-9001-257C-DWG-057 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4137-0369/BMN) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:20 | 2019-04-08 11:21 | 2019-04-08 11:21 | Yes | 2 |  |  | 2019-04-10 10:18 | [5 empty] | 2019-04-10 10:18 | Yes | -12 | 1204-Owner-v | 2019-05-10 09:25
VD-9001-257C-LST-001 | 1 | COMMISSIONING & START-UP S.P.LIST (4137/SPL1) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:20 | 2019-04-08 11:22 | 2019-04-08 11:22 | Yes | 2 |  |  | 2019-04-17 17:05 | [5 empty] | 2019-04-17 17:05 | Yes | -5 | 1204-Owner-v | 2019-05-10 09:11
VD-9001-257C-PCJ-004 | 2 | POST WELD HEAT TREATMENT PROCEDURE (4137/PWHT) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:53 | 2019-04-08 11:23 | 2019-04-08 11:24 | Yes | 2 |  |  | 2019-04-17 15:50 | [5 empty] | 2019-04-17 15:50 | Yes | -5
VD-9001-257C-PCJ-011 | 1 | LOCAL POST-WELD HEAT TREATMENT PROCEDURE(4137/LPWHT) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:53 | 2019-04-08 11:25 | 2019-04-08 11:25 | Yes | 2 |  |  | 2019-04-17 15:52 | [5 empty] | 2019-04-17 15:52 | Yes | -5
VD-9001-257C-WBK-001 | 2 | WELDING BOOK (4137-0364/W) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:54 | 2019-04-08 11:26 | 2019-04-08 11:27 | Yes | 2 |  |  |  | 2019-04-21 10:43 |  |  |  |  | 2019-04-21 10:43 | Yes | -1
VD-9001-257C-LST-004 | 1 | MASTER & DETAILED PACKING LIST (4137/PL) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-06 10:54 | 2019-04-08 11:22 | 2019-04-08 11:22 | Yes | 2 |  |  |  | 2019-04-13 16:27 |  |  |  |  | 2019-04-13 16:27 | Yes | -9 | 1204-Owner-v | 2019-05-10 09:12
VD-9001-204D-CAL-050 | 2 | PLATFORM STRUCTURAL ANALYSIS CALCULATION REPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-10 | 2019-04-11 12:23 | 2019-04-11 12:23 | Yes | 1 |  |  |  | 2019-05-06 08:07 |  |  |  |  | 2019-05-06 08:07 | Yes | 11
VD-9001-254-ISO-596 | 1 | ISOMERTRIC DWG. FOR FUEL OIL LINE (BOILER A) | HM-254 | AZAR AB | 2019-04-13 |  |  | No | 433 | [9 empty] | No | 0
VD-9001-254-ISO-597 | 1 | ISOMERTRIC DWG. FOR FUEL OIL LINE (BOILER B) | HM-254 | AZAR AB | 2019-04-13 |  |  | No | 433 | [9 empty] | No | 0
VD-9001-201B-LST-001 | 3 | COMMISSIONING & START-UP S.P.LIST (4134/SPL1) | PV-201B | Brembana & Rolle S.p.A. | 2019-04-24 20:59 | 2020-05-29 19:12 | 2020-05-29 19:12 | Yes | 401 |  |  | 2020-06-07 14:31 | [5 empty] | 2020-06-07 20:03 | Yes | -5
VD-9001-201B-LST-002 | 2 | 2 YEARS OPERATION S.P.LIST (4134/SPL2) | PV-201B | Brembana & Rolle S.p.A. | 2019-04-24 20:59 | 2020-06-18 19:17 | 2020-06-18 19:17 | Yes | 421 | [9 empty] | No | -13
VD-9001-204D-DWG-039 | 2 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-15 |  |  | No | 431 | [9 empty] | No | 0
VD-9001-204D-DWG-033 | 2 | LADDER & PLATFORM DETAILS DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-14 |  |  | No | 432 | [9 empty] | No | 0
VD-9001-251-DWG-033 | 2 | FLOOR PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:18 | 2019-04-13 09:18 | Yes | 0 |  |  | 2019-07-06 16:03 | [5 empty] | 2019-07-06 16:03 | Yes | 70 | 1204-Owner-v | 2020-04-25 16:51
VD-9001-251-DWG-034 | 2 | ARCH PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:21 | 2019-04-13 09:21 | Yes | 0 |  |  | 2019-04-27 15:02 | [5 empty] | 2019-04-27 15:02 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:51
VD-9001-251-DWG-035 | 4 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:21 | 2019-04-13 09:21 | Yes | 0 |  |  | 2019-05-08 14:13 | [5 empty] | 2019-05-08 14:13 | Yes | 11 | 1204-Owner-v | 2020-04-25 16:51
VD-9001-251-DWG-036 | 4 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:22 | 2019-04-13 09:22 | Yes | 0 |  |  | 2019-05-08 14:15 | [5 empty] | 2019-05-08 14:15 | Yes | 11 | 1204-Owner-v | 2020-04-25 16:51
VD-9001-251-DWG-037 | 3 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:22 | 2019-04-13 09:22 | Yes | 0 |  |  | 2019-05-08 14:16 | [5 empty] | 2019-05-08 14:16 | Yes | 11 | 1204-Owner-v | 2020-04-25 16:52
VD-9001-251-DWG-038 | 3 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:23 | 2019-04-13 09:23 | Yes | 0 |  |  | 2019-05-08 14:18 | [5 empty] | 2019-05-08 14:18 | Yes | 11 | 1204-Owner-v | 2020-04-25 16:52
VD-9001-204D-DWG-041 | 2 | PLATFORM | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-14 |  |  | No | 432 | [9 empty] | No | 0
VD-9001-251-DWG-039 | 3 | PLAN AND PLATFORMS TOS El+…. | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:23 | 2019-04-13 09:23 | Yes | 0 |  |  | 2019-05-19 15:53 | [5 empty] | 2019-05-19 15:53 | Yes | 22 | 1204-Owner-v | 2020-04-25 16:52
VD-9001-251-DWG-040 | 3 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:11 | 2019-04-13 09:23 | 2019-04-13 09:23 | Yes | 0 |  |  | 2019-05-19 15:54 | [5 empty] | 2019-05-19 15:54 | Yes | 22 | 1204-Owner-v | 2020-04-25 16:52
VD-9001-251-DWG-042 | 5 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:24 | 2019-04-13 09:24 | Yes | 0 |  |  | 2019-05-19 15:55 | [5 empty] | 2019-05-19 15:55 | Yes | 22 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-043 | 2 | GENERAL ARRANGEMENT STAIRS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:24 | 2019-04-13 09:24 | Yes | 0 |  |  | 2019-05-19 15:56 | [5 empty] | 2019-05-19 15:56 | Yes | 22 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-044 | 2 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:27 | 2019-04-13 09:27 | Yes | 0 |  |  | 2019-04-27 15:04 | [5 empty] | 2019-04-27 15:04 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-045 | 2 | VERTICAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:27 | 2019-04-13 09:27 | Yes | 0 |  |  | 2019-04-27 15:06 | [5 empty] | 2019-04-27 15:06 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-046 | 2 | HORIZONTAL CONVECTION END TUBESHEETS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:27 | 2019-04-13 09:27 | Yes | 0 |  |  | 2019-04-27 15:08 | [5 empty] | 2019-04-27 15:08 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-047 | 1 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:12 | 2019-04-13 09:27 | 2019-04-13 09:27 | Yes | 0 |  |  | 2019-04-27 15:10 | [5 empty] | 2019-04-27 15:10 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-048 | 1 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:28 | 2019-04-13 09:28 | Yes | 0 |  |  | 2019-04-27 15:11 | [5 empty] | 2019-04-27 15:11 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:54
VD-9001-251-DWG-049 | 1 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:28 | 2019-04-13 09:28 | Yes | 0 |  |  | 2019-04-27 15:13 | [5 empty] | 2019-04-27 15:13 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:54
VD-9001-251-DWG-050 | 4 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:28 | 2019-04-13 09:28 | Yes | 0 |  |  | 2019-04-27 15:15 | [5 empty] | 2019-04-27 15:15 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:27
VD-9001-251-DWG-051 | 4 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:29 | 2019-04-13 09:29 | Yes | 0 |  |  | 2019-04-27 15:16 | [5 empty] | 2019-04-27 15:16 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:27
VD-9001-251-DWG-052 | 4 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:29 | 2019-04-13 09:29 | Yes | 0 |  |  |  | 2019-04-27 11:35 |  |  |  |  | 2019-04-27 11:35 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:27
VD-9001-251-DWG-053 | 2 | MAIN COMBUSTION AIR DUCTS LAYOUT | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:13 | 2019-04-13 09:29 | 2019-04-13 09:29 | Yes | 0 |  |  | 2019-04-27 11:38 | [5 empty] | 2019-04-27 11:38 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:54
VD-9001-251-DWG-055 | 2 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:14 | 2019-04-13 09:30 | 2019-04-13 09:30 | Yes | 0 |  |  | 2019-04-27 11:56 | [5 empty] | 2019-04-27 11:56 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:27
VD-9001-251-DWG-056 | 2 | COMBUSTION AIR DUCT POST FIRING BURNERS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:14 | 2019-04-13 09:30 | 2019-04-13 09:30 | Yes | 0 |  |  | 2019-04-27 14:11 | [5 empty] | 2019-04-27 14:11 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:31
VD-9001-251-DWG-057 | 1 | COMBUSTION AIR DUCT TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:14 | 2019-04-13 09:31 | 2019-04-13 09:31 | Yes | 0 |  |  | 2019-04-27 14:13 | [5 empty] | 2019-04-27 14:13 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:28
VD-9001-251-DWG-058 | 1 | COMBUSTION AIR DUCT TUNNEL BURNERS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:14 | 2019-04-13 09:31 | 2019-04-13 09:31 | Yes | 0 |  |  | 2019-04-27 14:14 | [5 empty] | 2019-04-27 14:14 | Yes | 0 | 1204-Owner-v | 2019-04-15 08:28
VD-9001-251-DWG-059 | 2 | COLD AIR - PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:15 | 2019-04-13 09:31 | 2019-04-13 09:31 | Yes | 0 |  |  | 2019-04-27 14:17 | [5 empty] | 2019-04-27 14:17 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:55
VD-9001-251-DWG-060 | 2 | COLD AIR - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:15 | 2019-04-13 09:31 | 2019-04-13 09:31 | Yes | 0 |  |  | 2019-04-27 14:19 | [5 empty] | 2019-04-27 14:19 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:56
VD-9001-251-DWG-061 | 2 | FLUE GAS DUCTS - Convection - APH | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 09:15 | 2019-04-13 09:32 | 2019-04-13 09:32 | Yes | 0 |  |  | 2019-04-27 14:22 | [5 empty] | 2019-04-27 14:22 | Yes | 0 | 1204-Owner-v | 2019-08-15 14:28
VD-9001-204D-DWG-049 | 2 | GRATINGS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-14 |  |  | No | 432 | [9 empty] | No | 0
VD-9001-251-DWG-062 | 2 | FLUE GAS DUCTS - APH to FAN - PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:26 | 2019-04-13 10:26 | Yes | 0 |  |  | 2019-04-27 15:18 | [5 empty] | 2019-04-27 15:18 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:56
VD-9001-251-DWG-063 | 2 | FLUE GAS DUCTS - APH to FAN - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:26 | 2019-04-13 10:26 | Yes | 0 |  |  | 2019-04-27 15:20 | [5 empty] | 2019-04-27 15:20 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:56
VD-9001-251-DWG-065 | 2 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:26 | 2019-04-13 10:26 | Yes | 0 |  |  | 2019-04-27 15:22 | [5 empty] | 2019-04-27 15:22 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:56
VD-9001-251-DWG-067 | 2 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:27 | 2019-04-13 10:27 | Yes | 0 |  |  | 2019-04-13 17:05 | [5 empty] | 2019-04-13 17:05 | Yes | -14 | 1204-Owner-v | 2019-07-21 09:18
VD-9001-251-DWG-068 | 2 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:27 | 2019-04-13 10:27 | Yes | 0 |  |  | 2019-04-13 16:58 | [5 empty] | 2019-04-13 16:58 | Yes | -14 | 1204-Owner-v | 2019-07-21 09:19
VD-9001-251-DWG-069 | 2 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:27 | 2019-04-13 10:27 | Yes | 0 |  |  | 2019-04-13 16:47 | [5 empty] | 2019-04-13 16:47 | Yes | -14 | 1204-Owner-v | 2019-07-21 09:20
VD-9001-251-DWG-070 | 2 | REFORMER - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:27 | 2019-04-13 10:27 | Yes | 0 |  |  | 2019-04-13 16:49 | [5 empty] | 2019-04-13 16:49 | Yes | -14 | 1204-Owner-v | 2019-07-21 09:20
VD-9001-251-DWG-071 | 1 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:27 | 2019-04-13 10:27 | Yes | 0 |  |  | 2019-04-27 15:47 | [5 empty] | 2019-04-27 15:47 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:58
VD-9001-251-DWG-072 | 1 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:16 | 2019-04-13 10:28 | 2019-04-13 10:28 | Yes | 0 |  |  | 2019-04-27 15:48 | [5 empty] | 2019-04-27 15:48 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:58
VD-9001-251-DWG-073 | 2 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:17 | 2019-04-13 10:28 | 2019-04-13 10:28 | Yes | 0 |  |  | 2019-04-27 15:50 | [5 empty] | 2019-04-27 15:50 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:58
VD-9001-251-DWG-074 | 3 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:17 | 2019-04-13 10:28 | 2019-04-13 10:28 | Yes | 0 |  |  | 2019-04-27 15:53 | [5 empty] | 2019-04-27 15:53 | Yes | 0 | 1204-Owner-v | 2019-09-01 15:21
VD-9001-251-DWG-075 | 3 | PENTHOUSE PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:17 | 2019-04-13 10:28 | 2019-04-13 10:28 | Yes | 0 |  |  | 2019-04-27 15:54 | [5 empty] | 2019-04-27 15:54 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:59
VD-9001-251-DWG-076 | 3 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:17 | 2019-04-13 10:28 | 2019-04-13 10:29 | Yes | 0 |  |  | 2019-04-27 15:58 | [5 empty] | 2019-04-27 15:58 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:59
VD-9001-251-DWG-077 | 3 | PENTHOUSE ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:17 | 2019-04-13 10:29 | 2019-04-13 10:29 | Yes | 0 |  |  | 2019-04-27 15:59 | [5 empty] | 2019-04-27 15:59 | Yes | 0 | 1204-Owner-v | 2020-04-25 16:59
VD-9001-251-DWG-111 | 2 | COMBUSTION AIR DUCTS STEELWORK SUPPORT | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:18 | 2019-04-13 10:29 | 2019-04-13 10:29 | Yes | 0 |  |  | 2019-04-27 16:06 | [5 empty] | 2019-04-27 16:06 | Yes | 0 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-114 | 1 | VERTICAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:30 | 2019-04-13 10:30 | Yes | 0 |  |  | 2019-04-27 16:12 | [5 empty] | 2019-04-27 16:12 | Yes | 0 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-115 | 1 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:30 | 2019-04-13 10:30 | Yes | 0 |  |  | 2019-04-27 16:13 | [5 empty] | 2019-04-27 16:13 | Yes | 0 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-116 | 1 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:30 | 2019-04-13 10:30 | Yes | 0 |  |  | 2019-04-27 16:14 | [5 empty] | 2019-04-27 16:14 | Yes | 0 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-117 | 1 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:31 | 2019-04-13 10:31 | Yes | 0 |  |  | 2019-04-27 16:16 | [5 empty] | 2019-04-27 16:16 | Yes | 0 | 1204-Owner-v | 2020-04-25 17:20
VD-9001-251-DWG-118 | 1 | HORIZONTAL CONVECTION HEADER BOXES AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:31 | 2019-04-13 10:31 | Yes | 0 |  |  | 2019-04-13 17:02 | [5 empty] | 2019-04-13 17:02 | Yes | -14 | 1204-Owner-v | 2020-04-25 17:20
VD-9001-251-DWG-119 | 2 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:31 | 2019-04-13 10:31 | Yes | 0 |  |  | 2019-04-13 16:52 | [5 empty] | 2019-04-13 16:52 | Yes | -14 | 1204-Owner-v | 2020-04-25 18:30
VD-9001-251-DWG-120 | 2 | CONVECTION SECTION - STEEL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:31 | 2019-04-13 10:31 | Yes | 0 |  |  | 2019-04-13 17:00 | [5 empty] | 2019-04-13 17:00 | Yes | -14 | 1204-Owner-v | 2020-04-25 18:30
VD-9001-251-DWG-121 | 2 | STEELWORK SUPPORT AL. A – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:31 | 2019-04-13 10:32 | Yes | 0 |  |  | 2019-04-27 16:21 | [5 empty] | 2019-04-27 16:21 | Yes | 0 | 1204-Owner-v | 2019-05-08 14:45
VD-9001-251-DWG-122 | 2 | STEELWORK SUPPORT AL. 12 – GENERAL ARRANGEMENT | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:19 | 2019-04-13 10:32 | 2019-04-13 10:32 | Yes | 0 |  |  | 2019-04-27 16:23 | [5 empty] | 2019-04-27 16:23 | Yes | 0 | 1204-Owner-v | 2020-04-25 18:31
VD-9001-251-DWG-123 | 2 | STEELWORK SUPPORT AL. 12 – DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:20 | 2019-04-13 10:32 | 2019-04-13 10:32 | Yes | 0 |  |  | 2019-04-27 16:30 | [5 empty] | 2019-04-27 16:30 | Yes | 0 | 1204-Owner-v | 2019-06-10 16:49
VD-9001-251-DWG-124 | 2 | GENERAL ARRANGEMENT ALIGNMENTS “R-S” | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:20 | 2019-04-13 10:32 | 2019-04-13 10:32 | Yes | 0 |  |  | 2019-04-27 16:31 | [5 empty] | 2019-04-27 16:31 | Yes | 0 | 1204-Owner-v | 2019-04-15 09:15
VD-9001-251-DWG-125 | 2 | GENERAL ARRANGEMENT ALIGNMENTS “17-18-19” | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:20 | 2019-04-13 10:32 | 2019-04-13 10:32 | Yes | 0 |  |  | 2019-04-27 16:33 | [5 empty] | 2019-04-27 16:33 | Yes | 0 | 1204-Owner-v | 2020-04-25 18:31
VD-9001-251-DWG-127 | 2 | FAN AND FROM FAN TO STACK - DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:20 | 2019-04-13 10:33 | 2019-04-13 10:33 | Yes | 0 |  |  | 2019-04-13 16:54 | [5 empty] | 2019-04-13 16:54 | Yes | -14 | 1204-Owner-v | 2019-07-21 08:55
VD-9001-251-DWG-135 | 1 | Convection section – steel details | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:20 | 2019-04-13 10:33 | 2019-04-13 10:33 | Yes | 0 |  |  | 2019-04-13 16:56 | [5 empty] | 2019-04-13 16:56 | Yes | -14 | 1204-Owner-v | 2020-04-25 18:34
VD-9001-251-PPL-001 | 4 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:40 | 2019-04-13 10:40 | Yes | 0 |  |  |  | 2019-07-06 16:01 |  |  |  |  | 2019-07-06 16:01 | Yes | 70 | 1204-Owner-v | 2020-05-20 11:20
VD-9001-251-PPL-002 | 4 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:40 | 2019-04-13 10:40 | Yes | 0 |  |  | 2019-06-15 11:28 | [5 empty] | 2019-06-15 11:28 | Yes | 49 | 1204-Owner-v | 2020-05-12 11:01
VD-9001-251-PPL-003 | 4 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:40 | 2019-04-13 10:41 | Yes | 0 |  |  |  | 2019-06-15 11:30 |  |  |  |  | 2019-06-15 11:30 | Yes | 49
VD-9001-251-PPL-004 | 3 | REFORMER GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:41 | 2019-04-13 10:41 | Yes | 0 |  |  | 2019-06-15 11:31 | [5 empty] | 2019-06-15 11:31 | Yes | 49 | 1204-Owner-v | 2019-06-10 08:55
VD-9001-251-PPL-005 | 3 | REFORMER GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:41 | 2019-04-13 10:41 | Yes | 0 |  |  |  | 2019-06-15 11:27 |  |  |  |  | 2019-06-15 11:27 | Yes | 49
VD-9001-251-PPL-006 | 3 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:41 | 2019-04-13 10:41 | Yes | 0 |  |  | 2019-04-27 14:43 | [5 empty] | 2019-04-27 14:43 | Yes | 0 | 1204-Owner-v | 2020-05-12 11:07
VD-9001-251-PPL-007 | 3 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:41 | 2019-04-13 10:41 | Yes | 0 |  |  | 2019-04-27 14:45 | [5 empty] | 2019-04-27 14:45 | Yes | 0 | 1204-Owner-v | 2020-05-12 11:10
VD-9001-251-PPL-008 | 3 | VERTICAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:42 | 2019-04-13 10:42 | Yes | 0 |  |  | 2019-04-27 14:47 | [5 empty] | 2019-04-27 14:48 | Yes | 0 | 1204-Owner-v | 2020-05-12 11:12
VD-9001-251-PPL-009 | 3 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:38 | 2019-04-13 10:42 | 2019-04-13 10:42 | Yes | 0 |  |  | 2019-04-27 14:54 | [5 empty] | 2019-04-27 14:54 | Yes | 0 | 1204-Owner-v | 2020-05-12 11:14
VD-9001-251-PPL-010 | 3 | HORIZONTAL CONVECTION SECTION GENERAL ARRANGEMENT - CROSS SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 10:39 | 2019-04-13 10:42 | 2019-04-13 10:42 | Yes | 0 |  |  | 2019-04-27 14:55 | [5 empty] | 2019-04-27 14:55 | Yes | 0 | 1204-Owner-v | 2020-05-21 18:40
VD-9001-251-DWG-041 | 3 | PLAN AND PLATFORMS TOS El+…. - CONVECTION SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 14:04 | 2019-04-13 14:05 | 2019-04-13 14:05 | Yes | 0 |  |  | 2019-05-08 17:45 | [5 empty] | 2019-05-08 17:45 | Yes | 11 | 1204-Owner-v | 2020-04-25 16:53
VD-9001-251-DWG-132 | 2 | PLANS AND DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-04-13 14:08 | 2019-04-13 14:09 | 2019-04-13 14:09 | Yes | 0 |  |  | 2019-04-27 14:25 | [5 empty] | 2019-04-27 14:25 | Yes | 0 | 1204-Owner-v | 2020-04-25 18:34
VD-9001-257C-LST-004 | 2 | MASTER & DETAILED PACKING LIST (4137/PL) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 | 2019-06-24 11:22 | 2019-06-24 11:22 | Yes | 65 |  |  | 2019-06-29 12:51 |  |  |  | 2019-06-23 11:35 | 2019-06-23 11:35 | 2019-06-29 12:51 | Yes | -9 | 1204-Owner-v | 2019-06-15 16:34
VD-9001-251-CAL-020 | 1 | LIFTING CALCULATION | HM-251 | KT – Kinetics Technology SpA | 2019-04-20 |  |  | No | 426 | [9 empty] | No | 0
VD-9001-257C-PCJ-002 | 4 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-21 | 2019-04-16 13:41 | 2019-04-16 13:42 | Yes | -5 |  |  | 2019-04-21 10:45 | [5 empty] | 2019-04-21 10:45 | Yes | -9
VD-9001-204C-DWG-046 | 2 | GRATINGS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-04-16 11:28 | 2019-05-29 10:44 | 2019-05-29 10:44 | Yes | 43 |  |  | 2019-05-29 15:18 | [5 empty] | 2019-05-29 20:59 | Yes | -14
VD-9001-204D-GAD-002 | 6 | GENERAL ARRANGEMENT DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-17 | 2019-05-10 17:19 | 2019-05-10 17:19 | Yes | 23 |  |  | 2019-05-12 09:04 | [5 empty] | 2019-05-12 09:04 | Yes | -12 | 1204-Owner-v | 2019-05-11 08:02
VD-9001-204D-DWG-004 | 5 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-17 | 2019-05-10 17:22 | 2019-05-10 17:23 | Yes | 23 |  |  |  | 2019-05-18 09:42 |  |  |  |  | 2019-05-18 20:58 | Yes | -6 | 1204-Owner-v | 2019-05-11 07:59
VD-9001-204C-DWG-040 | 3 | ERECTION ASSEMBLY | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-04-16 16:10 |  |  | No | 430 | [9 empty] | No | 0
VD-9001-204C-PCJ-017 | 2 | PAINTING SPECIFICATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-04-30 20:59 | 2019-04-17 18:00 | 2019-04-17 18:00 | Yes | -13 |  |  |  | 2019-04-20 09:19 |  |  |  |  | 2019-04-20 20:59 | Yes | -11
VD-9001-204C-INR-031 | 2 | CERTIFICATION DOSSIER INDEX | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-04-17 10:22 | 2019-04-17 17:52 | 2019-04-17 17:52 | Yes | 0 |  |  |  | 2019-05-15 10:26 |  |  |  |  | 2019-05-15 20:58 | Yes | 14
VD-9001-204B-CAL-003 | 4 | Strength Calculation Book D-3006 | PV-204B | ABAN AIR COOLER. | 2019-04-17 11:28 | 2019-04-17 11:57 | 2019-04-17 11:58 | Yes | 0 |  |  | 2019-05-04 09:39 | [5 empty] | 2019-05-04 20:59 | Yes | 3 | 1204-Owner-v | 2020-04-29 07:59
VD-9001-257C-PCJ-003 | 3 | SURFACE PREPARATION AND PAINTING PROCEDURE (4137/SP) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 08:54 | 2019-04-29 11:14 | 2019-04-29 11:15 | Yes | 9 |  |  | 2019-05-19 10:03 | [5 empty] | 2019-05-19 10:03 | Yes | 6 | 1204-Owner-v | 2019-12-14 09:03
VD-9001-257C-DWG-006 | 2 | PAINTING PLAN (4137-0364/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:16 | 2019-04-29 11:17 | Yes | 9 |  |  | 2019-05-19 10:11 | [5 empty] | 2019-05-19 10:11 | Yes | 6
VD-9001-257C-DWG-012 | 3 | PAINTING PLAN (4137-0365/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:16 | 2019-04-29 11:17 | Yes | 9 |  |  | 2019-05-19 10:07 | [5 empty] | 2019-05-19 10:07 | Yes | 6
VD-9001-257C-DWG-018 | 2 | PAINTING PLAN (4137-0366/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:17 | 2019-04-29 11:18 | Yes | 9 |  |  | 2019-05-19 10:19 | [5 empty] | 2019-05-19 10:19 | Yes | 6
VD-9001-257C-DWG-024 | 2 | PAINTING PLAN (4137-0367/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:17 | 2019-04-29 11:18 | Yes | 9 |  |  | 2019-05-19 10:17 | [5 empty] | 2019-05-19 10:17 | Yes | 6 | 1204-Owner-v | 2019-05-10 10:32
VD-9001-257C-DWG-030 | 2 | PAINTING PLAN (4137-0368/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:17 | 2019-04-29 11:18 | Yes | 9 |  |  | 2019-05-19 10:15 | [5 empty] | 2019-05-19 10:15 | Yes | 6
VD-9001-257C-DWG-036 | 2 | PAINTING PLAN (4137-0369/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:18 | 2019-04-29 11:18 | Yes | 9 |  |  | 2019-05-19 10:21 | [5 empty] | 2019-05-19 10:21 | Yes | 6
VD-9001-257C-DWG-042 | 2 | PAINTING PLAN (4137-0370/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:19 | 2019-04-29 11:19 | Yes | 9 |  |  | 2019-05-19 10:22 | [5 empty] | 2019-05-19 10:22 | Yes | 6
VD-9001-257C-DWG-049 | 2 | PAINTING PLAN (4137-0371/V) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-20 10:40 | 2019-04-29 11:19 | 2019-04-29 11:19 | Yes | 9 |  |  | 2019-05-19 10:24 | [5 empty] | 2019-05-19 10:25 | Yes | 6
VD-9001-204C-PCJ-017 | 3 | PAINTING SPECIFICATION | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-04 20:59 | 2019-05-21 16:49 | 2019-05-21 16:50 | Yes | 17 |  |  | 2019-06-22 10:07 | [5 empty] | 2019-06-22 20:57 | Yes | 18
VD-9001-257C-WBK-007 | 4 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-28 | 2019-10-07 18:19 | 2019-10-07 18:20 | Yes | 162 |  |  |  |  | 2019-10-23 10:02 |  |  |  | 2019-10-23 10:02 | Yes | 2
VD-9001-257C-WBK-001 | 3 | WELDING BOOK (4137-0364/W) | HM-257C | Brembana & Rolle S.p.A. | 2019-04-28 | 2020-01-08 11:16 | 2020-01-08 11:18 | Yes | 255 |  |  | 2020-02-05 11:24 | [5 empty] | 2020-02-05 11:24 | Yes | 14
VD-9001-204D-PCJ-017 | 3 | PAINTING SPECIFICATION | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-04-22 09:04 | 2019-04-30 12:25 | 2019-04-30 12:25 | Yes | 8 |  |  | 2019-05-18 15:56 | [5 empty] | 2019-05-18 15:56 | Yes | 4
VD-9001-254-DIG-320 | 5 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2019-04-26 | 2019-04-28 09:57 | 2019-04-28 09:57 | Yes | 2 |  |  | 2019-04-30 16:02 | [5 empty] | 2019-04-30 16:02 | Yes | -12
VD-9001-254-LST-217 | 7 | WIRING LIST & CABLE ROUTH | HM-254 | AZAR AB | 2019-04-27 | 2019-04-22 15:16 | 2019-04-22 15:17 | Yes | -5 |  |  | 2019-05-05 09:25 | [5 empty] | 2019-05-05 09:25 | Yes | -1 | 1204-Owner-v | 2020-04-27 19:36
VD-9001-740B-PCJ-001 | 0 | QUALITY CONTROL PLAN | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-04-30 09:45 | 2019-04-30 09:45 | Yes | 5 |  |  |  | 2019-06-03 16:35 |  |  |  |  | 2019-06-03 16:35 | Yes | 20
VD-9001-740B-PCJ-002 | 0 | WELDING SPECIFICATION PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-04-30 09:45 | 2019-04-30 09:45 | Yes | 5 |  |  |  | 2019-06-03 16:37 |  |  |  |  | 2019-06-03 16:37 | Yes | 20
VD-9001-740B-PCJ-003 | 0 | PAINTING PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-04-30 09:46 | 2019-04-30 09:46 | Yes | 5 |  |  |  |  | 2019-06-16 08:38 |  |  |  | 2019-06-16 08:38 | Yes | 33
VD-9001-740B-PCJ-004 | 0 | LIQUID PENETRENT TEST PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-04-30 09:47 | 2019-04-30 09:47 | Yes | 5 |  |  |  | 2019-06-03 16:38 |  |  |  |  | 2019-06-03 16:38 | Yes | 20
VD-9001-740B-PCJ-005 | 0 | ULTRASONIC TEST PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-04-30 09:48 | 2019-04-30 09:48 | Yes | 5 |  |  |  | 2019-06-03 16:40 |  |  |  |  | 2019-06-03 16:40 | Yes | 20
VD-9001-740B-TEM-759 | 0 | TEKLA MODEL FOR TEMPLATE | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-05-04 10:23 | 2019-05-04 10:23 | Yes | 9 |  |  |  | 2019-05-15 11:32 |  |  |  |  | 2019-05-15 11:32 | Yes | -3
VD-9001-740B-GAD-00172 | 0 | GA DRAWINGS FOR PIPE BRIDE 1 | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-06-09 10:11 | 2019-06-09 10:20 | Yes | 45 |  |  |  |  | 2019-08-01 12:36 |  |  |  | 2019-08-01 12:36 | Yes | 39
VD-9001-740B-MOD-00172 | 0 | TEKLA MODEL FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-06-09 10:17 | 2019-06-09 10:20 | Yes | 45 |  |  |  |  | 2019-08-01 12:35 |  |  |  | 2019-08-01 12:35 | Yes | 39
VD-9001-740B-RPT-00172 | 0 | TEKLA REPORTS FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-06-09 09:45 | 2019-06-09 10:20 | Yes | 45 |  |  |  |  | 2019-08-01 12:37 |  |  |  | 2019-08-01 12:37 | Yes | 39
VD-9001-740B-SAD-00172 | 0 | ASSEMBLY DRAWINGS FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2020-02-25 14:42 | 2020-02-25 14:42 | Yes | 306 |  |  | 2020-03-02 10:35 | [5 empty] | 2020-03-02 20:00 | Yes | -8
VD-9001-740B-SPD-00172 | 0 | SINGLE PART DRAWINGS FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2020-02-11 14:25 | 2020-02-11 14:26 | Yes | 292 |  |  | 2020-03-02 10:37 | [5 empty] | 2020-03-02 20:00 | Yes | 6
VD-9001-740B-GAD-201171 | 0 | GA DRAWINGS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-05-14 16:35 | 2019-05-14 16:35 | Yes | 19 |  |  |  |  | 2019-07-25 08:13 |  |  |  | 2019-07-25 08:13 | Yes | 58
VD-9001-740B-MOD-201171 | 0 | TEKLA MODEL FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-05-14 17:04 | 2019-05-14 17:05 | Yes | 19 |  |  |  |  | 2019-07-23 16:58 |  |  |  | 2019-07-23 16:58 | Yes | 56
VD-9001-740B-RPT-201171 | 0 | TEKLA REPORTS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-05-14 16:40 | 2019-05-14 16:40 | Yes | 19 |  |  |  |  | 2019-08-01 12:36 |  |  |  | 2019-08-01 12:36 | Yes | 65
VD-9001-740B-SAD-201171 | 0 | ASSEMBLY DRAWINGS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2020-02-29 13:28 | 2020-02-29 14:07 | Yes | 310 |  |  | 2020-03-02 10:36 | [5 empty] | 2020-03-02 20:00 | Yes | -12
VD-9001-740B-SPD-201171 | 0 | SINGLE PART DRAWINGS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2020-02-29 12:33 | 2020-02-29 12:34 | Yes | 310 |  |  | 2020-03-02 10:38 | [5 empty] | 2020-03-02 20:00 | Yes | -12
VD-9001-740B-GAD-30319 | 0 | GA DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-10-12 14:16 | 2019-10-12 14:16 | Yes | 170 |  |  |  | 2019-10-24 13:07 |  |  |  |  | 2019-10-24 13:07 | Yes | -2
VD-9001-740B-MOD-30319 | 0 | TEKLA MODEL FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-10-12 14:16 | 2019-10-12 14:17 | Yes | 170 |  |  |  | 2019-10-24 11:51 |  |  |  |  | 2019-10-24 11:51 | Yes | -2
VD-9001-740B-RPT-30319 | 0 | TEKLA REPORTS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-10-12 14:36 | 2019-10-12 14:36 | Yes | 170 |  |  |  | 2019-10-24 12:59 |  |  |  |  | 2019-10-24 12:59 | Yes | -2
VD-9001-740B-SAD-30319 | 0 | ASSEMBLY DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2020-03-24 14:01 | 2020-03-24 14:04 | Yes | 334 |  |  | 2020-04-13 13:33 | [5 empty] | 2020-04-13 21:00 | Yes | 6
VD-9001-740B-SPD-30319 | 0 | SINGLE PART DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-04-25 | 2019-12-05 10:03 | 2019-12-05 10:06 | Yes | 224 |  |  |  | 2020-02-10 10:49 |  |  |  |  | 2020-02-10 20:00 | Yes | 53
VD-9001-201A-DWG-038 | 3 | GENERAL ASSEMBLY - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-05-01 | 2019-12-19 16:05 | 2019-12-19 16:05 | Yes | 232 | [9 empty] | No | 169 | 1204-Owner-v | 2020-01-20 12:46
VD-9001-201A-DWG-027 | 1 | LADDER & PLATFORM DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-05-01 |  |  | No | 415 | [9 empty] | No | 0
VD-9001-201A-DWG-009 | 1 | LADDER & PLATFORM DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-05-01 |  |  | No | 415 | [9 empty] | No | 0
VD-9001-201B-DSH-005 | 1 | THERMOCOUPLE/THERMOWELL DATA SHEET & DRAWING (4134-0359/TC) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-08 20:59 | 2019-08-26 11:35 | 2019-08-26 11:39 | Yes | 110 |  |  |  | 2019-09-16 16:33 |  |  |  |  | 2019-09-16 20:00 | Yes | 7
VD-9001-231B-DWG-0022 | 2 | Ladder and platform Detail D-4003 | PV-231B | Fars Ghaleb | 2019-04-27 10:18 | 2019-05-01 10:20 | 2019-05-01 10:25 | Yes | 4 |  |  | 2019-05-04 09:16 | [5 empty] | 2019-05-04 20:59 | Yes | -11
VD-9001-231B-DWG-0024 | 3 | Ladder and platform Detail D-4004 | PV-231B | Fars Ghaleb | 2019-04-27 10:19 | 2019-05-01 09:48 | 2019-05-01 09:56 | Yes | 4 |  |  | 2019-05-04 09:01 | [5 empty] | 2019-05-04 20:59 | Yes | -11
VD-9001-251-DWG-052 | 5 | COMBUSTION AIR DUCTS TO BURNERS G.A. & DETAILS/ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-05-04 |  |  | No | 412 | [9 empty] | No | 0
VD-9001-251-PPL-027 | 1 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-07 |  |  | No | 409 | [9 empty] | No | 0
VD-9001-251-DWG-106 | 3 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-05-11 |  |  | No | 405 | [9 empty] | No | 0
VD-9001-251-DWG-054 | 3 | MAIN COMBUSTION AIR DUCTS ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-05-04 |  |  | No | 412 | [9 empty] | No | 0
VD-9001-251-PPL-020 | 2 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-03 |  |  | No | 413 | [9 empty] | No | 0
VD-9001-251-PPL-022 | 2 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-02 |  |  | No | 414 | [9 empty] | No | 0
VD-9001-251-PPL-023 | 2 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-03 |  |  | No | 413 | [9 empty] | No | 0
VD-9001-251-PPL-024 | 2 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-08 |  |  | No | 408 | [9 empty] | No | 0
VD-9001-251-PPL-025 | 2 | PIPING LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-05-08 |  |  | No | 408 | [9 empty] | No | 0
VD-9001-251-DWG-066 | 3 | TRANSITION DUCT | HM-251 | KT – Kinetics Technology SpA | 2019-05-04 |  |  | No | 412 | [9 empty] | No | 0
VD-9001-251-DWG-107 | 3 | PIPING TIES-IN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-05-06 |  |  | No | 410 | [9 empty] | No | 0
VD-9001-257B-DWG-011 | 3 | GENERAL ARRANGEMENT DRAWING FOR E-1012 | HM-257B | FATEH SANAT KIMIA | 2019-05-07 | 2019-05-06 10:40 | 2019-05-06 10:41 | Yes | -1 |  |  | 2019-08-24 16:09 | [5 empty] | 2019-08-24 16:09 | Yes | 96 | 1204-Owner-v | 2019-05-23 08:33
VD-9001-254-DWG-222 | 3 | CABLE TRENCH LAYOUT | HM-254 | AZAR AB | 2019-05-08 | 2019-09-29 15:52 | 2019-09-29 15:53 | Yes | 144 |  |  | 2019-12-30 09:12 | [5 empty] | 2019-12-30 09:12 | Yes | 78
VD-9001-204D-CAL-050 | 3 | PLATFORM STRUCTURAL ANALYSIS CALCULATION REPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-05-07 | 2019-05-10 17:26 | 2019-05-10 17:28 | Yes | 3 |  |  | 2019-05-12 09:14 | [5 empty] | 2019-05-12 09:14 | Yes | -12
VD-9001-254-DWG-330 | 5 | GRAPHIC DISPLAYS FOR CONTROL SYSTEM & BMS | HM-254 | AZAR AB | 2019-05-11 | 2020-03-02 12:38 | 2020-03-02 12:38 | Yes | 296 |  |  | 2020-03-14 10:58 | [5 empty] | 2020-03-14 10:58 | Yes | -2
VD-9001-231B-DWG-0027 | 1 | Ladder and platform Arrangment D-6202 | PV-231B | Fars Ghaleb | 2019-05-07 10:30 | 2019-05-21 08:57 | 2019-05-21 08:57 | Yes | 14 |  |  | 2019-05-21 09:21 |  |  |  | 2019-05-12 15:15 | 2019-05-12 15:15 | 2019-05-21 09:21 | Yes | -14 | 1204-Owner-v | 2019-05-23 07:19
VD-9001-231B-DWG-0028 | 1 | Ladder and platform Detail D-6202 | PV-231B | Fars Ghaleb | 2019-05-07 10:30 | 2019-05-21 08:58 | 2019-05-21 08:58 | Yes | 14 |  |  | 2019-05-21 09:25 |  |  |  | 2019-05-11 15:35 | 2019-05-11 15:35 | 2019-05-21 09:25 | Yes | -14 | 1204-Owner-v | 2019-05-23 07:18
VD-9001-204C-DWG-010 | 3 | SHIPPING DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-08 08:59 | 2019-05-08 12:31 | 2019-05-08 12:32 | Yes | 0 |  |  | 2019-05-18 09:36 | [5 empty] | 2019-05-18 20:58 | Yes | -4 | 1204-Owner-v | 2019-05-11 07:52
VD-9001-251-ISO-001 | 1 | ISOMETRIC SKETCHES | HM-251 | KT – Kinetics Technology SpA | 2019-05-22 |  |  | No | 394 | [9 empty] | No | 0
VD-9001-257B-DWG-017 | 3 | GENERAL ARRANGEMENT DRAWING FOR E-2005 A/B | HM-257B | FATEH SANAT KIMIA | 2019-05-12 | 2019-06-08 13:47 | 2019-06-08 13:47 | Yes | 27 |  |  | 2019-06-11 16:26 | [5 empty] | 2019-06-11 16:26 | Yes | -11 | 1204-Owner-v | 2019-12-15 13:34
VD-9001-251-CAL-017 | 1 | STRESS ANALISYS CALCULATION (OUTLET SYSTEM) | HM-251 | KT – Kinetics Technology SpA | 2019-05-15 |  |  | No | 401 | [9 empty] | No | 0
VD-9001-254-DWG-965 | 0 | INSTALLATION & FAB. DWG. FOR ECO. CASING (LEFT & RIGHT) 3/4 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 14:03 | 2019-05-19 14:04 | Yes | 7 |  |  | 2019-05-20 11:16 | [5 empty] | 2019-05-20 11:16 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:03
VD-9001-254-DWG-966 | 0 | ASSEMBLY DWG. FOR ECO. CASING (BOTTOM) 4/4 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 14:06 | 2019-05-19 14:06 | Yes | 7 |  |  | 2019-05-20 11:14 | [5 empty] | 2019-05-20 11:14 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:04
VD-9001-254-DWG-967 | 0 | SHOP PRE-ASS. DWG. FOR AIR DUCT | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:16 | 2019-05-19 13:16 | Yes | 7 |  |  | 2019-05-28 08:38 | [5 empty] | 2019-05-28 08:38 | Yes | -5 | 1204-Owner-v | 2019-05-23 08:10
VD-9001-254-DWG-968 | 0 | SHOP PRE-ASSEMBLY DWG. FOR GAS DUCT | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:19 | 2019-05-19 13:19 | Yes | 7 |  |  | 2019-05-20 16:43 | [5 empty] | 2019-05-20 16:43 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:09
VD-9001-254-DWG-969 | 0 | ASSEMBLY DWG. OF EXPANSION JOINT FOR GAS DUCT (1/2) | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 14:48 | 2019-05-19 14:49 | Yes | 7 |  |  | 2019-05-20 11:10 | [5 empty] | 2019-05-20 11:10 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:02
VD-9001-254-DWG-970 | 0 | ASSEMBLY DWG. OF EXPANSION JOINT FOR GAS DUCT (2/2) | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:23 | 2019-05-19 13:23 | Yes | 7 |  |  | 2019-05-20 16:39 | [5 empty] | 2019-05-20 16:39 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:09
VD-9001-254-DWG-971 | 0 | ASSEMBLY DWG. FOR PRESS. BOSS | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:26 | 2019-05-19 13:26 | Yes | 7 |  |  | 2019-05-20 16:01 | [5 empty] | 2019-05-20 16:01 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:07
VD-9001-254-DWG-972 | 0 | ASSEMBLY DWG. FOR FUR. MANHOLE | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:29 | 2019-05-19 13:29 | Yes | 7 |  |  | 2019-05-20 15:59 | [5 empty] | 2019-05-20 15:59 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:07
VD-9001-254-DWG-973 | 0 | ASSEMBLY DWG. OF PEEP HOLE | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:32 | 2019-05-19 13:32 | Yes | 7 |  |  | 2019-05-20 15:23 | [5 empty] | 2019-05-20 15:24 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:05
VD-9001-254-DWG-974 | 0 | INSTALLATION DWG. FOR INTERNAL ATT. OF S/D (1/2) | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:20 | 2019-05-19 12:20 | Yes | 7 |  |  | 2019-05-21 11:29 | [5 empty] | 2019-05-21 11:29 | Yes | -12 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-254-DWG-975 | 0 | INSTALLATION DWG. FOR INTERNAL ATT. OF S/D (2/2) | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:21 | 2019-05-19 12:21 | Yes | 7 |  |  | 2019-05-21 11:31 | [5 empty] | 2019-05-21 11:31 | Yes | -12 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-254-DWG-976 | 0 | INSTALLATION DWG. FOR INTERNAL PIPE OF S/D 1/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:29 | 2019-05-19 12:29 | Yes | 7 |  |  | 2019-05-25 15:17 | [5 empty] | 2019-05-25 15:17 | Yes | -8 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-254-DWG-977 | 0 | INSTALLATION DWG. FOR INTERNAL PIPE OF S/D 2/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:36 | 2019-05-19 12:36 | Yes | 7 |  |  | 2019-05-25 15:19 | [5 empty] | 2019-05-25 15:20 | Yes | -8 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-254-DWG-978 | 0 | INSTALLATION DWG. FOR CHEVRON DRIERS OF S/D | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:39 | 2019-05-19 12:39 | Yes | 7 |  |  | 2019-05-25 15:24 | [5 empty] | 2019-05-25 15:24 | Yes | -8 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-254-DWG-979 | 0 | INSTALLATION & FAB. DWG. FOR ATTACH. OF W/D 1/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:41 | 2019-05-19 12:42 | Yes | 7 |  |  | 2019-05-25 15:27 | [5 empty] | 2019-05-25 15:27 | Yes | -8 | 1204-Owner-v | 2019-05-23 08:25
VD-9001-254-DWG-980 | 0 | INSTALLATION & FAB. DWG. FOR ATTACH. OF W/D 2/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:46 | 2019-05-19 12:46 | Yes | 7 |  |  | 2019-05-25 15:30 | [5 empty] | 2019-05-25 15:30 | Yes | -8 | 1204-Owner-v | 2019-05-23 08:25
VD-9001-254-DWG-981 | 0 | FABRICATION DRAWING FOR COVER PLATE (INTERNAL ATT. OF S/D) | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:51 | 2019-05-19 12:51 | Yes | 7 |  |  | 2019-05-28 08:33 | [5 empty] | 2019-05-28 08:33 | Yes | -5 | 1204-Owner-v | 2019-05-23 08:25
VD-9001-254-DWG-982 | 0 | ASSEMBLY DWG.FOR HORIZONTAL SEPARATOR | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 14:14 | 2019-05-19 14:14 | Yes | 7 |  |  | 2019-05-20 11:12 | [5 empty] | 2019-05-20 11:12 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:03
VD-9001-254-DWG-983 | 0 | V-SHAPE DRIER | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 12:58 | 2019-05-19 13:02 | Yes | 7 |  |  | 2019-05-28 08:35 | [5 empty] | 2019-05-28 08:35 | Yes | -5 | 1204-Owner-v | 2019-05-23 08:10
VD-9001-254-DWG-984 | 0 | FABRICATION DWG. FOR WATER COLUMN | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:46 | 2019-05-19 13:46 | Yes | 7 |  |  | 2019-06-23 09:17 | [5 empty] | 2019-06-23 09:17 | Yes | 21 | 1204-Owner-v | 2019-05-23 08:05
VD-9001-254-DWG-985 | 0 | FAB. DWG. FOR BASE PLATE | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:48 | 2019-05-19 13:48 | Yes | 7 |  |  | 2019-05-20 14:51 | [5 empty] | 2019-05-20 14:51 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:04
VD-9001-254-DWG-986 | 0 | FAB. DWG. FOR BASE PLATE2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:51 | 2019-05-19 13:51 | Yes | 7 |  |  | 2019-05-20 14:48 | [5 empty] | 2019-05-20 14:48 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:04
VD-9001-254-DWG-987 | 0 | DETAIL OF DUCT SUPORT | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 14:51 | 2019-05-19 14:51 | Yes | 7 |  |  | 2019-05-20 11:07 | [5 empty] | 2019-05-20 11:07 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:02
VD-9001-254-DWG-988 | 0 | FAB. INSTALL. DWG FOR AIR DUCT MANHOLE | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:56 | 2019-05-19 13:56 | Yes | 7 |  |  | 2019-05-20 14:44 | [5 empty] | 2019-05-20 14:44 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:03
VD-9001-254-DWG-989 | 0 | FAB. INSTALL. DWG FOR GAS DUCT MANHOLE | HM-254 | AZAR AB | 2019-05-12 | 2019-05-19 13:59 | 2019-05-19 13:59 | Yes | 7 |  |  | 2019-05-20 14:43 | [5 empty] | 2019-05-20 14:43 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:03
VD-9001-254-DWG-990 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & INSPECTION PLAT FORM AIR & GAS DUCT 1/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:18 | 2019-05-20 09:18 | Yes | 8 |  |  | 2019-05-28 08:42 | [5 empty] | 2019-05-28 08:42 | Yes | -6 | 1204-Owner-v | 2019-05-23 08:02
VD-9001-254-DWG-991 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 2/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:19 | 2019-05-20 09:19 | Yes | 8 |  |  |  | 2019-07-14 10:00 |  |  |  |  | 2019-07-14 10:00 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:40
VD-9001-254-DWG-992 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 3/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:19 | 2019-05-20 09:19 | Yes | 8 |  |  | 2019-07-14 14:22 | [5 empty] | 2019-07-14 14:22 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:40
VD-9001-254-DWG-993 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 4/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:20 | 2019-05-20 09:20 | Yes | 8 |  |  | 2019-07-14 14:24 | [5 empty] | 2019-07-14 14:24 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:38
VD-9001-254-DWG-994 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 5/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:21 | 2019-05-20 09:21 | Yes | 8 |  |  | 2019-07-14 14:26 | [5 empty] | 2019-07-14 14:26 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:38
VD-9001-254-DWG-995 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 6/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:21 | 2019-05-20 09:21 | Yes | 8 |  |  | 2019-07-15 11:01 | [5 empty] | 2019-07-15 11:01 | Yes | 42 | 1204-Owner-v | 2019-05-23 07:38
VD-9001-254-DWG-996 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 7/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:22 | 2019-05-20 09:22 | Yes | 8 |  |  | 2019-07-14 14:28 | [5 empty] | 2019-07-14 14:28 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-997 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT T8/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:22 | 2019-05-20 09:22 | Yes | 8 |  |  | 2019-07-14 14:29 | [5 empty] | 2019-07-14 14:29 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-998 | 0 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 9/9 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:23 | 2019-05-20 09:23 | Yes | 8 |  |  | 2019-07-14 14:31 | [5 empty] | 2019-07-14 14:31 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-999 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 1/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:39 | 2019-05-20 09:39 | Yes | 8 |  |  | 2019-05-28 17:22 | [5 empty] | 2019-05-28 17:22 | Yes | -6 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-1000 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 2/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:40 | 2019-05-20 09:40 | Yes | 8 |  |  | 2019-07-14 14:32 | [5 empty] | 2019-07-14 14:32 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-1001 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 3/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:40 | 2019-05-20 09:41 | Yes | 8 |  |  | 2019-07-14 14:35 | [5 empty] | 2019-07-14 14:35 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:36
VD-9001-254-DWG-1002 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 4/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:41 | 2019-05-20 09:41 | Yes | 8 |  |  | 2019-05-28 17:27 | [5 empty] | 2019-05-28 17:28 | Yes | -6 | 1204-Owner-v | 2019-05-23 07:37
VD-9001-254-DWG-1003 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 5/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:42 | 2019-05-20 09:42 | Yes | 8 |  |  | 2019-05-28 17:34 | [5 empty] | 2019-05-28 17:34 | Yes | -6 | 1204-Owner-v | 2019-05-23 07:35
VD-9001-254-DWG-1004 | 0 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 6/6 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:42 | 2019-05-20 09:42 | Yes | 8 |  |  | 2019-05-28 17:40 | [5 empty] | 2019-05-28 17:40 | Yes | -6 | 1204-Owner-v | 2019-05-23 07:35
VD-9001-254-DWG-1005 | 0 | ERECTION DWGS. OF AIR DUCT SUPPORT 1/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:53 | 2019-05-20 09:53 | Yes | 8 |  |  | 2019-07-14 14:37 | [5 empty] | 2019-07-14 14:37 | Yes | 41 | 1204-Owner-v | 2019-05-23 07:35
VD-9001-254-DWG-1006 | 0 | ERECTION DWGS. OF AIR DUCT SUPPORT 2/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:53 | 2019-05-20 09:53 | Yes | 8 |  |  | 2019-07-15 11:04 | [5 empty] | 2019-07-15 11:04 | Yes | 42 | 1204-Owner-v | 2019-05-23 07:35
VD-9001-254-DWG-1007 | 0 | ERECTION DWGS. FOR ECONOMIZER SUPP. 1/2 | HM-254 | AZAR AB | 2019-05-12 | 2019-05-20 09:55 | 2019-05-20 09:55 | Yes | 8 |  |  | 2019-07-15 11:06 | [5 empty] | 2019-07-15 11:06 | Yes | 42 | 1204-Owner-v | 2019-05-23 07:21
VD-9001-204D-DWG-009 | 4 | NAME PLATE DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-05-11 09:54 | 2019-05-13 12:17 | 2019-05-13 12:17 | Yes | 2 |  |  | 2019-05-14 08:30 | [5 empty] | 2019-05-14 08:30 | Yes | -13
VD-9001-204D-DWG-011 | 4 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-05-11 09:55 | 2019-05-13 12:24 | 2019-05-13 12:25 | Yes | 2 |  |  | 2019-05-14 08:32 | [5 empty] | 2019-05-14 08:32 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:28
VD-9001-204D-WMP-010 | 3 | WELDING DRAWING | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-05-11 09:55 | 2019-05-13 12:23 | 2019-05-13 12:23 | Yes | 2 |  |  | 2020-02-04 15:45 | [5 empty] | 2020-02-04 15:45 | Yes | 253 | 1204-Owner-v | 2019-05-23 08:28
VD-9001-204D-CAL-036 | 3 | CALCULATION FOR EXTERNAL ATTACHMENT AND CLIPS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-05-11 09:55 | 2019-05-13 12:21 | 2019-05-13 12:21 | Yes | 2 |  |  | 2019-05-14 08:42 | [5 empty] | 2019-05-14 08:42 | Yes | -13 | 1204-Owner-v | 2019-05-23 08:28
VD-9001-254-ISO-607 | 1 | ISOMERTIC DWG. FOR COOLING WATER RETURN FROM SMAPLING UNIT (BOILERB) | HM-254 | AZAR AB | 2019-05-15 |  |  | No | 401 | [9 empty] | No | 0
VD-9001-254-ISO-599 | 1 | ISOMETRIC DWG.FOR COOLING WATER SUPPLY FOR SAMPLING UNIT (BOILER B) | HM-254 | AZAR AB | 2019-05-15 |  |  | No | 401 | [9 empty] | No | 0
VD-9001-254-ISO-606 | 1 | ISOMERTIC DWG. FOR COOLING WATER RETURN FROM SMAPLING UNIT (BOILER A) | HM-254 | AZAR AB | 2019-05-15 |  |  | No | 401 | [9 empty] | No | 0
VD-9001-254-ISO-598 | 1 | ISOMETRIC DWG.FOR COOLING WATER SUPPLY FOR SAMPLING UNIT (BOILER A) | HM-254 | AZAR AB | 2019-05-15 |  |  | No | 401 | [9 empty] | No | 0
VD-9001-254-DWH-548 | 6 | TERMINAL POINT LIST & LOCATION OF PIPING | HM-254 | AZAR AB | 2019-05-11 14:06 | 2019-05-11 14:14 | 2019-05-11 14:15 | Yes | 0 |  |  | 2019-05-14 11:11 | [5 empty] | 2019-05-14 11:11 | Yes | -11 | 1204-Owner-v | 2019-05-23 08:29
VD-9001-201A-DWG-039 | 2 | NOZZLE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-05-22 |  |  | No | 394 | [9 empty] | No | 0
VD-9001-740B-TEM-759 | 1 | TEKLA MODEL FOR TEMPLATE | ST-740B | PETRO ADAK IRAN | 2019-05-22 | 2019-05-29 13:43 | 2019-05-29 13:43 | Yes | 7 |  |  |  | 2019-06-04 11:56 |  |  |  |  | 2019-06-04 11:56 | Yes | -8
VD-9001-204C-INR-031 | 3 | CERTIFICATION DOSSIER INDEX | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-29 20:58 | 2019-05-16 18:50 | 2019-05-16 18:50 | Yes | -13 |  |  | 2019-06-09 11:27 | [5 empty] | 2019-06-09 20:58 | Yes | 10 | 1204-Owner-v | 2019-05-23 08:26
VD-9001-204D-DWG-004 | 6 | SHELL DETAILS DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-06-01 20:58 |  | 2019-05-22 12:42 | Yes | 384 | [6 empty] | 2019-05-25 11:50 | 2019-05-25 11:50 |  | Yes | 0 | 1204-Owner-v | 2019-05-23 07:17
VD-9001-254-PPL-319 | 7 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2019-05-23 | 2019-07-10 08:07 | 2019-07-10 08:08 | Yes | 48 |  |  |  | 2019-09-01 09:27 |  |  |  |  | 2019-09-01 09:27 | Yes | 39
VD-9001-201A-PCJ-061 | 2 | PAINTING PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2020-04-27 09:15 | 2020-04-27 09:15 | Yes | 336 |  |  |  | 2020-05-06 18:08 |  |  |  |  | 2020-05-06 18:08 | Yes | -5
VD-9001-251B-RPT-060 | 0 | Reports for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-07-18 08:10 | 2019-07-18 08:10 | Yes | 61 |  |  |  | 2019-07-22 15:43 |  |  |  |  | 2019-07-22 15:43 | Yes | -10
VD-9001-251B-GAD-010 | 0 | General Arrangement DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2019-10-05 16:38 | 2019-10-05 16:48 | Yes | -7 |  |  |  | 2019-12-31 10:49 |  |  |  |  | 2019-12-31 10:49 | Yes | 73 | 1204-Owner-v | 2019-10-21 10:09
VD-9001-251B-SAD-010 | 0 | Assembly DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2019-10-05 16:51 | 2019-10-05 16:51 | Yes | -7 |  |  |  | 2019-12-31 10:48 |  |  |  |  | 2019-12-31 10:48 | Yes | 73 | 1204-Owner-v | 2019-10-21 10:22
VD-9001-251B-SPD-010 | 0 | Single Part DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2019-10-05 16:56 | 2019-10-05 16:58 | Yes | -7 |  |  |  | 2019-12-31 10:46 |  |  |  |  | 2019-12-31 10:46 | Yes | 73 | 1204-Owner-v | 2019-10-21 10:35
VD-9001-251B-RPT-010 | 0 | Reports for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2019-10-05 16:48 | 2019-10-05 16:48 | Yes | -7 |  |  |  | 2019-12-31 10:48 |  |  |  |  | 2019-12-31 10:48 | Yes | 73 | 1204-Owner-v | 2019-10-21 10:14
VD-9001-251B-GAD-011 | 0 | General Arrangement DWG for "TRANSFER LINE SUPPORT" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-011 | 0 | Assembly DWG for "TRANSFER LINE SUPPORT" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-011 | 0 | Reports for "TRANSFER LINE SUPPORT" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-020 | 0 | General Arrangement DWG for "RADIANT SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2020-03-03 15:22 | 2020-03-03 15:22 | Yes | 143 |  |  | 2020-04-07 13:40 | [5 empty] | 2020-04-07 13:40 | Yes | 21
VD-9001-251B-SAD-020 | 0 | Assembly DWG for "RADIANT SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2020-03-10 11:53 | 2020-03-10 11:53 | Yes | 150 |  |  | 2020-04-07 13:51 | [5 empty] | 2020-04-07 13:51 | Yes | 14 | 1204-Owner-v | 2020-05-02 17:27
VD-9001-251B-SPD-020 | 0 | Single Part DWG for "RADIANT SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2020-03-03 16:05 | 2020-03-03 16:05 | Yes | 143 |  |  | 2020-04-07 13:42 | [5 empty] | 2020-04-07 13:42 | Yes | 21
VD-9001-251B-RPT-020 | 0 | Reports for "RADIANT SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 | 2020-03-03 15:25 | 2020-03-03 15:25 | Yes | 143 |  |  |  | 2020-04-19 09:20 |  |  |  |  | 2020-04-19 09:20 | Yes | 33
VD-9001-251B-GAD-021 | 0 | General Arrangement DWG for "RADIANT SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-021 | 0 | Assembly DWG for "RADIANT SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-021 | 0 | Reports for "RADIANT SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-040 | 0 | General Arrangement DWG for "DUCTS & DUCTS SUPPORTS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-040 | 0 | Assembly DWG for "DUCTS & DUCTS SUPPORTS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-QCP-001 | 0 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-05-22 15:07 | 2019-05-22 15:07 | Yes | 4 |  |  |  | 2019-06-09 11:04 |  |  |  |  | 2019-06-09 11:05 | Yes | 4
VD-9001-251B-PCJ-001 | 0 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-05-22 15:01 | 2019-05-22 15:01 | Yes | 4 |  |  |  |  | 2019-06-09 14:29 |  |  |  | 2019-06-09 14:29 | Yes | 4
VD-9001-251B-PCJ-002 | 0 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-05-22 15:02 | 2019-05-22 15:02 | Yes | 4 |  |  |  | 2019-07-03 16:36 |  |  |  |  | 2019-07-03 16:36 | Yes | 28
VD-9001-251B-PCJ-003 | 0 | Welding & NDT Map | HM-251B | Bamdad Zendehroud Co. | 2019-05-21 | 2019-05-22 15:06 | 2019-05-22 15:06 | Yes | 1 |  |  |  | 2019-06-09 10:49 |  |  |  |  | 2019-06-09 10:49 | Yes | 4
VD-9001-251B-PCJ-004 | 0 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-05-25 11:53 | 2019-05-25 12:20 | Yes | 7 |  |  |  | 2019-06-15 14:17 |  |  |  |  | 2019-06-15 14:17 | Yes | 7 | 1204-Owner-v | 2019-06-02 10:47
VD-9001-251B-WPS-001 | 0 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-05-22 15:17 | 2019-05-22 15:17 | Yes | 4 |  |  |  |  | 2019-06-09 11:01 |  |  |  | 2019-06-09 11:01 | Yes | 4 | 1204-Owner-v | 2019-06-25 10:55
VD-9001-251B-LST-002 | 0 | Final Data Book Index | HM-251B | Bamdad Zendehroud Co. | 2019-09-22 |  |  | No | 271 | [9 empty] | No | 0
VD-9001-251B-FDB-001 | 0 | Final Data Book | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-079 | 0 | General Arrangement DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-11 08:43 | 2019-06-11 08:43 | Yes | 24 |  |  |  | 2019-06-15 14:34 |  |  |  |  | 2019-06-15 14:34 | Yes | -10 | 1204-Owner-v | 2019-06-25 11:06
VD-9001-251B-SAD-079 | 0 | Assembly DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-11 08:45 | 2019-06-11 08:45 | Yes | 24 |  |  | 2019-06-15 14:47 | [5 empty] | 2019-06-15 14:47 | Yes | -10 | 1204-Owner-v | 2019-07-17 13:16
VD-9001-251B-SPD-079 | 0 | Single Part DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-11 08:47 | 2019-06-11 08:53 | Yes | 24 |  |  | 2019-06-15 14:48 | [5 empty] | 2019-06-15 14:48 | Yes | -10 | 1204-Owner-v | 2019-07-17 09:53
VD-9001-251B-RPT-079 | 0 | Reports for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-11 08:43 | 2019-06-11 08:43 | Yes | 24 |  |  | 2019-06-15 14:46 | [5 empty] | 2019-06-15 14:46 | Yes | -10 | 1204-Owner-v | 2019-09-09 10:16
VD-9001-251B-GAD-080 | 0 | General Arrangement DWG for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-05-21 | 2019-06-12 07:49 | 2019-06-12 07:49 | Yes | 22 |  |  |  | 2019-06-16 15:28 |  |  | 2019-06-11 17:30 | 2019-06-11 17:30 | 2019-06-16 15:28 | Yes | -10
VD-9001-251B-SAD-080 | 0 | Assembly DWG for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-05-21 | 2019-06-12 07:50 | 2019-06-12 07:50 | Yes | 22 |  |  |  | 2019-06-16 15:36 |  |  | 2019-06-11 17:27 | 2019-06-11 17:27 | 2019-06-16 15:36 | Yes | -10
VD-9001-251B-RPT-080 | 0 | Reports for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-05-21 | 2019-06-12 07:49 | 2019-06-12 07:49 | Yes | 22 |  |  |  | 2019-06-16 15:38 |  |  | 2019-06-11 17:27 | 2019-06-11 17:27 | 2019-06-16 15:38 | Yes | -10
VD-9001-251B-GAD-060 | 0 | General Arrangement DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-12 07:51 | 2019-06-12 07:51 | Yes | 25 |  |  |  | 2019-06-16 15:09 |  |  | 2019-06-11 17:26 | 2019-06-11 17:26 | 2019-06-16 15:09 | Yes | -10
VD-9001-251B-SAD-060 | 0 | Assembly DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-07-18 08:24 | 2019-07-18 08:26 | Yes | 61 |  |  |  | 2019-07-20 11:48 |  |  |  |  | 2019-07-20 11:48 | Yes | -12
VD-9001-251B-SPD-060 | 0 | Single Part DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-05-18 | 2019-06-12 07:51 | 2019-06-12 07:51 | Yes | 25 |  |  |  | 2019-06-16 15:14 |  |  | 2019-06-11 17:24 | 2019-06-11 17:24 | 2019-06-16 15:14 | Yes | -10
VD-9001-251B-SPD-040 | 0 | Single Part DWG for "DUCTS & DUCTS SUPPORTS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-040 | 0 | Reports for "DUCTS & DUCTS SUPPORTS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-041 | 0 | General Arrangement DWG for "DUCTS & DUCTS SUPPORTS" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-041 | 0 | Assembly DWG for "DUCTS & DUCTS SUPPORTS" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-041 | 0 | Reports for "DUCTS & DUCTS SUPPORTS" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-030 | 0 | General Arrangement DWG for "CONVECTION SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-030 | 0 | Assembly DWG for "CONVECTION SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SPD-030 | 0 | Single Part DWG for "CONVECTION SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-030 | 0 | Reports for "CONVECTION SECTION" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-031 | 0 | General Arrangement DWG for "CONVECTION SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-031 | 0 | Assembly DWG for "CONVECTION SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-031 | 0 | Reports for "CONVECTION SECTION" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-050 | 0 | General Arrangement DWG for "MISC STRUCTURAL ITEMS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-050 | 0 | Assembly DWG for "MISC STRUCTURAL ITEMS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SPD-050 | 0 | Single Part DWG for "MISC STRUCTURAL ITEMS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-050 | 0 | Reports for "MISC STRUCTURAL ITEMS" | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-GAD-051 | 0 | General Arrangement DWG for "MISC STRUCTURAL ITEMS" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-SAD-051 | 0 | Assembly DWG for "MISC STRUCTURAL ITEMS" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-251B-RPT-051 | 0 | Reports for "MISC STRUCTURAL ITEMS"S GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-10-12 |  |  | No | 251 | [9 empty] | No | 0
VD-9001-201A-DWG-044 | 1 | SHIPPING AND LIFTING STYLE DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-05-27 |  |  | No | 389 | [9 empty] | No | 0
VD-9001-201A-DWG-026 | 1 | SHIPPING AND LIFTING STYLE DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2020-03-11 16:33 | 2020-03-11 16:34 | Yes | 289 |  |  |  | 2020-04-08 11:39 |  |  |  |  | 2020-04-08 11:39 | Yes | 14
VD-9001-201A-DWG-008 | 1 | SHIPPING AND LIFTING STYLE DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2020-03-11 16:31 | 2020-03-11 16:32 | Yes | 289 |  |  |  | 2020-04-08 11:41 |  |  |  |  | 2020-04-08 11:41 | Yes | 14
VD-9001-201A-DWG-005 | 2 | NAME PLATE DETAIL DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2019-08-24 12:44 | 2019-08-24 12:44 | Yes | 89 |  |  | 2019-08-26 17:28 | [5 empty] | 2019-08-26 17:28 | Yes | -12
VD-9001-201A-DWG-023 | 2 | NAME PLATE DETAIL DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2019-08-24 16:17 | 2019-08-24 16:17 | Yes | 89 |  |  | 2019-08-26 17:27 | [5 empty] | 2019-08-26 17:27 | Yes | -12
VD-9001-201A-DWG-041 | 2 | NAME PLATE DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-05-27 | 2019-08-26 16:46 | 2019-08-26 16:46 | Yes | 91 |  |  | 2019-08-26 17:26 | [5 empty] | 2019-08-26 17:26 | Yes | -14
VD-9001-254-LST-961 | 2 | CONTROL SYSTEM POWER CONSUMPTION AND HEAT DISSIPATION | HM-254 | AZAR AB | 2019-05-24 | 2020-06-15 11:41 | 2020-06-15 11:42 | Yes | 388 | [9 empty] | No | -10
VD-9001-201B-DWG-022 | 3 | REFRACTORY LINING REFORMER R-1004 - DOME BRICKS (4134-0359/RF6) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-22 09:39 | 2019-06-03 16:19 | 2019-06-03 16:19 | Yes | 12 |  |  | 2019-06-03 16:33 | [5 empty] | 2019-06-03 20:58 | Yes | -14 | 1204-Owner-v | 2019-07-21 09:24
VD-9001-204C-DWG-008 | 1 | DEMISTER & SUPPORT DRAWING with Internals & Internal attachments | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-22 09:56 | 2019-05-22 10:48 | 2019-05-22 11:00 | Yes | 0 |  |  | 2019-05-29 14:56 | [5 empty] | 2019-05-29 20:59 | Yes | -7 | 1204-Owner-v | 2019-05-23 07:18
VD-9001-201B-DWG-007 | 3 | LADDER AND PLATFORM DWG (4134-0359/3) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:48 | 2019-05-25 16:50 | 2019-05-25 16:50 | Yes | 0 |  |  | 2019-05-26 10:03 | [5 empty] | 2019-05-26 20:58 | Yes | -13 | 1204-Owner-v | 2020-04-28 09:04
VD-9001-201B-DWG-008 | 4 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:49 | 2019-05-25 16:51 | 2019-05-25 16:51 | Yes | 0 |  |  | 2019-05-26 10:01 | [5 empty] | 2019-05-26 20:58 | Yes | -13
VD-9001-201B-DWG-009 | 1 | LADDER AND PLATFORM DWG (4134-0359/5) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:49 | 2019-05-25 16:51 | 2019-05-25 16:51 | Yes | 0 |  |  | 2019-05-26 10:00 | [5 empty] | 2019-05-26 20:58 | Yes | -13
VD-9001-201B-DWG-025 | 2 | LADDER AND PLATFORM DWG. (4134-0359/6) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:49 | 2019-05-25 16:51 | 2019-05-25 16:51 | Yes | 0 |  |  | 2019-05-26 09:58 | [5 empty] | 2019-05-26 20:58 | Yes | -13
VD-9001-201B-DWG-026 | 1 | LADDER AND PLATFORM DWG. (4134-0359/7) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:49 | 2019-05-25 16:52 | 2019-05-25 16:52 | Yes | 0 |  |  | 2019-05-26 09:56 | [5 empty] | 2019-05-26 20:58 | Yes | -13
VD-9001-201B-DWG-027 | 1 | LADDER AND PLATFORM DWG. (4134-0359/8) FOR R-1004 | PV-201B | Brembana & Rolle S.p.A. | 2019-05-25 16:49 | 2019-05-25 16:52 | 2019-05-25 16:52 | Yes | 0 |  |  | 2019-05-26 09:54 | [5 empty] | 2019-05-26 20:58 | Yes | -13
VD-9001-201B-CAL-003 | 1 | HEAT TRANSFER CALCULATION (4134-0359/RHC) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-26 11:30 | 2019-05-27 13:08 | 2019-05-27 13:08 | Yes | 1 |  |  | 2019-06-30 15:12 | [5 empty] | 2019-06-30 20:57 | Yes | 20
VD-9001-201B-LST-005 | 2 | BILL OF MATERIALS R-1004 (4134-0359/RBOM) | PV-201B | Brembana & Rolle S.p.A. | 2019-05-26 11:30 | 2019-05-27 13:10 | 2019-05-27 13:10 | Yes | 1 |  |  | 2019-06-30 15:15 | [5 empty] | 2019-06-30 20:57 | Yes | 20 | 1204-Owner-v | 2019-06-01 14:22
VD-9001-204C-DWG-041 | 3 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:55 | 2019-05-28 15:57 | 2019-05-28 15:57 | Yes | 0 |  |  | 2019-05-29 15:24 | [5 empty] | 2019-05-29 20:59 | Yes | -13 | 1204-Owner-v | 2019-06-01 14:24
VD-9001-204C-DWG-042 | 1 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:55 | 2019-05-28 15:59 | 2019-05-28 15:59 | Yes | 0 |  |  | 2019-05-29 15:28 | [5 empty] | 2019-05-29 20:59 | Yes | -13 | 1204-Owner-v | 2019-05-28 17:28
VD-9001-204C-DWG-043 | 2 | HANDRAILS DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:55 | 2019-05-28 16:00 | 2019-05-28 16:00 | Yes | 0 |  |  | 2019-05-29 15:31 | [5 empty] | 2019-05-29 20:59 | Yes | -13 | 1204-Owner-v | 2019-05-28 17:26
VD-9001-204C-DWG-044 | 1 | LADDER DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:55 | 2019-05-28 16:00 | 2019-05-28 16:00 | Yes | 0 |  |  | 2019-05-29 15:34 | [5 empty] | 2019-05-29 20:59 | Yes | -13
VD-9001-204C-DWG-047 | 2 | PLATFORM DWG | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:55 | 2019-05-28 16:01 | 2019-05-28 16:01 | Yes | 0 |  |  | 2019-05-29 15:36 | [5 empty] | 2019-05-29 20:59 | Yes | -13
VD-9001-204C-DWG-035 | 4 | LADDER & PLATFORM S DWGS. | PV-204C | FBM HUDSON ITALIANA S.P.A | 2019-05-28 15:56 | 2019-05-28 15:57 | 2019-05-28 15:57 | Yes | 0 |  |  | 2019-05-29 15:21 | [5 empty] | 2019-05-29 20:59 | Yes | -13 | 1204-Owner-v | 2019-06-01 14:22
VD-9001-201B-DWG-020 | 2 | REFRACTORY LINING REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF4) | PV-201B | Brembana & Rolle S.p.A. | 2019-06-13 20:58 | 2019-06-10 11:59 | 2019-06-10 12:11 | Yes | -3 |  |  |  | 2019-06-10 18:00 |  |  |  |  | 2019-06-10 20:58 | Yes | -14
VD-9001-201B-DWG-021 | 2 | REFRACTORY ANCHORS REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF5) | PV-201B | Brembana & Rolle S.p.A. | 2019-06-13 20:58 | 2019-06-10 12:12 | 2019-06-10 12:12 | Yes | -3 |  |  |  | 2019-06-10 17:58 |  |  |  |  | 2019-06-10 20:58 | Yes | -14
VD-9001-254-PPL-348 | 1 | INSTRUMENTATION LOCATION LAYOUT | HM-254 | AZAR AB | 2019-06-05 |  |  | No | 380 | [9 empty] | No | 0
VD-9001-201A-WMP-029 | 1 | WELDING & NDT MAP - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-06-09 | 2019-11-09 14:34 | 2019-11-09 14:34 | Yes | 153 |  |  | 2019-12-26 12:32 | [5 empty] | 2019-12-26 12:32 | Yes | 33
VD-9001-201A-WMP-011 | 1 | WELDING & NDT MAP - R-1001 | PV-201A | FATEH SANAT KIMIA | 2019-06-09 | 2019-11-09 14:31 | 2019-11-09 14:32 | Yes | 153 |  |  | 2019-12-26 12:32 | [5 empty] | 2019-12-26 12:32 | Yes | 33
VD-9001-201A-WMP-047 | 1 | WELDING & NDT MAP - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-06-09 | 2019-11-09 14:37 | 2019-11-09 14:37 | Yes | 153 |  |  | 2019-12-26 12:31 | [5 empty] | 2019-12-26 12:31 | Yes | 33
VD-9001-201A-WBK-064 | 1 | WELDING DOCUMENT (WELDING MAP, WPS, PQR) - R-1001 &R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-06-09 | 2019-11-09 14:18 | 2019-11-09 14:18 | Yes | 153 |  |  | 2019-12-09 17:14 | [5 empty] | 2019-12-09 17:14 | Yes | 16
VD-9001-201A-WBK-053 | 1 | WELDING DOCUMENT (WELDING MAP, WPS, PQR) - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-06-09 | 2019-11-09 14:28 | 2019-11-09 14:29 | Yes | 153 |  |  | 2019-12-09 17:27 | [5 empty] | 2019-12-09 17:27 | Yes | 16
VD-9001-201A-DWG-006 | 1 | EXTERNAL ATTACHMENT DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-06-10 | 2019-09-01 12:48 | 2019-09-01 12:48 | Yes | 83 |  |  | 2019-10-16 15:46 | [5 empty] | 2019-10-16 15:46 | Yes | 31
VD-9001-201A-DWG-024 | 1 | EXTERNAL ATTACHMENT DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-06-10 | 2019-09-02 12:18 | 2019-09-02 12:18 | Yes | 84 |  |  | 2019-10-16 15:46 | [5 empty] | 2019-10-16 15:46 | Yes | 30
VD-9001-201A-DWG-042 | 1 | EXTERNAL ATTACHMENT DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-06-10 | 2019-09-03 14:33 | 2019-09-03 14:33 | Yes | 85 |  |  | 2019-10-16 16:15 | [5 empty] | 2019-10-16 16:15 | Yes | 29
VD-9001-740B-PCJ-001 | 1 | QUALITY CONTROL PLAN | ST-740B | PETRO ADAK IRAN | 2019-06-10 | 2019-06-08 10:16 | 2019-06-08 10:16 | Yes | -2 |  |  | 2019-09-29 15:16 | [5 empty] | 2019-09-29 15:16 | Yes | 99
VD-9001-201A-DWG-040 | 1 | INTERNAL DETAIL DRAWING - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-06-10 |  |  | No | 375 | [9 empty] | No | 0
VD-9001-740B-PCJ-002 | 1 | WELDING SPECIFICATION PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-06-10 | 2019-09-29 15:00 | 2019-09-29 15:00 | Yes | 111 |  |  |  | 2019-10-07 10:14 |  |  |  |  | 2019-10-07 10:14 | Yes | -6
VD-9001-740B-PCJ-004 | 1 | LIQUID PENETRENT TEST PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-06-10 | 2019-09-29 10:43 | 2019-09-29 10:43 | Yes | 111 |  |  | 2019-10-07 10:16 | [5 empty] | 2019-10-07 10:16 | Yes | -6
VD-9001-740B-PCJ-005 | 1 | ULTRASONIC TEST PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-06-10 | 2019-09-29 12:01 | 2019-12-26 13:53 | Yes | 111 |  |  |  | 2020-02-10 09:30 |  |  |  |  | 2020-02-10 20:00 | Yes | 120
VD-9001-740B-TEM-759 | 2 | TEKLA MODEL FOR TEMPLATE | ST-740B | PETRO ADAK IRAN | 2019-06-05 | 2019-06-08 10:17 | 2019-06-08 10:17 | Yes | 3 |  |  | 2019-06-11 16:52 | [5 empty] | 2019-06-11 16:52 | Yes | -11
VD-9001-251B-PCJ-003 | 1 | Welding & NDT Map | HM-251B | Bamdad Zendehroud Co. | 2019-06-16 | 2019-06-25 09:58 | 2019-06-25 09:58 | Yes | 9 |  |  |  | 2019-07-07 10:30 |  |  |  |  | 2019-07-07 10:30 | Yes | -2
VD-9001-251B-WPS-001 | 1 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-06-16 | 2019-07-17 08:09 | 2019-07-17 08:12 | Yes | 31 |  |  |  | 2019-07-20 10:34 |  |  |  |  | 2019-07-20 10:34 | Yes | -11 | 1204-Owner-v | 2019-07-17 13:17
VD-9001-251B-QCP-001 | 1 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-06-16 | 2019-06-25 09:58 | 2019-06-25 09:59 | Yes | 9 |  |  |  | 2019-07-07 10:31 |  |  |  |  | 2019-07-07 10:31 | Yes | -2
VD-9001-251-PCJ-001 | 2 | ERECTION PROCEDURE | HM-251 | KT – Kinetics Technology SpA | 2019-06-17 |  |  | No | 368 | [9 empty] | No | 0
VD-9001-251B-PCJ-001 | 1 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-06-16 | 2019-06-25 09:57 | 2019-06-25 09:57 | Yes | 9 |  |  |  | 2019-07-08 11:50 |  |  |  |  | 2019-07-08 11:50 | Yes | -1
VD-9001-251-PID-660 | 1 | Piping & Instrumentation Diagram (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-06-23 |  |  | No | 362 | [9 empty] | No | 0
VD-9001-251-PID-661 | 1 | Piping & Instrumentation Diagram (LOS/GB/TUR) | HM-251 | KT – Kinetics Technology SpA | 2019-06-23 |  |  | No | 362 | [9 empty] | No | 0
VD-9001-257C-LST-001 | 2 | COMMISSIONING & START-UP S.P.LIST (4137/SPL1) | HM-257C | Brembana & Rolle S.p.A. | 2019-06-10 11:03 | 2019-06-10 12:18 | 2019-06-10 12:18 | Yes | 0 |  |  | 2019-06-29 11:30 | [5 empty] | 2019-06-29 11:30 | Yes | 5
VD-9001-201B-DWG-021 | 3 | REFRACTORY ANCHORS REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF5) | PV-201B | Brembana & Rolle S.p.A. | 2019-06-24 20:58 | 2020-05-14 19:44 | 2020-05-14 19:44 | Yes | 325 |  |  | 2020-05-19 13:14 | [5 empty] | 2020-05-19 13:14 | Yes | -9
VD-9001-201B-DWG-020 | 3 | REFRACTORY LINING REFORMER R-1004 - SECTIONS AND DETAILS (4134-0359/RF4) | PV-201B | Brembana & Rolle S.p.A. | 2019-06-24 20:58 | 2019-06-27 11:17 | 2019-06-27 11:19 | Yes | 3 |  |  | 2019-06-30 14:51 | [5 empty] | 2019-06-30 20:57 | Yes | -11 | 1204-Owner-v | 2019-07-21 09:24
VD-9001-201B-DWG-001 | 6 | NOZZLE DETAIL DRAWING (4134-0359/1) | PV-201B | Brembana & Rolle S.p.A. | 2019-06-25 20:58 | 2019-06-13 17:49 | 2019-06-13 17:49 | Yes | -12 |  |  | 2019-06-26 11:38 | [5 empty] | 2019-06-26 20:57 | Yes | -1
VD-9001-251-DWG-133 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:29 | 2019-06-12 10:29 | Yes | 0 |  |  | 2019-07-21 10:37 | [5 empty] | 2019-07-21 10:37 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:34
VD-9001-251-DWG-136 | 0 | STEEL WORK SUPPORT TRANSFERLINE - GENERAL ARRANGEMENT | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:30 | 2019-06-12 10:30 | Yes | 0 |  |  | 2019-07-21 10:36 | [5 empty] | 2019-07-21 10:36 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:34
VD-9001-251-DWG-137 | 0 | STEEL WORK SUPPORT TRANSFERLINE - DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:30 | 2019-06-12 10:30 | Yes | 0 |  |  | 2019-07-21 10:34 | [5 empty] | 2019-07-21 10:34 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-138 | 0 | STEEL WORK SUPPORT TRANSFERLINE - DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:30 | 2019-06-12 10:30 | Yes | 0 |  |  | 2019-07-21 10:31 | [5 empty] | 2019-07-21 10:31 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-139 | 0 | PIPING STEEL WORK SUPPORT ON HORIZENTAL CONVECTIONS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:30 | 2019-06-12 10:30 | Yes | 0 |  |  | 2019-07-21 10:24 | [5 empty] | 2019-07-21 10:24 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-140 | 0 | PIPING STEEL WORK SUPPORT ON HORIZENTAL CONVECTIONS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:30 | 2019-06-12 10:30 | Yes | 0 |  |  | 2019-07-21 10:25 | [5 empty] | 2019-07-21 10:25 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-141 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:31 | 2019-06-12 10:31 | Yes | 0 |  |  | 2019-07-21 10:21 | [5 empty] | 2019-07-21 10:21 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-142 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:31 | 2019-06-12 10:31 | Yes | 0 |  |  | 2019-07-21 10:21 | [5 empty] | 2019-07-21 10:21 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-143 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:31 | 2019-06-12 10:31 | Yes | 0 |  |  | 2019-07-03 11:25 | [5 empty] | 2019-07-03 11:25 | Yes | 7 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-144 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:31 | 2019-06-12 10:31 | Yes | 0 |  |  | 2019-07-21 10:20 | [5 empty] | 2019-07-21 10:20 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:35
VD-9001-251-DWG-145 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:31 | 2019-06-12 10:31 | Yes | 0 |  |  | 2019-07-21 10:18 | [5 empty] | 2019-07-21 10:18 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:36
VD-9001-251-DWG-146 | 0 | MAIN HEADER ( TRANSFERLINE ) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:32 | 2019-06-12 10:32 | Yes | 0 |  |  | 2019-07-21 10:16 | [5 empty] | 2019-07-21 10:16 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:36
VD-9001-251-DWG-147 | 0 | FOUNDATION PLAN DRAWING PIPING STEEL WORK | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:32 | 2019-06-12 10:32 | Yes | 0 |  |  | 2019-07-21 10:29 | [5 empty] | 2019-07-21 10:29 | Yes | 25 | 1204-Owner-v | 2019-06-16 12:03
VD-9001-251-DWG-148 | 0 | FOUNDATIONS BASE PLATE DETAILS AND LOADINGS PIPING STEEL WORK | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 | 2019-06-12 10:32 | 2019-06-12 10:32 | Yes | 0 |  |  | 2019-07-20 14:48 | [5 empty] | 2019-07-20 14:48 | Yes | 24 | 1204-Owner-v | 2020-04-25 18:36
VD-9001-251-CAL-015 | 3 | STRUCTURAL STATICAL CALCULATONS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:56 | 2019-06-12 10:56 | Yes | 0 |  |  | 2019-07-21 11:45 | [5 empty] | 2019-07-21 11:45 | Yes | 25 | 1204-Owner-v | 2020-05-14 09:33
VD-9001-251-DWG-001 | 3 | CATALYST TUBE DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:56 | 2019-06-12 10:56 | Yes | 0 |  |  | 2019-06-15 11:34 | [5 empty] | 2019-06-15 11:34 | Yes | -11 | 1204-Owner-v | 2020-04-25 16:14
VD-9001-251-DWG-002 | 2 | INLET SYSTEM DRAWING - PLAN | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:56 | 2019-06-12 10:57 | Yes | 0 |  |  | 2019-07-03 16:19 | [5 empty] | 2019-07-03 16:19 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:15
VD-9001-251-DWG-003 | 2 | INLET SYSTEM DRAWING - ELEVATION | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:57 | 2019-06-12 10:57 | Yes | 0 |  |  | 2019-07-03 16:28 | [5 empty] | 2019-07-03 16:28 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:15
VD-9001-251-DWG-004 | 2 | INLET SYSTEM - MAIN HEADER DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:57 | 2019-06-12 10:57 | Yes | 0 |  |  | 2019-07-03 16:30 | [5 empty] | 2019-07-03 16:30 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:15
VD-9001-251-DWG-005 | 3 | OUTLET SYSTEM - GENERAL ARRANGEMENT DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:57 | 2019-06-12 10:57 | Yes | 0 |  |  | 2019-06-16 17:19 | [5 empty] | 2019-06-16 17:19 | Yes | -10 | 1204-Owner-v | 2020-04-25 16:16
VD-9001-251-DWG-006 | 2 | OUTLET SYSTEM DETAILS DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:38 | 2019-06-12 10:57 | 2019-06-12 10:57 | Yes | 0 |  |  | 2019-07-03 16:31 | [5 empty] | 2019-07-03 16:31 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:16
VD-9001-251-DWG-017 | 2 | CONVECTION COIL DRAWING & MANIFOLD HE-1001 / HE-1002 | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 10:58 | 2019-06-12 10:58 | Yes | 0 |  |  | 2019-07-06 15:32 | [5 empty] | 2019-07-06 15:32 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-018 | 3 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 10:58 | 2019-06-12 10:58 | Yes | 0 |  |  | 2019-07-06 15:04 | [5 empty] | 2019-07-06 15:05 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-019 | 3 | CONVECTION COIL DRAWING & MANIFOLD HE-1003 / HE-1004A | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 10:58 | 2019-06-12 10:58 | Yes | 0 |  |  | 2019-07-06 15:06 | [5 empty] | 2019-07-06 15:06 | Yes | 10 | 1204-Owner-v | 2019-07-02 08:09
VD-9001-251-DWG-020 | 4 | CONVECTION COIL DRAWING & MANIFOLD HE-1005 | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 10:58 | 2019-06-12 10:59 | Yes | 0 |  |  | 2019-07-06 15:07 | [5 empty] | 2019-07-06 15:07 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-025 | 2 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 11:00 | 2019-06-12 11:00 | Yes | 0 |  |  | 2019-07-03 15:52 | [5 empty] | 2019-07-03 15:52 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:49
VD-9001-251-DWG-026 | 1 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:39 | 2019-06-12 11:00 | 2019-06-12 11:00 | Yes | 0 |  |  | 2019-07-03 15:53 | [5 empty] | 2019-07-03 15:53 | Yes | 7 | 1204-Owner-v | 2020-04-25 16:50
VD-9001-251-DWG-028 | 6 | FOUNDATION LOADINGS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:40 | 2019-06-12 11:01 | 2019-06-12 11:01 | Yes | 0 |  |  | 2019-07-21 11:14 | [5 empty] | 2019-07-21 11:14 | Yes | 25 | 1204-Owner-v | 2020-05-13 15:07
VD-9001-251-DWG-029 | 4 | FOUNDATIONS BASE PLATES DETAIL | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:40 | 2019-06-12 11:01 | 2019-06-12 11:01 | Yes | 0 |  |  | 2019-07-21 11:12 | [5 empty] | 2019-07-21 11:12 | Yes | 25 | 1204-Owner-v | 2020-04-25 16:50
VD-9001-251-DWG-031 | 1 | MAIN COMPONENTS OVERALL DIMENSION | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 10:40 | 2019-06-12 11:02 | 2019-06-12 11:02 | Yes | 0 |  |  | 2019-07-06 15:19 | [5 empty] | 2019-07-06 15:19 | Yes | 10 | 1204-Owner-v | 2019-07-25 18:13
VD-9001-251-DWG-078 | 1 | FLUE GAS TUNNEL | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:21 | 2019-06-12 11:26 | 2019-06-12 11:26 | Yes | 0 |  |  | 2019-07-06 15:21 | [5 empty] | 2019-07-06 15:21 | Yes | 10 | 1204-Owner-v | 2020-04-25 16:59
VD-9001-251-DWG-080 | 1 | STACK PLAN & PLATFORMS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:21 | 2019-06-12 11:26 | 2019-06-12 11:26 | Yes | 0 |  |  | 2019-07-06 15:36 | [5 empty] | 2019-07-06 15:36 | Yes | 10 | 1204-Owner-v | 2019-07-23 09:42
VD-9001-251-DWG-099 | 2 | INSTRUMENTS CONNECTION DRAWINGS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:21 | 2019-06-12 11:29 | 2019-06-12 11:29 | Yes | 0 |  |  |  | 2019-07-13 11:11 |  |  |  |  | 2019-07-13 11:11 | Yes | 17
VD-9001-251-DWG-113 | 3 | FOUNDATIONS BASE PLATES DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:22 | 2019-06-12 11:29 | 2019-06-12 11:29 | Yes | 0 |  |  | 2019-07-21 11:09 | [5 empty] | 2019-07-21 11:09 | Yes | 25 | 1204-Owner-v | 2020-04-25 17:19
VD-9001-251-DWG-126 | 1 | STACK PLAN & PLATFORMS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:22 | 2019-06-12 11:30 | 2019-06-12 11:30 | Yes | 0 |  |  | 2019-07-03 16:39 | [5 empty] | 2019-07-03 16:39 | Yes | 7 | 1204-Owner-v | 2020-04-25 18:31
VD-9001-251-DWG-129 | 2 | Foundation base plate details (sh.7) | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:22 | 2019-06-12 11:30 | 2019-06-12 11:30 | Yes | 0 |  |  | 2019-07-21 11:05 | [5 empty] | 2019-07-21 11:05 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:31
VD-9001-251-DWG-130 | 2 | Foundation base plate details (sh.8) | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:23 | 2019-06-12 11:30 | 2019-06-12 11:30 | Yes | 0 |  |  | 2019-07-21 11:07 | [5 empty] | 2019-07-21 11:07 | Yes | 25 | 1204-Owner-v | 2020-04-25 18:32
VD-9001-251-SDG-002 | 2 | FINNING DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 11:38 | 2019-06-12 11:40 | 2019-06-12 11:40 | Yes | 0 |  |  | 2019-06-15 11:37 | [5 empty] | 2019-06-15 11:37 | Yes | -11 | 1204-Owner-v | 2020-05-13 16:56
VD-9001-251-SDG-003 | 1 | STRUCTURAL STEEL STANDARDS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 14:38 | 2019-06-12 14:51 | 2019-06-12 14:51 | Yes | 0 |  |  | 2019-07-22 14:59 | [5 empty] | 2019-07-22 14:59 | Yes | 26 | 1204-Owner-v | 2020-04-25 11:14
VD-9001-251-SDG-004 | 4 | STRUCTURAL STEEL STANDARDS FOR EXPANSION JOINTS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 14:39 | 2019-06-12 14:51 | 2019-06-12 14:51 | Yes | 0 |  |  | 2019-07-22 15:00 | [5 empty] | 2019-07-22 15:00 | Yes | 26 | 1204-Owner-v | 2020-04-25 11:13
VD-9001-251-SDG-005 | 1 | REFORMER TYPICAL DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 14:39 | 2019-06-12 14:51 | 2019-06-12 14:52 | Yes | 0 |  |  | 2019-06-15 11:39 | [5 empty] | 2019-06-15 11:39 | Yes | -11 | 1204-Owner-v | 2019-07-21 09:25
VD-9001-251-SDG-006 | 1 | REFRACTORY STANDARDS | HM-251 | KT – Kinetics Technology SpA | 2019-06-12 14:40 | 2019-06-12 14:52 | 2019-06-12 14:52 | Yes | 0 |  |  | 2019-06-15 11:40 | [5 empty] | 2019-06-15 11:40 | Yes | -11 | 1204-Owner-v | 2020-04-25 11:14
VD-9001-251-DWG-108 | 1 | PIPING SPECIAL SUPPORT | HM-251 | KT – Kinetics Technology SpA | 2019-06-24 |  |  | No | 361 | [9 empty] | No | 0
VD-9001-251-PPL-005 | 4 | REFORMER GENERAL ARRANGEMENT - LONGITUDINAL SECTION | HM-251 | KT – Kinetics Technology SpA | 2019-06-24 |  |  | No | 361 | [9 empty] | No | 0
VD-9001-251-PPL-003 | 5 | GENERAL LAYOUT - ELEVATION DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-06-24 |  |  | No | 361 | [9 empty] | No | 0
VD-9001-205A-FDB-001 | 0 | FINAL VENDOR DATA BOOK | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2019-06-15 | 2019-06-15 14:19 | 2019-06-15 14:19 | Yes | 0 |  |  |  | 2019-06-18 14:56 |  |  |  |  | 2019-06-18 20:58 | Yes | -11
VD-9001-251B-PCJ-004 | 1 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-06-22 | 2019-06-25 09:58 | 2019-06-25 09:58 | Yes | 3 |  |  |  |  | 2019-07-07 12:06 |  |  |  | 2019-07-07 12:06 | Yes | -2
VD-9001-251B-GAD-079 | 1 | General Arrangement DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-06-22 | 2019-09-24 11:04 | 2019-09-24 11:05 | Yes | 94 |  |  |  | 2019-10-07 16:13 |  |  |  |  | 2019-10-07 16:13 | Yes | -1
VD-9001-740B-PCJ-003 | 1 | PAINTING PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-06-23 |  |  | No | 362 | [9 empty] | No | 0
VD-9001-251B-GAD-060 | 1 | General Arrangement DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-06-19 | 2019-07-18 08:04 | 2019-07-18 08:04 | Yes | 29 |  |  |  | 2019-07-22 15:40 |  |  |  |  | 2019-07-22 15:40 | Yes | -10
VD-9001-251B-SPD-060 | 1 | Single Part DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-06-19 | 2019-07-18 08:10 | 2019-07-18 08:11 | Yes | 29 |  |  |  | 2019-07-22 15:48 |  |  |  |  | 2019-07-22 15:48 | Yes | -10
VD-9001-251B-GAD-080 | 1 | General Arrangement DWG for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-06-20 | 2019-07-18 08:15 | 2019-07-18 08:15 | Yes | 28 |  |  |  | 2019-07-22 16:44 |  |  |  |  | 2019-07-22 16:44 | Yes | -10 | 1204-Owner-v | 2019-08-15 14:14
VD-9001-251B-SAD-080 | 1 | Assembly DWG for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-06-20 | 2019-07-18 08:18 | 2019-07-18 08:23 | Yes | 28 |  |  | 2019-07-22 16:36 | [5 empty] | 2019-07-22 16:36 | Yes | -10 | 1204-Owner-v | 2019-07-23 09:41
VD-9001-251B-RPT-080 | 1 | Reports for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-06-17 | 2019-07-18 08:15 | 2019-07-18 08:15 | Yes | 31 |  |  |  | 2019-07-22 16:48 |  |  |  |  | 2019-07-22 16:48 | Yes | -10
VD-9001-205A-FDB-001 | 1 | FINAL VENDOR DATA BOOK | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2019-07-02 20:57 | 2019-06-19 12:32 | 2019-06-19 12:32 | Yes | -13 |  |  |  | 2019-06-23 16:15 |  |  |  |  | 2019-06-23 16:15 | Yes | -10
VD-9001-206B-DWG-042 | 3 | BODY & SUPPORT DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2019-06-23 09:37 | 2019-06-23 16:04 | 2019-06-23 16:04 | Yes | 0 |  |  | 2019-06-24 15:54 | [5 empty] | 2019-06-24 15:54 | Yes | -13 | 1204-Owner-v | 2020-05-11 11:33
VD-9001-206B-DWG-016 | 2 | INSULATION SUPPORT DRAWING -T-1001 | PV-206B | TASHA | 2019-06-23 10:02 | 2019-06-23 16:03 | 2019-06-23 16:03 | Yes | 0 |  |  | 2019-06-24 15:56 | [5 empty] | 2019-06-24 15:56 | Yes | -13 | 1204-Owner-v | 2020-05-11 11:28
VD-9001-205A-FDB-001 | 2 | FINAL VENDOR DATA BOOK | PV-205A | Pentane Chemistry Industries (PCI) Co. | 2019-06-26 | 2019-06-23 18:07 | 2019-06-23 18:08 | Yes | -3 |  |  | 2019-07-02 10:05 | [5 empty] | 2019-07-02 20:57 | Yes | -5
VD-9001-206B-DWG-013 | 3 | MANHOLE & NOZZLE DETAIL DRAWING -T-1001 | PV-206B | TASHA | 2019-06-26 17:41 | 2019-07-02 15:58 | 2019-07-02 15:58 | Yes | 6 |  |  | 2019-08-03 15:48 | [5 empty] | 2019-08-03 15:48 | Yes | 18 | 1204-Owner-v | 2020-05-11 11:31
VD-9001-206B-DWG-015 | 2 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-1001 | PV-206B | TASHA | 2019-06-26 17:41 | 2019-07-02 15:58 | 2019-07-02 15:58 | Yes | 6 |  |  | 2019-07-24 10:50 | [5 empty] | 2019-07-24 10:50 | Yes | 8 | 1204-Owner-v | 2020-05-11 14:49
VD-9001-251-DWG-023 | 2 | MAIN HEADER (TRANSFERLINE) DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-07-17 |  |  | No | 338 | [9 empty] | No | 0
VD-9001-251-DWG-082 | 1 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-07-10 |  |  | No | 345 | [9 empty] | No | 0
VD-9001-251-DWG-083 | 1 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-07-17 |  |  | No | 338 | [9 empty] | No | 0
VD-9001-251-DWG-084 | 1 | INLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-07-17 |  |  | No | 338 | [9 empty] | No | 0
VD-9001-251-DWG-085 | 1 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2019-07-17 | 2020-06-06 09:17 | 2020-06-06 09:18 | Yes | 325 |  |  |  | 2020-06-14 12:32 |  |  |  |  | 2020-06-14 12:32 | Yes | -6
VD-9001-251B-PCJ-002 | 1 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-06 15:04 | 2019-07-06 15:04 | Yes | -4 |  |  |  |  | 2019-07-09 10:21 |  |  |  | 2019-07-09 10:21 | Yes | -11
VD-9001-206B-DWG-043 | 3 | MANHOLE & NOZZLE DETAIL DRAWING -T-2001 | PV-206B | TASHA | 2019-07-06 14:18 | 2019-07-07 12:03 | 2019-07-07 12:07 | Yes | 1 |  |  | 2019-07-28 17:42 | [5 empty] | 2019-07-28 17:42 | Yes | 7 | 1204-Owner-v | 2020-05-11 11:31
VD-9001-206B-DWG-044 | 3 | INTERNAL ATTACHMENT DRAWING -T-2001 | PV-206B | TASHA | 2019-07-06 14:18 | 2019-07-07 11:45 | 2019-07-07 11:49 | Yes | 1 |  |  | 2019-08-03 15:53 | [5 empty] | 2019-08-03 15:53 | Yes | 13 | 1204-Owner-v | 2020-05-11 11:27
VD-9001-206B-DWG-045 | 3 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-2001 | PV-206B | TASHA | 2019-07-06 14:19 | 2019-07-07 12:15 | 2019-07-07 12:15 | Yes | 1 |  |  | 2019-07-24 10:36 | [5 empty] | 2019-07-24 10:36 | Yes | 3 | 1204-Owner-v | 2020-05-11 14:49
VD-9001-206B-DWG-051 | 3 | SHIPPING DRAWING-T-2001 | PV-206B | TASHA | 2019-07-06 14:19 | 2019-07-07 12:20 | 2019-07-07 12:23 | Yes | 1 |  |  | 2019-07-20 17:47 | [5 empty] | 2019-07-20 17:47 | Yes | -1 | 1204-Owner-v | 2019-07-10 11:22
VD-9001-251-DWG-101 | 1 | Instrument Hook up's (Mech.) | HM-251 | KT – Kinetics Technology SpA | 2019-07-15 |  |  | No | 340 | [9 empty] | No | 0
VD-9001-251-PPL-001 | 5 | GENERAL LAYOUT - PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2019-07-16 |  |  | No | 339 | [9 empty] | No | 0
VD-9001-201B-DWG-008 | 5 | LADDER AND PLATFORM DWG (4134-0359/4) | PV-201B | Brembana & Rolle S.p.A. | 2019-07-06 17:22 | 2019-07-08 11:33 | 2019-07-08 11:34 | Yes | 2 |  |  | 2019-07-08 14:56 | [5 empty] | 2019-07-08 20:57 | Yes | -14
VD-9001-201B-DWG-015 | 4 | BILL OF MATERIAL AND GENERAL NOTES (4134-0359/BMN) | PV-201B | Brembana & Rolle S.p.A. | 2019-07-06 17:22 | 2019-07-08 11:36 | 2019-07-08 11:36 | Yes | 2 |  |  | 2019-07-08 14:54 | [5 empty] | 2019-07-08 20:57 | Yes | -14
VD-9001-251B-PCJ-003 | 2 | Welding & NDT Map | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-22 08:44 | 2019-07-22 08:44 | Yes | 12 |  |  |  | 2019-08-03 09:35 |  |  |  |  | 2019-08-03 09:35 | Yes | -2
VD-9001-251B-QCP-001 | 2 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-07 12:01 | 2019-07-07 12:01 | Yes | -3 |  |  |  |  | 2019-07-09 09:31 |  |  |  | 2019-07-09 09:31 | Yes | -12
VD-9001-251B-PCJ-004 | 2 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-14 | 2019-07-18 10:50 | 2019-07-18 10:54 | Yes | 4 |  |  |  | 2019-07-23 16:26 |  |  |  |  | 2019-07-23 16:26 | Yes | -9 | 1204-Owner-v | 2019-07-28 16:23
VD-9001-251B-PCJ-001 | 2 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-08 14:16 | 2019-07-08 14:16 | Yes | -2 |  |  |  |  | 2019-07-09 10:20 |  |  |  | 2019-07-09 10:20 | Yes | -13
VD-9001-251-MTO-001 | 3 | STEELWORK MATERIAL TAKE OFF | HM-251 | KT – Kinetics Technology SpA | 2019-07-22 |  |  | No | 333 | [9 empty] | No | 0
VD-9001-251-DWG-032 | 2 | GENERAL NOTES & INFORMATION | HM-251 | KT – Kinetics Technology SpA | 2019-07-22 |  |  | No | 333 | [9 empty] | No | 0
VD-9001-251B-QCP-001 | 3 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-07-11 | 2019-07-09 09:49 | 2019-07-09 09:49 | Yes | -2 |  |  |  | 2019-07-13 17:04 |  |  |  |  | 2019-07-13 17:04 | Yes | -10 | 1204-Owner-v | 2019-07-17 13:14
VD-9001-251B-PCJ-001 | 3 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-10 16:28 | 2019-07-10 16:31 | Yes | 0 |  |  |  | 2019-07-13 16:59 |  |  |  |  | 2019-07-13 16:59 | Yes | -11
VD-9001-251B-PCJ-002 | 2 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-10 | 2019-07-10 16:21 | 2019-07-10 16:21 | Yes | 0 |  |  |  | 2019-07-13 16:57 |  |  |  |  | 2019-07-13 16:57 | Yes | -11
VD-9001-254-LST-302 | 8 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2019-07-10 10:37 | 2019-07-13 08:10 | 2019-07-13 08:11 | Yes | 3 |  |  |  | 2019-09-01 09:29 |  |  |  |  | 2019-09-01 09:29 | Yes | 36
VD-9001-251-PPL-011 | 1 | Instrument cable routing , tray & junction box layout | HM-251 | KT – Kinetics Technology SpA | 2019-07-22 | 2019-10-05 11:03 | 2019-10-05 11:03 | Yes | 75 |  |  | 2019-12-24 09:19 | [5 empty] | 2019-12-24 09:19 | Yes | 66
VD-9001-251-DWG-099 | 3 | INSTRUMENTS CONNECTION DRAWINGS | HM-251 | KT – Kinetics Technology SpA | 2019-07-22 |  |  | No | 333 | [9 empty] | No | 0
VD-9001-251B-PCJ-002 | 3 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-15 | 2019-07-15 15:36 | 2019-07-15 15:36 | Yes | 0 |  |  |  | 2019-07-20 10:44 |  |  |  |  | 2019-07-20 10:44 | Yes | -9
VD-9001-251B-PCJ-001 | 4 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-15 | 2019-07-15 15:25 | 2019-07-15 15:26 | Yes | 0 |  |  |  | 2019-07-20 10:51 |  |  |  |  | 2019-07-20 10:51 | Yes | -9
VD-9001-251B-QCP-001 | 4 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-07-15 | 2019-07-15 15:27 | 2019-07-15 15:28 | Yes | 0 |  |  |  | 2019-07-20 10:48 |  |  |  |  | 2019-07-20 10:48 | Yes | -9 | 1204-Owner-v | 2019-07-28 16:24
VD-9001-254-DWG-991 | 1 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 2/9 | HM-254 | AZAR AB | 2019-07-17 | 2020-01-04 13:51 | 2020-01-04 13:52 | Yes | 171 |  |  |  |  | 2020-02-24 11:24 |  |  |  | 2020-02-24 11:24 | Yes | 37
VD-9001-206B-DWG-071 | 5 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2019-07-16 16:37 | 2019-07-18 12:10 | 2019-07-18 12:11 | Yes | 2 |  |  |  | 2019-07-28 17:44 |  |  |  |  | 2019-07-28 17:44 | Yes | -4 | 1204-Owner-v | 2020-05-11 11:26
VD-9001-206B-DWG-072 | 3 | BODY & SUPPORT DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2019-07-16 16:37 | 2019-07-18 12:18 | 2019-07-18 12:19 | Yes | 2 |  |  | 2019-07-20 17:44 | [5 empty] | 2019-07-20 17:44 | Yes | -12 | 1204-Owner-v | 2020-05-11 14:48
VD-9001-206B-DWG-073 | 2 | MANHOLE & NOZZLE DETAIL DRAWING -T-4001 | PV-206B | TASHA | 2019-07-16 16:37 | 2019-07-18 12:28 | 2019-07-18 12:29 | Yes | 2 |  |  | 2019-08-03 15:50 | [5 empty] | 2019-08-03 15:50 | Yes | 2 | 1204-Owner-v | 2020-05-11 14:49
VD-9001-206B-DWG-075 | 4 | EXTERNAL ATTACHMENT & LADDER AND PLATFORM DRAWING-T-4001 | PV-206B | TASHA | 2019-07-16 16:37 | 2019-07-18 12:52 | 2019-07-18 12:52 | Yes | 2 |  |  | 2019-07-23 17:53 | [5 empty] | 2019-07-23 17:53 | Yes | -9 | 1204-Owner-v | 2020-05-11 14:49
VD-9001-206B-DWG-077 | 2 | TOP DAVIT DRAWING -T-4001 | PV-206B | TASHA | 2019-07-16 16:37 | 2019-07-18 12:40 | 2019-07-18 12:41 | Yes | 2 |  |  | 2019-07-23 17:55 | [5 empty] | 2019-07-23 17:55 | Yes | -9 | 1204-Owner-v | 2020-05-11 14:50
VD-9001-206B-DWG-081 | 2 | SHIPPING DRAWING-T-4001 | PV-206B | TASHA | 2019-07-16 16:38 | 2019-07-18 12:58 | 2019-07-18 12:58 | Yes | 2 |  |  | 2019-07-20 17:37 | [5 empty] | 2019-07-20 17:37 | Yes | -12
VD-9001-251B-WPS-001 | 2 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-07-22 | 2019-07-22 08:47 | 2019-07-22 08:48 | Yes | 0 |  |  |  | 2019-07-24 15:54 |  |  |  |  | 2019-07-24 15:54 | Yes | -12 | 1204-Owner-v | 2019-07-31 09:47
VD-9001-251B-PCJ-002 | 4 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-22 | 2019-07-31 12:15 | 2019-07-31 12:15 | Yes | 9 |  |  |  | 2019-08-05 09:53 |  |  |  |  | 2019-08-05 09:53 | Yes | -9
VD-9001-251B-QCP-001 | 5 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-07-22 | 2019-07-31 12:19 | 2019-07-31 12:19 | Yes | 9 |  |  |  | 2019-08-05 09:49 |  |  |  |  | 2019-08-05 09:49 | Yes | -9
VD-9001-251B-PCJ-001 | 5 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-22 | 2019-07-31 12:14 | 2019-07-31 12:14 | Yes | 9 |  |  |  | 2019-08-07 09:26 |  |  |  |  | 2019-08-07 09:26 | Yes | -7
VD-9001-251B-SAD-060 | 1 | Assembly DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-07-22 | 2019-07-20 15:59 | 2019-07-20 15:59 | Yes | -2 |  |  |  | 2019-07-22 15:16 |  |  |  |  | 2019-07-22 15:16 | Yes | -12 | 1204-Owner-v | 2020-02-16 11:43
VD-9001-251B-PCJ-005 | 0 | Pre-Assembly Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-20 |  |  | No | 335 | [9 empty] | No | 0
VD-9001-201B-LST-005 | 3 | BILL OF MATERIALS R-1004 (4134-0359/RBOM) | PV-201B | Brembana & Rolle S.p.A. | 2019-07-20 15:44 | 2019-07-22 11:14 | 2019-07-22 11:17 | Yes | 2 |  |  | 2019-08-13 16:40 | [5 empty] | 2019-08-13 20:00 | Yes | 8
VD-9001-251B-SAD-060 | 2 | Assembly DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-07-24 | 2019-07-23 16:22 | 2019-07-23 16:22 | Yes | -1 |  |  | 2019-07-27 10:18 | [5 empty] | 2019-07-27 10:18 | Yes | -10 | 1204-Owner-v | 2019-10-21 10:15
VD-9001-251B-GAD-060 | 2 | General Arrangement DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-07-24 | 2019-07-23 16:22 | 2019-07-23 16:22 | Yes | -1 |  |  | 2019-07-27 10:16 | [5 empty] | 2019-07-27 10:16 | Yes | -10 | 1204-Owner-v | 2019-10-21 10:10
VD-9001-251B-RPT-060 | 1 | Reports for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-07-23 | 2019-07-23 16:22 | 2019-07-23 16:22 | Yes | 0 |  |  | 2019-07-27 10:17 | [5 empty] | 2019-07-27 10:17 | Yes | -10 | 1204-Owner-v | 2020-01-06 09:31
VD-9001-251B-SPD-060 | 2 | Single Part DWG for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-07-23 | 2019-07-23 16:23 | 2019-07-23 16:23 | Yes | 0 |  |  | 2019-07-27 10:19 | [5 empty] | 2019-07-27 10:19 | Yes | -10 | 1204-Owner-v | 2019-10-21 10:20
VD-9001-251B-GAD-080 | 2 | General Arrangement DWG for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-07-24 | 2019-07-29 14:47 | 2019-07-29 14:51 | Yes | 5 |  |  | 2019-08-03 15:02 | [5 empty] | 2019-08-03 15:02 | Yes | -9 | 1204-Owner-v | 2019-10-21 10:12
VD-9001-251B-RPT-080 | 2 | Reports for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-07-23 | 2019-07-29 14:52 | 2019-07-29 14:53 | Yes | 6 |  |  |  | 2019-08-05 10:12 |  |  |  |  | 2019-08-05 10:12 | Yes | -7 | 1204-Owner-v | 2019-08-15 14:07
VD-9001-251-PPL-016 | 1 | Local Panel Layout & Wiring Diagram | HM-251 | KT – Kinetics Technology SpA | 2019-07-30 | 2019-10-05 11:03 | 2019-10-05 11:04 | Yes | 67 |  |  |  | 2019-12-31 10:57 |  |  |  |  | 2019-12-31 10:57 | Yes | 73
VD-9001-251B-PCJ-004 | 3 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-07-27 | 2019-07-31 12:17 | 2019-07-31 12:18 | Yes | 4 |  |  |  | 2019-08-05 11:06 |  |  |  |  | 2019-08-05 11:06 | Yes | -9
VD-9001-740B-MOD-201171 | 1 | TEKLA MODEL FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-07-31 | 2019-10-05 11:42 | 2019-10-05 11:42 | Yes | 66 |  |  |  | 2019-10-16 15:48 |  |  |  |  | 2019-10-16 15:48 | Yes | -3
VD-9001-251B-WPS-001 | 3 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-07-28 | 2019-07-31 12:55 | 2019-07-31 13:16 | Yes | 3 |  |  |  | 2019-08-05 09:45 |  |  |  |  | 2019-08-05 09:45 | Yes | -9
VD-9001-740B-GAD-201171 | 1 | GA DRAWINGS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-07-31 | 2019-10-05 11:28 | 2019-10-05 11:29 | Yes | 66 |  |  |  | 2019-10-16 15:51 |  |  |  |  | 2019-10-16 15:51 | Yes | -3
VD-9001-206B-DWG-071 | 6 | GENERAL ARRANGMENT DRAWING -T-4001 | PV-206B | TASHA | 2019-07-31 | 2019-07-30 11:30 | 2019-07-30 11:30 | Yes | -1 |  |  | 2019-08-11 09:47 | [5 empty] | 2019-08-11 09:47 | Yes | -2 | 1204-Owner-v | 2020-04-25 09:06
VD-9001-204D-DWG-011 | 5 | SHIPPING DWG. | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-07-31 10:57 | 2019-07-31 14:17 | 2019-07-31 14:17 | Yes | 0 |  |  | 2020-02-04 14:47 | [5 empty] | 2020-02-04 14:47 | Yes | 174
VD-9001-204D-DWG-037 | 3 | STEAM DRUM D-2003 / INSULATION SUPPORT | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-07-31 10:58 | 2019-07-31 14:22 | 2019-07-31 14:23 | Yes | 0 |  |  | 2020-02-04 14:44 | [5 empty] | 2020-02-04 14:44 | Yes | 174
VD-9001-204D-DWG-006 | 2 | EXTERNAL SUPPORTS | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-07-31 11:00 | 2019-07-31 14:13 | 2019-07-31 14:13 | Yes | 0 |  |  | 2020-02-04 14:54 | [5 empty] | 2020-02-04 14:55 | Yes | 174
VD-9001-204D-DWG-003 | 5 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2019-07-31 11:02 | 2019-07-31 14:09 | 2019-07-31 14:10 | Yes | 0 |  |  |  | 2020-02-04 15:35 |  |  |  |  | 2020-02-04 15:35 | Yes | 174
VD-9001-462A-PCJ-005 | 0 | Packing and Marking Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2019-07-31 | 2019-08-27 10:05 | 2019-08-27 10:05 | Yes | 27 |  |  | 2019-08-27 10:28 |  |  |  | 2019-08-14 14:33 | 2019-08-14 14:33 | 2019-08-27 10:28 | Yes | -14
VD-9001-462A-PCJ-006 | 0 | Material Handling and storage Procedure | PI-462A | (TSCE)مهندسی طرح اندیشان ایمنی و ارتباطات | 2019-07-31 | 2019-08-15 13:19 | 2019-08-15 13:19 | Yes | 15 |  |  | 2019-08-19 17:43 |  |  |  | 2019-08-14 14:44 | 2019-08-14 14:45 | 2019-08-19 17:46 | Yes | -10
VD-9001-740B-MOD-00172 | 1 | TEKLA MODEL FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-08-08 | 2019-09-30 09:21 | 2019-09-30 09:21 | Yes | 53 |  |  | 2019-10-02 09:52 | [5 empty] | 2019-10-02 09:52 | Yes | -12
VD-9001-740B-RPT-201171 | 1 | TEKLA REPORTS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-08-08 | 2019-10-05 11:44 | 2019-10-05 11:44 | Yes | 58 |  |  |  | 2019-11-18 17:23 |  |  |  |  | 2019-11-18 18:58 | Yes | 30
VD-9001-740B-GAD-00172 | 1 | GA DRAWINGS FOR PIPE BRIDE 1 | ST-740B | PETRO ADAK IRAN | 2019-08-08 | 2019-09-29 17:03 | 2019-09-29 17:03 | Yes | 52 |  |  |  | 2019-10-02 09:49 |  |  |  |  | 2019-10-02 09:49 | Yes | -11
VD-9001-740B-RPT-00172 | 1 | TEKLA REPORTS FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-08-08 | 2019-09-30 09:22 | 2019-09-30 09:22 | Yes | 53 |  |  | 2019-10-02 09:51 | 2019-11-19 12:58 |  |  |  |  | 2019-11-19 18:57 | Yes | 36
VD-9001-251B-PCJ-003 | 3 | Welding & NDT Map | HM-251B | Bamdad Zendehroud Co. | 2019-08-05 | 2019-08-13 14:39 | 2019-08-13 14:39 | Yes | 8 |  |  | 2019-08-17 14:47 |  |  |  | 2019-08-13 10:31 | 2019-08-13 10:31 | 2019-08-17 14:47 | Yes | -10 | 1204-Owner-v | 2019-09-02 17:29
VD-9001-251B-WPS-001 | 4 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-08-07 | 2019-08-11 10:26 | 2019-08-11 11:52 | Yes | 4 |  |  |  | 2019-08-17 14:37 |  |  |  |  | 2019-08-17 14:37 | Yes | -8 | 1204-Owner-v | 2019-08-13 15:22
VD-9001-251B-QCP-001 | 6 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-08-06 | 2019-08-13 14:40 | 2019-08-13 14:40 | Yes | 7 |  |  | 2019-08-17 14:48 |  |  |  | 2019-08-13 10:28 | 2019-08-13 10:28 | 2019-08-17 14:48 | Yes | -10
VD-9001-251B-PCJ-002 | 5 | NDT Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-08-06 | 2019-08-13 14:38 | 2019-08-13 14:39 | Yes | 7 |  |  | 2019-08-17 14:47 |  |  |  | 2019-08-13 10:33 | 2019-08-13 10:33 | 2019-08-17 14:47 | Yes | -10 | 1204-Owner-v | 2019-09-02 17:29
VD-9001-251B-RPT-080 | 3 | Reports for "STACK" GRATING | HM-251B | Bamdad Zendehroud Co. | 2019-08-07 | 2019-08-29 12:08 | 2019-08-29 12:08 | Yes | 22 |  |  | 2019-09-02 10:28 | [5 empty] | 2019-09-02 10:28 | Yes | -10 | 1204-Owner-v | 2020-01-01 14:58
VD-9001-251B-PCJ-004 | 4 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-08-07 | 2019-08-11 10:15 | 2019-08-11 10:15 | Yes | 4 |  |  |  | 2019-08-13 10:41 |  |  |  |  | 2019-08-13 10:41 | Yes | -12
VD-9001-251B-PCJ-001 | 6 | Painting Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-08-11 | 2019-08-13 14:37 | 2019-08-13 14:38 | Yes | 2 |  |  | 2019-08-17 14:46 |  |  |  | 2019-08-13 10:36 | 2019-08-13 10:36 | 2019-08-17 14:46 | Yes | -10 | 1204-Owner-v | 2019-09-02 17:28
VD-9001-251B-PCJ-004 | 5 | Shipping and Marking Procedure | HM-251B | Bamdad Zendehroud Co. | 2019-08-14 | 2019-08-13 14:47 | 2019-08-13 14:47 | Yes | -1 |  |  | 2019-08-17 14:49 | [5 empty] | 2019-08-17 14:49 | Yes | -10 | 1204-Owner-v | 2019-09-02 17:29
VD-9001-253(A)-DSH-061 | 3 | THERMAL & MECHANICAL DATA SHEET for AE-3002 | HM-253A | FATEH SANAT KIMIA | 2019-08-13 18:18 | 2019-08-14 15:37 | 2019-08-14 15:37 | Yes | 1 | [9 empty] | No | 296 | 1204-Owner-v | 2019-09-29 11:02
VD-9001-251B-WPS-001 | 5 | Welding NoteBook (WPS & PQR) | HM-251B | Bamdad Zendehroud Co. | 2019-08-18 | 2019-08-18 14:46 | 2019-08-18 15:10 | Yes | 0 |  |  | 2019-08-19 15:08 | [5 empty] | 2019-08-19 15:08 | Yes | -13 | 1204-Owner-v | 2019-12-07 09:09
VD-9001-201B-CAL-006 | 1 | REFRACTORY DOME SUPPORT CALCULATION ( 4134-0359/RDSC) | PV-201B | Brembana & Rolle S.p.A. | 2019-08-31 20:00 | 2020-05-08 16:40 | 2020-05-08 16:40 | Yes | 251 |  |  |  | 2020-05-18 18:52 |  |  |  |  | 2020-05-18 21:03 | Yes | -4
VD-9001-257C-GAD-004 | 5 | GENERAL ARRANGEMENT (4137-0367) | HM-257C | Brembana & Rolle S.p.A. | 2019-08-31 | 2020-01-03 18:54 | 2020-01-03 18:56 | Yes | 125 |  |  | 2020-02-16 11:15 | [5 empty] | 2020-02-16 11:15 | Yes | 30 | 1204-Owner-v | 2020-02-09 11:34
VD-9001-253(A)-DSH-001 | 5 | THERMAL & MECHANICAL DATA SHEET for AE-2001 | HM-253A | FATEH SANAT KIMIA | 2019-08-26 13:28 | 2019-08-27 08:43 | 2019-08-27 08:43 | Yes | 1 | [9 empty] | No | 283 | 1204-Owner-v | 2019-09-11 09:17
VD-9001-253(A)-DSH-031 | 3 | THERMAL & MECHANICAL DATA SHEET for AE-3001 | HM-253A | FATEH SANAT KIMIA | 2019-08-26 13:28 | 2019-08-28 16:58 | 2019-08-29 10:27 | Yes | 3 | [9 empty] | No | 282 | 1204-Owner-v | 2019-09-29 11:02
VD-9001-201A-ANL-031 | 2 | F.E.A. FOR SKIRT - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-201A-ANL-013 | 2 | F.E.A. FOR SKIRT - R1001 | PV-201A | FATEH SANAT KIMIA | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-201A-ANL-049 | 2 | F.E.A. FOR SKIRT - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-201A-ANL-032 | 2 | F.E.A. FOR NOZZLES - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-201A-ANL-050 | 2 | F.E.A. FOR NOZZLES - R1003 | PV-201A | FATEH SANAT KIMIA | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-251B-RPT-060 | 2 | Reports for "TEMPLATE RELATED TO STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-08-31 13:25 | 2019-08-31 14:06 | 2019-08-31 14:06 | Yes | 0 |  |  | 2019-09-02 10:29 | [5 empty] | 2019-09-02 10:29 | Yes | -12 | 1204-Owner-v | 2020-05-21 14:48
VD-9001-254-PPL-319 | 8 | LAYOUTS & WIRING DIAGRAMS FOR BMS PANELS | HM-254 | AZAR AB | 2019-09-04 | 2020-03-09 16:14 | 2020-03-09 16:14 | Yes | 187 |  |  | 2020-04-15 11:21 | [5 empty] | 2020-04-15 11:21 | Yes | 23
VD-9001-254-LST-302 | 9 | I/O LIST & I/O ASSIGNMENT FOR BMS | HM-254 | AZAR AB | 2019-09-04 |  |  | No | 289 | [9 empty] | No | 0
VD-9001-201B-DSH-005 | 2 | THERMOCOUPLE/THERMOWELL DATA SHEET & DRAWING (4134-0359/TC) | PV-201B | Brembana & Rolle S.p.A. | 2019-09-30 19:59 | 2020-06-08 12:36 | 2020-06-08 12:38 | Yes | 252 | [9 empty] | No | -3
VD-9001-201B-PCJ-007 | 1 | INSTALLATION REFRACTORY PROCEDURE AT SHOP (4134-0359/RIP) | PV-201B | Brembana & Rolle S.p.A. | 2019-09-21 08:27 | 2019-09-23 10:39 | 2019-09-23 10:54 | Yes | 2 |  |  | 2019-10-06 10:32 | [5 empty] | 2019-10-06 18:58 | Yes | -1
VD-9001-251B-RPT-079 | 1 | Reports for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-09-25 11:03 | 2019-09-25 12:05 | 2019-09-25 12:05 | Yes | 0 |  |  | 2019-10-07 16:15 | [5 empty] | 2019-10-07 16:15 | Yes | -2 | 1204-Owner-v | 2020-05-25 15:20
VD-9001-251B-SAD-079 | 1 | Assembly DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-09-25 11:05 | 2019-09-25 12:08 | 2019-09-25 12:09 | Yes | 0 |  |  | 2019-10-07 16:17 | [5 empty] | 2019-10-07 16:17 | Yes | -2 | 1204-Owner-v | 2019-10-21 10:24
VD-9001-251B-SPD-079 | 1 | Single Part DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-09-25 11:05 | 2019-09-25 12:13 | 2019-09-25 12:25 | Yes | 0 |  |  | 2019-10-07 16:21 | [5 empty] | 2019-10-07 16:21 | Yes | -2 | 1204-Owner-v | 2019-10-21 10:41
VD-9001-740B-PCJ-006 | 0 | MARKING AND PACKING PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-10-02 |  |  | No | 261 | [9 empty] | No | 0
VD-9001-740B-GAD-00172 | 2 | GA DRAWINGS FOR PIPE BRIDE 1 | ST-740B | PETRO ADAK IRAN | 2019-10-16 | 2019-11-11 10:50 | 2019-11-11 10:51 | Yes | 26 |  |  | 2019-11-18 15:39 | [5 empty] | 2019-11-18 15:39 | Yes | -7
VD-9001-740B-PCJ-002 | 2 | WELDING SPECIFICATION PROCEDURE | ST-740B | PETRO ADAK IRAN | 2019-10-14 |  |  | No | 249 | [9 empty] | No | 0
VD-9001-251B-GAD-079 | 2 | General Arrangement DWG for "STACK" | HM-251B | Bamdad Zendehroud Co. | 2019-10-09 | 2019-11-03 10:20 | 2019-11-03 10:27 | Yes | 25 |  |  | 2019-11-16 09:29 | [5 empty] | 2019-11-16 09:29 | Yes | -1 | 1204-Owner-v | 2020-01-01 14:33
VD-9001-251B-QCP-001 | 7 | Quality Control Plan (QCP) | HM-251B | Bamdad Zendehroud Co. | 2019-10-09 09:11 | 2019-10-09 09:44 | 2019-10-09 09:44 | Yes | 0 |  |  | 2019-10-14 09:37 | [5 empty] | 2019-10-14 09:37 | Yes | -9 | 1204-Owner-v | 2020-04-25 16:13
VD-9001-740B-MOD-201171 | 2 | TEKLA MODEL FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-10-23 | 2019-11-12 10:24 | 2019-11-12 10:24 | Yes | 20 |  |  | 2019-11-18 15:56 | [5 empty] | 2019-11-18 15:56 | Yes | -8
VD-9001-740B-GAD-201171 | 2 | GA DRAWINGS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-10-30 | 2019-11-12 09:55 | 2019-11-12 09:59 | Yes | 13 |  |  | 2019-11-18 16:04 | [5 empty] | 2019-11-18 16:04 | Yes | -8
VD-9001-251-DWG-103 | 2 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2019-10-31 |  |  | No | 232 | [9 empty] | No | 0
VD-9001-257C-WBK-007 | 5 | WELDING BOOK (4137-0370/W) | HM-257C | Brembana & Rolle S.p.A. | 2019-10-29 | 2019-12-24 10:39 | 2019-12-24 10:42 | Yes | 56 |  |  | 2020-01-07 16:36 | [5 empty] | 2020-01-07 16:36 | Yes | 0
VD-9001-740B-MOD-30319 | 1 | TEKLA MODEL FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-10-31 | 2019-11-05 11:01 | 2019-11-05 11:01 | Yes | 5 |  |  |  | 2019-11-09 17:08 |  |  |  |  | 2019-11-09 17:08 | Yes | -10
VD-9001-740B-RPT-30319 | 1 | TEKLA REPORTS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-10-31 | 2019-11-05 11:02 | 2019-11-05 11:02 | Yes | 5 |  |  |  | 2019-11-26 10:56 |  |  |  |  | 2019-11-26 18:58 | Yes | 7
VD-9001-740B-GAD-30319 | 1 | GA DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-10-31 | 2019-11-05 10:44 | 2019-11-05 10:45 | Yes | 5 |  |  |  | 2019-11-25 10:27 |  |  |  |  | 2019-11-25 18:58 | Yes | 6
VD-9001-251-DWG-105 | 2 | Power Supply Distribution | HM-251 | KT – Kinetics Technology SpA | 2019-11-04 |  |  | No | 228 | [9 empty] | No | 0
VD-9001-251-DWG-131 | 2 | POWER SUPPLY DISTRIBUTION ID FAN REMOTE I/O PANEL | HM-251 | KT – Kinetics Technology SpA | 2019-11-09 |  |  | No | 223 | [9 empty] | No | 0
VD-9001-740B-MOD-30319 | 2 | TEKLA MODEL FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-11-16 | 2019-11-11 09:54 | 2019-11-11 09:55 | Yes | -5 |  |  |  | 2019-11-18 16:30 |  |  |  |  | 2019-11-18 16:30 | Yes | -7
VD-9001-740B-MOD-30319 | 3 | TEKLA MODEL FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-11-25 | 2019-11-23 16:55 | 2019-11-23 16:55 | Yes | -2 |  |  | 2019-11-25 10:11 | [5 empty] | 2019-11-25 18:57 | Yes | -12
VD-9001-740B-RPT-201171 | 2 | TEKLA REPORTS FOR STRUCTURE M | ST-740B | PETRO ADAK IRAN | 2019-11-25 | 2020-02-29 15:00 | 2020-02-29 15:00 | Yes | 96 |  |  | 2020-03-02 10:34 | [5 empty] | 2020-03-02 20:00 | Yes | -12
VD-9001-740B-RPT-00172 | 2 | TEKLA REPORTS FOR PIPE BRIDGE 1 | ST-740B | PETRO ADAK IRAN | 2019-11-26 | 2020-02-25 11:37 | 2020-02-25 11:37 | Yes | 91 |  |  | 2020-03-02 10:33 | [5 empty] | 2020-03-02 20:00 | Yes | -8
VD-9001-740B-GAD-30319 | 2 | GA DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-12-02 | 2020-03-14 10:10 | 2020-03-14 10:10 | Yes | 103 |  |  |  | 2020-04-06 14:20 |  |  |  |  | 2020-04-06 20:59 | Yes | 9
VD-9001-257C-LST-004 | 3 | MASTER & DETAILED PACKING LIST (4137/PL) | HM-257C | Brembana & Rolle S.p.A. | 2019-11-26 16:11 | 2019-11-26 16:31 | 2019-11-26 18:15 | Yes | 0 |  |  |  | 2020-01-12 10:31 |  |  |  |  | 2020-01-12 10:31 | Yes | 33 | 1204-Owner-v | 2019-12-27 17:16
VD-9001-740B-RPT-30319 | 2 | TEKLA REPORTS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2019-12-07 | 2020-03-10 10:06 | 2020-03-10 10:07 | Yes | 94 |  |  | 2020-04-06 13:17 | [5 empty] | 2020-04-06 20:59 | Yes | 13
VD-9001-257B-NPL-034 | 2 | WELDING DOCUMENT (WPS,PQR) | HM-257B | FATEH SANAT KIMIA | 2019-12-10 | 2020-01-26 15:19 | 2020-01-26 15:19 | Yes | 47 |  |  |  | 2020-04-15 09:11 |  |  |  |  | 2020-04-15 09:11 | Yes | 66
VD-9001-254-PID-114 | 6 | BOILER WATER & STEAM P&I DIAGRAM | HM-254 | AZAR AB | 2019-12-17 09:05 | 2019-12-17 12:08 | 2019-12-17 12:08 | Yes | 0 |  |  | 2020-02-05 10:30 | [5 empty] | 2020-02-05 10:30 | Yes | 36 | 1204-Owner-v | 2019-12-18 13:04
VD-9001-254-PID-116 | 6 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2019-12-17 09:05 | 2019-12-17 12:08 | 2019-12-17 12:08 | Yes | 0 |  |  | 2020-02-05 10:28 | [5 empty] | 2020-02-05 10:28 | Yes | 36 | 1204-Owner-v | 2019-12-18 13:19
VD-9001-254-PID-118 | 5 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2019-12-17 09:05 | 2019-12-17 12:09 | 2019-12-17 12:09 | Yes | 0 |  |  |  | 2020-02-12 09:47 |  |  |  |  | 2020-02-12 09:47 | Yes | 43 | 1204-Owner-v | 2019-12-18 13:16
VD-9001-254-PID-117 | 5 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2019-12-17 09:06 | 2019-12-17 12:09 | 2019-12-17 12:09 | Yes | 0 |  |  |  | 2019-12-17 14:16 |  |  |  |  | 2019-12-17 14:16 | Yes | -14
VD-9001-254-DIG-338 | 3 | CAUSE AND EFFECT DIAGRAM | HM-254 | AZAR AB | 2019-12-17 14:03 | 2019-12-17 14:04 | 2019-12-17 14:04 | Yes | 0 |  |  |  | 2020-02-12 09:45 |  |  |  |  | 2020-02-12 09:45 | Yes | 43 | 1204-Owner-v | 2019-12-18 13:17
VD-9001-254-PID-117 | 6 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2019-12-17 | 2019-12-17 14:21 | 2019-12-17 14:22 | Yes | 0 |  |  |  | 2020-02-05 10:26 |  |  |  |  | 2020-02-05 10:26 | Yes | 36 | 1204-Owner-v | 2019-12-18 13:02
VD-9001-254-LST-112 | 1 | SET POINT LIST FOR BOILER PLANT | HM-254 | AZAR AB | 2019-12-23 | 2019-12-23 08:44 | 2019-12-23 08:44 | Yes | 0 |  |  |  | 2020-02-05 10:24 |  |  |  |  | 2020-02-05 10:24 | Yes | 30 | 1204-Owner-v | 2019-12-23 15:11
VD-9001-307A1-DIS-001 | 02 | VENDOR DOCUMENTS INDEX & SCHEDULE | MC-307A1 | Deep Blue Pump Co. | 2019-12-04 | 2019-12-31 11:36 | 2019-12-31 11:36 | Yes | 27 |  |  | 2020-01-06 10:59 | [5 empty] | 2020-01-06 18:57 | Yes | -8 | 1204-Owner-v | 2020-01-04 14:00
VD-9001-307A1-ITP-001 | 0 | INSPECTION & TEST PLAN FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-01-01 | 2020-04-04 08:18 | 2020-04-04 08:18 | Yes | 94 |  |  |  | 2020-04-28 09:39 |  |  |  |  | 2020-04-28 09:39 | Yes | 10 | 1204-Owner-v | 2020-04-20 10:13
VD-9001-307A1-ITP-002 | 0 | INSPECTION & TEST PLAN FOR ELECTRICAL MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-01-04 | 2020-05-09 08:38 | 2020-05-09 08:38 | Yes | 126 |  |  |  | 2020-06-02 11:43 |  |  |  |  | 2020-06-02 11:43 | Yes | 10
VD-9001-307A1-ITP-003 | 0 | INSPECTION & TEST PLAN FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-01-04 | 2020-05-09 08:38 | 2020-05-09 08:39 | Yes | 126 |  |  |  | 2020-05-19 17:32 |  |  |  |  | 2020-05-19 17:32 | Yes | -4
VD-9001-307A1-ITP-004 | 0 | INSPECTION & TEST PLAN FOR SURFACE CONDENSER | MC-307A1 | Deep Blue Pump Co. | 2020-01-04 | 2020-05-09 08:38 | 2020-05-09 08:39 | Yes | 126 |  |  |  | 2020-05-26 12:05 |  |  |  |  | 2020-05-26 12:05 | Yes | 3
VD-9001-307A1-ORC-001 | 0 | ORGANIZATION CHART | MC-307A1 | Deep Blue Pump Co. | 2019-12-25 |  |  | No | 177 | [9 empty] | No | 0
VD-9001-307A1-DWG-001 | 0 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(STEAM TURBINE DRIVEN) P2002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:23 | Yes | 11 |  |  |  | 2020-02-02 14:19 |  |  |  |  | 2020-02-02 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:02
VD-9001-307A1-DWG-002 | 0 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(MOTOR DRIVEN) P2002B | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:22 | Yes | 11 |  |  |  | 2020-02-02 14:22 |  |  |  |  | 2020-02-02 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:02
VD-9001-307A1-DWG-003 | 0 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(STEAM TURBINE DRIVEN) P2003A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:23 | Yes | 11 |  |  |  | 2020-02-02 10:32 |  |  |  |  | 2020-02-02 18:56 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:03
VD-9001-307A1-DWG-004 | 0 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(MOTOR DRIVEN) P2003B | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:24 | 2020-01-11 16:24 | Yes | 11 |  |  |  | 2020-02-02 10:25 |  |  |  |  | 2020-02-02 18:56 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:03
VD-9001-307A1-DWG-005 | 0 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMPS(STEAM TURBINE DRIVEN) P4001AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:24 | Yes | 11 |  |  |  | 2020-02-02 14:52 |  |  |  |  | 2020-02-02 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:04
VD-9001-307A1-DWG-006 | 0 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMP(MOTOR DRIVEN) P4001C | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:24 | 2020-01-11 16:24 | Yes | 11 |  |  |  | 2020-02-02 14:26 |  |  |  |  | 2020-02-02 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:04
VD-9001-307A1-DWG-007 | 0 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMP(STEAM TURBINE DRIVEN) P4002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:25 | Yes | 11 |  |  |  | 2020-02-02 14:32 |  |  |  |  | 2020-02-02 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:04
VD-9001-307A1-DWG-008 | 0 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMPS(MOTOR DRIVEN) P4002BC | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:25 | 2020-01-11 16:25 | Yes | 11 |  |  |  | 2020-02-02 14:15 |  |  |  |  | 2020-02-02 18:56 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:05
VD-9001-307A1-DWG-009 | 0 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(STEAM TURBINE DRIVEN) P6301AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-21 17:24 | 2020-01-21 17:25 | Yes | 21 |  |  |  | 2020-02-02 10:36 |  |  | 2020-01-15 10:16 | 2020-01-15 10:16 | 2020-02-02 18:56 | Yes | -2 | 1204-Owner-v | 2020-01-13 12:05
VD-9001-307A1-DWG-010 | 0 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(MOTOR DRIVEN) P6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-01-11 16:21 | 2020-01-11 16:26 | Yes | 11 |  |  |  | 2020-02-02 10:23 |  |  |  |  | 2020-02-02 18:56 | Yes | 8 | 1204-Owner-v | 2020-01-13 12:05
VD-9001-307A1-DWG-011 | 0 | PUMP GA DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-04-14 12:46 | 2020-04-14 12:47 | Yes | 105 |  |  |  |  | 2020-05-06 15:18 |  |  |  | 2020-05-06 15:18 | Yes | 8 | 1204-Owner-v | 2020-04-23 18:03
VD-9001-307A1-DWG-012 | 0 | PUMP CROSS SECTION DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 |  |  | No | 161 | [9 empty] | No | 0
VD-9001-307A1-DWG-013 | 0 | PUMP CROSS SECTION DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 |  |  | No | 161 | [9 empty] | No | 0
VD-9001-307A1-DWG-014 | 0 | PUMP CROSS SECTION DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 |  |  | No | 161 | [9 empty] | No | 0
VD-9001-307A1-DWG-015 | 0 | PUMP CROSS SECTION DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-06-13 08:18 | 2020-06-13 08:18 | Yes | 155 | [9 empty] | No | -8 | 1204-Owner-v | 2020-06-15 13:41
VD-9001-307A1-DWG-016 | 0 | PUMP CROSS SECTION DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 |  |  | No | 161 | [9 empty] | No | 0
VD-9001-307A1-DWG-017 | 0 | PUMP CROSS SECTION DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-05-21 13:47 | 2020-05-21 13:47 | Yes | 132 |  |  |  | 2020-05-31 10:25 |  |  |  |  | 2020-05-31 10:25 | Yes | -4
VD-9001-307A1-DWG-018 | 0 | STEAM TURBINE CROSS SECTION DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-04-25 08:33 | 2020-04-25 08:33 | Yes | 106 |  |  |  | 2020-05-16 14:32 |  |  |  |  | 2020-05-16 14:32 | Yes | 7
VD-9001-307A1-DWG-019 | 0 | STEAM TURBINE CROSS SECTION DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-04-25 08:33 | 2020-04-25 08:33 | Yes | 106 |  |  |  | 2020-05-16 14:33 |  |  |  |  | 2020-05-16 14:33 | Yes | 7
VD-9001-307A1-DWG-020 | 0 | STEAM TURBINE CROSS SECTION DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-04-25 08:45 | 2020-04-25 08:45 | Yes | 106 |  |  |  | 2020-05-16 14:35 |  |  |  |  | 2020-05-16 14:35 | Yes | 7
VD-9001-307A1-DWG-021 | 0 | STEAM TURBINE CROSS SECTION DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-04-25 08:47 | 2020-04-25 08:47 | Yes | 106 |  |  |  | 2020-05-16 14:36 |  |  |  |  | 2020-05-16 14:36 | Yes | 7
VD-9001-307A1-DWG-022 | 0 | STEAM TURBINE CROSS SECTION DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-10 | 2020-04-25 08:47 | 2020-04-25 08:47 | Yes | 106 |  |  |  | 2020-05-16 14:37 |  |  |  |  | 2020-05-16 14:37 | Yes | 7 | 1204-Owner-v | 2020-06-15 13:16
VD-9001-307A1-DWG-023 | 0 | MECHANICAL SEAL DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-024 | 0 | MECHANICAL SEAL DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-025 | 0 | MECHANICAL SEAL DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-026 | 0 | MECHANICAL SEAL DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-027 | 0 | MECHANICAL SEAL DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-028 | 0 | MECHANICAL SEAL DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-029 | 0 | SEAL SYSTEM DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-030 | 0 | SEAL SYSTEM DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-031 | 0 | SEAL SYSTEM DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-032 | 0 | SEAL SYSTEM DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 |  |  | No | 123 | [9 empty] | No | 0
VD-9001-307A1-DWG-033 | 0 | COUPLING DRAWING FOR BETWEEN STEAM TURBINE AND GEAR BOX & BETWEEN GEAR BOX AND PUMP P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-034 | 0 | COUPLING DRAWING FOR BETWEEN PUMP AND MOTOR P2002B | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-035 | 0 | COUPLING DRAWING FOR BETWEEN STEAM TURBINE AND GEAR BOX & BETWEEN GEAR BOX AND PUMP P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-036 | 0 | COUPLING DRAWING FOR BETWEEN PUMP AND MOTOR P2003B | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-037 | 0 | COUPLING DRAWING FOR BETWEEN STEAM TURBINE AND GEAR BOX & BETWEEN GEAR BOX AND PUMP P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-038 | 0 | COUPLING DRAWING FOR BETWEEN PUMP AND MOTOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-039 | 0 | COUPLING DRAWING FOR BETWEEN STEAM TURBINE AND PUMP P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-040 | 0 | COUPLING DRAWING FOR BETWEEN PUMP AND MOTOR P4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-041 | 0 | COUPLING DRAWING FOR BETWEEN STEAM TURBINE AND GEAR BOX & BETWEEN GEAR BOX AND PUMP P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-042 | 0 | COUPLING DRAWING FOR BETWEEN PUMP AND MOTOR P6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-043 | 0 | COUPLING DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-044 | 0 | MOTOR OUTLINE DRAWING FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-05-07 16:37 | 2020-05-07 16:37 | Yes | 123 |  |  |  | 2020-05-16 14:54 |  |  | 2020-04-04 14:10 | 2020-04-04 14:10 | 2020-05-16 14:54 | Yes | -5
VD-9001-307A1-DWG-045 | 0 | MOTOR OUTLINE DRAWING FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-05-07 16:37 | 2020-05-07 16:37 | Yes | 123 |  |  |  | 2020-05-16 14:55 |  |  | 2020-04-04 14:09 | 2020-04-04 14:09 | 2020-05-16 14:55 | Yes | -5
VD-9001-307A1-DWG-046 | 0 | MOTOR OUTLINE DRAWING FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-05-07 16:38 | 2020-05-07 16:38 | Yes | 123 |  |  |  | 2020-05-16 14:56 |  |  | 2020-04-04 14:08 | 2020-04-04 14:08 | 2020-05-16 14:56 | Yes | -5
VD-9001-307A1-DWG-047 | 0 | MOTOR OUTLINE DRAWING FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-03-13 09:07 | 2020-03-13 09:08 | Yes | 68 |  |  | 2020-04-08 08:44 | [5 empty] | 2020-04-08 08:44 | Yes | 12 | 1204-Owner-v | 2020-04-23 18:03
VD-9001-307A1-DWG-048 | 0 | MOTOR OUTLINE DRAWING FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-03-13 09:07 | 2020-03-13 09:08 | Yes | 68 |  |  | 2020-04-08 14:21 | [5 empty] | 2020-04-08 21:00 | Yes | 12 | 1204-Owner-v | 2020-04-23 18:04
VD-9001-307A1-DWG-049 | 0 | MOTOR OUTLINE DRAWING FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-03-13 09:07 | 2020-03-13 09:08 | Yes | 68 |  |  |  | 2020-04-20 14:14 |  |  |  |  | 2020-04-20 14:14 | Yes | 24
VD-9001-307A1-DWG-050 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-051 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-052 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-053 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-054 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-055 | 0 | MOTOR OUTLINE DRAWING FOR LUBE OIL AUX PUMP P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-056 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-057 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-058 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-059 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-060 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-061 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 |  |  | No | 166 | [9 empty] | No | 0
VD-9001-307A1-DWG-062 | 0 | LUBE OIL STATION GA DRAWING FOR CONVERTER BW CIRCULATION PUMP UNIT P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-19 09:32 | 2020-05-19 09:32 | Yes | 106 |  |  |  | 2020-06-01 12:33 |  |  |  |  | 2020-06-01 12:33 | Yes | -1
VD-9001-307A1-DWG-063 | 0 | LUBE OIL STATION GA DRAWING FOR FIRST SATURATOR PUMP UNIT P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-19 09:32 | 2020-05-19 09:32 | Yes | 106 |  |  |  | 2020-06-01 12:36 |  |  |  |  | 2020-06-01 12:36 | Yes | -1
VD-9001-307A1-DWG-064 | 0 | LUBE OIL STATION GA DRAWING FOR HP BOILER FEED WATER PUMP UNITS P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-19 09:31 | 2020-05-19 09:32 | Yes | 106 |  |  |  | 2020-06-08 10:55 |  |  |  |  | 2020-06-08 10:55 | Yes | 6
VD-9001-307A1-DWG-065 | 0 | LUBE OIL STATION GA DRAWING FOR HP BOILER FEED WATER PUMP UNIT P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-04-01 10:42 | 2020-04-01 10:42 | Yes | 58 |  |  |  | 2020-04-28 15:09 |  |  |  |  | 2020-04-28 15:09 | Yes | 13 | 1204-Owner-v | 2020-04-23 18:04
VD-9001-307A1-DWG-066 | 0 | LUBE OIL STATION GA DRAWING FOR MP BOILER FEED WATER PUMP UNIT P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-19 09:34 | 2020-05-19 09:34 | Yes | 106 |  |  |  | 2020-06-08 10:28 |  |  |  |  | 2020-06-08 10:28 | Yes | 6
VD-9001-307A1-DWG-067 | 0 | LUBE OIL STATION GA DRAWING FOR COOLING WATER SUPPLY PUMP UNITS P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-19 09:31 | 2020-05-19 09:33 | Yes | 106 |  |  |  | 2020-06-01 12:38 |  |  |  |  | 2020-06-01 12:38 | Yes | -1
VD-9001-307A1-DWG-068 | 0 | GEAR BOX DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-26 07:59 | 2020-05-26 07:59 | Yes | 113 |  |  |  |  | 2020-06-10 11:17 |  |  |  | 2020-06-10 11:17 | Yes | 1
VD-9001-307A1-DWG-069 | 0 | GEAR BOX DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-26 07:59 | 2020-05-26 08:00 | Yes | 113 |  |  |  |  | 2020-06-10 11:24 |  |  |  | 2020-06-10 11:24 | Yes | 1
VD-9001-307A1-DWG-070 | 0 | GEAR BOX DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-26 07:59 | 2020-05-26 07:59 | Yes | 113 |  |  |  |  | 2020-06-10 11:21 |  |  |  | 2020-06-10 11:21 | Yes | 1
VD-9001-307A1-DWG-071 | 0 | GEAR BOX DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-03 | 2020-05-26 07:59 | 2020-05-26 07:59 | Yes | 113 |  |  |  |  | 2020-06-10 11:23 |  |  |  | 2020-06-10 11:23 | Yes | 1
VD-9001-307A1-DWG-130 | 0 | LOCAL GAUGE BOARD DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-131 | 0 | LOCAL GAUGE BOARD DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-132 | 0 | LOCAL GAUGE BOARD DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-133 | 0 | LOCAL GAUGE BOARD DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-134 | 0 | START-STOP SEQUENCES FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 |  |  | No | 121 | [9 empty] | No | 0
VD-9001-307A1-DWG-135 | 0 | START-STOP SEQUENCES FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 |  |  | No | 121 | [9 empty] | No | 0
VD-9001-307A1-DWG-136 | 0 | START-STOP SEQUENCES FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 |  |  | No | 121 | [9 empty] | No | 0
VD-9001-307A1-DWG-137 | 0 | START-STOP SEQUENCES FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 |  |  | No | 121 | [9 empty] | No | 0
VD-9001-307A1-DWG-138 | 0 | START-STOP SEQUENCES FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 |  |  | No | 121 | [9 empty] | No | 0
VD-9001-307A1-DWG-139 | 0 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-31 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 109 |  |  |  | 2020-06-03 10:48 |  |  |  |  | 2020-06-03 10:48 | Yes | 1
VD-9001-307A1-DWG-140 | 0 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-01-31 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 109 |  |  |  | 2020-06-03 10:52 |  |  |  |  | 2020-06-03 10:52 | Yes | 1
VD-9001-307A1-DWG-141 | 0 | SURFACE CONDENSER OUTLINE DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-31 |  |  | No | 140 | [9 empty] | No | 0
VD-9001-307A1-DWG-142 | 0 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-31 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 109 |  |  |  | 2020-06-02 10:46 |  |  |  |  | 2020-06-02 10:46 | Yes | 0
VD-9001-307A1-DWG-143 | 0 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-31 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 109 |  |  |  | 2020-06-03 10:51 |  |  |  |  | 2020-06-03 10:51 | Yes | 1
VD-9001-307A1-DWG-144 | 0 | LUBE OIL COOLER DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 108 |  |  |  | 2020-06-02 13:24 |  |  |  |  | 2020-06-02 13:24 | Yes | 0
VD-9001-307A1-DWG-145 | 0 | LUBE OIL COOLER DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-19 09:42 | 2020-05-19 09:43 | Yes | 108 |  |  |  | 2020-06-03 10:55 |  |  |  |  | 2020-06-03 10:55 | Yes | 1
VD-9001-307A1-DWG-146 | 0 | LUBE OIL COOLER DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-19 09:42 | 2020-05-19 09:44 | Yes | 108 |  |  |  | 2020-06-02 13:27 |  |  |  |  | 2020-06-02 13:27 | Yes | 0
VD-9001-307A1-DWG-147 | 0 | LUBE OIL COOLER DRAWING FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-01 10:43 | 2020-04-01 10:43 | Yes | 60 |  |  |  | 2020-05-06 15:40 |  |  |  |  | 2020-05-06 15:40 | Yes | 21 | 1204-Owner-v | 2020-04-23 18:04
VD-9001-307A1-DWG-148 | 0 | LUBE OIL COOLER DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-19 09:42 | 2020-05-19 09:44 | Yes | 108 |  |  |  | 2020-06-08 08:19 |  |  |  |  | 2020-06-08 08:20 | Yes | 6
VD-9001-307A1-DWG-149 | 0 | LUBE OIL COOLER DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-19 09:44 | 2020-05-19 09:44 | Yes | 108 |  |  |  | 2020-06-03 10:56 |  |  |  |  | 2020-06-03 10:56 | Yes | 1
VD-9001-307A1-DWG-150 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-06-08 07:56 | 2020-06-08 07:56 | Yes | 128 | [9 empty] | No | -3
VD-9001-307A1-DWG-151 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-06-08 07:56 | 2020-06-08 07:56 | Yes | 128 | [9 empty] | No | -3
VD-9001-307A1-DWG-152 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-06-08 07:56 | 2020-06-08 07:57 | Yes | 128 | [9 empty] | No | -3
VD-9001-307A1-DWG-153 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-01 10:43 | 2020-04-01 10:43 | Yes | 60 |  |  |  | 2020-05-03 12:45 |  |  |  |  | 2020-05-03 12:45 | Yes | 18 | 1204-Owner-v | 2020-04-23 18:04
VD-9001-307A1-DWG-154 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-06-08 07:56 | 2020-06-08 07:57 | Yes | 128 | [9 empty] | No | -3
VD-9001-307A1-DWG-155 | 0 | RUN DOWN TANK GA DRAWING FOR UNIT P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-06-08 07:56 | 2020-06-08 07:57 | Yes | 128 | [9 empty] | No | -3
VD-9001-307A1-DWG-156 | 0 | Oil purifier DWG | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  | 2020-05-19 09:44 | Yes | 139 | [6 empty] | 2020-05-19 10:51 | 2020-05-19 10:51 |  | Yes | 0
VD-9001-307A1-DWG-157 | 0 | General Arrangement Drawing TWO-STAGE STEAM EJECTOR for PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DWG-158 | 0 | Lube oil heater drawings for PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-159 | 0 | Lube oil heater drawings for PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-160 | 0 | Lube oil heater drawings for PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-161 | 0 | Lube oil heater drawings for P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-162 | 0 | Lube oil heater drawings for PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-163 | 0 | Lube oil heater drawings for PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DWG-164 | 0 | INSTRUMENT LAYOUT & CABLE ROUTING DRAWING FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-DWG-165 | 0 | INSTRUMENT LAYOUT & CABLE ROUTING DRAWING FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-DWG-166 | 0 | INSTRUMENT LAYOUT & CABLE ROUTING DRAWING FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-DWG-167 | 0 | INSTRUMENT LAYOUT & CABLE ROUTING DRAWING FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-DWG-168 | 0 | INSTRUMENT LAYOUT & CABLE ROUTING DRAWING FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-DSH-001 | 0 | PUMP DATASHEET WITH CURVE FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:45 | 2019-12-28 12:46 | Yes | -3 |  |  |  | 2020-01-19 16:25 |  |  |  |  | 2020-01-19 18:58 | Yes | 8 | 1204-Owner-v | 2019-12-29 15:11
VD-9001-307A1-DSH-002 | 0 | PUMP DATASHEET WITH CURVE FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:46 | 2019-12-28 12:46 | Yes | -3 |  |  |  | 2020-01-19 16:22 |  |  |  |  | 2020-01-19 18:58 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:05
VD-9001-307A1-DSH-003 | 0 | PUMP DATASHEET WITH CURVE FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:46 | 2019-12-28 12:46 | Yes | -3 |  |  |  | 2020-01-19 16:18 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:05
VD-9001-307A1-DSH-004 | 0 | PUMP DATASHEET WITH CURVE FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:46 | 2019-12-28 12:46 | Yes | -3 |  |  |  | 2020-01-19 16:15 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:06
VD-9001-307A1-DSH-005 | 0 | PUMP DATASHEET WITH CURVE FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:46 | 2019-12-28 12:47 | Yes | -3 |  |  |  | 2020-01-22 08:36 |  |  |  |  | 2020-01-22 18:56 | Yes | 11 | 1204-Owner-v | 2020-01-07 10:06
VD-9001-307A1-DSH-006 | 0 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:46 | 2019-12-28 12:47 | Yes | -3 |  |  |  | 2020-01-19 16:12 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:07
VD-9001-307A1-DSH-007 | 0 | MOTOR DATASHEET WITH CURVE FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:26 | 2020-02-08 09:37 | Yes | 19 |  |  |  |  | 2020-02-10 11:25 |  |  |  | 2020-02-10 11:36 | Yes | -12
VD-9001-307A1-DSH-008 | 0 | MOTOR DATASHEET WITH CURVE FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:26 | 2020-02-08 09:41 | Yes | 19 |  |  |  |  | 2020-02-10 11:31 |  |  |  | 2020-02-10 11:31 | Yes | -12
VD-9001-307A1-DSH-009 | 0 | MOTOR DATASHEET WITH CURVE FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:21 | 2020-02-08 09:38 | Yes | 19 |  |  |  |  | 2020-02-10 11:27 |  |  |  | 2020-02-10 11:27 | Yes | -12
VD-9001-307A1-DSH-010 | 0 | MOTOR DATASHEET WITH CURVE FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:42 | 2020-02-08 09:43 | Yes | 19 |  |  |  |  | 2020-02-10 11:35 |  |  |  | 2020-02-10 11:35 | Yes | -12
VD-9001-307A1-DSH-011 | 0 | MOTOR DATASHEET WITH CURVE FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:21 | 2020-02-08 09:41 | Yes | 19 |  |  |  |  | 2020-02-10 11:33 |  |  |  | 2020-02-10 11:33 | Yes | -12
VD-9001-307A1-DSH-012 | 0 | MOTOR DATASHEET WITH CURVE FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-20 | 2020-02-08 09:26 | 2020-02-08 09:42 | Yes | 19 |  |  |  |  | 2020-02-10 11:34 |  |  |  | 2020-02-10 11:34 | Yes | -12
VD-9001-307A1-DSH-013 | 0 | MOTOR DATASHEET WITH CURVE FOR LUBE OIL AUX PUMP P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-014 | 0 | MOTOR DATASHEET WITH CURVE FOR LUBE OIL AUX PUMP P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-015 | 0 | MOTOR DATASHEET FOR WITH CURVE LUBE OIL AUX PUMP P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-016 | 0 | MOTOR DATASHEET WITH CURVE FOR LUBE OIL AUX PUMP P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-017 | 0 | MOTOR DATASHEET WITH CURVE FOR LUBE OIL AUX PUMP P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-018 | 0 | MOTOR DATASHEET FOR WITH CURVE LUBE OIL AUX PUMP P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-019 | 0 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:48 | 2019-12-28 12:48 | Yes | -3 |  |  |  | 2020-01-19 16:08 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:07
VD-9001-307A1-DSH-020 | 0 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:50 | 2019-12-28 12:50 | Yes | -3 |  |  |  | 2020-01-19 16:03 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:07
VD-9001-307A1-DSH-021 | 0 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:51 | 2019-12-28 12:51 | Yes | -3 |  |  |  | 2020-01-19 15:50 |  |  |  |  | 2020-01-19 18:56 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:08
VD-9001-307A1-DSH-022 | 0 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:55 | 2019-12-28 12:55 | Yes | -3 |  |  |  | 2020-01-19 16:04 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:08
VD-9001-307A1-DSH-023 | 0 | STEAM TURBINE DATASHEET WITH CURVE FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:55 | 2019-12-28 12:55 | Yes | -3 |  |  |  | 2020-01-19 15:55 |  |  |  |  | 2020-01-19 18:57 | Yes | 8 | 1204-Owner-v | 2020-01-07 10:09
VD-9001-307A1-DSH-024 | 0 | LUBE OIL STATION DATASHEET FOR CONVERTER BW CIRCULATION PUMPS P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-025 | 0 | LUBE OIL STATION DATASHEET FOR FIRST SATURATOR PUMPS P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-026 | 0 | LUBE OIL STATION DATASHEET FOR HP BOILER FEED WATER PUMPS P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-027 | 0 | LUBE OIL STATION DATASHEET FOR HP BOILER FEED WATER PUMPS P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-13 11:44 | 2020-05-13 11:45 | Yes | 102 |  |  |  |  | 2020-05-30 14:57 |  |  |  | 2020-05-30 14:57 | Yes | 3
VD-9001-307A1-DSH-028 | 0 | LUBE OIL STATION DATASHEET FOR MP BOILER FEED WATER PUMPS P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-029 | 0 | LUBE OIL STATION DATASHEET FOR COOLING WATER SUPPLY PUMPS P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-DSH-030 | 0 | GEAR BOX DATASHEET FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-26 07:54 | 2020-05-26 07:55 | Yes | 115 |  |  |  | 2020-06-09 18:47 |  |  |  |  | 2020-06-09 18:47 | Yes | 0
VD-9001-307A1-DSH-031 | 0 | GEAR BOX DATASHEET FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-26 07:55 | 2020-05-26 07:55 | Yes | 115 |  |  |  | 2020-06-09 18:48 |  |  |  |  | 2020-06-09 18:48 | Yes | 0
VD-9001-307A1-DSH-032 | 0 | GEAR BOX DATASHEET FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-26 07:55 | 2020-05-26 07:55 | Yes | 115 |  |  |  | 2020-06-09 18:48 |  |  |  |  | 2020-06-09 18:48 | Yes | 0
VD-9001-307A1-DWG-072 | 0 | ARC DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-073 | 0 | PUMP NAME PLATE DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:44 | Yes | 44 |  |  | 2020-04-12 09:05 | [5 empty] | 2020-04-12 20:59 | Yes | 4
VD-9001-307A1-DWG-074 | 0 | PUMP NAME PLATE DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:44 | Yes | 44 |  |  | 2020-04-12 11:49 | [5 empty] | 2020-04-12 21:00 | Yes | 4
VD-9001-307A1-DWG-075 | 0 | PUMP NAME PLATE DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:45 | Yes | 44 |  |  | 2020-04-12 11:51 | [5 empty] | 2020-04-12 21:01 | Yes | 4
VD-9001-307A1-DWG-076 | 0 | PUMP NAME PLATE DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:45 | Yes | 44 |  |  | 2020-04-12 11:52 | [5 empty] | 2020-04-12 21:01 | Yes | 4
VD-9001-307A1-DWG-077 | 0 | PUMP NAME PLATE DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:45 | Yes | 44 |  |  | 2020-04-12 11:53 | [5 empty] | 2020-04-12 21:01 | Yes | 4
VD-9001-307A1-DWG-078 | 0 | PUMP NAME PLATE DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-03-25 08:44 | 2020-03-25 08:45 | Yes | 44 |  |  |  | 2020-04-12 11:59 |  |  |  |  | 2020-04-12 21:02 | Yes | 4
VD-9001-307A1-DWG-079 | 0 | MOTOR NAME PLATE DRAWING FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-080 | 0 | MOTOR NAME PLATE DRAWING FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-081 | 0 | MOTOR NAME PLATE DRAWING FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-082 | 0 | MOTOR NAME PLATE DRAWING FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-083 | 0 | MOTOR NAME PLATE DRAWING FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-084 | 0 | MOTOR NAME PLATE DRAWING FOR P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-12 |  |  | No | 128 | [9 empty] | No | 0
VD-9001-307A1-DWG-085 | 0 | STEAM TURBINE NAME PLATE DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-06 13:27 | 2020-05-06 13:27 | Yes | 86 |  |  |  | 2020-05-16 14:41 |  |  |  |  | 2020-05-16 14:41 | Yes | -4
VD-9001-307A1-DWG-086 | 0 | STEAM TURBINE NAME PLATE DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-06 13:27 | 2020-05-06 13:27 | Yes | 86 |  |  |  | 2020-05-16 14:46 |  |  |  |  | 2020-05-16 14:46 | Yes | -4
VD-9001-307A1-DWG-087 | 0 | STEAM TURBINE NAME PLATE DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-06 13:28 | 2020-05-06 13:28 | Yes | 86 |  |  |  | 2020-05-16 14:47 |  |  |  |  | 2020-05-16 14:47 | Yes | -4
VD-9001-307A1-DWG-088 | 0 | STEAM TURBINE NAME PLATE DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-06 13:27 | 2020-05-06 13:27 | Yes | 86 |  |  |  | 2020-05-16 14:48 |  |  |  |  | 2020-05-16 14:48 | Yes | -4
VD-9001-307A1-DWG-089 | 0 | STEAM TURBINE NAME PLATE DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-06 13:27 | 2020-05-06 13:28 | Yes | 86 |  |  |  | 2020-05-16 14:50 |  |  |  |  | 2020-05-16 14:50 | Yes | -4
VD-9001-307A1-DWG-090 | 0 | GEAR BOX NAME PLATE DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-26 08:01 | 2020-05-26 08:01 | Yes | 106 |  |  |  | 2020-06-10 12:13 |  |  |  |  | 2020-06-10 12:13 | Yes | 1
VD-9001-307A1-DWG-091 | 0 | GEAR BOX NAME PLATE DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-26 08:00 | 2020-05-26 08:01 | Yes | 106 |  |  |  | 2020-06-10 12:14 |  |  |  |  | 2020-06-10 12:14 | Yes | 1
VD-9001-307A1-DWG-092 | 0 | GEAR BOX NAME PLATE DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-26 08:00 | 2020-05-26 08:01 | Yes | 106 |  |  |  | 2020-06-10 12:14 |  |  |  |  | 2020-06-10 12:14 | Yes | 1
VD-9001-307A1-DWG-093 | 0 | GEAR BOX NAME PLATE DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-26 08:01 | 2020-05-26 08:01 | Yes | 106 |  |  |  | 2020-06-10 12:15 |  |  |  |  | 2020-06-10 12:15 | Yes | 1
VD-9001-307A1-DWG-094 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-19 09:40 | 2020-05-19 09:40 | Yes | 99 |  |  |  | 2020-05-31 09:29 |  |  |  |  | 2020-05-31 09:29 | Yes | -2
VD-9001-307A1-DWG-095 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-19 09:40 | 2020-05-19 09:41 | Yes | 99 |  |  | 2020-05-31 09:28 | [5 empty] | 2020-05-31 09:28 | Yes | -2
VD-9001-307A1-DWG-096 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-19 09:40 | 2020-05-19 09:41 | Yes | 99 |  |  |  | 2020-05-31 09:27 |  |  |  |  | 2020-05-31 09:27 | Yes | -2
VD-9001-307A1-DWG-097 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-DWG-098 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-19 09:40 | 2020-05-19 09:41 | Yes | 99 |  |  |  | 2020-05-31 09:26 |  |  |  |  | 2020-05-31 09:26 | Yes | -2
VD-9001-307A1-DWG-099 | 0 | LUBE OIL STATION NAME PLATE DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 | 2020-05-19 09:40 | 2020-05-19 09:41 | Yes | 99 |  |  |  | 2020-05-31 09:23 |  |  |  |  | 2020-05-31 09:23 | Yes | -2
VD-9001-307A1-DWG-100 | 0 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2020-05-22 23:29 | 2020-05-22 23:31 | Yes | 97 |  |  |  | 2020-06-06 12:23 |  |  |  |  | 2020-06-06 12:23 | Yes | 1
VD-9001-307A1-DWG-101 | 0 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2020-05-22 23:29 | 2020-05-22 23:31 | Yes | 97 |  |  |  | 2020-06-06 12:24 |  |  |  |  | 2020-06-06 12:24 | Yes | 1
VD-9001-307A1-DWG-102 | 0 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2020-05-22 23:31 | 2020-05-22 23:31 | Yes | 97 |  |  |  | 2020-06-06 12:25 |  |  |  |  | 2020-06-06 12:25 | Yes | 1
VD-9001-307A1-DWG-103 | 0 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2020-05-22 23:29 | 2020-05-22 23:32 | Yes | 97 |  |  |  | 2020-06-06 12:26 |  |  |  |  | 2020-06-06 12:26 | Yes | 1
VD-9001-307A1-DWG-104 | 0 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 97 |  |  |  | 2020-06-06 12:27 |  |  |  |  | 2020-06-06 12:27 | Yes | 1
VD-9001-307A1-DWG-105 | 0 | GLAND SEALING AND LEAK-OFF SCHEMATIC AND BILL OF MATERIAL FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 95 |  |  | 2020-06-02 11:16 | [5 empty] | 2020-06-02 11:16 | Yes | -3
VD-9001-307A1-DWG-106 | 0 | GLAND SEALING AND LEAK-OFF SCHEMATIC AND BILL OF MATERIAL FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 95 |  |  | 2020-06-08 08:29 | [5 empty] | 2020-06-08 08:29 | Yes | 3
VD-9001-307A1-DWG-107 | 0 | GLAND SEALING AND LEAK-OFF SCHEMATIC AND BILL OF MATERIAL FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 95 |  |  | 2020-06-02 11:20 | [5 empty] | 2020-06-02 11:20 | Yes | -3
VD-9001-307A1-DWG-108 | 0 | GLAND SEALING AND LEAK-OFF SCHEMATIC AND BILL OF MATERIAL FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-17 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 95 |  |  | 2020-06-03 10:49 | [5 empty] | 2020-06-03 10:49 | Yes | -2
VD-9001-307A1-DWG-109 | 0 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-06 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 106 |  |  |  | 2020-06-07 09:16 |  |  |  |  | 2020-06-07 09:16 | Yes | 2
VD-9001-307A1-DWG-110 | 0 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-06 | 2020-05-22 23:30 | 2020-05-22 23:32 | Yes | 106 |  |  |  | 2020-06-07 09:28 |  |  |  |  | 2020-06-07 09:28 | Yes | 2
VD-9001-307A1-DWG-111 | 0 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-06 | 2020-05-22 23:31 | 2020-05-22 23:32 | Yes | 106 |  |  |  | 2020-06-07 09:19 |  |  |  |  | 2020-06-07 09:19 | Yes | 2
VD-9001-307A1-DWG-112 | 0 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-06 | 2020-05-22 23:31 | 2020-05-22 23:33 | Yes | 106 |  |  |  | 2020-06-07 09:29 |  |  |  |  | 2020-06-07 09:29 | Yes | 2
VD-9001-307A1-DWG-113 | 0 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-06 | 2020-05-22 23:31 | 2020-05-22 23:33 | Yes | 106 |  |  |  | 2020-06-07 09:29 |  |  |  |  | 2020-06-07 09:29 | Yes | 2
VD-9001-307A1-DWG-114 | 0 | INSTRUMENT HOOK UP DRAWING FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-115 | 0 | INSTRUMENT HOOK UP DRAWING FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-116 | 0 | INSTRUMENT HOOK UP DRAWING FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-117 | 0 | INSTRUMENT HOOK UP DRAWING FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-118 | 0 | INSTRUMENT HOOK UP DRAWING FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-119 | 0 | VIBRATION PPROBE SENSING AREA / SHAFT DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-120 | 0 | VIBRATION PPROBE SENSING AREA / SHAFT DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-121 | 0 | VIBRATION PPROBE SENSING AREA / SHAFT DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-122 | 0 | VIBRATION PPROBE SENSING AREA / SHAFT DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-123 | 0 | VIBRATION PPROBE SENSING AREA / SHAFT DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DWG-124 | 0 | JUNCTION BOX WITH TERMINAL ARRANGEMENT DRAWINGS FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-125 | 0 | JUNCTION BOX WITH TERMINAL ARRANGEMENT DRAWINGS FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-126 | 0 | JUNCTION BOX WITH TERMINAL ARRANGEMENT DRAWINGS FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-127 | 0 | JUNCTION BOX WITH TERMINAL ARRANGEMENT DRAWINGS FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-128 | 0 | JUNCTION BOX WITH TERMINAL ARRANGEMENT DRAWINGS FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DWG-129 | 0 | LOCAL GAUGE BOARD DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DSH-033 | 0 | GEAR BOX DATASHEET FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-26 07:55 | 2020-05-26 07:55 | Yes | 115 |  |  |  | 2020-06-09 18:49 |  |  |  |  | 2020-06-09 18:49 | Yes | 0
VD-9001-307A1-DSH-034 | 0 | MECHANICAL SEAL DATASHEET FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:25 | 2020-02-08 08:26 | Yes | 34 |  |  |  |  | 2020-02-10 11:38 |  |  |  | 2020-02-10 14:24 | Yes | -12
VD-9001-307A1-DSH-035 | 0 | MECHANICAL SEAL DATASHEET FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:24 | 2020-02-08 08:26 | Yes | 34 |  |  |  |  | 2020-02-10 11:39 |  |  |  | 2020-02-10 14:24 | Yes | -12
VD-9001-307A1-DSH-036 | 0 | MECHANICAL SEAL DATASHEET FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:24 | 2020-02-08 08:26 | Yes | 34 |  |  |  |  | 2020-02-10 11:38 |  |  |  | 2020-02-10 14:24 | Yes | -12
VD-9001-307A1-DSH-037 | 0 | MECHANICAL SEAL DATASHEET FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:25 | 2020-02-08 08:27 | Yes | 34 |  |  |  |  | 2020-02-10 11:37 |  |  |  | 2020-02-10 14:24 | Yes | -12
VD-9001-307A1-DSH-038 | 0 | MECHANICAL SEAL DATASHEET FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:25 | 2020-02-08 08:27 | Yes | 34 |  |  |  |  | 2020-02-10 11:39 |  |  |  | 2020-02-10 14:25 | Yes | -12
VD-9001-307A1-DSH-039 | 0 | MECHANICAL SEAL DATASHEET FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-05 | 2020-02-08 08:25 | 2020-02-08 08:27 | Yes | 34 |  |  |  |  | 2020-02-10 11:40 |  |  |  | 2020-02-10 14:25 | Yes | -12
VD-9001-307A1-DSH-040 | 0 | ARC VALVE DATASHEET FOR CONDENSATE PUMPS P-4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-307A1-DSH-041 | 0 | NOISE DATASHEET FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-042 | 0 | NOISE DATASHEET FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-043 | 0 | NOISE DATASHEET FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-044 | 0 | NOISE DATASHEET FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-045 | 0 | NOISE DATASHEET FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-046 | 0 | NOISE DATASHEET FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-05 |  |  | No | 106 | [9 empty] | No | 0
VD-9001-307A1-DSH-047 | 0 | INSTRUMENT DATASHEET FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-DSH-048 | 0 | INSTRUMENT DATASHEET FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-DSH-049 | 0 | INSTRUMENT DATASHEET FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-DSH-050 | 0 | INSTRUMENT DATASHEET FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-DSH-051 | 0 | INSTRUMENT DATASHEET FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-DSH-052 | 0 | Surface Condenser Data Sheet for PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-053 | 0 | Lube oil heater data-sheets for P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-054 | 0 | Lube oil heater data-sheets for P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-055 | 0 | Lube oil heater data-sheets for P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-056 | 0 | Lube oil heater data-sheets for P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-057 | 0 | Lube oil heater data-sheets for P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-058 | 0 | Lube oil heater data-sheets for P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-001 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-002 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-003 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-004 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-005 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-006 | 0 | CALCULATION SHEET OF CONTROL VALVES FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-007 | 0 | CALCULATION SHEET OF SAFETY VALVES FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-008 | 0 | CALCULATION SHEET OF SAFETY VALVES FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-009 | 0 | CALCULATION SHEET OF SAFETY VALVES FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-010 | 0 | CALCULATION SHEET OF SAFETY VALVES FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-CAL-011 | 0 | Stress analysis and calculation for thermo well for PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-CAL-012 | 0 | Stress analysis and calculation for thermo well for PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-CAL-013 | 0 | Stress analysis and calculation for thermo well for PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-CAL-014 | 0 | Stress analysis and calculation for thermo well for P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-CAL-015 | 0 | Stress analysis and calculation for thermo well for PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-CAL-016 | 0 | Stress analysis and calculation for thermo well for PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-PID-001 | 0 | PUMP P&I DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:26 | 2020-03-09 15:30 | Yes | 69 |  |  |  | 2020-04-29 10:42 |  |  |  |  | 2020-04-29 10:42 | Yes | 37
VD-9001-307A1-PID-002 | 0 | PUMP P&I DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:25 | 2020-03-09 15:30 | Yes | 69 |  |  |  | 2020-04-28 15:58 |  |  |  |  | 2020-04-28 20:59 | Yes | 36
VD-9001-307A1-PID-003 | 0 | PUMP P&I DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:25 | 2020-03-09 15:27 | Yes | 69 |  |  |  | 2020-04-29 10:36 |  |  |  |  | 2020-04-29 10:37 | Yes | 37
VD-9001-307A1-PID-004 | 0 | PUMP P&I DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:25 | 2020-03-09 15:27 | Yes | 69 |  |  |  | 2020-04-29 10:41 |  |  |  |  | 2020-04-29 10:41 | Yes | 37
VD-9001-307A1-PID-005 | 0 | PUMP P&I DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:25 | 2020-03-09 15:26 | Yes | 69 |  |  |  | 2020-04-28 16:08 |  |  |  |  | 2020-04-28 20:59 | Yes | 36
VD-9001-307A1-PID-006 | 0 | PUMP P&I DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-03-09 15:25 | 2020-03-09 15:26 | Yes | 69 |  |  |  | 2020-04-29 10:43 |  |  |  |  | 2020-04-29 10:43 | Yes | 37
VD-9001-307A1-PID-007 | 0 | THERMAL SYSTEM DIAGRAM FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2019-12-28 12:48 | 2019-12-28 12:49 | Yes | -49 |  |  |  | 2020-01-28 14:26 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-04 14:00
VD-9001-307A1-PID-008 | 0 | THERMAL SYSTEM DIAGRAM FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2019-12-28 12:49 | 2019-12-28 12:50 | Yes | -49 |  |  |  | 2020-01-28 14:24 |  |  |  |  | 2020-01-28 18:56 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:10
VD-9001-307A1-PID-009 | 0 | THERMAL SYSTEM DIAGRAM FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2019-12-28 12:52 | 2019-12-28 12:52 | Yes | -49 |  |  |  | 2020-01-28 14:47 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:11
VD-9001-307A1-PID-010 | 0 | THERMAL SYSTEM DIAGRAM FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2019-12-28 12:53 | 2019-12-28 12:54 | Yes | -49 |  |  |  | 2020-01-28 14:25 |  |  |  |  | 2020-01-28 18:56 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:11
VD-9001-307A1-PID-011 | 0 | THERMAL SYSTEM DIAGRAM FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 | 2019-12-28 12:56 | 2019-12-28 12:56 | Yes | -49 |  |  |  | 2020-01-28 14:28 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:11
VD-9001-307A1-PID-012 | 0 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:49 | 2019-12-28 12:49 | Yes | -3 |  |  |  | 2020-01-28 15:08 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:12
VD-9001-307A1-PID-013 | 0 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2003A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:50 | 2019-12-28 12:50 | Yes | -3 |  |  |  | 2020-01-28 15:04 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:12
VD-9001-307A1-PID-014 | 0 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P4001AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:52 | 2019-12-28 12:52 | Yes | -3 |  |  |  | 2020-01-28 14:56 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:13
VD-9001-307A1-PID-015 | 0 | LUBE OIL SYSTEM P&I DIAGRAM FOR HP BOILER FEED WATER PUMP P4001C | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-04-01 10:43 | 2020-04-01 10:43 | Yes | 92 |  |  |  |  | 2020-05-13 07:52 |  |  |  | 2020-05-13 07:52 | Yes | 28
VD-9001-307A1-PID-016 | 0 | LUBE OIL STATION P&I DRAWING FOR STEAM TURBINE P4002A | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:54 | 2019-12-28 12:54 | Yes | -3 |  |  |  | 2020-01-28 14:33 |  |  |  |  | 2020-01-28 18:57 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:13
VD-9001-307A1-PID-017 | 0 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P6301AB | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2019-12-28 12:56 | 2019-12-28 12:56 | Yes | -3 |  |  |  | 2020-01-28 11:23 |  |  |  |  | 2020-01-28 18:56 | Yes | 17 | 1204-Owner-v | 2020-01-07 10:14
VD-9001-307A1-DIG-001 | 0 | CAUSE & EFFECT FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-002 | 0 | CAUSE & EFFECT FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-003 | 0 | CAUSE & EFFECT FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-004 | 0 | CAUSE & EFFECT FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-005 | 0 | CAUSE & EFFECT FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-006 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-007 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-008 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-009 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-010 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-011 | 0 | CONNECTION DIAGRAM FOR LUBE OIL HEATER AND OTHER AUXILIARY FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-12 |  |  | No | 159 | [9 empty] | No | 0
VD-9001-307A1-DIG-012 | 0 | LOGIC DIAGRAM AND FUNCTIONAL CHARTS OF INTERLOCKS AND SEQUENCES CONTROL ALSO CAUSE & EFFECT FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DIG-013 | 0 | LOGIC DIAGRAM AND FUNCTIONAL CHARTS OF INTERLOCKS AND SEQUENCES CONTROL ALSO CAUSE & EFFECT FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DIG-014 | 0 | LOGIC DIAGRAM AND FUNCTIONAL CHARTS OF INTERLOCKS AND SEQUENCES CONTROL ALSO CAUSE & EFFECT FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DIG-015 | 0 | LOGIC DIAGRAM AND FUNCTIONAL CHARTS OF INTERLOCKS AND SEQUENCES CONTROL ALSO CAUSE & EFFECT FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DIG-016 | 0 | LOGIC DIAGRAM AND FUNCTIONAL CHARTS OF INTERLOCKS AND SEQUENCES CONTROL ALSO CAUSE & EFFECT FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DOC-001 | 0 | MMS(MACHINE MONITOR SYSTEM) DOCUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-307A1-DOC-002 | 0 | CMS(CONDITION MONITOR SYSTEM) DOCUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-3071A-DOC-003 | 0 | PLC DOCUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-307A1-DOC-004 | 0 | GII&505 DOCUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-307A1-LST-001 | 0 | MODBUS LIST | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-307A1-LST-002 | 0 | SPARE PARTS LIST FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-003 | 0 | SPARE PARTS LIST FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-004 | 0 | SPARE PARTS LIST FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-005 | 0 | SPARE PARTS LIST FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-006 | 0 | SPARE PARTS LIST FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-007 | 0 | SPARE PARTS LIST FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-008 | 0 | SPARE PARTS LIST FOR STEAM TURBINE PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-009 | 0 | SPARE PARTS LIST FOR STEAM TURBINE PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-010 | 0 | SPARE PARTS LIST FOR STEAM TURBINE PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-011 | 0 | SPARE PARTS LIST FOR STEAM TURBINE PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-012 | 0 | SPARE PARTS LIST FOR STEAM TURBINE PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-013 | 0 | 2 years Startup/commissioning Spare Part List For All Motors | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-014 | 0 | SPARE PARTS LIST FOR INSTRUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-015 | 0 | SPECIAL TOOLS LIST | MC-307A1 | Deep Blue Pump Co. | 2020-01-06 |  |  | No | 165 | [9 empty] | No | 0
VD-9001-307A1-LST-016 | 0 | INSTRUMENT LIST FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-017 | 0 | INSTRUMENT LIST FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-018 | 0 | INSTRUMENT LIST FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-019 | 0 | INSTRUMENT LIST FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-020 | 0 | INSTRUMENT LIST FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-021 | 0 | ALARM AND TRIP SET POINT LIST FOR UNIT P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-022 | 0 | ALARM AND TRIP SET POINT LIST FOR UNIT P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-023 | 0 | ALARM AND TRIP SET POINT LIST FOR UNIT P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-024 | 0 | ALARM AND TRIP SET POINT LIST FOR UNIT P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-025 | 0 | ALARM AND TRIP SET POINT LIST FOR UNIT P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-026 | 0 | LUBRICANT LIST | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-027 | 0 | Electric Load List (Include all Electric consumption) | MC-307A1 | Deep Blue Pump Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-307A1-LST-028 | 0 | SUB-VENDOR LIST | MC-307A1 | Deep Blue Pump Co. | 2019-12-31 | 2020-04-16 08:02 | 2020-04-16 08:02 | Yes | 107 |  |  |  | 2020-04-22 12:32 |  |  |  |  | 2020-04-22 12:32 | Yes | -8
VD-9001-307A1-LST-029 | 0 | UTILITY CONSUMPTION LIST | MC-307A1 | Deep Blue Pump Co. | 2020-02-10 |  |  | No | 130 | [9 empty] | No | 0
VD-9001-307A1-LST-030 | 0 | Detailed Packing List | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-LST-031 | 0 | LINE LIST | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-LST-032 | 0 | Equipment list | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-LST-033 | 0 | Tie in point list | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-LST-034 | 0 | Instrument CABLE LIST | MC-307A1 | Deep Blue Pump Co. | 2020-08-31 |  |  | No | -73 | [9 empty] | No | 0
VD-9001-307A1-LST-035 | 0 | I/O list | MC-307A1 | Deep Blue Pump Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307A1-PCJ-001 | 0 | FACTORY PERFORMANCE TEST PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:54 | 2020-04-07 09:58 | Yes | 66 |  |  | 2020-04-12 13:24 | [5 empty] | 2020-04-12 21:03 | Yes | -9
VD-9001-307A1-PCJ-002 | 0 | FACTORY MECHANICAL RUNNING TEST PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:40 | 2020-05-09 08:40 | Yes | 98 |  |  |  | 2020-05-19 10:40 |  |  |  |  | 2020-05-19 10:40 | Yes | -4 | 1204-Owner-v | 2020-06-09 11:10
VD-9001-307A1-PCJ-003 | 0 | FACTORY ACCEPTANCE TEST PROCEDURE for over speed protection(G2) and governor speed control system(WW505) | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-004 | 0 | FACTORY ACCEPTANCE TEST PROCEDURE for machine monitoring system (MMS&CMS) | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-005 | 0 | FACTORY ACCEPTANCE TEST PROCEDURE for machine monitoring system (PLC) | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-006 | 0 | HYDROTATIC TEST PROCEDURE FOR PUMP AND STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:41 | 2020-05-09 08:41 | Yes | 98 |  |  |  | 2020-05-30 09:12 |  |  |  |  | 2020-05-30 09:12 | Yes | 7
VD-9001-307A1-PCJ-007 | 0 | PACKING AND DELIVERY PROCEDURE(WOODEN CASE) FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-008 | 0 | PACKING AND DELIVERY PROCEDURE(STEEEL STRUCTURE) FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:58 | Yes | 66 |  |  |  | 2020-04-12 13:27 |  |  |  |  | 2020-04-12 21:04 | Yes | -9
VD-9001-307A1-PCJ-009 | 0 | SURFACE PREPARATION AND PAINTING PROCEDURE FOR PUMP AND STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-18 07:38 | 2020-04-18 07:39 | Yes | 77 |  |  |  | 2020-05-02 18:57 |  |  |  |  | 2020-05-02 18:57 | Yes | 0
VD-9001-307A1-PCJ-010 | 0 | BALANCING TEST PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-011 | 0 | NDT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-012 | 0 | PWHT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:59 | Yes | 66 |  |  |  | 2020-04-18 13:54 |  |  |  |  | 2020-04-18 21:01 | Yes | -3
VD-9001-307A1-PCJ-013 | 0 | HEAT TREATMENT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:59 | Yes | 66 |  |  |  | 2020-04-18 13:58 |  |  |  |  | 2020-04-18 21:02 | Yes | -3
VD-9001-307A1-PCJ-014 | 0 | MATERIAL TRACEABILITY & IDENTIFICATION PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:59 | Yes | 66 |  |  | 2020-04-12 13:25 | [5 empty] | 2020-04-12 21:03 | Yes | -9
VD-9001-307A1-PCJ-015 | 0 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:59 | 2020-04-07 09:59 | Yes | 66 |  |  |  | 2020-04-14 12:23 |  |  |  |  | 2020-04-14 21:01 | Yes | -7
VD-9001-307A1-PCJ-016 | 0 | REPAIR WELDIING PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:59 | Yes | 66 |  |  |  | 2020-04-14 12:21 |  |  |  |  | 2020-04-14 21:01 | Yes | -7
VD-9001-307A1-PCJ-017 | 0 | LONG TERM STORAGE PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-04-07 09:55 | 2020-04-07 09:59 | Yes | 66 |  |  | 2020-04-12 13:26 | [5 empty] | 2020-04-12 21:04 | Yes | -9
VD-9001-307A1-PCJ-018 | 0 | INSPECTION AND SHOP TEST PROCEDURE FOR MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:41 | 2020-05-09 08:42 | Yes | 98 |  |  | 2020-05-27 11:49 | [5 empty] | 2020-05-27 11:49 | Yes | 4
VD-9001-307A1-PCJ-019 | 0 | HARDNESS TEST PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-PCJ-020 | 0 | FACTORY PERFORMANCE TEST PROCEDURE FOR LUBE OIL SYSTEM P2002A/P2003A/P4001AB/P4001C/P4002A/P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:42 | 2020-05-09 08:42 | Yes | 98 |  |  |  | 2020-05-26 10:56 |  |  |  |  | 2020-05-26 10:56 | Yes | 3
VD-9001-307A1-PCJ-021 | 0 | LONG TERM STORAGE PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:43 | 2020-05-09 08:44 | Yes | 98 |  |  | 2020-05-10 17:56 | [5 empty] | 2020-05-10 17:56 | Yes | -13
VD-9001-307A1-WMP-001 | 0 | WELDING MAP FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-NPL-001 | 0 | NDT MAP FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-NPL-002 | 0 | NDT MAP FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 | 2020-05-09 08:39 | 2020-05-09 08:40 | Yes | 98 |  |  | 2020-05-27 09:44 | [5 empty] | 2020-05-27 09:44 | Yes | 4
VD-9001-307A1-WPS-001 | 0 | WPS & PQR FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-MNL-001 | 0 | PUMP IOM FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-10-15 |  |  | No | -118 | [9 empty] | No | 0
VD-9001-307A1-MNL-002 | 0 | PUMP IOM FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-003 | 0 | PUMP IOM FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-004 | 0 | PUMP IOM FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-005 | 0 | PUMP IOM FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-006 | 0 | PUMP IOM FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-007 | 0 | STEAM TURBINE IOM FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-MNL-008 | 0 | STEAM TURBINE IOM FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-MNL-009 | 0 | STEAM TURBINE IOM FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-MNL-010 | 0 | STEAM TURBINE IOM FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-MNL-011 | 0 | STEAM TURBINE IOM FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-MNL-012 | 0 | MOTOR INSTALLATION, OPERATION & MAINTENANCE MANUAL | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-013 | 0 | COUPLING INSTALLATION, OPERATION & MAINTENANCE MANUAL | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-014 | 0 | MECHANICAL SEAL INSTALLATION, OPERATION & MAINTENANCE MANUAL | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-015 | 0 | MECHANICAL SEAL SYSTEM INSTALLATION, OPERATION & MAINTENANCE MANUAL | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-016 | 0 | Installation/ Operation/ Maintenance manuals of GOVERNOR system (WW505) | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MNL-017 | 0 | Installation/ Operation/ Maintenance manuals of OVER SPEED PROTECTION system (GII) | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-001 | 0 | PUMP CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-002 | 0 | MOTOR CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-003 | 0 | MECHANICAL SEAL CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-004 | 0 | STEAM TURBINE CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-005 | 0 | COUPLING CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-006 | 0 | I/H CONVERTER CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-007 | 0 | SOLENOID VALVE CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-CAT-008 | 0 | INSTUMENT CATALOGUE | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-INX-001 | 0 | FINAL BOOK INDEX | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A1-MDB-001 | 0 | FINAL BOOK | MC-307A1 | Deep Blue Pump Co. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-307A-DIG-021 | 2 | P&ID ink. Parts List (Turbine) | MC-307A | KSB GERMANY | 2019-12-29 16:32 | 2019-12-29 16:33 |  | No | 173 | [9 empty] | No | 0
VD-9001-301-DCR-007 | 0 | nozzle load syngas turbine (customer data) | MC-301 | Siemens AG | 2019-12-29 | 2019-12-29 17:36 |  | No | 173 | [9 empty] | No | 0
VD-9001-301-DCR-008 | 0 | nozzle load circulator turbine (customer data) | MC-301 | Siemens AG | 2019-12-29 | 2019-12-29 17:36 |  | No | 173 | [9 empty] | No | 0
VD-9001-251B-SPD-010 | 1 | Single Part DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-01-04 | 2020-01-08 12:26 | 2020-01-08 12:27 | Yes | 4 |  |  |  | 2020-02-08 14:30 |  |  |  |  | 2020-02-08 14:30 | Yes | 17
VD-9001-251B-SAD-010 | 1 | Assembly DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-01-04 | 2020-01-08 12:06 | 2020-01-08 12:17 | Yes | 4 |  |  |  | 2020-02-08 14:31 |  |  |  |  | 2020-02-08 14:31 | Yes | 17 | 1204-Owner-v | 2020-02-16 12:14
VD-9001-251B-RPT-010 | 1 | Reports for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-01-04 | 2020-01-08 11:29 | 2020-01-08 11:29 | Yes | 4 |  |  |  | 2020-02-08 14:33 |  |  |  |  | 2020-02-08 14:33 | Yes | 17
VD-9001-251B-GAD-010 | 1 | General Arrangement DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-01-04 | 2020-01-08 11:28 | 2020-01-08 11:29 | Yes | 4 |  |  |  | 2020-02-08 14:34 |  |  |  |  | 2020-02-08 14:34 | Yes | 17
VD-9001-251-PPL-016 | 2 | Local Panel Layout & Wiring Diagram | HM-251 | KT – Kinetics Technology SpA | 2020-01-07 |  |  | No | 164 | [9 empty] | No | 0
VD-9001-257B-DIS-001 | 1 | VENDOR DOCUMENTS INDEX & SCHEDULE | HM-257B | FATEH SANAT KIMIA | 2020-01-06 | 2020-01-07 11:06 | 2020-01-07 11:07 | Yes | 1 |  |  | 2020-01-07 17:39 | [5 empty] | 2020-01-07 17:39 | Yes | -14
VD-9001-254-DWG-1002 | 1 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 4/6 | HM-254 | AZAR AB | 2020-01-04 16:09 | 2020-01-04 16:47 | 2020-01-04 16:47 | Yes | 0 |  |  |  |  | 2020-02-24 11:07 |  |  |  | 2020-02-24 11:07 | Yes | 37
VD-9001-254-DWG-996 | 1 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 7/9 | HM-254 | AZAR AB | 2020-01-04 16:48 | 2020-01-04 16:52 | 2020-01-04 16:53 | Yes | 0 |  |  |  |  | 2020-02-24 11:26 |  |  |  | 2020-02-24 11:26 | Yes | 37
VD-9001-257C-GAD-003 | 5 | GENERAL ARRANGEMENT (4137-0366) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-05 09:01 | 2020-01-07 13:45 | 2020-01-07 13:51 | Yes | 2 |  |  | 2020-02-16 11:13 | [5 empty] | 2020-02-16 11:13 | Yes | 26 | 1204-Owner-v | 2020-02-12 17:24
VD-9001-257C-DWG-014 | 5 | DETAILS DRAWING (4137-0366/2) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-05 09:01 | 2020-01-07 13:54 | 2020-01-07 13:54 | Yes | 2 |  |  | 2020-02-16 11:06 | [5 empty] | 2020-02-16 11:06 | Yes | 26 | 1204-Owner-v | 2020-03-07 09:51
VD-9001-257C-DWG-020 | 5 | DETAILS DRAWING (4137-0367/2) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-05 09:02 | 2020-01-07 13:55 | 2020-01-07 13:55 | Yes | 2 |  |  | 2020-02-16 11:00 | [5 empty] | 2020-02-16 11:00 | Yes | 26 | 1204-Owner-v | 2020-05-09 10:23
VD-9001-257C-DWG-064 | 4 | DETAILS DRAWING (4137-0367/3) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-05 09:13 | 2020-01-07 14:01 | 2020-01-07 14:01 | Yes | 2 |  |  | 2020-02-05 11:29 | [5 empty] | 2020-02-05 11:29 | Yes | 15 | 1204-Owner-v | 2020-05-09 10:26
VD-9001-257C-CAL-013 | 4 | PIPING STRESS ANALYSIS (4137-0367/PSA) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-05 09:13 | 2020-01-07 13:58 | 2020-01-07 13:59 | Yes | 2 |  |  | 2020-02-05 11:31 | [5 empty] | 2020-02-05 11:31 | Yes | 15
VD-9001-307A1-WPQ-001 | 0 | WELDER / OPERATOR QUALIFICATION REPORT FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-02-01 |  |  | No | 139 | [9 empty] | No | 0
VD-9001-307A1-WPQ-002 | 0 | WELDER / OPERATOR QUALIFICATION REPORT FOR STEAM TURBINE FOR P2002A/P2003A/P4001AB/P4002A/P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-20 |  |  | No | 91 | [9 empty] | No | 0
VD-9001-307A1-RPT-001 | 0 | NDT TEST REPORT FOR STEAM TURBINE FOR PT2002A/PT2003A/PT4001AB/PT4002A/PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-002 | 0 | HYDROSTATIC TEST REPORT FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-003 | 0 | BALANCE TEST REPORT FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-004 | 0 | BALANCE TEST REPORT FOR STEAM TURINE FOR PT2002A/PT2003A/PT4001AB/PT4002A/PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-005 | 0 | PERFORMANCE TEST AND RUNNING TEST REPORT FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-006 | 0 | TEST REPORT FOR MAIN MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-007 | 0 | TEST REPORT FOR OIL SYSTEM AUXILIARY MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-008 | 0 | Torsional analysis report for PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-009 | 0 | Torsional analysis report for PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-010 | 0 | Torsional analysis report for PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-011 | 0 | Torsional analysis report for PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-012 | 0 | Torsional analysis report for PT6301A/B | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-RPT-013 | 0 | HAZOP & SIL reports | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-CER-001 | 0 | Final Certificate of Compliance (MANUFACTURER's CERTIFICATE of COMPLIANCE) | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-DWG-169 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-170 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-171 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-172 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-173 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-174 | 0 | LUBE OIL STATION AUXILIARY ELECTRICAL MOTOR NAME PLATE DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-175 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-176 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-177 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-178 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-179 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DWG-180 | 0 | LUBE OIL STATION AUXILIARY MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-307A1-DOC-005 | 0 | HSE DOCUMENTS | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DSH-059 | 0 | Material Safety Datasheet for Lube oil | MC-307A1 | Deep Blue Pump Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-307A1-DIG-017 | 0 | LOOP WIRING DIAGRAM FOR PT2002A/PT2003A/PT4001AB/PT4002A/PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-257B-PCJ-037 | 1 | TUBE EXPAND PROCEDURE | HM-257B | FATEH SANAT KIMIA | 2020-01-23 | 2020-01-12 12:35 | 2020-01-12 12:35 | Yes | -11 |  |  | 2020-02-05 11:20 | [5 empty] | 2020-02-05 11:20 | Yes | 10 | 1204-Owner-v | 2020-02-09 11:36
VD-9001-257C-LST-004 | 4 | MASTER & DETAILED PACKING LIST (4137/PL) | HM-257C | Brembana & Rolle S.p.A. | 2020-01-23 |  |  | No | 148 | [9 empty] | No | 0
VD-9001-254-DSH-107 | 0 | DATA SHEET OF SEAL AIR FAN | HM-254 | AZAR AB | 2020-01-19 | 2020-01-20 07:58 | 2020-01-20 07:58 | Yes | 1 |  |  |  | 2020-05-02 07:57 |  |  |  |  | 2020-05-02 07:57 | Yes | 89
VD-9001-307A1-DSH-021 | 1 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-03-13 09:04 | 2020-03-13 09:05 | Yes | 40 |  |  |  |  | 2020-04-27 07:53 |  |  |  | 2020-04-27 07:53 | Yes | 31 | 1204-Owner-v | 2020-03-14 10:28
VD-9001-307A1-DSH-023 | 1 | STEAM TURBINE DATASHEET WITH CURVE FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-03-13 09:04 | 2020-03-13 09:05 | Yes | 40 |  |  |  |  | 2020-04-08 13:57 |  |  |  | 2020-04-08 21:00 | Yes | 12 | 1204-Owner-v | 2020-03-14 10:31
VD-9001-307A1-DSH-020 | 1 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-03-13 09:04 | 2020-03-13 09:05 | Yes | 40 |  |  |  |  | 2020-04-27 07:51 |  |  |  | 2020-04-27 07:51 | Yes | 31 | 1204-Owner-v | 2020-04-29 13:44
VD-9001-307A1-DSH-022 | 1 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-03-13 09:04 | 2020-03-13 09:05 | Yes | 40 |  |  |  |  | 2020-04-27 07:54 |  |  |  | 2020-04-27 07:54 | Yes | 31 | 1204-Owner-v | 2020-03-14 10:30
VD-9001-307A1-DSH-019 | 1 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-03-13 09:01 | 2020-03-13 09:02 | Yes | 40 |  |  |  |  | 2020-04-27 07:52 |  |  |  | 2020-04-27 07:52 | Yes | 31 | 1204-Owner-v | 2020-03-14 10:25
VD-9001-307A1-DSH-006 | 1 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-02-24 12:46 | 2020-02-24 12:47 | Yes | 22 |  |  |  |  | 2020-03-03 12:21 |  |  |  | 2020-03-03 12:21 | Yes | -6
VD-9001-307A1-DSH-004 | 1 | PUMP DATASHEET WITH CURVE FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-02-24 12:46 | 2020-02-24 12:47 | Yes | 22 |  |  |  |  | 2020-03-02 11:50 |  |  |  | 2020-03-02 20:01 | Yes | -7
VD-9001-307A1-DSH-003 | 1 | PUMP DATASHEET WITH CURVE FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-02-24 12:46 | 2020-02-24 12:47 | Yes | 22 |  |  |  |  | 2020-03-02 11:55 |  |  |  | 2020-03-02 20:01 | Yes | -7
VD-9001-307A1-DSH-002 | 1 | PUMP DATASHEET WITH CURVE FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-02-24 12:46 | 2020-02-24 12:47 | Yes | 22 |  |  |  |  | 2020-03-07 12:42 |  |  |  | 2020-03-07 12:42 | Yes | -2
VD-9001-307A1-DSH-001 | 1 | PUMP DATASHEET WITH CURVE FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-02 18:56 | 2020-02-24 12:45 | 2020-02-24 12:47 | Yes | 22 |  |  |  |  | 2020-03-02 11:21 |  |  |  | 2020-03-02 20:01 | Yes | -7
VD-9001-307A1-DSH-005 | 1 | PUMP DATASHEET WITH CURVE FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-05 18:56 | 2020-02-24 12:46 | 2020-02-24 12:47 | Yes | 19 |  |  |  | 2020-03-03 12:25 |  |  |  |  | 2020-03-03 12:25 | Yes | -6
VD-9001-257B-WMP-038 | 2 | WELDING AND NDT MAP | HM-257B | FATEH SANAT KIMIA | 2020-01-26 17:24 | 2020-01-27 08:10 | 2020-01-27 08:10 | Yes | 1 |  |  |  | 2020-02-24 08:32 |  |  |  |  | 2020-02-24 08:32 | Yes | 14
VD-9001-307A1-PID-017 | 1 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-19 13:26 | 2020-03-19 13:26 | Yes | 44 |  |  |  |  | 2020-05-13 07:59 |  |  |  | 2020-05-13 07:59 | Yes | 41
VD-9001-307A1-PID-008 | 1 | THERMAL SYSTEM DIAGRAM FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-14 07:32 | 2020-03-14 07:33 | Yes | 39 |  |  |  |  | 2020-05-07 12:15 |  |  |  | 2020-05-07 12:15 | Yes | 40
VD-9001-307A1-PID-010 | 1 | THERMAL SYSTEM DIAGRAM FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-14 07:33 | 2020-03-14 07:33 | Yes | 39 |  |  |  |  | 2020-05-10 17:33 |  |  |  | 2020-05-10 17:33 | Yes | 43
VD-9001-307A1-PID-007 | 1 | THERMAL SYSTEM DIAGRAM FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-14 07:32 | 2020-03-14 07:33 | Yes | 39 |  |  |  |  | 2020-05-03 18:45 |  |  |  | 2020-05-03 21:03 | Yes | 36
VD-9001-307A1-PID-011 | 1 | THERMAL SYSTEM DIAGRAM FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-14 07:33 | 2020-03-14 07:33 | Yes | 39 |  |  |  |  | 2020-05-10 17:28 |  |  |  | 2020-05-10 17:28 | Yes | 43 | 1204-Owner-v | 2020-06-15 13:16
VD-9001-307A1-PID-016 | 1 | LUBE OIL STATION P&I DRAWING FOR STEAM TURBINE P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-19 13:25 | 2020-03-19 13:25 | Yes | 44 |  |  |  |  | 2020-05-13 07:58 |  |  |  | 2020-05-13 07:58 | Yes | 41
VD-9001-307A1-PID-009 | 1 | THERMAL SYSTEM DIAGRAM FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-14 07:33 | 2020-03-14 07:33 | Yes | 39 |  |  |  |  | 2020-06-02 10:01 |  |  |  | 2020-06-02 10:01 | Yes | 66
VD-9001-307A1-PID-014 | 1 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-19 13:23 | 2020-03-19 13:23 | Yes | 44 |  |  |  |  | 2020-05-07 11:42 |  |  |  | 2020-05-07 11:42 | Yes | 35
VD-9001-307A1-PID-013 | 1 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-19 13:20 | 2020-03-19 13:20 | Yes | 44 |  |  |  |  | 2020-05-07 10:04 |  |  |  | 2020-05-07 10:04 | Yes | 35
VD-9001-307A1-PID-012 | 1 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-04 | 2020-03-19 13:19 | 2020-03-19 13:20 | Yes | 44 |  |  |  |  | 2020-05-12 18:14 |  |  |  | 2020-05-12 18:14 | Yes | 40
VD-9001-307A1-DWG-010 | 1 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(MOTOR DRIVEN) P6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-09 14:31 | 2020-03-09 14:31 | Yes | 22 |  |  |  | 2020-05-06 14:26 |  |  |  |  | 2020-05-06 14:26 | Yes | 44 | 1204-Owner-v | 2020-04-23 18:03
VD-9001-307A1-DWG-004 | 1 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(MOTOR DRIVEN) P2003B | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-09 14:30 | 2020-03-09 14:31 | Yes | 22 |  |  |  | 2020-05-06 14:28 |  |  |  |  | 2020-05-06 14:28 | Yes | 44 | 1204-Owner-v | 2020-04-23 18:02
VD-9001-307A1-DWG-003 | 1 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(STEAM TURBINE DRIVEN) P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-28 20:39 | 2020-03-28 20:39 | Yes | 41 |  |  |  | 2020-05-06 14:29 |  |  |  |  | 2020-05-06 14:29 | Yes | 25 | 1204-Owner-v | 2020-04-23 18:01
VD-9001-307A1-DWG-009 | 1 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(STEAM TURBINE DRIVEN) P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-28 20:39 | 2020-03-28 20:39 | Yes | 41 |  |  |  | 2020-05-06 14:25 |  |  |  |  | 2020-05-06 14:25 | Yes | 25 | 1204-Owner-v | 2020-04-23 18:03
VD-9001-307A1-DWG-008 | 1 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMPS(MOTOR DRIVEN) P4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-09 14:31 | 2020-03-09 14:31 | Yes | 22 |  |  |  | 2020-05-19 13:31 |  |  |  |  | 2020-05-19 13:31 | Yes | 57 | 1204-Owner-v | 2020-04-23 18:03
VD-9001-307A1-DWG-001 | 1 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(STEAM TURBINE DRIVEN) P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-28 20:38 | 2020-03-28 20:39 | Yes | 41 |  |  |  | 2020-05-06 14:23 |  |  |  |  | 2020-05-06 14:23 | Yes | 25 | 1204-Owner-v | 2020-04-13 09:53
VD-9001-307A1-DWG-002 | 1 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(MOTOR DRIVEN) P2002B | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-09 14:30 | 2020-03-09 14:31 | Yes | 22 |  |  |  | 2020-05-06 14:22 |  |  |  |  | 2020-05-06 14:22 | Yes | 44 | 1204-Owner-v | 2020-04-23 18:01
VD-9001-307A1-DWG-006 | 1 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMP(MOTOR DRIVEN) P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-09 14:30 | 2020-03-09 14:31 | Yes | 22 |  |  |  | 2020-05-19 13:34 |  |  |  |  | 2020-05-19 13:34 | Yes | 57 | 1204-Owner-v | 2020-04-23 18:02
VD-9001-307A1-DWG-007 | 1 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMP(STEAM TURBINE DRIVEN) P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-14 23:31 | 2020-03-14 23:31 | Yes | 27 |  |  |  | 2020-05-18 19:03 |  |  |  |  | 2020-05-18 19:03 | Yes | 51 | 1204-Owner-v | 2020-04-23 18:02
VD-9001-307A1-DWG-005 | 1 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMPS(STEAM TURBINE DRIVEN) P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-16 18:56 | 2020-03-28 20:39 | 2020-03-28 20:39 | Yes | 41 |  |  |  |  | 2020-05-19 12:47 |  |  |  | 2020-05-19 12:47 | Yes | 38 | 1204-Owner-v | 2020-04-23 18:02
VD-9001-104(1)-DIS-001 | 0 | Vendor Print Index Schedule (VPIS) | PR-104(1) | HATCO CO. | 2019-12-09 | 2020-05-11 20:03 | 2020-05-11 20:03 | Yes | 154 | [9 empty] | No | 25
VD-9001-104(1-S)-ARP-001 | 0 | Torsional Analysis For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1-S)-ARP-002 | 0 | Lateral Analysis For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1-M)-CAL-001 | 0 | PSV Calculation Sheet for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-M)-CAL-002 | 0 | Orifice and Restriction Orifice Calculation Sheet for Air Dryer Package (DR-6101) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-001 | 0 | Design Calculation – Blow-Off Valve – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-002 | 0 | Design Calculation – Flow Measurement – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-003 | 0 | Design Calculation – Safety Valve – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-004 | 0 | Foundation load calculation For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-04-28 14:15 | 2020-04-28 14:15 | Yes | -17 |  |  | 2020-05-06 12:46 | [5 empty] | 2020-05-06 12:46 | Yes | -6
VD-9001-104(1-S)-CAL-005 | 0 | Strength calculation for gas coolers For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-006 | 0 | Strength calculation for oil coolers For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1)-CAL-001 | 0 | Mechanical Strength Calculation Sheet for Dryer Vessels (DR-6101 A/B) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-CAL-002 | 0 | Mechanical Strength Calculation Sheet for Direct Contact Air Cooler (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-CAL-003 | 0 | Direct Contact Air Cooler Thermal calculation (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-K)-CAL-001 | 0 | Evaporation Condenser Thermal calculation (T-6101-EV-1) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-CAL-004 | 0 | Regeneration Gas Steam Heater Thermal calculation (DR-6101-HE-1) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1-C)-CAL-001 | 0 | Expansion Turbine Thermal calculation (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-CAL-005 | 0 | Mechanical Strength Calculation Sheet for LIN Tank (TK-6101) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-CAL-006 | 0 | LIN Evaporator Thermal Calculation (EV-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1)-CAL-007 | 0 | Pressure Part Calculation Book for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-CAL-008 | 0 | Steel Structure Calculation Book for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-CAL-009 | 0 | Foundation Loading for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-CAL-010 | 0 | Pressure Part Calculation Book for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-CAL-011 | 0 | Foundation Loading for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-CER-001 | 0 | Material certificate For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-001 | 0 | Logic diagram for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-002 | 0 | Loop Diagram for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-003 | 0 | Control panel terminal detail and wiring diagram For Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-004 | 0 | Graphic Display For Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-005 | 0 | Junction Box Tremination Diagram for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-S)-DIG-002 | 0 | Terminal Diagrams – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-S)-DIG-003 | 0 | Wiring Diagrams – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-006 | 0 | Graphic display | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-007 | 0 | Wiring Diagrams | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-S)-DIG-004 | 0 | Steam turbine – Diagram For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-04-18 13:12 | 2020-04-18 13:12 | Yes | -27 |  |  |  | 2020-04-23 13:27 |  |  |  |  | 2020-04-23 21:00 | Yes | -9 | 1204-Owner-v | 2020-04-19 09:59
VD-9001-104(1)-DIG-002 | 0 | Cause and Effect Chart for Dryer (DR-6101) | PR-104(1) | HATCO CO. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-008 | 0 | Instrument Data sheet for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-03-10 |  |  | No | 101 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-009 | 0 | Restriction Orifice Data Sheet for Air Dryer Package (DR-6101) | PR-104(1) | HATCO CO. | 2020-03-10 |  |  | No | 101 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-010 | 0 | Temperature Transmitter Data Sheet for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-03-10 |  |  | No | 101 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-001 | 0 | Instruments Data Sheets – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-002 | 0 | Data Sheet and Drawing – Blow-Off Valve – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-003 | 0 | Data Sheet – Safety Valve – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-004 | 0 | Data sheet For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-005 | 0 | Steam turbine data sheet For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-006 | 0 | Noise data sheet For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-007 | 0 | Steam turbine – Noise data sheet For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-008 | 0 | Auxiliary oil pump motor data sheet For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-009 | 0 | Main oil pump data sheet For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-010 | 0 | Oil heater – Data sheet For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-DSH-001 | 0 | Direct Contact Air Cooler Data Sheet (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:32 | 2020-05-26 17:31 | Yes | 41 |  |  |  | 2020-06-07 11:48 |  |  |  |  | 2020-06-07 11:48 | Yes | -2 | 1204-Owner-v | 2020-05-31 09:44
VD-9001-104(1)-DSH-002 | 0 | Evaporation Condenser Data Sheet (T-6101-EV-1) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:33 | 2020-05-26 17:32 | Yes | 41 |  |  |  | 2020-06-09 09:14 |  |  |  |  | 2020-06-09 09:14 | Yes | 0 | 1204-Owner-v | 2020-05-31 09:45
VD-9001-104(1)-DSH-003 | 0 | Cooling Water Pump Data sheet (P6101 A/B/C) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:34 | 2020-05-26 17:33 | Yes | 41 |  |  |  | 2020-06-10 10:15 |  |  |  |  | 2020-06-10 10:15 | Yes | 1 | 1204-Owner-v | 2020-05-31 13:34
VD-9001-104(1)-DSH-004 | 0 | Chilled Water Pump Data sheet (P6102 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:34 | 2020-05-26 17:34 | Yes | 41 |  |  |  | 2020-06-10 11:10 |  |  |  |  | 2020-06-10 11:10 | Yes | 1 | 1204-Owner-v | 2020-05-31 13:35
VD-9001-104(1)-DSH-005 | 0 | Condensate Water Pump Data sheet | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1)-DSH-006 | 0 | Regeneration Gas Steam Heater data sheet (DR-6101-HE-1) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:39 | 2020-05-26 17:39 | Yes | 41 |  |  |  | 2020-06-09 08:53 |  |  |  |  | 2020-06-09 08:53 | Yes | 0 | 1204-Owner-v | 2020-05-31 13:35
VD-9001-104(1-C)-DSH-001 | 0 | Expansion Turbine Data Sheet (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:47 | 2020-05-26 17:47 | Yes | 41 |  |  |  | 2020-06-08 13:17 |  |  |  |  | 2020-06-08 13:17 | Yes | -1
VD-9001-104(1-K)-DSH-001 | 0 | IC LOX Pump Data sheet (T-6101-P-2A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:48 | 2020-05-26 17:48 | Yes | 41 |  |  |  | 2020-06-08 11:08 |  |  |  |  | 2020-06-08 11:09 | Yes | -1 | 1204-Owner-v | 2020-05-31 13:42
VD-9001-104(1-K)-DSH-002 | 0 | IC LIN Pump Data sheet (T-6101-P-1A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:48 | 2020-06-10 12:37 | Yes | 41 |  |  |  | 2020-06-10 14:48 |  |  |  |  | 2020-06-10 14:48 | Yes | 1 | 1204-Owner-v | 2020-05-31 13:42
VD-9001-104(1)-DSH-007 | 0 | LIN Tank Data Sheet (TK-6101) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:42 | 2020-05-26 17:42 | Yes | 41 |  |  |  | 2020-06-09 11:24 |  |  |  |  | 2020-06-09 11:24 | Yes | 0 | 1204-Owner-v | 2020-05-31 13:36
VD-9001-104(1-K)-DSH-003 | 0 | LIN Evaporator Data Sheet (EV-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:50 | 2020-05-26 17:50 | Yes | 41 |  |  |  | 2020-06-09 13:27 |  |  |  |  | 2020-06-09 13:27 | Yes | 0 | 1204-Owner-v | 2020-05-31 13:42
VD-9001-104(1-K)-DSH-004 | 0 | LIN Back-up Pump Data sheet (P-6103) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:52 | 2020-05-26 17:53 | Yes | 41 |  |  |  | 2020-06-08 11:06 |  |  |  |  | 2020-06-08 11:06 | Yes | -1 | 1204-Owner-v | 2020-05-31 13:43
VD-9001-104(1-K)-DSH-005 | 0 | LIN Filling Station Data Sheet | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-006 | 0 | Cryogenic System (ASU) Data Sheet | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-007 | 0 | Brazed Aluminum Heat Exchanger Data Sheet | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DSH-008 | 0 | Dryer Package Data Sheet (DR-6101) | PR-104(1) | HATCO CO. | 2020-02-10 | 2020-05-26 17:42 | 2020-05-26 17:42 | Yes | 106 |  |  |  | 2020-06-09 09:57 |  |  |  |  | 2020-06-09 09:58 | Yes | 0 | 1204-Owner-v | 2020-05-31 13:36
VD-9001-104(1)-DSH-009 | 0 | Data Sheet for Special Items | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-DSH-010 | 0 | Air Intake Filer Data Sheet (C-6101-FT-A/B) | PR-104(1) | HATCO CO. | 2020-05-20 | 2020-05-26 17:44 | 2020-05-26 17:44 | Yes | 6 |  |  |  | 2020-06-03 11:38 |  |  |  |  | 2020-06-03 11:38 | Yes | -6 | 1204-Owner-v | 2020-05-31 13:38
VD-9001-104(1)-DSH-011 | 0 | Process Data Sheets for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-05-26 14:36 | 2020-05-26 14:37 | Yes | 36 |  |  |  | 2020-05-27 16:18 |  |  |  |  | 2020-05-27 16:18 | Yes | -13 | 1204-Owner-v | 2020-05-31 13:39
VD-9001-104(1)-DSH-012 | 0 | Fan Data Sheets for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1)-DSH-013 | 0 | Data Sheet for Motors for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1)-DSH-014 | 0 | Data Sheet of Vibration Switch for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1)-DSH-015 | 0 | Process Data Sheets for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-05-26 14:37 | 2020-05-26 14:48 | Yes | 36 |  |  |  | 2020-05-27 18:20 |  |  |  |  | 2020-05-27 18:20 | Yes | -13 | 1204-Owner-v | 2020-05-31 13:40
VD-9001-104(1-M)-DWG-001 | 0 | Instrument location drawing for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-M)-DWG-002 | 0 | Process hook-up drawing for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-M)-DWG-003 | 0 | Configuration of Control system for whole package | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-M)-DWG-004 | 0 | Control panel dimensional drawing with component list for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-M)-DWG-005 | 0 | Instrument Earthing Detail | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-001 | 0 | Instruments Hook Up Drawings – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-GAD-002 | 0 | General arrangement plan For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-04-28 14:16 | 2020-04-28 14:16 | Yes | 8 |  |  |  | 2020-05-06 12:38 |  |  |  |  | 2020-05-06 12:38 | Yes | -6
VD-9001-104(1-S)-DWG-003 | 0 | Foundation plan For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-04-27 14:41 | 2020-04-27 14:41 | Yes | 7 |  |  |  | 2020-05-13 16:31 |  |  |  |  | 2020-05-13 16:31 | Yes | 2 | 1204-Owner-v | 2020-06-02 09:46
VD-9001-104(1-S)-DWG-004 | 0 | Sectional drawing with part list For Air Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-005 | 0 | Steam turbine – Sectional Drawing with part list For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-006 | 0 | Auxiliary oil pump motor drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-007 | 0 | Oil mist separator – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-008 | 0 | Oil mist separator – Motor – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-009 | 0 | Oil heater – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-010 | 0 | Discharge Silencer – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-011 | 0 | Blow-off silencer – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-012 | 0 | Check Valve – Drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-013 | 0 | Rotor Clearance drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-014 | 0 | Gas cooler drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-015 | 0 | Oil cooler drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-016 | 0 | Piping arrangement drawing For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-017 | 0 | Maximum Allowable Forces and moment For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-018 | 0 | As built technical documents of all supplied equipment as final book in English For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1)-DWG-001 | 0 | Direct Contact Air Cooler General arrangement (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-05-13 12:50 | 2020-05-13 12:50 | Yes | 23 |  |  |  | 2020-06-02 12:38 |  |  |  |  | 2020-06-02 12:38 | Yes | 6
VD-9001-104(1-K)-DWG-001 | 0 | Condenser Cooler General arrangement (T-6101-EV-1) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1)-DWG-002 | 0 | Cooling Water Pump General Arrangement (P6101 A/B/C) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-06-06 12:27 | 2020-06-06 12:27 | Yes | 22 | [9 empty] | No | -1
VD-9001-104(1)-DWG-003 | 0 | Chilled Water Pump General Arrangement (P6102 A/B) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-06-06 12:29 | 2020-06-06 12:29 | Yes | 22 | [9 empty] | No | -1
VD-9001-104(1)-DWG-004 | 0 | Condensate Water Pump General Arrangement | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-005 | 0 | Regeneration Gas Steam Heater General arrangement (DR-6101-HE-1) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-C)-DWG-001 | 0 | Expansion Turbine General arrangement (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-C)-DWG-002 | 0 | Expansion Turbine Sectional Drawing with Part List (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-002 | 0 | IC LOX Pump General Arrangement (T-6101-P-2A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-003 | 0 | IC LIN Pump General Arrangement (T-6101-P-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-006 | 0 | LIN Tank General Arrangement (TK-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-007 | 0 | LIN Evaporator General Arrangement (EV-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-004 | 0 | LIN Back-up Pump General Arrangement (P-6103) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-005 | 0 | LIN Filling Station General Arrangement | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-006 | 0 | Cryogenic System (ASU) General arrangement | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-007 | 0 | Brazed Aluminum Heat Exchanger Drawings | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-008 | 0 | General Arrangement Drawing For Dryer Vessels (DR-6101 A/B) | PR-104(1) | HATCO CO. | 2020-03-15 | 2020-06-06 14:29 | 2020-06-06 14:29 | Yes | 83 |  |  |  | 2020-06-08 14:35 |  |  |  |  | 2020-06-08 14:35 | Yes | -12
VD-9001-104(1)-DWG-009 | 0 | Name Plate Drawing of Dryer Package (DR-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-PPL-010 | 0 | ASU PLOT PLAN | PR-104(1) | HATCO CO. | 2020-01-15 | 2020-02-16 14:58 | 2020-02-16 14:58 | Yes | 32 |  |  |  | 2020-02-29 16:59 |  |  | 2020-02-16 11:14 | 2020-02-16 11:14 | 2020-02-29 20:01 | Yes | -1 | 1204-Owner-v | 2020-02-18 10:00
VD-9001-104(1)-DWG-011 | 0 | Piping Arrangment Drawing | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1)-DWG-012 | 0 | General Assembly Drawing for Air Intake Filter (C-6101-FT-A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-DWG-013 | 0 | Electrical Drawing for Air Intake Filter (C-6101-FT-A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-DWG-014 | 0 | Steel Structure Motor & Walk Way Drawing for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1)-DWG-015 | 0 | Tube Bundle Detail for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-DWG-016 | 0 | General Arrangement Drawing for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-DWG-017 | 0 | Side Frame for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-018 | 0 | Steel Structure Drawing for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-019 | 0 | Fan & Motor Support for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-020 | 0 | Plenum & Fan Ring for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-021 | 0 | Fan & Pulley Guard for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-022 | 0 | Bearing Block Assembly for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-023 | 0 | Name Plate for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-DWG-024 | 0 | Tube Bundle Detail for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-025 | 0 | General Arrangement Drawing for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-DWG-026 | 0 | Name Plate for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-027 | 0 | Compressor House (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1)-EQL-001 | 0 | Equipment List | PR-104(1) | HATCO CO. | 2020-02-15 | 2020-05-26 17:56 | 2020-05-26 17:56 | Yes | 101 |  |  |  | 2020-05-27 16:50 |  |  |  |  | 2020-05-27 16:50 | Yes | -13
VD-9001-104(1)-INX-001 | 0 | Final Book Index | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-ISO-001 | 0 | Piping Isometric Drawing for Interconnecting inside B.L | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-ITP-001 | 0 | Inspection and test plan For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 | 2020-05-11 19:33 | 2020-05-11 19:33 | Yes | -75 |  |  |  | 2020-06-08 13:25 |  |  |  |  | 2020-06-08 13:25 | Yes | 14
VD-9001-104(1)-ITP-001 | 0 | Inspection And Test Plan for Air Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-01-20 |  |  | No | 151 | [9 empty] | No | 0
VD-9001-104(1)-ITP-002 | 0 | Inspection & Test Plan for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-ITP-003 | 0 | Inspection & Test Plan for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-M)-LAY-001 | 0 | Instrument Cable Route | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-LAY-001 | 0 | Funnel Location Plan | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-001 | 0 | I/O list for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-002 | 0 | Instrument List for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-003 | 0 | Instrument Cable list | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-004 | 0 | UCP Heat Dissipation for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-005 | 0 | Modbus list & hardwire cable interface list for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-09-10 |  |  | No | -83 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-012 | 0 | Radiography Test Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-013 | 0 | Tube Expand Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-014 | 0 | Pickling And Passivation Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-015 | 0 | Painting Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-016 | 0 | Packing ,Shipping ,Handling & Storage Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-017 | 0 | Operation ,Installation ,Maintenance & Lubrication Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-018 | 0 | Repair Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-019 | 0 | Ultrasonic Test Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-020 | 0 | Hydrostatic Test Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-021 | 0 | Liquid Penetrant Examination Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-022 | 0 | Radiography Test Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-023 | 0 | Tube Expand Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-024 | 0 | Pickling And Passivation Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-025 | 0 | Painting Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-026 | 0 | Packing ,Shipping ,Handling & Storage Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-027 | 0 | Operation ,Installation ,Maintenance & Lubrication Procedure for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-PCU-001 | 0 | Performance maps For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-28 10:53 | 2020-04-28 10:53 | Yes | 13 |  |  |  | 2020-04-29 15:25 |  |  |  |  | 2020-04-29 21:02 | Yes | -13
VD-9001-104(1-S)-PCU-002 | 0 | Steam flow versus power curve For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1)-PFD-001 | 0 | Process flow diagram For ASU | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-02-04 10:46 | 2020-02-04 10:47 | Yes | -71 |  |  |  | 2020-02-12 17:02 |  |  |  |  | 2020-02-12 20:00 | Yes | -6 | 1204-Owner-v | 2020-02-18 10:04
VD-9001-104(1-S)-PID-001 | 0 | Compressor P&ID For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-12 13:33 | 2020-04-12 13:33 | Yes | -3 |  |  |  | 2020-04-23 14:39 |  |  |  |  | 2020-04-23 21:03 | Yes | -3 | 1204-Owner-v | 2020-04-18 12:11
VD-9001-104(1-S)-PID-002 | 0 | Steam turbine P&ID For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-04-20 12:34 | 2020-04-20 12:36 | Yes | -25 |  |  |  | 2020-04-26 11:51 |  |  |  |  | 2020-04-26 11:51 | Yes | -8
VD-9001-104(1-S)-PID-003 | 0 | Common lube oil P&ID For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-04-12 13:34 | 2020-04-12 13:35 | Yes | -33 |  |  |  | 2020-04-26 11:54 |  |  |  |  | 2020-04-26 11:54 | Yes | 0 | 1204-Owner-v | 2020-04-18 12:32
VD-9001-104(1-M)-PPL-001 | 0 | Instrument Cable Route | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-06-02 11:43 | 2020-06-02 11:43 | Yes | 43 | [9 empty] | No | 3
VD-9001-104(1-M)-PPL-002 | 0 | Instrument Air Piping Tubing Layout | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-PPL-001 | 0 | Logic Diagram – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1-S)-PPL-002 | 0 | Junctionbox Layout (incl. Local Control Panel) – Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1-M)-PPL-005 | 0 | Control panel layout | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-PQR-001 | 0 | PQR | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PQR-002 | 0 | Procedure Qualification Record (PQR) for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PQR-003 | 0 | Procedure Qualification Record (PQR) for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-M)-PRC-002 | 0 | Control Philosophy | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-RPT-001 | 0 | SIL Study action Report | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1)-RPT-002 | 0 | HAZOP study report | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1)-RPT-003 | 0 | Stress Analysis & Flexibility Calculation and Report | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1)-RPT-004 | 0 | 3D Model report | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-S)-SCH-001 | 0 | Time schedule For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-SLD-001 | 0 | Structural Single Line For Compressor House (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-TBL-001 | 0 | Time Table for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-S)-VDR-001 | 0 | Quality documentation For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1)-WMP-001 | 0 | Welding/NDT Plan for Dryer Vessel (DR-6101 A/B) | PR-104(1) | HATCO CO. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-104(1)-WMP-002 | 0 | Welding/NDT Plan for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-WMP-003 | 0 | Welding/NDT Plan for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-WPQ-001 | 0 | Welder And Operation List for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-104(1)-WPS-001 | 0 | WPS for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-20 |  |  | No | 120 | [9 empty] | No | 0
VD-9001-104(1)-WPS-002 | 0 | Welding Procedure Specification (WPS) for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-WPS-003 | 0 | Welding Procedure Specification (WPS) for Water Cooled Condenser (WCC) (E-6103) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-DWG-028 | 0 | Special Pipe Support Drawing | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-KPL-001 | 0 | Key Plan For ASU Unit | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-029 | 0 | UG Piping Basic Rout | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-PDS-001 | 0 | Process description | PR-104(1) | HATCO CO. | 2020-03-25 | 2020-05-26 17:54 | 2020-05-26 17:54 | Yes | 62 |  |  |  | 2020-05-30 14:44 |  |  |  |  | 2020-05-30 14:44 | Yes | -10 | 1204-Owner-v | 2020-06-06 15:13
VD-9001-104(1-K)-BFD-001 | 0 | Block Flow Diagram | PR-104(1) | HATCO CO. | 2020-03-25 |  |  | No | 86 | [9 empty] | No | 0
VD-9001-104(1-K)-MNL-001 | 0 | Operating / maintenance and safety manual | PR-104(1) | HATCO CO. | 2020-10-15 |  |  | No | -118 | [9 empty] | No | 0
VD-9001-104(1-K)-CAL-005 | 0 | Mechanical Strength Calculation Sheet for lower column (T-6101-T-1) | PR-104(1) | HATCO CO. | 2020-03-25 |  |  | No | 86 | [9 empty] | No | 0
VD-9001-104(1-K)-CAL-002 | 0 | Mechanical Strength Calculation Sheet for evaporator condenser (T-6101-EV-1) | PR-104(1) | HATCO CO. | 2020-03-25 |  |  | No | 86 | [9 empty] | No | 0
VD-9001-104(1-K)-CAL-003 | 0 | Mechanical Strength Calculation Sheet for Plate fin heat exchanger (T-6101-E-2/3) | PR-104(1) | HATCO CO. | 2020-03-25 |  |  | No | 86 | [9 empty] | No | 0
VD-9001-104(1-K)-CAL-004 | 0 | Strength calculation Calculation Sheet for Cold box steel structure (PU-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-008 | 0 | Distillation lower column General arrangement (T-6101-T-1) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-13 12:51 | 2020-05-13 12:52 | Yes | 28 |  |  |  | 2020-06-02 15:47 |  |  |  |  | 2020-06-02 15:47 | Yes | 6
VD-9001-104(1-K)-DWG-009 | 0 | Distillation upper column General arrangement (T-6101-T-2) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-13 12:52 | 2020-05-13 12:52 | Yes | 28 |  |  |  | 2020-06-02 15:07 |  |  |  |  | 2020-06-02 15:07 | Yes | 6
VD-9001-104(1-K)-DWG-010 | 0 | HP Plate fin heat exchanger General arrangement (T-6101-E-2A~D) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-011 | 0 | LP Plate fin heat exchanger General arrangement (T-6101-E-3A~G) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-13 12:53 | 2020-05-13 12:53 | Yes | 28 |  |  |  | 2020-06-02 13:35 |  |  |  |  | 2020-06-02 13:35 | Yes | 6
VD-9001-104(1-K)-DWG-012 | 0 | Sub cooler General arrangement | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-13 12:53 | 2020-05-13 12:53 | Yes | 28 |  |  |  | 2020-06-02 13:58 |  |  |  |  | 2020-06-02 13:58 | Yes | 6
VD-9001-104(1-K)-DWG-013 | 0 | Cold box foundation drawing (PU-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-014 | 0 | Cold box General arrangement (PU-6101) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1)-DWG-030 | 0 | Piping plan drawing in cold box (PU-6101) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-015 | 0 | Cold box landing (PU-6101) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-K)-PCU-001 | 0 | Performance maps For LOX pump (T-6101-P-2A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-006 | 0 | I/O assignment for control system for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-09-10 |  |  | No | -83 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-007 | 0 | Instrument Power Consumption List | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-M)-LST-008 | 0 | Electrical Load List | PR-104(1) | HATCO CO. | 2020-05-15 | 2020-05-19 16:35 | 2020-05-19 16:37 | Yes | 4 |  |  |  | 2020-05-24 11:56 |  |  |  |  | 2020-05-24 11:56 | Yes | -9 | 1204-Owner-v | 2020-05-20 14:24
VD-9001-104(1-S)-LST-001 | 0 | I/O and Signal List (Alarm / Trip List) – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-002 | 0 | MODBUS Communication List & Hardwire Cable Interface List – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-003 | 0 | Instruments List – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-004 | 0 | Power Control and Instrument Cables List – Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-005 | 0 | Utility consumer list For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-006 | 0 | Lubrication list For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-007 | 0 | Gas cooler part list For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-008 | 0 | Oil cooler part list For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-LST-001 | 0 | Spare parts list for Erection, Commissioning and Start up | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1)-LST-003 | 0 | Capital spare part list | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1)-LST-004 | 0 | TIE-IN Point List and Location | PR-104(1) | HATCO CO. | 2020-03-10 | 2020-04-29 15:52 | 2020-04-29 15:53 | Yes | 50 |  |  |  | 2020-05-11 14:38 |  |  |  |  | 2020-05-11 14:38 | Yes | -2 | 1204-Owner-v | 2020-05-03 10:56
VD-9001-104(1)-LST-005 | 0 | LINE LIST | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-LST-006 | 0 | Pipe Support list | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1)-LST-007 | 0 | Critical Line List | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1)-LST-008 | 0 | Utility Consumption List | PR-104(1) | HATCO CO. | 2020-05-20 | 2020-05-11 15:50 | 2020-05-11 15:50 | Yes | -9 |  |  |  | 2020-05-12 12:57 |  |  |  |  | 2020-05-12 21:00 | Yes | -13 | 1204-Owner-v | 2020-05-20 08:39
VD-9001-104(1)-LST-009 | 0 | List of main sub vendors | PR-104(1) | HATCO CO. | 2020-02-20 | 2020-02-26 14:29 | 2020-02-26 14:30 | Yes | 6 |  |  |  | 2020-03-11 11:26 |  |  |  |  | 2020-03-11 20:00 | Yes | 0 | 1204-Owner-v | 2020-04-19 09:48
VD-9001-104(1)-MDB-001 | 0 | Final Book | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1-S)-MNL-001 | 0 | Installation and Operating manual For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-104(1)-MNL-001 | 0 | Operating & Maintenance Manual for Dryer (DR-6101) | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-MTO-001 | 0 | MTO of Bulk Material for Instrument | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-104(1)-MTO-002 | 0 | Piping Material Take off for Interconnecting inside B.L | PR-104(1) | HATCO CO. | 2020-03-15 |  |  | No | 96 | [9 empty] | No | 0
VD-9001-104(1)-MTO-003 | 0 | Pipe Support MTO | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1)-ORC-001 | 0 | Organization Chart | PR-104(1) | HATCO CO. | 2020-01-15 |  |  | No | 156 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-001 | 0 | Hydrostatic Test Procedure for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1-S)-PCJ-001 | 0 | Painting procedure/specification For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-03-15 | 2020-04-18 13:16 | 2020-04-18 13:16 | Yes | 34 |  |  |  | 2020-04-27 18:08 |  |  |  |  | 2020-04-27 20:59 | Yes | -5 | 1204-Owner-v | 2020-04-19 10:06
VD-9001-104(1)-PCJ-002 | 0 | Material Storage & Presevation | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-003 | 0 | Painting Procedure for Air Dryer Package and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-004 | 0 | NDT Personnel Qualification List for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-005 | 0 | NDT Procedure for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-006 | 0 | Shipping & Packing Procedure | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-007 | 0 | Repair Procedure for Dryer and Interconnecting | PR-104(1) | HATCO CO. | 2020-02-15 |  |  | No | 125 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-008 | 0 | Repair Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-009 | 0 | Ultrasonic Test Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-010 | 0 | Hydrostatic Test Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1)-PCJ-011 | 0 | Liquid Penetrant Examination Procedure for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-104(1-K)-PCU-002 | 0 | Performance maps For Lin pump (T-6101-P-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-001 | 0 | P&ID For LOX pump (T-6101-P-2A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-002 | 0 | P&ID For LIN pump (T-6101-P-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-C)-PID-001 | 0 | P&ID For expander turbine (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-251-DSH-664 | 1 | Turbines Data Sheet (TUR | HM-251 | KT – Kinetics Technology SpA | 2020-02-18 |  |  | No | 122 | [9 empty] | No | 0
VD-9001-204D-DWG-003 | 6 | MATERIAL LIST AND GENERAL NOTES | PV-204D | FBM HUDSON ITALIANA S.P.A | 2020-02-05 |  |  | No | 135 | [9 empty] | No | 0
VD-9001-254-LST-112 | 2 | SET POINT LIST FOR BOILER PLANT | HM-254 | AZAR AB | 2020-02-09 | 2020-02-18 16:37 | 2020-02-18 16:37 | Yes | 9 |  |  | 2020-04-11 11:38 | [5 empty] | 2020-04-11 11:38 | Yes | 39
VD-9001-254-PID-117 | 7 | BURNER AREA P&I DIAGRAM | HM-254 | AZAR AB | 2020-02-08 | 2020-03-09 13:08 | 2020-03-09 13:08 | Yes | 30 |  |  | 2020-04-15 12:10 | [5 empty] | 2020-04-15 12:10 | Yes | 23
VD-9001-201A-PCJ-076 | 1 | PRODUCTION TEST PLATE (PTP) PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2020-02-15 | 2020-03-12 08:59 | 2020-03-12 08:59 | Yes | 26 |  |  |  | 2020-03-15 11:25 |  |  |  |  | 2020-03-15 11:25 | Yes | -11
VD-9001-251B-SPD-010 | 2 | Single Part DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-02-11 | 2020-02-15 12:09 | 2020-02-15 12:09 | Yes | 4 |  |  | 2020-02-18 17:12 | [5 empty] | 2020-02-18 17:12 | Yes | -11
VD-9001-251B-SAD-010 | 2 | Assembly DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-02-11 | 2020-02-15 12:02 | 2020-02-15 12:03 | Yes | 4 |  |  | 2020-02-18 17:11 | [5 empty] | 2020-02-18 17:11 | Yes | -11
VD-9001-251B-RPT-010 | 2 | Reports for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-02-11 | 2020-02-15 11:44 | 2020-02-15 11:44 | Yes | 4 |  |  | 2020-02-18 17:10 | [5 empty] | 2020-02-18 17:10 | Yes | -11
VD-9001-251B-GAD-010 | 2 | General Arrangement DWG for "TRANSFER LINE SUPPORT" | HM-251B | Bamdad Zendehroud Co. | 2020-02-11 | 2020-02-15 11:43 | 2020-02-15 11:43 | Yes | 4 |  |  | 2020-02-18 17:09 | [5 empty] | 2020-02-18 17:09 | Yes | -11 | 1204-Owner-v | 2020-04-25 16:09
VD-9001-251-PCU-661 | 1 | Performance Curve (TUR) | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-PCU-660 | 1 | Performance Curve (TUR) | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-DSH-663 | 1 | Turbines Data Sheet (TUR | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-DSH-689 | 1 | Eqpt filled-in data sheets | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-DSH-686 | 1 | Eqpt filled-in data sheets | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-DSH-667 | 1 | 'Auxilliaries Data Sheets & Pump performance curve Only for Lube Oil pump, Heat Exchanger & Filter (LOS) | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-251-DSH-668 | 1 | 'Auxilliaries Data Sheets & Pump performance curve Only for Lube Oil pump, Heat Exchanger & Filter (LOS) | HM-251 | KT – Kinetics Technology SpA | 2020-02-24 |  |  | No | 116 | [9 empty] | No | 0
VD-9001-254-PCJ-846 | 0 | ERECTION TOLERANCE FOR BOILER | HM-254 | AZAR AB | 2020-02-10 | 2020-02-12 14:12 | 2020-02-12 14:12 | Yes | 2 |  |  |  | 2020-02-12 14:19 |  |  |  |  | 2020-02-12 14:19 | Yes | -14
VD-9001-307A1-DSH-009 | 1 | MOTOR DATASHEET WITH CURVE FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 | 2020-03-07 10:39 | 2020-03-07 10:40 | Yes | 16 |  |  |  |  | 2020-03-15 13:52 |  |  |  | 2020-03-15 13:52 | Yes | -6
VD-9001-307A1-DSH-008 | 1 | MOTOR DATASHEET WITH CURVE FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 | 2020-03-07 10:39 | 2020-03-07 10:40 | Yes | 16 |  |  |  |  | 2020-04-06 13:58 |  |  |  | 2020-04-06 13:58 | Yes | 16 | 1204-Owner-v | 2020-04-01 10:33
VD-9001-307A1-DSH-011 | 1 | MOTOR DATASHEET WITH CURVE FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 | 2020-03-07 10:39 | 2020-03-07 10:41 | Yes | 16 |  |  |  |  | 2020-03-15 14:00 |  |  |  | 2020-03-15 14:00 | Yes | -6
VD-9001-307A1-DSH-012 | 1 | MOTOR DATASHEET WITH CURVE FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 | 2020-03-07 10:39 | 2020-03-07 10:42 | Yes | 16 |  |  |  |  | 2020-03-15 13:56 |  |  |  | 2020-03-15 13:56 | Yes | -6
VD-9001-307A1-DSH-010 | 1 | MOTOR DATASHEET WITH CURVE FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-02-20 | 2020-03-07 10:39 | 2020-03-07 10:40 | Yes | 16 |  |  |  |  | 2020-03-15 13:48 |  |  |  | 2020-03-15 13:48 | Yes | -6
VD-9001-307A1-DSH-007 | 1 | MOTOR DATASHEET WITH CURVE FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 11:36 | 2020-03-07 10:38 | 2020-03-07 10:41 | Yes | 12 |  |  |  |  | 2020-03-15 13:45 |  |  |  | 2020-03-15 13:45 | Yes | -6 | 1204-Owner-v | 2020-04-19 10:39
VD-9001-307A1-DSH-037 | 1 | MECHANICAL SEAL DATASHEET FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:24 | 2020-02-17 13:30 | 2020-02-17 13:33 | Yes | -7 |  |  | 2020-02-29 09:01 | [5 empty] | 2020-02-29 09:01 | Yes | -2
VD-9001-307A1-DSH-034 | 1 | MECHANICAL SEAL DATASHEET FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:24 | 2020-02-17 13:29 | 2020-02-17 13:32 | Yes | -7 |  |  | 2020-02-29 08:57 | [5 empty] | 2020-02-29 08:57 | Yes | -2
VD-9001-307A1-DSH-036 | 1 | MECHANICAL SEAL DATASHEET FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:24 | 2020-02-17 13:29 | 2020-02-17 13:33 | Yes | -7 |  |  | 2020-02-29 09:00 | [5 empty] | 2020-02-29 09:00 | Yes | -2
VD-9001-307A1-DSH-035 | 1 | MECHANICAL SEAL DATASHEET FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:24 | 2020-02-17 13:29 | 2020-02-17 13:33 | Yes | -7 |  |  | 2020-02-29 08:58 | [5 empty] | 2020-02-29 08:58 | Yes | -2 | 1204-Owner-v | 2020-04-27 10:46
VD-9001-307A1-DSH-038 | 1 | MECHANICAL SEAL DATASHEET FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:25 | 2020-02-17 13:30 | 2020-02-17 13:33 | Yes | -7 |  |  | 2020-02-29 09:01 | [5 empty] | 2020-02-29 09:02 | Yes | -2
VD-9001-307A1-DSH-039 | 1 | MECHANICAL SEAL DATASHEET FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-02-24 14:25 | 2020-02-17 13:30 | 2020-02-17 13:33 | Yes | -7 |  |  | 2020-02-29 09:02 | [5 empty] | 2020-02-29 09:02 | Yes | -2
VD-9001-740B-PCJ-005 | 2 | ULTRASONIC TEST PROCEDURE | ST-740B | PETRO ADAK IRAN | 2020-02-17 | 2020-02-11 08:44 | 2020-02-11 08:45 | Yes | -6 |  |  | 2020-03-02 10:41 | [5 empty] | 2020-03-02 20:01 | Yes | 6
VD-9001-740B-SPD-30319 | 1 | SINGLE PART DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2020-02-17 | 2020-03-20 10:54 | 2020-03-20 11:28 | Yes | 32 |  |  | 2020-04-13 14:04 | [5 empty] | 2020-04-13 21:00 | Yes | 10
VD-9001-254-DIG-338 | 4 | CAUSE AND EFFECT DIAGRAM | HM-254 | AZAR AB | 2020-02-15 | 2020-02-22 16:48 | 2020-02-22 16:48 | Yes | 7 |  |  | 2020-04-11 11:37 | [5 empty] | 2020-04-11 11:37 | Yes | 35
VD-9001-254-PID-118 | 6 | INSTRUMENT AIR P&I DIAGRAM | HM-254 | AZAR AB | 2020-02-15 | 2020-03-09 13:09 | 2020-03-09 13:09 | Yes | 23 |  |  | 2020-04-15 11:17 | [5 empty] | 2020-04-15 11:17 | Yes | 23
VD-9001-254-PCJ-846 | 1 | ERECTION TOLERANCE FOR BOILER | HM-254 | AZAR AB | 2020-02-15 | 2020-02-16 10:41 | 2020-02-16 10:41 | Yes | 1 |  |  | 2020-02-16 11:29 | [5 empty] | 2020-02-16 11:29 | Yes | -14 | 1204-Owner-v | 2020-05-18 17:03
VD-9001-104(1)-PFD-001 | 1 | Process flow diagram For ASU | PR-104(1) | HATCO CO. | 2020-02-26 20:00 | 2020-03-06 17:04 | 2020-03-06 17:04 | Yes | 9 |  |  |  | 2020-04-13 12:13 |  |  |  |  | 2020-04-13 20:59 | Yes | 24 | 1204-Owner-v | 2020-03-25 16:16
VD-9001-307A1-DIS-001 | 03 | VENDOR DOCUMENTS INDEX & SCHEDULE | MC-307A1 | Deep Blue Pump Co. | 2020-02-19 12:09 | 2020-02-19 13:06 | 2020-02-19 13:06 | Yes | 0 |  |  | 2020-05-06 14:50 | [5 empty] | 2020-05-06 14:50 | Yes | 63 | 1204-Owner-v | 2020-04-19 10:23
VD-9001-257B-WMP-038 | 3 | WELDING AND NDT MAP | HM-257B | FATEH SANAT KIMIA | 2020-03-02 | 2020-05-12 11:08 | 2020-05-12 11:07 | Yes | 71 |  |  | 2020-05-16 12:39 | [5 empty] | 2020-05-16 12:39 | Yes | -10
VD-9001-254-DWG-1002 | 2 | ERECTION DWGS. FOR ST. STR. OF BLR REAR 4/6 | HM-254 | AZAR AB | 2020-02-28 | 2020-02-24 15:31 | 2020-02-24 15:32 | Yes | -4 |  |  | 2020-04-19 12:00 | [5 empty] | 2020-04-19 12:00 | Yes | 41
VD-9001-254-DWG-991 | 2 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 2/9 | HM-254 | AZAR AB | 2020-02-28 | 2020-02-24 15:26 | 2020-02-24 15:26 | Yes | -4 |  |  | 2020-04-19 09:34 | [5 empty] | 2020-04-19 09:34 | Yes | 41
VD-9001-254-DWG-996 | 2 | ERECTION DWG. FOR ST. STR. OF BLR FRONT & NSPECTION PLAT FORM AIR & GAS DUCT 7/9 | HM-254 | AZAR AB | 2020-02-28 | 2020-02-24 15:27 | 2020-02-24 15:30 | Yes | -4 |  |  | 2020-04-19 09:35 | [5 empty] | 2020-04-19 09:35 | Yes | 41
VD-9001-251C-DWG-032 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1002 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-033 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1003 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-034 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1004 A | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-035 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1005 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-036 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1004 B | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-037 | 0 | VERTICAL CONVECTION END TUBESHEET ASSEMBLY DRAWING | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-038 | 0 | HORIZENTAL CONVECTION END TUBESHEET ASSEMBLY DRAWING | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-039 | 0 | VERTICAL CONVECTION HEADER BOXES AND DETAILS ASSEMBLY DRAWING | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-040 | 0 | HORIZENTAL CONVECTION HEADER BOXES AND DETAILS ASSEMBLY DRAWING | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-041 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1001 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-042 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1002 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-043 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1003 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-044 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1004A | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-045 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1005 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-30 |  |  | No | -103 | [9 empty] | No | 0
VD-9001-251C-DWG-046 | 0 | CONVECTION MODULE STEEL WORK FOR COIL BUNDLE TRANSPORT - HE-1004B | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-DWG-047 | 0 | FINNING DRAWING FOR HE-1002 | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-DWG-048 | 0 | FINNING DRAWING FOR HE-1004A | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-DWG-049 | 0 | FINNING DRAWING FOR HE-1005 | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-PCJ-050 | 0 | NDT PROCEDURE FOR TUBESHEET CASTING (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-PCJ-051 | 0 | NDT PROCEDURE FOR FINNING (IF REQUIRED) | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-052 | 0 | DRY OUT PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-ITP-053 | 0 | INSPECTION AND TEST PLAN FOR TUBESHEETS CASTING (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-ITP-054 | 0 | INSPECTION AND TEST PLAN FOR FINNING (IF REQUIRED) | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-NPL-055 | 0 | WELDING DOCUMENT (WPS,PQR,MAP,NDT MAP) FOR TUBESHEETS CASTING (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-NPL-056 | 0 | WELDING DOCUMENT (WPS,PQR,MAP,NDT MAP) FOR FINNING (IF REQUIRED) | HM-251C | Fateh Sanat Kimia Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-251C-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | HM-251C | Fateh Sanat Kimia Co. | 2020-02-25 | 2020-05-19 11:11 | 2020-05-19 11:11 | Yes | 84 |  |  | 2020-05-20 10:41 | [5 empty] | 2020-05-20 10:41 | Yes | -13 | 1204-Owner-v | 2020-05-19 11:51
VD-9001-251C-LST-002 | 0 | COMMISSIONING SPARE PART LIST | HM-251C | Fateh Sanat Kimia Co. | 2020-10-05 |  |  | No | -108 | [9 empty] | No | 0
VD-9001-251C-LST-003 | 0 | 2 YEARS SPARE PART LIST FOR (IF REQUIRED) | HM-251C | Fateh Sanat Kimia Co. | 2020-12-18 |  |  | No | -182 | [9 empty] | No | 0
VD-9001-251C-VDR-005 | 0 | FINAL VENDOR DATA BOOK INDEX | HM-251C | Fateh Sanat Kimia Co. | 2020-12-18 |  |  | No | -182 | [9 empty] | No | 0
VD-9001-251C-MPR-006 | 0 | MONTHLY PROGRESS REPORT | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-007 | 0 | PAINTING PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-008 | 0 | P.W.H.T. PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-009 | 0 | NDT PROCEDURE FOR PIPE, WELDING FITTING AND COIL ASSEMBLYING | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-010 | 0 | HYDROSTATIC TEST PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-251C-NPL-011 | 0 | WELDING DOCUMENT (WPS,PQR,MAP,NDT MAP) FOR PIPE, FITTING WELDING AND COILS ASSEMBLYING | HM-251C | Fateh Sanat Kimia Co. | 2020-02-25 |  |  | No | 115 | [9 empty] | No | 0
VD-9001-251C-ITP-012 | 0 | INSPECTION AND TEST PLAN FOR PIPE, FITTING WELDING AND COILS ASSEMBLYING | HM-251C | Fateh Sanat Kimia Co. | 2020-12-29 | 2020-05-04 15:53 | 2020-05-04 15:53 | Yes | -239 |  |  |  | 2020-05-16 08:43 |  |  |  |  | 2020-05-16 08:43 | Yes | -2
VD-9001-251C-VDR-013 | 0 | FINAL VENDOR DATABOOK | HM-251C | Fateh Sanat Kimia Co. | 2020-02-27 |  |  | No | 113 | [9 empty] | No | 0
VD-9001-251C-PCJ-014 | 0 | PMI PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-02-28 |  |  | No | 112 | [9 empty] | No | 0
VD-9001-251C-PCJ-015 | 0 | HARDNESS TEST PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-016 | 0 | PICKLING AND PASSIVATION PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-05-01 |  |  | No | 49 | [9 empty] | No | 0
VD-9001-251C-LST-017 | 0 | SUB-VENDOR LIST | HM-251C | Fateh Sanat Kimia Co. | 2020-02-29 |  |  | No | 111 | [9 empty] | No | 0
VD-9001-251C-PCJ-018 | 0 | REPAIR PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-03-01 |  |  | No | 110 | [9 empty] | No | 0
VD-9001-251C-PCJ-019 | 0 | WELDER QUALIFICATION RECORD | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-020 | 0 | CASTING PROCEDURE FOR INTERMEDIATE TUBESHEET (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-021 | 0 | FINNING PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-022 | 0 | REFRACTORY ANCHOR LAYOUT DRAWING | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-023 | 0 | WELDER QUALIFICATION RECORD | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-024 | 0 | RT PROCEDURE CASTING (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-025 | 0 | ASSEMBLYING PROCEDURE | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-PCJ-027 | 0 | CASTING LIQUID PENETRANT CONTROL PROCEDURE (BY CASTING VENDOR) | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-CSS-028 | 0 | GENERAL SPECIFICATION FOR STATICAL CAST SUPPORTING COMPONENT FOR HIGHT TEMPRATURE SERVICE MAT. G-X40NICRCOW 35-25-15-5-"SUPPER THERM" (OR EQUIVALENT) | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-CSS-029 | 0 | GENERAL SPECIFICATION FOR STATICAL CAST SUPPORTING COMPONENT FOR HIGHT TEMPRATURE SERVICE MAT. P22-ASTM A217 GR WC 9 | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-CSS-030 | 0 | GENERAL SPECIFICATION FOR STATICAL CAST SUPPORTING COMPONENT FOR HIGHT TEMPRATURE SERVICE MAT. 19 CR-9 NI-ASTM A297 GR HF | HM-251C | Fateh Sanat Kimia Co. | 2020-07-02 |  |  | No | -13 | [9 empty] | No | 0
VD-9001-251C-CSS-031 | 0 | GENERAL SPECIFICATION FOR CAST PARTS INSPECTION | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-251C-DWG-031 | 0 | CONVECTION COIL DRAWING & MANIFOLD ASSEMBLY DRAWING HE-1001 | HM-251C | Fateh Sanat Kimia Co. | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-104(1)-PPL-010 | 1 | ASU PLOT PLAN | PR-104(1) | HATCO CO. | 2020-03-14 20:00 | 2020-05-20 08:42 | 2020-05-20 08:42 | Yes | 67 |  |  |  | 2020-05-27 15:39 |  |  |  |  | 2020-05-27 15:39 | Yes | -7 | 1204-Owner-v | 2020-05-20 08:51
VD-9001-254-LST-362 | 6 | CONTROL SYSTEM MTO | HM-254 | AZAR AB | 2020-03-02 13:54 | 2020-03-03 07:33 | 2020-03-03 07:33 | Yes | 1 |  |  | 2020-03-14 11:00 | [5 empty] | 2020-03-14 11:00 | Yes | -3 | 1204-Owner-v | 2020-03-07 10:17
VD-9001-307A1-DSH-001 | 2 | PUMP DATASHEET WITH CURVE FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-16 20:00 | 2020-03-19 13:05 | 2020-03-19 13:06 | Yes | 3 |  |  |  | 2020-04-20 12:21 |  |  |  |  | 2020-04-20 12:21 | Yes | 18 | 1204-Owner-v | 2020-04-01 10:32
VD-9001-307A1-DSH-004 | 2 | PUMP DATASHEET WITH CURVE FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-16 20:00 | 2020-03-19 13:06 | 2020-03-19 13:06 | Yes | 3 |  |  |  | 2020-04-20 12:30 |  |  |  |  | 2020-04-20 12:30 | Yes | 18 | 1204-Owner-v | 2020-04-01 10:33
VD-9001-307A1-DSH-003 | 2 | PUMP DATASHEET WITH CURVE FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-03-16 20:00 | 2020-03-19 13:06 | 2020-03-19 13:06 | Yes | 3 |  |  |  | 2020-04-20 12:28 |  |  |  |  | 2020-04-20 12:28 | Yes | 18 | 1204-Owner-v | 2020-04-01 10:33
VD-9001-307A1-DSH-006 | 2 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-13 | 2020-03-19 13:06 | 2020-03-19 13:07 | Yes | 6 |  |  |  |  | 2020-05-06 14:44 |  |  |  | 2020-05-06 14:44 | Yes | 34 | 1204-Owner-v | 2020-04-01 10:33
VD-9001-307A1-DSH-005 | 2 | PUMP DATASHEET WITH CURVE FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-13 | 2020-03-19 13:06 | 2020-03-19 13:07 | Yes | 6 |  |  |  | 2020-04-20 13:07 |  |  |  |  | 2020-04-20 13:07 | Yes | 18 | 1204-Owner-v | 2020-04-01 10:33
VD-9001-307A1-DSH-002 | 2 | PUMP DATASHEET WITH CURVE FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-17 | 2020-03-19 13:05 | 2020-03-19 13:06 | Yes | 2 |  |  |  | 2020-04-20 12:23 |  |  |  |  | 2020-04-20 12:23 | Yes | 18 | 1204-Owner-v | 2020-04-01 10:32
VD-9001-740C-MOD-271 | 0 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-09 15:50 | 2020-03-09 15:50 | Yes | -1 |  |  |  | 2020-04-13 14:15 |  |  |  |  | 2020-04-13 21:00 | Yes | 21
VD-9001-740C-GAD-271 | 0 | General Arrangement Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-09 15:21 | 2020-03-09 15:21 | Yes | -1 |  |  |  | 2020-04-14 14:03 |  |  |  |  | 2020-04-14 14:03 | Yes | 22 | 1204-Owner-v | 2020-03-11 14:19
VD-9001-740C-SAD-271 | 0 | Assembly drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-05-09 14:26 | 2020-05-09 14:26 | Yes | 60 |  |  |  | 2020-05-10 08:43 |  |  |  |  | 2020-05-10 14:49 | Yes | -13
VD-9001-740C-RPT-271 | 0 | Reports For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-12 14:22 | 2020-03-12 14:22 | Yes | 2 |  |  |  | 2020-04-14 13:49 |  |  |  |  | 2020-04-14 13:49 | Yes | 19
VD-9001-740C-SPD-271 | 0 | Single Part Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-05-21 10:47 | 2020-05-21 10:52 | Yes | 72 |  |  |  | 2020-05-31 10:02 |  |  | 2020-05-18 09:43 | 2020-05-18 09:43 | 2020-05-31 10:02 | Yes | -4 | 1204-Owner-v | 2020-05-26 08:37
VD-9001-740C-ITP-271 | 0 | inspection and test plan (ITP) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 11:29 | 2020-03-10 11:29 | Yes | 0 |  |  |  | 2020-04-06 14:26 |  |  |  |  | 2020-04-06 21:00 | Yes | 13
VD-9001-740C-WPS-001 | 0 | WELDING BOOK (WPS,PQR,WELDING MAP,WPQ) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 12:45 | 2020-03-10 12:45 | Yes | 0 |  |  |  | 2020-04-29 15:48 |  |  |  |  | 2020-04-29 21:03 | Yes | 36
VD-9001-740C-PCJ-001 | 0 | NDT PROCEDURE AND NDT MAP For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 11:50 | 2020-03-10 11:50 | Yes | 0 |  |  |  | 2020-04-06 14:37 |  |  |  |  | 2020-04-06 21:00 | Yes | 13 | 1204-Owner-v | 2020-05-19 19:05
VD-9001-740C-PCJ-002 | 0 | WELDING SEQUENCE PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 12:06 | 2020-03-11 12:57 | Yes | 0 |  |  |  | 2020-04-23 11:58 |  |  |  |  | 2020-04-23 20:59 | Yes | 30
VD-9001-740C-PCJ-003 | 0 | PAINTING AND COATING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 12:11 | 2020-03-10 12:13 | Yes | 0 |  |  |  | 2020-04-06 14:35 |  |  |  |  | 2020-04-06 21:00 | Yes | 13
VD-9001-740C-PCJ-004 | 0 | PACKING & MARKING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-03-10 | 2020-03-10 12:16 | 2020-03-11 12:57 | Yes | 0 |  |  |  | 2020-05-03 18:24 |  |  |  |  | 2020-05-03 21:02 | Yes | 40
VD-9001-254-PPL-318 | 8 | LAYOUTS & WIRING DIAGRAMS FOR CONTROL SYSTEM PANELS | HM-254 | AZAR AB | 2020-03-10 09:20 | 2020-03-10 10:51 | 2020-03-10 10:54 | Yes | 0 |  |  | 2020-04-15 11:24 | [5 empty] | 2020-04-15 11:24 | Yes | 22
VD-9001-254-DIG-320 | 6 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2020-03-10 10:51 | 2020-03-10 11:05 | 2020-03-10 11:07 | Yes | 0 |  |  |  | 2020-04-15 11:15 |  |  |  |  | 2020-04-15 11:15 | Yes | 22
VD-9001-254-DIG-336 | 3 | BMS LOGIC DIAGRAM | HM-254 | AZAR AB | 2020-03-10 10:51 | 2020-03-10 11:00 | 2020-03-10 11:03 | Yes | 0 |  |  | 2020-04-15 12:08 | [5 empty] | 2020-04-15 12:08 | Yes | 22
VD-9001-254-DIG-339 | 3 | ABC & SUPERVISORY FLOW DIAGRAMS | HM-254 | AZAR AB | 2020-03-10 12:00 | 2020-03-10 12:05 | 2020-03-10 12:06 | Yes | 0 |  |  | 2020-04-15 12:06 | [5 empty] | 2020-04-15 12:06 | Yes | 22
VD-9001-254-PID-115 | 6 | AIR & FLUE GAS P&I DIAGRAM | HM-254 | AZAR AB | 2020-03-10 12:06 | 2020-03-10 12:31 | 2020-03-10 12:32 | Yes | 0 |  |  | 2020-04-15 12:18 | [5 empty] | 2020-04-15 12:18 | Yes | 22
VD-9001-254-PID-116 | 7 | FUEL & COMBUSTION P&I DIAGRAM | HM-254 | AZAR AB | 2020-03-10 12:07 | 2020-03-10 12:33 | 2020-03-10 12:33 | Yes | 0 |  |  | 2020-04-15 12:13 | [5 empty] | 2020-04-15 12:13 | Yes | 22
VD-9001-254-PID-119 | 4 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2020-03-10 12:07 | 2020-03-10 12:33 | 2020-03-10 12:34 | Yes | 0 |  |  |  | 2020-05-02 08:02 |  |  |  |  | 2020-05-02 08:02 | Yes | 39
VD-9001-104(1)-LST-009 | 1 | List of main sub vendors | PR-104(1) | HATCO CO. | 2020-03-25 19:59 |  | 2020-03-17 16:32 | Yes | 86 | [6 empty] | 2020-04-09 11:47 | 2020-04-09 11:47 |  | Yes | 0 | 1204-Owner-v | 2020-03-25 04:31
VD-9001-260-DWG-009 | 0 | Body & Bundle detail drawing E-3009 | HM-260 | ABAN AIR COOLER. | 2020-06-22 | 2020-05-16 15:32 | 2020-05-16 15:42 | Yes | -37 | [9 empty] | No | 20
VD-9001-260-DWG-010 | 0 | Body & Bundle detail drawing E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-06-29 | 2020-06-15 11:44 | 2020-06-15 11:44 | Yes | -14 | [9 empty] | No | -10
VD-9001-260-DWG-011 | 0 | Name Plate Drawing E-1007 | HM-260 | ABAN AIR COOLER. | 2020-05-26 | 2020-06-07 15:26 | 2020-06-07 15:45 | Yes | 12 | [9 empty] | No | -2
VD-9001-260-DWG-012 | 0 | Name Plate Drawing E-1010 | HM-260 | ABAN AIR COOLER. | 2020-06-07 | 2020-06-07 15:49 | 2020-06-07 15:49 | Yes | 0 | [9 empty] | No | -2
VD-9001-260-DWG-013 | 0 | Name Plate Drawing E-3008 | HM-260 | ABAN AIR COOLER. | 2020-06-14 |  |  | No | 5 | [9 empty] | No | 0
VD-9001-260-DWG-014 | 0 | Name Plate Drawing E-3009 | HM-260 | ABAN AIR COOLER. | 2020-06-22 | 2020-06-07 15:53 | 2020-06-07 15:54 | Yes | -15 | [9 empty] | No | -2
VD-9001-260-DWG-015 | 0 | Name Plate Drawing E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-06-29 |  |  | No | -10 | [9 empty] | No | 0
VD-9001-260-WMP-001 | 0 | Welding & NDT Map | HM-260 | ABAN AIR COOLER. | 2020-07-13 |  |  | No | -24 | [9 empty] | No | 0
VD-9001-260-WBK-001 | 0 | Welding Book(WPS,PQR) | HM-260 | ABAN AIR COOLER. | 2020-07-13 | 2020-05-17 10:40 | 2020-05-17 10:42 | Yes | -57 |  |  |  | 2020-06-01 11:19 |  |  |  |  | 2020-06-01 11:19 | Yes | 1
VD-9001-260-PRC-001 | 0 | Welding Repair Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-20 | 2020-05-07 09:36 | 2020-05-07 09:37 | Yes | -74 |  |  | 2020-05-16 12:37 | [5 empty] | 2020-05-16 12:37 | Yes | -5
VD-9001-260-PRC-002 | 0 | NDT procedur | HM-260 | ABAN AIR COOLER. | 2020-07-20 | 2020-04-14 17:33 | 2020-04-14 17:35 | Yes | -97 |  |  |  | 2020-04-25 10:37 |  |  |  |  | 2020-04-25 10:37 | Yes | -3
VD-9001-260-PRC-003 | 0 | Hydrostatic Test Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-20 | 2020-05-16 07:24 | 2020-05-16 07:24 | Yes | -65 |  |  |  | 2020-05-25 14:42 |  |  |  |  | 2020-05-25 14:42 | Yes | -5
VD-9001-260-PRC-004 | 0 | Tube to Tube Sheet Joint Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-20 | 2020-05-12 12:45 | 2020-05-12 12:48 | Yes | -69 |  |  |  | 2020-06-01 11:36 |  |  |  |  | 2020-06-01 11:36 | Yes | 6
VD-9001-260-PRC-005 | 0 | Post Weld Heat Treatment | HM-260 | ABAN AIR COOLER. | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-260-PRC-006 | 0 | Hardness test Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-260-PRC-007 | 0 | Surface Preparation and Painting Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-25 | 2020-05-12 18:44 | 2020-05-12 18:45 | Yes | -74 |  |  |  | 2020-05-25 14:24 |  |  |  |  | 2020-05-25 14:24 | Yes | -1
VD-9001-260-PRC-008 | 0 | Packing,Marking and Shipping Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-25 | 2020-05-12 13:53 | 2020-05-12 13:55 | Yes | -74 | [9 empty] | No | 24
VD-9001-260-PRC-009 | 0 | Material IdentificationAnd Traceability Procedure | HM-260 | ABAN AIR COOLER. | 2020-07-25 | 2020-04-15 10:17 | 2020-04-15 10:18 | Yes | -101 |  |  |  | 2020-04-27 15:53 |  |  |  |  | 2020-04-27 15:53 | Yes | -2
VD-9001-260-PRC-010 | 0 | Bolt Tightening Procedurefor | HM-260 | ABAN AIR COOLER. | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-260-PRC-011 | 0 | Preservation and Protection Procedure | HM-260 | ABAN AIR COOLER. | 2020-08-01 |  |  | No | -43 | [9 empty] | No | 0
VD-9001-260-PRC-012 | 0 | Pickling and Passivation Procedure ( for S.S. component if applicable | HM-260 | ABAN AIR COOLER. | 2020-08-01 |  |  | No | -43 | [9 empty] | No | 0
VD-9001-260-ITP-001 | 0 | Inspection and Test Plan | HM-260 | ABAN AIR COOLER. | 2020-05-02 | 2020-05-31 10:48 | 2020-05-31 10:48 | Yes | 29 |  |  |  | 2020-06-10 10:25 |  |  |  |  | 2020-06-10 10:25 | Yes | -4
VD-9001-260-DIS-001 | 0 | Vendor Print Index & Schedule | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-03-14 16:11 | 2020-03-14 16:11 | Yes | -37 |  |  |  | 2020-04-25 10:50 |  |  |  |  | 2020-04-25 10:50 | Yes | 28
VD-9001-260-LIS-001 | 0 | Sub Vendor List | HM-260 | ABAN AIR COOLER. | 2020-05-02 | 2020-05-03 11:23 | 2020-05-03 11:23 | Yes | 1 |  |  |  |  | 2020-05-04 08:50 |  |  |  | 2020-05-04 08:50 | Yes | -13
VD-9001-260-LIS-002 | 0 | Spare Parts For Pre-Commissioning, Commissioning and Start up | HM-260 | ABAN AIR COOLER. | 2020-07-19 |  |  | No | -30 | [9 empty] | No | 0
VD-9001-260-DSH-001 | 0 | Process Data Sheet E-1007 | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-04-12 12:31 | 2020-04-12 12:40 | Yes | -8 |  |  |  | 2020-04-19 10:55 |  |  |  |  | 2020-04-19 10:55 | Yes | -7
VD-9001-260-DSH-002 | 0 | Process Data Sheet E-1010 | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-04-12 12:42 | 2020-04-12 12:58 | Yes | -8 |  |  |  | 2020-04-19 10:59 |  |  |  |  | 2020-04-19 10:59 | Yes | -7
VD-9001-260-DSH-003 | 0 | Process Data Sheet E-3008 | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-04-12 13:02 | 2020-04-12 13:10 | Yes | -8 |  |  |  | 2020-04-19 11:01 |  |  |  |  | 2020-04-19 11:01 | Yes | -7
VD-9001-260-DSH-004 | 0 | Process Data Sheet E-3009 | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-04-12 13:05 | 2020-04-12 13:05 | Yes | -8 |  |  |  | 2020-04-19 11:54 |  |  |  |  | 2020-04-19 11:54 | Yes | -7
VD-9001-260-DSH-005 | 0 | Process Data Sheet E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-04-20 | 2020-04-12 13:13 | 2020-04-12 13:27 | Yes | -8 |  |  |  | 2020-04-19 11:58 |  |  |  |  | 2020-04-19 11:58 | Yes | -7
VD-9001-260-CAL-001 | 0 | Mechanical Calculation Book E-1007 | HM-260 | ABAN AIR COOLER. | 2020-05-03 | 2020-04-29 15:41 | 2020-04-29 15:44 | Yes | -4 |  |  |  |  | 2020-05-30 09:43 |  |  |  | 2020-05-30 09:43 | Yes | 17
VD-9001-260-CAL-002 | 0 | Mechanical Calculation Book E-1010 | HM-260 | ABAN AIR COOLER. | 2020-05-03 | 2020-05-19 15:56 | 2020-05-19 16:07 | Yes | 16 | [9 empty] | No | 17
VD-9001-260-CAL-003 | 0 | Mechanical Calculation Book E-3008 | HM-260 | ABAN AIR COOLER. | 2020-05-17 | 2020-06-16 18:14 | 2020-06-16 18:15 | Yes | 30 | [9 empty] | No | -11
VD-9001-260-CAL-004 | 0 | Mechanical Calculation Book E-3009 | HM-260 | ABAN AIR COOLER. | 2020-05-17 | 2020-04-21 16:25 | 2020-04-21 16:25 | Yes | -26 |  |  |  |  | 2020-05-30 12:10 |  |  |  | 2020-05-30 12:10 | Yes | 25
VD-9001-260-CAL-005 | 0 | Mechanical Calculation Book E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-05-17 | 2020-06-07 12:16 | 2020-06-07 12:19 | Yes | 21 | [9 empty] | No | -2
VD-9001-260-DWG-001 | 0 | General Arrangement Drawing E-1007 | HM-260 | ABAN AIR COOLER. | 2020-05-03 | 2020-04-29 15:52 | 2020-04-29 15:52 | Yes | -4 | [9 empty] | No | 37
VD-9001-260-DWG-002 | 0 | General Arrangement Drawing E-1010 | HM-260 | ABAN AIR COOLER. | 2020-05-10 | 2020-05-19 16:23 | 2020-05-19 16:23 | Yes | 9 | [9 empty] | No | 17
VD-9001-260-DWG-003 | 0 | General Arrangement Drawing E-3008 | HM-260 | ABAN AIR COOLER. | 2020-05-17 | 2020-06-16 17:56 | 2020-06-16 17:58 | Yes | 30 | [9 empty] | No | -11
VD-9001-260-DWG-004 | 0 | General Arrangement Drawing E-3009 | HM-260 | ABAN AIR COOLER. | 2020-05-27 | 2020-04-21 16:43 | 2020-04-21 16:44 | Yes | -36 | [9 empty] | No | 45
VD-9001-260-DWG-005 | 0 | General Arrangement Drawing E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-06-10 | 2020-06-07 12:20 | 2020-06-07 12:25 | Yes | -3 | [9 empty] | No | -2
VD-9001-260-DWG-006 | 0 | Body & Bundle detail drawing E-1007 | HM-260 | ABAN AIR COOLER. | 2020-05-26 | 2020-05-20 11:10 | 2020-05-20 11:10 | Yes | -6 | [9 empty] | No | 16
VD-9001-260-DWG-007 | 0 | Body & Bundle detail drawing E-1010 | HM-260 | ABAN AIR COOLER. | 2020-06-07 | 2020-06-02 15:30 | 2020-06-02 15:30 | Yes | -5 | [9 empty] | No | 3
VD-9001-260-DWG-008 | 0 | Body & Bundle detail drawing E-3008 | HM-260 | ABAN AIR COOLER. | 2020-06-14 |  |  | No | 5 | [9 empty] | No | 0
VD-9001-260-LIS-003 | 0 | Spare Part For Two-Years Operation | HM-260 | ABAN AIR COOLER. | 2020-07-19 |  |  | No | -30 | [9 empty] | No | 0
VD-9001-260-QCP-001 | 0 | Quality Control Plan (QCP) | HM-260 | ABAN AIR COOLER. | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-260-QCP-002 | 0 | Vendor 's Quality Assurance Plan | HM-260 | ABAN AIR COOLER. | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-260-CER-001 | 0 | Welders Qulalification Certificates | HM-260 | ABAN AIR COOLER. | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-260-CER-002 | 0 | NDT Personal Qualificaton Certificate | HM-260 | ABAN AIR COOLER. | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-260-CER-003 | 0 | Tools and equipment Calibration certificates. | HM-260 | ABAN AIR COOLER. | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-260-INX-001 | 0 | Final Data Book Index | HM-260 | ABAN AIR COOLER. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-260-FDB-001 | 0 | Final Data Book | HM-260 | ABAN AIR COOLER. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-201A-PCJ-076 | 2 | PRODUCTION TEST PLATE (PTP) PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2020-03-29 | 2020-04-05 10:38 | 2020-04-05 10:38 | Yes | 7 |  |  |  | 2020-04-23 12:58 |  |  |  |  | 2020-04-23 12:58 | Yes | 4
VD-9001-307A1-DSH-007 | 2 | MOTOR DATASHEET WITH CURVE FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-03-28 |  |  | No | 83 | [9 empty] | No | 0
VD-9001-307A1-DSH-010 | 2 | MOTOR DATASHEET WITH CURVE FOR PM4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-03-27 |  |  | No | 84 | [9 empty] | No | 0
VD-9001-307A1-DSH-009 | 2 | MOTOR DATASHEET WITH CURVE FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-03-27 |  |  | No | 84 | [9 empty] | No | 0
VD-9001-307A1-DSH-012 | 2 | MOTOR DATASHEET WITH CURVE FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-03-27 |  |  | No | 84 | [9 empty] | No | 0
VD-9001-307A1-DSH-011 | 2 | MOTOR DATASHEET WITH CURVE FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-03-27 |  |  | No | 84 | [9 empty] | No | 0
VD-9001-213B1-PRG-002 | 0 | Planned time scheduled | PV-213B1 | PAYSAZ Co. | 2020-03-05 | 2020-04-05 13:02 | 2020-04-05 13:02 | Yes | 31 |  |  | 2020-04-07 08:41 | [5 empty] | 2020-04-07 20:59 | Yes | -12
VD-9001-213B1-WBS-003 | 0 | Work Break Down Structure (WBS) | PV-213B1 | PAYSAZ Co. | 2020-03-05 | 2020-04-05 12:51 | 2020-04-05 12:51 | Yes | 31 |  |  | 2020-04-07 08:40 | [5 empty] | 2020-04-07 20:59 | Yes | -12
VD-9001-213B1-CAL-005 | 0 | Mechanical Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-03-05 | 2020-04-05 13:10 | 2020-04-05 13:11 | Yes | 31 |  |  | 2020-04-19 13:14 | [5 empty] | 2020-04-19 20:59 | Yes | 0 | 1204-Owner-v | 2020-06-03 09:34
VD-9001-213B1-ITP-030 | 0 | Inspection and Test Plan (ITP) | PV-213B1 | PAYSAZ Co. | 2020-03-11 | 2020-04-13 12:34 | 2020-04-13 12:34 | Yes | 33 |  |  |  |  | 2020-04-28 08:43 |  |  |  | 2020-04-28 20:59 | Yes | 1
VD-9001-213B1-PCJ-031 | 0 | NDT Procedure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-03-11 | 2020-04-15 10:40 | 2020-04-15 10:41 | Yes | 35 |  |  |  |  | 2020-04-28 08:44 |  |  |  | 2020-04-28 20:59 | Yes | -1
VD-9001-213B1-PCJ-037 | 0 | Painting & Pickling and Passivation Procedure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-03-11 | 2020-04-13 12:56 | 2020-04-13 12:57 | Yes | 33 |  |  |  |  | 2020-05-02 12:33 |  |  |  | 2020-05-02 20:58 | Yes | 5
VD-9001-307A1-DSH-008 | 2 | MOTOR DATASHEET WITH CURVE FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-04-13 |  |  | No | 67 | [9 empty] | No | 0
VD-9001-740B-GAD-30319 | 3 | GA DRAWINGS FOR STRUCTURE C | ST-740B | PETRO ADAK IRAN | 2020-04-13 | 2020-04-12 08:33 | 2020-04-12 08:35 | Yes | -1 |  |  | 2020-04-13 13:20 | [5 empty] | 2020-04-13 20:59 | Yes | -13
VD-9001-740C-ITP-271 | 1 | inspection and test plan (ITP) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-13 | 2020-04-11 13:39 | 2020-04-11 13:40 | Yes | -2 |  |  |  | 2020-04-22 19:26 |  |  |  |  | 2020-04-22 21:04 | Yes | -3
VD-9001-740C-PCJ-003 | 1 | PAINTING AND COATING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-13 | 2020-04-11 13:38 | 2020-04-11 13:38 | Yes | -2 |  |  |  | 2020-05-02 12:03 |  |  |  |  | 2020-05-02 20:58 | Yes | 7
VD-9001-740C-PCJ-001 | 1 | NDT PROCEDURE AND NDT MAP For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-13 | 2020-04-11 13:39 | 2020-04-11 13:39 | Yes | -2 |  |  | 2020-04-22 19:23 | [5 empty] | 2020-04-22 21:03 | Yes | -3 | 1204-Owner-v | 2020-05-26 08:15
VD-9001-251E-DIS-001 | 0 | Vendor Documents Index & Schedule | HM-251E | Iran Industrial Vibrations Co. | 2020-03-07 |  |  | No | 104 | [9 empty] | No | 0
VD-9001-251E-DWG-002 | 0 | Assembly Drawing for DWG No.: F-OF16220 | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 08:26 | 2020-04-11 08:36 | Yes | 28 |  |  |  |  | 2020-04-25 17:56 |  |  |  | 2020-04-25 17:56 | Yes | 0
VD-9001-251E-DWG-003 | 0 | Assembly Drawn for DWG No.:F-OF16230 | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 08:39 | 2020-04-11 08:40 | Yes | 28 |  |  |  |  | 2020-04-25 17:52 |  |  |  | 2020-04-25 17:52 | Yes | 0
VD-9001-251E-DWG-004 | 0 | Assembly Drawing for DWG No.:F-OF16240 | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 08:48 | 2020-04-11 08:49 | Yes | 28 |  |  |  |  | 2020-04-25 17:53 |  |  |  | 2020-04-25 17:53 | Yes | 0
VD-9001-251E-ITP-005 | 0 | Inspection & Test Plan (ITP) | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 08:56 | 2020-04-11 08:58 | Yes | 28 |  |  |  | 2020-04-19 09:26 |  |  |  |  | 2020-04-19 09:26 | Yes | -6
VD-9001-251E-VLS-006 | 0 | Sub Vendor List | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 08:51 | 2020-04-11 08:53 | Yes | 28 |  |  | 2020-04-27 16:31 | [5 empty] | 2020-04-27 16:31 | Yes | 2
VD-9001-251E-WPS-007 | 0 | Welding Book( WPS &PQR & WQT) | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 |  |  | No | 97 | [9 empty] | No | 0
VD-9001-251E-PCJ-008 | 0 | Assmbly Instuction | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 |  |  | No | 97 | [9 empty] | No | 0
VD-9001-251E-PCJ-009 | 0 | Painting Procedure | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-04-11 09:01 | 2020-04-11 09:04 | Yes | 28 |  |  |  | 2020-04-19 11:09 |  |  |  |  | 2020-04-19 11:09 | Yes | -6
VD-9001-251E-PCJ-010 | 0 | Dimensional and Visual Inspection | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 |  |  | No | 97 | [9 empty] | No | 0
VD-9001-251E-PCJ-011 | 0 | Packing Procedure | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 | 2020-05-09 15:49 | 2020-05-09 15:50 | Yes | 56 |  |  | 2020-05-16 11:17 | [5 empty] | 2020-05-16 11:17 | Yes | -7
VD-9001-251E-INX-012 | 0 | Final Data Book Index | HM-251E | Iran Industrial Vibrations Co. | 2020-03-14 |  |  | No | 97 | [9 empty] | No | 0
VD-9001-251E-FDB-013 | 0 | Final Data Book | HM-251E | Iran Industrial Vibrations Co. | 2020-04-10 |  |  | No | 70 | [9 empty] | No | 0
VD-9001-201B-DWG-003 | 3 | NAME PLATE DET.DWG (4134-0359/A) | PV-201B | Brembana & Rolle S.p.A. | 2020-04-07 09:26 | 2020-04-08 11:24 | 2020-04-08 11:26 | Yes | 1 |  |  | 2020-04-12 08:33 | [5 empty] | 2020-04-12 20:59 | Yes | -10
VD-9001-201A-DWG-026 | 2 | SHIPPING AND LIFTING STYLE DRAWING - R-1002 A/B | PV-201A | FATEH SANAT KIMIA | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-201A-DWG-008 | 2 | SHIPPING AND LIFTING STYLE DRAWING - R1001 | PV-201A | FATEH SANAT KIMIA | 2020-04-15 |  |  | No | 65 | [9 empty] | No | 0
VD-9001-307A1-DSH-023 | 2 | STEAM TURBINE DATASHEET WITH CURVE FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-04-21 | 2020-06-01 13:03 | 2020-06-01 13:03 | Yes | 41 |  |  |  |  | 2020-06-15 12:26 |  |  |  | 2020-06-15 12:26 | Yes | 0
VD-9001-307A1-DWG-078 | 1 | PUMP NAME PLATE DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-04-26 20:59 | 2020-04-14 12:47 | 2020-04-14 12:47 | Yes | -12 |  |  | 2020-04-18 13:49 | [5 empty] | 2020-04-18 21:00 | Yes | -10
VD-9001-307A1-PCJ-008 | 1 | PACKING AND DELIVERY PROCEDURE(STEEEL STRUCTURE) FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-04-26 20:59 | 2020-04-14 12:47 | 2020-04-14 12:47 | Yes | -12 |  |  | 2020-04-18 13:50 | [5 empty] | 2020-04-18 21:00 | Yes | -10
VD-9001-104(1-S)-DWG-025 | 0 | Air Compressor oil purifying unit General arrangement plan (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-026 | 0 | Air Compressor Suction strainer drawing (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-104(1-S)-WIN-001 | 0 | Air Compressor planning notes (drains) (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-10 | 2020-04-28 10:51 | 2020-04-28 10:51 | Yes | 18 |  |  | 2020-04-29 14:39 | [5 empty] | 2020-04-29 21:01 | Yes | -13 | 1204-Owner-v | 2020-05-11 09:04
VD-9001-104(1-S)-DWG-027 | 0 | Air Compressor measuring point location plan (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-WIN-002 | 0 | Air Compressor start-up instruction (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-028 | 0 | Air Compressor control oil unit (dimension drawing) | PR-104(1) | HATCO CO. | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-104(1-S)-WIN-003 | 0 | Air Compressor planning notes (piping; equipm.; found.) (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-10 | 2020-04-28 10:51 | 2020-04-28 10:51 | Yes | 18 |  |  |  | 2020-04-29 15:14 |  |  |  |  | 2020-04-29 21:02 | Yes | -13 | 1204-Owner-v | 2020-06-02 09:42
VD-9001-104(1-S)-DWG-029 | 0 | Air Compressor expansion joint (dimension drawing) (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-MDB-001 | 0 | Manufacturer data book (MDB) SST core turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2021-08-30 |  |  | No | -437 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-019 | 0 | Data Sheet – Safety Valve – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-DIG-016 | 0 | Cause and effect diagram For Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-019 | 0 | Compressor Coupling Drawing (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-010 | 0 | Customer connection list For Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-020 | 0 | Gear Box Drawing For Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-021 | 0 | Lifting arrangement For Air Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-09-15 |  |  | No | -88 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-022 | 0 | Air Compressor Control valve – Drawing (Anti-surge, By-pass, Blow-off) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-023 | 0 | Oil Unit General Arrangement Plan for Air Compressor | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-011 | 0 | Control panel (Communication list / Data exchange list) for Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-10-30 |  |  | No | -133 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-016 | 0 | Air Compressor Control valve – Data Sheet (Anti-surge, By-pass, Blow-off) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-012 | 0 | Air Compressor waste heat list (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-30 | 2020-04-27 17:38 | 2020-04-27 17:38 | Yes | -33 |  |  |  | 2020-04-29 15:40 |  |  |  |  | 2020-04-29 21:03 | Yes | -12
VD-9001-104(1-S)-DSH-017 | 0 | Air Compressor thermodynamical data sheets (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-30 | 2020-04-28 10:52 | 2020-04-28 10:53 | Yes | -2 |  |  |  | 2020-04-29 15:01 |  |  |  |  | 2020-04-29 21:01 | Yes | -13
VD-9001-104(1-S)-DSH-018 | 0 | Gas cooler data sheet For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-024 | 0 | Drawing – Safety Valve – Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-WIN-004 | 0 | Planning notes (limiting and protection) – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-10 | 2020-04-28 10:48 | 2020-04-28 10:51 | Yes | 18 |  |  | 2020-04-29 15:21 | [5 empty] | 2020-04-29 21:02 | Yes | -13
VD-9001-104(1-S)-ITP-002 | 0 | Inspection and test plan – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-30 | 2020-04-28 11:31 | 2020-04-28 11:31 | Yes | -2 |  |  |  | 2020-04-29 16:34 |  |  |  |  | 2020-04-29 21:04 | Yes | -13
VD-9001-104(1-S)-CAL-007 | 0 | Foundation load calculation – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-013 | 0 | Lateral analysis – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-104(1-S)-PCJ-002 | 0 | Painting specification – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-10 | 2020-04-28 10:52 | 2020-04-28 10:52 | Yes | 18 |  |  |  | 2020-05-09 17:58 |  |  |  |  | 2020-05-09 21:04 | Yes | -3
VD-9001-104(1-S)-MNL-002 | 0 | Operating manual – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2021-08-30 |  |  | No | -437 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-030 | 0 | lifting arrangement – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-031 | 0 | Moisture Separators Drawing For All Stages Air Compressor package | PR-104(1) | HATCO CO. | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-008 | 0 | Piping Stress Calculation For Air Compressor package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-10-30 |  |  | No | -133 | [9 empty] | No | 0
VD-9001-104(1-S)-STR-002 | 0 | Control Philosophy For Stean Turbine | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-032 | 0 | Rating plate – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-09-20 |  |  | No | -93 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-014 | 0 | Special Tools List – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2021-04-10 |  |  | No | -295 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-015 | 0 | Customer connection list – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-DIA-003 | 0 | Control oil diagram – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-04-18 13:09 | 2020-04-18 13:09 | Yes | -2 |  |  |  | 2020-05-04 12:41 |  |  |  |  | 2020-05-04 12:41 | Yes | 2 | 1204-Owner-v | 2020-04-18 13:25
VD-9001-104(1-S)-DIA-004 | 0 | Cause and effect diagram – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-016 | 0 | Air Compressor Package Instrument List (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-104(1-S)-PCJ-003 | 0 | Erection documentation – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2021-04-20 |  |  | No | -305 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-017 | 0 | Air Compressor Package Setting list (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-018 | 0 | Utility consumer list– Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-04-18 13:14 | 2020-04-18 13:14 | Yes | -2 |  |  |  | 2020-05-03 19:04 |  |  |  |  | 2020-05-03 21:03 | Yes | 1 | 1204-Owner-v | 2020-04-19 10:00
VD-9001-104(1-S)-LST-019 | 0 | colli list– Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-033 | 0 | Junction box incl. Local control panel – Wiring diagram– Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-020 | 0 | Measurement point list - remote For Air Compressor Package | PR-104(1) | HATCO CO. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-104(1-S)-LST-021 | 0 | Sub-supplier list For Air Compressor Package | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1-S)-DWG-034 | 0 | Main steam isolating valve and bypass | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-04-28 11:30 | 2020-04-28 11:30 | Yes | 8 |  |  | 2020-04-29 15:24 | [5 empty] | 2020-04-29 21:02 | Yes | -13
VD-9001-104(1-K)-PID-003 | 0 | ASU P&ID Index | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:08 | 2020-04-26 14:09 | Yes | 11 |  |  |  | 2020-05-02 11:39 |  |  |  |  | 2020-05-02 11:39 | Yes | -8
VD-9001-104(1-K)-PID-004 | 0 | ASU P&ID - PIPELINE, EQUIPMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:09 | 2020-04-26 14:09 | Yes | 11 |  |  |  | 2020-05-03 18:15 |  |  |  |  | 2020-05-03 18:15 | Yes | -7
VD-9001-104(1-K)-PID-005 | 0 | ASU P&ID - INSTRUMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:09 | 2020-04-26 14:09 | Yes | 11 |  |  |  | 2020-05-03 17:03 |  |  |  |  | 2020-05-03 17:03 | Yes | -7
VD-9001-104(1-K)-PID-006 | 0 | ASU P&ID - INTERLOCK POINT LISTS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:10 | 2020-04-26 14:10 | Yes | 11 |  |  |  | 2020-05-02 12:59 |  |  |  |  | 2020-05-02 12:59 | Yes | -8
VD-9001-104(1-K)-PID-007 | 0 | ASU P&ID - AIR FILTERING & COMPRESSION LINE1 | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:10 | 2020-04-26 14:10 | Yes | 11 |  |  |  | 2020-05-11 15:21 |  |  |  |  | 2020-05-11 15:21 | Yes | 1
VD-9001-104(1-K)-PID-008 | 0 | ASU P&ID - AIR FILTERING & COMPRESSION LINE2 | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:10 | 2020-04-26 14:10 | Yes | 11 |  |  |  | 2020-05-11 15:27 |  |  |  |  | 2020-05-11 15:27 | Yes | 1
VD-9001-104(1-K)-PID-009 | 0 | ASU P&ID - PRE-COOLING SYSTEM, AIR COOLING TOWER, COOLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:10 | 2020-04-26 14:10 | Yes | 11 |  |  |  | 2020-05-05 17:59 |  |  |  |  | 2020-05-05 21:02 | Yes | -5
VD-9001-104(1-K)-PID-010 | 0 | ASU P&ID - PRE-COOLING SYSTEM, WATER COOLING TOWER, CHILLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:10 | 2020-04-26 14:10 | Yes | 11 |  |  |  | 2020-05-05 18:25 |  |  |  |  | 2020-05-05 21:02 | Yes | -5
VD-9001-104(1-K)-PID-011 | 0 | ASU P&ID - PURIFICATION SYSTEM ADSORBER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:11 | 2020-04-26 14:11 | Yes | 11 |  |  |  | 2020-05-05 18:32 |  |  |  |  | 2020-05-05 21:02 | Yes | -5
VD-9001-104(1-K)-PID-012 | 0 | ASU P&ID - PURIFICATION SYSTEM STEAM HEATER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:11 | 2020-04-26 14:11 | Yes | 11 |  |  |  | 2020-05-05 18:39 |  |  |  |  | 2020-05-05 21:03 | Yes | -5
VD-9001-104(1-K)-PID-013 | 0 | ASU P&ID - PURIFICATION TEMP. DECREASED, PRESSURE REDUCER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:11 | 2020-04-26 14:11 | Yes | 11 |  |  |  | 2020-05-05 18:44 |  |  |  |  | 2020-05-05 21:03 | Yes | -5
VD-9001-104(1-K)-PID-014 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, EXPANDER SYSTEM | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:11 | 2020-04-26 14:11 | Yes | 11 |  |  |  | 2020-05-27 15:54 |  |  |  |  | 2020-05-27 15:54 | Yes | 17
VD-9001-104(1-K)-PID-015 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, DETAILED DWG. A EXPANDER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:12 | 2020-04-26 14:12 | Yes | 11 |  |  |  | 2020-05-27 16:01 |  |  |  |  | 2020-05-27 16:01 | Yes | 17
VD-9001-104(1-K)-PID-016 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, DETAILED DWG. B EXPANDER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:12 | 2020-04-26 14:12 | Yes | 11 |  |  |  | 2020-05-27 16:09 |  |  |  |  | 2020-05-27 16:09 | Yes | 17 | 1204-Owner-v | 2020-05-03 11:37
VD-9001-104(1-K)-PID-017 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:12 | 2020-04-26 14:12 | Yes | 11 |  |  |  | 2020-05-23 16:20 |  |  |  |  | 2020-05-23 16:20 | Yes | 13
VD-9001-104(1-K)-PID-018 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:12 | 2020-04-26 14:12 | Yes | 11 |  |  |  | 2020-05-23 16:37 |  |  |  |  | 2020-05-23 16:37 | Yes | 13
VD-9001-104(1-K)-PID-019 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, SUB-COOLER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:13 | 2020-04-26 14:13 | Yes | 11 |  |  |  | 2020-05-09 18:57 |  |  |  |  | 2020-05-09 21:05 | Yes | -1
VD-9001-104(1-K)-PID-020 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LOWER COLUMN | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:13 | 2020-04-26 14:13 | Yes | 11 |  |  |  | 2020-05-09 17:14 |  |  |  |  | 2020-05-09 21:03 | Yes | -1
VD-9001-104(1-K)-PID-021 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, UPPER COLUMN | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:13 | 2020-04-26 14:13 | Yes | 11 |  |  |  | 2020-05-09 17:03 |  |  |  |  | 2020-05-09 21:03 | Yes | -1
VD-9001-104(1-K)-PID-022 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP LOX PUMP A | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-26 14:13 | 2020-04-26 14:13 | Yes | 11 |  |  |  | 2020-05-13 17:06 |  |  |  |  | 2020-05-13 17:06 | Yes | 3
VD-9001-104(1-K)-PID-023 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP LOX PUMP B | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:15 | 2020-04-22 10:15 | Yes | 7 |  |  |  | 2020-05-23 15:27 |  |  |  |  | 2020-05-23 15:27 | Yes | 17
VD-9001-104(1-K)-PID-024 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP LIN PUMP A | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:15 | 2020-04-22 10:15 | Yes | 7 |  |  |  | 2020-05-02 09:44 |  |  |  |  | 2020-05-02 09:44 | Yes | -4
VD-9001-104(1-K)-PID-025 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP LIN PUMP B | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:16 | 2020-04-22 10:16 | Yes | 7 |  |  |  | 2020-05-02 10:03 |  |  |  |  | 2020-05-02 10:03 | Yes | -4
VD-9001-104(1-K)-PID-026 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LIQUID DRAINAGE SYSTEM | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:16 | 2020-04-22 10:16 | Yes | 7 |  |  |  | 2020-05-02 10:11 |  |  |  |  | 2020-05-02 10:12 | Yes | -4
VD-9001-104(1-K)-PID-027 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, OXYGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:16 | 2020-04-22 10:16 | Yes | 7 |  |  |  | 2020-05-02 10:47 |  |  |  |  | 2020-05-02 10:47 | Yes | -4
VD-9001-104(1-K)-PID-028 | 0 | ASU P&ID - RECTIFICATION COLUMN SYSTEM,NITROGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:16 | 2020-04-22 10:16 | Yes | 7 |  |  |  | 2020-05-02 11:31 |  |  |  |  | 2020-05-02 11:31 | Yes | -4
VD-9001-104(1-K)-PID-029 | 0 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VACUM STORAGE TANK | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:17 | 2020-04-22 10:17 | Yes | 7 |  |  |  | 2020-05-02 08:54 |  |  |  |  | 2020-05-02 08:54 | Yes | -4
VD-9001-104(1-K)-PID-030 | 0 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM BACK UP LIN PUMP | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:17 | 2020-04-22 10:17 | Yes | 7 |  |  |  | 2020-05-02 08:24 |  |  |  |  | 2020-05-02 08:24 | Yes | -4
VD-9001-104(1-K)-PID-031 | 0 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VAPORIZER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:17 | 2020-04-22 10:17 | Yes | 7 |  |  |  | 2020-05-02 08:01 |  |  |  |  | 2020-05-02 08:02 | Yes | -4
VD-9001-104(1-K)-PID-032 | 0 | ASU P&ID -PRODUCT INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:17 | 2020-04-22 10:17 | Yes | 7 |  |  |  | 2020-05-06 12:02 |  |  |  |  | 2020-05-06 20:58 | Yes | 0
VD-9001-104(1-K)-PID-033 | 0 | ASU P&ID -PUBLIC UTILITIES RECYCLING WATER, DEMINERALIZED WATER | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:18 | 2020-04-22 10:18 | Yes | 7 |  |  |  | 2020-05-23 14:59 |  |  |  |  | 2020-05-23 14:59 | Yes | 17
VD-9001-104(1-K)-PID-034 | 0 | ASU P&ID -PUBLIC UTILITIES SEAL GAS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:19 | 2020-04-22 10:19 | Yes | 7 |  |  |  | 2020-05-02 08:00 |  |  |  |  | 2020-05-02 08:00 | Yes | -4
VD-9001-104(1-K)-PID-035 | 0 | ASU P&ID -PUBLIC UTILITIES WARMING GAS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:19 | 2020-04-22 10:19 | Yes | 7 |  |  |  | 2020-05-02 07:59 |  |  |  |  | 2020-05-02 07:59 | Yes | -4
VD-9001-104(1-K)-PID-036 | 0 | ASU P&ID -PUBLIC UTILITIES INSTRUMENT AIR | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:20 | 2020-04-22 10:20 | Yes | 7 |  |  |  | 2020-05-02 08:59 |  |  |  |  | 2020-05-02 08:59 | Yes | -4
VD-9001-104(1-K)-PID-037 | 0 | ASU P&ID -UTILITIES INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-04-22 10:20 | 2020-04-22 10:20 | Yes | 7 |  |  |  | 2020-05-23 15:26 |  |  |  |  | 2020-05-23 15:26 | Yes | 17
VD-9001-104(1)-CAL-012 | 0 | Mechanical Strength Calculation Sheet for Water Cooling Tower (T-6102) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-CAL-013 | 0 | Water Cooling Tower Thermal calculation (T-6102) | PR-104(1) | HATCO CO. | 2020-04-20 |  |  | No | 60 | [9 empty] | No | 0
VD-9001-104(1)-DSH-016 | 0 | Water Cooling Tower Data Sheet (T-6102) | PR-104(1) | HATCO CO. | 2020-04-15 | 2020-05-26 17:46 | 2020-05-26 17:46 | Yes | 41 |  |  |  | 2020-06-07 11:39 |  |  |  |  | 2020-06-07 11:39 | Yes | -2 | 1204-Owner-v | 2020-05-31 13:41
VD-9001-104(1)-DWG-033 | 0 | Water Cooling Tower General arrangement (T-6102) | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-05-13 12:50 | 2020-05-13 12:51 | Yes | 23 |  |  |  | 2020-06-06 13:42 |  |  |  |  | 2020-06-06 13:42 | Yes | 10
VD-9001-104(1-S)-LST-009 | 0 | Air compressor 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:58 | Yes | 50 | [6 empty] | 2020-04-29 17:47 | 2020-04-29 17:47 |  | Yes | 0
VD-9001-104(1)-LST-011 | 0 | Air Compressor Intake Filter 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:55 | Yes | 50 | [6 empty] | 2020-04-29 18:00 | 2020-04-29 18:00 |  | Yes | 0
VD-9001-104(1)-LST-012 | 0 | Control Valve 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:55 | Yes | 50 | [6 empty] | 2020-04-29 17:58 | 2020-04-29 17:58 |  | Yes | 0
VD-9001-104(1)-LST-013 | 0 | Cooling & Chilling Water Pumps 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:55 | Yes | 50 | [6 empty] | 2020-04-29 17:55 | 2020-04-29 17:55 |  | Yes | 0
VD-9001-104(1-S)-DSH-011 | 0 | Expansion Turbine 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:59 | Yes | 50 | [6 empty] | 2020-04-29 17:46 | 2020-04-29 17:46 |  | Yes | 0
VD-9001-104(1)-LST-014 | 0 | I & C 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:56 | Yes | 50 | [6 empty] | 2020-04-29 17:52 | 2020-04-29 17:53 |  | Yes | 0
VD-9001-104(1)-LST-015 | 0 | LOX & LIN Pumps 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:56 | Yes | 50 | [6 empty] | 2020-04-29 17:49 | 2020-04-29 17:49 |  | Yes | 0
VD-9001-104(1-S)-DSH-012 | 0 | Steam Turbine & Lube Oil System 2 years spare part | PR-104(1) | HATCO CO. | 2020-04-30 |  | 2020-04-29 15:59 | Yes | 50 | [6 empty] | 2020-04-29 17:42 | 2020-04-29 17:42 |  | Yes | 0
VD-9001-104(1-S)-DSH-013 | 0 | installation diagram (Control system architecture) For Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-15 |  |  | No | -57 | [9 empty] | No | 0
VD-9001-104(1-S)-PFD-001 | 0 | PFD For Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-04-25 |  |  | No | 55 | [9 empty] | No | 0
VD-9001-104(1-S)-DSH-014 | 0 | List of special tools For Compressor (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-S)-STR-001 | 0 | Control Philosophy For Compressor Package | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1)-PFD-001 | 2 | Process flow diagram For ASU | PR-104(1) | HATCO CO. | 2020-04-27 20:59 |  |  | No | 53 | [9 empty] | No | 0
VD-9001-740C-MOD-271 | 1 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-20 | 2020-04-20 09:56 | 2020-04-20 10:09 | Yes | 0 |  |  |  | 2020-04-26 12:39 |  |  |  |  | 2020-04-26 12:39 | Yes | -8
VD-9001-740C-RPT-271 | 1 | Reports For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-21 | 2020-04-20 11:26 | 2020-04-20 11:26 | Yes | -1 |  |  |  | 2020-04-26 12:36 |  |  |  |  | 2020-04-26 12:36 | Yes | -8
VD-9001-740C-GAD-271 | 1 | General Arrangement Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-21 | 2020-04-20 09:50 | 2020-04-20 09:50 | Yes | -1 |  |  |  | 2020-04-26 12:36 |  |  |  |  | 2020-04-26 12:36 | Yes | -8 | 1204-Owner-v | 2020-04-25 09:19
VD-9001-307A1-PCJ-016 | 1 | REPAIR WELDIING PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-04-28 20:59 | 2020-04-25 08:28 | 2020-04-25 08:29 | Yes | -3 |  |  | 2020-05-06 15:02 | [5 empty] | 2020-05-06 15:02 | Yes | -3
VD-9001-307A1-PCJ-015 | 1 | POSITIVE MATERIAL IDENTIFICATION (PMI) PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-04-28 20:59 | 2020-04-25 08:28 | 2020-04-25 08:29 | Yes | -3 |  |  | 2020-05-06 15:00 | [5 empty] | 2020-05-06 15:00 | Yes | -3
VD-9001-201B-CAL-005 | 1 | TRANSPORTATION SADDLE CALCULATION (4134-0359/MC1) | PV-201B | Brembana & Rolle S.p.A. | 2020-04-28 20:59 | 2020-05-07 10:32 | 2020-05-07 10:34 | Yes | 9 |  |  | 2020-05-18 19:01 | [5 empty] | 2020-05-18 19:01 | Yes | -3
VD-9001-257B-NPL-034 | 3 | WELDING DOCUMENT (WPS,PQR) | HM-257B | FATEH SANAT KIMIA | 2020-04-22 | 2020-04-26 10:45 | 2020-04-26 10:45 | Yes | 4 |  |  | 2020-05-04 08:54 | [5 empty] | 2020-05-04 08:54 | Yes | -6
VD-9001-104(1)-PPL-001 | 0 | Funnel Location Plan | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1-M)-PPL-003 | 0 | Electrical Cable Route Layout | PR-104(1) | HATCO CO. | 2020-04-20 | 2020-05-27 14:14 | 2020-05-27 14:14 | Yes | 37 |  |  |  | 2020-05-31 11:19 |  |  |  |  | 2020-05-31 11:19 | Yes | -10 | 1204-Owner-v | 2020-06-02 09:48
VD-9001-104(1-S)-DIG-001 | 0 | Logic Diagram – Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-104(1-M)-STR-002 | 0 | Control Philosophy | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-104(1-K)-PPL-001 | 0 | F&G sensors layout | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-104(1)-SLD-003 | 0 | Structural Single line diagram for Pipe Racks | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PPL-002 | 0 | ASU Foundation Layout | PR-104(1) | HATCO CO. | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-104(1-M)-DIG-011 | 0 | Electrical power supply distribution diagram | PR-104(1) | HATCO CO. | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-307B-PCJ-012 | 0 | POSITIVE MATERIAL INDPMTIFICATION(PMI) PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-013 | 0 | REPAIR WELDIING PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-014 | 0 | LONG TERM STORAGE PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-015 | 0 | HARDNESS TEST PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-WPQ-001 | 0 | WELDER / OPERATOR QUALIFICATION REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-WMP-001 | 0 | WELDING MAP | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-NPL-001 | 0 | NDT MAP | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-WPS-001 | 0 | WPS & PQR | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-001 | 0 | Material Test certificate | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-002 | 0 | NDT TEST REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-003 | 0 | HYDROSTATIC TEST REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-004 | 0 | BALANCE TEST REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-005 | 0 | PERFORMANCE TEST AND RUNNING TEST REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-006 | 0 | PAINTING INSPECTION RECORDS AND REPORT | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-007 | 0 | INSPECTION AND TEST REPORT FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-008 | 0 | INSPECTION AND TEST REPORT FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-009 | 0 | INSPECTION AND TEST REPORT FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-010 | 0 | INSPECTION AND TEST REPORT FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-011 | 0 | INSPECTION AND TEST REPORT FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-DWG-039 | 0 | MECHANICAL SEAL DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-040 | 0 | MECHANICAL SEAL DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-041 | 0 | MECHANICAL SEAL DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-042 | 0 | MECHANICAL SEAL DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-043 | 0 | MECHANICAL SEAL DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-044 | 0 | MECHANICAL SEAL DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-045 | 0 | MECHANICAL SEAL DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-046 | 0 | MECHANICAL SEAL DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-047 | 0 | MECHANICAL SEAL DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-048 | 0 | MECHANICAL SEAL DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-049 | 0 | MECHANICAL SEAL DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-050 | 0 | MECHANICAL SEAL DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-051 | 0 | MECHANICAL SEAL DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-RPT-012 | 0 | INSPECTION AND TEST REPORT FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-013 | 0 | INSPECTION AND TEST REPORT FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-014 | 0 | INSPECTION AND TEST REPORT FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-015 | 0 | INSPECTION AND TEST REPORT FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-016 | 0 | INSPECTION AND TEST REPORT FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-017 | 0 | INSPECTION AND TEST REPORT FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-018 | 0 | INSPECTION AND TEST REPORT FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-019 | 0 | INSPECTION AND TEST REPORT FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-020 | 0 | INSPECTION AND TEST REPORT FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-021 | 0 | INSPECTION AND TEST REPORT FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-022 | 0 | INSPECTION AND TEST REPORT FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-023 | 0 | INSPECTION AND TEST REPORT FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-RPT-024 | 0 | INSPECTION AND TEST REPORT FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-DWG-105 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:06 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-DWG-106 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:31 |  |  |  |  | 2020-06-14 20:02 | Yes | -4
VD-9001-307B-DWG-107 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:08 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-108 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:10 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-109 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:12 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-110 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:46 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:14 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-111 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:15 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-112 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:18 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-113 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:19 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-114 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:20 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-115 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:23 |  |  |  |  | 2020-06-14 20:01 | Yes | -4
VD-9001-307B-DWG-116 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:47 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:25 |  |  |  |  | 2020-06-14 20:02 | Yes | -4
VD-9001-307B-DWG-117 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:48 | 2020-06-04 01:49 | Yes | 20 |  |  |  | 2020-06-14 10:28 |  |  |  |  | 2020-06-14 20:02 | Yes | -4
VD-9001-307B-DWG-118 | 0 | ARC DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-119 | 0 | ARC DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-120 | 0 | ARC DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-121 | 0 | ARC DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-122 | 0 | ARC DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-123 | 0 | ARC DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-124 | 0 | ARC DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-125 | 0 | ARC DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-126 | 0 | PUMP NAME PLATE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:29 | 2020-05-09 08:31 | Yes | -13 |  |  |  | 2020-05-18 08:52 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-127 | 0 | PUMP NAME PLATE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:32 | 2020-05-09 08:32 | Yes | -13 |  |  |  | 2020-05-18 08:56 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-128 | 0 | PUMP NAME PLATE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:29 | 2020-05-09 08:32 | Yes | -13 |  |  |  | 2020-05-18 08:59 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-129 | 0 | PUMP NAME PLATE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:33 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:07 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-130 | 0 | PUMP NAME PLATE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:30 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:12 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-131 | 0 | PUMP NAME PLATE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:33 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:17 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-132 | 0 | PUMP NAME PLATE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:30 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:19 |  |  |  |  | 2020-05-18 20:58 | Yes | -5
VD-9001-307B-DWG-133 | 0 | PUMP NAME PLATE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:30 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:24 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-134 | 0 | PUMP NAME PLATE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:33 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:48 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-135 | 0 | PUMP NAME PLATE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:30 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:52 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-136 | 0 | PUMP NAME PLATE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:33 | Yes | -13 |  |  |  | 2020-05-18 09:56 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-137 | 0 | PUMP NAME PLATE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:34 | 2020-05-09 08:34 | Yes | -13 |  |  |  | 2020-05-18 10:02 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-138 | 0 | PUMP NAME PLATE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:34 | Yes | -13 |  |  |  | 2020-05-18 10:23 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-139 | 0 | PUMP NAME PLATE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:34 | Yes | -13 |  |  |  | 2020-05-18 10:26 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-140 | 0 | PUMP NAME PLATE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:34 | Yes | -13 |  |  |  | 2020-05-18 10:32 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-141 | 0 | PUMP NAME PLATE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:34 | Yes | -13 |  |  |  | 2020-05-18 10:35 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-142 | 0 | PUMP NAME PLATE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:35 | 2020-05-09 08:35 | Yes | -13 |  |  |  | 2020-05-18 10:43 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-143 | 0 | PUMP NAME PLATE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-22 | 2020-05-09 08:31 | 2020-05-09 08:35 | Yes | -13 |  |  |  | 2020-05-18 10:53 |  |  |  |  | 2020-05-18 20:59 | Yes | -5
VD-9001-307B-DWG-144 | 0 | MOTOR NAME PLATE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-145 | 0 | MOTOR NAME PLATE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-146 | 0 | MOTOR NAME PLATE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-147 | 0 | MOTOR NAME PLATE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-148 | 0 | MOTOR NAME PLATE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-149 | 0 | MOTOR NAME PLATE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-150 | 0 | MOTOR NAME PLATE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-151 | 0 | MOTOR NAME PLATE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-152 | 0 | MOTOR NAME PLATE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-153 | 0 | MOTOR NAME PLATE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-154 | 0 | MOTOR NAME PLATE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-155 | 0 | MOTOR NAME PLATE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-156 | 0 | MOTOR NAME PLATE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-157 | 0 | MOTOR NAME PLATE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-158 | 0 | MOTOR NAME PLATE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-159 | 0 | MOTOR NAME PLATE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-160 | 0 | MOTOR NAME PLATE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-161 | 0 | MOTOR NAME PLATE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DSH-001 | 0 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:07 | 2020-04-15 12:09 | Yes | 22 |  |  |  | 2020-05-16 08:12 |  |  |  |  | 2020-05-16 20:58 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:39
VD-9001-307B-DSH-002 | 0 | PUMP DATASHEET WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:07 | 2020-04-15 12:09 | Yes | 22 |  |  |  | 2020-05-16 10:24 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:39
VD-9001-307B-DSH-003 | 0 | PUMP DATASHEET WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:07 | 2020-04-15 12:10 | Yes | 22 |  |  |  | 2020-05-16 10:25 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:40
VD-9001-307B-DSH-004 | 0 | PUMP DATASHEET WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:07 | 2020-04-15 12:11 | Yes | 22 |  |  |  | 2020-05-16 10:26 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:40
VD-9001-307B-DSH-005 | 0 | PUMP DATASHEET WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:07 | 2020-04-15 12:11 | Yes | 22 |  |  |  | 2020-05-16 10:23 |  |  |  |  | 2020-05-16 20:58 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:41
VD-9001-307B-DSH-006 | 0 | PUMP DATASHEET WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:12 | 2020-04-15 12:12 | Yes | 22 |  |  |  | 2020-05-16 10:22 |  |  |  |  | 2020-05-16 20:58 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:41
VD-9001-307B-DSH-007 | 0 | PUMP DATASHEET WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:12 | Yes | 22 |  |  |  | 2020-05-16 12:46 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:42
VD-9001-307B-DSH-008 | 0 | PUMP DATASHEET WITH CURVE FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:12 | 2020-04-15 12:12 | Yes | 22 |  |  |  | 2020-05-16 12:44 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:42
VD-9001-307B-DSH-009 | 0 | PUMP DATASHEET WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:12 | Yes | 22 |  |  |  | 2020-06-06 09:53 |  |  |  |  | 2020-06-06 20:00 | Yes | 38 | 1204-Owner-v | 2020-04-27 08:43
VD-9001-307B-DSH-010 | 0 | PUMP DATASHEET WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:14 | Yes | 22 |  |  |  | 2020-05-16 13:35 |  |  |  |  | 2020-05-16 20:59 | Yes | 17 | 1204-Owner-v | 2020-04-27 08:43
VD-9001-307B-DSH-011 | 0 | PUMP DATASHEET WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:13 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 14:57 |  |  |  |  | 2020-05-17 20:59 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:43
VD-9001-307B-DSH-012 | 0 | PUMP DATASHEET WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:16 | Yes | 22 |  |  |  | 2020-05-17 15:36 |  |  |  |  | 2020-05-17 21:00 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:44
VD-9001-307B-DSH-013 | 0 | PUMP DATASHEET WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:14 | Yes | 22 |  |  |  | 2020-05-17 16:40 |  |  |  |  | 2020-05-17 21:01 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:45
VD-9001-307B-DSH-014 | 0 | PUMP DATASHEET WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 16:41 |  |  |  |  | 2020-05-17 21:01 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:45
VD-9001-307B-DSH-015 | 0 | PUMP DATASHEET WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:08 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 16:57 |  |  |  |  | 2020-05-17 21:01 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:46
VD-9001-307B-DSH-016 | 0 | PUMP DATASHEET WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:09 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 17:04 |  |  |  |  | 2020-05-17 21:02 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:46
VD-9001-307B-DSH-017 | 0 | PUMP DATASHEET WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:09 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 17:16 |  |  |  |  | 2020-05-17 21:02 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:46
VD-9001-307B-DSH-018 | 0 | PUMP DATASHEET WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-03-24 | 2020-04-15 12:09 | 2020-04-15 12:15 | Yes | 22 |  |  |  | 2020-05-17 17:24 |  |  |  |  | 2020-05-17 21:02 | Yes | 18 | 1204-Owner-v | 2020-04-27 08:47
VD-9001-307B-DSH-019 | 0 | MOTOR DATASHEET WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:58 | 2020-05-02 08:00 | Yes | -13 |  |  |  | 2020-05-14 10:45 |  |  |  |  | 2020-05-14 20:59 | Yes | -2 | 1204-Owner-v | 2020-05-31 13:50
VD-9001-307B-DSH-020 | 0 | MOTOR DATASHEET WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:58 | 2020-05-02 08:00 | Yes | -13 |  |  |  | 2020-05-14 10:45 |  |  |  |  | 2020-05-14 20:59 | Yes | -2
VD-9001-307B-DSH-021 | 0 | MOTOR DATASHEET WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:01 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:02 |  |  |  |  | 2020-05-14 20:59 | Yes | -2
VD-9001-307B-DSH-022 | 0 | MOTOR DATASHEET WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:01 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:06 |  |  |  |  | 2020-05-14 20:59 | Yes | -2
VD-9001-307B-DSH-023 | 0 | MOTOR DATASHEET WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:10 |  |  |  |  | 2020-05-14 21:00 | Yes | -2
VD-9001-307B-DSH-024 | 0 | MOTOR DATASHEET WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:16 |  |  |  |  | 2020-05-14 21:00 | Yes | -2
VD-9001-307B-DSH-025 | 0 | MOTOR DATASHEET WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:24 |  |  |  |  | 2020-05-14 21:00 | Yes | -2
VD-9001-307B-DSH-026 | 0 | MOTOR DATASHEET WITH CURVE FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:01 | Yes | -13 |  |  |  | 2020-05-14 11:27 |  |  |  |  | 2020-05-14 21:00 | Yes | -2
VD-9001-307B-DSH-027 | 0 | MOTOR DATASHEET WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:02 | 2020-05-02 08:02 | Yes | -13 |  |  |  | 2020-05-14 11:32 |  |  |  |  | 2020-05-14 21:01 | Yes | -2
VD-9001-307B-DSH-028 | 0 | MOTOR DATASHEET WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:02 | 2020-05-02 08:02 | Yes | -13 |  |  |  | 2020-05-17 14:35 |  |  |  |  | 2020-05-17 20:59 | Yes | 1
VD-9001-307B-DSH-029 | 0 | MOTOR DATASHEET WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:02 | Yes | -13 |  |  |  | 2020-05-14 19:31 |  |  |  |  | 2020-05-14 21:01 | Yes | -2
VD-9001-307B-DSH-030 | 0 | MOTOR DATASHEET WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:02 | 2020-05-02 08:04 | Yes | -13 |  |  |  | 2020-05-14 19:38 |  |  |  |  | 2020-05-14 21:02 | Yes | -2
VD-9001-307B-DSH-031 | 0 | MOTOR DATASHEET WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 07:59 | 2020-05-02 08:02 | Yes | -13 |  |  |  | 2020-05-14 19:35 |  |  |  |  | 2020-05-14 21:02 | Yes | -2
VD-9001-307B-DSH-032 | 0 | MOTOR DATASHEET WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:02 | 2020-05-02 08:05 | Yes | -13 |  |  |  | 2020-05-14 19:43 |  |  |  |  | 2020-05-14 21:02 | Yes | -2
VD-9001-307B-DSH-033 | 0 | MOTOR DATASHEET WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:03 | 2020-05-02 08:03 | Yes | -13 |  |  |  | 2020-05-14 19:46 |  |  |  |  | 2020-05-14 21:03 | Yes | -2
VD-9001-307B-DSH-034 | 0 | MOTOR DATASHEET WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:03 | 2020-05-02 08:03 | Yes | -13 |  |  |  | 2020-05-14 19:49 |  |  |  |  | 2020-05-14 21:03 | Yes | -2
VD-9001-307B-DSH-035 | 0 | MOTOR DATASHEET WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:00 | 2020-05-02 08:03 | Yes | -13 |  |  |  | 2020-05-14 19:53 |  |  |  |  | 2020-05-14 21:03 | Yes | -2
VD-9001-307B-DSH-036 | 0 | MOTOR DATASHEET WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-02 08:03 | 2020-05-02 08:04 | Yes | -13 |  |  |  | 2020-05-14 19:55 |  |  |  |  | 2020-05-14 21:04 | Yes | -2
VD-9001-307B-DSH-037 | 0 | MECHANICAL SEAL DATASHEET FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-038 | 0 | MECHANICAL SEAL DATASHEET FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-039 | 0 | MECHANICAL SEAL DATASHEET FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-040 | 0 | MECHANICAL SEAL DATASHEET FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-041 | 0 | MECHANICAL SEAL DATASHEET FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-042 | 0 | MECHANICAL SEAL DATASHEET FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-043 | 0 | MECHANICAL SEAL DATASHEET FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-044 | 0 | MECHANICAL SEAL DATASHEET FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-045 | 0 | MECHANICAL SEAL DATASHEET FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-046 | 0 | MECHANICAL SEAL DATASHEET FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-047 | 0 | MECHANICAL SEAL DATASHEET FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-048 | 0 | MECHANICAL SEAL DATASHEET FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-049 | 0 | MECHANICAL SEAL DATASHEET FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-050 | 0 | MECHANICAL SEAL DATASHEET FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-051 | 0 | MECHANICAL SEAL DATASHEET FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-052 | 0 | MECHANICAL SEAL DATASHEET FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-053 | 0 | MECHANICAL SEAL DATASHEET FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DSH-054 | 0 | ARC DATASHEET FOR CRUDE METHANOL TRANSFER PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-055 | 0 | ARC DATASHEET FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-056 | 0 | ARC DATASHEET FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-057 | 0 | ARC DATASHEET FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-058 | 0 | ARC DATASHEET FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-059 | 0 | ARC DATASHEET FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-060 | 0 | ARC DATASHEET FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-061 | 0 | ARC DATASHEET FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-062 | 0 | NOISE DATASHEET FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-063 | 0 | NOISE DATASHEET FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-064 | 0 | NOISE DATASHEET FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-065 | 0 | NOISE DATASHEET FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-066 | 0 | NOISE DATASHEET FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-067 | 0 | NOISE DATASHEET FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-068 | 0 | NOISE DATASHEET FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-069 | 0 | NOISE DATASHEET FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-070 | 0 | NOISE DATASHEET FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-MNL-018 | 0 | Pump IOM FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-028 | 0 | Motor Installation Operation & Maintenance Manuals | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-029 | 0 | coupling Installation Operation & Maintenance Manuals | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-030 | 0 | MECHANICAL SEAL Installation Operation & Maintenance Manuals | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-CAT-001 | 0 | PUMP CATALOGUE | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-CAT-002 | 0 | MOTOR CATALOGUE | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-CAT-003 | 0 | MECHANICAL SEAL CATALOGUE | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-CAT-005 | 0 | COUPLING CATALOGUE | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-INX-001 | 0 | FINAL BOOK INDEX | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MDB-001 | 0 | FINAL BOOK | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-002 | 0 | Pump IOM FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-003 | 0 | Pump IOM FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-004 | 0 | Pump IOM FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-005 | 0 | Pump IOM FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-006 | 0 | Pump IOM FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-007 | 0 | Pump IOM FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-008 | 0 | Pump IOM FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-009 | 0 | Pump IOM FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-010 | 0 | Pump IOM FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-011 | 0 | Pump IOM FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-012 | 0 | Pump IOM FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-013 | 0 | Pump IOM FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-PCJ-010 | 0 | HEAT TRETMENT PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-MNL-014 | 0 | Pump IOM FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-015 | 0 | Pump IOM FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-016 | 0 | Pump IOM FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-MNL-017 | 0 | Pump IOM FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-DWG-052 | 0 | MECHANICAL SEAL DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-053 | 0 | MECHANICAL SEAL DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-054 | 0 | SEAL SYSTEM DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-055 | 0 | SEAL SYSTEM DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-056 | 0 | SEAL SYSTEM DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-057 | 0 | SEAL SYSTEM DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-058 | 0 | SEAL SYSTEM DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-059 | 0 | SEAL SYSTEM DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-060 | 0 | SEAL SYSTEM DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-061 | 0 | SEAL SYSTEM DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-062 | 0 | SEAL SYSTEM DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-063 | 0 | SEAL SYSTEM DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-064 | 0 | COUPLING DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-065 | 0 | COUPLING DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-066 | 0 | COUPLING DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-067 | 0 | COUPLING DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-068 | 0 | COUPLING DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-069 | 0 | COUPLING DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-070 | 0 | COUPLING DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-071 | 0 | COUPLING DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-072 | 0 | COUPLING DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-073 | 0 | COUPLING DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-074 | 0 | COUPLING DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-075 | 0 | COUPLING DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-076 | 0 | COUPLING DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-077 | 0 | COUPLING DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-078 | 0 | COUPLING DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-079 | 0 | COUPLING DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-080 | 0 | COUPLING DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-081 | 0 | COUPLING DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-DWG-082 | 0 | MOTOR OUTLINE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:36 | 2020-04-15 13:36 | Yes | -23 |  |  |  | 2020-05-04 11:16 |  |  |  |  | 2020-05-04 20:58 | Yes | 5 | 1204-Owner-v | 2020-04-23 18:09
VD-9001-307B-DWG-083 | 0 | MOTOR OUTLINE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:33 | 2020-04-15 13:36 | Yes | -23 |  |  |  | 2020-05-04 11:17 |  |  |  |  | 2020-05-04 20:58 | Yes | 5
VD-9001-307B-DWG-084 | 0 | MOTOR OUTLINE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:36 | Yes | -23 |  |  |  | 2020-05-04 11:17 |  |  |  |  | 2020-05-04 20:59 | Yes | 5
VD-9001-307B-DWG-085 | 0 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:36 | Yes | -23 |  |  |  | 2020-05-04 11:18 |  |  |  |  | 2020-05-04 20:59 | Yes | 5
VD-9001-307B-DWG-086 | 0 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:36 | Yes | -23 |  |  |  | 2020-05-04 11:19 |  |  |  |  | 2020-05-04 20:59 | Yes | 5
VD-9001-307B-DWG-087 | 0 | MOTOR OUTLINE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:19 |  |  |  |  | 2020-05-04 20:59 | Yes | 5
VD-9001-307B-DWG-088 | 0 | MOTOR OUTLINE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:20 |  |  |  |  | 2020-05-04 21:00 | Yes | 5
VD-9001-307B-DWG-089 | 0 | MOTOR OUTLINE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:37 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:20 |  |  |  |  | 2020-05-04 21:00 | Yes | 5
VD-9001-307B-DWG-090 | 0 | MOTOR OUTLINE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:20 |  |  |  |  | 2020-05-04 21:00 | Yes | 5
VD-9001-307B-DWG-091 | 0 | MOTOR OUTLINE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:21 |  |  |  |  | 2020-05-04 21:00 | Yes | 5
VD-9001-307B-DWG-092 | 0 | MOTOR OUTLINE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:21 |  |  |  |  | 2020-05-04 21:00 | Yes | 5
VD-9001-307B-DWG-093 | 0 | MOTOR OUTLINE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:34 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:22 |  |  |  |  | 2020-05-04 21:01 | Yes | 5
VD-9001-307B-DWG-094 | 0 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:37 | Yes | -23 |  |  |  | 2020-05-04 11:23 |  |  |  |  | 2020-05-04 21:01 | Yes | 5
VD-9001-307B-DWG-095 | 0 | MOTOR OUTLINE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:38 | Yes | -23 |  |  |  | 2020-05-04 11:23 |  |  |  |  | 2020-05-04 21:01 | Yes | 5
VD-9001-307B-DWG-096 | 0 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:38 | Yes | -23 |  |  |  | 2020-05-04 11:24 |  |  |  |  | 2020-05-04 21:01 | Yes | 5
VD-9001-307B-DWG-097 | 0 | MOTOR OUTLINE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:38 | Yes | -23 |  |  |  | 2020-05-04 11:24 |  |  |  |  | 2020-05-04 21:01 | Yes | 5
VD-9001-307B-DWG-098 | 0 | MOTOR OUTLINE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:38 | Yes | -23 |  |  |  | 2020-05-04 11:25 |  |  |  |  | 2020-05-04 21:02 | Yes | 5
VD-9001-307B-DWG-099 | 0 | MOTOR OUTLINE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-15 13:35 | 2020-04-15 13:39 | Yes | -23 |  |  |  | 2020-05-04 11:25 |  |  |  |  | 2020-05-04 21:02 | Yes | 5
VD-9001-307B-DWG-100 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:45 | 2020-06-04 01:47 | Yes | 20 |  |  |  | 2020-06-14 09:47 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-DWG-101 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:45 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 09:51 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-DWG-102 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:45 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 09:52 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-DWG-103 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:45 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:00 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-DWG-104 | 0 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-06-04 01:45 | 2020-06-04 01:48 | Yes | 20 |  |  |  | 2020-06-14 10:03 |  |  |  |  | 2020-06-14 20:00 | Yes | -4
VD-9001-307B-MNL-001 | 0 | Pump IOM FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2021-06-30 |  |  | No | -376 | [9 empty] | No | 0
VD-9001-307B-RPT-025 | 0 | Motor EX/IP Certificate | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PID-018 | 0 | PUMP P&I DRAWING WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:14 | 2020-04-27 08:14 | Yes | -11 |  |  |  | 2020-06-07 08:41 |  |  |  |  | 2020-06-07 20:00 | Yes | 27
VD-9001-307B-LST-001 | 0 | Instrument List | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-LST-002 | 0 | List of alarms and trips with set point | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-LST-003 | 0 | Lubricant List | MC-307B | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307B-LST-004 | 0 | Electric Load List (Include all Electric consumption) | MC-307B | Deep Blue Pump Co. | 2020-06-12 |  |  | No | 7 | [9 empty] | No | 0
VD-9001-307B-LST-005 | 0 | SUB-VENDOR LIST | MC-307B | Deep Blue Pump Co. | 2020-04-24 | 2020-04-16 07:39 | 2020-04-16 07:39 | Yes | -8 |  |  |  | 2020-05-20 07:43 |  |  |  |  | 2020-05-20 20:58 | Yes | 20
VD-9001-307B-LST-006 | 0 | UTILITY CONSUMPTION LIST | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-LST-007 | 0 | Detailed Packing List | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-LST-008 | 0 | Spare Part List | MC-307B | Deep Blue Pump Co. | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-307B-PCJ-001 | 0 | FACTORY PERFORMANCE TEST PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 | 2020-04-29 10:05 | 2020-04-29 10:05 | Yes | -27 |  |  |  | 2020-05-09 16:42 |  |  |  |  | 2020-05-09 21:02 | Yes | -4
VD-9001-307B-PCJ-002 | 0 | HYDROTATIC TEST PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-003 | 0 | PACKING AND DELIVERY PROCEDURE(WOODEN CASE) | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-004 | 0 | PACKING AND DELIVERY PROCEDURE(STEEEL STRUCTURE) | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-005 | 0 | SURFACE PREPARATION AND PAINTING PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 | 2020-04-20 08:06 | 2020-04-20 08:06 | Yes | -36 |  |  |  | 2020-05-06 07:49 |  |  |  |  | 2020-05-06 20:58 | Yes | 2
VD-9001-307B-PCJ-006 | 0 | BALANCING TEST PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-007 | 0 | LIQUID PENETRANT EXAMINATION PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-008 | 0 | ULTRASONIC EXAMINATION PROCEDURE-FORGING&BAR | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-PCJ-009 | 0 | PWHT PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-DSH-071 | 0 | NOISE DATASHEET FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-072 | 0 | NOISE DATASHEET FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-073 | 0 | NOISE DATASHEET FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-074 | 0 | NOISE DATASHEET FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-075 | 0 | NOISE DATASHEET FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-076 | 0 | NOISE DATASHEET FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-077 | 0 | NOISE DATASHEET FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-078 | 0 | NOISE DATASHEET FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-079 | 0 | NOISE DATASHEET FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-DSH-080 | 0 | INSTRUMENT DATASHEET FOR SEAL SYSTEM FOR ALL ITEMS | MC-307B | Deep Blue Pump Co. | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-307B-PID-001 | 0 | PUMP P&I DRAWING WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:09 | 2020-04-27 08:09 | Yes | -11 |  |  |  | 2020-05-19 15:48 |  |  |  |  | 2020-05-19 21:00 | Yes | 8
VD-9001-307B-PID-002 | 0 | PUMP P&I DRAWING WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:10 | 2020-04-27 08:10 | Yes | -11 |  |  |  | 2020-05-19 16:43 |  |  |  |  | 2020-05-19 21:01 | Yes | 8
VD-9001-307B-PID-003 | 0 | PUMP P&I DRAWING WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:10 | 2020-04-27 08:10 | Yes | -11 |  |  |  | 2020-05-19 18:05 |  |  |  |  | 2020-05-19 21:01 | Yes | 8
VD-9001-307B-PID-004 | 0 | PUMP P&I DRAWING WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:10 | 2020-04-27 08:10 | Yes | -11 |  |  |  | 2020-06-06 12:22 |  |  |  |  | 2020-06-06 20:02 | Yes | 26
VD-9001-307B-PID-005 | 0 | PUMP P&I DRAWING WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:10 | 2020-04-27 08:11 | Yes | -11 |  |  |  | 2020-06-06 13:58 |  |  |  |  | 2020-06-06 20:03 | Yes | 26
VD-9001-307B-PID-006 | 0 | PUMP P&I DRAWING WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:11 | 2020-04-27 08:11 | Yes | -11 |  |  |  | 2020-06-06 13:38 |  |  |  |  | 2020-06-06 20:03 | Yes | 26
VD-9001-307B-PID-007 | 0 | PUMP P&I DRAWING WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:11 | 2020-04-27 08:11 | Yes | -11 |  |  |  | 2020-06-06 13:33 |  |  |  |  | 2020-06-06 20:02 | Yes | 26
VD-9001-307B-PID-008 | 0 | PUMP P&I DRAWING WITH CURVE FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 |  |  | No | 42 | [9 empty] | No | 0
VD-9001-307B-PID-009 | 0 | PUMP P&I DRAWING WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:11 | 2020-04-27 08:11 | Yes | -11 |  |  |  | 2020-06-06 14:45 |  |  |  |  | 2020-06-06 20:03 | Yes | 26
VD-9001-307B-PID-010 | 0 | PUMP P&I DRAWING WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:11 | 2020-04-27 08:11 | Yes | -11 |  |  |  | 2020-06-06 10:34 |  |  |  |  | 2020-06-06 20:01 | Yes | 26
VD-9001-307B-PID-011 | 0 | PUMP P&I DRAWING WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:12 | 2020-04-27 08:12 | Yes | -11 |  |  |  | 2020-05-23 17:18 |  |  |  |  | 2020-05-23 21:00 | Yes | 12
VD-9001-307B-PID-012 | 0 | PUMP P&I DRAWING WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:12 | 2020-04-27 08:12 | Yes | -11 |  |  |  | 2020-05-23 16:03 |  |  |  |  | 2020-05-23 20:58 | Yes | 12
VD-9001-307B-PID-013 | 0 | PUMP P&I DRAWING WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:12 | 2020-04-27 08:12 | Yes | -11 |  |  |  | 2020-05-23 16:56 |  |  |  |  | 2020-05-23 20:59 | Yes | 12
VD-9001-307B-PID-014 | 0 | PUMP P&I DRAWING WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:13 | 2020-04-27 08:13 | Yes | -11 |  |  |  | 2020-05-23 17:05 |  |  |  |  | 2020-05-23 20:59 | Yes | 12
VD-9001-307B-PID-015 | 0 | PUMP P&I DRAWING WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:13 | 2020-04-27 08:13 | Yes | -11 |  |  |  | 2020-06-07 08:55 |  |  |  |  | 2020-06-07 20:00 | Yes | 27
VD-9001-307B-PID-016 | 0 | PUMP P&I DRAWING WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:13 | 2020-04-27 08:13 | Yes | -11 |  |  |  | 2020-05-23 16:40 |  |  |  |  | 2020-05-23 20:59 | Yes | 12
VD-9001-307B-PID-017 | 0 | PUMP P&I DRAWING WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-27 08:13 | 2020-04-27 08:13 | Yes | -11 |  |  |  | 2020-06-07 08:29 |  |  |  |  | 2020-06-07 20:00 | Yes | 27
VD-9001-307B-PCJ-011 | 0 | MATERIAL TRACEABILITY & IDENTIFICATION PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307B-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | MC-307B | Deep Blue Pump Co. | 2020-03-13 |  |  | No | 98 | [9 empty] | No | 0
VD-9001-307B-ITP-001 | 0 | PUMP TEST & INSPECTION PLAN | MC-307B | Deep Blue Pump Co. | 2020-04-24 | 2020-04-29 07:30 | 2020-04-29 07:30 | Yes | 5 |  |  |  | 2020-05-09 16:28 |  |  |  |  | 2020-05-09 21:02 | Yes | -4
VD-9001-307B-ITP-002 | 0 | ELECTRICAL MOTORS TEST & INSPECTION PLAN | MC-307B | Deep Blue Pump Co. | 2020-05-15 | 2020-05-09 08:20 | 2020-05-09 08:20 | Yes | -6 |  |  |  | 2020-06-08 09:05 |  |  |  |  | 2020-06-08 20:00 | Yes | 16
VD-9001-307B-ORC-001 | 0 | ORGANIZATION CHART | MC-307B | Deep Blue Pump Co. | 2020-05-08 |  |  | No | 42 | [9 empty] | No | 0
VD-9001-307B-DWG-001 | 0 | GA DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:21 | 2020-04-23 10:21 | Yes | -15 |  |  |  |  | 2020-06-13 09:07 |  |  |  | 2020-06-13 20:00 | Yes | 37 | 1204-Owner-v | 2020-04-23 18:06
VD-9001-307B-DWG-002 | 0 | GA DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:21 | 2020-04-23 10:21 | Yes | -15 |  |  |  | 2020-06-13 09:31 |  |  |  |  | 2020-06-13 20:00 | Yes | 37 | 1204-Owner-v | 2020-04-23 18:06
VD-9001-307B-DWG-003 | 0 | GA DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:22 | 2020-04-23 10:22 | Yes | -15 |  |  |  | 2020-06-13 10:32 |  |  |  |  | 2020-06-13 20:01 | Yes | 37 | 1204-Owner-v | 2020-04-23 18:06
VD-9001-307B-DWG-004 | 0 | GA DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:23 | 2020-04-23 10:23 | Yes | -15 |  |  |  | 2020-06-11 09:45 |  |  |  |  | 2020-06-11 20:00 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:07
VD-9001-307B-DWG-005 | 0 | GA DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:23 | 2020-04-23 10:23 | Yes | -15 |  |  |  | 2020-06-11 11:19 |  |  |  |  | 2020-06-11 20:01 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:07
VD-9001-307B-DWG-006 | 0 | GA DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:23 | 2020-04-23 10:23 | Yes | -15 |  |  |  |  | 2020-06-11 11:20 |  |  |  | 2020-06-11 20:01 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:07
VD-9001-307B-DWG-007 | 0 | GA DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:23 | 2020-04-23 10:24 | Yes | -15 |  |  |  | 2020-06-11 11:21 |  |  |  |  | 2020-06-11 20:01 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:07
VD-9001-307B-DWG-008 | 0 | GA DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 |  |  | No | 42 | [9 empty] | No | 0
VD-9001-307B-DWG-009 | 0 | GA DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:24 | 2020-04-23 10:24 | Yes | -15 |  |  |  | 2020-06-13 12:04 |  |  |  |  | 2020-06-13 20:02 | Yes | 37 | 1204-Owner-v | 2020-04-23 18:07
VD-9001-307B-DWG-010 | 0 | GA DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:27 | 2020-04-23 10:30 | Yes | -15 |  |  |  | 2020-06-11 13:58 |  |  |  |  | 2020-06-11 20:02 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-011 | 0 | GA DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:25 | 2020-04-23 10:27 | Yes | -15 |  |  |  | 2020-06-10 09:47 |  |  |  |  | 2020-06-10 20:00 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-012 | 0 | GA DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:27 | Yes | -15 |  |  |  | 2020-06-10 09:51 |  |  |  |  | 2020-06-10 20:00 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-013 | 0 | GA DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:27 | Yes | -15 |  |  |  | 2020-06-10 10:30 |  |  |  |  | 2020-06-10 20:00 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-014 | 0 | GA DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:28 | 2020-04-23 10:28 | Yes | -15 |  |  |  | 2020-06-10 12:52 |  |  |  |  | 2020-06-10 20:00 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-015 | 0 | GA DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:28 | Yes | -15 |  |  |  | 2020-06-10 12:54 |  |  |  |  | 2020-06-10 20:00 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-016 | 0 | GA DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:28 | Yes | -15 |  |  |  | 2020-06-10 12:56 |  |  |  |  | 2020-06-10 20:01 | Yes | 34 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-017 | 0 | GA DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:28 | Yes | -15 |  |  |  | 2020-06-11 11:38 |  |  |  |  | 2020-06-11 20:01 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-018 | 0 | GA DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-08 | 2020-04-23 10:26 | 2020-04-23 10:28 | Yes | -15 |  |  |  | 2020-06-11 12:10 |  |  |  |  | 2020-06-11 20:02 | Yes | 35 | 1204-Owner-v | 2020-04-23 18:08
VD-9001-307B-DWG-019 | 0 | PUMP CROSS SECTION DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-020 | 0 | PUMP CROSS SECTION DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-021 | 0 | PUMP CROSS SECTION DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-022 | 0 | PUMP CROSS SECTION DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-023 | 0 | PUMP CROSS SECTION DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-024 | 0 | PUMP CROSS SECTION DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-025 | 0 | PUMP CROSS SECTION DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-026 | 0 | PUMP CROSS SECTION DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-027 | 0 | PUMP CROSS SECTION DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-028 | 0 | PUMP CROSS SECTION DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-029 | 0 | PUMP CROSS SECTION DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-030 | 0 | PUMP CROSS SECTION DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-031 | 0 | PUMP CROSS SECTION DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-032 | 0 | PUMP CROSS SECTION DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-033 | 0 | PUMP CROSS SECTION DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-034 | 0 | PUMP CROSS SECTION DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-035 | 0 | PUMP CROSS SECTION DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-036 | 0 | PUMP CROSS SECTION DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307B-DWG-037 | 0 | MECHANICAL SEAL DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-307B-DWG-038 | 0 | MECHANICAL SEAL DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-254-DIG-320 | 7 | OUTLINE DRAWING & WIRING DIAGRAMS FOR LBSP | HM-254 | AZAR AB | 2020-04-20 | 2020-06-14 11:43 | 2020-06-14 11:43 | Yes | 55 | [9 empty] | No | -9
VD-9001-201B-PCJ-003 | 1 | NITROGEN PURGING (4134/N) | PV-201B | Brembana & Rolle S.p.A. | 2020-05-02 20:59 | 2020-05-11 16:28 | 2020-05-11 16:28 | Yes | 9 |  |  | 2020-05-19 08:39 | [5 empty] | 2020-05-19 08:39 | Yes | -6
VD-9001-307A1-PCJ-012 | 1 | PWHT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-02 | 2020-04-25 08:27 | 2020-04-25 08:28 | Yes | -7 |  |  |  | 2020-05-27 11:12 |  |  |  |  | 2020-05-27 11:12 | Yes | 18
VD-9001-307A1-PCJ-013 | 1 | HEAT TREATMENT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-02 | 2020-04-25 08:29 | 2020-04-25 08:29 | Yes | -7 |  |  | 2020-05-02 18:55 | [5 empty] | 2020-05-02 18:55 | Yes | -7
VD-9001-251B-RPT-020 | 1 | Reports for "RADIANT SECTION" | HM-251B | Bamdad Zendehroud Co. | 2020-04-21 | 2020-04-20 15:26 | 2020-04-20 15:26 | Yes | -1 |  |  | 2020-05-10 09:27 | [5 empty] | 2020-05-10 09:27 | Yes | 6 | 1204-Owner-v | 2020-05-18 18:47
VD-9001-251E-ITP-005 | 1 | Inspection & Test Plan (ITP) | HM-251E | Iran Industrial Vibrations Co. | 2020-04-21 | 2020-05-09 15:06 | 2020-05-09 15:44 | Yes | 18 |  |  | 2020-05-16 11:14 | [5 empty] | 2020-05-16 11:14 | Yes | -7
VD-9001-260-DSH-001 | 1 | Process Data Sheet E-1007 | HM-260 | ABAN AIR COOLER. | 2020-04-26 | 2020-04-27 16:21 | 2020-04-27 16:21 | Yes | 1 |  |  |  |  | 2020-05-03 16:27 |  |  |  | 2020-05-03 16:27 | Yes | -8 | 1204-Owner-v | 2020-06-01 10:38
VD-9001-260-DSH-002 | 1 | Process Data Sheet E-1010 | HM-260 | ABAN AIR COOLER. | 2020-04-26 | 2020-04-27 16:22 | 2020-04-27 16:23 | Yes | 1 |  |  | 2020-05-03 16:32 | [5 empty] | 2020-05-03 16:32 | Yes | -8 | 1204-Owner-v | 2020-06-01 10:41
VD-9001-260-DSH-003 | 1 | Process Data Sheet E-3008 | HM-260 | ABAN AIR COOLER. | 2020-04-26 | 2020-04-27 16:24 | 2020-04-27 16:25 | Yes | 1 |  |  |  |  | 2020-05-03 16:36 |  |  |  | 2020-05-03 16:36 | Yes | -8
VD-9001-251E-PCJ-009 | 1 | Painting Procedure | HM-251E | Iran Industrial Vibrations Co. | 2020-04-21 |  |  | No | 59 | [9 empty] | No | 0
VD-9001-260-DSH-004 | 1 | Process Data Sheet E-3009 | HM-260 | ABAN AIR COOLER. | 2020-04-26 | 2020-04-27 16:25 | 2020-04-27 16:26 | Yes | 1 |  |  |  |  | 2020-05-03 16:40 |  |  |  | 2020-05-03 16:40 | Yes | -8
VD-9001-260-DSH-005 | 1 | Process Data Sheet E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-04-26 | 2020-04-27 16:27 | 2020-04-27 16:28 | Yes | 1 |  |  |  |  | 2020-05-03 17:04 |  |  |  | 2020-05-03 17:04 | Yes | -8
VD-9001-307A1-DSH-001 | 3 | PUMP DATASHEET WITH CURVE FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-04-28 13:51 | 2020-04-28 13:52 | Yes | 1 |  |  |  | 2020-05-09 12:39 |  |  |  |  | 2020-05-09 12:39 | Yes | -3 | 1204-Owner-v | 2020-04-29 13:41
VD-9001-307A1-DSH-002 | 3 | PUMP DATASHEET WITH CURVE FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-04-28 13:51 | 2020-04-28 13:52 | Yes | 1 |  |  |  | 2020-05-09 12:40 |  |  |  |  | 2020-05-09 12:40 | Yes | -3 | 1204-Owner-v | 2020-04-29 13:42
VD-9001-307A1-DSH-003 | 3 | PUMP DATASHEET WITH CURVE FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-04-28 13:51 | 2020-04-28 13:52 | Yes | 1 |  |  | 2020-05-09 12:41 | [5 empty] | 2020-05-09 12:41 | Yes | -3 | 1204-Owner-v | 2020-04-29 13:42
VD-9001-307A1-DSH-004 | 3 | PUMP DATASHEET WITH CURVE FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-04-28 13:51 | 2020-04-28 13:53 | Yes | 1 |  |  |  | 2020-05-09 12:43 |  |  |  |  | 2020-05-09 12:43 | Yes | -3 | 1204-Owner-v | 2020-04-29 13:43
VD-9001-307A1-DSH-005 | 3 | PUMP DATASHEET WITH CURVE FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-04-28 13:53 | 2020-04-28 13:53 | Yes | 1 |  |  | 2020-05-10 17:39 | [5 empty] | 2020-05-10 17:39 | Yes | -2 | 1204-Owner-v | 2020-04-29 13:43
VD-9001-307A1-DWG-049 | 1 | MOTOR OUTLINE DRAWING FOR PM4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-04-27 | 2020-06-04 12:33 | 2020-06-04 12:34 | Yes | 38 | [9 empty] | No | 1
VD-9001-201B-CAL-001 | 2 | MECHANICAL CALCULATION (4134-0359/MC) | PV-201B | Brembana & Rolle S.p.A. | 2020-05-04 20:58 | 2020-05-11 16:24 | 2020-05-11 16:26 | Yes | 7 |  |  |  | 2020-05-21 13:46 |  |  |  |  | 2020-05-21 21:01 | Yes | -4
VD-9001-213B1-DWG-010 | 0 | Shell Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-04-22 | 2020-04-26 08:47 | 2020-04-26 08:47 | Yes | 4 |  |  |  |  | 2020-05-02 12:22 |  | 2020-04-26 08:23 | 2020-04-26 08:23 | 2020-05-02 20:58 | Yes | -8
VD-9001-213B1-DWG-011 | 0 | Bottom Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-04-22 | 2020-04-21 15:06 | 2020-04-21 15:07 | Yes | -1 |  |  |  |  | 2020-05-04 11:25 |  |  |  | 2020-05-04 21:02 | Yes | -1 | 1204-Owner-v | 2020-04-28 13:19
VD-9001-213B1-DWG-012 | 0 | Fixed Roof Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-04-22 | 2020-04-26 08:50 | 2020-04-26 08:50 | Yes | 4 |  |  |  |  | 2020-05-06 12:16 |  | 2020-04-26 08:22 | 2020-04-26 08:22 | 2020-05-06 20:59 | Yes | -4 | 1204-Owner-v | 2020-05-03 13:05
VD-9001-213B1-DWG-015 | 0 | Wind Girder for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-04-22 | 2020-04-25 09:17 | 2020-04-25 09:17 | Yes | 3 |  |  | 2020-05-06 12:17 | [5 empty] | 2020-05-06 20:59 | Yes | -3 | 1204-Owner-v | 2020-06-03 09:34
VD-9001-307A1-LST-028 | 1 | SUB-VENDOR LIST | MC-307A1 | Deep Blue Pump Co. | 2020-04-28 | 2020-04-28 13:52 | 2020-04-28 13:53 | Yes | 0 |  |  | 2020-05-06 14:58 | [5 empty] | 2020-05-06 14:58 | Yes | -6 | 1204-Owner-v | 2020-05-11 19:59
VD-9001-740C-ITP-271 | 2 | inspection and test plan (ITP) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-29 | 2020-04-25 08:40 | 2020-04-25 08:41 | Yes | -4 |  |  |  | 2020-05-03 18:27 |  |  |  |  | 2020-05-03 21:03 | Yes | -6 | 1204-Owner-v | 2020-04-25 09:17
VD-9001-201A-PCJ-076 | 3 | PRODUCTION TEST PLATE (PTP) PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2020-04-30 | 2020-05-04 09:19 | 2020-05-04 09:19 | Yes | 4 |  |  | 2020-05-12 14:48 | [5 empty] | 2020-05-12 14:48 | Yes | -6
VD-9001-301-1-DWG-212 | 0 | Syn Gas Compressor (C-2001) Thrust & Radial Bearing Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-213 | 0 | Syn Gas Steam Turbine (STC-2001) Gov. & Exh. Side Bearing Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-214 | 0 | Syn Gas Compressor (C-2001) Rotor Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-215 | 0 | Syn Gas Steam Turbine (STC-2001) Rotor Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-216 | 0 | Common Oil Cooler (C-2001) Drawing | MC-301-1 | NEW JCM | 2020-05-11 |  |  | No | 39 | [9 empty] | No | 0
VD-9001-301-1-DWG-217 | 0 | Common Oil Filter (C-2001) Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:50 | 2020-06-09 12:51 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DWG-218 | 0 | Common Oil Heater (C-2001) Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:39 | 2020-06-09 12:50 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DWG-219 | 0 | Syn Gas (C-2001) Seal Panel Drawing | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-DWG-220 | 0 | Syn Gas (C-2001) Lifting Arrangemnt Drawing | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-201 | 0 | Syn Gas Steam Turbine Blade Campbell/ Goodman Diagram | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-202 | 0 | Syn Gas (C-2001) Alignment Data | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-203 | 0 | Syn Gas Turbine (STC-2001) Start Up Diagram | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-PPL-201 | 0 | Syn Gas (C-2001) General Arrangement & Foundation Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:44 | 2020-04-26 08:50 | Yes | 25 |  |  |  | 2020-05-14 11:42 |  |  |  |  | 2020-05-14 11:42 | Yes | 4 | 1204-Owner-v | 2020-06-02 13:39
VD-9001-301-1-PPL-202 | 0 | General Arrangement for Common Oil Unit (C-2001) | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-PPL-203 | 0 | Syn Gas (C-2001) On Skid Piping Arrangement | MC-301-1 | NEW JCM | 2020-08-25 |  |  | No | -67 | [9 empty] | No | 0
VD-9001-301-1-LST-201 | 0 | Syn Gas (C-2001) Utility Consumption List | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-05 05:53 | 2020-06-05 05:53 | Yes | 25 | [9 empty] | No | 0
VD-9001-301-1-LST-202 | 0 | Syn Gas Compressor Train (C-2001) Lubricant Oil List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-203 | 0 | Syn Gas Compressor Train (C-2001) Spare Part List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-204 | 0 | Syn Gas Compressor Train (C-2001) Special Tools List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-205 | 0 | Syn Gas (C-2001) Connection List | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-10 12:42 | 2020-06-10 12:43 | Yes | 30 | [9 empty] | No | -5
VD-9001-301-1-PCJ-201 | 0 | Mechanical Running Test Procedure for Syn Gas Compressor (C-2001) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-202 | 0 | Mechanical Running Test Procedure for Syn Gas Steam Turbine (STC-2001) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-203 | 0 | Syn Gas (C-2001) String Test Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-204 | 0 | Common Oil Console (C-2001) Test Procedure | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-PCJ-205 | 0 | Syn Gas Compressor (C-2001) Shop Performance Test Procedure | MC-301-1 | NEW JCM | 2020-10-11 |  |  | No | -114 | [9 empty] | No | 0
VD-9001-301-1-MNL-201 | 0 | Syn Gas Compressor (C-2001) / Turbine Manual Book (Erection, Commissioning) | MC-301-1 | NEW JCM | 2020-10-11 |  |  | No | -114 | [9 empty] | No | 0
VD-9001-301-1-MNL-202 | 0 | Syn Gas Compressor (C-2001) Manual Book (Operation & Maintenance) | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-MNL-203 | 0 | Syn Gas Steam Turbine (STC-2001) Manual Book (Operation & Maintenance) | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-ITP-201 | 0 | ITP for Syn Gas Compressor (C-2001) | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-ARP-201 | 0 | Syn Gas (C-2001) Rotor Dynamics Lateral Analysis Report | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-ARP-202 | 0 | Syn Gas (C-2001) Torsional Analysis Report | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-WPS-201 | 0 | Syn Gas WPS/PQR for Compressor (C-2001) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-WPS-202 | 0 | Syn Gas WPS/PQR for Turbine (STC-2001) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-251 | 0 | Syn Gas (C-2001) Local Gauge Board Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-252 | 0 | Syn Gas (C-2001) Hook-up Drawing | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DWG-253 | 0 | Syn Gas (C-2001) PLC System and IRC Cabinets Layout | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DWG-254 | 0 | Syn Gas (C-2001) On Skid Instrument Layout Drawing | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-251 | 0 | Syn Gas (C-2001) Control System Overview | MC-301-1 | NEW JCM | 2020-04-01 |  |  | No | 79 | [9 empty] | No | 0
VD-9001-301-1-DIG-252 | 0 | Syn Gas (C-2001) Logic Diagram- Trip and Interlocks | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-253 | 0 | Syn Gas (C-2001) Logic Diagram- Motor Startup | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-254 | 0 | Syn Gas (C-2001) Logic Diagram- Alarms | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-255 | 0 | Syn Gas (C-2001) Governor Wiring Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-256 | 0 | Syn Gas (C-2001) Electric Wiring Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-257 | 0 | Syn Gas (C-2001) Cause & Effects Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-258 | 0 | Syn Gas (C-2001) PLC Program List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DIG-259 | 0 | Syn Gas Compressor (C-2001) Anti-Surge Control Diagram | MC-301-1 | NEW JCM | 2020-05-11 |  |  | No | 39 | [9 empty] | No | 0
VD-9001-301-1-PCJ-251 | 0 | Syn Gas (C-2001) Control Acceptance Test Procedure | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DSH-251 | 0 | Syn Gas (C-2001) Instrument Data Sheet | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DSH-252 | 0 | Syn Gas Compressor (C-2001) Anti-Surge Valve Data Sheet & Drawing | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-DSH-253 | 0 | Syn Gas (C-2001) Flow Element Data Sheet for Anti-Surge System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-DSH-254 | 0 | Syn Gas (C-2001) Flow Transmitter Data Sheet for Anti-Surge System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-CAL-251 | 0 | Syn Gas (C-2001) Control Valves Calculation Data | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-LST-156 | 0 | REC (C-2002) Modbus Address List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-LST-157 | 0 | REC (C-2002) Cable List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-158 | 0 | REC (C-2002) Instrument List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-SKT-151 | 0 | REC (C-2002) HMI Screen Shoot | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-CAL-252 | 0 | Syn Gas (C-2001) Flow Element Calculation Data | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-LST-251 | 0 | Syn Gas (C-2001) IO List with Set Points | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-252 | 0 | Syn Gas (C-2001) Bently Nevada 3500 Communication List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-LST-253 | 0 | Syn Gas Turbine (STC-2001) Governor IO List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-254 | 0 | Syn Gas Turbine (STC-2001) Governor program List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-255 | 0 | Syn Gas (C-2001) Vibration and Axial Position Monitor System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-LST-256 | 0 | Syn Gas (C-2001) Modbus Address List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-LST-257 | 0 | Syn Gas (C-2001) Cable List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-258 | 0 | Syn Gas (C-2001) Instrument List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-SKT-251 | 0 | Syn Gas (C-2001) HMI Screen Shoot | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-PID-101 | 0 | REC Compressor (C-2002) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:26 | 2020-04-26 08:38 | Yes | 25 |  |  |  | 2020-06-01 11:19 |  |  |  |  | 2020-06-01 11:19 | Yes | 22
VD-9001-301-1-PID-102 | 0 | REC Steam Turbine (STC-2002) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:27 | 2020-04-26 08:38 | Yes | 25 |  |  |  | 2020-06-01 12:47 |  |  |  |  | 2020-06-01 12:48 | Yes | 22
VD-9001-301-1-PID-103 | 0 | REC Compressor (C-2002) Lube Oil System (Base) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:27 | 2020-04-26 08:39 | Yes | 25 |  |  |  | 2020-05-28 10:12 |  |  |  |  | 2020-05-28 10:12 | Yes | 18
VD-9001-301-1-PID-105 | 0 | REC (C-2002) Machine Monitoring Diagram | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:27 | 2020-04-26 08:39 | Yes | 25 |  |  |  | 2020-05-17 15:31 |  |  |  |  | 2020-05-17 15:32 | Yes | 7
VD-9001-301-1-PID-106 | 0 | REC Compressor (C-2002) Dry Gas Seal System PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:27 | 2020-04-26 08:40 | Yes | 25 |  |  |  | 2020-05-28 10:59 |  |  |  |  | 2020-05-28 10:59 | Yes | 18
VD-9001-301-1-PID-107 | 0 | REC Turbine (STC-2002) Governing System PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:28 | 2020-04-26 08:40 | Yes | 25 |  |  |  | 2020-05-28 11:34 |  |  |  |  | 2020-05-28 11:34 | Yes | 18
VD-9001-301-1-PID-108 | 0 | REC Compressor (C-2002) Control System Overview PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:28 | 2020-04-26 08:40 | Yes | 25 |  |  |  | 2020-05-19 18:06 |  |  |  |  | 2020-05-19 18:07 | Yes | 9
VD-9001-301-1-DSH-101 | 0 | REC Compressor (C-2002) Data Sheet | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 07:55 | 2020-04-26 08:10 | Yes | 25 |  |  |  | 2020-05-12 14:03 |  |  |  |  | 2020-05-12 14:03 | Yes | 2
VD-9001-301-1-DSH-102 | 0 | REC Steam Turbine (STC-2002) Data Sheet | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:01 | 2020-04-26 08:10 | Yes | 25 |  |  |  | 2020-05-12 13:20 |  |  |  |  | 2020-05-12 13:21 | Yes | 2 | 1204-Owner-v | 2020-06-01 11:20
VD-9001-301-1-DSH-104 | 0 | REC Compressor (C-2002) Process PSV Data Sheets | MC-301-1 | NEW JCM | 2020-04-01 |  |  | No | 79 | [9 empty] | No | 0
VD-9001-301-1-DSH-105 | 0 | REC (STC-2002) Gland Condenser Data Sheet | MC-301-1 | NEW JCM | 2020-04-01 | 2020-06-09 11:47 | 2020-06-09 12:34 | Yes | 69 | [9 empty] | No | -4
VD-9001-301-1-DSH-110 | 0 | REC Compressor (C-2002) Noise Data Sheet | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 11:48 | 2020-06-09 12:34 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-PCU-101 | 0 | REC Compressor (C-2002) Performance Curve | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:26 | 2020-04-26 08:37 | Yes | 25 |  |  |  | 2020-05-12 08:24 |  |  |  |  | 2020-05-12 08:25 | Yes | 2
VD-9001-301-1-PCU-102 | 0 | REC Turbine (STC-2002) Expected Performance Curve | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:25 | 2020-04-26 08:37 | Yes | 25 |  |  |  | 2020-05-12 08:32 |  |  |  |  | 2020-05-12 08:32 | Yes | 2
VD-9001-301-1-DWG-101 | 0 | REC Compressor (C-2002) Outline Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:04 | 2020-04-26 08:21 | Yes | 25 |  |  |  | 2020-05-13 18:22 |  |  |  |  | 2020-05-13 18:22 | Yes | 3 | 1204-Owner-v | 2020-05-02 09:29
VD-9001-301-1-DWG-102 | 0 | REC Compressor (C-2002) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:04 | 2020-04-26 08:21 | Yes | 25 |  |  |  |  | 2020-05-13 16:27 |  |  |  | 2020-05-13 16:27 | Yes | 3
VD-9001-301-1-DWG-103 | 0 | REC Steam Turbine (STC-2002) Outline Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:06 | 2020-04-26 08:21 | Yes | 25 |  |  |  | 2020-05-14 09:43 |  |  |  |  | 2020-05-14 09:44 | Yes | 4
VD-9001-301-1-DWG-104 | 0 | REC Steam Turbine (STC-2002) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:07 | 2020-04-26 08:22 | Yes | 25 |  |  |  | 2020-05-14 09:46 |  |  |  |  | 2020-05-14 09:47 | Yes | 4
VD-9001-301-1-DWG-105 | 0 | REC (STC-2002) Gland Condenser Outline Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:38 | 2020-06-09 12:49 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DIS-001 | 0 | VDIS for Syn Gas and REC Compressor | MC-301-1 | NEW JCM | 2020-04-01 |  |  | No | 79 | [9 empty] | No | 0
VD-9001-301-1-PCJ-001 | 0 | Hydrostatic Test Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-002 | 0 | Packing and Shipping Procedure | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-PCJ-003 | 0 | NDT Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-004 | 0 | Heat Treatment Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-005 | 0 | Balance Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-SPE-001 | 0 | Painting Specification | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-LST-001 | 0 | Sub-Vendor List | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-17 11:28 | 2020-06-17 11:29 | Yes | 37 | [9 empty] | No | -12
VD-9001-301-1-ARP-001 | 0 | HAZOP Report | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-ARP-002 | 0 | SIL Report | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-PID-201 | 0 | Synthesis Gas Compressor (C-2001) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:39 | 2020-04-26 08:48 | Yes | 25 |  |  |  | 2020-05-18 11:13 |  |  |  |  | 2020-05-18 11:14 | Yes | 8
VD-9001-301-1-PID-202 | 0 | Syn Gas Steam Turbine (STC-2001) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:29 | 2020-04-26 08:48 | Yes | 25 |  |  |  | 2020-05-18 15:10 |  |  |  |  | 2020-05-18 15:10 | Yes | 8
VD-9001-301-1-PID-203 | 0 | Common Lube Oil System (C-2001) (Tank) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:29 | 2020-04-26 08:48 | Yes | 25 |  |  |  | 2020-05-28 09:19 |  |  |  |  | 2020-05-28 09:19 | Yes | 18
VD-9001-301-1-PID-204 | 0 | Syn Gas Compressor (C-2001) Lube Oil System (Base) PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:29 | 2020-04-26 08:48 | Yes | 25 |  |  |  | 2020-05-19 17:26 |  |  |  |  | 2020-05-19 17:27 | Yes | 9
VD-9001-301-1-PID-205 | 0 | Syn Gas (C-2001) Machine Monitoring Diagram | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:42 | 2020-04-26 08:48 | Yes | 25 |  |  |  | 2020-05-17 15:31 |  |  |  |  | 2020-05-17 15:31 | Yes | 7
VD-9001-301-1-PID-206 | 0 | Syn Gas Compressor (C-2001) Dry Gas Seal System PID | MC-301-1 | NEW JCM | 2020-05-11 | 2020-04-26 08:42 | 2020-04-26 08:49 | Yes | -15 |  |  |  | 2020-05-20 11:34 |  |  |  |  | 2020-05-20 11:34 | Yes | 10
VD-9001-301-1-PID-207 | 0 | Syn Gas Turbine (STC-2001) Governing System PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:42 | 2020-04-26 08:50 | Yes | 25 |  |  |  | 2020-05-19 19:26 |  |  |  |  | 2020-05-19 19:26 | Yes | 9
VD-9001-301-1-PID-208 | 0 | Syn Gas Compressor (C-2001) Control System Overview PID | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:42 | 2020-04-26 08:49 | Yes | 25 |  |  |  | 2020-05-18 10:07 |  |  |  |  | 2020-05-18 10:07 | Yes | 8
VD-9001-301-1-DSH-201 | 0 | Syn Gas Compressor (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:01 | 2020-04-26 08:16 | Yes | 25 |  |  |  | 2020-05-13 17:31 |  |  |  |  | 2020-05-13 17:36 | Yes | 3
VD-9001-301-1-DSH-202 | 0 | Syn Gas Steam Turbine (STC-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:01 | 2020-04-26 08:20 | Yes | 25 |  |  |  | 2020-05-12 13:51 |  |  |  |  | 2020-05-12 13:51 | Yes | 2 | 1204-Owner-v | 2020-06-01 11:17
VD-9001-301-1-DSH-203 | 0 | Common Oil System (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DSH-204 | 0 | Syn Gas Compressor (C-2001) Process PSV Data Sheets | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DSH-205 | 0 | Syn Gas (STC-2001) Gland Condenser Data Sheet | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 11:48 | 2020-06-09 12:35 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DSH-206 | 0 | Common Oil Pumps (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DSH-207 | 0 | Common Oil Cooler (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 11:48 | 2020-06-09 12:35 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DSH-208 | 0 | Common Oil Heater (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 11:48 | 2020-06-09 12:35 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DSH-209 | 0 | Common Oil Filter (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:37 | 2020-06-09 12:48 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DSH-210 | 0 | Syngas Compressor (C-2001) Noise Data Sheet | MC-301-1 | NEW JCM | 2020-04-15 | 2020-06-09 12:37 | 2020-06-09 12:49 | Yes | 55 | [9 empty] | No | -4
VD-9001-301-1-SPE-201 | 0 | Common Oil Pump (C-2001) Motor Specifications (DHS, Curve & Docs.) | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-SPE-202 | 0 | Common Oil Pump (C-2001) Steam Turbine Specifications (DHS, Curve & Docs.) | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-SPE-203 | 0 | Common Oil Mist Fan (C-2001) Motor Specification | MC-301-1 | NEW JCM | 2020-10-11 |  |  | No | -114 | [9 empty] | No | 0
VD-9001-301-1-PCU-201 | 0 | Syn Gas Compressor (C-2001) Performance Curve | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:27 | 2020-04-26 08:37 | Yes | 25 |  |  |  | 2020-05-12 08:28 |  |  |  |  | 2020-05-12 08:28 | Yes | 2
VD-9001-301-1-PCU-202 | 0 | Syn Gas Turbine (STC-2001) Expected Performance Curve | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:25 | 2020-04-26 08:38 | Yes | 25 |  |  |  | 2020-05-12 08:35 |  |  |  |  | 2020-05-12 08:35 | Yes | 2
VD-9001-301-1-DWG-201 | 0 | Syn Gas Compressor (C-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 07:34 | 2020-04-26 08:22 | Yes | 25 |  |  |  | 2020-05-13 18:13 |  |  |  |  | 2020-05-13 18:13 | Yes | 3
VD-9001-301-1-DWG-202 | 0 | Syn Gas Compressor (C-2001) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:07 | 2020-04-26 08:23 | Yes | 25 |  |  |  | 2020-05-13 16:11 |  |  |  |  | 2020-05-13 16:11 | Yes | 3
VD-9001-301-1-DWG-203 | 0 | Syn Gas Steam Turbine (STC-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:08 | 2020-04-26 08:23 | Yes | 25 |  |  |  | 2020-05-14 09:50 |  |  |  |  | 2020-05-14 09:50 | Yes | 4
VD-9001-301-1-DWG-204 | 0 | Syn Gas Steam Turbine (STC-2001) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:09 | 2020-04-26 08:23 | Yes | 25 |  |  |  | 2020-05-14 09:52 |  |  |  |  | 2020-05-14 09:52 | Yes | 4
VD-9001-301-1-DWG-205 | 0 | Syn Gas (STC-2001) Gland Condenser Outline Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:39 | 2020-06-09 12:49 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DWG-206 | 0 | Syn Gas Compressor (C-2001) Lube Oil Run Down Tank Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:39 | 2020-06-09 12:50 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DWG-207 | 0 | Syn Gas Compressor (C-2001) Suction Strainer Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-208 | 0 | Syn Gas Steam Turbine (STC-2001) Duct Assembly Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-209 | 0 | Syn Gas (C-2001) Couplings Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-210 | 0 | Syn Gas (C-2001) DGS Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-211 | 0 | Common Oil Pumps (C-2001) Data Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-106 | 0 | REC Compressor (C-2002) Lube Oil Run Down Tank Drawing | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-09 12:38 | 2020-06-09 12:49 | Yes | 29 | [9 empty] | No | -4
VD-9001-301-1-DWG-107 | 0 | REC Compressor (C-2002) Suction Strainer Drawing | MC-301-1 | NEW JCM | 2020-05-25 |  |  | No | 25 | [9 empty] | No | 0
VD-9001-301-1-DWG-109 | 0 | REC (C-2002) Couplings Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-110 | 0 | REC (C-2002) DGS Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-112 | 0 | REC Compressor (C-2002) Thrust & Radial Bearing Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-113 | 0 | REC Steam Turbine (STC-2002) Gov. & Exh. Side Bearing Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-114 | 0 | REC Compressor (C-2002) Rotor Assembly Drawing | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-115 | 0 | REC Steam Turbine (STC-2002) Rotor Assembly Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-119 | 0 | REC (C-2002) Seal Panel Drawing | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-DWG-120 | 0 | REC (C-2002) Lifting Arrangemnt Drawing | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-101 | 0 | REC Steam Turbine (STC-2002) Blade Campbell/ Goodman Diagram | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-102 | 0 | REC (C-2002) Alignment Data | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-103 | 0 | REC Turbine (STC-2002) Start Up Diagram | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-PPL-101 | 0 | REC (C-2002) General Arrangement & Foundation Drawing | MC-301-1 | NEW JCM | 2020-04-01 | 2020-04-26 08:43 | 2020-04-26 08:50 | Yes | 25 |  |  |  |  | 2020-05-14 11:38 |  |  |  | 2020-05-14 11:39 | Yes | 4 | 1204-Owner-v | 2020-06-02 13:40
VD-9001-301-1-PPL-103 | 0 | REC (C-2002) On Skid Piping Arrangement | MC-301-1 | NEW JCM | 2020-08-25 |  |  | No | -67 | [9 empty] | No | 0
VD-9001-301-1-LST-101 | 0 | REC (C-2002) Utility Consumption List | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-05 05:52 | 2020-06-05 05:52 | Yes | 25 | [9 empty] | No | 0
VD-9001-301-1-LST-102 | 0 | REC Compressor (C-2002) Train Lubricant Oil List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-103 | 0 | REC Compressor (C-2002) Train Spare Part List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-104 | 0 | REC Compressor Train (C-2002) Special Tools List | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-LST-105 | 0 | REC (C-2002) Connection List | MC-301-1 | NEW JCM | 2020-05-11 | 2020-06-10 12:42 | 2020-06-10 12:43 | Yes | 30 | [9 empty] | No | -5
VD-9001-301-1-PCJ-101 | 0 | Mechanical Running Test Procedure for REC Compressor (C-2002) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-102 | 0 | Mechanical Running Test Procedure for REC Steam Turbine (STC-2002) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-103 | 0 | REC (C-2002) String Test Procedure | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-PCJ-105 | 0 | REC Compressor (C-2002) Shop Performance Test Procedure | MC-301-1 | NEW JCM | 2020-10-25 |  |  | No | -128 | [9 empty] | No | 0
VD-9001-301-1-MNL-101 | 0 | REC Compressor (C-2002) / Turbine Manual Book (Erection, Commissioning) | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-MNL-102 | 0 | REC Compressor (C-2002) Manual Book (Operation & Maintenance) | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-MNL-103 | 0 | REC Steam Turbine (STC-2002) Manual Book (Operation & Maintenance) | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-ITP-101 | 0 | ITP for REC Compressor (C-2002) | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-ARP-101 | 0 | REC (C-2002) Rotor Dynamics Lateral Analysis Report | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-ARP-102 | 0 | REC (C-2002) Torsional Analysis Report | MC-301-1 | NEW JCM | 2020-07-25 |  |  | No | -36 | [9 empty] | No | 0
VD-9001-301-1-WPS-101 | 0 | REC WPS/PQR for Compressor (C-2002) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-WPS-102 | 0 | REC WPS/PQR for Turbine (STC-2002) | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DWG-151 | 0 | REC (C-2002) Local Gauge Board Drawing | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DWG-152 | 0 | REC (C-2002) Hook-up Drawing | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DWG-153 | 0 | REC (C-2002) PLC System and IRC Cabinets Layout | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DWG-154 | 0 | REC (C-2002) On Skid Instrument Layout Drawing | MC-301-1 | NEW JCM | 2020-09-11 |  |  | No | -84 | [9 empty] | No | 0
VD-9001-301-1-DIG-151 | 0 | REC (C-2002) Control System Overview | MC-301-1 | NEW JCM | 2020-04-01 |  |  | No | 79 | [9 empty] | No | 0
VD-9001-301-1-DIG-152 | 0 | REC (C-2002) Logic Diagram- Trip and Interlocks | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-153 | 0 | REC (C-2002) Logic Diagram- Motor Startup | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-154 | 0 | REC (C-2002) Logic Diagram- Alarms | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-155 | 0 | REC (C-2002) Governor Wiring Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-156 | 0 | REC (C-2002) Electric Wiring Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-157 | 0 | REC (C-2002) Cause & Effects Diagram | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-DIG-158 | 0 | REC (C-2002) PLC Program List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DIG-159 | 0 | REC (C-2002) Compressor Anti-Surge Control Diagram | MC-301-1 | NEW JCM | 2020-05-11 |  |  | No | 39 | [9 empty] | No | 0
VD-9001-301-1-PCJ-151 | 0 | REC (C-2002) Control Acceptance Test Procedure | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-DSH-151 | 0 | REC (C-2002) Instrument Data Sheet | MC-301-1 | NEW JCM | 2020-07-11 |  |  | No | -22 | [9 empty] | No | 0
VD-9001-301-1-DSH-152 | 0 | REC Compressor (C-2002) Anti-Surge Valve Data Sheet & Drawing | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-DSH-153 | 0 | REC (C-2002) Flow Element Data Sheet for Anti-Surge System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-DSH-154 | 0 | REC (C-2002) Flow Transmitter Data Sheet for Anti-Surge System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-CAL-151 | 0 | REC (C-2002) Control Valves Calculation Data | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-CAL-152 | 0 | REC (C-2002) Flow Element Calculation Data | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-301-1-LST-151 | 0 | REC (C-2002) IO List with Set Points | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-152 | 0 | REC (C-2002) Bently Nevada 3500 Communication List | MC-301-1 | NEW JCM | 2020-12-11 |  |  | No | -175 | [9 empty] | No | 0
VD-9001-301-1-LST-153 | 0 | REC Turbine (STC-2002) Governor IO List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-154 | 0 | REC Turbine (STC-2002) Governor program List | MC-301-1 | NEW JCM | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-LST-155 | 0 | REC (C-2002) Vibration and Axial Position Monitor System | MC-301-1 | NEW JCM | 2020-08-11 |  |  | No | -53 | [9 empty] | No | 0
VD-9001-740C-PCJ-002 | 1 | WELDING SEQUENCE PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-04-30 | 2020-04-27 13:01 | 2020-04-27 13:01 | Yes | -3 |  |  |  | 2020-05-03 18:29 |  |  |  |  | 2020-05-03 21:03 | Yes | -8
VD-9001-104(1-S)-DIG-004 | 1 | Steam turbine – Diagram For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-04-30 |  |  | No | 50 | [9 empty] | No | 0
VD-9001-104(1-S)-PID-001 | 1 | Compressor P&ID For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-04-29 | 2020-06-08 12:29 | 2020-06-08 12:29 | Yes | 40 | [9 empty] | No | -3
VD-9001-260-PRC-002 | 1 | NDT procedur | HM-260 | ABAN AIR COOLER. | 2020-05-02 | 2020-05-13 10:02 | 2020-05-13 10:05 | Yes | 11 |  |  |  | 2020-05-25 14:32 |  |  |  |  | 2020-05-25 14:32 | Yes | -2
VD-9001-260-DIS-001 | 1 | Vendor Print Index & Schedule | HM-260 | ABAN AIR COOLER. | 2020-05-02 | 2020-04-25 20:07 | 2020-04-25 20:08 | Yes | -7 |  |  | 2020-04-26 08:00 | [5 empty] | 2020-04-26 08:00 | Yes | -13
VD-9001-257C-FDB-004 | 1 | MANUFACTURING DATA BOOK (0644/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-04-30 | 2020-04-27 18:11 | 2020-04-27 18:12 | Yes | -3 |  |  | 2020-04-28 10:04 | [5 empty] | 2020-04-28 10:04 | Yes | -13
VD-9001-257C-FDB-003 | 1 | MANUFACTURING DATA BOOK (0643/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-04-30 | 2020-04-27 17:19 | 2020-04-27 17:21 | Yes | -3 |  |  | 2020-04-28 09:58 | [5 empty] | 2020-04-28 09:58 | Yes | -13
VD-9001-251E-DWG-003 | 1 | Assembly Drawn for DWG No.:F-OF16230 | HM-251E | Iran Industrial Vibrations Co. | 2020-04-28 | 2020-04-27 08:57 | 2020-04-27 09:03 | Yes | -1 |  |  |  | 2020-05-12 12:10 |  |  |  |  | 2020-05-12 12:10 | Yes | 1
VD-9001-251E-DWG-004 | 1 | Assembly Drawing for DWG No.:F-OF16240 | HM-251E | Iran Industrial Vibrations Co. | 2020-04-28 | 2020-04-27 09:17 | 2020-04-27 09:18 | Yes | -1 |  |  |  | 2020-05-10 13:00 |  |  |  |  | 2020-05-10 13:00 | Yes | -1
VD-9001-251E-DWG-002 | 1 | Assembly Drawing for DWG No.: F-OF16220 | HM-251E | Iran Industrial Vibrations Co. | 2020-04-28 | 2020-04-27 08:49 | 2020-04-27 08:53 | Yes | -1 |  |  |  |  | 2020-05-16 08:41 |  |  |  | 2020-05-16 08:41 | Yes | 5
VD-9001-251B1-ITP-001 | 0 | INSPECTION & TEST PLAN | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-04-27 | 2020-05-02 13:49 | 2020-05-02 13:51 | Yes | 5 |  |  |  | 2020-05-10 09:30 |  |  |  |  | 2020-05-10 09:30 | Yes | -6 | 1204-Owner-v | 2020-05-23 14:16
VD-9001-251B1-DWG-001 | 0 | DETAIL DRAWINGS | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-04-27 | 2020-04-27 17:59 | 2020-04-27 17:59 | Yes | 0 |  |  |  | 2020-04-28 09:07 |  |  |  |  | 2020-04-28 09:07 | Yes | -13
VD-9001-251B1-CAT-001 | 0 | CATALOGUE | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-251B1-CER-001 | 0 | CERTIFICATE | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-06 |  |  | No | 44 | [9 empty] | No | 0
VD-9001-251B1-NDT-001 | 0 | NDT PROCEDURE | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-251B1-WPS-001 | 0 | WELDING PROCEDURE SPECIFICATION | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-06-05 | 2020-05-05 17:42 | 2020-05-05 17:43 | Yes | -31 |  |  |  | 2020-05-13 14:24 |  |  |  |  | 2020-05-13 14:24 | Yes | -6
VD-9001-251B1-PQR-001 | 0 | PROCEDURE QUALIFICATION RECORD | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-251B1-WQR-001 | 0 | WELDER QUALIFICATION REPORT | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-251B1-LST-001 | 0 | PACKING AND MARKING PROCEDURE | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-06 |  |  | No | 44 | [9 empty] | No | 0
VD-9001-251B1-PMI-001 | 0 | POSITIVE MATERIAL IDENTIFICATION | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-12-06 |  |  | No | -170 | [9 empty] | No | 0
VD-9001-251B1-VEX-001 | 0 | VISUAL EXAMINATION | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-06 |  |  | No | 44 | [9 empty] | No | 0
VD-9001-251B1-INX-001 | 0 | FINAL VENDOR DATAOOK INDEX | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-251B1-BOM-001 | 0 | BILL OF MATERIAL | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-06-05 | 2020-05-05 09:59 | 2020-05-05 10:00 | Yes | -31 |  |  | 2020-05-10 09:34 | [5 empty] | 2020-05-10 09:34 | Yes | -9
VD-9001-251B1-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-04-25 | 2020-04-27 14:35 | 2020-04-27 17:59 | Yes | 2 |  |  | 2020-04-28 09:08 | [5 empty] | 2020-04-28 09:08 | Yes | -13 | 1204-Owner-v | 2020-05-23 14:15
VD-9001-251B1-FDB-001 | 0 | FINAL VENDOR DATA BOOK | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-10-06 |  |  | No | -109 | [9 empty] | No | 0
VD-9001-104(1-S)-PID-002 | 1 | Steam turbine P&ID For Air Compressor Package (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-03 | 2020-06-08 12:30 | 2020-06-08 12:30 | Yes | 36 | [9 empty] | No | -3
VD-9001-104(1-S)-PID-003 | 1 | Common lube oil P&ID For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-03 | 2020-06-08 12:31 | 2020-06-08 12:31 | Yes | 36 | [9 empty] | No | -3
VD-9001-740C-GAD-271 | 2 | General Arrangement Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-03 | 2020-04-30 08:15 | 2020-04-30 08:16 | Yes | -3 |  |  |  | 2020-05-27 10:16 |  |  |  |  | 2020-05-27 10:16 | Yes | 13 | 1204-Owner-v | 2020-05-26 08:14
VD-9001-740C-RPT-271 | 2 | Reports For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-03 | 2020-04-30 08:22 | 2020-04-30 08:22 | Yes | -3 |  |  |  | 2020-05-04 14:50 |  |  |  |  | 2020-05-04 14:50 | Yes | -10
VD-9001-740C-MOD-271 | 2 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-03 | 2020-04-30 08:21 | 2020-04-30 08:21 | Yes | -3 |  |  |  | 2020-05-02 13:49 |  |  |  |  | 2020-05-02 20:58 | Yes | -12 | 1204-Owner-v | 2020-05-12 18:42
VD-9001-307A1-DSH-020 | 2 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 | 2020-06-01 13:02 | 2020-06-01 13:02 | Yes | 24 |  |  |  |  | 2020-06-15 13:44 |  |  |  | 2020-06-15 13:44 | Yes | 0
VD-9001-307A1-DSH-019 | 2 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 | 2020-06-01 13:02 | 2020-06-01 13:02 | Yes | 24 |  |  |  |  | 2020-06-15 12:41 |  |  |  | 2020-06-15 12:41 | Yes | 0
VD-9001-307A1-DSH-021 | 2 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 | 2020-06-01 13:03 | 2020-06-01 13:03 | Yes | 24 |  |  |  | 2020-06-18 11:38 |  |  |  |  | 2020-06-18 11:38 | Yes | 3
VD-9001-307A1-DSH-022 | 2 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 | 2020-06-01 13:03 | 2020-06-01 13:04 | Yes | 24 |  |  |  |  | 2020-06-15 13:50 |  |  |  | 2020-06-15 13:50 | Yes | 0
VD-9001-260-PRC-009 | 1 | Material IdentificationAnd Traceability Procedure | HM-260 | ABAN AIR COOLER. | 2020-05-04 |  |  | No | 46 | [9 empty] | No | 0
VD-9001-605-1-DIS-001 | 0 | Vendor Documents Index & Schedule | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-18 | 2020-05-10 12:03 | 2020-05-10 12:06 | Yes | 22 |  |  |  | 2020-05-13 17:05 |  |  |  |  | 2020-05-13 17:05 | Yes | -11
VD-9001-605-1-VLS-001 | 0 | Sub Vendor List | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-25 | 2020-05-10 12:03 | 2020-05-10 12:06 | Yes | 15 |  |  |  | 2020-05-13 16:33 |  |  |  |  | 2020-05-13 16:33 | Yes | -11
VD-9001-605-1-DWG-001 | 0 | General Arrangements drawing including BOM | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-DWG-002 | 0 | Pneumatic Drawing | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-DWG-003 | 0 | Deimensional and section Drawing | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-DSH-001 | 0 | Instrument Data Sheets | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 | 2020-05-10 12:07 | 2020-05-10 12:08 | Yes | 5 |  |  |  |  | 2020-05-28 08:38 |  |  |  | 2020-05-28 08:38 | Yes | 4 | 1204-Owner-v | 2020-05-11 16:26
VD-9001-605-1-CAL-001 | 0 | Calculation Sheet | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-ITP-001 | 0 | Inspection and Test Plan | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-29 | 2020-06-14 15:14 | 2020-06-14 15:15 | Yes | 46 | [9 empty] | No | -9
VD-9001-605-1-CAT-001 | 0 | Catalogue Data | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-25 | 2020-05-10 12:02 | 2020-05-10 12:07 | Yes | 15 |  |  |  | 2020-05-13 16:11 |  |  |  |  | 2020-05-13 16:11 | Yes | -11
VD-9001-605-1-LST-001 | 0 | Master Packing List | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-LST-002 | 0 | Detailed Packing List | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-PCJ-001 | 0 | NDE Procedure (PMI) | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-12 09:23 | 2020-05-12 09:24 | Yes | 14 |  |  |  |  | 2020-05-19 18:30 |  |  |  | 2020-05-19 18:30 | Yes | -7
VD-9001-605-1-PCJ-002 | 0 | Surface Preparatioon and Coating(painting) Specification | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-605-1-PCJ-003 | 0 | Hydrostatic Shell Test Procedure | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-12 09:24 | 2020-05-12 09:24 | Yes | 14 |  |  |  |  | 2020-05-19 18:27 |  |  |  | 2020-05-19 18:27 | Yes | -7
VD-9001-605-1-PCJ-004 | 0 | FAT Procedure including Leak test procedure | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-605-1-RPT-001 | 0 | Factory Acceptance Test Reports (Material Certificate icluded) | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-CER-001 | 0 | Quality Management System Certification / Manufacture certificates | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-MNL-001 | 0 | Installation, Commissioning, Operating and Maintenance Manuals | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-16 12:55 | 2020-05-16 12:56 | Yes | 18 | [9 empty] | No | 20
VD-9001-605-1-MNL-002 | 0 | Functional Safety documents | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-605-1-SCH-001 | 0 | Spare part list for Commissioning | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 | 2020-05-16 15:14 | 2020-05-16 15:14 | Yes | 11 | [9 empty] | No | 20
VD-9001-605-1-SCH-002 | 0 | Spare part list for 2 years | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 | 2020-05-16 15:14 | 2020-05-16 15:14 | Yes | 11 | [9 empty] | No | 20
VD-9001-605-1-DIS-002 | 0 | Final Vendor Data Book Index | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-605-1-MDB-001 | 0 | Final Vendor Data Book | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-DIS-001 | 0 | Vendor Documents Index & Schedule | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-18 | 2020-05-10 11:00 | 2020-05-10 11:01 | Yes | 22 |  |  |  | 2020-05-12 10:50 |  |  |  |  | 2020-05-12 10:50 | Yes | -12
VD-9001-604-1-VLS-001 | 0 | Sub Vendor List | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-25 | 2020-05-10 09:35 | 2020-05-10 09:36 | Yes | 15 |  |  |  | 2020-05-12 10:25 |  |  |  |  | 2020-05-12 10:25 | Yes | -12
VD-9001-604-1-DWG-001 | 0 | General Arrangements drawing including BOM | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-DWG-002 | 0 | Pneumatic Drawing | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-DWG-003 | 0 | Deimensional and section Drawing | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-DSH-001 | 0 | Instrument Data Sheets | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 | 2020-05-10 11:01 | 2020-05-10 11:02 | Yes | 5 |  |  |  | 2020-05-18 10:40 |  |  |  |  | 2020-05-18 10:40 | Yes | -6 | 1204-Owner-v | 2020-05-11 16:26
VD-9001-604-1-ITP-001 | 0 | Inspection and Test Plan | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-29 |  |  | No | 51 | [9 empty] | No | 0
VD-9001-604-1-CAT-001 | 0 | Catalogue Data | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-25 | 2020-05-10 11:00 | 2020-05-10 11:00 | Yes | 15 |  |  |  | 2020-05-13 14:41 |  |  |  |  | 2020-05-13 14:41 | Yes | -11
VD-9001-604-1-LST-001 | 0 | Master Packing List | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-LST-002 | 0 | Detailed Packing List | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-PCJ-001 | 0 | NDE Procedure (PMI) | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-12 09:07 | 2020-05-12 09:08 | Yes | 14 |  |  |  |  | 2020-05-19 18:35 |  |  |  | 2020-05-19 18:35 | Yes | -7
VD-9001-604-1-PCJ-002 | 0 | Surface Preparatioon and Coating(painting) Specification | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-604-1-PCJ-003 | 0 | Hydrostatic Shell Test Procedure | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-12 09:08 | 2020-05-12 09:08 | Yes | 14 |  |  |  |  | 2020-05-19 18:33 |  |  |  | 2020-05-19 18:33 | Yes | -7
VD-9001-604-1-PCJ-004 | 0 | FAT Procedure including Leak test procedure | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-604-1-RPT-001 | 0 | Factory Acceptance Test Reports (Material Certificate icluded) | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-CER-001 | 0 | Quality Management System Certification / Manufacture certificates | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-MNL-001 | 0 | Installation, Commissioning, Operating and Maintenance Manuals | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 | 2020-05-16 12:14 | 2020-05-16 12:12 | Yes | 18 |  |  |  | 2020-06-14 13:07 |  |  |  |  | 2020-06-14 13:07 | Yes | 15
VD-9001-604-1-MNL-002 | 0 | Functional Safety documents | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-04-28 |  |  | No | 52 | [9 empty] | No | 0
VD-9001-604-1-SCH-001 | 0 | Spare part list for Commissioning | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-SCH-002 | 0 | Spare part list for 2 years | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-DIS-002 | 0 | Final Vendor Data Book Index | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-604-1-MDB-001 | 0 | Final Vendor Data Book | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-201B-MNL-001 | 1 | INSTRUCTION OPERATING MANUAL (4134/IOM) | PV-201B | Brembana & Rolle S.p.A. | 2020-05-11 20:58 | 2020-05-20 19:19 | 2020-05-20 19:20 | Yes | 9 |  |  |  | 2020-06-16 15:07 |  |  |  |  | 2020-06-16 20:06 | Yes | 13
VD-9001-104(1-S)-PCJ-001 | 1 | Painting procedure/specification For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-11 |  |  | No | 39 | [9 empty] | No | 0
VD-9001-251B1-DWG-001 | 1 | DETAIL DRAWINGS | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-02 | 2020-04-29 15:23 | 2020-04-29 15:23 | Yes | -3 |  |  |  |  | 2020-04-30 10:18 |  |  |  | 2020-04-30 10:18 | Yes | -13 | 1204-Owner-v | 2020-06-01 16:38
VD-9001-307A1-ITP-001 | 1 | INSPECTION & TEST PLAN FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-09 | 2020-04-28 13:52 | 2020-04-28 13:53 | Yes | -11 |  |  | 2020-05-06 14:53 | [5 empty] | 2020-05-06 14:53 | Yes | -6
VD-9001-307A1-DWG-065 | 1 | LUBE OIL STATION GA DRAWING FOR HP BOILER FEED WATER PUMP UNIT P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 |  |  | No | 42 | [9 empty] | No | 0
VD-9001-213B1-ITP-030 | 1 | Inspection and Test Plan (ITP) | PV-213B1 | PAYSAZ Co. | 2020-05-12 20:58 | 2020-05-05 16:40 | 2020-05-05 16:40 | Yes | -7 |  |  |  |  | 2020-05-18 11:03 |  |  |  | 2020-05-18 20:59 | Yes | -1
VD-9001-213B1-PCJ-031 | 1 | NDT Procedure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-12 20:58 | 2020-04-29 16:35 | 2020-04-29 16:35 | Yes | -13 |  |  | 2020-05-05 14:50 | [5 empty] | 2020-05-05 21:00 | Yes | -8 | 1204-Owner-v | 2020-05-21 07:52
VD-9001-307A1-PID-002 | 1 | PUMP P&I DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-12 20:58 | 2020-05-28 08:21 | 2020-05-28 08:21 | Yes | 16 |  |  |  | 2020-06-16 00:39 |  |  |  |  | 2020-06-16 00:39 | Yes | 5
VD-9001-307A1-PID-005 | 1 | PUMP P&I DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-05-12 20:58 | 2020-05-28 08:21 | 2020-05-28 08:23 | Yes | 16 |  |  |  |  | 2020-06-16 12:10 |  |  |  | 2020-06-16 12:10 | Yes | 5
VD-9001-307A1-PID-003 | 1 | PUMP P&I DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-05-07 | 2020-05-28 08:21 | 2020-05-28 08:21 | Yes | 21 |  |  |  | 2020-06-17 01:13 |  |  |  |  | 2020-06-17 01:13 | Yes | 6
VD-9001-307A1-PID-004 | 1 | PUMP P&I DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-05-08 | 2020-05-28 08:22 | 2020-05-28 08:22 | Yes | 20 |  |  |  |  | 2020-06-15 18:03 |  |  |  | 2020-06-15 18:03 | Yes | 4
VD-9001-307A1-PID-001 | 1 | PUMP P&I DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-07 | 2020-05-28 08:21 | 2020-05-28 08:21 | Yes | 21 |  |  |  | 2020-06-15 18:01 |  |  |  |  | 2020-06-15 18:01 | Yes | 4
VD-9001-307A1-PID-006 | 1 | PUMP P&I DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-07 | 2020-05-28 08:21 | 2020-05-28 08:22 | Yes | 21 |  |  |  | 2020-06-16 12:40 |  |  |  |  | 2020-06-16 12:40 | Yes | 5
VD-9001-104(1-S)-DSH-017 | 1 | Air Compressor thermodynamical data sheets (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-13 20:59 | 2020-04-30 11:02 | 2020-04-30 18:04 | Yes | -13 |  |  |  |  | 2020-05-03 16:13 |  |  |  | 2020-05-03 16:13 | Yes | -11
VD-9001-104(1-S)-WIN-003 | 1 | Air Compressor planning notes (piping; equipm.; found.) (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-13 20:59 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-104(1-S)-PCU-001 | 1 | Performance maps For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-13 20:59 | 2020-04-30 11:03 | 2020-04-30 11:03 | Yes | -13 |  |  |  | 2020-05-03 16:18 |  |  |  |  | 2020-05-03 16:18 | Yes | -11
VD-9001-104(1-S)-LST-012 | 1 | Air Compressor waste heat list (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-13 20:59 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-740C-WPS-001 | 1 | WELDING BOOK (WPS,PQR,WELDING MAP,WPQ) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-06 | 2020-04-30 12:55 | 2020-04-30 12:56 | Yes | -6 |  |  | 2020-05-03 18:16 | [5 empty] | 2020-05-03 21:02 | Yes | -11
VD-9001-104(1-S)-ITP-002 | 1 | Inspection and test plan – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-06 | 2020-04-30 11:04 | 2020-04-30 11:04 | Yes | -6 |  |  |  | 2020-05-13 17:53 |  |  |  |  | 2020-05-13 17:53 | Yes | -1
VD-9001-251B1-DWG-001 | 2 | DETAIL DRAWINGS | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-02 | 2020-05-02 11:55 | 2020-05-02 11:55 | Yes | 0 |  |  | 2020-05-03 15:25 | [5 empty] | 2020-05-03 15:25 | Yes | -13
VD-9001-254-DSH-107 | 1 | DATA SHEET OF SEAL AIR FAN | HM-254 | AZAR AB | 2020-05-05 |  |  | No | 45 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-035 | 1 | ASU P&ID -PUBLIC UTILITIES WARMING GAS | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-31 08:44 | 2020-05-31 08:44 | Yes | 24 |  |  |  | 2020-06-13 12:43 |  |  |  |  | 2020-06-13 12:43 | Yes | -1
VD-9001-104(1-K)-PID-034 | 1 | ASU P&ID -PUBLIC UTILITIES SEAL GAS | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-31 08:43 | 2020-05-31 08:43 | Yes | 24 |  |  |  | 2020-06-13 13:52 |  |  |  |  | 2020-06-13 13:52 | Yes | -1
VD-9001-104(1-K)-PID-031 | 1 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VAPORIZER | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:53 | 2020-05-30 14:53 | Yes | 23 |  |  |  | 2020-06-13 14:55 |  |  |  |  | 2020-06-13 14:55 | Yes | 0
VD-9001-254-PID-119 | 5 | PLANT & MISCELLANEOUS AIR P&I DIAGRAM | HM-254 | AZAR AB | 2020-05-06 |  |  | No | 44 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-030 | 1 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM BACK UP LIN PUMP | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:53 | 2020-05-30 14:53 | Yes | 23 | [9 empty] | No | 6
VD-9001-104(1-K)-PID-029 | 1 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VACUM STORAGE TANK | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:53 | 2020-05-30 14:53 | Yes | 23 |  |  |  | 2020-06-13 15:14 |  |  |  |  | 2020-06-13 15:14 | Yes | 0
VD-9001-104(1-K)-PID-036 | 1 | ASU P&ID -PUBLIC UTILITIES INSTRUMENT AIR | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-31 08:44 | 2020-05-31 08:44 | Yes | 24 |  |  |  | 2020-06-13 12:17 |  |  |  |  | 2020-06-13 12:17 | Yes | -1
VD-9001-104(1-K)-PID-024 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP LIN PUMP A | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:51 | 2020-05-30 14:51 | Yes | 23 | [9 empty] | No | 6
VD-9001-104(1-K)-PID-025 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP LIN PUMP B | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:51 | 2020-05-30 14:51 | Yes | 23 | [9 empty] | No | 6
VD-9001-104(1-K)-PID-026 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LIQUID DRAINAGE SYSTEM | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:51 | 2020-05-30 14:51 | Yes | 23 |  |  |  | 2020-06-14 11:13 |  |  |  |  | 2020-06-14 11:13 | Yes | 1
VD-9001-104(1-K)-PID-027 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, OXYGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:52 | 2020-05-30 14:52 | Yes | 23 |  |  |  | 2020-06-14 09:47 |  |  |  |  | 2020-06-14 09:47 | Yes | 1 | 1204-Owner-v | 2020-06-13 09:26
VD-9001-104(1-K)-PID-028 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM,NITROGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:52 | 2020-05-30 14:52 | Yes | 23 |  |  |  | 2020-06-13 16:07 |  |  |  |  | 2020-06-13 16:07 | Yes | 0
VD-9001-104(1-K)-PID-003 | 1 | ASU P&ID Index | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 12:52 | 2020-05-30 12:52 | Yes | 23 |  |  |  | 2020-06-14 11:30 |  |  |  |  | 2020-06-14 11:30 | Yes | 1
VD-9001-104(1-K)-PID-006 | 1 | ASU P&ID - INTERLOCK POINT LISTS | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:33 | 2020-05-30 14:33 | Yes | 23 |  |  |  | 2020-06-14 12:20 |  |  |  |  | 2020-06-14 12:20 | Yes | 1
VD-9001-307A1-PCJ-009 | 1 | SURFACE PREPARATION AND PAINTING PROCEDURE FOR PUMP AND STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-09 | 2020-05-07 16:38 | 2020-05-07 16:38 | Yes | -2 |  |  |  | 2020-05-26 12:02 |  |  |  |  | 2020-05-26 12:02 | Yes | 5
VD-9001-740C-PCJ-003 | 2 | PAINTING AND COATING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-09 | 2020-05-03 14:24 | 2020-05-03 14:24 | Yes | -6 |  |  |  | 2020-05-16 12:17 |  |  |  |  | 2020-05-16 12:17 | Yes | -1
VD-9001-213B1-DWG-010 | 1 | Shell Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-09 | 2020-05-05 17:26 | 2020-05-05 17:26 | Yes | -4 |  |  |  | 2020-05-06 12:09 |  |  |  |  | 2020-05-06 20:58 | Yes | -13
VD-9001-213B1-PCJ-037 | 1 | Painting & Pickling and Passivation Procedure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-09 | 2020-05-04 13:11 | 2020-05-04 13:11 | Yes | -5 |  |  | 2020-05-17 17:58 | [5 empty] | 2020-05-17 21:04 | Yes | -1 | 1204-Owner-v | 2020-05-21 07:08
VD-9001-740C-MOD-271 | 3 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-09 | 2020-05-03 08:26 | 2020-05-03 08:27 | Yes | -6 |  |  |  | 2020-05-04 15:10 |  |  |  |  | 2020-05-04 15:10 | Yes | -13 | 1204-Owner-v | 2020-05-12 12:16
VD-9001-307A1-DWG-153 | 1 | RUN DOWN TANK GA DRAWING FOR UNIT P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-10 | 2020-05-21 13:47 | 2020-05-21 13:47 | Yes | 11 |  |  |  | 2020-06-08 10:03 |  |  |  |  | 2020-06-08 10:03 | Yes | 4
VD-9001-104(1-S)-DSH-017 | 2 | Air Compressor thermodynamical data sheets (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-04 |  |  | No | 46 | [9 empty] | No | 0
VD-9001-104(1-S)-PCU-001 | 2 | Performance maps For Air Compressor Package (C-6101 & C-6102) | PR-104(1) | HATCO CO. | 2020-05-04 |  |  | No | 46 | [9 empty] | No | 0
VD-9001-260-DSH-001 | 2 | Process Data Sheet E-1007 | HM-260 | ABAN AIR COOLER. | 2020-05-10 | 2020-05-05 09:15 | 2020-05-05 09:16 | Yes | -5 |  |  | 2020-05-09 18:51 | [5 empty] | 2020-05-09 18:51 | Yes | -10 | 1204-Owner-v | 2020-06-01 10:38
VD-9001-260-DSH-003 | 2 | Process Data Sheet E-3008 | HM-260 | ABAN AIR COOLER. | 2020-05-10 | 2020-05-05 09:20 | 2020-05-05 09:23 | Yes | -5 |  |  | 2020-05-09 18:53 | [5 empty] | 2020-05-09 18:53 | Yes | -10
VD-9001-260-DSH-004 | 2 | Process Data Sheet E-3009 | HM-260 | ABAN AIR COOLER. | 2020-05-10 | 2020-05-05 09:21 | 2020-05-05 09:23 | Yes | -5 |  |  | 2020-05-09 18:55 | [5 empty] | 2020-05-09 18:55 | Yes | -10 | 1204-Owner-v | 2020-06-01 10:29
VD-9001-104(1-K)-PID-005 | 1 | ASU P&ID - INSTRUMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:33 | 2020-05-30 14:33 | Yes | 23 |  |  |  | 2020-06-14 11:40 |  |  |  |  | 2020-06-14 11:40 | Yes | 1 | 1204-Owner-v | 2020-06-15 15:18
VD-9001-260-DSH-005 | 2 | Process Data Sheet E-4001A/B | HM-260 | ABAN AIR COOLER. | 2020-05-10 | 2020-05-05 09:26 | 2020-05-05 09:29 | Yes | -5 |  |  | 2020-05-09 18:56 | [5 empty] | 2020-05-09 18:56 | Yes | -10 | 1204-Owner-v | 2020-06-01 10:35
VD-9001-104(1-K)-PID-004 | 1 | ASU P&ID - PIPELINE, EQUIPMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-05-07 | 2020-05-30 14:32 | 2020-05-30 14:32 | Yes | 23 |  |  |  | 2020-06-14 11:34 |  |  |  |  | 2020-06-14 11:34 | Yes | 1 | 1204-Owner-v | 2020-06-15 15:20
VD-9001-740C-PCJ-004 | 1 | PACKING & MARKING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-10 | 2020-05-13 09:49 | 2020-05-13 09:49 | Yes | 3 | [9 empty] | No | 23 | 1204-Owner-v | 2020-05-26 08:17
VD-9001-740C-ITP-271 | 3 | inspection and test plan (ITP) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-10 | 2020-05-04 12:18 | 2020-05-04 12:18 | Yes | -6 |  |  |  | 2020-05-16 07:53 |  |  |  |  | 2020-05-16 07:53 | Yes | -2
VD-9001-740C-PCJ-002 | 2 | WELDING SEQUENCE PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-10 | 2020-05-04 12:18 | 2020-05-04 12:18 | Yes | -6 |  |  | 2020-05-16 07:50 | [5 empty] | 2020-05-16 07:50 | Yes | -2 | 1204-Owner-v | 2020-05-26 08:15
VD-9001-307A1-PID-007 | 2 | THERMAL SYSTEM DIAGRAM FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-10 | 2020-06-04 01:41 | 2020-06-04 01:41 | Yes | 25 | [9 empty] | No | 1
VD-9001-104(1-S)-LST-018 | 1 | Electrical consumer list– Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-10 |  |  | No | 40 | [9 empty] | No | 0
VD-9001-260-LIS-001 | 1 | Sub Vendor List | HM-260 | ABAN AIR COOLER. | 2020-05-11 | 2020-06-15 12:29 | 2020-06-15 12:30 | Yes | 35 | [9 empty] | No | -10
VD-9001-740C-WPS-001 | 2 | WELDING BOOK (WPS,PQR,WELDING MAP,WPQ) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-04 09:22 | 2020-05-05 14:16 | 2020-05-05 14:16 | Yes | 1 |  |  | 2020-05-10 08:31 | [5 empty] | 2020-05-10 18:43 | Yes | -9 | 1204-Owner-v | 2020-06-17 07:57
VD-9001-251-DWG-027 | 6 | FOUNDATION PLAN DRAWING | HM-251 | KT – Kinetics Technology SpA | 2020-05-04 12:21 | 2020-05-04 12:23 | 2020-05-04 12:23 | Yes | 0 |  |  | 2020-05-04 12:42 | [5 empty] | 2020-05-04 12:42 | Yes | -14 | 1204-Owner-v | 2020-05-12 11:41
VD-9001-251-LST-005 | 1 | Instruments List | HM-251 | KT – Kinetics Technology SpA | 2020-05-04 12:36 | 2020-05-04 12:37 | 2020-05-04 12:41 | Yes | 0 |  |  |  | 2020-06-14 12:35 |  |  |  |  | 2020-06-14 12:35 | Yes | 27
VD-9001-104(1-S)-DIA-003 | 1 | Control oil diagram – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-07 |  |  | No | 43 | [9 empty] | No | 0
VD-9001-213B1-CAL-006 | 0 | Roof Structure Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-06 11:58 | 2020-05-06 11:58 | Yes | 1 |  |  |  |  | 2020-05-19 14:36 |  |  |  | 2020-05-19 21:00 | Yes | -1
VD-9001-213B1-CAL-007 | 0 | Nozzle load Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-04 13:45 | 2020-05-04 13:45 | Yes | -1 |  |  |  |  | 2020-05-31 10:57 |  |  |  | 2020-05-31 20:01 | Yes | 13
VD-9001-213B1-CAL-008 | 0 | Roof Structure Lifting Calculation for Erection for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-12 10:36 | 2020-05-12 10:37 | Yes | 7 |  |  |  |  | 2020-05-19 14:37 |  |  |  | 2020-05-19 21:00 | Yes | -7
VD-9001-213B1-CAL-009 | 0 | Pipe Support Calculation For TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-04 13:47 | 2020-05-04 13:47 | Yes | -1 |  |  |  |  | 2020-06-07 13:31 |  |  |  | 2020-06-07 20:02 | Yes | 20
VD-9001-213B1-DWG-013 | 0 | Fixed roof Orientation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-20 09:01 | 2020-05-20 09:01 | Yes | 15 |  |  |  |  | 2020-05-20 12:35 |  |  |  | 2020-05-20 20:58 | Yes | -14
VD-9001-213B1-DWG-016 | 0 | Anchor Chair for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-05 15:58 | 2020-05-05 15:58 | Yes | 0 |  |  | 2020-05-09 18:31 | [5 empty] | 2020-05-09 21:04 | Yes | -10 | 1204-Owner-v | 2020-05-09 12:31
VD-9001-213B1-DWG-017 | 0 | Earth Lug for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-04 13:56 | 2020-05-04 13:56 | Yes | -1 |  |  | 2020-05-09 18:32 | [5 empty] | 2020-05-09 21:05 | Yes | -9 | 1204-Owner-v | 2020-06-03 09:32
VD-9001-213B1-DWG-018 | 0 | Name Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-06 09:11 | 2020-05-06 09:11 | Yes | 1 |  |  |  |  | 2020-05-17 17:51 |  |  |  | 2020-05-17 21:03 | Yes | -3
VD-9001-213B1-DWG-025 | 0 | Instrument Cable Support for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-05 | 2020-05-05 11:22 | 2020-05-05 11:24 | Yes | 0 |  |  | 2020-05-16 10:10 | [5 empty] | 2020-05-16 20:58 | Yes | -3 | 1204-Owner-v | 2020-06-03 09:31
VD-9001-740C-RPT-271 | 3 | Reports For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-11 | 2020-05-09 12:32 | 2020-05-09 12:39 | Yes | -2 |  |  |  | 2020-05-10 08:35 |  |  |  |  | 2020-05-10 14:50 | Yes | -13 | 1204-Owner-v | 2020-05-18 14:27
VD-9001-740C-MOD-271 | 4 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-11 | 2020-05-09 12:17 | 2020-05-09 12:17 | Yes | -2 |  |  |  | 2020-05-12 19:13 |  |  |  |  | 2020-05-12 19:13 | Yes | -11 | 1204-Owner-v | 2020-05-12 12:14
VD-9001-307B-DWG-082 | 1 | MOTOR OUTLINE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:42 | 2020-06-02 10:45 | Yes | 15 |  |  |  | 2020-06-08 14:38 |  |  |  |  | 2020-06-08 20:07 | Yes | -8
VD-9001-307B-DWG-083 | 1 | MOTOR OUTLINE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:42 | 2020-06-02 10:45 | Yes | 15 |  |  |  | 2020-06-08 14:31 |  |  |  |  | 2020-06-08 20:06 | Yes | -8
VD-9001-307B-DWG-084 | 1 | MOTOR OUTLINE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:45 | 2020-06-02 10:49 | Yes | 15 |  |  |  | 2020-06-08 10:10 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-307B-DWG-085 | 1 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 14:23 |  |  |  |  | 2020-06-08 20:05 | Yes | -8
VD-9001-307B-DWG-086 | 1 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 14:07 |  |  |  |  | 2020-06-08 20:05 | Yes | -8
VD-9001-307B-DWG-087 | 1 | MOTOR OUTLINE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 14:01 |  |  |  |  | 2020-06-08 20:04 | Yes | -8
VD-9001-307B-DWG-088 | 1 | MOTOR OUTLINE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:46 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 13:44 |  |  |  |  | 2020-06-08 20:04 | Yes | -8
VD-9001-307B-DWG-089 | 1 | MOTOR OUTLINE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 13:39 |  |  |  |  | 2020-06-08 20:03 | Yes | -8
VD-9001-307B-DWG-090 | 1 | MOTOR OUTLINE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 13:29 |  |  |  |  | 2020-06-08 20:02 | Yes | -8
VD-9001-307B-DWG-091 | 1 | MOTOR OUTLINE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:46 | Yes | 15 |  |  |  | 2020-06-08 12:17 |  |  |  |  | 2020-06-08 20:02 | Yes | -8
VD-9001-307B-DWG-092 | 1 | MOTOR OUTLINE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:43 | 2020-06-02 10:47 | Yes | 15 |  |  |  | 2020-06-08 12:02 |  |  |  |  | 2020-06-08 20:02 | Yes | -8
VD-9001-307B-DWG-093 | 1 | MOTOR OUTLINE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:47 | 2020-06-02 10:47 | Yes | 15 |  |  |  | 2020-06-08 11:54 |  |  |  |  | 2020-06-08 20:02 | Yes | -8
VD-9001-307B-DWG-094 | 1 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:44 | 2020-06-02 10:47 | Yes | 15 |  |  |  | 2020-06-08 11:43 |  |  |  |  | 2020-06-08 20:02 | Yes | -8
VD-9001-307B-DWG-095 | 1 | MOTOR OUTLINE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:44 | 2020-06-02 10:47 | Yes | 15 |  |  |  | 2020-06-08 11:31 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-307B-DWG-096 | 1 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:47 | 2020-06-02 10:47 | Yes | 15 |  |  |  | 2020-06-08 11:02 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-307B-DWG-097 | 1 | MOTOR OUTLINE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:48 | 2020-06-02 10:48 | Yes | 15 |  |  |  | 2020-06-08 10:55 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-213B1-DWG-011 | 1 | Bottom Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-18 20:58 | 2020-05-05 15:56 | 2020-05-05 15:56 | Yes | -13 |  |  | 2020-05-06 12:13 | [5 empty] | 2020-05-06 20:59 | Yes | -13 | 1204-Owner-v | 2020-05-10 09:58
VD-9001-307B-DWG-098 | 1 | MOTOR OUTLINE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:44 | 2020-06-02 10:48 | Yes | 15 |  |  |  | 2020-06-08 10:30 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-307B-DWG-099 | 1 | MOTOR OUTLINE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-18 20:58 | 2020-06-02 10:44 | 2020-06-02 10:48 | Yes | 15 |  |  |  | 2020-06-08 10:22 |  |  |  |  | 2020-06-08 20:01 | Yes | -8
VD-9001-201B-PCJ-013 | 1 | PACKING, MARKING & SHIPPING PROCEDURE (4134/PP) | PV-201B | Brembana & Rolle S.p.A. | 2020-05-18 20:58 | 2020-05-12 11:18 | 2020-05-12 11:20 | Yes | -6 |  |  |  | 2020-06-10 12:52 |  |  |  |  | 2020-06-10 20:00 | Yes | 15
VD-9001-104(1-K)-PID-009 | 1 | ASU P&ID - PRE-COOLING SYSTEM, AIR COOLING TOWER, COOLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-05-19 | 2020-05-30 14:36 | 2020-05-30 14:36 | Yes | 11 |  |  |  | 2020-06-15 12:52 |  |  |  |  | 2020-06-15 12:52 | Yes | 2
VD-9001-104(1-K)-PID-010 | 1 | ASU P&ID - PRE-COOLING SYSTEM, WATER COOLING TOWER, CHILLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-05-19 | 2020-05-30 14:37 | 2020-05-30 14:37 | Yes | 11 |  |  |  | 2020-06-15 13:07 |  |  |  |  | 2020-06-15 13:07 | Yes | 2
VD-9001-104(1-K)-PID-011 | 1 | ASU P&ID - PURIFICATION SYSTEM ADSORBER | PR-104(1) | HATCO CO. | 2020-05-19 | 2020-05-30 14:37 | 2020-05-30 14:37 | Yes | 11 |  |  |  | 2020-06-15 15:37 |  |  |  |  | 2020-06-15 15:37 | Yes | 2
VD-9001-104(1-K)-PID-012 | 1 | ASU P&ID - PURIFICATION SYSTEM STEAM HEATER | PR-104(1) | HATCO CO. | 2020-05-19 | 2020-05-30 14:38 | 2020-05-30 14:38 | Yes | 11 |  |  |  | 2020-06-16 12:27 |  |  |  |  | 2020-06-16 12:27 | Yes | 3
VD-9001-104(1-K)-PID-013 | 1 | ASU P&ID - PURIFICATION TEMP. DECREASED, PRESSURE REDUCER | PR-104(1) | HATCO CO. | 2020-05-19 | 2020-05-30 14:38 | 2020-05-30 14:38 | Yes | 11 |  |  |  | 2020-06-16 12:55 |  |  |  |  | 2020-06-16 12:55 | Yes | 3
VD-9001-740D-PCJ-001 | 0 | QUALITY CONTROL PLAN | ST-740D | PETRO ADAK IRAN | 2020-07-05 | 2020-05-18 15:23 | 2020-05-18 15:23 | Yes | -48 |  |  |  | 2020-05-26 07:50 |  |  |  |  | 2020-05-26 20:58 | Yes | -6
VD-9001-740D-PCJ-002 | 0 | WELDING SPECIFICATION PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-PCJ-003 | 0 | PAINTING PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-PCJ-004 | 0 | LIQUID PENETRENT TEST PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 | 2020-05-18 15:30 | 2020-05-18 15:30 | Yes | -48 |  |  | 2020-05-26 07:54 | [5 empty] | 2020-05-26 20:58 | Yes | -6 | 1204-Owner-v | 2020-06-08 10:52
VD-9001-740D-PCJ-005 | 0 | ULTRASONIC INSPECTION PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 | 2020-05-18 15:40 | 2020-05-18 15:43 | Yes | -48 |  |  | 2020-05-26 07:55 | [5 empty] | 2020-05-26 20:59 | Yes | -6
VD-9001-740D-PCJ-006 | 0 | WELDING SEQUENCE PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-PCJ-007 | 0 | PACKING AND MARKING PROCEDURE | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-FDB-001 | 0 | FINAL DATA BOOK | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-INX-001 | 0 | FINAL DATA BOOK INDEX | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-TEM-759 | 0 | TEKLA MODEL FOR TEMPLATE | ST-740D | PETRO ADAK IRAN | 2020-07-05 | 2020-05-09 12:29 | 2020-05-09 12:29 | Yes | -57 |  |  |  |  | 2020-05-16 10:19 |  |  |  | 2020-05-16 10:19 | Yes | -7
VD-9001-740D-GAD-00184 | 0 | GA DRAWINGS FOR PIPERACK ZONE 13 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-MOD-00184 | 0 | TEKLA MODEL FOR PIPERACK ZONE 13 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-RPT-00184 | 0 | TEKLA REPORTS FOR PIPERACK ZONE 13 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SAD-00184 | 0 | ASSEMBLY DRAWINGS FOR PIPERACK ZONE 13 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SPD-00184 | 0 | SINGLE PART DRAWINGS FOR PIPERACK ZONE 13 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-GAD-00193 | 0 | GA DRAWINGS FOR PIPERACK ZONE 16 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-MOD-00193 | 0 | TEKLA MODEL FOR PIPERACK ZONE 16 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-RPT-00193 | 0 | TEKLA REPORTS FOR PIPERACK ZONE 16 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SAD-00193 | 0 | ASSEMBLY DRAWINGS FOR PIPERACK ZONE 16 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SPD-00193 | 0 | SINGLE PART DRAWINGS FOR PIPERACK ZONE 16 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-GAD-00078 | 0 | GA DRAWINGS FOR PIPERACK ZONE 12 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-MOD-00078 | 0 | TEKLA MODEL FOR PIPERACK ZONE 12 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-RPT-00078 | 0 | TEKLA REPORTS FOR PIPERACK ZONE 12 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SAD-00078 | 0 | ASSEMBLY DRAWINGS FOR PIPERACK ZONE 12 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-SPD-00078 | 0 | SINGLE PART DRAWINGS FOR PIPERACK ZONE 12 | ST-740D | PETRO ADAK IRAN | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-740D-GAD-30322 | 0 | GA DRAWINGS FOR STRUCTURE D | ST-740D | PETRO ADAK IRAN | 2020-10-05 | 2020-06-09 11:13 | 2020-06-09 11:13 | Yes | -118 | [9 empty] | No | -4
VD-9001-740D-MOD-30322 | 0 | TEKLA MODEL FOR STRUCTURE D | ST-740D | PETRO ADAK IRAN | 2020-10-05 | 2020-06-09 11:01 | 2020-06-09 11:14 | Yes | -118 | [9 empty] | No | -4
VD-9001-740D-RPT-30322 | 0 | TEKLA REPORTS FOR STRUCTURE D | ST-740D | PETRO ADAK IRAN | 2020-10-05 | 2020-06-09 11:02 | 2020-06-09 11:14 | Yes | -118 | [9 empty] | No | -4
VD-9001-740D-SAD-30322 | 0 | ASSEMBLY DRAWINGS FOR STRUCTURE D | ST-740D | PETRO ADAK IRAN | 2020-10-05 |  |  | No | -108 | [9 empty] | No | 0
VD-9001-740D-SPD-30322 | 0 | SINGLE PART DRAWINGS FOR STRUCTURE D | ST-740D | PETRO ADAK IRAN | 2020-10-05 |  |  | No | -108 | [9 empty] | No | 0
VD-9001-740D-GAD-10133 | 0 | GA DRAWINGS FOR STRUCTURE Q | ST-740D | PETRO ADAK IRAN | 2020-09-05 |  |  | No | -78 | [9 empty] | No | 0
VD-9001-740D-MOD-10133 | 0 | TEKLA MODEL FOR STRUCTURE Q | ST-740D | PETRO ADAK IRAN | 2020-09-05 |  |  | No | -78 | [9 empty] | No | 0
VD-9001-740D-RPT-10133 | 0 | TEKLA REPORTS FOR STRUCTURE Q | ST-740D | PETRO ADAK IRAN | 2020-09-05 |  |  | No | -78 | [9 empty] | No | 0
VD-9001-740D-SAD-10133 | 0 | ASSEMBLY DRAWINGS FOR STRUCTURE Q | ST-740D | PETRO ADAK IRAN | 2020-09-05 |  |  | No | -78 | [9 empty] | No | 0
VD-9001-740D-SPD-10133 | 0 | SINGLE PART DRAWINGS FOR STRUCTURE Q | ST-740D | PETRO ADAK IRAN | 2020-09-05 |  |  | No | -78 | [9 empty] | No | 0
VD-9001-104(1-S)-GAD-002 | 1 | General arrangement Drawing For Air Compressor Package (C-6101 , C-6102 ) | PR-104(1) | HATCO CO. | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-104(1-S)-CAL-004 | 1 | Foundation load calculation For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-307A1-DWG-002 | 2 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(MOTOR DRIVEN) P2002B | MC-307A1 | Deep Blue Pump Co. | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-307A1-DWG-001 | 2 | PUMP GA DRAWING FOR CONVERTER BW CIRCULATION PUMP(STEAM TURBINE DRIVEN) P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-307A1-DWG-009 | 2 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(STEAM TURBINE DRIVEN) P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-DWG-010 | 2 | PUMP GA DRAWING FOR COOLING WATER SUPPLY PUMPS(MOTOR DRIVEN) P6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-DWG-004 | 2 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(MOTOR DRIVEN) P2003B | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-DWG-003 | 2 | PUMP GA DRAWING FOR FIRST SATURATOR PUMP(STEAM TURBINE DRIVEN) P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-DSH-006 | 3 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 | 2020-05-16 09:47 | 2020-05-16 09:48 | Yes | -4 |  |  |  |  | 2020-05-26 09:09 |  |  |  | 2020-05-26 09:09 | Yes | -4 | 1204-Owner-v | 2020-06-15 13:33
VD-9001-307A1-DWG-011 | 1 | PUMP GA DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-DWG-147 | 1 | LUBE OIL COOLER DRAWING FOR P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 | 2020-05-13 11:46 | 2020-05-13 11:46 | Yes | -7 |  |  | 2020-05-27 09:41 | [5 empty] | 2020-05-27 09:41 | Yes | 0
VD-9001-201A-PCJ-061 | 3 | PAINTING PROCEDURE | PV-201A | FATEH SANAT KIMIA | 2020-05-13 | 2020-05-18 10:50 | 2020-05-18 10:50 | Yes | 5 |  |  | 2020-06-18 12:34 | [5 empty] | 2020-06-18 12:34 | Yes | 17
VD-9001-307B-PCJ-005 | 1 | SURFACE PREPARATION AND PAINTING PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-20 20:58 | 2020-05-27 12:32 | 2020-05-27 12:32 | Yes | 7 |  |  | 2020-06-08 09:14 | [5 empty] | 2020-06-08 20:01 | Yes | -2
VD-9001-104(1-K)-PID-032 | 1 | ASU P&ID -PRODUCT INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-05-20 20:58 | 2020-05-31 08:42 | 2020-05-31 08:42 | Yes | 11 |  |  |  | 2020-06-15 09:56 |  |  |  |  | 2020-06-15 09:56 | Yes | 1
VD-9001-213B1-DWG-010 | 2 | Shell Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-20 20:58 | 2020-05-10 09:35 | 2020-05-10 09:35 | Yes | -10 |  |  | 2020-05-14 12:04 | [5 empty] | 2020-05-14 21:01 | Yes | -10 | 1204-Owner-v | 2020-05-18 14:28
VD-9001-213B1-DWG-012 | 1 | Fixed Roof Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-20 20:58 | 2020-05-12 09:23 |  | No | 30 | [9 empty] | No | 0 | 1204-Owner-v | 2020-05-18 14:33
VD-9001-307A1-PID-013 | 2 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-21 |  |  | No | 29 | [9 empty] | No | 0
VD-9001-307A1-PID-014 | 2 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-21 |  |  | No | 29 | [9 empty] | No | 0
VD-9001-307A1-PID-008 | 2 | THERMAL SYSTEM DIAGRAM FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-21 | 2020-06-04 01:41 | 2020-06-04 01:41 | Yes | 14 | [9 empty] | No | 1
VD-9001-307A1-DSH-001 | 4 | PUMP DATASHEET WITH CURVE FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-16 | 2020-05-16 09:47 | 2020-05-16 09:47 | Yes | 0 |  |  | 2020-05-27 10:44 | [5 empty] | 2020-05-27 10:44 | Yes | -3 | 1204-Owner-v | 2020-06-06 09:20
VD-9001-307A1-DSH-002 | 4 | PUMP DATASHEET WITH CURVE FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-16 | 2020-05-16 09:47 | 2020-05-16 09:47 | Yes | 0 |  |  | 2020-05-27 10:48 | [5 empty] | 2020-05-27 10:48 | Yes | -3 | 1204-Owner-v | 2020-06-15 13:32
VD-9001-307A1-DSH-004 | 4 | PUMP DATASHEET WITH CURVE FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-05-16 | 2020-05-16 09:47 | 2020-05-16 09:48 | Yes | 0 |  |  | 2020-05-27 11:07 | [5 empty] | 2020-05-27 11:07 | Yes | -3 | 1204-Owner-v | 2020-06-15 13:33
VD-9001-307B-PCJ-016 | 0 | INSPECTION AND SHOP TEST PROCEDURE FOR MOTOR | MC-307B | Deep Blue Pump Co. | 2020-05-10 | 2020-05-09 15:13 | 2020-05-09 15:13 | Yes | -1 |  |  | 2020-05-23 15:33 | [5 empty] | 2020-05-23 20:58 | Yes | 0
VD-9001-601-ARP-037 | 0 | System configuration including system key codes and software allocation | IN-601 | Novin Danesh Ayandeh | 2020-08-26 |  |  | No | -68 | [9 empty] | No | 0
VD-9001-601-ARP-038 | 0 | Logging and report formats | IN-601 | Novin Danesh Ayandeh | 2020-08-27 |  |  | No | -69 | [9 empty] | No | 0
VD-9001-601-SPC-039 | 0 | All software tech. descriptions / All software operational terms and user guides | IN-601 | Novin Danesh Ayandeh | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-601-ARP-040 | 0 | A fault finding / trouble shooting narrative for the complete system | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-CAL-041 | 0 | Calculation of overall system MTBF/availability/reliability including the failure mode and analysis for ESD system | IN-601 | Novin Danesh Ayandeh | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-601-LST-042 | 0 | Modbus Lists | IN-601 | Novin Danesh Ayandeh | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-601-MPR-043 | 0 | Physical Progress Report (monthly) | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-SCH-044 | 0 | Engineering, Procurement, Manufacturing and Test Schedule | IN-601 | Novin Danesh Ayandeh | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-601-LST-051 | 0 | FCS Material Take Off (MTO) | IN-601 | Novin Danesh Ayandeh | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-601-CAL-052 | 0 | FCS Power Consumption And Heat Dissipation Calculation | IN-601 | Novin Danesh Ayandeh | 2020-08-03 |  |  | No | -45 | [9 empty] | No | 0
VD-9001-601-DWG-053 | 0 | FCS Cabinets Arrangement | IN-601 | Novin Danesh Ayandeh | 2020-10-05 |  |  | No | -108 | [9 empty] | No | 0
VD-9001-601-DWG-054 | 0 | FCS Cabinets Overview | IN-601 | Novin Danesh Ayandeh | 2020-07-27 |  |  | No | -38 | [9 empty] | No | 0
VD-9001-601-LST-055 | 0 | FCS I/O Assignment | IN-601 | Novin Danesh Ayandeh | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-601-DIG-056 | 0 | FCS Circuit Wiring Diagram | IN-601 | Novin Danesh Ayandeh | 2020-11-11 |  |  | No | -145 | [9 empty] | No | 0
VD-9001-601-LST-057 | 0 | FCS Loop wiring data file (Excel) | IN-601 | Novin Danesh Ayandeh | 2020-11-16 |  |  | No | -150 | [9 empty] | No | 0
VD-9001-601-LST-058 | 0 | FCS Termination Diagram & Cable Schedule | IN-601 | Novin Danesh Ayandeh | 2020-11-18 |  |  | No | -152 | [9 empty] | No | 0
VD-9001-601-SDC-059 | 0 | FCS Faceplate Pages | IN-601 | Novin Danesh Ayandeh | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-601-SDC-060 | 0 | FCS HMI Pages | IN-601 | Novin Danesh Ayandeh | 2020-08-19 |  |  | No | -61 | [9 empty] | No | 0
VD-9001-601-SDC-061 | 0 | FCS Logic Diagram Printout | IN-601 | Novin Danesh Ayandeh | 2020-11-18 |  |  | No | -152 | [9 empty] | No | 0
VD-9001-601-LST-101 | 0 | FCS Substation Remote IO Material Take Off (MTO) | IN-601 | Novin Danesh Ayandeh | 2020-05-18 |  |  | No | 32 | [9 empty] | No | 0
VD-9001-601-CAL-102 | 0 | FCS Substation Remote IO Power Consumption And Heat Dissipation Calculation | IN-601 | Novin Danesh Ayandeh | 2020-08-03 |  |  | No | -45 | [9 empty] | No | 0
VD-9001-601-DWG-103 | 0 | FCS Substation Remote IO Cabinets Arrangement | IN-601 | Novin Danesh Ayandeh | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-601-DWG-104 | 0 | FCS Substation Remote IO Cabinets Overview | IN-601 | Novin Danesh Ayandeh | 2020-07-27 |  |  | No | -38 | [9 empty] | No | 0
VD-9001-601-LST-105 | 0 | FCS Substation Remote IO I/O Assignment | IN-601 | Novin Danesh Ayandeh | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-601-DIG-106 | 0 | FCS Substation Remote IO Circuit Wiring Diagram | IN-601 | Novin Danesh Ayandeh | 2020-11-25 |  |  | No | -159 | [9 empty] | No | 0
VD-9001-601-LST-107 | 0 | FCS Substation Remote IO Loop wiring data file (Excel) | IN-601 | Novin Danesh Ayandeh | 2020-11-30 |  |  | No | -164 | [9 empty] | No | 0
VD-9001-601-LST-108 | 0 | FCS Substation Remote IO Termination Diagram & Cable Schedule | IN-601 | Novin Danesh Ayandeh | 2020-12-02 |  |  | No | -166 | [9 empty] | No | 0
VD-9001-601-SDC-109 | 0 | FCS Substation Remote IO Faceplate Pages | IN-601 | Novin Danesh Ayandeh | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-601-SDC-110 | 0 | FCS Substation Remote IO HMI Pages | IN-601 | Novin Danesh Ayandeh | 2020-08-19 |  |  | No | -61 | [9 empty] | No | 0
VD-9001-601-SDC-111 | 0 | FCS Substation Remote IO Logic Diagram Printout | IN-601 | Novin Danesh Ayandeh | 2020-12-02 |  |  | No | -166 | [9 empty] | No | 0
VD-9001-601-LST-151 | 0 | ESD Material Take Off (MTO) | IN-601 | Novin Danesh Ayandeh | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-601-CAL-152 | 0 | ESD Power Consumption And Heat Dissipation Calculation | IN-601 | Novin Danesh Ayandeh | 2020-08-05 |  |  | No | -47 | [9 empty] | No | 0
VD-9001-601-DWG-153 | 0 | ESD Cabinets Arrangement | IN-601 | Novin Danesh Ayandeh | 2020-10-05 |  |  | No | -108 | [9 empty] | No | 0
VD-9001-601-DWG-154 | 0 | ESD Cabinets Overview | IN-601 | Novin Danesh Ayandeh | 2020-08-01 |  |  | No | -43 | [9 empty] | No | 0
VD-9001-601-LST-155 | 0 | ESD I/O Assignment | IN-601 | Novin Danesh Ayandeh | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-601-DIG-156 | 0 | ESD Circuit Wiring Diagram | IN-601 | Novin Danesh Ayandeh | 2020-11-29 |  |  | No | -163 | [9 empty] | No | 0
VD-9001-601-LST-157 | 0 | ESD Loop wiring data file (Excel) | IN-601 | Novin Danesh Ayandeh | 2020-12-02 |  |  | No | -166 | [9 empty] | No | 0
VD-9001-601-LST-158 | 0 | ESD Termination Diagram & Cable Schedule | IN-601 | Novin Danesh Ayandeh | 2020-12-06 |  |  | No | -170 | [9 empty] | No | 0
VD-9001-601-SDC-159 | 0 | ESD Faceplate Pages | IN-601 | Novin Danesh Ayandeh | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-601-SDC-160 | 0 | ESD HMI Pages | IN-601 | Novin Danesh Ayandeh | 2020-08-19 |  |  | No | -61 | [9 empty] | No | 0
VD-9001-601-SDC-161 | 0 | ESD Logic Diagram Printout | IN-601 | Novin Danesh Ayandeh | 2020-08-19 |  |  | No | -61 | [9 empty] | No | 0
VD-9001-601-LST-201 | 0 | PDP Material Take Off (MTO) | IN-601 | Novin Danesh Ayandeh | 2020-05-27 |  |  | No | 23 | [9 empty] | No | 0
VD-9001-601-CAL-202 | 0 | PDP Power Consumption And Heat Dissipation Calculation | IN-601 | Novin Danesh Ayandeh | 2020-08-05 |  |  | No | -47 | [9 empty] | No | 0
VD-9001-601-DWG-203 | 0 | PDP Cabinets Arrangement | IN-601 | Novin Danesh Ayandeh | 2020-10-13 |  |  | No | -116 | [9 empty] | No | 0
VD-9001-601-DWG-204 | 0 | PDP Cabinets Overview | IN-601 | Novin Danesh Ayandeh | 2020-08-01 |  |  | No | -43 | [9 empty] | No | 0
VD-9001-601-DIG-205 | 0 | PDP Circuit Wiring Diagram | IN-601 | Novin Danesh Ayandeh | 2020-10-28 |  |  | No | -131 | [9 empty] | No | 0
VD-9001-601-LST-206 | 0 | ESD Consoles Material Take Off (MTO) | IN-601 | Novin Danesh Ayandeh | 2020-12-30 |  |  | No | -194 | [9 empty] | No | 0
VD-9001-601-CAL-207 | 0 | ESD Consoles Power Consumption And Heat Dissipation Calculation | IN-601 | Novin Danesh Ayandeh | 2021-01-06 |  |  | No | -201 | [9 empty] | No | 0
VD-9001-601-DWG-208 | 0 | ESD Consoles Arrangement | IN-601 | Novin Danesh Ayandeh | 2020-12-30 |  |  | No | -194 | [9 empty] | No | 0
VD-9001-601-DWG-209 | 0 | ESD Consoles Overview | IN-601 | Novin Danesh Ayandeh | 2020-12-20 |  |  | No | -184 | [9 empty] | No | 0
VD-9001-601-DIG-210 | 0 | ESD Consoles Wiring Diagram | IN-601 | Novin Danesh Ayandeh | 2021-01-04 |  |  | No | -199 | [9 empty] | No | 0
VD-9001-601-INX-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE (VDIS) | IN-601 | Novin Danesh Ayandeh | 2020-05-06 |  |  | No | 44 | [9 empty] | No | 0
VD-9001-601-ITP-002 | 0 | Inspection Test Plan (ITP) | IN-601 | Novin Danesh Ayandeh | 2020-07-18 | 2020-05-29 19:20 | 2020-05-29 19:20 | Yes | -50 | [9 empty] | No | 7
VD-9001-601-QCP-003 | 0 | Quality Control Plan (QCP) | IN-601 | Novin Danesh Ayandeh | 2020-07-19 | 2020-06-01 13:06 | 2020-06-01 13:06 | Yes | -48 | [9 empty] | No | 4
VD-9001-601-DWG-004 | 0 | System description , system block diagram and interconnections | IN-601 | Novin Danesh Ayandeh | 2020-08-31 |  |  | No | -73 | [9 empty] | No | 0
VD-9001-601-SPE-005 | 0 | Functional design specification for hardware of FCS | IN-601 | Novin Danesh Ayandeh | 2020-07-01 |  |  | No | -12 | [9 empty] | No | 0
VD-9001-601-SPE-006 | 0 | Functional design specification for hardware of FCS Remote IO | IN-601 | Novin Danesh Ayandeh | 2020-07-08 |  |  | No | -19 | [9 empty] | No | 0
VD-9001-601-SPE-007 | 0 | Functional design specification for hardware of ESD | IN-601 | Novin Danesh Ayandeh | 2020-07-15 |  |  | No | -26 | [9 empty] | No | 0
VD-9001-601-SPE-008 | 0 | Components specification sheets / filled-in data sheets with part No.’s | IN-601 | Novin Danesh Ayandeh | 2021-01-02 |  |  | No | -197 | [9 empty] | No | 0
VD-9001-601-CAT-009 | 0 | Catalogues and Brochures | IN-601 | Novin Danesh Ayandeh | 2021-01-06 |  |  | No | -201 | [9 empty] | No | 0
VD-9001-601-DWG-010 | 0 | System Earthing Diagram | IN-601 | Novin Danesh Ayandeh | 2020-07-21 | 2020-06-07 11:03 | 2020-06-07 11:03 | Yes | -44 | [9 empty] | No | -2
VD-9001-601-DWG-011 | 0 | Operation Desk Overview | IN-601 | Novin Danesh Ayandeh | 2020-12-21 |  |  | No | -185 | [9 empty] | No | 0
VD-9001-601-PCJ-012 | 0 | FAT Procedure | IN-601 | Novin Danesh Ayandeh | 2020-12-22 | 2020-05-29 19:16 | 2020-05-29 19:16 | Yes | -207 | [9 empty] | No | 7
VD-9001-601-PCJ-013 | 0 | SAT Procedure | IN-601 | Novin Danesh Ayandeh | 2020-12-23 |  |  | No | -187 | [9 empty] | No | 0
VD-9001-601-RPT-014 | 0 | FAT Report | IN-601 | Novin Danesh Ayandeh | 2020-12-23 |  |  | No | -187 | [9 empty] | No | 0
VD-9001-601-DIG-015 | 0 | System Typical Wiring & Loop Diagram | IN-601 | Novin Danesh Ayandeh | 2020-08-22 |  |  | No | -64 | [9 empty] | No | 0
VD-9001-601-LST-016 | 0 | List of sub-Vendor’s and main suppliers | IN-601 | Novin Danesh Ayandeh | 2020-12-24 |  |  | No | -188 | [9 empty] | No | 0
VD-9001-601-LST-017 | 0 | List of the special tools (if any) needed to operate the system | IN-601 | Novin Danesh Ayandeh | 2020-12-25 |  |  | No | -189 | [9 empty] | No | 0
VD-9001-601-LST-018 | 0 | List of Spare Parts for Erection, Commissioning and Start-up | IN-601 | Novin Danesh Ayandeh | 2020-12-28 |  |  | No | -192 | [9 empty] | No | 0
VD-9001-601-LST-019 | 0 | List of Spare Parts for 2 Years Operation | IN-601 | Novin Danesh Ayandeh | 2020-12-29 |  |  | No | -193 | [9 empty] | No | 0
VD-9001-601-PCJ-020 | 0 | Erection procedures, list of consumables for erection, commissioning and start-up | IN-601 | Novin Danesh Ayandeh | 2021-01-04 |  |  | No | -199 | [9 empty] | No | 0
VD-9001-601-LST-021 | 0 | Filled-out SPLIR form | IN-601 | Novin Danesh Ayandeh | 2021-01-18 |  |  | No | -213 | [9 empty] | No | 0
VD-9001-601-LST-022 | 0 | Packing Lists and Release Note | IN-601 | Novin Danesh Ayandeh | 2021-01-10 |  |  | No | -205 | [9 empty] | No | 0
VD-9001-601-PCJ-023 | 0 | Painting Procedure | IN-601 | Novin Danesh Ayandeh | 2021-01-06 |  |  | No | -201 | [9 empty] | No | 0
VD-9001-601-MNL-024 | 0 | Installation , Operation & Maintenance Manual | IN-601 | Novin Danesh Ayandeh | 2021-01-13 |  |  | No | -208 | [9 empty] | No | 0
VD-9001-601-DWG-025 | 0 | Dimensional layout for the control and auxiliary rooms | IN-601 | Novin Danesh Ayandeh | 2021-01-21 |  |  | No | -216 | [9 empty] | No | 0
VD-9001-601-DIG-026 | 0 | Power distribution diagram | IN-601 | Novin Danesh Ayandeh | 2020-12-16 |  |  | No | -180 | [9 empty] | No | 0
VD-9001-601-DCI-027 | 0 | Functional Saftey Documents | IN-601 | Novin Danesh Ayandeh | 2021-01-24 |  |  | No | -219 | [9 empty] | No | 0
VD-9001-601-RPT-028 | 0 | Test records (Vendor’s quality control) for ESD | IN-601 | Novin Danesh Ayandeh | 2021-01-25 |  |  | No | -220 | [9 empty] | No | 0
VD-9001-601-LST-029 | 0 | List of references where the offered system is at least 2 years in operation for ESD | IN-601 | Novin Danesh Ayandeh | 2021-01-27 |  |  | No | -222 | [9 empty] | No | 0
VD-9001-601-DWG-030 | 0 | Name plate drawing | IN-601 | Novin Danesh Ayandeh | 2020-07-27 |  |  | No | -38 | [9 empty] | No | 0
VD-9001-601-INX-031 | 0 | As built | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-SPC-032 | 0 | Functional design specification for software of FCS | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-SPC-033 | 0 | Functional design specification for software of FCS Remote IO | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-SPC-034 | 0 | Functional design specification for software of ESD | IN-601 | Novin Danesh Ayandeh | 2020-06-03 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-601-ARP-035 | 0 | System configuration, parameterization and settings | IN-601 | Novin Danesh Ayandeh | 2020-09-09 |  |  | No | -82 | [9 empty] | No | 0
VD-9001-601-ARP-036 | 0 | System communications and networking capabilities and specifications | IN-601 | Novin Danesh Ayandeh | 2020-09-16 |  |  | No | -89 | [9 empty] | No | 0
VD-9001-307B-ITP-001 | 1 | PUMP TEST & INSPECTION PLAN | MC-307B | Deep Blue Pump Co. | 2020-05-23 20:58 | 2020-05-27 13:00 | 2020-05-27 13:00 | Yes | 4 |  |  |  | 2020-06-15 15:05 |  |  |  |  | 2020-06-15 20:02 | Yes | 5
VD-9001-307B-PCJ-001 | 1 | FACTORY PERFORMANCE TEST PROCEDURE | MC-307B | Deep Blue Pump Co. | 2020-05-23 20:58 | 2020-05-27 13:00 | 2020-05-27 13:00 | Yes | 4 |  |  | 2020-06-13 13:32 | [5 empty] | 2020-06-13 20:02 | Yes | 3
VD-9001-104(1-K)-PID-021 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, UPPER COLUMN | PR-104(1) | HATCO CO. | 2020-05-23 20:58 | 2020-05-30 14:50 | 2020-05-30 14:50 | Yes | 7 | [9 empty] | No | 6
VD-9001-104(1-K)-PID-020 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LOWER COLUMN | PR-104(1) | HATCO CO. | 2020-05-23 20:58 | 2020-05-30 14:48 | 2020-05-30 14:48 | Yes | 7 |  |  |  | 2020-06-18 16:26 |  |  |  |  | 2020-06-18 16:26 | Yes | 5
VD-9001-104(1-S)-PCJ-002 | 1 | Painting specification – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-23 20:58 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-019 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, SUB-COOLER | PR-104(1) | HATCO CO. | 2020-05-23 20:58 | 2020-05-30 14:49 | 2020-05-30 14:50 | Yes | 7 |  |  |  | 2020-06-18 14:04 |  |  |  |  | 2020-06-18 14:04 | Yes | 5
VD-9001-251B1-ITP-001 | 1 | INSPECTION & TEST PLAN | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-12 |  |  | No | 38 | [9 empty] | No | 0
VD-9001-251E-DWG-004 | 2 | Assembly Drawing for DWG No.:F-OF16240 | HM-251E | Iran Industrial Vibrations Co. | 2020-05-12 | 2020-05-12 10:03 | 2020-05-12 10:05 | Yes | 0 |  |  |  | 2020-05-20 10:36 |  |  |  |  | 2020-05-20 10:36 | Yes | -6
VD-9001-740C-SAD-271 | 1 | Assembly drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-17 | 2020-06-09 17:41 | 2020-06-10 06:54 | Yes | 24 | [6 empty] | 2020-05-31 09:47 | 2020-05-31 09:47 |  | Yes | -23 | 1204-Owner-v | 2020-05-19 18:09
VD-9001-740C-RPT-271 | 4 | Reports For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-17 | 2020-06-10 08:12 | 2020-06-10 08:13 | Yes | 24 | [6 empty] | 2020-05-27 10:22 | 2020-05-27 10:22 |  | Yes | -28 | 1204-Owner-v | 2020-05-26 08:17
VD-9001-307A1-PID-011 | 2 | THERMAL SYSTEM DIAGRAM FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 | 2020-06-04 01:41 | 2020-06-04 01:41 | Yes | 15 | [9 empty] | No | 1
VD-9001-307A1-PID-010 | 2 | THERMAL SYSTEM DIAGRAM FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 | 2020-06-04 01:41 | 2020-06-04 01:41 | Yes | 15 | [9 empty] | No | 1
VD-9001-104(1)-LST-004 | 1 | TIE-IN Point List and Location | PR-104(1) | HATCO CO. | 2020-05-18 | 2020-06-01 18:39 | 2020-06-01 18:39 | Yes | 14 |  |  |  | 2020-06-08 11:57 |  |  |  |  | 2020-06-08 11:57 | Yes | -7 | 1204-Owner-v | 2020-06-02 09:45
VD-9001-104(1-K)-PID-007 | 1 | ASU P&ID - AIR FILTERING & COMPRESSION LINE1 | PR-104(1) | HATCO CO. | 2020-05-16 | 2020-05-30 14:36 | 2020-05-30 14:36 | Yes | 14 |  |  |  | 2020-06-14 14:31 |  |  |  |  | 2020-06-14 14:31 | Yes | 1
VD-9001-104(1-K)-PID-008 | 1 | ASU P&ID - AIR FILTERING & COMPRESSION LINE2 | PR-104(1) | HATCO CO. | 2020-05-16 | 2020-05-30 14:36 | 2020-05-30 14:36 | Yes | 14 |  |  |  | 2020-06-14 14:46 |  |  |  |  | 2020-06-14 14:46 | Yes | 1
VD-9001-301-1-PCU-101 | 1 | REC Compressor (C-2002) Performance Curve | MC-301-1 | NEW JCM | 2020-05-26 08:25 | 2020-06-08 12:05 | 2020-06-08 12:07 | Yes | 13 | [9 empty] | No | -3
VD-9001-301-1-PCU-201 | 1 | Syn Gas Compressor (C-2001) Performance Curve | MC-301-1 | NEW JCM | 2020-05-26 08:28 | 2020-06-08 12:05 | 2020-06-08 12:07 | Yes | 13 | [9 empty] | No | -3
VD-9001-301-1-PCU-102 | 1 | REC Turbine (STC-2002) Expected Performance Curve | MC-301-1 | NEW JCM | 2020-05-26 08:32 | 2020-06-09 13:19 | 2020-06-09 13:20 | Yes | 14 |  |  | 2020-06-16 14:19 | [5 empty] | 2020-06-16 14:19 | Yes | -7
VD-9001-301-1-PCU-202 | 1 | Syn Gas Turbine (STC-2001) Expected Performance Curve | MC-301-1 | NEW JCM | 2020-05-26 08:35 | 2020-06-09 13:16 | 2020-06-09 13:19 | Yes | 14 |  |  | 2020-06-16 14:35 | [5 empty] | 2020-06-16 14:36 | Yes | -7
VD-9001-604-1-VLS-001 | 1 | Sub Vendor List | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-16 | 2020-05-13 15:10 | 2020-05-13 15:10 | Yes | -3 |  |  |  | 2020-05-13 15:49 |  |  |  |  | 2020-05-13 15:49 | Yes | -14
VD-9001-604-1-DIS-001 | 1 | Vendor Documents Index & Schedule | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-16 | 2020-05-14 09:40 | 2020-05-14 09:40 | Yes | -2 |  |  | 2020-05-19 17:02 | [5 empty] | 2020-05-19 17:02 | Yes | -9
VD-9001-251E-DWG-003 | 2 | Assembly Drawn for DWG No.:F-OF16230 | HM-251E | Iran Industrial Vibrations Co. | 2020-05-14 | 2020-05-13 13:09 | 2020-05-13 13:11 | Yes | -1 |  |  |  | 2020-05-19 17:47 |  |  |  |  | 2020-05-19 17:47 | Yes | -8
VD-9001-301-1-DSH-102 | 1 | REC Steam Turbine (STC-2002) Data Sheet | MC-301-1 | NEW JCM | 2020-05-26 13:21 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-301-1-DSH-202 | 1 | Syn Gas Steam Turbine (STC-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-05-26 13:51 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-301-1-DSH-101 | 1 | REC Compressor (C-2002) Data Sheet | MC-301-1 | NEW JCM | 2020-05-26 14:03 | 2020-06-16 12:15 | 2020-06-16 12:15 | Yes | 21 | [9 empty] | No | -11
VD-9001-307A1-PID-012 | 2 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-740C-MOD-271 | 5 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-19 | 2020-05-18 14:13 | 2020-05-18 14:14 | Yes | -1 |  |  |  | 2020-05-19 15:29 |  |  | 2020-05-17 15:21 | 2020-05-17 15:21 | 2020-05-19 15:29 | Yes | -13 | 1204-Owner-v | 2020-05-28 15:57
VD-9001-104(1)-LST-008 | 1 | Utility Consumption List | PR-104(1) | HATCO CO. | 2020-05-26 20:59 | 2020-06-08 10:08 | 2020-06-08 10:09 | Yes | 13 |  |  |  |  | 2020-06-13 12:07 |  |  |  | 2020-06-13 12:07 | Yes | -9
VD-9001-307A1-PID-015 | 1 | LUBE OIL SYSTEM P&I DIAGRAM FOR HP BOILER FEED WATER PUMP P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-307A1-PID-016 | 2 | LUBE OIL STATION P&I DRAWING FOR STEAM TURBINE P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-307A1-PID-017 | 2 | LUBE OIL SYSTEM P&I DIAGRAM FOR STEAM TURBINE P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-251B1-WPS-001 | 1 | WELDING PROCEDURE SPECIFICATION | HM-251B1 | Zarif Sanat Pishro Eng.co | 2020-05-16 |  |  | No | 34 | [9 empty] | No | 0
VD-9001-604-1-CAT-001 | 1 | Catalogue Data | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-16 | 2020-05-14 09:43 | 2020-05-14 09:42 | Yes | -2 |  |  |  |  | 2020-05-19 17:29 |  |  |  | 2020-05-19 17:29 | Yes | -9 | 1204-Owner-v | 2020-05-17 14:46
VD-9001-604-1-VLS-001 | 2 | Sub Vendor List | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-16 | 2020-05-14 09:40 | 2020-05-14 09:40 | Yes | -2 |  |  | 2020-05-19 16:55 | [5 empty] | 2020-05-19 16:55 | Yes | -9
VD-9001-307A1-PCJ-022 | 0 | HYDROTATIC TEST PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-06-14 16:40 | 2020-06-14 16:40 | Yes | 30 |  |  |  | 2020-06-15 09:26 |  |  |  |  | 2020-06-15 09:26 | Yes | -13
VD-9001-307A1-PCJ-023 | 0 | PACKING AND DELIVERY PROCEDURE(WOODEN CASE) FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-307A1-PCJ-024 | 0 | SURFACE PREPARATION AND PAINTING PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-05-13 16:37 | 2020-05-13 16:38 | Yes | -2 |  |  |  | 2020-05-27 11:44 |  |  |  |  | 2020-05-27 11:44 | Yes | 0
VD-9001-307A1-PCJ-025 | 0 | BALANCING TEST PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-05-13 16:38 | 2020-05-13 16:38 | Yes | -2 |  |  |  | 2020-05-26 11:48 |  |  |  |  | 2020-05-26 11:48 | Yes | -1
VD-9001-307A1-PCJ-026 | 0 | NDT PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-05-13 16:38 | 2020-05-13 16:38 | Yes | -2 |  |  |  | 2020-05-27 11:39 |  |  |  |  | 2020-05-27 11:39 | Yes | 0
VD-9001-307A1-PCJ-027 | 0 | HARDNESS TEST PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-05-13 16:38 | 2020-05-13 16:38 | Yes | -2 |  |  |  | 2020-05-27 11:30 |  |  |  |  | 2020-05-27 11:30 | Yes | 0
VD-9001-307A1-WPS-002 | 0 | WPS & PQR FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-15 | 2020-05-13 16:39 | 2020-05-13 16:39 | Yes | -2 |  |  | 2020-05-27 11:42 | [5 empty] | 2020-05-27 11:42 | Yes | 0
VD-9001-605-1-CAT-001 | 1 | Catalogue Data | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-16 | 2020-05-16 12:48 | 2020-05-16 12:48 | Yes | 0 | [9 empty] | No | 20 | 1204-Owner-v | 2020-05-19 10:54
VD-9001-301-1-DWG-202 | 1 | Syn Gas Compressor (C-2001) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-05-27 16:11 | 2020-06-06 09:18 | 2020-06-06 09:22 | Yes | 10 |  |  |  | 2020-06-10 12:58 |  |  |  |  | 2020-06-10 12:59 | Yes | -10
VD-9001-301-1-DWG-102 | 1 | REC Compressor (C-2002) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-05-27 16:27 | 2020-06-06 09:19 | 2020-06-06 09:21 | Yes | 10 | [9 empty] | No | -1
VD-9001-104(1-S)-DWG-003 | 1 | Foundation plan For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-605-1-VLS-001 | 1 | Sub Vendor List | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-17 | 2020-05-14 10:12 | 2020-05-14 10:12 | Yes | -3 |  |  | 2020-05-19 17:48 | [5 empty] | 2020-05-19 17:48 | Yes | -9 | 1204-Owner-v | 2020-05-16 09:06
VD-9001-605-1-DIS-001 | 1 | Vendor Documents Index & Schedule | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-17 | 2020-05-14 10:15 | 2020-05-14 10:15 | Yes | -3 |  |  | 2020-05-19 18:16 | [5 empty] | 2020-05-19 18:16 | Yes | -9 | 1204-Owner-v | 2020-05-16 09:05
VD-9001-104(1-K)-PID-022 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP LOX PUMP A | PR-104(1) | HATCO CO. | 2020-05-20 | 2020-05-30 14:50 | 2020-05-30 14:50 | Yes | 10 | [9 empty] | No | 6
VD-9001-301-1-DSH-201 | 1 | Syn Gas Compressor (C-2001) Data Sheet | MC-301-1 | NEW JCM | 2020-05-27 17:36 | 2020-06-16 12:15 | 2020-06-16 12:15 | Yes | 20 | [9 empty] | No | -11
VD-9001-104(1-S)-ITP-002 | 2 | Inspection and test plan – Steam Turbine (STC-6101 & STC-6102) | PR-104(1) | HATCO CO. | 2020-05-20 |  |  | No | 30 | [9 empty] | No | 0
VD-9001-301-1-DWG-201 | 1 | Syn Gas Compressor (C-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-05-27 18:13 | 2020-05-25 05:13 | 2020-05-25 05:51 | Yes | -2 |  |  |  | 2020-06-10 12:17 |  |  |  |  | 2020-06-10 12:29 | Yes | 2 | 1204-Owner-v | 2020-06-02 13:34
VD-9001-301-1-DWG-101 | 1 | REC Compressor (C-2002) Outline Drawing | MC-301-1 | NEW JCM | 2020-05-27 18:22 | 2020-06-06 08:53 | 2020-06-06 08:56 | Yes | 10 | [6 empty] | 2020-05-27 16:36 | 2020-05-27 16:36 |  | Yes | -24
VD-9001-301-1-DWG-103 | 1 | REC Steam Turbine (STC-2002) Outline Drawing | MC-301-1 | NEW JCM | 2020-05-28 09:44 | 2020-05-25 05:14 | 2020-05-25 05:51 | Yes | -3 |  |  |  | 2020-06-10 14:43 |  |  |  |  | 2020-06-10 14:44 | Yes | 2 | 1204-Owner-v | 2020-06-02 13:31
VD-9001-301-1-DWG-104 | 1 | REC Steam Turbine (STC-2002) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-05-28 09:47 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-301-1-DWG-203 | 1 | Syn Gas Steam Turbine (STC-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-05-28 09:50 | 2020-05-25 05:14 | 2020-05-25 05:52 | Yes | -3 |  |  |  | 2020-06-10 14:16 |  |  |  |  | 2020-06-10 14:16 | Yes | 2 | 1204-Owner-v | 2020-06-02 13:35
VD-9001-301-1-DWG-204 | 1 | Syn Gas Steam Turbine (STC-2001) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-05-28 09:52 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-301-1-PPL-101 | 1 | REC (C-2002) General Arrangement & Foundation Drawing | MC-301-1 | NEW JCM | 2020-05-28 11:39 | 2020-06-05 16:37 | 2020-06-05 16:42 | Yes | 8 | [9 empty] | No | 0
VD-9001-301-1-PPL-201 | 1 | Syn Gas (C-2001) General Arrangement & Foundation Drawing | MC-301-1 | NEW JCM | 2020-05-28 11:42 | 2020-06-05 16:38 | 2020-06-05 16:42 | Yes | 8 | [9 empty] | No | 0
VD-9001-307B-DSH-019 | 1 | MOTOR DATASHEET WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-28 20:58 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-307B-DSH-020 | 1 | MOTOR DATASHEET WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-28 20:58 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-307B-DSH-021 | 1 | MOTOR DATASHEET WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-28 20:58 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-307B-DSH-022 | 1 | MOTOR DATASHEET WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-023 | 1 | MOTOR DATASHEET WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-024 | 1 | MOTOR DATASHEET WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-025 | 1 | MOTOR DATASHEET WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-026 | 1 | MOTOR DATASHEET WITH CURVE FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-027 | 1 | MOTOR DATASHEET WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-029 | 1 | MOTOR DATASHEET WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-031 | 1 | MOTOR DATASHEET WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-030 | 1 | MOTOR DATASHEET WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-032 | 1 | MOTOR DATASHEET WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-033 | 1 | MOTOR DATASHEET WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-034 | 1 | MOTOR DATASHEET WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-035 | 1 | MOTOR DATASHEET WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-307B-DSH-036 | 1 | MOTOR DATASHEET WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-17 |  |  | No | 33 | [9 empty] | No | 0
VD-9001-740C-ITP-271 | 4 | inspection and test plan (ITP) For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-23 | 2020-05-17 13:53 | 2020-05-17 13:53 | Yes | -6 |  |  | 2020-05-23 18:11 | [5 empty] | 2020-05-23 18:11 | Yes | -8 | 1204-Owner-v | 2020-05-26 08:11
VD-9001-251E-DWG-002 | 2 | Assembly Drawing for DWG No.: F-OF16220 | HM-251E | Iran Industrial Vibrations Co. | 2020-05-18 | 2020-05-17 14:56 | 2020-05-17 15:03 | Yes | -1 |  |  | 2020-05-19 17:46 | [5 empty] | 2020-05-19 17:46 | Yes | -12
VD-9001-251C-ITP-012 | 1 | INSPECTION AND TEST PLAN FOR PIPE, FITTING WELDING AND COILS ASSEMBLYING | HM-251C | Fateh Sanat Kimia Co. | 2020-05-18 |  |  | No | 32 | [9 empty] | No | 0
VD-9001-307A1-PCJ-028 | 0 | REPAIR WELDING PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-17 | 2020-05-16 09:57 | 2020-05-16 09:58 | Yes | -1 |  |  |  | 2020-05-27 11:47 |  |  |  |  | 2020-05-27 11:47 | Yes | -3
VD-9001-740D-TEM-759 | 1 | TEKLA MODEL FOR TEMPLATE | ST-740D | PETRO ADAK IRAN | 2020-05-23 | 2020-05-26 12:02 | 2020-05-26 12:02 | Yes | 3 | [9 empty] | No | 10 | 1204-Owner-v | 2020-05-28 18:49
VD-9001-213B1-DWG-021 | 0 | Shell Manhole for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-17 | 2020-05-16 11:02 | 2020-05-16 11:03 | Yes | -1 |  |  |  | 2020-05-23 17:57 |  |  |  |  | 2020-05-23 21:01 | Yes | -7
VD-9001-213B1-DWG-022 | 0 | Roof Manhole for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-17 | 2020-05-16 11:06 | 2020-05-16 11:07 | Yes | -1 |  |  |  | 2020-05-23 17:57 |  |  |  |  | 2020-05-23 21:00 | Yes | -7
VD-9001-740C-PCJ-003 | 3 | PAINTING AND COATING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-23 | 2020-05-18 08:22 | 2020-05-18 08:24 | Yes | -5 |  |  |  | 2020-05-23 18:06 |  |  |  |  | 2020-05-23 18:06 | Yes | -9
VD-9001-307A1-DWG-018 | 1 | STEAM TURBINE CROSS SECTION DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-13 08:16 | 2020-06-13 08:16 | Yes | 18 | [9 empty] | No | -8
VD-9001-307A1-DWG-019 | 1 | STEAM TURBINE CROSS SECTION DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-13 08:15 | 2020-06-13 08:16 | Yes | 18 | [9 empty] | No | -8
VD-9001-307A1-DWG-020 | 1 | STEAM TURBINE CROSS SECTION DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-021 | 1 | STEAM TURBINE CROSS SECTION DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-13 08:15 | 2020-06-13 08:16 | Yes | 18 | [9 empty] | No | -8
VD-9001-307A1-DWG-022 | 1 | STEAM TURBINE CROSS SECTION DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-13 08:16 | 2020-06-13 08:16 | Yes | 18 | [9 empty] | No | -8
VD-9001-307A1-DWG-085 | 1 | STEAM TURBINE NAME PLATE DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-086 | 1 | STEAM TURBINE NAME PLATE DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-087 | 1 | STEAM TURBINE NAME PLATE DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-088 | 1 | STEAM TURBINE NAME PLATE DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-089 | 1 | STEAM TURBINE NAME PLATE DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-307A1-DWG-044 | 1 | MOTOR OUTLINE DRAWING FOR PM2002B | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-04 12:33 | 2020-06-04 12:33 | Yes | 9 | [9 empty] | No | 1
VD-9001-307A1-DWG-045 | 1 | MOTOR OUTLINE DRAWING FOR PM2003B | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-04 12:33 | 2020-06-04 12:33 | Yes | 9 | [9 empty] | No | 1
VD-9001-307A1-DWG-046 | 1 | MOTOR OUTLINE DRAWING FOR PM4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-04 12:33 | 2020-06-04 12:34 | Yes | 9 | [9 empty] | No | 1
VD-9001-307B-DSH-001 | 1 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-30 20:58 | 2020-06-11 12:19 | 2020-06-11 12:21 | Yes | 12 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:06
VD-9001-307B-DSH-006 | 1 | PUMP DATASHEET WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:24 | 2020-06-11 12:24 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:11
VD-9001-307B-DSH-005 | 1 | PUMP DATASHEET WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:23 | 2020-06-11 12:29 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:10
VD-9001-307B-DSH-002 | 1 | PUMP DATASHEET WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:19 | 2020-06-11 12:21 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:06
VD-9001-307B-DSH-003 | 1 | PUMP DATASHEET WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:20 | 2020-06-11 12:30 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:06
VD-9001-307B-DSH-004 | 1 | PUMP DATASHEET WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:22 | 2020-06-11 12:29 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:06
VD-9001-307B-DSH-008 | 1 | PUMP DATASHEET WITH CURVE FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:20 | 2020-06-11 12:25 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:19
VD-9001-307B-DSH-007 | 1 | PUMP DATASHEET WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:24 | 2020-06-11 12:24 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:11
VD-9001-307B-DSH-010 | 1 | PUMP DATASHEET WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-19 | 2020-06-11 12:20 | 2020-06-11 12:25 | Yes | 23 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:20
VD-9001-307A1-DSH-003 | 4 | PUMP DATASHEET WITH CURVE FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-05-17 14:25 | 2020-05-17 14:26 | 2020-05-17 14:26 | Yes | 0 |  |  | 2020-05-27 11:18 | [5 empty] | 2020-05-27 11:18 | Yes | -4 | 1204-Owner-v | 2020-06-15 13:32
VD-9001-307A1-DSH-005 | 4 | PUMP DATASHEET WITH CURVE FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-05-17 14:25 | 2020-05-17 14:26 | 2020-05-17 14:26 | Yes | 0 |  |  | 2020-05-27 11:25 | [5 empty] | 2020-05-27 11:25 | Yes | -4 | 1204-Owner-v | 2020-06-15 13:33
VD-9001-301-1-PID-205 | 1 | Syn Gas (C-2001) Machine Monitoring Diagram | MC-301-1 | NEW JCM | 2020-05-31 15:31 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-301-1-PID-105 | 1 | REC (C-2002) Machine Monitoring Diagram | MC-301-1 | NEW JCM | 2020-05-31 15:32 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-603-DIS-001 | 0 | Vendor Documents Index & Schedule (VDIS) | IN-603 | Sandroos Sanat | 2020-04-29 | 2020-06-02 13:20 | 2020-06-02 13:20 | Yes | 34 | [9 empty] | No | 3
VD-9001-603-LST-002 | 0 | List of Sub-Suppliers | IN-603 | Sandroos Sanat | 2020-05-09 | 2020-05-19 11:09 | 2020-05-19 11:12 | Yes | 10 | [9 empty] | No | 17
VD-9001-603-DSH-003 | 0 | Analyzer Data Sheet | IN-603 | Sandroos Sanat | 2020-05-12 | 2020-05-20 16:21 | 2020-05-20 16:22 | Yes | 8 |  |  |  |  | 2020-06-01 11:28 |  |  |  | 2020-06-01 11:28 | Yes | -2
VD-9001-603-MPR-005 | 0 | Monthly Progress Report | IN-603 | Sandroos Sanat | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-603-LST-006 | 0 | Utility & Electrical Power Consumption List | IN-603 | Sandroos Sanat | 2020-05-16 | 2020-05-30 14:08 | 2020-05-30 14:08 | Yes | 14 | [9 empty] | No | 6
VD-9001-603-CAL-007 | 0 | Calculation (HVAC,lag Time, Cooler Capacity) | IN-603 | Sandroos Sanat | 2020-05-19 | 2020-06-01 13:25 | 2020-06-01 13:25 | Yes | 13 | [9 empty] | No | 4
VD-9001-603-CAL-031 | 0 | Calculation sheet for calibration And career cylinders | IN-603 | Sandroos Sanat | 2020-05-19 | 2020-05-31 16:55 | 2020-05-31 16:57 | Yes | 12 | [9 empty] | No | 5
VD-9001-603-LST-008 | 0 | Tie-in Connection List | IN-603 | Sandroos Sanat | 2020-05-27 | 2020-06-02 17:03 | 2020-06-02 17:03 | Yes | 6 | [9 empty] | No | 3
VD-9001-603-DIG-009 | 0 | P&ID Drawing | IN-603 | Sandroos Sanat | 2020-05-27 | 2020-05-31 16:48 | 2020-05-31 16:50 | Yes | 4 | [9 empty] | No | 5
VD-9001-603-DWG-010 | 0 | Power Distribution Drawing | IN-603 | Sandroos Sanat | 2020-05-30 | 2020-06-02 17:00 | 2020-06-02 17:00 | Yes | 3 | [9 empty] | No | 3
VD-9001-603-DWG-011 | 0 | General Arrangement | IN-603 | Sandroos Sanat | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-603-DIG-012 | 0 | Signal & F&G Witing Diagram | IN-603 | Sandroos Sanat | 2020-06-06 | 2020-06-10 16:32 | 2020-06-10 16:32 | Yes | 4 | [9 empty] | No | -5
VD-9001-603-DIG-032 | 0 | Instrument cable interconnection, field Cabinets and sample handling system | IN-603 | Sandroos Sanat | 2020-06-13 | 2020-06-13 16:44 | 2020-06-13 16:45 | Yes | 0 | [9 empty] | No | -8
VD-9001-603-MTO-013 | 0 | Bill Of Material | IN-603 | Sandroos Sanat | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-603-DIG-014 | 0 | Cause and Effect | IN-603 | Sandroos Sanat | 2020-06-06 | 2020-06-09 17:28 | 2020-06-09 17:29 | Yes | 3 | [9 empty] | No | -4
VD-9001-603-DWG-015 | 0 | Sampling System Layout | IN-603 | Sandroos Sanat | 2020-06-02 | 2020-06-07 17:40 | 2020-06-07 17:41 | Yes | 5 | [9 empty] | No | -2
VD-9001-603-DWG-033 | 0 | Lab Sample Handling System layout drawing | IN-603 | Sandroos Sanat | 2020-06-10 | 2020-06-07 17:41 | 2020-06-07 17:42 | Yes | -3 | [9 empty] | No | -2
VD-9001-603-LST-016 | 0 | Commissioning & Spare Part List | IN-603 | Sandroos Sanat | 2020-06-07 |  |  | No | 12 | [9 empty] | No | 0
VD-9001-603-LST-017 | 0 | 2 Years Spare Part List | IN-603 | Sandroos Sanat | 2020-06-07 |  |  | No | 12 | [9 empty] | No | 0
VD-9001-603-LST-018 | 0 | Modbus List | IN-603 | Sandroos Sanat | 2020-06-07 | 2020-06-15 16:17 | 2020-06-15 16:23 | Yes | 8 | [9 empty] | No | -10
VD-9001-603-MNL-019 | 0 | Installation & operation manual of HVAC | IN-603 | Sandroos Sanat | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-603-PCJ-020 | 0 | Analyzer Calibration Procedure | IN-603 | Sandroos Sanat | 2020-06-29 |  |  | No | -10 | [9 empty] | No | 0
VD-9001-603-LST-021 | 0 | Calibration Cylinder List | IN-603 | Sandroos Sanat | 2020-06-06 | 2020-06-16 16:56 | 2020-06-16 16:56 | Yes | 10 | [9 empty] | No | -11
VD-9001-603-QCP-022 | 0 | Sandroos Quality Control Records | IN-603 | Sandroos Sanat | 2020-12-28 |  |  | No | -192 | [9 empty] | No | 0
VD-9001-603-ITP-023 | 0 | Inspection & Test Plan | IN-603 | Sandroos Sanat | 2020-05-07 | 2020-05-18 13:21 | 2020-05-18 13:23 | Yes | 11 |  |  |  | 2020-06-08 08:18 |  |  |  |  | 2020-06-08 08:18 | Yes | 7
VD-9001-603-PCJ-034 | 0 | FAT / SAT Procedures | IN-603 | Sandroos Sanat | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-603-MNL-024 | 0 | Quality Accurance Manual / Certificte | IN-603 | Sandroos Sanat | 2021-01-09 |  |  | No | -204 | [9 empty] | No | 0
VD-9001-603-PCJ-025 | 0 | Shipping & Packing Procedure | IN-603 | Sandroos Sanat | 2021-03-15 |  |  | No | -269 | [9 empty] | No | 0
VD-9001-603-SRN-026 | 0 | Release Note for Shipment | IN-603 | Sandroos Sanat | 2021-03-10 |  |  | No | -264 | [9 empty] | No | 0
VD-9001-603-CAT-027 | 0 | Catalogue | IN-603 | Sandroos Sanat | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-603-CER-028 | 0 | Certificates | IN-603 | Sandroos Sanat | 2020-12-28 |  |  | No | -192 | [9 empty] | No | 0
VD-9001-603-LST-029 | 0 | Packing List | IN-603 | Sandroos Sanat | 2021-04-09 |  |  | No | -294 | [9 empty] | No | 0
VD-9001-603-INX-030 | 0 | Final Data Book Index | IN-603 | Sandroos Sanat | 2021-04-14 |  |  | No | -299 | [9 empty] | No | 0
VD-9001-603-MDB-031 | 0 | Final Data Book | IN-603 | Sandroos Sanat | 2021-04-22 |  |  | No | -307 | [9 empty] | No | 0
VD-9001-307B-DSH-028 | 1 | MOTOR DATASHEET WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-307B-DSH-011 | 1 | PUMP DATASHEET WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:20 | 2020-06-11 12:25 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:21
VD-9001-307B-DSH-012 | 1 | PUMP DATASHEET WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:25 | 2020-06-11 12:28 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:22
VD-9001-307B-DSH-013 | 1 | PUMP DATASHEET WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:20 | 2020-06-11 12:25 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:23
VD-9001-307B-DSH-014 | 1 | PUMP DATASHEET WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:26 | 2020-06-11 12:26 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:23
VD-9001-307B-DSH-015 | 1 | PUMP DATASHEET WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:21 | 2020-06-11 12:26 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:26
VD-9001-307B-DSH-016 | 1 | PUMP DATASHEET WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:21 | 2020-06-11 12:27 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:25
VD-9001-307B-DSH-017 | 1 | PUMP DATASHEET WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:27 | 2020-06-11 12:27 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:26
VD-9001-307B-DSH-018 | 1 | PUMP DATASHEET WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-05-31 20:58 | 2020-06-11 12:21 | 2020-06-11 12:27 | Yes | 11 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:26
VD-9001-213B1-DWG-018 | 1 | Name Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-31 20:58 | 2020-05-18 08:35 | 2020-05-18 08:35 | Yes | -13 |  |  |  |  | 2020-05-18 12:56 |  |  |  | 2020-05-18 21:00 | Yes | -14
VD-9001-301-1-PID-208 | 1 | Syn Gas Compressor (C-2001) Control System Overview PID | MC-301-1 | NEW JCM | 2020-06-01 10:07 |  |  | No | 18 | [9 empty] | No | 0
VD-9001-604-1-DSH-001 | 1 | Instrument Data Sheets | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-23 | 2020-06-01 10:37 | 2020-06-01 10:37 | Yes | 9 | [9 empty] | No | 4
VD-9001-301-1-PID-201 | 1 | Synthesis Gas Compressor (C-2001) PID | MC-301-1 | NEW JCM | 2020-06-01 11:14 |  |  | No | 18 | [9 empty] | No | 0
VD-9001-301-1-PID-202 | 1 | Syn Gas Steam Turbine (STC-2001) PID | MC-301-1 | NEW JCM | 2020-06-01 15:10 |  |  | No | 18 | [9 empty] | No | 0
VD-9001-307A1-DWG-007 | 2 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMP(STEAM TURBINE DRIVEN) P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-307B-DWG-126 | 1 | PUMP NAME PLATE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 |  |  |  | 2020-06-16 08:51 |  |  |  |  | 2020-06-16 20:00 | Yes | -9
VD-9001-307B-DWG-127 | 1 | PUMP NAME PLATE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 |  |  |  | 2020-06-16 08:51 |  |  |  |  | 2020-06-16 20:00 | Yes | -9
VD-9001-307B-DWG-128 | 1 | PUMP NAME PLATE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 |  |  |  | 2020-06-16 08:53 |  |  |  |  | 2020-06-16 20:00 | Yes | -9
VD-9001-307B-DWG-129 | 1 | PUMP NAME PLATE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-130 | 1 | PUMP NAME PLATE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-131 | 1 | PUMP NAME PLATE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-132 | 1 | PUMP NAME PLATE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:21 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-133 | 1 | PUMP NAME PLATE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:22 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-134 | 1 | PUMP NAME PLATE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:22 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-135 | 1 | PUMP NAME PLATE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:24 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-136 | 1 | PUMP NAME PLATE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-137 | 1 | PUMP NAME PLATE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-138 | 1 | PUMP NAME PLATE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:25 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-139 | 1 | PUMP NAME PLATE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-140 | 1 | PUMP NAME PLATE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-141 | 1 | PUMP NAME PLATE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-142 | 1 | PUMP NAME PLATE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:23 | 2020-06-11 08:25 | Yes | 10 | [9 empty] | No | -6
VD-9001-307B-DWG-143 | 1 | PUMP NAME PLATE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-01 20:58 | 2020-06-11 08:26 | 2020-06-11 08:26 | Yes | 10 | [9 empty] | No | -6
VD-9001-213B1-ITP-030 | 2 | Inspection and Test Plan (ITP) | PV-213B1 | PAYSAZ Co. | 2020-06-01 20:58 | 2020-05-20 14:41 | 2020-05-20 14:41 | Yes | -12 |  |  |  |  | 2020-05-31 10:56 |  |  |  | 2020-05-31 20:01 | Yes | -3 | 1204-Owner-v | 2020-05-21 07:08
VD-9001-213B1-DWG-018 | 2 | Name Plate for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-01 20:58 | 2020-05-19 09:24 | 2020-05-19 09:24 | Yes | -13 |  |  | 2020-05-19 14:25 | [5 empty] | 2020-05-19 21:00 | Yes | -14 | 1204-Owner-v | 2020-06-03 09:29
VD-9001-201B-CAL-006 | 2 | REFRACTORY DOME SUPPORT CALCULATION ( 4134-0359/RDSC) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-01 | 2020-05-20 11:50 | 2020-05-20 11:52 | Yes | -12 |  |  | 2020-05-26 15:49 | [5 empty] | 2020-05-26 15:49 | Yes | -8
VD-9001-307A1-PCJ-002 | 1 | FACTORY MECHANICAL RUNNING TEST PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-29 | 2020-06-13 08:19 | 2020-06-13 08:19 | Yes | 15 | [9 empty] | No | -8
VD-9001-307A1-DWG-005 | 2 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMPS(STEAM TURBINE DRIVEN) P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307A1-DWG-008 | 2 | PUMP GA DRAWING FOR MP BOILER FEED WATER PUMPS(MOTOR DRIVEN) P4002BC | MC-307A1 | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-307A1-DWG-006 | 2 | PUMP GA DRAWING FOR HP BOILER FEED WATER PUMP(MOTOR DRIVEN) P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-05-29 |  |  | No | 21 | [9 empty] | No | 0
VD-9001-740C-MOD-271 | 6 | Tekla Model For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-26 | 2020-06-13 07:56 | 2020-06-13 07:56 | Yes | 18 | [6 empty] | 2020-05-31 10:07 | 2020-05-31 10:07 |  | Yes | -27 | 1204-Owner-v | 2020-05-26 08:12
VD-9001-254-INR-154 | 1 | TEST & INSPECTION MANUAL FOR F.D.FAN | HM-254 | AZAR AB | 2020-05-22 | 2020-05-20 12:03 | 2020-05-20 12:04 | Yes | -2 |  |  | 2020-06-02 13:17 | [5 empty] | 2020-06-02 13:17 | Yes | -1
VD-9001-257C-FDB-010 | 0 | MANUFACTURING DATA BOOK (0840/MDB) For E-2002B | HM-257C | Brembana & Rolle S.p.A. | 2020-05-20 | 2020-05-21 15:01 | 2020-05-21 15:04 | Yes | 1 |  |  |  | 2020-06-08 11:52 |  |  |  |  | 2020-06-08 11:52 | Yes | 4
VD-9001-301-1-PID-204 | 1 | Syn Gas Compressor (C-2001) Lube Oil System (Base) PID | MC-301-1 | NEW JCM | 2020-06-02 17:27 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-604-1-CAT-001 | 2 | Catalogue Data | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-23 | 2020-05-20 13:05 | 2020-05-20 13:05 | Yes | -3 |  |  | 2020-06-14 13:39 | [5 empty] | 2020-06-14 13:39 | Yes | 11
VD-9001-307A1-ITP-003 | 1 | INSPECTION & TEST PLAN FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-05-26 | 2020-06-08 15:19 | 2020-06-08 15:19 | Yes | 13 | [9 empty] | No | -3
VD-9001-251E-DWG-003 | 3 | Assembly Drawn for DWG No.:F-OF16230 | HM-251E | Iran Industrial Vibrations Co. | 2020-05-23 | 2020-05-26 16:30 | 2020-05-26 16:41 | Yes | 3 |  |  | 2020-05-28 09:47 | [5 empty] | 2020-05-28 09:47 | Yes | -12
VD-9001-301-1-PID-108 | 1 | REC Compressor (C-2002) Control System Overview PID | MC-301-1 | NEW JCM | 2020-06-02 18:07 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-605-1-PCJ-003 | 1 | Hydrostatic Shell Test Procedure | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-23 | 2020-05-21 10:25 | 2020-05-21 10:25 | Yes | -2 |  |  | 2020-06-14 11:14 | [5 empty] | 2020-06-14 11:15 | Yes | 10
VD-9001-605-1-PCJ-001 | 1 | NDE Procedure (PMI) | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-05-23 | 2020-05-21 10:25 | 2020-05-21 10:25 | Yes | -2 |  |  |  | 2020-06-14 11:20 |  |  |  |  | 2020-06-14 11:20 | Yes | 10
VD-9001-604-1-PCJ-003 | 1 | Hydrostatic Shell Test Procedure | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-24 | 2020-05-20 13:06 | 2020-05-20 13:06 | Yes | -4 |  |  | 2020-06-08 08:36 | [5 empty] | 2020-06-08 08:36 | Yes | 5
VD-9001-604-1-PCJ-001 | 1 | NDE Procedure (PMI) | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-05-24 | 2020-05-20 13:12 | 2020-05-20 13:12 | Yes | -4 |  |  |  | 2020-06-08 08:44 |  |  |  |  | 2020-06-08 08:44 | Yes | 5
VD-9001-301-1-PID-207 | 1 | Syn Gas Turbine (STC-2001) Governing System PID | MC-301-1 | NEW JCM | 2020-06-02 19:26 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-213B1-CAL-006 | 1 | Roof Structure Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-02 | 2020-05-23 11:40 | 2020-05-23 11:40 | Yes | -10 |  |  |  |  | 2020-05-31 14:33 |  |  |  | 2020-05-31 20:03 | Yes | -6
VD-9001-213B1-CAL-008 | 1 | Roof Structure Lifting Calculation for Erection for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-02 | 2020-05-23 11:41 | 2020-05-23 11:41 | Yes | -10 |  |  |  |  | 2020-05-31 14:32 |  |  |  | 2020-05-31 20:03 | Yes | -6
VD-9001-307B-PID-001 | 1 | PUMP P&I DRAWING WITH CURVE FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-307B-PID-002 | 1 | PUMP P&I DRAWING WITH CURVE FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-307B-PID-003 | 1 | PUMP P&I DRAWING WITH CURVE FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-251E-DWG-004 | 3 | Assembly Drawing for DWG No.:F-OF16240 | HM-251E | Iran Industrial Vibrations Co. | 2020-05-23 | 2020-05-26 16:43 | 2020-05-26 16:44 | Yes | 3 |  |  | 2020-05-28 09:47 | [5 empty] | 2020-05-28 09:47 | Yes | -12
VD-9001-301-1-PID-206 | 1 | Syn Gas Compressor (C-2001) Dry Gas Seal System PID | MC-301-1 | NEW JCM | 2020-06-03 11:34 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-213B1-DWG-014 | 0 | Roof Structure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-23 | 2020-06-07 14:13 | 2020-06-07 14:17 | Yes | 15 |  |  |  |  | 2020-06-14 09:22 |  |  |  | 2020-06-14 20:00 | Yes | -7
VD-9001-307B-LST-005 | 1 | SUB-VENDOR LIST | MC-307B | Deep Blue Pump Co. | 2020-06-03 20:58 | 2020-05-30 08:06 | 2020-05-30 08:06 | Yes | -4 |  |  |  | 2020-06-13 13:44 |  |  |  |  | 2020-06-13 20:02 | Yes | 0
VD-9001-213B1-DWG-013 | 1 | Fixed roof Orientation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-03 20:58 |  |  | No | 16 | [9 empty] | No | 0
VD-9001-201B-CAL-001 | 3 | MECHANICAL CALCULATION (4134-0359/MC) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-04 20:58 | 2020-05-29 19:09 | 2020-05-29 19:11 | Yes | -6 |  |  |  | 2020-06-07 13:48 |  |  |  |  | 2020-06-07 20:02 | Yes | -5
VD-9001-104(1-K)-PID-033 | 1 | ASU P&ID -PUBLIC UTILITIES RECYCLING WATER, DEMINERALIZED WATER | PR-104(1) | HATCO CO. | 2020-05-27 | 2020-05-31 08:43 | 2020-05-31 08:43 | Yes | 4 |  |  |  | 2020-06-14 15:55 |  |  |  |  | 2020-06-14 15:55 | Yes | 0
VD-9001-104(1-K)-PID-037 | 1 | ASU P&ID -UTILITIES INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-05-27 | 2020-05-31 08:50 | 2020-05-31 08:50 | Yes | 4 |  |  |  | 2020-06-15 11:14 |  |  |  |  | 2020-06-15 11:14 | Yes | 1
VD-9001-104(1-K)-PID-023 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP LOX PUMP B | PR-104(1) | HATCO CO. | 2020-05-27 | 2020-05-30 14:50 | 2020-05-30 14:50 | Yes | 3 | [9 empty] | No | 6
VD-9001-307A1-ITP-001 | 2 | INSPECTION & TEST PLAN FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-05-23 16:15 | 2020-06-08 15:15 | 2020-06-08 15:15 | Yes | 16 | [9 empty] | No | -3
VD-9001-104(1-K)-PID-017 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-05-27 | 2020-05-30 14:43 | 2020-05-30 14:43 | Yes | 3 |  |  |  | 2020-06-16 14:55 |  |  |  |  | 2020-06-16 14:55 | Yes | 3
VD-9001-104(1-K)-PID-018 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-05-27 | 2020-05-30 14:48 | 2020-05-30 14:48 | Yes | 3 |  |  |  | 2020-06-18 10:03 |  |  |  |  | 2020-06-18 10:03 | Yes | 5
VD-9001-740C-PCJ-003 | 4 | PAINTING AND COATING PROCEDURE For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-213B1-DWG-019 | 0 | Shell Nozzle for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-23 | 2020-05-26 07:59 | 2020-05-26 08:14 | Yes | 3 |  |  |  |  | 2020-05-31 10:59 |  |  |  | 2020-05-31 20:01 | Yes | -9
VD-9001-213B1-DWG-020 | 0 | Roof Nozzle for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-23 | 2020-05-26 08:28 | 2020-05-26 08:44 | Yes | 3 |  |  |  |  | 2020-05-31 11:02 |  |  |  | 2020-05-31 20:01 | Yes | -9
VD-9001-213B1-DWG-023 | 0 | Drain Sump for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-23 | 2020-05-26 10:13 | 2020-05-26 10:13 | Yes | 3 |  |  |  |  | 2020-05-31 11:04 |  |  |  | 2020-05-31 20:01 | Yes | -9
VD-9001-213B1-DWG-024 | 0 | Pipe Support for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-05-23 | 2020-05-26 11:02 | 2020-05-26 11:03 | Yes | 3 |  |  | 2020-06-11 09:13 | [5 empty] | 2020-06-11 20:00 | Yes | 2 | 1204-Owner-v | 2020-06-03 09:28
VD-9001-307B-PID-012 | 1 | PUMP P&I DRAWING WITH CURVE FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307B-PID-016 | 1 | PUMP P&I DRAWING WITH CURVE FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307B-PID-013 | 1 | PUMP P&I DRAWING WITH CURVE FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307B-PID-014 | 1 | PUMP P&I DRAWING WITH CURVE FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307B-PID-011 | 1 | PUMP P&I DRAWING WITH CURVE FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-213B1-DWG-022 | 1 | Roof Manhole for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-06 | 2020-05-26 09:07 | 2020-05-26 09:07 | Yes | -11 |  |  | 2020-05-31 11:05 | [5 empty] | 2020-05-31 20:01 | Yes | -9 | 1204-Owner-v | 2020-06-03 09:27
VD-9001-213B1-DWG-021 | 1 | Shell Manhole for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-06 | 2020-06-01 11:18 | 2020-06-01 11:19 | Yes | -5 |  |  | 2020-06-08 08:39 | [5 empty] | 2020-06-08 20:00 | Yes | -7 | 1204-Owner-v | 2020-06-03 09:27
VD-9001-104(1-M)-LST-008 | 1 | Electrical Load List | PR-104(1) | HATCO CO. | 2020-05-28 | 2020-06-08 10:32 | 2020-06-08 10:33 | Yes | 11 |  |  |  |  | 2020-06-14 11:22 |  |  |  | 2020-06-14 11:22 | Yes | -8
VD-9001-260-PRC-007 | 1 | Surface Preparation and Painting Procedure | HM-260 | ABAN AIR COOLER. | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-260-PRC-002 | 2 | NDT procedur | HM-260 | ABAN AIR COOLER. | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-260-PRC-003 | 1 | Hydrostatic Test Procedure | HM-260 | ABAN AIR COOLER. | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-307A1-DSH-006 | 4 | PUMP DATASHEET WITH CURVE FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307A1-PCJ-020 | 1 | FACTORY PERFORMANCE TEST PROCEDURE FOR LUBE OIL SYSTEM P2002A/P2003A/P4001AB/P4001C/P4002A/P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307A1-PCJ-025 | 1 | BALANCING TEST PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-13 08:21 | 2020-06-13 08:22 | Yes | 7 | [9 empty] | No | -8
VD-9001-307A1-PCJ-009 | 2 | SURFACE PREPARATION AND PAINTING PROCEDURE FOR PUMP AND STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-05-28 08:20 | 2020-05-28 08:20 | Yes | -9 |  |  | 2020-06-03 10:43 | [5 empty] | 2020-06-03 10:43 | Yes | -8
VD-9001-307A1-ITP-004 | 1 | INSPECTION & TEST PLAN FOR SURFACE CONDENSER | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-08 15:19 | 2020-06-08 15:19 | Yes | 2 | [9 empty] | No | -3
VD-9001-740D-PCJ-001 | 1 | QUALITY CONTROL PLAN | ST-740D | PETRO ADAK IRAN | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-740C-GAD-271 | 3 | General Arrangement Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-05-28 | 2020-06-13 08:04 | 2020-06-13 08:04 | Yes | 16 | [6 empty] | 2020-05-31 10:15 | 2020-05-31 10:15 |  | Yes | -27 | 1204-Owner-v | 2020-05-28 16:01
VD-9001-307A1-PCJ-012 | 2 | PWHT PROCEDURE FOR PUMP | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-04 01:40 | 2020-06-04 01:40 | Yes | -2 |  |  | 2020-06-09 18:52 | [5 empty] | 2020-06-09 18:53 | Yes | -9
VD-9001-307A1-PCJ-027 | 1 | HARDNESS TEST PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-13 08:22 | 2020-06-13 08:22 | Yes | 7 | [9 empty] | No | -8
VD-9001-307A1-PCJ-026 | 1 | NDT PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-13 08:22 | 2020-06-13 08:22 | Yes | 7 | [9 empty] | No | -8
VD-9001-307A1-PCJ-024 | 1 | SURFACE PREPARATION AND PAINTING PROCEDURE FOR STEAM SURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-13 08:21 | 2020-06-13 08:21 | Yes | 7 | [9 empty] | No | -8
VD-9001-307A1-PCJ-028 | 1 | REPAIR WELDING PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 | 2020-06-13 08:22 | 2020-06-13 08:22 | Yes | 7 | [9 empty] | No | -8
VD-9001-307A1-PCJ-018 | 1 | INSPECTION AND SHOP TEST PROCEDURE FOR MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-104(1)-PPL-010 | 2 | ASU PLOT PLAN | PR-104(1) | HATCO CO. | 2020-05-31 | 2020-06-01 18:43 | 2020-06-01 18:44 | Yes | 1 |  |  |  | 2020-06-16 11:31 |  |  |  |  | 2020-06-16 11:31 | Yes | 1 | 1204-Owner-v | 2020-06-02 09:34
VD-9001-104(1-K)-PID-014 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, EXPANDER SYSTEM | PR-104(1) | HATCO CO. | 2020-05-30 | 2020-05-30 14:39 | 2020-05-30 14:39 | Yes | 0 |  |  |  | 2020-06-16 14:02 |  |  |  |  | 2020-06-16 14:02 | Yes | 3
VD-9001-104(1-K)-PID-015 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, DETAILED DWG. A EXPANDER | PR-104(1) | HATCO CO. | 2020-05-30 | 2020-05-30 14:40 |  | No | 20 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-016 | 1 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, DETAILED DWG. B EXPANDER | PR-104(1) | HATCO CO. | 2020-05-30 | 2020-05-30 14:42 | 2020-05-30 14:42 | Yes | 0 | [9 empty] | No | 6
VD-9001-104(1)-DSH-011 | 1 | Process Data Sheets for Air Cooled Condenser (ACC) (AE-6101) | PR-104(1) | HATCO CO. | 2020-05-31 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-502-DWG-023 | 0 | Substation Layout Arrangement Drawing For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-05-25 |  |  | No | 25 | [9 empty] | No | 0
VD-9001-502-PCJ-024 | 0 | Test Procedure for AIS Panel | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-PCJ-025 | 0 | Test Procedure for Bus doct | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-ITP-026 | 0 | Test & Inspection Plan(ITP) for AIS Panel | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-ITP-027 | 0 | Test & Inspection Plan(ITP) for Bus duct | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-SRN-028 | 0 | Packing, Marking and Shipping Procedure for AIS Panel | EL-502 | IRAN TABLO | 2020-10-25 |  |  | No | -128 | [9 empty] | No | 0
VD-9001-502-PCJ-029 | 0 | Painting Procedure for AIS Panel | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-MNL-030 | 0 | Switchgear Installation / Operation / Maintenance Manual for AIS Panel & Bus duct | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-LST-031 | 0 | Packing List (Include in VDB) for AIS Panel & Bus duct | EL-502 | IRAN TABLO | 2020-12-25 |  |  | No | -189 | [9 empty] | No | 0
VD-9001-502-RPT-032 | 0 | Final Test Reports (Include in VDB) for AIS Panel | EL-502 | IRAN TABLO | 2020-12-25 |  |  | No | -189 | [9 empty] | No | 0
VD-9001-502-LST-033 | 0 | Sub Vendor List | EL-502 | IRAN TABLO | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-502-PCJ-034 | 0 | Storage Procedure for AIS Panel | EL-502 | IRAN TABLO | 2020-05-28 |  |  | No | 22 | [9 empty] | No | 0
VD-9001-502-WBS-035 | 0 | Work Breakdown Structure(WBS) | EL-502 | IRAN TABLO | 2020-05-23 | 2020-06-06 09:13 | 2020-06-06 09:13 | Yes | 14 | [9 empty] | No | -1 | 1204-Owner-v | 2020-06-14 16:59
VD-9001-502-CAT-036 | 0 | Catalogue | EL-502 | IRAN TABLO | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-502-SCH-037 | 0 | Time schedule of project | EL-502 | IRAN TABLO | 2020-06-01 |  |  | No | 18 | [9 empty] | No | 0
VD-9001-502-VDR-038 | 0 | Final Vendor Data Book Index | EL-502 | IRAN TABLO | 2020-12-25 |  |  | No | -189 | [9 empty] | No | 0
VD-9001-502-VDR-039 | 0 | Final Vendor Data Book | EL-502 | IRAN TABLO | 2020-12-30 |  |  | No | -194 | [9 empty] | No | 0
VD-9001-502-GAD-001 | 0 | General arrangement , front view & opening diagrams For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-05-21 | 2020-06-13 17:17 | 2020-06-13 17:17 | Yes | 23 |  |  |  | 2020-06-16 13:52 |  |  |  |  | 2020-06-16 20:02 | Yes | -11
VD-9001-502-SLD-002 | 0 | Single Line diagrams for MV switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-05-21 | 2020-06-13 17:28 | 2020-06-13 17:28 | Yes | 23 | [9 empty] | No | -8
VD-9001-502-DIG-003 | 0 | Schematic Diagrams of Incoming A&B , Buscoupler ,Measurement & Riser Feeders (Power & Controls) For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-502-DIG-004 | 0 | Schematic Diagrams of Outgoing Typical Circuit Drawings (Power & Controls) For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-502-DWG-005 | 0 | Name Plate Drawing For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-05-25 |  |  | No | 25 | [9 empty] | No | 0
VD-9001-502-DIG-006 | 0 | Internal Terminal Diagrams Of MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-10-25 |  |  | No | -128 | [9 empty] | No | 0
VD-9001-502-DIG-007 | 0 | Logic Diagrams Of MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-07 |  |  | No | 12 | [9 empty] | No | 0
VD-9001-502-DSH-008 | 0 | Filled Out Data Sheet For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-502-MAL-009 | 0 | Material List For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-502-DBS-010 | 0 | Basic Design For MV Bus Duct (US-B2A/B) | EL-502 | IRAN TABLO | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-502-ISO-011 | 0 | Isometric Drawing For MV Bus Duct (US-B2A/B) | EL-502 | IRAN TABLO | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-502-MAL-012 | 0 | Material List For MV Bus duct (US-B2A/B) | EL-502 | IRAN TABLO | 2020-07-05 |  |  | No | -16 | [9 empty] | No | 0
VD-9001-502-DBS-013 | 0 | Basic Design For MV Bus Duct (AS-B2A/B) | EL-502 | IRAN TABLO | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-502-ISO-014 | 0 | Isometric Drawing For MV Bus Duct (AS-B2A/B) | EL-502 | IRAN TABLO | 2020-06-28 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-502-MAL-015 | 0 | Material List For MV Bus duct (AS-B2A/B) | EL-502 | IRAN TABLO | 2020-07-12 |  |  | No | -23 | [9 empty] | No | 0
VD-9001-502-LST-016 | 0 | Comissioning & Start up For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-502-LST-017 | 0 | 2 Years Spare Parts List For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-502-LST-018 | 0 | Special Tools List For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-502-CAL-019 | 0 | Heat Dissipation Calculation For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-502-CAL-020 | 0 | AC and DC power consumption For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-502-CAL-021 | 0 | Fuse Sizing Calculation For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-502-CAL-022 | 0 | CT & PT Sizing Calculation For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-01 |  |  | No | 18 | [9 empty] | No | 0
VD-9001-104(1)-EQL-001 | 1 | Equipment List | PR-104(1) | HATCO CO. | 2020-05-31 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-104(1)-DSH-015 | 1 | Process Data Sheets for Water Cooled Condenser (WCC) (E-6104) | PR-104(1) | HATCO CO. | 2020-05-31 |  |  | No | 19 | [9 empty] | No | 0
VD-9001-605-1-DSH-001 | 1 | Instrument Data Sheets | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-301-1-PID-203 | 1 | Common Lube Oil System (C-2001) (Tank) PID | MC-301-1 | NEW JCM | 2020-06-11 09:19 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-PID-103 | 1 | REC Compressor (C-2002) Lube Oil System (Base) PID | MC-301-1 | NEW JCM | 2020-06-11 10:12 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-501-DIS-001 | 0 | VDIS | EL-501 | Paarsun Construction & Engineering Co. | 2020-05-18 |  |  | No | 32 | [9 empty] | No | 0
VD-9001-501-VLS-002 | 0 | Subvendor List | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 | 2020-06-11 09:52 | 2020-06-11 09:53 | Yes | 5 |  |  |  | 2020-06-14 11:50 |  |  |  |  | 2020-06-14 11:50 | Yes | -11
VD-9001-501-DSH-003 | 0 | Data sheet for CT | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-05-31 14:26 | 2020-05-31 14:26 | Yes | -2 |  |  |  | 2020-06-06 11:01 |  |  |  |  | 2020-06-06 11:02 | Yes | -8
VD-9001-501-DWG-004 | 0 | Outline for CT | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-05-31 14:28 | 2020-05-31 14:28 | Yes | -2 |  |  |  | 2020-06-06 11:03 |  |  |  |  | 2020-06-06 11:07 | Yes | -8
VD-9001-501-DSH-005 | 0 | Data Sheet For MS-NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-06-11 09:56 | 2020-06-11 09:56 | Yes | 9 |  |  |  | 2020-06-14 11:51 |  |  |  |  | 2020-06-14 11:51 | Yes | -11
VD-9001-501-DWG-006 | 0 | Outline Drawing For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-06-11 09:50 | 2020-06-11 09:50 | Yes | 9 |  |  |  | 2020-06-14 11:45 |  |  |  |  | 2020-06-14 11:45 | Yes | -11
VD-9001-501-DIG-007 | 0 | Connection Diagram For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-06-11 09:49 | 2020-06-11 09:49 | Yes | 9 |  |  |  | 2020-06-14 11:44 |  |  |  |  | 2020-06-14 11:44 | Yes | -11
VD-9001-501-DWG-008 | 0 | Name Plate For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 | 2020-06-11 09:48 | 2020-06-11 09:49 | Yes | 9 |  |  |  | 2020-06-14 11:40 |  |  |  |  | 2020-06-14 11:40 | Yes | -11
VD-9001-501-IPM-009 | 0 | ITP | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-08 | 2020-06-11 11:59 | 2020-06-11 11:59 | Yes | 3 | [9 empty] | No | -6
VD-9001-501-PCJ-010 | 0 | Test Procedure | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 | 2020-06-11 09:47 | 2020-06-11 09:47 | Yes | 5 |  |  |  | 2020-06-15 10:01 |  |  |  |  | 2020-06-15 10:01 | Yes | -10
VD-9001-501-RPT-011 | 0 | Final Test Report | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-501-CER-012 | 0 | Type Test Certificate | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-08 |  |  | No | 11 | [9 empty] | No | 0
VD-9001-501-CAT-013 | 0 | Catalogue for all Components | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-08 |  |  | No | 11 | [9 empty] | No | 0
VD-9001-501-MNL-014 | 0 | Installation, Operation & Maintenance Manual | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 | 2020-06-11 09:45 | 2020-06-11 09:46 | Yes | 5 |  |  |  | 2020-06-14 11:11 |  |  |  |  | 2020-06-14 11:11 | Yes | -11
VD-9001-501-WIN-015 | 0 | Storage Instruction | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 | 2020-06-11 09:37 | 2020-06-11 09:38 | Yes | 5 |  |  |  | 2020-06-14 11:09 |  |  |  |  | 2020-06-14 11:09 | Yes | -11
VD-9001-501-EQL-016 | 0 | Spare Part List and Interchangeability Record (SPIR form) | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-08 |  |  | No | 11 | [9 empty] | No | 0
VD-9001-501-MAL-017 | 0 | Part List | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-501-CAL-018 | 0 | Temperature Rise Calculation | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 | 2020-06-11 10:56 | 2020-06-11 10:56 | Yes | 5 |  |  |  |  | 2020-06-14 13:09 |  |  |  | 2020-06-14 13:09 | Yes | -11
VD-9001-501-MDB-019 | 0 | Final Vendor Data Book | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-501-INX-020 | 0 | Final Vendor Data Book Index | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-301-1-PID-106 | 1 | REC Compressor (C-2002) Dry Gas Seal System PID | MC-301-1 | NEW JCM | 2020-06-11 10:59 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-PID-107 | 1 | REC Turbine (STC-2002) Governing System PID | MC-301-1 | NEW JCM | 2020-06-11 11:34 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-PCJ-006 | 1 | HYDROTATIC TEST PROCEDURE FOR PUMP AND STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-260-CAL-001 | 1 | Mechanical Calculation Book E-1007 | HM-260 | ABAN AIR COOLER. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-260-CAL-004 | 1 | Mechanical Calculation Book E-3009 | HM-260 | ABAN AIR COOLER. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-202G-DWG-089 | 0 | Steel Structure Platform +18.965m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-090 | 0 | Steel Structure Platform +18.965m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-091 | 0 | Steel Structure Platform +18.965m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-092 | 0 | Steel Structure Platform +18.965m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-093 | 0 | Steel Structure Platform +18.965m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-094 | 0 | Steel Structure Platform +19.500m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-095 | 0 | Steel Structure Platform +19.500m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-096 | 0 | Steel Structure Platform +19.500m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-097 | 0 | Steel Structure Platform +19.500m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-098 | 0 | Steel Structure Platform +19.500m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-099 | 0 | Steel Structure Platform +19.500m TOS Part 6 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-100 | 0 | Steel Structure Platform +23.500m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-101 | 0 | Steel Structure Platform +23.500m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-102 | 0 | Steel Structure Platform +23.500m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-103 | 0 | Steel Structure Platform +23.500m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-104 | 0 | Steel Structure Platform +23.500m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-105 | 0 | Steel Structure Stair Tower Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-106 | 0 | Steel Structure Stair Tower Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-107 | 0 | Steel Structure Stair Tower Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-108 | 0 | Steel Structure Stair Tower Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-109 | 0 | Steel Structure Stair Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-110 | 0 | Steel Structure Stair Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-111 | 0 | Steel Structure Stair Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-112 | 0 | Steel Structure Stair Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-113 | 0 | Steel Structure Stair Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-114 | 0 | Steel Structure Stair Part 6 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-115 | 0 | Steel Structure Stair Part 7 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-116 | 0 | Steel Structure Stair Part 8 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-117 | 0 | Steel Structure Stair Part 9 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-118 | 0 | Steel Structure Stair Part 10 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-119 | 0 | Steel Structure Stair Part 11 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-120 | 0 | Steel Structure Stair Part 12 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-121 | 0 | Anchor Plates for PGB and SSH | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-ITP-001 | 0 | Inspection And Test Plan (ITP) | PV-202G | Sabz Ashian APadana Engineering Company | 2020-04-27 | 2020-06-02 12:06 | 2020-06-02 12:06 | Yes | 36 |  |  |  | 2020-06-11 11:26 |  |  |  |  | 2020-06-11 20:01 | Yes | -5
VD-9001-202G-WBK-001 | 0 | Welding Book | PV-202G | Sabz Ashian APadana Engineering Company | 2020-04-29 | 2020-06-02 12:33 | 2020-06-02 12:33 | Yes | 34 |  |  |  | 2020-06-07 10:21 |  |  |  |  | 2020-06-07 20:01 | Yes | -9
VD-9001-202G-PCJ-001 | 0 | NDT Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-04-30 | 2020-06-02 12:07 | 2020-06-02 12:08 | Yes | 33 |  |  |  | 2020-06-07 10:18 |  |  |  |  | 2020-06-07 20:01 | Yes | -9
VD-9001-202G-PCJ-002 | 0 | Dimensional check procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-02 12:12 | 2020-06-02 12:12 | Yes | 18 |  |  |  | 2020-06-07 10:16 |  |  |  |  | 2020-06-07 20:01 | Yes | -9
VD-9001-202G-PCJ-004 | 0 | Trial assembly procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-02 12:16 | 2020-06-02 12:16 | Yes | 18 | [9 empty] | No | 3
VD-9001-202G-PCJ-005 | 0 | Fabrication Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-02 12:17 | 2020-06-02 12:17 | Yes | 18 |  |  |  | 2020-06-11 11:41 |  |  |  |  | 2020-06-11 20:01 | Yes | -5
VD-9001-202G-MTO-001 | 0 | Field required paint MTO | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-202G-MDB-001 | 0 | Vendor Final Data Book Index | PV-202G | Sabz Ashian APadana Engineering Company | 2020-10-10 |  |  | No | -113 | [9 empty] | No | 0
VD-9001-202G-MDB-002 | 0 | Final Data Book | PV-202G | Sabz Ashian APadana Engineering Company | 2020-10-15 |  |  | No | -118 | [9 empty] | No | 0
VD-9001-202G-DWG-031 | 0 | Steel Structure Column axis 3/A - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-032 | 0 | Steel Structure Column axis 4/A - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-033 | 0 | Steel Structure Column axis 4/A - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-034 | 0 | Steel Structure Column axis 1/B - Stage I ±0.000m to +8.800m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-035 | 0 | Steel Structure Column axis 2/B - Stage I ±0.000m to +8.800m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-036 | 0 | Steel Structure Column axis 2/B - Stage I ±0.000m to +8.800m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-037 | 0 | Steel Structure Column axis 3/B - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-038 | 0 | Steel Structure Column axis 3/B - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-039 | 0 | Steel Structure Column axis 4/B - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-040 | 0 | Steel Structure Column axis 4/B - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-041 | 0 | Steel Structure Column axis 2/C - Stage I ±0.000m to +8.800m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-042 | 0 | Steel Structure Column axis 2/C - Stage I ±0.000m to +8.800m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-043 | 0 | Steel Structure Column axis 3/C - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-044 | 0 | Steel Structure Column axis 3/C - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-045 | 0 | Steel Structure Column axis 4/C - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-046 | 0 | Steel Structure Column axis 4/C - Stage I ±0.000m to +10.785m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-047 | 0 | Steel Structure Platform +7.150m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-048 | 0 | Steel Structure Platform +7.150m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-049 | 0 | Steel Structure Platform +7.150m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-050 | 0 | Steel Structure Platform +7.150m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-051 | 0 | Steel Structure Platform +7.150m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-052 | 0 | Steel Structure Platform +8.500m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-053 | 0 | Steel Structure Platform +8.500m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-054 | 0 | Steel Structure Platform +8.500m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-055 | 0 | Steel Structure Platform +8.500m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-056 | 0 | Steel Structure Platform +8.500m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-057 | 0 | Steel Structure Platform +8.500m TOS Part 6 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-058 | 0 | Steel Structure Platform +12.150m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-059 | 0 | Steel Structure Platform +12.150m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-060 | 0 | Steel Structure Platform +12.150m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-PCJ-003 | 0 | Blasting ,Painting Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-03 | 2020-06-02 12:11 | 2020-06-02 12:11 | Yes | 30 |  |  |  | 2020-06-11 12:14 |  |  |  |  | 2020-06-11 20:02 | Yes | -5
VD-9001-202G-SRN-001 | 0 | Packing, marking, Shipping and Release Note procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-04 | 2020-06-02 12:30 | 2020-06-02 12:30 | Yes | 29 |  |  |  | 2020-06-14 12:19 |  |  |  |  | 2020-06-14 20:02 | Yes | -2
VD-9001-202G-PCJ-006 | 0 | welding sequence procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-02 12:18 | 2020-06-08 14:34 | Yes | 24 | [9 empty] | No | 3
VD-9001-202G-PCJ-007 | 0 | Repair Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-02 12:28 | 2020-06-02 12:28 | Yes | 18 |  |  |  | 2020-06-07 10:13 |  |  |  |  | 2020-06-07 20:01 | Yes | -9
VD-9001-202G-WPQ-001 | 0 | Welder performance Qualification report | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 | 2020-06-08 12:22 | 2020-06-08 12:24 | Yes | 24 | [9 empty] | No | -3
VD-9001-202G-FMT-001 | 0 | SPIR forms | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-202G-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-05 | 2020-06-02 11:59 | 2020-06-02 11:59 | Yes | 28 |  |  | 2020-06-07 12:00 | [5 empty] | 2020-06-07 20:02 | Yes | -9 | 1204-Owner-v | 2020-06-08 10:57
VD-9001-202G-DWG-001 | 0 | 3D Tekla Model | PV-202G | Sabz Ashian APadana Engineering Company | 2020-04-23 | 2020-06-09 12:56 | 2020-06-09 12:57 | Yes | 47 | [9 empty] | No | -4
VD-9001-202G-DWG-002 | 0 | Steel Structure Assembly Plan Main Steel Structure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-003 | 0 | Steel Structure Assembly Plan +3.100m and +7.150m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-004 | 0 | Steel Structure Assembly Plan +8.500m and +12.150m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-005 | 0 | Steel Structure Assembly Plan +14.875m and +18.965m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-006 | 0 | Steel Structure Assembly Plan +19.500m and +23.500m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-007 | 0 | Steel Structure Assembly Plan Stair Tower | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-008 | 0 | Steel Structure Grating Outline Plan +3.125m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-009 | 0 | Steel Structure Grating Outline Plan +8.525m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-010 | 0 | Steel Structure Grating Outline Plan +12.175m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-011 | 0 | Steel Structure Grating Outline Plan +14.900m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-012 | 0 | Steel Structure Grating Outline Plan +19.525m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-013 | 0 | Steel Structure Grating Outline Plan +23.525m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-014 | 0 | Steel Structure Grating Outline Plan Stair Tower | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-015 | 0 | Steel Structure Platform +3.100m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-016 | 0 | Steel Structure Platform +3.100m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-017 | 0 | Steel Structure Platform +3.100m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-018 | 0 | Steel Structure Platform +3.100m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-019 | 0 | Steel Structure Platform +3.100m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-020 | 0 | Steel Structure Platform +3.100m TOS Part 6 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-021 | 0 | Steel Structure Platform +3.100m TOS Part 7 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-022 | 0 | Steel Structure Platform +3.100m TOS Part 8 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-023 | 0 | Steel Structure Platform +3.100m TOS Part 9 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-024 | 0 | Steel Structure Platform +3.100m TOS Part 10 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-025 | 0 | Steel Structure Platform +3.100m TOS Part 11 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-026 | 0 | Steel Structure Platform +3.100m TOS Part 12 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-027 | 0 | Steel Structure Column axis 1/A , 1/C - Stage I ±0.000m to +8.800m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-028 | 0 | Steel Structure Column axis 2/A - Stage I ±0.000m to +8.800m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-029 | 0 | Steel Structure Column axis 2/A - Stage I ±0.000m to +8.800m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-030 | 0 | Steel Structure Column axis 3/A - Stage I ±0.000m to +10.785m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-061 | 0 | Steel Structure Platform +12.150m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-062 | 0 | Steel Structure Platform +12.150m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-063 | 0 | Steel Structure Platform +12.150m TOS Part 6 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-064 | 0 | Steel Structure Platform +12.150m TOS Part 7 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-065 | 0 | Steel Structure Platform +12.150m TOS Part 8 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-066 | 0 | Steel Structure Platform +12.150m TOS Part 9 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-067 | 0 | Steel Structure Platform +12.150m TOS Part 10 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-068 | 0 | Steel Structure Platform +12.150m TOS Part 11 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-069 | 0 | Steel Structure Column axis 1/A , 1/C - Stage I I +8.800m to +19.000m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-070 | 0 | Steel Structure Column axis 1/B - Stage I I +8.800m to +19.000m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-071 | 0 | Steel Structure Column axis 1/A , 2/B , 1/C - Stage I I +8.800m to +19.000m | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-072 | 0 | Steel Structure Column axis 3/A - Stage I I +10.785m to +19.500m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-073 | 0 | Steel Structure Column axis 3/A - Stage I I +10.785m to +19.500m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-074 | 0 | Steel Structure Column axis 1/A - Stage I I +10.785m to +19.500m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-075 | 0 | Steel Structure Column axis 1/A - Stage I I +10.785m to +19.500m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-076 | 0 | Steel Structure Column axis 4/A - Stage I I +10.785m to +19.815m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-077 | 0 | Steel Structure Column axis 4/A - Stage I I +10.785m to +19.815m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-078 | 0 | Steel Structure Column axis 4/C - Stage I I +10.785m to +19.815m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-079 | 0 | Steel Structure Column axis 4/C - Stage I I +10.785m to +19.815m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-080 | 0 | Steel Structure Column axis 3/B - Stage I I +10.785m to +19.500m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-081 | 0 | Steel Structure Column axis 3/B - Stage I I +10.785m to +19.500m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-082 | 0 | Steel Structure Column axis 4/B - Stage I I +10.785m to +19.500m Sheet 1/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-083 | 0 | Steel Structure Column axis 4/B - Stage I I +10.785m to +19.500m Sheet 2/2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-084 | 0 | Steel Structure Platform +14.875m TOS Part 1 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-085 | 0 | Steel Structure Platform +14.875m TOS Part 2 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-086 | 0 | Steel Structure Platform +14.875m TOS Part 3 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-087 | 0 | Steel Structure Platform +14.875m TOS Part 4 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-202G-DWG-088 | 0 | Steel Structure Platform +14.875m TOS Part 5 | PV-202G | Sabz Ashian APadana Engineering Company | 2020-05-15 |  |  | No | 35 | [9 empty] | No | 0
VD-9001-104(1-K)-PDS-001 | 1 | Process description | PR-104(1) | HATCO CO. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-509A-SCH-001 | 0 | Cable Drum Schedule | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-509A-DSH-001 | 0 | Cable Data Sheet | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-509A-ITP-001 | 0 | Cable Inspection & Test Plan | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-509A-IPM-001 | 0 | Cable Test Procedure | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-509A-INR-001 | 0 | Final Test Reports | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-08-10 |  |  | No | -52 | [9 empty] | No | 0
VD-9001-509A-MNL-001 | 0 | Cable Marking & Drum Handling and Storage Procedure | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-509A-LST-003 | 0 | Bill of Material List | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-509A-LST-004 | 0 | Final Data Book | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-12-30 |  |  | No | -194 | [9 empty] | No | 0
VD-9001-509A-LST-005 | 0 | Final Data Book Index | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-11-30 |  |  | No | -164 | [9 empty] | No | 0
VD-9001-509A-LST-006 | 0 | List of Sub-supplier | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-509A-MNL-002 | 0 | Quality Manual | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-07-10 |  |  | No | -21 | [9 empty] | No | 0
VD-9001-509A-RPT-001 | 0 | Inspection Release Note | EL-509A | KERMAN & KAVIAN CABLE IND (KCI) | 2020-08-30 |  |  | No | -72 | [9 empty] | No | 0
VD-9001-307A1-DSH-027 | 1 | LUBE OIL STATION DATASHEET FOR HP BOILER FEED WATER PUMPS P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-307A1-DWG-099 | 1 | LUBE OIL STATION NAME PLATE DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-098 | 1 | LUBE OIL STATION NAME PLATE DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-096 | 1 | LUBE OIL STATION NAME PLATE DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-095 | 1 | LUBE OIL STATION NAME PLATE DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-094 | 1 | LUBE OIL STATION NAME PLATE DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-740C-SPD-271 | 1 | Single Part Drawings For STRUCTURE A | ST-740C | TIR O SETON PARS CO. | 2020-06-06 | 2020-06-10 09:24 | 2020-06-10 12:37 | Yes | 4 | [9 empty] | No | -5
VD-9001-307A1-DWG-017 | 1 | PUMP CROSS SECTION DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 | 2020-06-13 08:18 | 2020-06-13 08:19 | Yes | 2 | [9 empty] | No | -8
VD-9001-104(1-M)-PPL-003 | 1 | Electrical Cable Route Layout | PR-104(1) | HATCO CO. | 2020-06-02 |  |  | No | 17 | [9 empty] | No | 0
VD-9001-213B1-ITP-030 | 3 | Inspection and Test Plan (ITP) | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-01 16:56 | 2020-06-01 16:57 | Yes | -13 | [9 empty] | No | 4
VD-9001-213B1-CAL-007 | 1 | Nozzle load Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-07 09:45 | 2020-06-07 09:45 | Yes | -7 |  |  | 2020-06-08 14:37 | [5 empty] | 2020-06-08 20:06 | Yes | -13
VD-9001-213B1-DWG-019 | 1 | Shell Nozzle for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-07 09:52 | 2020-06-07 09:52 | Yes | -7 |  |  | 2020-06-08 14:39 | [5 empty] | 2020-06-08 20:07 | Yes | -13
VD-9001-213B1-DWG-020 | 1 | Roof Nozzle for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-01 12:12 | 2020-06-01 12:13 | Yes | -13 |  |  | 2020-06-03 10:59 | [5 empty] | 2020-06-03 20:00 | Yes | -12 | 1204-Owner-v | 2020-06-03 09:27
VD-9001-213B1-DWG-023 | 1 | Drain Sump for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-01 12:13 | 2020-06-01 12:14 | Yes | -13 |  |  | 2020-06-03 10:57 | [5 empty] | 2020-06-03 20:00 | Yes | -12 | 1204-Owner-v | 2020-06-03 09:26
VD-9001-213B1-CAL-008 | 2 | Roof Structure Lifting Calculation for Erection for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 | 2020-06-07 16:20 | 2020-06-07 16:21 | Yes | -7 |  |  |  |  | 2020-06-14 09:23 |  |  |  | 2020-06-14 20:00 | Yes | -7
VD-9001-213B1-CAL-006 | 2 | Roof Structure Calculation for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-14 20:01 |  |  | No | 5 | [9 empty] | No | 0
VD-9001-213B1-CAL-004 | 0 | Shell Manhole Reinforce Calculation TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-01 | 2020-06-01 11:19 | 2020-06-01 11:20 | Yes | 0 |  |  |  |  | 2020-06-03 11:00 |  |  |  | 2020-06-03 20:00 | Yes | -12 | 1204-Owner-v | 2020-06-03 09:25
VD-9001-251D-DIS-001 | 0 | VENDOR DOCUMENTS INDEX & SCHEDULE | HM-251D | Fateh Sanat Kimia Co. | 2020-04-14 | 2020-06-01 15:16 | 2020-06-01 15:16 | Yes | 48 |  |  | 2020-06-02 10:48 | [5 empty] | 2020-06-02 10:48 | Yes | -13
VD-9001-251D-LST-002 | 0 | COMMISSIONING SPARE PART LIST | HM-251D | Fateh Sanat Kimia Co. | 2020-05-22 |  |  | No | 28 | [9 empty] | No | 0
VD-9001-251D-VDR-003 | 0 | FINAL VENDOR DATA BOOK INDEX | HM-251D | Fateh Sanat Kimia Co. | 2021-01-23 |  |  | No | -218 | [9 empty] | No | 0
VD-9001-251D-PCJ-005 | 0 | PAINTING PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-PCJ-006 | 0 | P.W.H.T. PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-PCJ-007 | 0 | NDT PROCEDURE FOR PIPE, WELDING FITTING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 | 2020-06-01 10:05 | 2020-06-01 10:05 | Yes | -15 |  |  |  | 2020-06-02 13:06 |  |  |  |  | 2020-06-02 13:06 | Yes | -13
VD-9001-251D-PCJ-008 | 0 | HYDROSTATIC TEST PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-NPL-009 | 0 | WELDING DOCUMENT (WPS,PQR,MAP,NDT MAP) FOR PIPE, FITTING WELDING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-ITP-010 | 0 | INSPECTION AND TEST PLAN FOR PIPE, FITTING WELDING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 | 2020-06-01 10:00 | 2020-06-01 10:00 | Yes | -15 |  |  |  | 2020-06-09 11:02 |  |  |  |  | 2020-06-09 11:02 | Yes | -6
VD-9001-251D-VDR-011 | 0 | FINAL VENDOR DATABOOK | HM-251D | Fateh Sanat Kimia Co. | 2021-02-23 |  |  | No | -249 | [9 empty] | No | 0
VD-9001-251D-PCJ-012 | 0 | PMI PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-PCJ-013 | 0 | HARDNESS TEST PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 | 2020-06-01 10:03 | 2020-06-01 10:03 | Yes | -15 |  |  |  | 2020-06-02 13:05 |  |  |  |  | 2020-06-02 13:05 | Yes | -13
VD-9001-251D-PCJ-014 | 0 | PICKLING AND PASSIVATION PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 | 2020-06-01 10:08 | 2020-06-01 10:08 | Yes | -15 |  |  |  | 2020-06-02 13:02 |  |  |  |  | 2020-06-02 13:02 | Yes | -13
VD-9001-251D-LST-015 | 0 | SUB-VENDOR LIST | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-PCJ-016 | 0 | REPAIR PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 | 2020-06-01 10:10 | 2020-06-01 10:10 | Yes | -15 |  |  |  | 2020-06-02 12:57 |  |  |  |  | 2020-06-02 12:57 | Yes | -13
VD-9001-251D-PCJ-017 | 0 | WELDER QUALIFICATION RECORD | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-DWG-018 | 0 | REFRACTORY ANCHOR LAYOUT DRAWING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-PCJ-019 | 0 | PACKING AND MARKING PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-251D-PCJ-020 | 0 | INSTALLATION AND DRY OUT PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-CAL-021 | 0 | CALCULATION BOOK FOR COLD COLLECTOR | HM-251D | Fateh Sanat Kimia Co. | 2020-05-23 |  |  | No | 27 | [9 empty] | No | 0
VD-9001-251D-CAL-022 | 0 | CALCULATION BOOK FOR TRANSFER LINE | HM-251D | Fateh Sanat Kimia Co. | 2020-05-27 |  |  | No | 23 | [9 empty] | No | 0
VD-9001-251D-DWG-023 | 0 | GENERAL ARRANGEMENT DRAWING FOR COLD COLLECTOR | HM-251D | Fateh Sanat Kimia Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-251D-DWG-024 | 0 | GENERAL ARRANGEMENT DRAWING FOR TRANSFER LINE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-251D-PCJ-025 | 0 | INTERNAL REFRACTORY LINING SPECIFICATION | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-PCJ-026 | 0 | WORK SHOP ASSEMBLY PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-251D-PCJ-027 | 0 | VISUAL TEST EXAMINATION | HM-251D | Fateh Sanat Kimia Co. | 2020-05-09 | 2020-06-02 12:24 | 2020-06-02 12:24 | Yes | 24 |  |  |  | 2020-06-07 10:21 |  |  |  |  | 2020-06-07 10:21 | Yes | -9
VD-9001-251D-CAL-028 | 0 | STRESS ANALYSIS CALCULATION | HM-251D | Fateh Sanat Kimia Co. | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-251D-PCJ-029 | 0 | SHOP CURING PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-05-26 |  |  | No | 24 | [9 empty] | No | 0
VD-9001-251D-DWG-030 | 0 | RECRACTORY DETAIL DRAWING | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-MTO-031 | 0 | REFRACTORY MATERIAL TAKE OFF | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-DSH-032 | 0 | RECRACTORIES DATA SHEET | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-CAL-033 | 0 | HEAT TRANSFER CALCULATION (REFRACTORY THICKNESS VERIFICATION) | HM-251D | Fateh Sanat Kimia Co. | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-251D-DWG-034 | 0 | DETAIL DRAWINGS FOR TRANSFER LINE | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-DWG-035 | 0 | SUPPORT DETAIL DRAWINGS | HM-251D | Fateh Sanat Kimia Co. | 2020-05-19 |  |  | No | 31 | [9 empty] | No | 0
VD-9001-251D-LST-036 | 0 | 2 YEARS SPARE PART LIST | HM-251D | Fateh Sanat Kimia Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-504-DIS-001 | 0 | VDIS | EL-504 | IRAN TRANSFO | 2020-05-13 |  |  | No | 37 | [9 empty] | No | 0
VD-9001-504-DWG-001 | 0 | Foundation drawing of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-05-30 | 2020-06-14 12:58 | 2020-06-14 15:14 | Yes | 15 | [9 empty] | No | -9
VD-9001-504-DWG-002 | 0 | Foundation drawing of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-05-30 | 2020-06-14 14:25 | 2020-06-14 15:14 | Yes | 15 | [9 empty] | No | -9
VD-9001-504-DWG-003 | 0 | Outline drawing of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-05-30 | 2020-06-14 14:30 | 2020-06-14 15:14 | Yes | 15 | [9 empty] | No | -9
VD-9001-504-DWG-004 | 0 | Outline drawing of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-05-30 | 2020-06-14 15:14 | 2020-06-14 15:14 | Yes | 15 | [9 empty] | No | -9
VD-9001-504-DWG-005 | 0 | Connection digram of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-10-06 |  |  | No | -109 | [9 empty] | No | 0
VD-9001-504-DWG-006 | 0 | Connection digram of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-10-06 |  |  | No | -109 | [9 empty] | No | 0
VD-9001-504-DWG-007 | 0 | Name plate of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-504-DWG-008 | 0 | Name plate of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-06-17 | 2020-06-14 15:14 | 2020-06-14 15:15 | Yes | -3 | [9 empty] | No | -9
VD-9001-504-DSH-009 | 0 | Data sheet of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-504-DSH-010 | 0 | Data sheet of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-05-30 |  |  | No | 20 | [9 empty] | No | 0
VD-9001-504-CER-001 | 0 | test certificate | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-ITP-011 | 0 | ITP plan for 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-05-19 | 2020-06-02 10:55 | 2020-06-02 11:15 | Yes | 14 | [9 empty] | No | 3
VD-9001-504-ITP-012 | 0 | ITP plan for 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-05-19 | 2020-06-02 11:08 | 2020-06-02 11:12 | Yes | 14 | [9 empty] | No | 3
VD-9001-504-LST-001 | 0 | Packing list of 28/35 MVA | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-LST-002 | 0 | Packiing list of 3150/4000 KVA | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-FDB-001 | 0 | Final Book for 28/35MVA including installation and erection Manual& recommandations for storage | EL-504 | IRAN TRANSFO | 2020-09-06 |  |  | No | -79 | [9 empty] | No | 0
VD-9001-504-FDB-002 | 0 | Final book for 3150/4000KVA including installation and erection Manual& recommandations for storage | EL-504 | IRAN TRANSFO | 2020-09-06 |  |  | No | -79 | [9 empty] | No | 0
VD-9001-504-RPT-001 | 0 | Test report for 28/35MVA Transformer | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-RPT-002 | 0 | Test report for 3150/4000 KVA Transformer | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-PCJ-001 | 0 | Test procedure for 28/35MVA | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-PCJ-002 | 0 | Test procedure for 3150/4000KVA | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-LST-003 | 0 | Spare parts list for pre-comissioning,comissioning and Start-Up | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-LST-004 | 0 | Spare part list for 2 years normal operation | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-LST-005 | 0 | SPIR form | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-LST-006 | 0 | Sub vendor list | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-CUR-001 | 0 | Transformer overload capability curve for 35MVA & 4000KVA | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-CAT-005 | 0 | Technical catalogues of instruments | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-504-SPE-005 | 0 | Oil specifications for transformers | EL-504 | IRAN TRANSFO | 2020-05-09 |  |  | No | 41 | [9 empty] | No | 0
VD-9001-260-WBK-001 | 1 | Welding Book(WPS,PQR) | HM-260 | ABAN AIR COOLER. | 2020-06-08 |  |  | No | 11 | [9 empty] | No | 0
VD-9001-301-1-PID-101 | 1 | REC Compressor (C-2002) PID | MC-301-1 | NEW JCM | 2020-06-15 11:19 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-603-DSH-003 | 1 | Analyzer Data Sheet | IN-603 | Sandroos Sanat | 2020-06-06 | 2020-06-15 16:15 | 2020-06-15 16:17 | Yes | 9 | [6 empty] | 2020-06-15 10:21 | 2020-06-15 10:21 |  | Yes | -14
VD-9001-260-PRC-004 | 1 | Tube to Tube Sheet Joint Procedure | HM-260 | ABAN AIR COOLER. | 2020-06-08 |  |  | No | 11 | [9 empty] | No | 0
VD-9001-307A1-DWG-062 | 1 | LUBE OIL STATION GA DRAWING FOR CONVERTER BW CIRCULATION PUMP UNIT P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-063 | 1 | LUBE OIL STATION GA DRAWING FOR FIRST SATURATOR PUMP UNIT P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-307A1-DWG-067 | 1 | LUBE OIL STATION GA DRAWING FOR COOLING WATER SUPPLY PUMP UNITS P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-301-1-PID-102 | 1 | REC Steam Turbine (STC-2002) PID | MC-301-1 | NEW JCM | 2020-06-15 12:48 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-201B-CAL-008 | 2 | LADDER AND PLATFORM CALCULATION (4134-0359/MC2) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-15 20:00 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-307A1-PID-009 | 2 | THERMAL SYSTEM DIAGRAM FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-12 |  |  | No | 7 | [9 empty] | No | 0
VD-9001-307A1-DWG-142 | 1 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-12 | 2020-06-13 08:12 | 2020-06-13 08:13 | Yes | 1 | [9 empty] | No | -8
VD-9001-307A1-ITP-002 | 1 | INSPECTION & TEST PLAN FOR ELECTRICAL MOTOR | MC-307A1 | Deep Blue Pump Co. | 2020-06-12 | 2020-06-04 01:40 | 2020-06-04 01:40 | Yes | -8 | [9 empty] | No | 1
VD-9001-104(1)-DWG-001 | 1 | Direct Contact Air Cooler General arrangement (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-251D-PCJ-016 | 1 | REPAIR PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-251D-PCJ-014 | 1 | PICKLING AND PASSIVATION PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-251D-PCJ-013 | 1 | HARDNESS TEST PROCEDURE | HM-251D | Fateh Sanat Kimia Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-251D-PCJ-007 | 1 | NDT PROCEDURE FOR PIPE, WELDING FITTING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-06 |  |  | No | 13 | [9 empty] | No | 0
VD-9001-307A1-DWG-144 | 1 | LUBE OIL COOLER DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-12 |  |  | No | 7 | [9 empty] | No | 0
VD-9001-307A1-DWG-146 | 1 | LUBE OIL COOLER DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-12 |  |  | No | 7 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-011 | 1 | LP Plate fin heat exchanger General arrangement (T-6101-E-3A~G) | PR-104(1) | HATCO CO. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-012 | 1 | Sub cooler General arrangement | PR-104(1) | HATCO CO. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-009 | 1 | Distillation upper column General arrangement (T-6101-T-2) | PR-104(1) | HATCO CO. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-104(1-K)-DWG-008 | 1 | Distillation lower column General arrangement (T-6101-T-1) | PR-104(1) | HATCO CO. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-307A1-DWG-139 | 1 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-13 | 2020-06-13 08:12 | 2020-06-13 08:13 | Yes | 0 | [9 empty] | No | -8
VD-9001-307A1-DWG-143 | 1 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-13 | 2020-06-13 08:13 | 2020-06-13 08:13 | Yes | 0 | [9 empty] | No | -8
VD-9001-307A1-DWG-140 | 1 | GLAND SEALING COOLER OUTLINE DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-13 | 2020-06-13 08:12 | 2020-06-13 08:13 | Yes | 0 | [9 empty] | No | -8
VD-9001-307A1-DWG-145 | 1 | LUBE OIL COOLER DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-307A1-DWG-149 | 1 | LUBE OIL COOLER DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-104(1)-DSH-010 | 1 | Air Intake Filer Data Sheet (C-6101-FT-A/B) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-213B1-CAL-004 | 1 | Shell Manhole Reinforce Calculation TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-09 | 2020-06-07 09:22 | 2020-06-07 09:22 | Yes | -2 |  |  | 2020-06-08 08:38 |  |  |  | 2020-06-07 09:13 | 2020-06-07 09:13 | 2020-06-08 20:00 | Yes | -13
VD-9001-257C-FDB-001 | 1 | MANUFACTURING DATA BOOK (0641/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-11 | 2020-06-18 17:08 | 2020-06-18 17:10 | Yes | 7 | [9 empty] | No | -13
VD-9001-307A1-DWG-048 | 1 | MOTOR OUTLINE DRAWING FOR PM6301CDEF | MC-307A1 | Deep Blue Pump Co. | 2020-06-06 08:39 | 2020-06-06 08:43 | 2020-06-06 08:43 | Yes | 0 | [9 empty] | No | -1
VD-9001-251-DWG-086 | 1 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2020-06-06 09:16 | 2020-06-06 09:18 | 2020-06-06 09:18 | Yes | 0 |  |  |  | 2020-06-14 12:32 |  |  |  |  | 2020-06-14 12:32 | Yes | -6
VD-9001-201B-DWG-007 | 4 | LADDER AND PLATFORM DWG (4134-0359/3) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-06 10:56 | 2020-06-08 12:31 | 2020-06-08 12:33 | Yes | 2 | [9 empty] | No | -3
VD-9001-201B-DWG-009 | 2 | LADDER AND PLATFORM DWG (4134-0359/5) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-06 10:56 | 2020-06-08 12:34 | 2020-06-08 12:34 | Yes | 2 | [9 empty] | No | -3
VD-9001-501-DSH-003 | 1 | Data sheet for CT | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-20 11:02 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-501-DWG-004 | 1 | Outline for CT | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-20 11:07 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-257C-FDB-002 | 1 | MANUFACTURING DATA BOOK (0642/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 | 2020-06-18 17:22 | 2020-06-18 17:24 | Yes | 5 | [9 empty] | No | -13
VD-9001-307A1-DWG-100 | 1 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307A1-DWG-101 | 1 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307A1-DWG-102 | 1 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307A1-DWG-103 | 1 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307A1-DWG-104 | 1 | SEAL ASSEMBLY DRAWING AND BILL OF MATERIAL FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-405A-DIS-001 | 0 | Vendor Documents Index & Schedule | PI-405A | PART SAZI MASHHAD | 2020-01-06 | 2020-06-06 13:58 | 2020-06-06 13:59 | Yes | 152 |  |  | 2020-06-07 13:10 | [5 empty] | 2020-06-07 13:11 | Yes | -13
VD-9001-405A-ITP-001 | 0 | Inspection and Test Plan | PI-405A | PART SAZI MASHHAD | 2020-11-06 |  |  | No | -140 | [9 empty] | No | 0
VD-9001-405A-LST-001 | 0 | Sub-Vendor List | PI-405A | PART SAZI MASHHAD | 2020-11-06 | 2020-06-06 14:59 | 2020-06-06 14:59 | Yes | -153 |  |  |  | 2020-06-08 08:07 |  |  |  |  | 2020-06-08 08:07 | Yes | -12
VD-9001-405A-PCJ-001 | 0 | Packing & Marking Procedure | PI-405A | PART SAZI MASHHAD | 2020-11-06 | 2020-06-06 15:55 | 2020-06-06 15:55 | Yes | -153 |  |  |  |  | 2020-06-08 14:05 |  |  |  | 2020-06-08 14:05 | Yes | -12
VD-9001-405A-PCJ-002 | 0 | Test Procedure | PI-405A | PART SAZI MASHHAD | 2020-11-06 |  |  | No | -140 | [9 empty] | No | 0
VD-9001-405A-CER-001 | 0 | Material Test Certificate (Including Raw Material, Dimensional & Mechanicl Report) | PI-405A | PART SAZI MASHHAD | 2020-09-21 |  |  | No | -94 | [9 empty] | No | 0
VD-9001-405A-LST-002 | 0 | Packing Lists | PI-405A | PART SAZI MASHHAD | 2020-09-21 |  |  | No | -94 | [9 empty] | No | 0
VD-9001-405A-IRN-001 | 0 | TPI Release Note | PI-405A | PART SAZI MASHHAD | 2020-03-10 |  |  | No | 101 | [9 empty] | No | 0
VD-9001-405A-INX-001 | 0 | Final Vendor Data Book Index | PI-405A | PART SAZI MASHHAD | 2020-10-21 |  |  | No | -124 | [9 empty] | No | 0
VD-9001-405A-FDB-001 | 0 | Final Vendor Data Book | PI-405A | PART SAZI MASHHAD | 2020-12-31 |  |  | No | -195 | [9 empty] | No | 0
VD-9001-104(1)-DWG-033 | 1 | Water Cooling Tower General arrangement (T-6102) | PR-104(1) | HATCO CO. | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-307B-DSH-009 | 1 | PUMP DATASHEET WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-20 20:00 | 2020-06-11 12:25 | 2020-06-11 12:25 | Yes | -9 | [9 empty] | No | -6 | 1204-Owner-v | 2020-06-15 13:19
VD-9001-307B-PID-010 | 1 | PUMP P&I DRAWING WITH CURVE FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-20 20:00 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307B-PID-004 | 1 | PUMP P&I DRAWING WITH CURVE FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-20 20:00 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307B-PID-007 | 1 | PUMP P&I DRAWING WITH CURVE FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-307B-PID-006 | 1 | PUMP P&I DRAWING WITH CURVE FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-307B-PID-005 | 1 | PUMP P&I DRAWING WITH CURVE FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-307B-PID-009 | 1 | PUMP P&I DRAWING WITH CURVE FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-307A1-DWG-109 | 1 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307A1-DWG-111 | 1 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307A1-DWG-110 | 1 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307A1-DWG-112 | 1 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307A1-DWG-113 | 1 | THRUST AND RADIAL BEARING ASSEMBLY DRAWING WITH PARTS LIST FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-251D-PCJ-027 | 1 | VISUAL TEST EXAMINATION | HM-251D | Fateh Sanat Kimia Co. | 2020-06-09 |  |  | No | 10 | [9 empty] | No | 0
VD-9001-257C-FDB-005 | 1 | MANUFACTURING DATA BOOK (0645/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-14 | 2020-06-18 17:34 | 2020-06-18 17:37 | Yes | 4 | [9 empty] | No | -13
VD-9001-104(1)-DSH-016 | 1 | Water Cooling Tower Data Sheet (T-6102) | PR-104(1) | HATCO CO. | 2020-06-14 |  |  | No | 5 | [9 empty] | No | 0
VD-9001-257C-FDB-006 | 1 | MANUFACTURING DATA BOOK (0646/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-14 | 2020-06-18 17:46 | 2020-06-18 17:47 | Yes | 4 | [9 empty] | No | -13
VD-9001-104(1)-DSH-001 | 1 | Direct Contact Air Cooler Data Sheet (DCAC) (T-6101) | PR-104(1) | HATCO CO. | 2020-06-14 |  |  | No | 5 | [9 empty] | No | 0
VD-9001-307B-PID-017 | 1 | PUMP P&I DRAWING WITH CURVE FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-21 20:00 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-307B-PID-018 | 1 | PUMP P&I DRAWING WITH CURVE FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-21 20:00 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-307B-PID-015 | 1 | PUMP P&I DRAWING WITH CURVE FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-21 20:00 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-202G-PCJ-007 | 1 | Repair Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-202G-PCJ-002 | 1 | Dimensional check procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-202G-PCJ-001 | 1 | NDT Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-202G-WBK-001 | 1 | Welding Book | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-213B1-CAL-009 | 1 | Pipe Support Calculation For TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-11 | 2020-06-08 16:39 | 2020-06-08 16:39 | Yes | -3 |  |  |  |  | 2020-06-09 14:48 |  |  |  | 2020-06-09 20:04 | Yes | -13
VD-9001-201B-CAL-001 | 4 | MECHANICAL CALCULATION (4134-0359/MC) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-405A-LST-001 | 1 | Sub-Vendor List | PI-405A | PART SAZI MASHHAD | 2020-06-22 08:07 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-603-ITP-023 | 1 | Inspection & Test Plan | IN-603 | Sandroos Sanat | 2020-06-13 |  |  | No | 6 | [9 empty] | No | 0
VD-9001-307A1-DWG-148 | 1 | LUBE OIL COOLER DRAWING FOR P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-604-1-PCJ-001 | 2 | NDE Procedure (PMI) | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-06-10 | 2020-06-10 12:55 | 2020-06-10 12:55 | Yes | 0 | [9 empty] | No | -5
VD-9001-307A1-DWG-153 | 2 | RUN DOWN TANK GA DRAWING FOR UNIT P4001C | MC-307A1 | Deep Blue Pump Co. | 2020-06-18 | 2020-06-15 12:50 | 2020-06-15 12:50 | Yes | -3 | [9 empty] | No | -10
VD-9001-307A1-DWG-066 | 1 | LUBE OIL STATION GA DRAWING FOR MP BOILER FEED WATER PUMP UNIT P4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-307A1-DWG-064 | 1 | LUBE OIL STATION GA DRAWING FOR HP BOILER FEED WATER PUMP UNITS P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-004 | 1 | LIN Back-up Pump Data sheet (P-6103) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-001 | 1 | IC LOX Pump Data sheet (T-6101-P-2A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-257C-FDB-009 | 1 | MANUFACTURING DATA BOOK (0649/MDB) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-15 | 2020-06-18 18:03 | 2020-06-18 18:04 | Yes | 3 | [9 empty] | No | -13
VD-9001-257C-FDB-010 | 1 | MANUFACTURING DATA BOOK (0840/MDB) For E-2002B | HM-257C | Brembana & Rolle S.p.A. | 2020-06-15 | 2020-06-18 18:16 | 2020-06-18 18:17 | Yes | 3 | [9 empty] | No | -13
VD-9001-104(1)-LST-004 | 2 | TIE-IN Point List and Location | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-C)-DSH-001 | 1 | Expansion Turbine Data Sheet (T-6101-TE-1A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-104(1-S)-ITP-001 | 1 | Inspection and test plan For Air Compressor Package (C-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-405A-PCJ-001 | 1 | Packing & Marking Procedure | PI-405A | PART SAZI MASHHAD | 2020-06-22 14:05 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-104(1)-DWG-008 | 1 | General Arrangement Drawing For Dryer Vessels (DR-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-15 |  |  | No | 4 | [9 empty] | No | 0
VD-9001-307B-ITP-002 | 1 | ELECTRICAL MOTORS TEST & INSPECTION PLAN | MC-307B | Deep Blue Pump Co. | 2020-06-22 20:00 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-084 | 2 | MOTOR OUTLINE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 20:00 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-099 | 2 | MOTOR OUTLINE DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-22 20:00 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-098 | 2 | MOTOR OUTLINE DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-097 | 2 | MOTOR OUTLINE DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-096 | 2 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-095 | 2 | MOTOR OUTLINE DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-094 | 2 | MOTOR OUTLINE DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-093 | 2 | MOTOR OUTLINE DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-092 | 2 | MOTOR OUTLINE DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-091 | 2 | MOTOR OUTLINE DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-090 | 2 | MOTOR OUTLINE DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-089 | 2 | MOTOR OUTLINE DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-088 | 2 | MOTOR OUTLINE DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-087 | 2 | MOTOR OUTLINE DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-086 | 2 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-085 | 2 | MOTOR OUTLINE DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-083 | 2 | MOTOR OUTLINE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307B-DWG-082 | 2 | MOTOR OUTLINE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-104(1)-DSH-006 | 1 | Regeneration Gas Steam Heater data sheet (DR-6101-HE-1) | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-104(1)-DSH-002 | 1 | Evaporation Condenser Data Sheet (T-6101-EV-1) | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-104(1)-DSH-008 | 1 | Dryer Package Data Sheet (DR-6101) | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251D-ITP-010 | 1 | INSPECTION AND TEST PLAN FOR PIPE, FITTING WELDING | HM-251D | Fateh Sanat Kimia Co. | 2020-06-11 |  |  | No | 8 | [9 empty] | No | 0
VD-9001-104(1)-DSH-007 | 1 | LIN Tank Data Sheet (TK-6101) | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-003 | 1 | LIN Evaporator Data Sheet (EV-6101 A/B) | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307A1-DSH-030 | 1 | GEAR BOX DATASHEET FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-19 |  |  | No | 0 | [9 empty] | No | 0
VD-9001-307A1-DSH-031 | 1 | GEAR BOX DATASHEET FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-19 |  |  | No | 0 | [9 empty] | No | 0
VD-9001-307A1-DSH-032 | 1 | GEAR BOX DATASHEET FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-19 |  |  | No | 0 | [9 empty] | No | 0
VD-9001-307A1-DSH-033 | 1 | GEAR BOX DATASHEET FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-19 |  |  | No | 0 | [9 empty] | No | 0
VD-9001-213B1-CAL-009 | 2 | Pipe Support Calculation For TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-15 | 2020-06-10 15:08 | 2020-06-10 15:08 | Yes | -5 |  |  | 2020-06-11 09:12 | [5 empty] | 2020-06-11 20:00 | Yes | -13
VD-9001-104(1)-DSH-003 | 1 | Cooling Water Pump Data sheet (P6101 A/B/C) | PR-104(1) | HATCO CO. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-260-ITP-001 | 1 | Inspection and Test Plan | HM-260 | ABAN AIR COOLER. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-104(1)-DSH-004 | 1 | Chilled Water Pump Data sheet (P6102 A/B) | PR-104(1) | HATCO CO. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307A1-DWG-068 | 1 | GEAR BOX DRAWING FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-070 | 1 | GEAR BOX DRAWING FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-071 | 1 | GEAR BOX DRAWING FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-069 | 1 | GEAR BOX DRAWING FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-090 | 1 | GEAR BOX NAME PLATE DRAWING FOR P2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-091 | 1 | GEAR BOX NAME PLATE DRAWING FOR P2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-092 | 1 | GEAR BOX NAME PLATE DRAWING FOR P4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-DWG-093 | 1 | GEAR BOX NAME PLATE DRAWING FOR P6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-301-1-DWG-201 | 2 | Syn Gas Compressor (C-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-06-24 12:29 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-301-1-DWG-202 | 2 | Syn Gas Compressor (C-2001) Cross Section Drawing | MC-301-1 | NEW JCM | 2020-06-24 12:59 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-301-1-DWG-203 | 2 | Syn Gas Steam Turbine (STC-2001) Outline Drawing | MC-301-1 | NEW JCM | 2020-06-24 14:16 | 2020-06-19 07:37 | 2020-06-19 07:38 | Yes | -5 | [9 empty] | No | -14
VD-9001-301-1-DWG-103 | 2 | REC Steam Turbine (STC-2002) Outline Drawing | MC-301-1 | NEW JCM | 2020-06-24 14:44 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-104(1-K)-DSH-002 | 1 | IC LIN Pump Data sheet (T-6101-P-1A/B) | PR-104(1) | HATCO CO. | 2020-06-17 |  |  | No | 2 | [9 empty] | No | 0
VD-9001-307B-DWG-011 | 1 | GA DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-307B-DWG-012 | 1 | GA DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-307B-DWG-013 | 1 | GA DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-307B-DWG-014 | 1 | GA DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-201B-PCJ-013 | 2 | PACKING, MARKING & SHIPPING PROCEDURE (4134/PP) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-307B-DWG-015 | 1 | GA DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-307B-DWG-016 | 1 | GA DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-24 20:00 |  |  | No | -5 | [9 empty] | No | 0
VD-9001-201B-INX-001 | 2 | MANUFACTURER DATA REPORT INDEX (4134/ED) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-11 12:42 | 2020-06-11 12:49 | 2020-06-11 12:51 | Yes | 0 | [9 empty] | No | -6
VD-9001-307B-DWG-004 | 1 | GA DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-DWG-005 | 1 | GA DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-DWG-006 | 1 | GA DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-DWG-007 | 1 | GA DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-202G-ITP-001 | 1 | Inspection And Test Plan (ITP) | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-DWG-017 | 1 | GA DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-202G-PCJ-005 | 1 | Fabrication Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-25 20:00 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-DWG-018 | 1 | GA DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-202G-PCJ-003 | 1 | Blasting ,Painting Procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-307B-DWG-010 | 1 | GA DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-201B-LST-001 | 4 | COMMISSIONING & START-UP S.P.LIST (4134/SPL1) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-13 08:01 | 2020-06-15 11:03 | 2020-06-15 11:07 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-001 | 3 | INSPECTION & TESTING PLAN (4137-0364/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:12 | 2020-06-15 12:16 | 2020-06-15 12:16 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-002 | 3 | INSPECTION & TESTING PLAN (4137-0365/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:13 | 2020-06-15 12:21 | 2020-06-15 12:21 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-003 | 3 | INSPECTION & TESTING PLAN (4137-0366/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:14 | 2020-06-15 12:22 | 2020-06-15 12:24 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-004 | 4 | INSPECTION & TESTING PLAN (4137-0367/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:29 | 2020-06-15 12:30 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-005 | 4 | INSPECTION & TESTING PLAN (4137-0368/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:31 | 2020-06-15 12:31 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-006 | 5 | INSPECTION & TESTING PLAN (4137-0369/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:32 | 2020-06-15 12:33 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-007 | 4 | INSPECTION & TESTING PLAN (4137-0370/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:34 | 2020-06-15 12:34 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-ITP-008 | 5 | INSPECTION & TESTING PLAN (4137-0371/ITP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:37 | 2020-06-15 12:40 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-002 | 5 | MANUFACTURING & NDE PROCEDURE (4137/MP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 11:38 | 2020-06-15 11:40 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-001 | 2 | HYDROSTATIC PROCEDURE (4137/HT) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 11:14 | 2020-06-15 11:15 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-003 | 4 | SURFACE PREPARATION AND PAINTING PROCEDURE (4137/SP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 12:02 | 2020-06-15 12:03 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-004 | 3 | POST WELD HEAT TREATMENT PROCEDURE (4137/PWHT) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:15 | 2020-06-15 11:57 | 2020-06-15 11:57 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-006 | 1 | PICKLING & PASSIVATION PROCEDURE (4137/PKP) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:16 | 2020-06-15 11:54 | 2020-06-15 11:56 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-009 | 2 | PHASED ARRAY PROCEDURE (4137/PHA) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:16 | 2020-06-15 11:51 | 2020-06-15 11:52 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-010 | 2 | TOFD PROCEDURE (4137/TOFD) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:17 | 2020-06-15 12:05 | 2020-06-15 12:06 | Yes | 2 | [9 empty] | No | -10
VD-9001-257C-PCJ-011 | 2 | LOCAL POST-WELD HEAT TREATMENT PROCEDURE(4137/LPWHT) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-13 09:17 | 2020-06-15 11:17 | 2020-06-15 11:17 | Yes | 2 | [9 empty] | No | -10
VD-9001-104(1)-LST-008 | 2 | Utility Consumption List | PR-104(1) | HATCO CO. | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-036 | 2 | ASU P&ID -PUBLIC UTILITIES INSTRUMENT AIR | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-035 | 2 | ASU P&ID -PUBLIC UTILITIES WARMING GAS | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-034 | 2 | ASU P&ID -PUBLIC UTILITIES SEAL GAS | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-031 | 2 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VAPORIZER | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-029 | 2 | ASU P&ID - LIQUID STORAGE & VAPORIZATION SYSTEM LIN VACUM STORAGE TANK | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-028 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM,NITROGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307B-DWG-001 | 1 | GA DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-307B-DWG-002 | 1 | GA DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-307B-DWG-003 | 1 | GA DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-307B-DWG-009 | 1 | GA DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-307B-LST-005 | 2 | SUB-VENDOR LIST | MC-307B | Deep Blue Pump Co. | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-027 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, OXYGEN PRODUCT | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-501-WIN-015 | 1 | Storage Instruction | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:09 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-501-MNL-014 | 1 | Installation, Operation & Maintenance Manual | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:11 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-026 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LIQUID DRAINAGE SYSTEM | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-605-1-PCJ-001 | 2 | NDE Procedure (PMI) | IN-605-1 | Radman Process Control Co. (RAPCO) | 2020-06-18 | 2020-06-16 09:55 | 2020-06-16 09:55 | Yes | -2 | [9 empty] | No | -11
VD-9001-104(1-M)-LST-008 | 2 | Electrical Load List | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-003 | 2 | ASU P&ID Index | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-004 | 2 | ASU P&ID - PIPELINE, EQUIPMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-005 | 2 | ASU P&ID - INSTRUMENT SYMBOL SIGNS | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-501-DWG-008 | 1 | Name Plate For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:40 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-501-DIG-007 | 1 | Connection Diagram For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:44 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-501-DWG-006 | 1 | Outline Drawing For MS- NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:45 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-501-VLS-002 | 1 | Subvendor List | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:50 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-501-DSH-005 | 1 | Data Sheet For MS-NGR2A/B-01 | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 11:51 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-006 | 2 | ASU P&ID - INTERLOCK POINT LISTS | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-251-DWG-085 | 2 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251-DWG-086 | 2 | OUTLET SYSTEM - SUPPORT LAYOUT & DETAILS | HM-251 | KT – Kinetics Technology SpA | 2020-06-16 |  |  | No | 3 | [9 empty] | No | 0
VD-9001-251-LST-005 | 2 | Instruments List | HM-251 | KT – Kinetics Technology SpA | 2020-06-23 |  |  | No | -4 | [9 empty] | No | 0
VD-9001-251-DSH-007 | 1 | DATA SHEET DAMPERS | HM-251 | KT – Kinetics Technology SpA | 2020-06-23 |  |  | No | -4 | [9 empty] | No | 0
VD-9001-604-1-MNL-001 | 1 | Installation, Commissioning, Operating and Maintenance Manuals | IN-604-1 | Radman Process Control Co. (RAPCO) | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-501-CAL-018 | 1 | Temperature Rise Calculation | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-28 13:09 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-510-MNL-003 | 0 | Cathodic Protection Transformer RectifierOperating Manual | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-DIS-001 | 0 | Vendor Documents Index and Schedule | EL-510 | BORNA ELECTRONIC | 2020-06-05 |  |  | No | 14 | [9 empty] | No | 0
VD-9001-510-VLS-001 | 0 | Cathodic Protection on Sub Vendor List | EL-510 | BORNA ELECTRONIC | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-510-MTO-001 | 0 | Material List for Permanent Cathodic protection system | EL-510 | BORNA ELECTRONIC | 2020-06-16 | 2020-06-16 08:26 | 2020-06-16 08:28 | Yes | 0 | [9 empty] | No | -11
VD-9001-510-CAL-001 | 0 | Design Report and Calculation Notes for Permanent Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-16 | 2020-06-16 08:22 | 2020-06-16 08:22 | Yes | 0 | [9 empty] | No | -11
VD-9001-510-DSH-001 | 0 | Equipment Data Sheet for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-DWG-001 | 0 | General Layout for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-16 | 2020-06-16 08:25 | 2020-06-16 08:25 | Yes | 0 | [9 empty] | No | -11
VD-9001-510-DWG-002 | 0 | General Aboveground Layout for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-510-DWG-003 | 0 | Schematic Wiring and Cable Route Layout for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-510-DWG-004 | 0 | Terminal Boxes Detail Drawing for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-510-SDG-001 | 0 | Equipment and Material Installation Details for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-SCH-001 | 0 | Cable Schedule for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-510-INX-001 | 0 | Final Data Book Index for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-30 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-510-MDB-001 | 0 | Final Data Book | EL-510 | BORNA ELECTRONIC | 2020-09-13 |  |  | No | -86 | [9 empty] | No | 0
VD-9001-510-DWG-005 | 0 | Cathodic Protection Transformer Rectifier General View and Foundation Layout | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-DIG-001 | 0 | Cathodic Protection Transformer Rectifier Wiring Diagram | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-EQL-001 | 0 | Cathodic Protection Transformer Rectifier Part List | EL-510 | BORNA ELECTRONIC | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-510-LST-001 | 0 | Spare Part List for Pre-Commissioning, Commissioning and Start-Up | EL-510 | BORNA ELECTRONIC | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-510-LST-002 | 0 | Spare Part List for 2 Years Normal Operation | EL-510 | BORNA ELECTRONIC | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-510-LST-003 | 0 | Completed SPIR Form | EL-510 | BORNA ELECTRONIC | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-510-QCP-001 | 0 | Inspection & test Plan (Quality Control Plan) | EL-510 | BORNA ELECTRONIC | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-510-ITP-001 | 0 | Equipment Inspection & test Plan Specification/procedure | EL-510 | BORNA ELECTRONIC | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-510-CER-001 | 0 | Certificate of Materials | EL-510 | BORNA ELECTRONIC | 2020-08-28 |  |  | No | -70 | [9 empty] | No | 0
VD-9001-510-RPT-001 | 0 | Final Test Reports | EL-510 | BORNA ELECTRONIC | 2020-08-28 |  |  | No | -70 | [9 empty] | No | 0
VD-9001-510-LST-004 | 0 | Master Packing List | EL-510 | BORNA ELECTRONIC | 2020-08-28 |  |  | No | -70 | [9 empty] | No | 0
VD-9001-510-LST-005 | 0 | Detailed Packing List | EL-510 | BORNA ELECTRONIC | 2020-08-28 |  |  | No | -70 | [9 empty] | No | 0
VD-9001-510-PCJ-001 | 0 | Pre-Commissioning & Commissioning Procedure and CommissioningCheck List for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-510-MNL-001 | 0 | Erection and Installation Manuals for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-510-MNL-002 | 0 | Maintenance and Operating Manuals for Cathodic Protection System | EL-510 | BORNA ELECTRONIC | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-007 | 2 | ASU P&ID - AIR FILTERING & COMPRESSION LINE1 | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-008 | 2 | ASU P&ID - AIR FILTERING & COMPRESSION LINE2 | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-033 | 2 | ASU P&ID -PUBLIC UTILITIES RECYCLING WATER, DEMINERALIZED WATER | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-213B1-DWG-014 | 1 | Roof Structure for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-213B1-CAL-008 | 3 | Roof Structure Lifting Calculation for Erection for TK-6402 | PV-213B1 | PAYSAZ Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-100 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-101 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-102 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-103 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR TOPPING COLUMN REFLUX PUMPS P-3001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-104 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR TOPPING COLUMN BOTTOM PUMPS P-3002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-105 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR 1ST REFINING COLUMN REFLUX PUMPS P-3003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-107 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR BOTTOM WATER RECOVERY PUMPS P-3006 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-108 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR WASTE METHANOL PUMP P-3007 | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-109 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR LP CONDENSATE PUMPS P-4003 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-110 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CONDENSATE TRANSFER PUMPS P-6401 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-111 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR DEMIN WATER TRANSFER PUMPS P-6402 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-112 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SULFURIC ACID TRANSFER PUMPS P-6403 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-113 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CAUSTIC TRANSFER PUMPS P-6404 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-114 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR SULFURIC ACID UNLOADING PUMP P-6405 | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-115 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CAUSTIC UNLOADING PUMP P-6406 | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-116 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR Daily Methanol Transfer Pumps P-7101 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-117 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR CRUDE METHANOL TRANSFER PUMPS P-7201 A/B/C | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307B-DWG-106 | 1 | MOTOR TERMINAL BOX DRAWING AND WIRING/CONNECTION DRAWING FOR 2nd REFINING COLUMN REFLUX PUMPS P-3004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-202G-SRN-001 | 1 | Packing, marking, Shipping and Release Note procedure | PV-202G | Sabz Ashian APadana Engineering Company | 2020-06-28 20:00 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-307A1-PCJ-022 | 1 | HYDROTATIC TEST PROCEDURE FOR STEAM TURBINE | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 | 2020-06-15 09:33 | 2020-06-15 09:33 | Yes | -10 | [9 empty] | No | -10
VD-9001-104(1-K)-PID-032 | 2 | ASU P&ID -PRODUCT INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-501-PCJ-010 | 1 | Test Procedure | EL-501 | Paarsun Construction & Engineering Co. | 2020-06-29 10:01 |  |  | No | -10 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-037 | 2 | ASU P&ID -UTILITIES INTERCONNECTIONS | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-257C-PCJ-007 | 1 | FIELD TEST PROCEDURE (4137/MP1) | HM-257C | Brembana & Rolle S.p.A. | 2020-06-22 | 2020-06-15 15:08 | 2020-06-15 15:16 | Yes | -7 | [9 empty] | No | -10
VD-9001-307A1-DSH-023 | 3 | STEAM TURBINE DATASHEET WITH CURVE FOR PT6301AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307A1-DSH-019 | 3 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-009 | 2 | ASU P&ID - PRE-COOLING SYSTEM, AIR COOLING TOWER, COOLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-010 | 2 | ASU P&ID - PRE-COOLING SYSTEM, WATER COOLING TOWER, CHILLING WATER PUMP | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-307A1-DSH-020 | 3 | STEAM TURBINE DATASHEET WITH CURVE FOR PT2003A | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307A1-DSH-022 | 3 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4002A | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-210-DIS-001 | 0 | Vendor Document Index and Schedule | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-02 | 2020-06-16 12:53 | 2020-06-16 12:53 | Yes | 14 |  |  |  | 2020-06-18 12:13 |  |  | 2020-06-16 12:15 | 2020-06-16 12:15 | 2020-06-18 12:13 | Yes | -12
VD-9001-210-TIS-001 | 0 | Time Schedule | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-18 |  |  | No | 1 | [9 empty] | No | 0
VD-9001-210-ITP-001 | 0 | Inspection and Test Plan | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-04 |  |  | No | -46 | [9 empty] | No | 0
VD-9001-210-QCP-001 | 0 | Quality Control Plan | PV-210 | Masnout Felezi Sangin (MFS) | 2020-10-15 |  |  | No | -118 | [9 empty] | No | 0
VD-9001-210-LST-001 | 0 | Sub Vendor List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-12 |  |  | No | -54 | [9 empty] | No | 0
VD-9001-210-LST-002 | 0 | Spare Part List and Interchangeability Record (SPIR) | PV-210 | Masnout Felezi Sangin (MFS) | 2020-01-30 |  |  | No | 141 | [9 empty] | No | 0
VD-9001-210-INX-001 | 0 | Final Data Book Index | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-15 |  |  | No | -149 | [9 empty] | No | 0
VD-9001-210-CAL-001 | 0 | Process Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-10 |  |  | No | 9 | [9 empty] | No | 0
VD-9001-210-PFD-001 | 0 | Process Flow Diagram | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-10 | 2020-06-18 11:22 | 2020-06-18 11:23 | Yes | 8 | [9 empty] | No | -13
VD-9001-210-CAL-002 | 0 | Dispersion Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-12-03 |  |  | No | -167 | [9 empty] | No | 0
VD-9001-210-PID-001 | 0 | Piping and Instrumentation Diagram | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-21 | 2020-06-16 17:12 | 2020-06-16 17:12 | Yes | -5 | [9 empty] | No | -11
VD-9001-210-LST-003 | 0 | Utility Consumption List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-10 |  |  | No | -52 | [9 empty] | No | 0
VD-9001-210-DSH-001 | 0 | Flare Data Sheet | PV-210 | Masnout Felezi Sangin (MFS) | 2020-12-20 |  |  | No | -184 | [9 empty] | No | 0
VD-9001-210-CAL-003 | 0 | Structural Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-28 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-210-DWG-001 | 0 | Derrick Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-06 |  |  | No | -79 | [9 empty] | No | 0
VD-9001-210-DWG-002 | 0 | Derrick Assembly and Bolt Location Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-210-DWG-003 | 0 | Template Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-01 |  |  | No | -43 | [9 empty] | No | 0
VD-9001-210-DWG-004 | 0 | Foundation Loading and Anchor Bolts Arrangement | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-06 |  |  | No | -48 | [9 empty] | No | 0
VD-9001-210-CAL-004 | 0 | Mechanical Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-06 |  |  | No | -17 | [9 empty] | No | 0
VD-9001-210-DWG-005 | 0 | General Arrangement Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-16 |  |  | No | -89 | [9 empty] | No | 0
VD-9001-210-DWG-006 | 0 | Flare Tip Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-22 |  |  | No | -64 | [9 empty] | No | 0
VD-9001-210-DWG-007 | 0 | Molecular Seal Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-05 |  |  | No | -47 | [9 empty] | No | 0
VD-9001-210-DWG-008 | 0 | Riser Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-29 |  |  | No | -40 | [9 empty] | No | 0
VD-9001-210-DWG-009 | 0 | Seal Pot Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-29 |  |  | No | -102 | [9 empty] | No | 0
VD-9001-210-DWG-010 | 0 | Ladder and Platform Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-12-02 |  |  | No | -166 | [9 empty] | No | 0
VD-9001-210-CAL-005 | 0 | Davit Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-30 |  |  | No | -41 | [9 empty] | No | 0
VD-9001-210-DWG-011 | 0 | Davit and Winch Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-31 |  |  | No | -73 | [9 empty] | No | 0
VD-9001-210-DWG-012 | 0 | Ground Winch and Pulley Detail Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-10-01 |  |  | No | -104 | [9 empty] | No | 0
VD-9001-210-DWG-013 | 0 | Tip Lowering Layout | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-12 |  |  | No | -85 | [9 empty] | No | 0
VD-9001-210-DWG-014 | 0 | Key Plan | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-29 |  |  | No | -40 | [9 empty] | No | 0
VD-9001-210-DWG-015 | 0 | Name Plate Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-23 |  |  | No | -96 | [9 empty] | No | 0
VD-9001-210-DWG-016 | 0 | NDT Map Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-27 |  |  | No | -100 | [9 empty] | No | 0
VD-9001-210-DWG-017 | 0 | Service Piping Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-28 |  |  | No | -101 | [9 empty] | No | 0
VD-9001-210-LST-004 | 0 | Line List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-15 |  |  | No | -57 | [9 empty] | No | 0
VD-9001-210-CAL-006 | 0 | Safety Valves Calculation | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-13 |  |  | No | -55 | [9 empty] | No | 0
VD-9001-210-LST-005 | 0 | Alarm and Set Point List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-21 |  |  | No | -32 | [9 empty] | No | 0
VD-9001-210-LST-006 | 0 | Instrument List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-27 |  |  | No | -38 | [9 empty] | No | 0
VD-9001-210-LST-007 | 0 | I/O List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-02 |  |  | No | -44 | [9 empty] | No | 0
VD-9001-210-DSH-002 | 0 | Instrument Data Sheet | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-06 |  |  | No | -48 | [9 empty] | No | 0
VD-9001-210-DWG-018 | 0 | Ignition and Control Panel Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-16 |  |  | No | -58 | [9 empty] | No | 0
VD-9001-210-DWG-019 | 0 | Instrument Hook Up Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-13 |  |  | No | -55 | [9 empty] | No | 0
VD-9001-210-DWG-020 | 0 | Instrument Layout and Cable Routing Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-13 |  |  | No | -86 | [9 empty] | No | 0
VD-9001-210-DWG-021 | 0 | Junction Box Terminal Arrangement | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-210-DWG-022 | 0 | Ignition and Control Panel Wiring Diagram | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-20 |  |  | No | -31 | [9 empty] | No | 0
VD-9001-210-CAT-001 | 0 | Instrument Catalogue | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-17 |  |  | No | -151 | [9 empty] | No | 0
VD-9001-210-DWG-023 | 0 | AWL Support Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-11 |  |  | No | -145 | [9 empty] | No | 0
VD-9001-210-DWG-024 | 0 | AWL Conduit Drawing | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-13 |  |  | No | -86 | [9 empty] | No | 0
VD-9001-210-LST-008 | 0 | Cable List | PV-210 | Masnout Felezi Sangin (MFS) | 2020-09-13 |  |  | No | -86 | [9 empty] | No | 0
VD-9001-210-DWG-025 | 0 | AWL Panel Wiring Diagram | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-26 |  |  | No | -37 | [9 empty] | No | 0
VD-9001-210-SLD-001 | 0 | Single Line Diagram | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-28 |  |  | No | -162 | [9 empty] | No | 0
VD-9001-210-CAT-002 | 0 | AWL Catalogue | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-17 |  |  | No | -151 | [9 empty] | No | 0
VD-9001-210-WBK-001 | 0 | Welding Book | PV-210 | Masnout Felezi Sangin (MFS) | 2020-07-29 |  |  | No | -40 | [9 empty] | No | 0
VD-9001-210-WPS-001 | 0 | Welding Procedure for Site Welds | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-19 |  |  | No | -153 | [9 empty] | No | 0
VD-9001-210-PCJ-001 | 0 | NDT Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-09 |  |  | No | -51 | [9 empty] | No | 0
VD-9001-210-PCJ-002 | 0 | PMI Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-13 |  |  | No | -55 | [9 empty] | No | 0
VD-9001-210-PCJ-003 | 0 | Surface Preparation and Painting Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-14 |  |  | No | -148 | [9 empty] | No | 0
VD-9001-210-PCJ-004 | 0 | Packing, Shipping and Marking Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-14 |  |  | No | -148 | [9 empty] | No | 0
VD-9001-210-PCJ-005 | 0 | Winch Test Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-30 |  |  | No | -164 | [9 empty] | No | 0
VD-9001-210-PCJ-006 | 0 | Functional Test Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-12-24 |  |  | No | -188 | [9 empty] | No | 0
VD-9001-210-PCJ-007 | 0 | Pickling and Passivation Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-14 |  |  | No | -148 | [9 empty] | No | 0
VD-9001-210-PCJ-008 | 0 | Erection Procedure | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-20 |  |  | No | -62 | [9 empty] | No | 0
VD-9001-210-PCJ-009 | 0 | Hydrostatic Test Procedure for Molecular Seal | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-12 |  |  | No | -146 | [9 empty] | No | 0
VD-9001-210-PCJ-010 | 0 | Pneumatic Test Procedure for Control Panel | PV-210 | Masnout Felezi Sangin (MFS) | 2020-11-23 |  |  | No | -157 | [9 empty] | No | 0
VD-9001-210-MNL-001 | 0 | Operating and Safety Manual | PV-210 | Masnout Felezi Sangin (MFS) | 2020-12-02 |  |  | No | -166 | [9 empty] | No | 0
VD-9001-210-MNL-002 | 0 | HSE Plan | PV-210 | Masnout Felezi Sangin (MFS) | 2020-08-12 |  |  | No | -54 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-011 | 2 | ASU P&ID - PURIFICATION SYSTEM ADSORBER | PR-104(1) | HATCO CO. | 2020-06-21 |  |  | No | -2 | [9 empty] | No | 0
VD-9001-307A1-PID-001 | 2 | PUMP P&I DRAWING FOR CONVERTER BW CIRCULATION PUMPS P2002AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307A1-PID-004 | 2 | PUMP P&I DRAWING FOR MP BOILER FEED WATER PUMPS P4002ABC | MC-307A1 | Deep Blue Pump Co. | 2020-06-25 |  |  | No | -6 | [9 empty] | No | 0
VD-9001-307B-ITP-001 | 2 | PUMP TEST & INSPECTION PLAN | MC-307B | Deep Blue Pump Co. | 2020-06-29 20:01 |  |  | No | -10 | [9 empty] | No | 0
VD-9001-307A1-PID-002 | 2 | PUMP P&I DRAWING FOR FIRST SATURATOR PUMPS P2003AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-104(1)-PPL-010 | 3 | ASU PLOT PLAN | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-PID-005 | 2 | PUMP P&I DRAWING FOR COOLING WATER SUPPLY PUMPS P6301ABCDEF | MC-307A1 | Deep Blue Pump Co. | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-012 | 2 | ASU P&ID - PURIFICATION SYSTEM STEAM HEATER | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307A1-PID-006 | 2 | PUMP P&I DRAWING FOR CONDENSATE PUMPS P4005AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-26 |  |  | No | -7 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-013 | 2 | ASU P&ID - PURIFICATION TEMP. DECREASED, PRESSURE REDUCER | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-014 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, EXPANDER SYSTEM | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-017 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, HP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-06-20 |  |  | No | -1 | [9 empty] | No | 0
VD-9001-307B-DWG-127 | 2 | PUMP NAME PLATE DRAWING FOR SECOND SATURATION PUMPS P-1002 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-30 20:00 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307B-DWG-126 | 2 | PUMP NAME PLATE DRAWING FOR CONDENSATE PUMPS P-1001 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-30 20:00 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-307B-DWG-128 | 2 | PUMP NAME PLATE DRAWING FOR CONVERTER STEAM CONDENSATE PUMPS P-2004 A/B | MC-307B | Deep Blue Pump Co. | 2020-06-30 20:00 |  |  | No | -11 | [9 empty] | No | 0
VD-9001-502-GAD-001 | 1 | General arrangement , front view & opening diagrams For MV Switchgear (MS-SWB2A-01) | EL-502 | IRAN TABLO | 2020-06-23 |  |  | No | -4 | [9 empty] | No | 0
VD-9001-201B-MNL-001 | 2 | INSTRUCTION OPERATING MANUAL (4134/IOM) | PV-201B | Brembana & Rolle S.p.A. | 2020-06-23 |  |  | No | -4 | [9 empty] | No | 0
VD-9001-307A1-PID-003 | 2 | PUMP P&I DRAWING FOR HP BOILER FEED WATER PUMPS P4001ABC | MC-307A1 | Deep Blue Pump Co. | 2020-06-27 |  |  | No | -8 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-018 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LP MAIN HEAT EXCHANGER | PR-104(1) | HATCO CO. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-307A1-DSH-021 | 3 | STEAM TURBINE DATASHEET WITH CURVE FOR PT4001AB | MC-307A1 | Deep Blue Pump Co. | 2020-06-28 |  |  | No | -9 | [9 empty] | No | 0
VD-9001-210-DIS-001 | 1 | Vendor Document Index and Schedule | PV-210 | Masnout Felezi Sangin (MFS) | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-019 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, SUB-COOLER | PR-104(1) | HATCO CO. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0
VD-9001-104(1-K)-PID-020 | 2 | ASU P&ID - RECTIFICATION COLUMN SYSTEM, LOWER COLUMN | PR-104(1) | HATCO CO. | 2020-06-22 |  |  | No | -3 | [9 empty] | No | 0