## DCI1 (2)
1204-00-PV-TBA-204B | 01 | TECHNICAL BID ANALYSIS FOR PRESSURE VESSELS (GROUP II) | DE | IFE | MD | PS-OT-T-0105 | 2015-09-23 |  | No | 1685 | 1204-Owner-v | 2015-09-26 15:14 | TBA | 2015-09-23 | 0 | 0 | 0 | 2015-09-23 | 2015-11-19 |  | complete | 100%
1204-00-PI-APL-1300 | 00 | PIPING PLAN AREA-13 | DE | IFR | PI | PS-OT-T-0283 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:50 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-00-PI-REQ-404B | 00 | REQUISITION FOR A/G VALVES(MTO II) | DE | IFI | PI | PS-OT-T-0946 | 2020-04-11 |  | No | 23 |  |  | REQ | 2020-05-28 | 0 | 0 | 2020-06-10 | * |  |  | InProgress | 90%
1204-00-PI-UPL-6400 | 03 | UNDER GROUND PIPING PLAN AREA-64 | DE | IFC-WH | PI | PS-OT-T-0629 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-18 13:10 | CDW | 2018-06-25 | 0 | 0 | 0 | 2018-06-25 | 2018-06-24 | MT-PS-9609-CS-088 | InProgress | 90%
1204-10-PR-PID-103 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- HYDROGENATION & DESULPHURIZATION | DE | IFC-WH | PR | PS-OT-T-0749 | 2019-01-23 |  | No | 467 | 1204-Owner-v | 2019-01-27 13:53 | EDW | 2021-04-01 | 0 | 0 | 2021-04-01 | 2019-01-30 | 2020-04-20 | MT-PS-9609-CS-0331 | InProgress | 90%
1204-10-PR-PID-110 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- FUEL GAS SYSTEM | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:23 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-22-PR-DSH-131 | 00 | Process Instrument Data Sheet for Control Valves | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-30-PR-PID-308 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-PURE METHANOL COOLING | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:44 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-10-ST-DWG-150 | 01 | REFORMER (VERTICAL COLD AIR DUCT) / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0672 | 2018-08-28 |  | No | 615 | 1204-Owner-v | 2018-09-01 09:43 | CDW | 2018-09-03 | 0 | 0 | 0 | 2018-09-03 |  |  | complete | 100%
1204-04-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-04 | DE | IFR | EL | PS-OT-T-0296 | 2016-06-25 | 2016-07-21 14:39 | Yes | 12 | 1204-Owner-v | 2016-06-26 08:29 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | 2016-07-02 | 2016-06-29 | MT-PS-9301-CS-168 | InProgress | 80%
1204-90-EL-DWG-410 | 01 | CLINIC & TECHNICAL BUILDING LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:12 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-84-HS-DSH-002 | 00 | DATA SHEET FOR POC WATER SUMP SU-8401 | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:03 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-84-HS-DSH-006 | 02 | DATA SHEET FOR SANITARY DISCHARGE PUMPS (P-8402A/B) | DE | IFR | HSE | PS-OT-T-0861 | 2020-01-01 |  | No | 124 | 1204-Owner-v | 2020-01-02 08:27 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 0 | 14.01.2020 | MT-PS-9301-CS-0256 | InProgress | 80%
1204-00-IN-DSH-642 | 01 | DATA SHEET FOR PCV | DE | IFR | IN | PS-OT-T-0918 | 2020-02-26 |  | No | 68 | 1204-Owner-v | 2020-02-26 16:28 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-03-14 | MT-PS-9609-CS-0311 | InProgress | 80%
1204-00-IN-DWG-001 | 01 | INSTRUMENT LAYOUT KEY PLAN | DE | IFR | IN | PS-OT-T-373 | 2016-12-06 |  | No | 1245 | 1204-Owner-v | 2016-12-07 08:56 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | * | 2017-02-15 | MT-PS-9301-CS-213 | InProgress | 80%
1204-00-IN-SKT-006 | 01 | INSTRUMENT MOUNTING DETAILS | DE | IFC | IN | PS-OT-T-0233 | 2016-04-10 |  | No | 1485 | 1204-Owner-v | 2016-04-11 13:27 | CDW | 2016-04-10 | 0 | 0 | 0 | 2016-04-10 |  |  | complete | 100%
1204-00-HM-TBA-254 | 00 | TECHNICAL BID ANALYSIS FOR AUXILIARY BOILER | DE | IFE | MD | TM-OT-9001-T-0416 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:33 | TBA | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 | 2014-12-10 | MT-TM-9301-CS-024 | complete | 100%
1204-00-PV-REQ-210 | 01 | REQUISITION FOR FLARE STACK | DE | IFP | MD | PS-OT-T-0930 | 2020-03-07 |  | No | 58 | 1204-Owner-v | 2020-03-09 09:11 | REQ | 2020-03-07 | 0 | 0 | 0 | 2020-03-07 |  |  | complete | 100%
1204-30-PR-PID-307 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-FUSEL OIL PUMPS | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:44 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-40-PR-PID-406 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- STEAM CONDENSATE COLLECTION | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:09 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-62-PR-DSH-131 | 00 | Process Instrument Data Sheet for Control Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | * | 2016-01-24 | MT-PS-9301-CS-093 | InProgress | 80%
1204-63-PR-DSH-139 | 00 | Process Instrument Data Sheet for Temperature Gauges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-00-ST-DWG-053 | 02 | PIPE RACK ZONE 8 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0034 | 2015-05-06 |  | No | 1825 | 1204-Owner-v | 2015-05-07 09:17 | CDW | 2015-05-06 | 0 | 0 | 0 | 2015-05-06 |  |  | complete | 100%
1204-10-ST-DWG-135 | 01 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 /STEEL STRUCTURE (ELEVATION & DETS.) | DE | IFC | ST | PS-OT-T-0788 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:19 | CDW | 2019-05-08 | 0 | 0 | 0 | 2019-05-08 |  |  | complete | 100%
1204-30-ST-DWG-307 | 04 | STRUCTURE "B" FOR D-3003 & E-3003A/B / CONCRETE STRUCTURE (G.A. PLAN & DETAILS) | DE | IFC | ST | PS-OT-T-0441 | 2017-04-17 |  | No | 1113 | 1204-Owner-v | 2017-04-18 07:38 | CDW | 2017-04-30 | 0 | 0 | 0 | 2017-04-30 |  |  | complete | 100%
1204-30-ST-DWG-345 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / COLUMNS (G.A. PLAN & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0393 | 2016-12-28 |  | No | 1223 | 1204-Owner-v | 2016-12-28 16:37 | CDW | 2016-12-28 | 0 | 0 | 0 | 2016-12-28 |  |  | complete | 100%
1204-90-ST-DWG-1006 | 02 | CONTROL ROOM & LABORATORY / BEAMS (R.C. DETAILS II ) | DE | IFC | ST | TM-OT-9001-T-0347 | 2014-01-22 |  | No | 2294 | 1204-Owner-v | 2015-09-16 18:22 | CDW | 2014-01-22 | 0 | 0 | 0 | 2014-01-22 |  |  | complete | 100%
1204-90-ST-DWG-941 | 01 | SUBSTATION / BEAMS (R.C. I) | DE | IFC | ST | TM-OT-9001-T-0300 | 2013-07-04 |  | No | 2496 | 1204-TKT-COLANGELI | 2013-07-03 11:40 | CDW | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-10-ST-DWG-158 | 01 | T-1001 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0208 | 2016-03-02 |  | No | 1524 | 1204-Owner-v | 2016-03-05 13:34 | CDW | 2016-03-02 | 0 | 0 | 0 | 2016-03-02 |  | Final Checked | complete | 100%
1204-04-EL-DWG-011 | 00 | LIGHTING LAYOUT AREA-04 R-1001, R-1002 A/B, T-1001 AND ADJACENT EQUIPMENT | DE | IFR | EL | PS-OT-T-477 | 2017-08-29 |  | No | 979 | 1204-Owner-v | 2017-08-30 09:55 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | * | 2018-05-31 | MT-PS-9301-CS-241-R | InProgress | 80%
1204-00-ST-DWG-085 | 02 | PIPE RACK STAIRS (ZONE 1 TO 5) / STRUCTURE (G.A. & SECTIONS) | DE | IFC | ST | PS-OT-T-0276 | 2016-06-05 |  | No | 1429 | 1204-Owner-v | 2016-06-06 09:13 | CDW | 2016-06-12 | 0 | 0 | 0 | 2016-06-12 |  |  | complete | 100%
1204-90-HV-DSH-023 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR BATTERY ROOM IN SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:40 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-90-HV-DSH-017 | 00 | DATA SHEET FOR LABORATORY HOOD CENTRIFUGAL EXHAUST FAN FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:20 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-30-ST-DWG-336 | 02 | STRUCTURE "E" FOR E-3004,E-3012 / COLUMNS (G.A. PLAN & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0413 | 2017-02-07 |  | No | 1182 | 1204-Owner-v | 2017-02-08 14:34 | CDW | 2017-02-14 | 0 | 0 | 0 | 2017-02-14 |  |  | complete | 100%
1204-00-ST-DWG-1105 | 01 | RETAINING WALL / G.A. PLAN & R.C. DETAILS (II) | DE | IFC | ST | TM-OT-9001-T-0367 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 13:31 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-20-PI-LST-6500 | 01 | U/G ISOMETRIC LIST OF AREA-65 | DE | IFC-WH | PI | PS-OT-T-0665 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-17 09:38 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 90%
1204-30-PI-APL-2800 | 01 | PIPING PLAN AREA-28 | DE | IFC-WH | PI | PS-OT-T-0666 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-17 09:37 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-60-PI-UPL-6200 | 02 | UNDER GROUND PIPING PLAN AREA-62 | DE | IFC-WH | PI | PS-OT-T-0597 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:25 | CDW | 2018-05-03 | 0 | 0 | 0 | 2018-05-03 |  |  | InProgress | 90%
1204-00-PI-TBA-463A | 00 | TECHNICAL BID ANALYSIS FOR U/G GASKETS(MTO I) | DE | IFE | PI | PS-OT-T-0266 | 2016-05-18 |  | No | 1447 | 1204-Owner-v | 2016-05-18 16:10 | TBA | 2016-05-28 | 0 | 0 | 0 | 2016-05-28 |  |  | complete | 100%
1204-00-PI-ISO-3900 | 00 | A/G ISOMETRIC DRAWING OF AREA-39 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:03 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-30-ST-DWG-343 | 02 | STRUCTURE "F" FOR D-3004, D-3005, E-3003C/D, E-3005, E-3009/CONCRETE STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0444 | 2017-04-23 |  | No | 1107 | 1204-Owner-v | 2017-04-30 15:59 | CDW | 2017-05-07 | 0 | 0 | 0 | 2017-05-07 |  |  | complete | 100%
1204-00-IN-LST-010 | 00 | INSTRUMENT LIST (UNITS 200, 300 & UTILITIES) | DE | IFR | IN | TM-OT-9001-T-0298 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:46 | LIST | 2020-04-14 | 0 | 0 | 2020-04-14 | 2013-07-03 |  |  | InProgress | 90%
1204-90-HS-DWG-006 | 02 | FIRE ALARM LAYOUT FOR FIRE STATION | DE | IFE | HSE | PS-OT-T-379 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:09 | EDW | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-10-PI-LST-6800 | 01 | U/G ISOMETRIC LIST OF AREA-68 | DE | IFC-WH | PI | PS-OT-T-0647 | 2018-07-15 |  | No | 659 | 1204-Owner-v | 2018-07-19 10:31 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-07-21 | 2018-08-04 | MT-PS-9609-CS-098-R | InProgress | 90%
1204-10-PI-ISO-7200 | 01 | U/G ISOMETRIC DRAWING OF AREA-72 | DE | IFC-WH | PI | PS-OT-T-0614 | 2018-05-19 |  | No | 716 | 1204-Owner-v | 2018-05-20 12:53 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-06-02 |  |  | InProgress | 90%
1204-22-PI-APL-1900 | 00 | PIPING PLAN AREA-19 | DE | IFR | PI | PS-OT-T-0195 | 2016-02-13 |  | No | 1542 | 1204-Owner-v | 2016-02-15 11:29 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 0 | 0 | 0 | InProgress | 80%
1204-30-PI-LST-6700 | 01 | U/G ISOMETRIC LIST OF AREA-67 | DE | IFC-WH | PI | PS-OT-T-0650 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-29 09:23 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-07-29 | MT-PS-9609-CS-102 | InProgress | 90%
1204-60-PI-LST-6200 | 01 | U/G ISOMETRIC LIST OF AREA-62 | DE | IFC-WH | PI | PS-OT-T-0597 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:19 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 90%
1204-90-HV-DSH-029 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR CO2 ROOM IN SUBSTATION | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:38 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-00-IN-REQ-602 | 01 | REQUISITION FOR EMERGENCY SHUTDOWN SYSTEM | DE | IFP | IN | PS-OT-T-0910 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 17:07 | REQ | 2020-02-24 | 0 | 0 | 0 | 2020-02-24 | 2020-03-02 | MT-PS-9609-CS-0300 | complete | 100%
1204-40-PI-APL-4200 | 00 | PIPING PLAN AREA-42 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:04 | CDW | 2020-01-13 | 0 | 0 | 2020-06-25 | 2016-09-03 |  |  | InProgress | 80%
1204-10-PV-DSH-202 | 00 | MECHANICAL DATA SHEET FOR SULPHUR REMOVAL REACTORS (R-1002A/B) | DE | IFR | MD | PS-OT-T-0124 | 2015-11-02 |  | No | 1645 | 1204-Owner-v | 2015-11-02 16:28 | DSH | 2015-11-04 | 0 | 0 | 0 | 2015-11-04 | 2015-11-14 | MT-PS-9301-CS-041 | InProgress | 80%
1204-40-ST-DWG-451 | 02 | BOILER (PU-4006 A ) / FDN. (G.A. & R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0237 | 2016-04-13 |  | No | 1482 | 1204-Owner-v | 2016-04-16 14:09 | CDW | 2016-04-19 | 0 | 0 | 0 | 2016-04-19 |  |  | complete | 100%
1204-02-EL-DWG-021 | 00 | EARTHING LAYOUT FOR AREA-02 D-2003, E-2001A/B, 2002, 2003A/B, 2005A/B, 2006 AND R-2001 | DE | IFR | EL | PS-OT-T-0114 | 2015-10-10 | 2016-01-14 12:02 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:07 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-10-14 | 2015-11-19 | MT-PS-9301-CS-042 | InProgress | 80%
1204-00-IN-MSS-615 | 01 | MATERIAL STANDARD SPECIFICATION FOR SIGHT GLASSES | DE | IFE | IN | PS-OT-T-360 | 2016-11-12 |  | No | 1269 | 1204-Owner-v | 2016-11-16 11:17 | SPEC | 2016-11-12 | 0 | 0 | 0 | 2016-11-12 | 2016-11-29 | MT-PS-9301-CS-198 | complete | 100%
1204-71-IN-DWG-033 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 33) | DE | IFR | IN | PS-OT-T-0161 | 2015-12-28 |  | No | 1589 | 1204-Owner-v | 2015-12-30 13:59 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | 2016-01-06 | 2016-01-10 | MT-PS-9301-CS-081 | InProgress | 80%
1204-02-EL-DWG-002 | 00 | POWER LAYOUT AREA-02 (AE-2001) | DE | IFR | EL | PS-OT-T-0193 | 2016-02-02 | 2016-07-21 15:09 | Yes | 156 | 1204-Owner-v | 2016-02-02 17:01 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2016-02-17 | 2016-02-13 | MT-PS-9301-CS-106 | InProgress | 80%
1204-00-EL-DSH-5172 | 01 | DATA SHEET FOR LV VSD PANELS - MS-VSD-02 | DE | IFR | EL | PS-OT-T-0731 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:56 | DSH | 2020-04-21 | 0 | 0 | 2020-04-21 | * |  |  | InProgress | 80%
1204-00-PI-MTO-466A | 00 | MATERIAL TAKE OFF FOR U/G POLYPROPYLENE ITEMS (MTO I) | DE | IFE | PI | PS-OT-T-0542 | 2018-01-21 |  | No | 834 | 1204-Owner-v | 2018-01-27 14:51 | LIST | 2018-01-21 | 0 | 0 | 0 | 2018-01-21 | 2018-01-28 | MT-PS-9609-CS-020 | complete | 100%
1204-65-PR-DSH-102 | 00 | DATA SHEET FOR FUEL GAS FILTER | BE | IFR | PR | TM-OT-9001-T-0276 | 2013-05-16 |  | No | 2545 | 1204-TKT-COLANGELI | 2013-05-16 11:58 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2013-05-16 |  |  | InProgress | 80%
1204-90-HS-DWG-008 | 02 | FIRE ALARM LAYOUT FOR WORK SHOP | DE | IFE | HSE | PS-OT-T-0128 | 2015-11-04 |  | No | 1643 | 1204-Owner-v | 2015-11-05 10:30 | EDW | 2015-11-17 | 0 | 0 | 0 | 2015-11-17 | 2015-11-29 | MT-PS-9301-CS-048 | complete | 100%
1204-90-ST-DWG-1008 | 02 | SUBSTATION / INSERT PLATES II | DE | IFC | ST | PS-OT-T-0014 | 2015-04-04 |  | No | 1857 | 1204-Owner-v | 2015-04-05 16:09 | CDW | 2015-04-04 | 0 | 0 | 0 | 2015-04-04 |  |  | complete | 100%
1204-10-PI-LST-7200 | 01 | U/G ISOMETRIC LIST OF AREA-72 | DE | IFC-WH | PI | PS-OT-T-0614 | 2018-05-19 |  | No | 716 | 1204-Owner-v | 2018-05-20 12:57 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-06-02 |  |  | InProgress | 90%
1204-65-PR-LST-001 | 01 | EQUIPMENT LIST FOR FUEL GAS SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 11:59 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 |  |  | complete | 100%
1204-00-ST-REQ-743 | 00 | REQUISITION FOR STEEL GRATING | DE | IFI | ST | PS-OT-T-0493 | 2017-09-23 |  | No | 954 | 1204-Owner-v | 2017-09-25 08:18 | REQ | 2017-10-02 | 0 | 0 | 0 | 2017-10-02 | 2017-11-22 | MT-PS-9301-CS-264 | InProgress | 90%
1204-40-ST-DWG-429 | 01 | D-4004 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0272 | 2016-05-29 |  | No | 1436 | 1204-Owner-v | 2016-05-30 10:17 | CDW | 2016-05-29 | 0 | 0 | 0 | 2016-05-29 | 2016-06-01 | MT-PS-9301-CS-156 | complete | 100%
1204-90-ST-DWG-903 | 05 | CONTROL ROOM & LABORATORY / G.A PLAN | DE | IFC-WH | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:18 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 |  |  | complete | 100%
1204-90-ST-DWG-917 | 04 | CONTROL ROOM & LABORATORY / SLABS (G.A. , R.C. & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:57 | CDW | 2014-08-20 | 0 | 0 | 0 | 2014-08-20 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-90-ST-DWG-968 | 01 | ADMINISTRATION , RESTAURANT & CLINIC BLDG. / G.A FOR GROUND FLOOR PLAN | DE | IFC | ST | TM-OT-9001-T-0116 | 2012-06-19 |  | No | 2876 | 1204-Owner-v | 2015-09-16 18:35 | CDW | 2012-06-19 | 0 | 0 | 0 | 2012-06-19 |  |  | complete | 100%
1204-90-HV-DSH-090 | 01 | DATA SHEET FOR ROOF TYPE EXHAUST FAN FOR WAREHOUSE AREA IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:46 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-65-PR-PID-651 | 01 | PIPING & INSTRUMENTAITION DIAGRAM FOR FUEL GAS SYSTEM | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:30 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | * | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-84-HS-BOD-001 | 01 | BASIS OF DESIGN FOR EFFLUENT WATER TREATMENT | DE | IFR | HSE | PS-OT-T-0688 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:21 | EDW | 2019-10-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-00-EL-DSH-5023 | 01 | DATA SHEET FOR 6KV SWITCHGEAR (SS01-SWB2A,B-01) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:07 | Yes | 28 | 1204-Owner-v | 2018-01-02 12:24 | DSH | 2020-05-25 | 0 | 0 | 2020-05-25 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-03-EL-DWG-014 | 00 | LIGHTING LAYOUT FOR AREA-03 AE-3002 | DE | IFR | EL | PS-OT-T-0186 | 2016-01-18 | 2016-07-24 11:28 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:39 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2016-01-24 | 2016-01-26 | MT-PS-9301-CS-096 | InProgress | 80%
1204-03-EL-DWG-023 | 00 | EARTHING LAYOUT AREA-03 AE-3002 | DE | IFR | EL | PS-OT-T-0204 | 2016-02-28 | 2016-07-23 10:08 | Yes | 132 | 1204-Owner-v | 2016-03-02 15:18 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2016-04-05 | MT-PS-9301-CS-119-1 | InProgress | 80%
1204-20-ST-DWG-265 | 01 | E-2004 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0299 | 2016-06-28 |  | No | 1406 | 1204-Owner-v | 2016-06-28 17:33 | CDW | 2016-06-28 | 0 | 0 | 0 | 2016-06-28 |  |  | complete | 100%
1204-00-PI-REQ-461AF | 01 | REQUISITION FOR U/G FITTINGS(MTO I) | DE | IFP | PI | PS-OT-T-0404 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-06-06 12:15 | REQ | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-30-PI-APL-2400 | 00 | PIPING PLAN AREA-24 | DE | IFR | PI | PS-OT-T-0437 | 2017-04-09 |  | No | 1121 | 1204-Owner-v | 2017-04-16 14:53 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2017-04-25 |  |  | InProgress | 80%
1204-20-PR-PID-205 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS CONVERTER | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:24 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-22-PR-DSH-132 | 00 | Process Instrument Data Sheet for On / Off Valves | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-62-PR-DSH-133 | 00 | Process Instrument Data Sheet for Safety Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-07-24 |  |  | InProgress | 80%
1204-62-PR-PID-621 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR INSTRUMENT AIR / PLANT AIR SYSTEM (1 OF 2) | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:26 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-64-PR-REQ-101 | 00 | REQUISITION FOR MIXED BED POLISHER UNIT (PU-6401) | DE | IFI | PR | PS-OT-T-0055 | 2015-06-01 |  | No | 1799 | 1204-Owner-v | 2015-06-02 14:52 | REQ | 2020-04-14 | 0 | 0 | 2020-04-14 | 2015-06-01 |  |  | InProgress | 60%
1204-10-ST-DWG-147 | 03 | REFORMER (H-1001) / FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0796 | 2019-05-20 |  | No | 350 | 1204-Owner-v | 2019-05-22 18:20 | CDW | 2019-05-23 | 0 | 0 | 0 | 2019-05-23 |  |  | complete | 100%
1204-10-ST-DWG-151 | 02 | REFORMER (FT-1002) / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0697 | 2018-10-09 |  | No | 573 | 1204-Owner-v | 2018-10-13 14:15 | CDW | 2018-10-15 | 0 | 0 | 0 | 2018-10-15 |  |  | complete | 100%
1204-64-PV-DSH-209 | 01 | MECHANICAL DATA SHEET FOR CAUSTIC STORAGE DRUM (D-6402) | DE | IFE | MD | TM-OT-9001-T-0149 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2014-09-30 11:00 | DSH | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-20-QC-SOI-105 | 00 | SCOPE OF INSPECTION FOR HYDROGEN RECOVERY UNIT | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-30-PV-DSH-233 | 01 | MECHANICAL DATA SHEET FOR FIRST REFINING COLUMN (T-3002) | DE | IFE | MD | TM-OT-9001-T-0343 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:20 | DSH | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-22-PR-DSH-143 | 00 | Process Instrument Data Sheet for Pressure Switches | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-64-ST-DWG-711 | 02 | TK-6401 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0364 | 2014-05-06 |  | No | 2190 | 1204-TKT-COLANGELI | 2014-05-06 12:28 | CDW | 2014-05-06 | 0 | 0 | 0 | 2014-05-06 |  |  | complete | 100%
1204-20-RE-DSH-037 | 01 | DATA SHEET FOR CONVERTER STEAM CONDENSATE PUMPS (P-2004 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:19 | DSH | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 | 2017-05-03 | MT-PS-9301-CS-225-R | InProgress | 80%
1204-40-RE-DSH-046 | 00 | DATA SHEET FOR CONDENSATE PUMPS FOR AE-4001 (P-4004 A/B) | DE | IFR | MC | PS-OT-T-0838 | 2019-11-20 |  | No | 166 | 1204-Owner-v | 2019-11-27 10:21 | DSH | 2019-11-20 | 0 | 0 | 0 | 0 |  | MT-PS-9301-CS-0246 | InProgress | 80%
1204-30-HM-DSH-246 | 00 | MECHANICAL DATA SHEET FOR FIRST REFINING COLUMN FEED PREHEATER (E-3012) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:27 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DWG-045 | 00 | ADMINISTRATION - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFE | HV | PS-TM-T-0306 | 1930-06-14 |  | No | 32832 | 1204-TKT-COLANGELI | 2014-07-07 13:12 | CDW | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-10-19 |  | complete | 100%
1204-00-ST-DWG-016 | 01 | PIPE RACK STAIRS / FDN. (G.A. PLANS & R.C. DETAILS I) | DE | IFC | ST | PS-OT-T-0155 | 2015-12-21 |  | No | 1596 | 1204-Owner-v | 2015-12-22 15:43 | CDW | 2015-12-21 | 0 | 0 | 0 | 2015-12-21 | 2015-12-23 | MT-PS-9301-CS-063 | complete | 100%
1204-00-QC-SOI-201B | 00 | SCOPE OF AUTO THERMAL REACTOR | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-ST-DWG-172 | 02 | PIPE BRIDGE " I " / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0725 | 2018-12-10 |  | No | 511 | 1204-Owner-v | 2018-12-12 08:11 | CDW | 2018-12-10 | 0 | 0 | 0 | 2018-12-10 |  |  | complete | 100%
1204-00-ST-DWG-1140 | 01 | VB-6301 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0609 | 2018-05-13 |  | No | 722 | 1204-Owner-v | 2018-05-13 17:06 | CDW | 2018-05-15 | 0 | 0 | 0 | 2018-05-15 | 2018-05-15 | MT-PS-9609-CS-072-R | complete | 100%
1204-00-QC-SOI-745 | 00 | SCOPE OF INSPECTION FOR FABRICATION & SUPPLY OF GUARD RAIL | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PI-MTO-418 | 01 | MATERIAL TAKE OFF FOR FITTING FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0953 | 2020-04-21 |  | No | 13 | 1204-Owner-v | 2020-04-22 18:39 | MTO | 2020-04-21 | #N/A | #N/A | #N/A | 0 | 0 | 0 | complete | 100%
1204-30-ST-DWG-303 | 02 | STRUCTURE "B" FOR D-3003 & E-3003A/B / STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0452 | 2017-05-31 |  | No | 1069 | 1204-Owner-v | 2017-06-18 12:51 | CDW | 2017-05-31 | 0 | 0 | 0 | 2017-05-31 |  |  | complete | 100%
1204-90-ST-DWG-1023 | 02 | WORK SHOP / PLUMBING LAYOUT & DETAILS | DE | IFC | ST | PS-OT-T-0162 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2015-12-30 17:51 | CDW | 2015-12-30 | 0 | 0 | 0 | 2015-12-30 | 2016-01-16 | Final Checked | complete | 100%
1204-00-QC-SOI-531 | 00 | SCOPE OF INSPECTION FOR CABLE TRAYS AND LADDERS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-62-PR-DSH-140 | 00 | Process Instrument Data Sheet for Pressure Switches | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:57 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-07-24 |  |  | InProgress | 80%
1204-00-PI-REQ-421 | 00 | REQUISITION FOR BOLT&NUT FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-13 13:21 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-30-ST-DWG-322 | 01 | STRUCTURE "D" FOR E-3006,E-3010A/B / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0789 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:25 | CDW | 2019-05-08 | 0 | 0 | 0 | 2019-05-08 |  |  | complete | 100%
1204-20-PR-PID-210 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS STEAM CONDENSER | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:19 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-90-HS-LST-004 | 02 | SAFETY EQUIPMENT LIST FOR SUBSTATION | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:55 | LIST | 2016-12-16 | 0 | 0 | 0 | 2016-12-16 |  |  | complete | 100%
1204-00-ST-DWG-1114 | 01 | PIPE CULVERT / R.C. DETAILS (I) | DE | IFC | ST | PS-OT-T-0022 | 2015-04-18 |  | No | 1843 | 1204-Owner-v | 2015-04-19 10:24 | CDW | 2015-04-18 | 0 | 0 | 0 | 2015-04-18 |  |  | complete | 100%
1204-00-PI-APL-3900 | 00 | PIPING PLAN AREA-39 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:02 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 0 | 0 | 0 | InProgress | 80%
1204-10-IN-DWG-047 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 47) | DE | IFR | IN | PS-OT-T-0355 | 2016-10-29 |  | No | 1283 | 1204-Owner-v | 2016-11-02 14:09 | CDW | 2020-06-26 | 0 | 0 | 2020-06-26 | 0 | 0 | 0 | InProgress | 80%
1204-05-EL-SLD-068 | 00 | SINGLE LINE DIAGRAM FOR 05-LP-01 | DE | IFR | EL | PS-OT-T-0221 | 2016-03-14 | 2016-07-24 11:35 | Yes | 118 | 1204-Owner-v | 2016-03-14 11:10 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-17 | 2016-03-28 | MT-PS-9301-CS-118 | InProgress | 80%
1204-00-EL-DSH-5171 | 01 | DATA SHEET FOR LV VSD PANEL MS-VSD-01 | DE | IFR | EL | PS-OT-T-0731 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:56 | DSH | 2020-04-21 | 0 | 0 | 2020-04-21 | * |  |  | InProgress | 80%
1204-30-ST-DWG-324 | 01 | STRUCTURE "D" FOR E-3006 ,E-3010A/B / STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0789 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:25 | CDW | 2019-05-13 | 0 | 0 | 0 | 2019-05-13 |  |  | complete | 100%
1204-00-ST-DWG-183 | 01 | PIPE RACK ZONE 13 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0942 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:06 | CDW | 2020-03-31 | 0 | 0 | 2020-05-31 | * | 2020-04-06 | MT-PS-9609-CS-0325 | complete | 100%
1204-90-ST-DWG-1033 | 02 | WAREHOUSE / ELEVATIONS | DE | IFC | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 18:02 | CDW | 2013-01-10 | 0 | 0 | 0 | 2013-01-10 |  |  | complete | 100%
1204-90-ST-MTO-1073 | 00 | MATERIAL TAKE OFF FOR FIRE STATION. / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:26 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-008 | complete | 100%
1204-30-PV-DSH-234 | 01 | MECHANICAL DATA SHEET FOR SECOND REFINING COLUMN (T-3003) | DE | IFE | MD | TM-OT-9001-T-0348 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:35 | DSH | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-PR-UDD-019 | 03 | UTILITY DISTRIBUTION DIAGRAM FOR OILY WASTE WATER SYSTEM | DE | IFC-WH | PR | PS-OT-T-0624 | 2018-06-03 |  | No | 701 | 1204-Owner-v | 2018-06-13 14:52 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2018-06-17 | 2018-06-13 | MT-PS-9609-CS-081 | InProgress | 90%
1204-30-PV-DSH-218 | 01 | MECHANICAL DATA SHEET FOR FIRST REFINING COLUMN REFLUX DRUM (D-3003) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 14:35 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-00-EL-TBA-504 | 02 | TECHNICAL BID ANALYSIS FOR POWER & DISTRIBUTION TRANSFORMERS | DE | IFE | EL | PS-OT-T-0591 | 2018-04-19 |  | No | 746 | 1204-Owner-v | 2018-04-22 12:54 | TBA | 2019-12-31 | 0 | 0 | 2020-01-20 | 2018-05-09 | 2018-05-31 | MT-PS-9609-CS-066-R | complete | 100%
1204-22-PR-DSH-142 | 00 | Process Instrument Data Sheet for Level Switches | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-24 |  |  | InProgress | 80%
1204-64-PR-DSH-140 | 00 | Process Instrument Data Sheet for Analyzers | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-20-IN-DWG-026 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 26) | DE | IFR | IN | PS-OT-T-0140 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 09:07 | CDW | 2020-06-22 | 0 | 0 | 2020-06-22 | 2015-12-15 | 2016-01-12 | MT-PS-9301-CS-086 | InProgress | 80%
1204-63-IN-DWG-018 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 18) | DE | IFR | IN | PS-OT-T-0220 | 2016-03-14 |  | No | 1512 | 1204-Owner-v | 2016-03-14 11:10 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | * | 2016-03-16 | MT-PS-9301-CS-117-1 | InProgress | 80%
1204-40-RE-DSH-045 | 01 | DATA SHEET FOR LP CONDENSATE PUMPS (P-4003 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:20 | DSH | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 | 2017-05-03 | MT-PS-9301-CS-225-R | InProgress | 80%
1204-90-HV-DSH-014 | 00 | DATA SHEET FOR BAL. & SOL. ROOM HOOD CENTRIFUGAL EXHAUST FAN FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:15 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DWG-043 | 01 | ADMINISTRATION - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | TM-OT-9001-T-0382 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 13:19 | CDW | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-10-19 |  | complete | 100%
1204-00-PV-TBA-206A | 00 | TECHNICAL BID ANALYSIS FOR COLUMNS (GROUP I) | DE | IFE | MD | TM-OT-9001-T-0150 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2015-09-16 17:05 | TBA | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-00-PI-APL-3400 | 00 | PIPING PLAN AREA-34 | DE | IFR | PI | PS-OT-T-0287 | 2016-06-13 |  | No | 1421 | 1204-Owner-v | 2016-06-14 09:49 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-00-PI-UPL-6000 | 03 | UNDER GROUND PIPING PLAN AREA-60 | DE | IFC-WH | PI | PS-OT-T-0628 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-18 13:10 | CDW | 2018-06-24 | 0 | 0 | 0 | 2018-06-24 | 2018-06-24 | MT-PS-9609-CS-087 | InProgress | 90%
1204-10-PR-PID-106 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- PRE REFORMER | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-12-10 11:37 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-30-PR-PID-304 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-FIRST REFINING COLUMN | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:44 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-00-ST-DWG-060 | 04 | PIPE RACK ZONE 9 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0176 | 2016-01-09 |  | No | 1577 | 1204-Owner-v | 2016-01-10 09:13 | CDW | 2016-01-16 | 0 | 0 | 0 | 2016-01-16 | 2016-01-10 | MT-PS-9301-CS-084 | complete | 100%
1204-90-HV-DWG-071 | 02 | GUARD HOUSE - HVAC SYSTEM LAYOUT | DE | IFC | HV | TM-OT-9001-T-0379 | 2014-06-26 |  | No | 2139 | 1204-TKT-COLANGELI | 2014-06-26 13:14 | CDW | 2014-06-26 | 0 | 0 | 0 | 2014-06-26 | 2014-11-30 | MT-TM-9301-CS-018 | complete | 100%
1204-90-HV-DSH-037 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR LCR. AND SWR. IN FIRE STATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 15:01 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-ST-DWG-049 | 01 | PIPE RACK ZONE 7 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0087 | 2015-08-05 |  | No | 1734 | 1204-Owner-v | 2015-08-08 15:53 | CDW | 2015-08-05 | 0 | 0 | 0 | 2015-08-05 |  |  | complete | 100%
1204-30-ST-DWG-332 | 02 | STRUCTURE "E" FOR E-3004,E-3012 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0413 | 2017-02-07 |  | No | 1182 | 1204-Owner-v | 2017-02-08 14:32 | CDW | 2017-02-14 | 0 | 0 | 0 | 2017-02-14 |  |  | complete | 100%
1204-30-ST-DWG-396 | 01 | T-3002 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0392 | 2014-09-09 |  | No | 2064 | 1204-TKT-COLANGELI | 2014-09-09 12:42 | CDW | 2014-09-09 | 0 | 0 | 0 | 2014-09-09 | 2014-08-06 | MT-OT-9301-CS-023 | complete | 100%
1204-90-HS-DWG-014 | 02 | SAFETY EQUIPMENT LAYOUT FOR WAREHOUSE | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-19 15:42 | EDW | 2016-12-16 | 0 | 0 | 0 | 2016-12-16 |  |  | complete | 100%
1204-00-PI-LST-1500 | 00 | A/G ISOMETRIC LIST OF AREA-15 | DE | IFR | PI | PS-OT-T-0172 | 2016-01-04 |  | No | 1582 | 1204-Owner-v | 2016-01-06 10:53 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-09 |  |  | InProgress | 80%
1204-00-PI-LST-6000 | 01 | U/G ISOMETRIC LIST OF AREA-60 | DE | IFC-WH | PI | PS-OT-T-0628 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-18 15:31 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-06-24 | MT-PS-9609-CS-087 | InProgress | 90%
1204-64-PI-APL-3100 | 00 | PIPING PLAN AREA-31 | DE | IFR | PI | PS-OT-T-0324 | 2016-08-23 |  | No | 1350 | 1204-Owner-v | 2016-08-24 15:15 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-08-29 |  |  | InProgress | 80%
1204-90-ST-DWG-920 | 03 | CONTROL ROOM & LABORATORY / WALLS (R.C.DETAILS I ) | DE | IFC | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 12:14 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-00-QC-SOI-505 | 00 | SCOPE OF INSPECTION FOR POWER DISTRIBUTION CONTROL SYSTEM | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 | 1204-Owner-v | 2020-05-13 13:50 | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-HM-TBA-253A | 00 | TECHNICAL BID ANALYSIS FOR AIR COOLED HEAT EXCHANGERS | DE | IFE | MD | TM-OT-9001-T-0220 | 2013-01-07 |  | No | 2674 | 1204-TKT-COLANGELI | 2013-01-07 11:37 | TBA | 2013-01-07 | 0 | 0 | 0 | 2013-01-07 |  |  | complete | 100%
1204-00-PV-TBA-220A | 00 | TECHNICAL BID ANALYSIS FOR SILENCERS | DE | IFE | MD | PS-OT-T-0914 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 12:44 | TBA | 2020-02-24 | 0 | 0 | 2020-03-13 | * | 2020-02-26 | MT-PS-9301-CS-0270 | complete | 100%
1204-90-ST-DWG-912 | 03 | CONTROL ROOM & LABORATORY / ROOF SLOPING PLAN | DE | IFC | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:50 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-20-PV-DSH-231 | 01 | MECHANICAL DATA SHEET FOR PURGE GAS SCRUBBER COLUMN (T-2001) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:30 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | complete | 100%
1204-00-EL-REQ-507 | 00 | REQUISITION FOR BATTERY CHARGER | DE | IFI | EL | PS-OT-T-0490 | 2017-09-18 | 2017-10-18 11:44 | Yes | 16 | 1204-Owner-v | 2017-09-21 08:10 | REQ | 2017-09-20 | 0 | 0 | 0 | 2017-09-20 | 2017-10-09 | MT-PS-9301-CS-255 | InProgress | 90%
1204-00-RE-TBA-307B | 02 | TECHNICAL BID ANALYSIS FOR CENTRIFUGAL PUMPS (GROUP B) | DE | IFE | MC | PS-OT-T-0849 | 2019-12-23 |  | No | 133 | 1204-Owner-v | 2019-12-24 09:20 | TBA | 2019-12-23 | 0 | 0 | 0 | 0 |  | MT-PS-9301-CS-0247 | complete | 100%
1204-30-RE-DSH-043 | 01 | DATA SHEET FOR BOTTOM WATER RECOVERY PUMPS (P-3006 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:22 | DSH | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 |  |  | InProgress | 80%
1204-90-HV-DSH-100 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR FRESH AIR IN HVAC ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:45 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-90-HV-DSH-223 | 01 | DATA SHEET FOR NON RETURN DAMPER FOR SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:50 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-90-HV-DSH-261 | 00 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR CLINIC AND TRAINING | DE | IFE | HV | TM-OT-9001-T-0317 | 2013-09-16 |  | No | 2422 | 1204-TKT-COLANGELI | 2013-09-11 15:06 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DWG-023 | 03 | SUBSTATION - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | TM-OT-9001-T-0441 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:18 | CDW | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-90-HV-DID-054 | 02 | RESTAURANT - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:32 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 | 2014-10-19 |  | complete | 100%
1204-90-HV-DSH-081 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR LOCKER IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:45 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-00-PI-LST-1300 | 00 | A/G ISOMETRIC LIST OF AREA-13 | DE | IFR | PI | PS-OT-T-0283 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:44 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-20-PI-ISO-6500 | 01 | U/G ISOMETRIC DRAWING OF AREA-65 | DE | IFC-WH | PI | PS-OT-T-0665 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-17 09:39 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 90%
1204-40-PI-ISO-4400 | 01 | A/G ISOMETRIC DRAWING OF AREA-44 | DE | IFC-WH | PI | PS-OT-T-0681 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:40 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | * |  |  | InProgress | 90%
1204-00-MC-MSS-012 | 00 | MATERIAL STANDARD SPECIFICATION FOR RECIPROCATING COMPRESSORS | DE | IFR | MC | PS-OT-T-0836 | 2019-11-16 |  | No | 170 | 1204-Owner-v | 2020-01-05 07:58 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 |  |  |  | InProgress | 80%
1204-00-PV-TBA-201B | 00 | TECHNICAL BID ANALYSIS FOR AUTO THERMAL REACTOR | DE | IFE | MD | PS-OT-T-0224 | 2016-03-16 |  | No | 1510 | 1204-Owner-v | 2016-03-16 15:33 | TBA | 2016-03-17 | 0 | 0 | 0 | 2016-03-17 | 2016-04-18 | MT-PS-9301-CS-127 | complete | 100%
1204-03-EL-DWG-011 | 00 | LIGHTING LAYOUT AREA-03 (D-3006, E-3006, 3004, 3010A/B, T-3002) | DE | IFR | EL | PS-OT-T-0159 | 2015-12-28 | 2016-07-21 15:12 | Yes | 192 | 1204-Owner-v | 2015-12-30 13:56 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2016-01-16 | 2016-01-19 | MT-PS-9301-CS-078-1 | InProgress | 80%
1204-00-IN-DWG-038 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 38) | DE | IFR | IN | PS-OT-T-342 | 2016-10-01 |  | No | 1311 | 1204-Owner-v | 2016-10-08 15:58 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | * | 2016-10-18 | MT-PS-9301-CS-190-R | InProgress | 80%
1204-40-ST-DWG-459 | 01 | BOILER (PU-4006 A ) / FDN. (G.A. & DETAILS III ) | DE | IFC | ST | PS-OT-T-0243 | 2016-04-16 |  | No | 1479 | 1204-Owner-v | 2016-04-17 14:18 | CDW | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 |  |  | complete | 100%
1204-00-PR-LST-020 | 00 | LINE LIST FOR UTILITY DISTRIBUTION DIAGRAM | DE | IFR | PR | PS-OT-T-0419 | 2017-02-14 |  | No | 1175 | 1204-Owner-v | 2017-02-25 14:09 | LIST | 2020-06-01 | 0 | 0 | 2020-06-30 | 0 | 0 | 0 | InProgress | 90%
1204-00-PI-TBA-467A | 00 | TECHNICAL BID ANALYSIS FOR U/G HDPE ITEMS(MTO I) | DE | IFE | PI | PS-OT-T-0656 | 2018-07-25 |  | No | 649 | 1204-Owner-v | 2018-08-03 10:31 | TBA | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-ST-DWG-1144 | 01 | VB-6303 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0562 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-27 09:31 | CDW | 2018-02-21 | 0 | 0 | 0 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-038 | complete | 100%
1204-00-ST-MTO-1134 | 00 | MATERIAL TAKE OFF FOR VB-6102 | DE | IFE | ST | PS-OT-T-0594 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-28 08:39 | LIST | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 | 2018-05-09 | MT-PS-9609-CS-064 | complete | 100%
1204-20-RE-DSH-061 | 01 | DATA SHEET FOR E.O.T CRANE FOR SYNGAS COMPRESSOR, CN-2001 | DE | IFR | MC | PS-OT-T-0660 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-15 15:50 | DSH | 2018-08-05 | 0 | 0 | 0 | 2018-08-05 |  |  | InProgress | 80%
1204-30-PI-LST-2200 | 01 | A/G ISOMETRIC LIST OF AREA-22 | DE | IFC-WH | PI | PS-OT-T-0661 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-14 11:33 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-00-PI-APL-3600 | 00 | PIPING PLAN AREA-36 | DE | IFR | PI | PS-OT-T-0340 | 2016-09-28 |  | No | 1314 | 1204-Owner-v | 2016-10-01 13:20 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-10-PI-ISO-4500 | 00 | A/G ISOMETRIC DRAWING OF AREA-45 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:04 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-09-03 |  |  | InProgress | 80%
1204-00-EL-SLD-009 | 00 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR -SS01-SWB3A,B-01 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:57 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:40 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2018-05-31 | MT-PS-9609-CS-008-R | InProgress | 80%
1204-00-PI-PPL-008 | 00 | PLOT PLAN UNIT 400 | DE | IFR | PI | PS-OT-T-0426 | 2017-03-05 |  | No | 1156 | 1204-Owner-v | 2017-03-07 09:03 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * | 2017-03-12 | MT-PS-9301-CS-219-R | InProgress | 80%
1204-30-IN-DWG-022 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 22) | DE | IFR | IN | PS-OT-T-0140 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 09:06 | CDW | 2020-06-22 | 0 | 0 | 2020-06-22 | 2015-12-15 | 2016-01-12 | MT-PS-9301-CS-086 | InProgress | 80%
1204-40-ST-DWG-461 | 01 | BOILER (PU-4006 B ) / FDN. (G.A. & DETAILS III ) | DE | IFC | ST | PS-OT-T-0243 | 2016-04-16 |  | No | 1479 | 1204-Owner-v | 2016-04-17 14:42 | CDW | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 |  |  | complete | 100%
1204-05-EL-DWG-002 | 00 | POWER LAYOUT AREA-05 AE-3002 | DE | IFR | EL | PS-OT-T-0204 | 2016-02-28 | 2016-07-23 10:09 | Yes | 132 | 1204-Owner-v | 2016-03-02 15:18 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | * | 2016-04-05 | MT-PS-9301-CS-119-1 | InProgress | 80%
1204-00-EL-DSH-5071 | 00 | DATA SHEET FOR BATTERY CHARGER (MS-CH-01) | DE | IFR | EL | PS-OT-T-0489 | 2017-09-18 | 2017-10-18 16:08 | Yes | 16 | 1204-Owner-v | 2017-09-21 08:07 | DSH | 2020-04-24 | 0 | 0 | 2020-04-24 | 2017-09-19 | 2017-10-09 | MT-PS-9301-CS-253 | InProgress | 80%
1204-00-PI-MTO-467A | 00 | MATERIAL TAKE OFF FOR U/G HDPE ITEMS(MTO I) | DE | IFE | PI | PS-OT-T-0542 | 2018-01-21 |  | No | 834 | 1204-Owner-v | 2018-01-28 14:05 | LIST | 2018-01-21 | 0 | 0 | 0 | 2018-01-21 | 2018-01-28 | MT-PS-9609-CS-020 | complete | 100%
1204-00-ST-DWG-1121 | 01 | DV-6101 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0580 | 2018-03-13 |  | No | 783 | 1204-Owner-v | 2018-04-14 11:39 | CDW | 2018-03-13 | 0 | 0 | 0 | 2018-03-13 |  |  | complete | 100%
1204-00-ST-DWG-1149 | 00 | DV-6601 / R.C. DETAILS | DE | IFR | ST | PS-OT-T-0722 | 2018-12-01 |  | No | 520 | 1204-Owner-v | 2018-12-03 10:04 | CDW | 2018-12-01 | 0 | 0 | 0 | 2018-12-01 |  |  | InProgress | 80%
1204-90-HV-DWG-062 | 01 | CLINIC AND TRAINING - SECTION OF DUCTING | DE | IFC | HV | TM-OT-9001-T-0380 | 2014-07-01 |  | No | 2134 | 1204-TKT-COLANGELI | 2014-07-01 14:46 | CDW | 2014-07-01 | 0 | 0 | 0 | 2014-07-01 |  |  | complete | 100%
1204-90-HV-DSH-036 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET IN FIRE STATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:58 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-HM-ESS-287 | 01 | ENGINEERING STANDARD SPECIFICATION FOR DOUBLE PIPE HEAT EXCHANGERS | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-03-03 11:25 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-00-ST-DWG-042 | 03 | PIPE RACK ZONE 6 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0176 | 2016-01-09 |  | No | 1577 | 1204-Owner-v | 2016-01-10 09:14 | CDW | 2016-01-16 | 0 | 0 | 0 | 2016-01-16 | 2016-01-10 | MT-PS-9301-CS-084 | complete | 100%
1204-30-ST-DWG-500 | 01 | T-3003 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0392 | 2014-09-09 |  | No | 2064 | 1204-TKT-COLANGELI | 2014-09-09 12:49 | CDW | 2014-09-09 | 0 | 0 | 0 | 2014-09-09 | 2014-08-06 | MT-OT-9301-CS-023 | complete | 100%
1204-90-HS-DWG-013 | 02 | SAFETY EQUIPMENT LAYOUT FOR WORK SHOP | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-19 15:43 | EDW | 2016-12-16 | 0 | 0 | 0 | 2016-12-16 |  |  | complete | 100%
1204-10-QC-SOI-251F | 00 | SCOPE OF INSPECTION FOR FOR CATALYST TUBES ASSEBLIES-OUTLET | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-20-RE-DSH-003 | 00 | DATA SHEET FOR SYNTHESIS GAS CIRCULATOR C-2002 | DE | IFR | MC | PS-OT-T-0157 | 2015-12-21 |  | No | 1596 | 1204-Owner-v | 2015-12-22 15:46 | DSH | 2015-12-23 | 0 | 0 | 0 | 2015-12-23 | 2016-01-06 | MT-PS-9301-CS-076 | InProgress | 80%
1204-63-PI-LST-1600 | 00 | A/G ISOMETRIC LIST OF AREA-16 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-64-PI-ISO-2000 | 00 | A/G ISOMETRIC DRAWING OF AREA-20 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:12 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-10-PI-LST-4600 | 00 | A/G ISOMETRIC LIST OF AREA-46 | DE | IFR | PI | PS-OT-T-0349 | 2016-10-10 |  | No | 1302 | 1204-Owner-v | 2016-10-23 09:11 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-19 |  |  | InProgress | 80%
1204-84-HS-DSH-007 | 00 | DATA SHEET FOR COC WATER SUMP SU-8403 | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:05 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-03-EL-DWG-021 | 00 | EARTHING LAYOUT FOR AREA-03D-3001, 3002, E-3002, 3004, 3006, 3007, 3010A/B, 3011 | DE | IFR | EL | PS-OT-T-0115 | 2015-10-10 | 2016-01-14 11:59 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:08 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-10-14 | 2015-11-19 | MT-PS-9301-CS-043 | InProgress | 80%
1204-05-EL-SLD-070 | 00 | SINGLE LINE DIAGRAM FOR 05-DP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:03 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:42 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-00-PI-TBA-460A | 00 | TECHNICAL BID ANALYSIS FOR COATING & WRAPPING(MTO I) | DE | IFE | PI | PS-OT-T-0505 | 2017-11-26 |  | No | 890 | 1204-Owner-v | 2017-12-02 11:41 | TBA | 2017-12-02 | 0 | 0 | 0 | 2017-12-02 | 2017-12-20 | MT-PS-9301-CS-273 | complete | 100%
1204-00-ST-DWG-1132 | 01 | VB-6102 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0562 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-27 09:27 | CDW | 2018-02-21 | 0 | 0 | 0 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-038 | complete | 100%
1204-00-ST-TBA-740C | 00 | TECHNICAL BID ANALYSIS FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART C) | DE | IFE | ST | PS-OT-T-0874 | 2020-01-22 |  | No | 103 | 1204-Owner-v | 2020-01-25 08:45 | TBA | 2020-01-09 | 0 | 0 | 2020-01-10 | * | 2020-02-08 | MT-PS-9609-CS-0267 | complete | 100%
1204-20-ST-DWG-216 | 01 | T-SUPPORTS ON COMBINED FDN. OF STR. “ A & M “ / CON. STRUCTURE (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0800 | 2019-05-28 |  | No | 342 | 1204-Owner-v | 2019-05-28 18:16 | CDW | 2019-05-28 | 0 | 0 | 0 | 2019-05-28 |  |  | complete | 100%
1204-30-ST-DWG-321 | 02 | STRUCTURE "D" FOR E-3006 ,E-3010A/B / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0761 | 2019-03-09 |  | No | 422 | 1204-Owner-v | 2019-03-10 11:08 | CDW | 2019-03-10 | 0 | 0 | 0 | 2019-03-10 |  |  | complete | 100%
1204-40-ST-DWG-425 | 01 | D-4002 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0272 | 2016-05-29 |  | No | 1436 | 1204-Owner-v | 2016-05-30 10:15 | CDW | 2016-05-29 | 0 | 0 | 0 | 2016-05-29 | 2016-06-01 | MT-PS-9301-CS-156 | complete | 100%
1204-90-ST-DWG-902 | 01 | CONTROL ROOM & LABORATORY / FDN.. OF NON BLAST PART(R.C.DETAILS) | DE | IFC | ST | PS-TM-T-0255 | 2021-09-13 |  | No | -497 | 1204-TKT-COLANGELI | 2013-09-27 11:04 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-90-ST-DWG-997 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / PLUMBING LAYOUT (SECOND FLOOR PLAN ) | DE | IFR | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 15:08 | CDW | 2020-04-30 | 0 | 0 | 2020-04-30 | 2013-01-10 |  |  | InProgress | 80%
1204-90-ST-MTO-1000 | 00 | MATERIAL TAKE OFF FOR ADMINISTRATION , RESTAURANT & CLINIC BUILDING / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:24 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-008 | complete | 100%
1204-00-HM-REQ-256B | 00 | Requisition for Filters | DE | IFI | MD | TM-OT-9001-T-0098 | 2012-06-01 |  | No | 2894 | 1204-Owner-v | 2015-08-05 10:22 | REQ | 2020-04-28 | 0 | 0 | 2020-05-11 | 2012-06-01 |  |  | InProgress | 90%
1204-63-QC-SOI-108 | 01 | SCOPE OF INSPECTION FOR COOLING WATER SYSTEM | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-HM-TBA-256A | 00 | TECHNICAL BID ANALYSIS FOR COOLING WATER SIDE STREAM FILTERS | DE | IFE | MD | PS-OT-T-0473 | 2017-08-27 |  | No | 981 | 1204-Owner-v | 2017-08-30 11:34 | TBA | 2017-10-03 | 0 | 0 | 0 | 2017-10-03 | 2017-10-04 | MT-PS-9301-CS-244-1 | complete | 100%
1204-00-EL-REQ-522 | 00 | REQUISITION FOR MV ELECTRICAL MOTORS FOR PRIMERY REFORMER | DE | IFI | EL | PS-OT-T-0719 | 2018-11-12 |  | No | 539 | 1204-Owner-v | 2018-11-13 17:05 | REQ | 2019-12-24 | 0 | 0 | 2020-01-06 | 2018-11-17 |  |  | InProgress | 90%
1204-00-ST-DWG-192 | 01 | PIPE RACK ZONE 16 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0845 | 2019-12-18 |  | No | 138 | 1204-Owner-v | 2019-12-21 15:11 | CDW | 2019-12-26 | 0 | 0 | 0 | 2019-12-26 |  | MT-PS-9609-CS-0244 | complete | 100%
1204-90-ST-DWG-962 | 01 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (R.C. PLAN & DETAILS II ) | DE | IFC | ST | PS-OT-T-0952 | 2020-04-21 |  | No | 13 | 1204-Owner-v | 2020-04-22 11:23 | DWG | 2020-04-21 | #N/A | #N/A | #N/A | 2020-04-21 |  |  | complete | 100%
1204-00-PI-REQ-463A | 01 | REQUISITION FOR U/G GASKETS(MTO I) | DE | IFP | PI | PS-OT-T-0404 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-01-23 09:43 | REQ | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-65-PV-DSH-214 | 00 | MECHANICAL DATA SHEET FOR FUEL GAS CONDENSATE POT (D-6501) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:43 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | complete | 100%
1204-63-IN-DWG-016 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 16) | DE | IFR | IN | PS-OT-T-0220 | 2016-03-14 |  | No | 1512 | 1204-Owner-v | 2016-03-14 11:11 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | * | 2016-03-16 | MT-PS-9301-CS-117-1 | InProgress | 80%
1204-30-ST-DWG-346 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / BEAMS (G.A. PLAN & R.C. DETAILS II) | DE | IFC | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 08:07 | CDW | 2017-01-01 | 0 | 0 | 0 | 2017-01-01 |  |  | complete | 100%
1204-00-PI-REQ-465A | 01 | REQUISITION FOR U/G BOLTS & NUTS(MTO I) | DE | IFP | PI | PS-OT-T-0513 | 2017-12-11 |  | No | 875 | 1204-Owner-v | 2017-12-16 11:08 | REQ | 2017-12-11 | 0 | 0 | 0 | 2017-12-11 | 2018-01-08 | MT-PS-9609-CS-004 | complete | 100%
1204-30-HM-DSH-240 | 00 | MECHANICAL DATA SHEET FOR REFINING STEAM HEATED REBOILER (E-3004) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:12 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DSH-064 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET IN ADMINISTRATION , CLINIC AND RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:43 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | InProgress | 80%
1204-71-HS-PID-002 | 02 | PIPING AND INSTRUMENTATION DIAGRAM FOR FOAM SYSTEM FOR TK-7101 A/B & TK-7201 | DE | IFR | HSE | PS-OT-T-0066 | 2015-06-27 |  | No | 1773 | 1204-Owner-v | 2015-06-28 08:37 | EDW | 2019-10-01 | 2019-11-11 | 0 | 2020-07-30 | * |  |  | InProgress | 80%
1204-00-ST-DWG-036 | 00 | PIPE RACK ZONE 5 / FRAMING PLANS & DETAILS | DE | IFR | ST | TM-OT-9001-T-0286 | 2013-06-05 |  | No | 2525 | 1204-TKT-COLANGELI | 2013-06-04 15:48 | CDW | 2020-06-03 | 0 | 0 | 2020-08-12 | 2013-06-05 |  |  | InProgress | 80%
1204-90-HV-DSH-019 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET & CLEAN TOOLS IN LABORATORY | DE | IFE | HV | PS-OT-T-0009 | 2015-03-14 |  | No | 1878 | 1204-Owner-v | 2015-03-17 11:12 | DSH | 2015-03-14 | 0 | 0 | 0 | 2015-03-14 |  |  | complete | 100%
1204-00-ST-DWG-1104 | 03 | RETAINING WALL / G.A. PLAN & R.C. DETAILS (I) | DE | IFC | ST | TM-OT-9001-T-0418 | 2014-12-09 |  | No | 1973 | 1204-TKT-COLANGELI | 2014-12-09 13:11 | CDW | 2014-12-09 | 0 | 0 | 0 | 2014-12-09 | 2014-12-30 | MT-TM-9301-CS-029 | complete | 100%
1204-00-HS-PID-001 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR SPRAY NOZZLE SYSTEM FOR PUMPS | DE | IFR | HSE | PS-OT-T-0739 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:00 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * | 2020-04-05 | MT-PS-9609-CS-0313-1 | InProgress | 80%
1204-00-PI-LST-1100 | 00 | A/G ISOMETRIC LIST OF AREA-11 | DE | IFR | PI | PS-OT-T-0073 | 2015-07-07 |  | No | 1763 | 1204-Owner-v | 2015-07-11 16:10 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2015-07-07 |  |  | InProgress | 80%
1204-20-PR-PID-209 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS STEAM PRODUCTION | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:20 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-63-PI-ISO-2100 | 01 | A/G ISOMETRIC DRAWING OF AREA-21 | DE | IFC-WH | PI | PS-OT-T-0933 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 15:57 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-20-ST-DWG-272 | 02 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/STEEL STR.(PLAN & DET. II) | DE | IFC-WH | ST | PS-OT-T-0852 | 2019-09-25 |  | No | 222 | 1204-Owner-v | 2019-12-29 08:52 | CDW | 2019-12-31 | 0 | 0 | 0 | 2019-12-31 |  | MT-PS-9609-CS-0250 | complete | 100%
1204-00-IN-DSH-655 | 00 | DATA SHEET FOR DESUPERHEATER VALVES | DE | IFR | IN | PS-OT-T-0148 | 2015-12-19 |  | No | 1598 | 1204-Owner-v | 2015-12-20 18:00 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2016-08-06 | MT-PS-9301-CS-107-1 | InProgress | 80%
1204-00-PR-LST-012 | 00 | LINE LIST FOR PROCESS UNIT | DE | IFR | PR | PS-OT-T-0141 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 14:15 | LIST | 2020-03-27 | 0 | 0 | 2020-05-06 | * | 2015-12-23 | MT-PS-9301-CS-057-01 | InProgress | 90%
1204-02-EL-DWG-013 | 00 | LIGHTING LAYOUT FOR AREA-02 AE-2001 | DE | IFR | EL | PS-OT-T-0186 | 2016-01-18 | 2016-07-24 11:27 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:38 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2016-01-24 | 2016-01-26 | MT-PS-9301-CS-096 | InProgress | 80%
1204-00-ST-DWG-1124 | 02 | DV-6202 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0616 | 2018-05-21 |  | No | 714 | 1204-Owner-v | 2018-05-22 11:55 | CDW | 2018-05-26 | 0 | 0 | 0 | 2018-05-26 | 2018-05-22 | MT-PS-9609-CS-075 | complete | 100%
1204-00-ST-DWG-1152 | 01 | VB-6905 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0562 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-27 09:29 | CDW | 2018-02-21 | 0 | 0 | 0 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-038 | complete | 100%
1204-00-EL-PCJ-501 | 00 | ELECTRICAL EQUIPMENT FIELD TEST PROCEDURE | DE | IFR | EL | PS-OT-T-0648 | 2018-07-17 |  | No | 657 | 1204-Owner-v | 2018-07-21 09:20 | LIST | 2018-07-17 | 0 | 0 | 0 | 2018-07-17 |  |  | InProgress | 90%
1204-00-PI-ISO-4000 | 00 | A/G ISOMETRIC DRAWING OF AREA-40 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:03 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-00-PI-LST-3500 | 00 | A/G ISOMETRIC LIST OF AREA-35 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:04 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-09-03 |  |  | InProgress | 80%
1204-90-RE-DSH-063 | 01 | DATA SHEET FOR E.O.T CRANE FOR WORKSHOPS, CN-9002A/B | DE | IFR | MC | PS-OT-T-0660 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-15 15:53 | DSH | 2018-08-05 | 0 | 0 | 0 | 2018-08-05 |  |  | InProgress | 80%
1204-30-ST-DWG-310 | 01 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 /CONCRETE STRUCTURE (R.C. & DETS.) | DE | IFC | ST | PS-OT-T-0751 | 2019-02-05 |  | No | 454 | 1204-Owner-v | 2019-02-06 09:21 | CDW | 2019-02-05 | 0 | 0 | 0 | 2019-02-05 |  |  | complete | 100%
1204-00-ST-DWG-1108 | 01 | RETAINING WALL / G.A. PLAN & R.C. DETAILS (III) | DE | IFC | ST | TM-OT-9001-T-0423 | 2014-12-15 |  | No | 1967 | 1204-TKT-COLANGELI | 2014-12-15 12:20 | CDW | 2014-12-15 | 0 | 0 | 0 | 2014-12-15 |  |  | complete | 100%
1204-20-ST-DWG-270 | 02 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/CONC. STR. (G.A. & DETS.) | DE | IFC | ST | PS-OT-T-0810 | 2019-06-24 |  | No | 315 | 1204-Owner-v | 2019-06-25 14:57 | CDW | 2019-07-11 | 0 | 0 | 0 | 2019-07-11 |  |  | complete | 100%
1204-10-ST-DWG-165 | 02 | REFORMER (TRANSFERLINE SUPPORTS 8 & 9) / FDN.(G.A. & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0818 | 2019-07-22 |  | No | 287 | 1204-Owner-v | 2019-07-24 10:35 | CDW | 2019-07-24 | 0 | 0 | 0 | 2019-07-24 |  |  | complete | 100%
1204-30-ST-DWG-312 | 01 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 /STEEL STRUCTURE (ELE. & DETS.) | DE | IFC | ST | PS-OT-T-0751 | 2019-02-05 |  | No | 454 | 1204-Owner-v | 2019-02-06 09:21 | CDW | 2019-02-05 | 0 | 0 | 0 | 2019-02-05 |  |  | complete | 100%
1204-00-EL-DSH-5021 | 02 | DATA SHEET FOR 6KV SWITCHGEAR, MS-SWB2A,B-01 | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:11 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:03 | DSH | 2020-05-11 | 0 | 0 | 2020-05-11 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-20-RE-DSH-004 | 00 | DATA SHEET FOR STEAM TURBINE FOR SYNTHESIS GAS CIRCULATOR STC-2002 | DE | IFR | MC | PS-OT-T-0157 | 2015-12-21 |  | No | 1596 | 1204-Owner-v | 2015-12-22 15:47 | DSH | 2015-12-23 | 0 | 0 | 0 | 2015-12-23 | 2016-01-06 | MT-PS-9301-CS-076 | InProgress | 80%
1204-72-PI-UPL-7300 | 03 | UNDER GROUND PIPING PLAN AREA-73 | DE | IFC-WH | PI | PS-OT-T-0599 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:39 | CDW | 2018-05-03 | 0 | 0 | 0 | 2018-05-03 |  |  | complete | 100%
1204-00-PI-REQ-464A | 01 | REQUISITION FOR U/G VALVES(MTO I) | DE | IFP | PI | PS-OT-T-0404 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-05-07 09:25 | REQ | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-00-PI-LST-4000 | 00 | A/G ISOMETRIC LIST OF AREA-40 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:01 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-00-IN-CAL-001 | 00 | CALCULATION SHEET FOR CONTROL VALVES | DE | IFR | IN | TM-OT-9001-T-0320 | 2013-09-24 |  | No | 2414 | 1204-TKT-COLANGELI | 2013-09-24 13:18 | CAL | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-71-ST-MTO-757 | 00 | MATERIAL TAKE OFF FOR DYKE WALL OF TK-7101 A/B & TK-7201 | DE | IFE | ST | TM-OT-9001-T-0432 | 2015-01-21 |  | No | 1930 | 1204-TKT-COLANGELI | 2015-01-20 12:52 | LIST | 2015-01-20 | 0 | 0 | 0 | 2015-01-20 |  |  | complete | 100%
1204-90-HS-DWG-007 | 02 | FIRE ALARM LAYOUT FOR GUARD HOUSE | DE | IFE | HSE | PS-OT-T-379 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:08 | EDW | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-10-PI-UPL-6800 | 02 | UNDER GROUND PIPING PLAN AREA-68 | DE | IFC-WH | PI | PS-OT-T-0647 | 2018-07-15 |  | No | 659 | 1204-Owner-v | 2018-07-16 10:02 | CDW | 2018-07-21 | 0 | 0 | 0 | 2018-07-21 | 2018-08-04 | MT-PS-9609-CS-098-R | InProgress | 90%
1204-40-PI-ISO-6600 | 01 | U/G ISOMETRIC DRAWING OF AREA-66 | DE | IFC-WH | PI | PS-OT-T-0682 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:38 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-10-02 |  |  | InProgress | 90%
1204-63-PI-ISO-1600 | 00 | A/G ISOMETRIC DRAWING OF AREA-16 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:14 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-64-PI-LST-2000 | 00 | A/G ISOMETRIC LIST OF AREA-20 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:10 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-71-PI-UPL-7400 | 03 | UNDER GROUND PIPING PLAN AREA-74 | DE | IFC-WH | PI | PS-OT-T-0598 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:35 | CDW | 2018-05-03 | 0 | 0 | 0 | 2018-05-03 |  |  | InProgress | 90%
1204-10-PI-APL-4500 | 00 | PIPING PLAN AREA-45 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:04 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-09-03 |  |  | InProgress | 80%
1204-03-EL-SLD-061 | 00 | SINGLE LINE DIAGRAM FOR 03-ELP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:01 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:41 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-90-ST-DWG-1086 | 02 | GUARD HOUSE / 3D VIEWS | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 13:40 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-90-HV-DSH-071 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR LAVATORY IN GUARD HOUSE | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:37 | DSH | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-05-EL-SLD-069 | 00 | SINGLE LINE DIAGRAM FOR 05-ELP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:03 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:42 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-10-HM-REQ-251D | 01 | REQUSITION FOR REFORMER INLET AND OUTLET LINES, COLD COLLECTOR & TRANSFER LINE INCLUDING REFRACTORYMATERIAL SUPPLY AND INSTALLATION | DE | IFP | MD | PS-OT-T-0894 | 2020-02-16 |  | No | 78 | 1204-Owner-v | 2020-02-26 15:54 | REQ | 2019-10-01 | 0 | 0 | 2019-10-14 | * | 2020-03-04 | MT-PS-9609-CS-0296 | complete | 100%
1204-00-ST-DWG-781 | 01 | INTERCONNECTION CONCRETE CABLE TRENCH / SECTIONS & DETAILS (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0769 | 2019-03-16 |  | No | 415 | 1204-Owner-v | 2019-03-18 10:10 | CDW | 2019-03-18 | 0 | 0 | 0 | 2019-03-18 |  |  | complete | 100%
1204-00-ST-DWG-187 | 00 | PIPE RACK ZONE 14 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFR | ST | PS-OT-T-0973 | 2020-05-13 |  | No | -9 | 1204-Owner-v | 2020-05-16 08:35 | CDW | 2020-03-23 | 0 | 0 | 2020-03-23 | 0 | 0 | 0 | InProgress | 50%
1204-04-EL-DWG-013 | 00 | LIGHTING LAYOUT FOR AREA-04-AE-3001 AND DA-4001 | DE | IFR | EL | PS-OT-T-0313 | 2016-07-27 | 2016-10-10 17:06 | Yes | 61 | 1204-Owner-v | 2016-07-27 16:06 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | 2016-08-08 | 2016-07-27 | MT-PS-9301-CS-181 | InProgress | 80%
1204-00-PV-REQ-231B | 00 | REQUISITION FOR LADDER AND PLATFORMS | DE | IFI | MD | PS-OT-T-0455 | 2017-07-02 |  | No | 1037 | 1204-Owner-v | 2017-08-09 14:18 | REQ | 2017-07-05 | 0 | 0 | 0 | 2017-07-05 |  |  | InProgress | 90%
1204-00-ST-MTO-1154 | 00 | MATERIAL TAKE OFF FOR VB-6905 | DE | IFE | ST | PS-OT-T-0594 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-28 08:40 | LIST | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 | 2018-05-09 | MT-PS-9609-CS-064 | complete | 100%
1204-90-HS-DWG-016 | 00 | FIRE AND GAS ALARM LAYOUT FOR ASU CONTROL ROOM | DE | IFR | HSE | PS-OT-T-0713 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-06 17:14 | EDW | 2020-07-10 | 0 | 0 | 2020-07-10 | * |  |  | InProgress | 80%
1204-00-ST-DWG-1148 | 00 | DV-6601 /FDN. (G.A. & DETAILS) | DE | IFR | ST | PS-OT-T-0722 | 2018-12-01 |  | No | 520 | 1204-Owner-v | 2018-12-03 10:04 | CDW | 2018-12-01 | 0 | 0 | 0 | 2018-12-01 |  |  | InProgress | 80%
1204-00-PI-MTO-421 | 00 | MATERIAL TAKE OFF FOR BOLT&NUT FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0944 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:43 | MTO | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-QC-SOI-206B | 00 | SCOPE OF INSPECTION FOR SPECIAL COLUMNS (GROUP II) | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-90-ST-DWG-1053 | 01 | FIRE STATION / SECTIONS & ELEVATIONS | DE | IFR | ST | TM-OT-9001-T-0196 | 2012-10-30 |  | No | 2743 | 1204-Owner-v | 2015-08-26 21:07 | CDW | 2012-10-30 | 0 | 0 | 0 | 2012-10-30 |  |  | InProgress | 80%
1204-90-ST-DWG-914 | 03 | CONTROL ROOM & LABORATORY / BEAMS , WALLS & COLUMNS (G.A. PLAN & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0334 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 13:07 | CDW | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-ST-DWG-935 | 01 | SUBSTATION / SECTIONS | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 11:14 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-00-QC-SOI-508 | 00 | SCOPE OF INSPECTION FOR LIGHTING & DISTRIBUTION PANEL BOARDS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-40-RE-DSH-047 | 00 | DATA SHEET FOR CONDENSATE PUMPS FOR E-4005 (P-4005 A/B) | DE | IFR | MC | PS-OT-T-0838 | 2019-11-20 |  | No | 166 | 1204-Owner-v | 2019-11-27 10:22 | DSH | 2019-11-20 | 0 | 0 | 0 | 0 |  | MT-PS-9301-CS-0246 | InProgress | 80%
1204-90-HV-DSH-260 | 02 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR CLINIC AND TRAINING | DE | IFE | HV | PS-OT-T-0270 | 2016-05-25 |  | No | 1440 | 1204-Owner-v | 2016-05-25 15:29 | DSH | 2016-05-28 | 0 | 0 | 0 | 2016-05-28 |  |  | complete | 100%
1204-90-HV-DWG-065 | 00 | CLINIC AND TRAINING - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFE | HV | TM-OT-9001-T-0380 | 2014-07-01 |  | No | 2134 | 1204-TKT-COLANGELI | 2014-07-01 17:38 | CDW | 2014-07-01 | 0 | 0 | 0 | 2014-07-01 |  |  | complete | 100%
1204-00-ST-DWG-020 | 02 | PIPE RACK ZONE 2 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0023 | 2015-04-19 |  | No | 1842 | 1204-Owner-v | 2015-04-20 07:46 | CDW | 2015-04-19 | 0 | 0 | 0 | 2015-04-19 |  |  | complete | 100%
1204-10-ST-DWG-101 | 02 | D-1001 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0318 | 2016-08-10 |  | No | 1363 | 1204-Owner-v | 2016-08-11 08:35 | CDW | 2016-08-16 | 0 | 0 | 0 | 2016-08-16 |  |  | complete | 100%
1204-20-ST-DWG-220 | 01 | T-2001/ FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0171 | 2016-01-04 |  | No | 1582 | 1204-Owner-v | 2016-01-04 16:59 | CDW | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 |  |  | complete | 100%
1204-90-ST-DWG-943 | 02 | SUBSTATION / COLUMNS (G.A. , R.C. & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-21 15:55 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-00-EL-DIG-517 | 00 | VSD CONTROL CIRCUIT DIAGRAM | DE | IFR | EL | PS-OT-T-0730 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:56 | CDW | 2020-04-22 | 0 | 0 | 2020-04-22 | * |  |  | InProgress | 80%
1204-20-RE-DSH-030 | 00 | Data Sheet for Steam Turbine for First Saturator Pumps PT-2003 A | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:40 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-00-PR-UDD-016 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR NITROGEN, INSTRUMENT AIR, PLANT AIR & FUEL GAS DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:25 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-EL-REQ-517 | 01 | REQUISITION FOR LV VSD PANELS | DE | IFI | EL | PS-OT-T-0732 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:57 | REQ | 2018-12-22 | 0 | 0 | 0 | 2018-12-22 |  |  | InProgress | 90%
1204-22-PR-DSH-144 | 00 | Process Instrument Data Sheet for Restriction Orifice | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-24 |  |  | InProgress | 80%
1204-90-HV-DSH-070 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR TEA ROOM IN GUARD HOUSE | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:36 | DSH | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DWG-001 | 05 | CONTROL ROOM - DUCTING LAYOUT | DE | IFC | HV | PS-OT-T-0706 | 2018-10-22 |  | No | 560 | 1204-Owner-v | 2018-10-24 16:28 | CDW | 2018-10-22 | 0 | 0 | 0 | 2018-10-22 |  |  | complete | 100%
1204-90-HV-DSH-038 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR PRAYER ROOM IN FIRE STATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 15:04 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-83-HS-DBS-001 | 00 | DESIGN BASIS FOR FLARE SYSTEM | DE | IFR | HSE | PS-TM-T-0196 | 2014-01-13 |  | No | 2303 | 1204-TKT-COLANGELI | 2013-01-15 11:55 | DBS | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-30-ST-DWG-358 | 01 | D-3007 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-338 | 2016-09-19 |  | No | 1323 | 1204-Owner-v | 2016-09-21 09:24 | CDW | 2016-09-19 | 0 | 0 | 0 | 2016-09-19 | 2016-09-21 | MT-PS-9301-CS-189 | complete | 100%
1204-30-ST-DWG-392 | 01 | T-3001 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0394 | 2014-09-15 |  | No | 2058 | 1204-TKT-COLANGELI | 2014-09-12 11:53 | CDW | 2014-07-15 | 0 | 0 | 0 | 2014-07-15 |  |  | complete | 100%
1204-20-RE-DSH-001 | 00 | DATA SHEET FOR SYNTHESIS GAS COMPRESSOR C-2001 | DE | IFR | MC | PS-OT-T-0157 | 2015-12-21 |  | No | 1596 | 1204-Owner-v | 2015-12-22 15:46 | DSH | 2015-12-23 | 0 | 0 | 0 | 2015-12-23 | 2016-01-06 | MT-PS-9301-CS-076 | InProgress | 80%
1204-00-PI-LST-3400 | 00 | A/G ISOMETRIC LIST OF AREA-34 | DE | IFR | PI | PS-OT-T-0287 | 2016-06-13 |  | No | 1421 | 1204-Owner-v | 2016-06-14 09:48 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-71-PI-APL-3200 | 00 | PIPING PLAN AREA-32 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-12 11:49 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-00-PI-TBA-464A | 01 | TECHNICAL BID ANALYSIS FOR U/G VALVES(MTO I) | DE | IFE | PI | PS-OT-T-0266 | 2016-05-18 |  | No | 1447 | 1204-Owner-v | 2016-05-18 16:10 | TBA | 2016-05-18 | 0 | 0 | 0 | 2016-05-18 |  |  | complete | 100%
1204-02-EL-SLD-057 | 00 | SINGLE LINE DIAGRAM FOR 02-ELP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:00 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:40 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-03-EL-SLD-060 | 00 | SINGLE LINE DIAGRAM FOR 03-LP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:00 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:41 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-03-EL-DWG-022 | 00 | EARTHING LAYOUT FOR AREA-03 D-3003, 3004, 3005& E-3003A/B/C/D | DE | IFR | EL | PS-OT-T-0230 | 2013-04-06 | 2016-07-23 10:17 | Yes | 1190 | 1204-Owner-v | 2016-04-07 10:37 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-130 | InProgress | 80%
1204-00-ST-MTO-1130 | 00 | MATERIAL TAKE OFF FOR DV-6301 | DE | IFE | ST | PS-OT-T-0594 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-28 08:39 | LIST | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 | 2018-05-09 | MT-PS-9609-CS-064 | complete | 100%
1204-00-PV-REQ-205B | 00 | REQUISITION FOR INTERNALS (GROUP II) | DE | IFI | MD | PS-OT-T-0605 | 2018-05-12 |  | No | 723 | 1204-Owner-v | 2018-05-13 15:01 | REQ | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 |  |  | InProgress | 90%
1204-10-HM-TBA-251D | 01 | TECHNICAL BID ANALYSIS FOR REFORMER INLET AND OUTLET LINES, COLD COLLECTOR & TRANSFER LINE INCLUDING REFRACTORYMATERIAL SUPPLY AND INSTALLATION | DE | IFE | MD | PS-OT-T-0872 | 2020-01-20 |  | No | 105 | 1204-Owner-v | 2020-01-23 11:55 | TBA | 2020-01-18 | 0 | 0 | 2020-01-31 | * |  |  | complete | 100%
1204-10-HM-TBA-251E | 00 | TECHNICAL BID ANALYSIS FOR EXPANSION JOINTS OF PRIMARY REFORMER PACKAGE | DE | IFE | MD | PS-OT-T-0871 | 2020-01-15 |  | No | 110 | 1204-Owner-v | 2020-01-15 17:21 | TBA | 2020-06-30 | 0 | 0 | 2020-07-21 | * | 2020-01-03 | MT-PS-9609-CS-0262 | complete | 100%
1204-00-PR-PID-013 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR UNIT 50- BATTERY LIMIT | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:26 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-10-HM-REQ-251B | 02 | REQUISITION FOR STEEL WORK SUPPLY AND SHOP PREFABRICATION (FURNACE) | DE | IFP | MD | PS-OT-T-0792 | 2019-05-11 |  | No | 359 | 1204-Owner-v | 2019-05-12 15:56 | REQ | 2019-05-15 | 0 | 0 | 0 | 2019-05-15 |  |  | complete | 100%
1204-30-PI-LST-2800 | 01 | A/G ISOMETRIC LIST OF AREA-28 | DE | IFC-WH | PI | PS-OT-T-0666 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-17 09:36 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-40-PI-ISO-4200 | 00 | A/G ISOMETRIC DRAWING OF AREA-42 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:06 | CDW | 2020-01-13 | 0 | 0 | 2020-06-25 | 2016-09-03 |  |  | InProgress | 80%
1204-10-PV-DSH-201 | 00 | MECHANICAL DATA SHEET FOR HYDROGENATOR REACTOR (R-1001) | DE | IFR | MD | PS-OT-T-0124 | 2015-11-02 |  | No | 1645 | 1204-Owner-v | 2015-11-02 16:28 | DSH | 2015-11-04 | 0 | 0 | 0 | 2015-11-04 | 2015-11-14 | MT-PS-9301-CS-041 | InProgress | 80%
1204-83-PV-DSH-213 | 00 | MECHANICAL DATA SHEET FOR FLARE KNOCK-OUT DRUM (D-8301) | DE | IFR | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:42 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | InProgress | 80%
1204-00-PR-UDD-022 | 00 | UTILITY DISTRIBUTION DIAGRAM FOR LP STEAM DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:26 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2017-02-23 |  |  | InProgress | 80%
1204-00-IN-DWG-039 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 39) | DE | IFR | IN | PS-OT-T-358 | 2016-11-07 |  | No | 1274 | 1204-Owner-v | 2016-11-09 09:52 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | * | 2017-01-11 | MT-PS-9301-CS-196-R | InProgress | 80%
1204-05-EL-DWG-011 | 00 | LIGHTING LAYOUT FOR AREA-05 AE-3002 | DE | IFR | EL | PS-OT-T-0186 | 2016-01-18 | 2016-07-24 11:29 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:39 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | 2016-01-24 | 2016-01-26 | MT-PS-9301-CS-096 | InProgress | 80%
1204-62-RE-DSH-023 | 00 | DATA SHEET FOR EMERGENCY AIR COMPRESSOR C-6201 | DE | IFR | MC | PS-OT-T-0436 | 2017-04-09 |  | No | 1121 | 1204-Owner-v | 2017-04-18 11:44 | DSH | 2017-04-16 | 0 | 0 | 0 | 2017-04-16 |  |  | InProgress | 80%
1204-00-PI-TBA-465A | 00 | TECHNICAL BID ANALYSIS FOR U/G BOLTS & NUTS(MTO I) | DE | IFE | PI | PS-OT-T-0463 | 2017-08-05 |  | No | 1003 | 1204-Owner-v | 2017-08-06 14:10 | TBA | 2017-08-08 | 0 | 0 | 0 | 2017-08-08 | 2017-08-13 | MT-PS-9301-CS-230 | complete | 100%
1204-10-ST-DWG-146 | 01 | REFORMER (S-1001) / FDN. (G.A.& R.C.) | DE | IFC | ST | PS-OT-T-0635 | 2018-06-23 |  | No | 681 | 1204-Owner-v | 2018-06-26 11:27 | CDW | 2018-08-25 | 0 | 0 | 0 | 2018-08-25 | 2018-07-01 | MT-PS-9609-CS-091 | complete | 100%
1204-30-ST-DWG-306 | 04 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 / CONCRETE STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0778 | 2019-04-14 |  | No | 386 | 1204-Owner-v | 2019-04-17 17:14 | CDW | 2019-04-18 | 0 | 0 | 0 | 2019-04-18 |  |  | complete | 100%
1204-00-ST-DWG-1116 | 04 | RETAINING WALL (WEST) / G.A. PLANS & DETAILS | DE | IFC-WH | ST | PS-OT-T-0816 | 2019-07-15 |  | No | 294 | 1204-Owner-v | 2019-07-20 16:35 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-72-PR-DSH-102 | 00 | DATA SHEET FOR CRUDE METHANOL TRANSFER PUMPS (P-7201 A/B) | BE | IFR | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-Owner-v | 2015-09-16 18:09 | DSH | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-00-HS-ESS-155 | 02 | ENGINEERING STANDARD SPECIFICATION FOR FIRE PROOFING CRITERIA | DE | IFE | HSE | PS-OT-T-0097 | 2015-09-09 |  | No | 1699 | 1204-Owner-v | 2015-09-10 10:17 | SPEC | 2015-09-17 | 0 | 0 | 0 | 2015-09-17 |  |  | complete | 100%
1204-63-PR-DBS-101 | 00 | Basic Engineering Design Basis For Cooling Water System | BE | IFR | PR | TM-OT-9001-T-0007 | 2011-05-10 |  | No | 3282 | 1204-TKT-proietti | 2011-05-09 18:06 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2011-05-10 |  |  | InProgress | 80%
1204-03-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-03 | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:50 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:43 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2015-12-17 | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-03-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 03 | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:52 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:44 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2015-12-17 | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-05-EL-DWG-001 | 01 | POWER LAYOUT - AREA 05 | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 11:02 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:04 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | * | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-90-EL-DWG-730 | 01 | WORK SHOP BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:04 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:45 | CDW | 2014-01-29 | 0 | 0 | 0 | 2014-01-29 |  |  | complete | 100%
1204-00-EL-MSS-514 | 01 | MATERIAL STANDARD SPECIFICATION FOR CLOSED CIRCUIT TELEVISION SYSTEM | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:55 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-PI-SDG-404 | 01 | STANDARD DRAWING FOR PIPING SUPPORT | DE | IFE | PI | TM-OT-9001-T-0426 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-07 16:04 | SPEC | 2015-01-12 | 0 | 0 | 0 | 2015-01-12 |  |  | complete | 100%
1204-00-PV-ESS-244 | 01 | ENGINEERING STANDARD SPECIFICATION FOR ATMOSPHERIC STORAGE TANK | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-04-10 11:08 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-72-PR-UFD-721 | 01 | UTILITY FLOW DIAGRAM FOR CRUDE METHANOL STORAGE TANK | BE/DE | IFE | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-TKT-COLANGELI | 2013-03-12 12:09 | EDW | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-00-ST-SDG-765 | 01 | STANDARD DRAWING FOR PLUMBING | DE | IFC | ST | PS-OT-T-0045 | 2015-05-18 |  | No | 1813 | 1204-Owner-v | 2015-05-19 10:42 | SPEC | 2015-05-18 | 0 | 0 | 0 | 2015-05-18 |  |  | complete | 100%
1204-00-ST-ESS-738 | 01 | ENGINEERING STANDARD SPECIFICATION FOR BUILDING PLUMBING | DE | IFC | ST | PS-OT-T-0031 | 2015-05-04 |  | No | 1827 | 1204-Owner-v | 2015-05-05 08:36 | SPEC | 2015-05-04 | 0 | 0 | 0 | 2015-05-04 |  |  | complete | 100%
1204-72-PR-DBS-101 | 01 | BASIC ENGINEERING DESIGN BASIS FOR CRUDE METHANOL STORAGE TANK | BE/DE | IFE | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:20 | EDW | 2013-07-03 | 0 | 0 | 0 | 2013-07-03 |  |  | complete | 100%
1204-00-EL-DSH-5034 | 01 | DATA SHEET FOR LV SWITCHGEAR (MS-SWB3A,B-04) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:24 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:04 | DSH | 2020-05-12 | 0 | 0 | 2020-05-12 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-MSS-505 | 01 | MATERIAL STANDARD SPECIFICATION FOR POWER DISTRIBUTION CONTROL SYSTEM | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:00 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-64-PR-UFD-641 | 02 | UTILITY FLOW DIAGRAM FOR WATER POLISHING SYSTEM | BE/DE | IFE | PR | PS-OT-T-0053 | 2015-05-30 |  | No | 1801 | 1204-Owner-v | 2015-05-30 15:37 | EDW | 2015-05-30 | 0 | 0 | 0 | 2015-05-30 |  |  | complete | 100%
1204-00-EL-SCH-5032 | 00 | LV SWITCHGEAR SCHEDULE (MS-SWB3A,B-02) | DE | IFR | EL | TM-OT-9001-T-0319 | 2013-09-25 |  | No | 2413 | 1204-TKT-COLANGELI | 2013-09-23 11:25 | LIST | 2020-05-11 | 0 | 0 | 2020-05-11 | 2013-09-24 |  |  | InProgress | 90%
1204-06-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-06 | DE | IFR | EL | PS-OT-T-0186 | 2016-01-18 | 2016-07-24 11:30 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:40 | CDW | 2020-08-20 | 0 | 0 | 2020-08-20 | 2016-01-24 | 2016-01-26 | MT-PS-9301-CS-096 | InProgress | 80%
1204-90-EL-DWG-021 | 01 | SUBSTATION LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:00 | CDW | 2012-10-19 | 0 | 0 | 0 | 2012-10-19 |  |  | complete | 100%
1204-90-EL-SLD-034 | 01 | SUBSTATION NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:44 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:35 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-SCH-001 | 02 | FIRE PROOFING SCHEDULE FOR PROCESS UNITS | DE | IFC-WH | HSE | PS-OT-T-0383 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:11 | LIST | 2020-07-10 | 0 | 0 | 2020-07-10 | 2016-12-19 |  |  | complete | 100%
1204-20-HS-PID-002 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR FOAM SYSTEM FOR C-2001 & C-2002 | DE | IFR | HSE | PS-OT-T-0545 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 08:25 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * | 2018-02-07 | MT-PS-9609-CS-024 | InProgress | 80%
1204-84-HS-PID-840 | 00 | PIPING AND INSTRUMENTATION DIAGRAM FOR OILY WATER TREATMENT SYSTEM | DE | IFR | HSE | PS-OT-T-0687 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:19 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * |  |  | InProgress | 80%
1204-00-IN-TBA-605 | 01 | TECHNICAL BID ANALYSIS FOR CONTROL VALVES | DE | IFE | IN | PS-OT-T-0860 | 2020-01-01 |  | No | 124 | 1204-Owner-v | 2020-01-01 16:07 | TBA | 2020-01-01 | 0 | 0 | 0 | 2020-01-01 | 26-01-2020 | MT-PS-9609-CS-0258 | complete | 100%
1204-00-EL-MSS-520 | 01 | MATERIAL STANDARD SPECIFICATION FOR AIR CRAFT WARNING LIGHTS | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:34 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-625 | 01 | MATERIAL STANDARD SPECIFICATION FOR TEMP. ELEMENTS / TRANSMITTERS & THERMOWELLS | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:08 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-641 | 01 | MATERIAL STANDARD SPECIFICATION FOR TEMPERATURE GAUGES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:09 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-62-PR-DSH-103 | 01 | DATA SHEET FOR EMERGENCY INSTRUMENT AIR STORAGE (D-6202) | BE | IFE | PR | PS-OT-T-0179 | 2016-01-11 |  | No | 1575 | 1204-Owner-v | 2016-01-12 09:39 | DSH | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 | 2016-01-26 | MT-PS-9301-CS-093-1 | complete | 100%
1204-00-EL-SCH-5031 | 00 | LV SWITCHGEAR SCHEDULE (MS-SWB3A,B-01) | DE | IFR | EL | TM-OT-9001-T-0319 | 2013-09-25 |  | No | 2413 | 1204-TKT-COLANGELI | 2013-09-23 11:21 | LIST | 2020-05-11 | 0 | 0 | 2020-05-11 | 2013-09-24 |  |  | InProgress | 90%
1204-90-EL-DWG-721 | 01 | WORK SHOP BUILDING LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:27 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-DWG-910 | 01 | WAREHOUSE BUILDING LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:31 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-EL-MSS-501 | 01 | MATERIAL STANDARD SPECIFICATION FOR NEUTRAL GROUNDING RESISTORS | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:50 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 | 2014-12-31 | MT-TM-9301-CS-032 | complete | 100%
1204-00-IN-MSS-607 | 01 | MATERIAL STANDARD SPECIFICATION FOR RUPTURE DISCS | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:03 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-00-ST-SDG-758 | 01 | STANDARD DRAWING FOR FIRE PROOFING | DE | IFC | ST | PS-OT-T-0041 | 2015-05-13 |  | No | 1818 | 1204-Owner-v | 2015-05-13 16:10 | SPEC | 2015-05-13 | 0 | 0 | 0 | 2015-05-13 |  |  | complete | 100%
1204-22-PR-DSH-103 | 00 | Data Sheet For Machinery Cooling Water Storage Tank (TK-2201) | BE | IFR | PR | TM-OT-9001-T-0013 | 2011-06-06 |  | No | 3255 | 1204-TKT-proietti | 2011-06-06 14:30 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 80%
1204-22-PR-DSH-104 | 00 | Data Sheet For Machinery Cooling Water Coolers (E-2201) | BE | IFR | PR | TM-OT-9001-T-0012 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:22 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 |  |  |  | InProgress | 80%
1204-64-PR-DSH-104 | 01 | DATA SHEET FOR DEMIN WATER STORAGE TANK (TK-6402) | BE | IFE | PR | TM-OT-9001-T-0299 | 2013-07-04 |  | No | 2496 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-00-EL-MSS-512 | 01 | MATERIAL STANDARD SPECIFICATION FOR TELEPHONE SYSTEM | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:10 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-64-PR-DSH-110 | 00 | Data Sheet For Caustic Unloading Pump (P-6406) | BE | IFR | PR | TM-OT-9001-T-0013 | 2011-06-06 |  | No | 3255 | 1204-TKT-proietti | 2011-06-06 14:37 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-06 |  |  | InProgress | 80%
1204-00-HM-MSS-288 | 00 | Material Standard Specification Of Plate Heat Exchanger | DE | IFR | MD | TM-OT-9001-T-0080 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-14 09:32 | SPEC | 2012-05-29 | #N/A | #N/A | #N/A | 2012-05-29 |  |  | InProgress | 80%
1204-00-EL-SLD-004 | 01 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR - MS-SWB3A,B-02 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:55 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:36 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2018-01-20 | MT-PS-9609-CS-008 | InProgress | 80%
1204-90-EL-DWG-011 | 01 | SUBSTATION SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:43 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:59 | CDW | 2012-10-19 | 0 | 0 | 0 | 2012-10-19 |  |  | complete | 100%
1204-00-PI-CSS-411 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR PIPING FABRICATION & ERECTION | DE | IFE | PI | TM-OT-9001-T-0426 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-07 14:47 | SPEC | 2015-01-12 | 0 | 0 | 0 | 2015-01-12 |  |  | complete | 100%
1204-00-ST-SDG-756 | 01 | STANDARD DRAWING FOR STEEL STAIRS | DE | IFC | ST | PS-OT-T-0041 | 2015-05-13 |  | No | 1818 | 1204-Owner-v | 2015-05-13 16:10 | SPEC | 2015-05-13 | 0 | 0 | 0 | 2015-05-13 |  |  | complete | 100%
1204-00-EL-SCH-5035 | 00 | LV SWITCHGEAR SCHEDULE (MS-SWB3A,B,C-05) | DE | IFR | EL | TM-OT-9001-T-0319 | 2013-09-25 |  | No | 2413 | 1204-TKT-COLANGELI | 2013-09-23 11:33 | LIST | 2020-05-12 | 0 | 0 | 2020-05-12 | 2013-09-24 |  |  | InProgress | 90%
1204-00-EL-TBA-502 | 00 | TECHNICAL BID ANALYSIS FOR MEDIUM VOLTAGE SWITCHGEARS | DE | IFE | EL | PS-OT-T-0619 | 2018-05-28 |  | No | 707 | 1204-Owner-v | 2018-06-03 11:19 | TBA | 2018-05-28 | 0 | 0 | 0 | 2018-05-28 | 2018-06-23 | MT-PS-9609-CS-085-R | complete | 100%
1204-00-EL-MSS-503 | 01 | MATERIAL STANDARD SPECIFICATION FOR L.V SWITCHGEARS/MCC | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:56 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-EL-MSS-524 | 01 | MATERIAL STANDARD SPECIFICATION FOR ELECTRICAL EQUIPMENT AS PART OF PACKAGE | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:39 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-605 | 01 | MATERIAL STANDARD SPECIFICATION FOR CONTROL VALVES | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:05 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-ST-SDG-755 | 01 | STANDARD DRAWING FOR GRATING AND CHEQUERED PLATE | DE | IFC | ST | PS-OT-T-0040 | 2015-05-12 |  | No | 1819 | 1204-Owner-v | 2015-05-13 14:23 | SPEC | 2015-05-12 | 0 | 0 | 0 | 2015-05-12 |  |  | complete | 100%
1204-00-ST-ESS-745 | 01 | ENGINEERING STANDARD SPECIFICATION FOR BLAST RESISTANT STRUCTURES | DE | IFC | ST | TM-OT-9001-T-0425 | 2015-01-09 |  | No | 1942 | 1204-TKT-COLANGELI | 2015-01-09 12:22 | SPEC | 2015-01-09 | 0 | 0 | 0 | 2015-01-09 | 2015-01-28 | MT-TM-9301-CS-034 | complete | 100%
1204-22-PR-DSH-101 | 00 | Data Sheet For Corrosion Inhibitor Vessel (D-2201) | BE | IFR | PR | TM-OT-9001-T-0012 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:16 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 80%
1204-22-PR-DSH-102 | 00 | Data Sheet For Machinery Cooling Water Pumps (P-2201 A/b) | BE | IFR | PR | TM-OT-9001-T-0012 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:17 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 80%
1204-00-EL-DIG-528 | 01 | MOTOR CONTROL STATION CIRCUIT DIAGRAMS | DE | IFR | EL | PS-OT-T-0509 | 2017-12-09 | 2018-02-13 09:05 | Yes | 52 | 1204-Owner-v | 2017-12-11 09:27 | CDW | 2020-04-23 | 0 | 0 | 2020-04-23 | * | 2017-12-18 | MT-PS-9301-CS-270 | InProgress | 80%
1204-00-EL-DSH-506 | 00 | DATA SHEET FOR 110V AC UPS (CR-UPS-01) | DE | IFR | EL | PS-OT-T-481 | 2017-09-11 |  | No | 966 | 1204-Owner-v | 2017-09-13 11:35 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | * | 2018-06-10 | MT-PS-9301-CS-250-R | InProgress | 80%
1204-00-EL-SDG-621 | 01 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - LIGHTING | DE | IFR | EL | PS-OT-T-0118 | 2015-10-12 | 2015-11-28 09:18 | Yes | 33 | 1204-Owner-v | 2015-10-13 17:16 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | * | 2015-11-19 | MT-PS-9301-CS-044 | InProgress | 80%
1204-00-EL-MSS-502 | 01 | MATERIAL STANDARD SPECIFICATION FOR M.V SWITCHGEARS | DE | IFI | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:52 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-PI-CSS-414 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR COATING & WRAPPING OF UNDERGROUND PIPING | DE | IFE | PI | PS-OT-T-0494 | 2017-09-24 |  | No | 953 | 1204-Owner-v | 2017-09-25 08:31 | SPEC | 2017-09-25 | 0 | 0 | 0 | 2017-09-25 | 2017-10-23 | MT-PS-9301-CS-261 | complete | 100%
1204-90-EL-SLD-044 | 01 | ADMIN. NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:47 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DWG-001 | 02 | FIRE PROOFING LAYOUT | DE | IFC-WH | HSE | PS-OT-T-380 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:10 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2016-12-16 |  |  | complete | 100%
1204-00-HS-REQ-153 | 01 | REQUISITION FOR AUTOMATIC CO2/CLEAN AGENT SYSTEM | DE | IFI | HSE | PS-OT-T-0898 | 2020-02-18 |  | No | 76 | 1204-Owner-v | 2020-02-18 16:59 | REQ | 2020-08-31 | 0 | 0 | 2020-09-11 | * | 2020-03-01 | MT-PS-9609-CS-0288 | InProgress | 90%
1204-82-HS-DWG-001 | 02 | FIRE WATER NETWORK | DE | IFC-WH | HSE | PS-OT-T-377 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:03 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2016-12-16 | 2017-01-30 | MT-PS-9301-CS-209 | InProgress | 90%
1204-00-IN-DSH-603 | 01 | DATA SHEET FOR PROCESS STREAM ANALYZERS | DE | IFR | IN | PS-OT-T-462 | 2017-07-30 |  | No | 1009 | 1204-Owner-v | 2017-07-31 12:56 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2017-10-10 | 2017-10-15 | MT-PS-9301-CS-233-1 | InProgress | 80%
1204-00-IN-REQ-611 | 00 | REQUISITION FOR MASS FLOW METER | DE | IFI | IN | PS-OT-T-0149 | 2015-12-20 |  | No | 1597 | 1204-Owner-v | 2015-12-21 11:12 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | 2015-12-23 | 2016-02-09 | MT-PS-9301-CS-105 | InProgress | 90%
1204-00-IN-REQ-612 | 00 | REQUISITION FOR ORIFICE PLATES & FLANGES | DE | IFI | IN | PS-OT-T-0187 | 2016-01-19 |  | No | 1567 | 1204-Owner-v | 2016-01-21 12:04 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | 2016-01-24 | 2016-02-07 | MT-PS-9301-CS-101 | InProgress | 90%
1204-00-PV-REQ-204A | 01 | REQUISITION FOR PRESSURE VESSELS (GROUP I) | DE | IFP | MD | PS-OT-T-0105 | 2015-09-23 |  | No | 1685 | 1204-Owner-v | 2015-09-26 15:18 | REQ | 2015-09-23 | 0 | 0 | 0 | 2015-09-23 | 2015-11-19 |  | complete | 100%
1204-00-PV-REQ-204B | 01 | REQUISITION FOR PRESSURE VESSELS (GROUP II) | DE | IFP | MD | PS-OT-T-0166 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:51 | REQ | 2015-12-30 | 0 | 0 | 0 | 2015-12-30 | 2016-01-17 | MT-PS-9301-CS-088 | complete | 100%
1204-00-ST-ESS-747 | 01 | ENGINEERING STANDARD SPECIFICATION FOR STORAGE TANK FDN. | DE | IFC | ST | TM-OT-9001-T-0425 | 2015-01-09 |  | No | 1942 | 1204-TKT-COLANGELI | 2015-01-09 12:28 | SPEC | 2015-01-09 | 0 | 0 | 0 | 2015-01-09 | 2015-01-28 | MT-TM-9301-CS-034 | complete | 100%
1204-02-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-02 | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 11:00 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:03 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-11-12 | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-07-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-07 | DE | IFR | EL | PS-OT-T-0159 | 2015-12-28 | 2016-07-21 15:14 | Yes | 192 | 1204-Owner-v | 2015-12-30 13:57 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2016-01-16 | 2016-01-19 | MT-PS-9301-CS-078-1 | InProgress | 80%
1204-90-EL-DWG-930 | 01 | WAREHOUSE BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:03 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:48 | CDW | 2014-01-29 | 0 | 0 | 0 | 2014-01-29 |  |  | complete | 100%
1204-00-PI-ESS-408 | 01 | ENGINEERING STANDARD SPECIFICATION FOR EFFLUENT GATHERING SYSTEM | DE | IFE | PI | TM-OT-9001-T-0370 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 13:59 | SPEC | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 | 2014-06-25 | MT-OT-9301-CS-004 | complete | 100%
1204-00-IN-MSS-624 | 01 | MATERIAL STANDARD SPECIFICATION FOR ELECTRONIC TRANSMITTERS | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:08 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-ST-SDG-762 | 01 | STANDARD DRAWING FOR BRACINGS | DE | IFC | ST | PS-OT-T-0043 | 2015-05-17 |  | No | 1814 | 1204-Owner-v | 2015-05-18 09:31 | SPEC | 2015-05-17 | 0 | 0 | 0 | 2015-05-17 |  |  | complete | 100%
1204-65-PR-DBS-101 | 01 | BASIC ENGINEERING DESIGN BASIS FOR FUEL GAS SYSTEM | BE/DE | IFE | PR | TM-OT-9001-T-0276 | 2013-05-16 |  | No | 2545 | 1204-TKT-COLANGELI | 2013-05-16 11:55 | EDW | 2013-05-16 | 0 | 0 | 0 | 2013-05-16 |  |  | complete | 100%
1204-00-EL-DWG-009 | 02 | OVERALL CCTV LOCATION LAYOUT | DE | IFR | EL | PS-OT-T-0879 | 2020-02-04 |  | No | 90 | 1204-Owner-v | 2020-02-08 09:43 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | * | 2020-03-07 | MT-PS-9609-CS-0303 | InProgress | 80%
1204-00-PI-ESS-406 | 03 | ENGINEERING STANDARD SPECIFICATION FOR PAINTING | DE | IFE | PI | PS-OT-T-0531 | 2017-01-07 |  | No | 1213 | 1204-Owner-v | 2018-01-13 11:32 | SPEC | 2018-01-21 | 0 | 0 | 0 | 2018-01-21 | 2018-01-28 | MT-PS-9609-CS-019 | complete | 100%
1204-00-IN-MSS-614 | 01 | MATERIAL STANDARD SPECIFICATION FOR ROTAMETERS | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:06 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-HM-ESS-290 | 01 | ENGINEERING STANDARD SPECIFICATION FOR AIR COOLED HEAT EXCHANGERS | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-03-03 11:25 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-00-ST-ESS-741 | 01 | ENGINEERING STANDARD SPECIFICATION FOR YARD PAVING | DE | IFC | ST | TM-OT-9001-T-0411 | 2014-11-18 |  | No | 1994 | 1204-TKT-COLANGELI | 2014-11-17 12:47 | SPEC | 2014-11-18 | 0 | 0 | 0 | 2014-11-18 |  |  | complete | 100%
1204-00-ST-ESS-748 | 01 | ENGINEERING STANDARD SPECIFICATION FOR GROUTING | DE | IFC | ST | PS-OT-T-0031 | 2015-05-04 |  | No | 1827 | 1204-Owner-v | 2015-05-05 08:36 | SPEC | 2015-05-04 | 0 | 0 | 0 | 2015-05-04 |  |  | complete | 100%
1204-00-ST-CSS-753 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR BUILDING MATERIALS AND CONSTRUCTION | DE | IFC | ST | TM-OT-9001-T-0425 | 2015-01-09 |  | No | 1942 | 1204-TKT-COLANGELI | 2015-01-09 12:33 | SPEC | 2015-01-09 | 0 | 0 | 0 | 2015-01-09 | 2015-01-28 | MT-TM-9301-CS-034 | complete | 100%
1204-00-EL-DSH-5035 | 01 | DATA SHEET FOR LV SWITCHGEAR (MS-SWB3A,B-05) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:25 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:04 | DSH | 2020-05-08 | 0 | 0 | 2020-05-08 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-ESS-501 | 01 | ENGINEERING STANDARD SPECIFICATION FOR ELECTRICAL SYSTEM DESIGN | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:43 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-EL-ESS-501 | 01 | ENGINEERING STANDARD SPECIFICATION FOR ELECTRICAL SYSTEM DESIGN | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:43 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-ST-SDG-754 | 01 | STANDARD DRAWING FOR HANDRAIL | DE | IFC | ST | PS-OT-T-0040 | 2015-05-12 |  | No | 1819 | 1204-Owner-v | 2015-05-13 14:16 | SPEC | 2015-05-12 | 0 | 0 | 0 | 2015-05-12 |  |  | complete | 100%
1204-64-PR-DSH-107 | 01 | DATA SHEET FOR DEMIN WATER TRANSFER PUMPS (P-6402 A/B) | BE | IFE | PR | TM-OT-9001-T-0299 | 2013-07-04 |  | No | 2496 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-64-PR-DSH-109 | 00 | Data Sheet For Sulfuric Acid Transfer Pumps (P-6403 A/b) | BE | IFR | PR | TM-OT-9001-T-0011 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:49 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-01 |  |  | InProgress | 80%
1204-00-EL-REQ-502 | 01 | REQUISITION FOR MEDIUM VOLTAGE SWITCHGEARS | DE | IFP | EL | PS-OT-T-0882 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:27 | REQ | 2020-02-06 | 0 | 0 | 0 | 2020-02-06 |  |  | complete | 100%
1204-03-EL-DWG-020 | 01 | EARTHING LAYOUT - AREA 03 | DE | IFR | EL | PS-OT-T-0115 | 2015-10-10 | 2016-01-14 11:58 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:08 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2015-11-19 | MT-PS-9301-CS-043 | InProgress | 80%
1204-00-ST-ESS-746 | 03 | ENGINEERING STANDARD SPECIFICATION FOR ANCHOR BOLTS | DE | IFC | ST | PS-OT-T-0205 | 2016-03-01 |  | No | 1525 | 1204-Owner-v | 2016-03-02 15:17 | SPEC | 2016-03-09 | 0 | 0 | 0 | 2016-03-09 |  | Final Checked | complete | 100%
1204-63-PR-DSH-106 | 03 | DATA SHEET FOR ANTI FOULING INJECTION PACKAGE (PU-6303) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-00-MC-MSS-003 | 00 | Matreial Standard Specification for General Purpose Steam Turbines | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-01-17 13:58 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-DSH-5044 | 01 | DATA SHEET FOR DISTRIBUTION TRANSFORMERS -2500 KVA | DE | IFR | EL | PS-OT-T-0246 | 2016-04-18 | 2016-07-23 10:16 | Yes | 82 | 1204-Owner-v | 2016-04-18 17:29 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | * | 2016-04-23 | MT-PS-9301-CS-137 | InProgress | 80%
1204-00-PV-ESS-241 | 01 | ENGINEERING STANDARD SPECIFICATION FOR PRESSURE VESSELS | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-04-10 11:09 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-65-PR-UFD-651 | 01 | UTILITY FLOW DIAGRAM FOR FUEL GAS SYSTEM | BE/DE | IFR | PR | TM-OT-9001-T-0276 | 2013-05-16 |  | No | 2545 | 1204-TKT-COLANGELI | 2013-05-16 12:02 | EDW | 2020-06-01 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 80%
1204-61-PR-LST-001 | 01 | EQUIPMENT LIST FOR NITROGEN (ASU) SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 12:00 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-00-EL-DSH-5036 | 01 | DATA SHEET FOR AUTO/MANUAL TRANSFER 400V SWITCHGEARS | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:26 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:04 | DSH | 2020-05-08 | 0 | 0 | 2020-05-08 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-DWG-003 | 02 | ELECTRICAL AREA DIVISION DRAWING | DE | IFR | EL | PS-OT-T-0112 | 2015-10-10 | 2015-11-08 08:25 | Yes | 15 | 1204-Owner-v | 2015-10-10 13:05 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2015-10-14 | 2015-11-02 | MT-PS-9301-CS-038 | InProgress | 80%
1204-00-EL-ESS-504 | 01 | ENGINEERING STANDARD SPECIFICATION FOR LIGHTNING PROTECTION | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:47 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-ST-SDG-703 | 01 | STANDARD DRAWING FOR EQUIVALENT BUILT-UP SECTIONS | DE | IFC | ST | PS-OT-T-0040 | 2015-05-12 |  | No | 1819 | 1204-Owner-v | 2015-05-13 14:22 | SPEC | 2015-05-12 | 0 | 0 | 0 | 2015-05-12 |  |  | complete | 100%
1204-00-ST-SDG-761 | 02 | STANDARD DRAWING FOR DOORS AND WINDOWS | DE | IFC | ST | PS-OT-T-0028 | 2015-04-29 |  | No | 1832 | 1204-Owner-v | 2015-05-03 11:05 | SPEC | 2015-04-29 | 0 | 0 | 0 | 2015-04-29 |  |  | complete | 100%
1204-64-PR-DBS-101 | 01 | BASIC ENGINEERING DESIGN BASIS FOR WATER POLISHING SYSTEM SYSTEM | BE/DE | IFE | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:03 | EDW | 2013-07-03 | 0 | 0 | 0 | 2013-07-03 |  |  | complete | 100%
1204-00-EL-MTO-003 | 00 | MATERIAL TAKE OFF FOR EARTHING AND LIGHTNING PROTECTION | DE | IFE | EL | PS-OT-T-0232 | 2013-04-06 | 2016-07-21 15:06 | Yes | 1188 | 1204-Owner-v | 2016-04-07 10:38 | LIST | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-132 | complete | 100%
1204-00-EL-SDG-623 | 00 | Electrical Installation Standard Drawings - Lightning Protection | DE | IFR | EL | TM-OT-9001-T-0096 | 2012-05-31 | 2015-08-12 12:08 | Yes | 1154 | 1204-Owner-v | 2015-09-14 17:19 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | 2012-05-31 | 2014-12-01 | MT-TM-9301-CS-021 | InProgress | 80%
1204-90-EL-SLD-040 | 01 | RESTAURANT NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:44 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-014 | 00 | DATA SHEET FOR WHEELED CO2 EXTINGUISHER | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:16 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-00-HS-DSH-016 | 01 | DATA SHEET FOR SAFETY SHOWER AND EYE WASH | DE | IFR | HSE | PS-OT-T-0084 | 2015-08-02 |  | No | 1737 | 1204-Owner-v | 2015-08-03 09:26 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * | 2015-08-24 | MT-PS-9301-CS-009 | InProgress | 80%
1204-84-HS-PID-841 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR SANITARY WATER COLLECTION SYSTEM | DE | IFR | HSE | PS-OT-T-0856 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2019-12-30 09:21 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * |  | MT-PS-9301-CS-0249 | InProgress | 80%
1204-00-IN-MTO-001 | 00 | MATERIAL TAKE OFF FOR INSTRUMENT CABLES | DE | IFE | IN | PS-OT-T-0895 | 2020-02-18 |  | No | 76 | 1204-Owner-v | 2020-02-18 16:56 | LIST | 2019-12-25 | 0 | 0 | 2020-04-28 | * | 2020-04-14 | MT-PS-9609-CS- 0276-R | complete | 100%
1204-00-EL-MSS-522 | 01 | MATERIAL STANDARD SPECIFICATION FOR MEDIUM VOLTAGE INDUCTION ELECTRIC MOTORS | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:38 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-606 | 01 | MATERIAL STANDARD SPECIFICATION FOR PRESSURE RELIEF VALVES | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:05 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-PV-SDG-250 | 00 | Standard Drawing for Storage Tank | DE | IFR | MD | TM-OT-9001-T-0077 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:06 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | 2012-05-29 |  |  | InProgress | 80%
1204-62-PR-DSH-101 | 01 | DATA SHEET FOR EMERGENCY AIR COMPRESSOR (C-6201) | BE | IFE | PR | PS-OT-T-0179 | 2016-01-11 |  | No | 1575 | 1204-Owner-v | 2016-01-12 09:38 | DSH | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 | 2016-01-26 | MT-PS-9301-CS-093-1 | complete | 100%
1204-90-EL-SLD-046 | 01 | FIRE STATION NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:34 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:48 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-008 | 00 | DATA SHEET FOR FOAM TANK SYSTEM | DE | IFR | HSE | PS-OT-T-0065 | 2015-06-27 |  | No | 1773 | 1204-Owner-v | 2015-06-28 08:21 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2015-06-27 |  |  | InProgress | 80%
1204-84-HS-LST-002 | 01 | LINE LIST FOR EFFLUENT WATER TREATMENT UNIT | DE | IFR | HSE | PS-OT-T-0853 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:50 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2020-02-12 | MT-PS-9301-CS-0268 | InProgress | 90%
1204-00-IN-DSH-605 | 04 | DATA SHEET FOR CONTROL VALVES | DE | IFR | IN | PS-OT-T-0918 | 2020-02-26 |  | No | 68 | 1204-Owner-v | 2020-02-27 12:00 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-03-14 | MT-PS-9609-CS-0311 | InProgress | 80%
1204-00-EL-MSS-521 | 01 | MATERIAL STANDARD SPECIFICATION FOR LOW VOLTAGE INDUCTION ELECTRIC MOTORS | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:36 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-PI-CSS-412 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR TESTING ,FLUSHING & REINSTATEMENT OF PIPING | DE | IFE | PI | TM-OT-9001-T-0426 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-09 13:26 | SPEC | 2015-01-12 | 0 | 0 | 0 | 2015-01-12 |  |  | complete | 100%
1204-00-ST-SDG-757 | 01 | STANDARD DRAWING FOR LADDER | DE | IFC | ST | PS-OT-T-0040 | 2015-05-12 |  | No | 1819 | 1204-Owner-v | 2015-05-13 14:24 | SPEC | 2015-05-12 | 0 | 0 | 0 | 2015-05-12 |  |  | complete | 100%
1204-63-PR-DSH-107 | 03 | DATA SHEET FOR SCALE INHIBITOR INJECTION PACKAGE (PU-6304) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-64-PR-DSH-102 | 00 | Data Sheet For Sulfuric Acid Storage Drum (D-6401) | BE | IFR | PR | TM-OT-9001-T-0011 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:43 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-01 |  |  | InProgress | 80%
1204-61-PR-DBS-101 | 00 | Basic Engineering Design Basis For Nitrogen (ASU) System | BE | IFR | PR | TM-OT-9001-T-0007 | 2011-05-10 |  | No | 3282 | 1204-TKT-proietti | 2011-05-09 18:14 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2011-05-10 |  |  | InProgress | 80%
1204-00-EL-DIG-502 | 01 | MV MOTOR STARTER CONTROL CIRCUIT DIAGRAMS | DE | IFR | EL | PS-OT-T-0509 | 2017-12-09 | 2018-02-13 08:50 | Yes | 52 | 1204-Owner-v | 2017-12-11 09:27 | CDW | 2020-04-22 | 0 | 0 | 2020-04-22 | * | 2017-12-18 | MT-PS-9301-CS-270 | InProgress | 80%
1204-00-EL-DIG-503 | 01 | LV MOTOR STARTER CONTROL CIRCUIT DIAGRAMS | DE | IFR | EL | PS-OT-T-0509 | 2017-12-09 | 2018-02-13 08:58 | Yes | 52 | 1204-Owner-v | 2017-12-11 09:27 | CDW | 2020-04-22 | 0 | 0 | 2020-04-22 | * | 2017-12-18 | MT-PS-9301-CS-270 | InProgress | 80%
1204-00-EL-TBA-505 | 00 | TECHNICAL BID ANALYSIS FOR POWER DISTRIBUTION CONTROL SYS | DE | IFE | EL | PS-OT-T-0945 | 2020-04-05 | 2020-05-05 11:24 | Yes | 16 | 1204-Owner-v | 2020-04-11 08:28 | TBA | 2020-12-14 | 0 | 0 | 2021-01-01 | * |  |  | complete | 100%
1204-06-EL-DWG-001 | 01 | POWER LAYOUT - AREA 06 | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:53 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:45 | CDW | 2020-08-20 | 0 | 0 | 2020-08-20 | * | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-00-EL-MSS-528 | 01 | MATERIAL STANDARD SPECIFICATION FOR LOCAL CONTROL STATIONS | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:40 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-603 | 01 | MATERIAL STANDARD SPECIFICATION FOR PROCESS STREAM ANALYZERS | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:05 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-628 | 01 | MATERIAL STANDARD SPECIFICATION FOR INSTRUMENT CABLES | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:04 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-00-IN-MSS-630 | 01 | MATERIAL STANDARD SPECIFICATION FOR INSTRUMENT CABLE LADDER/TRAY & ACCESSORIES | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:04 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-00-HM-SDG-285 | 00 | Standard Drawing for Shell and Tube Heat Exchangers | DE | IFR | MD | TM-OT-9001-T-0071 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-01 15:16 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | 2012-05-29 |  |  | InProgress | 80%
1204-00-PV-SDG-245 | 00 | Standard Drawing for Ladder and Platforms | DE | IFR | MD | TM-OT-9001-T-0071 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:05 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | 2012-05-29 |  |  | InProgress | 80%
1204-02-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 02 | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:49 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:43 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-12-17 | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-00-HS-DSH-025 | 00 | DATA SHEET FOR EVACUATION BELL | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:23 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HS-DSH-028 | 00 | DATA SHEET FOR MOTOR SIREN | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:26 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HS-REQ-151 | 00 | REQUISITION FOR SPRAY NOZZLE | DE | IFI | HSE | PS-OT-T-0740 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:01 | REQ | 2021-01-05 | 0 | 0 | 2021-01-11 | * |  |  | InProgress | 90%
1204-00-EL-ESS-503 | 01 | ENGINEERING STANDARD SPECIFICATION FOR LIGHTING SYSTEM DESIGN | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:44 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-62-PR-UFD-621 | 00 | Utility Flow Diagram Of Instrument Air /Plant Air System | BE | IFR | PR | TM-OT-9001-T-0009 | 2011-05-11 |  | No | 3281 | 1204-TKT-proietti | 2011-05-09 18:23 | EDW | 2020-06-01 | 0 | 0 | 2020-06-30 | 2011-05-11 |  |  | InProgress | 80%
1204-00-ST-SDG-702 | 01 | STANDARD DRAWING FOR BAR BENDING SHAPE CODE | DE | IFC | ST | PS-OT-T-0043 | 2015-05-17 |  | No | 1814 | 1204-Owner-v | 2015-05-18 09:30 | SPEC | 2015-05-17 | 0 | 0 | 0 | 2015-05-17 |  |  | complete | 100%
1204-64-PR-DSH-101 | 00 | Data Sheet For Caustic Storage Drum (D-6402) | BE | IFR | PR | TM-OT-9001-T-0011 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:41 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-01 |  |  | InProgress | 80%
1204-00-EL-DSH-5042 | 01 | DATA SHEET FOR DISTRIBUTION TRANSFORMERS -1600 KVA | DE | IFR | EL | PS-OT-T-0246 | 2016-04-18 | 2016-07-23 10:16 | Yes | 82 | 1204-Owner-v | 2016-04-18 17:29 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | * | 2016-04-23 | MT-PS-9301-CS-137 | InProgress | 80%
1204-00-EL-MTO-004 | 00 | MATERIAL TAKE OFF FOR LIGHTING SYSTEM | DE | IFE | EL | PS-OT-T-0232 | 2013-04-06 | 2016-07-21 15:06 | Yes | 1188 | 1204-Owner-v | 2016-04-07 10:39 | LIST | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-132 | complete | 100%
1204-02-EL-DWG-020 | 01 | EARTHING LAYOUT - AREA 02 | DE | IFR | EL | PS-OT-T-0114 | 2015-10-10 | 2016-01-14 12:02 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:07 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2015-11-19 | MT-PS-9301-CS-042 | InProgress | 80%
1204-82-HS-DWG-002 | 00 | MAIN FIRE ZONE | DE | IFR | HSE | PS-OT-T-0375 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-19 15:36 | EDW | 2019-10-10 | 0 | 0 | 2019-11-07 | 2016-12-16 |  |  | InProgress | 80%
1204-00-EL-MSS-506 | 01 | MATERIAL STANDARD SPECIFICATION FOR AC UPS | DE | IFE | EL | TM-OT-9001-T-0403 | 2014-10-30 | 2015-03-03 08:52 | Yes | 110 | 1204-TKT-COLANGELI | 2014-10-30 12:57 | SPEC | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 |  |  | complete | 100%
1204-00-PI-ESS-407 | 01 | ENGINEERING STANDARD SPECIFICATION FOR THERMAL INSULATION | DE | IFE | PI | PS-OT-T-0528 | 2018-01-02 |  | No | 853 | 1204-Owner-v | 2018-01-07 13:26 | SPEC | 2018-01-08 | 0 | 0 | 0 | 2018-01-08 | 2018-01-28 | MT-PS-9609-CS-018 | complete | 100%
1204-00-PI-ESS-409 | 00 | ENGINEERING STANDARD SPECIFICATION FOR PIPING FLEXIBILITY ANALYSIS | DE | IFR | PI | TM-OT-9001-T-0426 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-07 14:27 | SPEC | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-HM-ESS-286 | 01 | ENGINEERING STANDARD SPECIFICATION FOR SHELL AND TUBE HEAT EXCHANGERS | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-03-03 11:24 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-61-PR-UFD-611 | 00 | Utility Flow Diagram Of Nitrogen (ASU) System | BE | IFR | PR | TM-OT-9001-T-0009 | 2011-05-11 |  | No | 3281 | 1204-TKT-proietti | 2011-05-09 18:15 | EDW | 2020-06-01 | 0 | 0 | 2020-06-30 | 2011-05-11 |  |  | InProgress | 80%
1204-00-ST-SDG-759 | 01 | STANDARD DRAWING FOR STRUCTURAL STEEL CONNECTIONS | DE | IFC | ST | PS-OT-T-0041 | 2015-05-13 |  | No | 1818 | 1204-Owner-v | 2015-05-13 16:10 | SPEC | 2015-05-13 | 0 | 0 | 0 | 2015-05-13 |  |  | complete | 100%
1204-00-IN-MSS-617 | 01 | MATERIAL STANDARD SPECIFICATION FOR VENTURI TUBES & FLOW NOZZLES | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:06 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-620 | 01 | MATERIAL STANDARD SPECIFICATION FOR LEVEL GAUGES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:07 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-63-PR-DSH-109 | 05 | DATA SHEET FOR COOLING WATER SIDE STREAM FILTERS (FT-6301 A/B/C) | BE | IFE | PR | PS-OT-T-0518 | 2017-12-16 |  | No | 870 | 1204-Owner-v | 2017-12-17 13:23 | DSH | 2017-12-19 | 0 | 0 | 0 | 2017-12-19 | 2018-01-13 | MT-PS-9609-CS-006 | complete | 100%
1204-00-IN-MSS-654 | 01 | MATERIAL STANDARD SPECIFICATION FOR POWER DISTRIBUTION PANEL | DE | IFE | IN | PS-OT-T-0257 | 2016-05-08 |  | No | 1457 | 1204-Owner-v | 2016-05-09 09:06 | SPEC | 2016-05-08 | 0 | 0 | 0 | 2016-05-08 |  |  | complete | 100%
1204-00-MC-MSS-007 | 00 | Matreial Standard Specification for Centrifugal Fans | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-04-15 14:19 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-MC-MSS-009 | 00 | Matreial Standard Specification for E.O.T Cranes | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-04-15 14:19 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-DWG-007 | 02 | OVERALL EARTHING LAYOUT | DE | IFR | EL | PS-OT-T-0061 | 2015-06-14 | 2015-07-22 16:04 | Yes | 24 | 1204-Owner-v | 2015-06-15 16:15 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | * | 2015-06-23 | MT-PS-9301-CS-04 | InProgress | 80%
1204-63-PR-DSH-108 | 03 | DATA SHEET FOR PH ADJUSTMENT INJECTION PACKAGE (PU-6305) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-62-PR-DBS-101 | 00 | Basic Engineering Design Basis For Instrument Air / Plant Air System | BE | IFR | PR | TM-OT-9001-T-0007 | 2011-05-10 |  | No | 3282 | 1204-TKT-proietti | 2011-05-09 18:17 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2011-05-10 |  |  | InProgress | 80%
1204-00-EL-SCH-505 | 01 | PDCS I/O LIST | DE | IFR | EL | PS-OT-T-0734 | 2018-12-22 | 2019-01-22 16:00 | Yes | 17 | 1204-Owner-v | 2018-12-23 11:58 | LIST | 2020-05-13 | 0 | 0 | 2020-05-13 | * |  |  | InProgress | 90%
1204-05-EL-DWG-010 | 00 | LIGHTING LAYOUT AREA-05 | DE | IFR | EL | PS-OT-T-0159 | 2015-12-28 | 2016-07-21 15:13 | Yes | 192 | 1204-Owner-v | 2015-12-30 13:57 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | 2016-01-16 | 2016-01-19 | MT-PS-9301-CS-078-1 | InProgress | 80%
1204-90-EL-DWG-121 | 01 | CONTROL ROOM & LABORATORY BUILDING LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:03 | CDW | 2012-10-19 | 0 | 0 | 0 | 2012-10-19 |  |  | complete | 100%
1204-00-EL-MSS-509 | 02 | MATERIAL STANDARD SPECIFICATION FOR ELECTRICAL CABLES AND WIRES | DE | IFE | EL | PS-OT-T-0864 | 2020-01-04 |  | No | 121 | 1204-Owner-v | 2020-01-04 16:03 | SPEC | 2020-01-04 | 0 | 0 | 0 | 2020-01-04 | 2020-01-18 | MT-PS-9609-CS-0255-2 | complete | 100%
1204-00-PI-MSS-401 | 01 | PIPING MATERIAL STANDARD SPECIFICATION | DE | IFE | PI | PS-OT-T-0258 | 2016-05-10 |  | No | 1455 | 1204-Owner-v | 2016-05-14 11:43 | SPEC | 2016-05-10 | 0 | 0 | 0 | 2016-05-10 |  |  | complete | 100%
1204-00-EL-DSH-5031 | 01 | DATA SHEET FOR LV SWITCHGEAR (MS-SWB3A,B-01) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:22 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:05 | DSH | 2020-05-12 | 0 | 0 | 2020-05-12 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-07-EL-DWG-020 | 00 | EARTHING LAYOUT - AREA 07 | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 10:59 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:04 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2015-11-12 | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-90-EL-DWG-130 | 02 | CONTROL ROOM & LABORATORY BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0439 | 2015-02-11 | 2015-03-02 17:54 | Yes | 5 | 1204-TKT-COLANGELI | 2015-02-10 18:56 | CDW | 2015-02-11 | 0 | 0 | 0 | 2015-02-11 |  |  | complete | 100%
1204-90-EL-DWG-710 | 01 | WORK SHOP BUILDING LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:25 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-030 | 00 | MAIN NORMAL DISTRIBUTION PANEL SINGLE LINE DIAGRAM, MS-DP-01 | DE | IFR | EL | PS-OT-T-0231 | 2013-04-06 | 2016-07-21 14:45 | Yes | 1188 | 1204-Owner-v | 2016-04-07 10:37 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-131 | InProgress | 80%
1204-00-HS-DSH-004 | 00 | DATA SHEET FOR HOSE BOX | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:13 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-00-IN-MSS-622 | 01 | MATERIAL STANDARD SPECIFICATION FOR PRESSURE GAUGES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:07 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-648 | 01 | MATERIAL STANDARD SPECIFICATION FOR ULTRASONIC LEVEL TRANSMITTERS | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:09 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-22-PR-UFD-221 | 00 | Utility Flow Diagram Of Machinery Cooling Water System | BE | IFR | PR | TM-OT-9001-T-0009 | 2011-05-11 |  | No | 3281 | 1204-TKT-proietti | 2011-05-09 17:22 | EDW | 2020-06-01 | 0 | 0 | 2020-06-30 | 2011-05-11 |  |  | InProgress | 80%
1204-00-ST-SDG-760 | 01 | STANDARD DRAWING FOR BUILDINGS | DE | IFC | ST | TM-OT-9001-T-0425 | 2015-01-09 |  | No | 1942 | 1204-TKT-COLANGELI | 2015-01-07 12:41 | SPEC | 2015-01-09 | 0 | 0 | 0 | 2015-01-09 |  |  | complete | 100%
1204-62-PR-DSH-102 | 01 | DATA SHEET FOR PLANT / INSTRUMENT AIR RECEIVER (D-6201) | BE | IFE | PR | PS-OT-T-0179 | 2016-01-11 |  | No | 1575 | 1204-Owner-v | 2016-01-12 09:38 | DSH | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 | 2016-01-26 | MT-PS-9301-CS-093-1 | complete | 100%
1204-64-PR-DSH-108 | 00 | Data Sheet For Sulfuric Acid Unloading Pump (P-6405) | BE | IFR | PR | TM-OT-9001-T-0011 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:49 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-01 |  |  | InProgress | 80%
1204-00-HS-ESS-153 | 01 | ENGINEERING STANDARD SPECIFICATION FOR CO2/CLEAN AGENT FIRE EXTINGUISHING SYSTEM | DE | IFE | HSE | TM-OT-9001-T-0396 | 2014-10-02 |  | No | 2041 | 1204-TKT-COLANGELI | 2014-10-01 10:43 | SPEC | 2014-10-02 | 0 | 0 | 0 | 2014-10-02 | 2014-11-08 | MT-TM-9301-CS-001 | complete | 100%
1204-00-EL-SDG-624 | 01 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - COMMUNICATION | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 14:57 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:41 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | * | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-00-HS-DSH-024 | 00 | DATA SHEET FOR ALARM LIGHTING | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:22 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-83-HS-DSH-001 | 01 | DATA SHEET FOR FLARE STACK | DE | IFR | HSE | PS-OT-T-0323 | 2016-08-21 |  | No | 1352 | 1204-Owner-v | 2016-08-23 15:25 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-00-EL-MSS-510 | 01 | MATERIAL STANDARD SPECIFICATION FOR CATHODIC PROTECTION | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:07 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-PI-SDG-402 | 03 | STANDARD DRAWING FOR ABOVE GROUND PIPING | DE | IFE | PI | PS-OT-T-0937 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 16:13 | SPEC | 2020-03-14 | 0 | 0 | 0 | 2020-03-14 | 2020-03-17 | MT-PS-9609-CS-0314 | complete | 100%
1204-00-PV-ESS-243 | 01 | ENGINEERING STANDARD SPECIFICATION FOR TOWERS | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-04-10 11:11 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-00-ST-SDG-763 | 01 | STANDARD DRAWING FOR ALLOWABLE TOLERANCES FOR STEEL STRUCTURE | DE | IFC | ST | PS-OT-T-0043 | 2015-05-17 |  | No | 1814 | 1204-Owner-v | 2015-05-18 09:31 | SPEC | 2015-05-17 | 0 | 0 | 0 | 2015-05-17 |  |  | complete | 100%
1204-71-PR-DSH-101 | 01 | DATA SHEET FOR DAILY METHANOL STORAGE TANKS (TK-7101 A/B) | BE | IFE | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-Owner-v | 2015-09-16 18:06 | DSH | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-22-PR-LST-001 | 01 | EQUIPMENT LIST FOR MACHINERY COOLING WATER SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 12:00 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-62-PR-LST-001 | 01 | EQUIPMENT LIST FOR INSTRUMENT AIR / PLANT AIR SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 12:00 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-00-EL-DIG-003 | 01 | PAGING AND INTERCOM SYSTEM RISER DIAGRAM | DE | IFR | EL | PS-OT-T-0907 | 2020-02-23 |  | No | 71 | 1204-Owner-v | 2020-02-25 16:42 | CDW | 2020-04-20 | 0 | 0 | 2020-04-20 | * | 2020-02-29 | MT-PS-9609-CS-0285 | InProgress | 80%
1204-00-EL-DWG-004 | 02 | OVERALL MAIN UNDERGROUND CABLE ROUTING LAYOUT | DE | IFR | EL | PS-OT-T-0113 | 2015-10-10 | 2016-07-24 10:44 | Yes | 274 | 1204-Owner-v | 2015-10-10 13:06 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2015-10-13 | 2015-11-02 | MT-PS-9301-CS-039 | InProgress | 80%
1204-00-EL-REQ-506 | 00 | REQUISITION FOR AC UPS | DE | IFI | EL | PS-OT-T-482 | 2017-09-11 |  | No | 966 | 1204-Owner-v | 2017-09-13 09:56 | REQ | 2017-09-11 | 0 | 0 | 0 | 2017-09-11 | 2018-06-10 | MT-PS-9301-CS-251-R | InProgress | 90%
1204-00-EL-SLD-003 | 01 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR - MS-SWB3A,B-01 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:55 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:39 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2018-01-20 | 2018-05-31 | MT-PS-9609-CS-008-R | InProgress | 80%
1204-62-PR-DSH-132 | 00 | Process Instrument Data Sheet for On / Off Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | * | 2016-01-24 | MT-PS-9301-CS-093 | InProgress | 80%
1204-62-PR-DSH-134 | 00 | Process Instrument Data Sheet for Level Gauges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-07-24 |  |  | InProgress | 80%
1204-00-ST-DWG-012 | 03 | PIPE RACK ZONE 1 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0110 | 2015-10-07 |  | No | 1671 | 1204-Owner-v | 2015-10-08 11:43 | CDW | 2015-10-20 | 0 | 0 | 0 | 2015-10-20 | 2015-10-20 | MT-PS-9301-CS-027 | complete | 100%
1204-00-ST-DWG-073 | 03 | PIPE RACK ZONE 11 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0411 | 2017-01-21 |  | No | 1199 | 1204-Owner-v | 2017-01-22 13:12 | CDW | 2017-01-23 | 0 | 0 | 0 | 2017-01-23 |  | Closed | complete | 100%
1204-90-ST-DWG-1031 | 02 | WAREHOUSE / FDN.. (R.C. DETAILS I) | DE | IFC | ST | PS-TM-T-0252 | 2017-09-13 |  | No | 964 | 1204-TKT-COLANGELI | 2013-09-26 14:03 | CDW | 2017-09-13 | 0 | 0 | 0 | 2017-09-13 |  |  | complete | 100%
1204-90-ST-DWG-930 | 03 | SUBSTATION / FDN. (G.A. & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-20 15:54 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-90-EL-SLD-053 | 01 | WAREHOUSE EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:53 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-IN-DSH-608 | 00 | DATA SHEET FOR ANNUBAR FLOW ELEMENTS | DE | IFR | IN | PS-OT-T-0392 | 2016-12-27 |  | No | 1224 | 1204-Owner-v | 2017-01-11 12:15 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2017-01-31 | MT-PS-9301-CS-206-R | InProgress | 80%
1204-00-IN-DSH-611 | 01 | DATA SHEET FOR MASS FLOW METERS | DE | IFR | IN | PS-OT-T-0524 | 2018-01-01 |  | No | 854 | 1204-Owner-v | 2018-01-02 11:01 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2018-01-06 | 2018-01-13 | MT-PS-9609-CS-001-1 | InProgress | 80%
1204-00-IN-REQ-603 | 01 | REQUISITION FOR PROCESS STREAM ANALYZERS | DE | IFP | IN | PS-OT-T-0949 | 2020-04-13 |  | No | 21 | 1204-Owner-v | 2020-04-14 15:04 | REQ | 2020-04-13 | 0 | 0 | 0 | 2020-04-13 | 2020-04-20 | MT-PS-9609-CS-0330 | complete | 100%
1204-00-IN-REQ-623 | 00 | REQUISITION FOR PRESSURE SWITCHES | DE | IFI | IN | PS-OT-T-0970 | 2020-05-13 |  | No | -9 | 1204-Owner-v | 2020-05-16 08:50 | REQ | 2020-04-24 | 0 | 0 | 2020-05-07 |  |  |  | complete | 100%
1204-00-PI-PPL-001 | 06 | OVERALL PLOT PLAN | DE | IFR | PI | PS-OT-T-0684 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-09-27 14:14 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-00-EL-REQ-505 | 02 | REQUISITION FOR POWER DISTRIBUTION CONTROL SYSTEM (PDCS) | DE | IFI | EL | PS-OT-T-0844 | 2019-12-17 |  | No | 139 | 1204-Owner-v | 2019-12-28 14:33 | REQ | 2020-10-08 | 0 | 0 | 2020-10-21 | 2019-12-26 |  | MT-PS-9609-CS-0451 | InProgress | 90%
1204-83-HS-DSH-002 | 01 | DATA SHEET FOR K.O. DRUM | DE | IFR | HSE | PS-OT-T-0567 | 2018-02-25 |  | No | 799 | 1204-Owner-v | 2018-02-26 15:03 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * | 2018-03-10 | MT-PS-9609-CS-045 | InProgress | 80%
1204-00-IN-REQ-648 | 00 | REQUISITION FOR ULTRASONIC LEVEL TRANSMITTERS | DE | IFI | IN | PS-OT-T-0547 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 10:53 | REQ | 2020-04-14 | 0 | 0 | 2020-04-27 | 2018-02-05 | 2018-02-15 | MT-PS-9609-CS-028 | InProgress | 90%
1204-00-PV-TBA-204A | 00 | TECHNICAL BID ANALYSIS FOR PRESSURE VESSELS GROUP I | DE | IFE | MD | TM-OT-9001-T-0195 | 2012-10-24 |  | No | 2749 | 1204-Owner-v | 2015-06-06 12:03 | TBA | 2012-10-24 | 0 | 0 | 0 | 2012-10-24 |  |  | complete | 100%
1204-00-PI-MTO-460A | 01 | MATERIAL TAKE OFF FOR COATING AND WRAPPING (MTO I) | DE | IFE | PI | PS-OT-T-0227 | 2016-04-03 |  | No | 1492 | 1204-Owner-v | 2016-04-04 09:43 | LIST | 2016-04-05 | 0 | 0 | 0 | 2016-04-05 | 2016-05-14 | MT-PS-9301-CS-147 | complete | 100%
1204-00-PR-LST-004 | 00 | OVERAL UTILITY SUMMARY FOR UTILITY UNIT | DE | IFR | PR | TM-OT-9001-T-0201 | 2012-11-08 |  | No | 2734 | 1204-Owner-v | 2015-03-17 10:55 | LIST | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-00-PR-PID-002 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR PIPING SYMBOLS I | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-12-10 11:41 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-00-PR-PID-006 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR GENERAL NOTES | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:30 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-63-PR-DSH-134 | 00 | Process Instrument Data Sheet for Analyzers | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-64-PR-LST-002 | 00 | LINE LIST FOR WATER POLISHING SYSTEM SYSTEM | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:08 | LIST | 2020-03-30 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-00-PI-MTO-403A | 03 | MATERIAL TAKE OFF FOR GASKETS ABOVE GROUND (MTO I) | DE | IFE | PI | PS-OT-T-0471 | 2017-08-27 |  | No | 981 | 1204-Owner-v | 2017-08-30 15:05 | LIST | 2017-08-30 | 0 | 0 | 0 | 2017-08-30 |  |  | complete | 100%
1204-00-PI-MTO-405A | 01 | MATERIAL TAKE OFF FOR BOLTS & NUTS ABOVE GROUND (MTO I) | DE | IFE | PI | PS-OT-T-0402 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-06-10 09:51 | LIST | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-00-PI-MTO-463A | 03 | MATERIAL TAKE OFF FOR U/G GASKETS (MTO I) | DE | IFE | PI | PS-OT-T-0348 | 2016-10-08 |  | No | 1304 | 1204-Owner-v | 2016-10-09 11:00 | LIST | 2016-10-19 | 0 | 0 | 0 | 2016-10-19 |  |  | complete | 100%
1204-00-PI-MTO-465A | 00 | MATERIAL TAKE OFF FOR U/G BOLTS & NUTS (MTO I) | DE | IFE | PI | PS-OT-T-0356 | 2016-11-01 |  | No | 1280 | 1204-Owner-v | 2016-11-02 14:11 | LIST | 2016-11-03 | 0 | 0 | 0 | 2016-11-03 |  |  | complete | 100%
1204-00-PR-PID-001 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR EQUIPMENT SYMBOLS | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-12-10 11:41 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-40-PR-PID-402 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- BFW PUMPS TURBINE | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:09 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-40-PR-PID-403 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- BFW CHEMICALS DOSING PACKAGES | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:03 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-71-PR-PID-711 | 03 | PIPING & INSTRUMENTATION DIAGRAM FOR DAILY METHANOL STORAGE TANK A | BE/DE | IFC-WH | PR | PS-OT-T-0652 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-29 11:13 | EDW | 2020-05-01 | 0 | 0 | 2020-06-30 | 2018-08-02 | 2018-08-13 | MT-PS-9609-CS-109 | complete | 100%
1204-00-ST-DWG-017 | 02 | PIPE RACK ZONE 2 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0402 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-29 16:04 | CDW | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 | 2014-11-11 | MT-TM-9301-CS-006 | complete | 100%
1204-00-ST-DWG-066 | 03 | PIPE RACK ZONE 10 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-328 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:06 | CDW | 2016-09-03 | 0 | 0 | 0 | 2016-09-03 |  |  | complete | 100%
1204-10-ST-DWG-154 | 01 | REFORMER (HORIZONTAL CONVECTION SECTION) / FDN. (G.A.) | DE | IFC | ST | PS-OT-T-0672 | 2018-08-28 |  | No | 615 | 1204-Owner-v | 2018-09-01 09:43 | CDW | 2018-08-28 | 0 | 0 | 0 | 2018-08-28 |  |  | complete | 100%
1204-90-EL-SLD-041 | 01 | RESTAURANT EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:45 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-050 | 01 | GUARD HOUSE NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:36 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:51 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-006 | 00 | DATA SHEET FOR SPRAY NOZZLE | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:15 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-84-HS-DSH-005 | 01 | DATA SHEET FOR SANITARY WATER COLLECTION BASIN (SU-8402) | DE | IFR | HSE | PS-OT-T-0854 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:52 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * | 2020-02-12 | MT-PS-9301-CS-0269-1 | InProgress | 80%
1204-00-IN-DSH-606 | 01 | DATA SHEET FOR PRESSURE SAFETY/RELIEF VALVES | DE | IFR | IN | PS-OT-T-0137 | 2015-11-21 |  | No | 1626 | 1204-Owner-v | 2015-11-29 08:45 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2016-08-10 | 2016-08-13 | MT-PS-9301-CS-075-1 | InProgress | 80%
1204-00-PI-ISO-1300 | 00 | A/G ISOMETRIC DRAWING OF AREA-13 | DE | IFR | PI | PS-OT-T-0283 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:55 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-00-PI-KPL-007 | 02 | UNDER GROUND PIPING PLAN KEY PLAN | DE | IFR | PI | PS-OT-T-0046 | 2015-05-20 |  | No | 1811 | 1204-Owner-v | 2015-05-20 23:33 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-00-PI-MTO-411A | 00 | MATERIAL TAKE OFF FOR HOSE & HOSE COUPLING (MTO I) | DE | IFE | PI | PS-OT-T-0964 | 2020-05-05 |  | No | -1 | 1204-Owner-v | 2020-05-07 13:18 | LIST | 2020-06-15 | 0 | 0 | 2020-07-01 |  |  |  | complete | 100%
1204-00-PI-TBA-404A | 02 | TECHNICAL BID ANALYSIS FOR A/G VALVES(MTO I) | DE | IFE | PI | PS-OT-T-0522 | 2017-12-20 |  | No | 866 | 1204-Owner-v | 2017-12-30 12:01 | TBA | 2018-01-01 | 0 | 0 | 0 | 2018-01-01 | 2018-01-08 | MT-PS-9609-CS-005 | complete | 100%
1204-10-PR-PID-101 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- NATURAL GAS SUPPLY | DE | IFC-WH | PR | PS-OT-T-0749 | 2019-01-23 |  | No | 467 | 1204-Owner-v | 2019-01-27 13:49 | EDW | 2021-04-01 | 0 | 0 | 2021-04-01 | 2019-01-30 | 2020-04-20 | MT-PS-9609-CS-0331 | InProgress | 90%
1204-10-PR-PID-105 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- FEED GAS SATURATION | DE | IFC-WH | PR | PS-OT-T-0749 | 2019-01-23 |  | No | 467 | 1204-Owner-v | 2019-01-27 13:56 | EDW | 2021-04-01 | 0 | 0 | 2021-04-01 | 2019-01-30 | 2020-04-20 | MT-PS-9609-CS-0331 | InProgress | 90%
1204-90-EL-DWG-610 | 01 | FIRE STATION LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:33 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 12:20 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-076 | 00 | STREET LIGHTING PANEL ONE LINE DIAGRAM | DE | IFR | EL | TM-OT-9001-T-0189 | 2012-10-19 |  | No | 2754 | 1204-Owner-v | 2015-09-16 18:15 | CDW | 2020-05-30 | 0 | 0 | 2020-05-30 | 2012-10-19 |  |  | InProgress | 80%
1204-00-HS-DSH-027 | 00 | DATA SHEET FOR MANUAL RELEASE SWITCHES | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:25 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-84-HS-LST-003 | 00 | ALARM AND TRIP SET POINTS FOR EFFLUENT WATER TREATMENT SYSTEM | DE | IFR | HSE | PS-OT-T-0686 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:18 | LIST | 2019-10-01 | 2019-11-22 | 0 | 2020-07-15 | * |  |  | InProgress | 90%
1204-00-RE-TBA-301 | 03 | TECHNICAL BID ANALYSIS FOR CENTRIFUGAL COMPRESSORS | DE | IFE | MC | PS-OT-T-0831 | 2019-10-28 |  | No | 189 | 1204-Owner-v | 2019-10-28 11:13 | TBA | 2019-10-28 | 0 | 0 | 0 | 0 |  |  | complete | 100%
1204-00-PI-ISO-6000 | 01 | U/G ISOMETRIC DRAWING OF AREA-60 | DE | IFC-WH | PI | PS-OT-T-0628 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-18 14:09 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-06-24 | MT-PS-9609-CS-087 | InProgress | 90%
1204-00-EL-SCH-5034 | 00 | LV SWITCHGEAR SCHEDULE (MS-SWB3A,B-04) | DE | IFR | EL | TM-OT-9001-T-0319 | 2013-09-25 |  | No | 2413 | 1204-TKT-COLANGELI | 2013-09-23 11:31 | LIST | 2020-05-12 | 0 | 0 | 2020-05-12 | 2013-09-24 |  |  | InProgress | 90%
1204-06-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 06 | DE | IFR | EL | PS-OT-T-0204 | 2016-02-28 | 2016-07-23 10:11 | Yes | 132 | 1204-Owner-v | 2016-03-02 15:19 | CDW | 2020-08-20 | 0 | 0 | 2020-08-20 | * | 2016-04-05 | MT-PS-9301-CS-119-1 | InProgress | 80%
1204-90-EL-DWG-921 | 01 | WAREHOUSE BUILDING LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:32 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-022 | 00 | DATA SHEET FOR ALARM SOUNDER | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:19 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-90-HS-DWG-002 | 02 | SAFETY EQUIPMENT LAYOUT FOR SUBSTATION | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:56 | EDW | 2016-12-16 | 0 | 0 | 0 | 2016-12-16 |  |  | complete | 100%
1204-00-IN-DIG-001 | 00 | FCS LOGIC DIAGRAM | DE | IFR | IN | TM-OT-9001-T-0313 | 2015-08-08 |  | No | 1731 | 1204-TKT-COLANGELI | 2013-08-08 11:35 | EDW | 2020-05-27 | 0 | 0 | 2020-05-27 | 2013-08-08 |  |  | InProgress | 80%
1204-00-IN-DSH-619 | 01 | DATA SHEET FOR LEVEL SWITCHES | DE | IFR | IN | PS-OT-T-0546 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 08:44 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2018-02-15 | 2018-08-04 | MT-PS-9609-CS-027-R | InProgress | 80%
1204-00-IN-MTO-002 | 00 | MATERIAL TAKE OFF FOR INSTRUMENT JUNCTION BOX | DE | IFE | IN | PS-OT-T-0880 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:11 | LIST | 2019-12-25 | 0 | 0 | 2020-04-28 | * | 2020-04-16 | MT-PS-9609-CS-0271-R | complete | 100%
1204-00-IN-MTO-004 | 00 | MATERIAL TAKE OFF FOR INSTRUMENT CABLE TRAYS / LADDERS AND ACCESSORIES | DE | IFE | IN | PS-OT-T-0919 | 2020-02-26 |  | No | 68 | 1204-Owner-v | 2020-02-27 12:16 | LIST | 2019-12-25 | 0 | 0 | 2020-04-28 | * | 2020-03-03 | MT-PS-9609-CS-0295 | complete | 100%
1204-90-EL-SLD-078 | 00 | PHOTOCELL RELAY BOX WIRING DIAGRAM | DE | IFR | EL | TM-OT-9001-T-0194 | 2012-10-22 |  | No | 2751 | 1204-Owner-v | 2015-09-16 18:15 | CDW | 2020-05-30 | 0 | 0 | 2020-05-30 | 2012-10-22 |  |  | InProgress | 80%
1204-00-IN-DIG-003 | 00 | JUNCTION BOX TERMINAL ARRANGEMENT DIAGRAM | DE | IFR | IN | PS-OT-T-0885 | 2020-02-08 |  | No | 86 | 1204-Owner-v | 2020-02-09 09:19 | EDW | 2020-11-10 | 0 | 0 | 2020-11-10 | * | 2020-04-16 | MT-PS-9609-CS-0273-R | InProgress | 80%
1204-00-IN-DSH-623 | 01 | DATA SHEET FOR PRESSURE SWITCHES | DE | IFR | IN | PS-OT-T-0957 | 2020-04-28 |  | No | 6 | 1204-Owner-v | 2020-04-29 14:25 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 |  |  |  | InProgress | 80%
1204-00-IN-TBA-630 | 00 | TECHNICAL BID ANALYSIS FOR INSTRUMENT CABLE LADDERS / TRAYS & ACCESSORIES | DE | IFE | IN | PS-OT-T-0969 | 2020-05-13 |  | No | -9 | 1204-Owner-v | 2020-05-16 08:47 | TBA | 2020-07-21 | 0 | 0 | 2020-07-27 |  |  |  | complete | 100%
1204-00-PI-KPL-006 | 04 | PIPING PLAN KEY PLAN | DE | IFR | PI | PS-OT-T-0368 | 2016-11-15 |  | No | 1266 | 1204-Owner-v | 2016-11-19 16:43 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2016-11-20 |  |  | InProgress | 80%
1204-64-PR-PID-642 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR WATER POLISHING SYSTEM (2 OF 3) | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:28 | EDW | 2017-02-23 | 0 | 0 | 0 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | complete | 100%
1204-00-ST-DWG-041 | 01 | PIPE RACK ZONE 6 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0049 | 2015-05-25 |  | No | 1806 | 1204-Owner-v | 2015-05-26 11:07 | CDW | 2015-05-25 | 0 | 0 | 0 | 2015-05-25 |  |  | complete | 100%
1204-00-ST-DWG-047 | 02 | PIPE RACK ZONE 7 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0049 | 2015-05-25 |  | No | 1806 | 1204-Owner-v | 2015-05-26 11:07 | CDW | 2015-05-25 | 0 | 0 | 0 | 2015-05-25 |  |  | complete | 100%
1204-00-HS-DSH-005 | 00 | DATA SHEET FOR HOSE REEL | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:14 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-00-HS-DSH-012 | 00 | DATA SHEET FOR WHEELED DRY POWDER EXTINGUISHER | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:16 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-00-HS-DSH-023 | 00 | DATA SHEET FOR ALARM SOUNDERS AND FLASHERS | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:20 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-IN-DSH-622 | 01 | DATA SHEET FOR PRESSURE GAUGES | DE | IFR | IN | PS-OT-T-0549 | 2018-02-06 |  | No | 818 | 1204-Owner-v | 2018-02-07 12:07 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2018-02-12 | 2018-02-17 | MT-PS-9609-CS-030 | InProgress | 80%
1204-00-IN-DSH-624 | 02 | DATA SHEET FOR ELECTRONIC TRANSMITTERS | DE | IFR | IN | PS-OT-T-0932 | 2020-03-11 |  | No | 54 | 1204-Owner-v | 2020-03-17 12:05 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-04-05 | MT-PS-9609-CS-0326 | InProgress | 80%
1204-00-IN-TBA-604 | 02 | TECHNICAL BID ANALYSIS FOR ON / OFF VALVES | DE | IFE | IN | PS-OT-T-0744 | 2019-01-06 |  | No | 484 | 1204-Owner-v | 2019-01-08 09:14 | TBA | 2019-01-08 | 0 | 0 | 0 | 2019-01-08 |  |  | complete | 100%
1204-00-PV-TBA-204C | 01 | TECHNICAL BID ANALYSIS FOR PRESSURE VESSEL (GROUP III) | DE | IFE | MD | PS-OT-T-0228 | 2016-04-06 |  | No | 1489 | 1204-Owner-v | 2016-04-09 10:43 | TBA | 2016-04-06 | 0 | 0 | 0 | 2016-04-06 | 2016-04-18 | MT-PS-9301-CS-128 | complete | 100%
1204-00-PI-ISO-1200 | 00 | A/G ISOMETRIC DRAWING OF AREA-12 | DE | IFR | PI | PS-OT-T-0175 | 2016-01-06 |  | No | 1580 | 1204-Owner-v | 2016-01-07 12:49 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2016-01-16 | 2016-05-07 | MT-PS-9301-CS-144 | InProgress | 80%
1204-00-PI-ISO-6400 | 01 | U/G ISOMETRIC DRAWING OF AREA-64 | DE | IFC-WH | PI | PS-OT-T-0629 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-19 08:59 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-06-24 | MT-PS-9609-CS-088 | InProgress | 90%
1204-90-EL-SLD-042 | 01 | CLINIC NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:46 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-049 | 01 | WORK SHOP EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:51 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-HS-DWG-001 | 02 | SAFETY EQUIPMENT LAYOUT FOR CONTROL ROOM | DE | IFC | HSE | PS-OT-T-0026 | 2015-04-20 |  | No | 1841 | 1204-Owner-v | 2015-04-22 10:16 | EDW | 2015-04-20 | 0 | 0 | 0 | 2015-04-20 |  |  | complete | 100%
1204-00-HV-MSS-781 | 01 | MATERIAL STANDARD SPECIFICATION FOR HVAC EQUIPMENT | DE | IFE | HV | TM-OT-9001-T-0422 | 2014-12-11 |  | No | 1971 | 1204-TKT-COLANGELI | 2014-12-10 15:04 | SPEC | 2014-12-11 | 0 | 0 | 0 | 2014-12-11 |  |  | complete | 100%
1204-00-HV-REQ-790 | 02 | REQUISITION FOR HVAC EQUIPMENT | DE | IFI | HV | PS-OT-T-0565 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-24 09:18 | REQ | 2018-03-01 | 0 | 0 | 0 | 2018-03-01 | 2018-03-05 | MT-PS-9609-CS-040 | complete | 100%
1204-00-IN-DSH-620 | 00 | DATA SHEET FOR LEVEL GAUGES | DE | IFR | IN | TM-OT-9001-T-0277 | 2013-05-16 |  | No | 2545 | 1204-TKT-COLANGELI | 2013-05-16 12:20 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2013-05-16 |  |  | InProgress | 80%
1204-00-RE-REQ-301 | 04 | REQUISITION FOR CENTRIFUGAL COMPRESSORS | DE | IFP | MC | PS-OT-T-0492 | 2017-09-18 |  | No | 959 | 1204-Owner-v | 2017-09-19 15:39 | REQ | 2017-10-09 | 0 | 0 | 0 | 2017-10-09 |  |  | complete | 100%
1204-00-HM-REQ-257B | 01 | REQUISITION FOR SHELL & TUBE HEAT EXCHANGERS (GROUP II) | DE | IFP | MD | PS-OT-T-0570 | 2018-02-27 |  | No | 797 | 1204-Owner-v | 2018-04-15 15:31 | REQ | 2018-02-27 | 0 | 0 | 0 | 2018-02-27 |  |  | complete | 100%
1204-00-IN-REQ-606 | 00 | REQUISITION FOR PRESSURE SAFETY/RELIEF VALVES | DE | IFI | IN | PS-OT-T-0136 | 2015-11-21 |  | No | 1626 | 1204-Owner-v | 2015-11-21 13:15 | REQ | 2015-12-01 | 0 | 0 | 0 | 2015-12-01 | 2015-12-14 | MT-PS-9301-CS-055 | InProgress | 90%
1204-00-IN-REQ-619 | 00 | REQUISITION FOR LEVEL SWITCHES | DE | IFI | IN | PS-OT-T-0547 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 08:52 | REQ | 2020-04-28 | 0 | 0 | 2020-05-11 | 2018-02-05 | 2018-02-15 | MT-PS-9609-CS-028 | InProgress | 90%
1204-00-PI-ISO-1400 | 00 | A/G ISOMETRIC DRAWING OF AREA-14 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-06 |  |  | InProgress | 80%
1204-00-PI-MTO-402A | 03 | MATERIAL TAKE OFF FOR FLANGES ABOVE GROUND (MTO I) | DE | IFE | PI | PS-OT-T-0469 | 2017-08-26 |  | No | 982 | 1204-Owner-v | 2017-09-24 09:13 | LIST | 2017-08-30 | 0 | 0 | 0 | 2017-08-30 | 2017-10-23 | MT-PS-9301-CS-259 | complete | 100%
1204-00-PI-PPL-005 | 01 | PLOT PLAN UTILITY/TANKAGE | DE | IFR | PI | PS-OT-T-0433 | 2017-04-04 |  | No | 1126 | 1204-Owner-v | 2017-04-08 08:29 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-10-PR-PID-104 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- NATURAL GAS FEED PREHEATING | DE | IFC-WH | PR | PS-OT-T-0749 | 2019-01-23 |  | No | 467 | 1204-Owner-v | 2019-01-27 13:56 | EDW | 2021-04-01 | 0 | 0 | 2021-04-01 | 2019-01-30 | 2020-04-20 | MT-PS-9609-CS-0331 | InProgress | 90%
1204-10-PR-PID-116 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- PROCESS CONDENSATE PUMPS | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:13 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-00-HS-DWG-002 | 01 | SAFETY EQUIPMENT LAYOUT FOR PROCESS UNIT | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:58 | EDW | 2021-06-01 | 0 | 0 | 2021-06-01 | * |  |  | complete | 100%
1204-00-HV-TBA-792 | 00 | TECHNICAL BID ANALYSIS FOR DUCT ACCESSORIES | DE | IFE | HV | PS-OT-T-0388 | 2016-12-21 |  | No | 1230 | 1204-Owner-v | 2016-12-24 08:37 | TBA | 2016-12-21 | 0 | 0 | 0 | 2016-12-21 |  |  | complete | 100%
1204-00-IN-DSH-607 | 01 | DATA SHEET FOR RUPTURE DISCS | DE | IFR | IN | PS-OT-T-0926 | 2020-03-07 |  | No | 58 | 1204-Owner-v | 2020-03-09 09:06 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-03-26 | MT-PS-9609-CS-0322 | InProgress | 80%
1204-00-HM-TBA-257B | 00 | TECHNICAL BID ANALYSIS FOR SHELL & TUBE HEAT EXCHANGERS (GROUP II) | DE | IFE | MD | PS-OT-T-0202 | 2016-02-17 |  | No | 1538 | 1204-Owner-v | 2016-02-21 15:16 | TBA | 2016-02-17 | 0 | 0 | 0 | 2016-02-17 |  |  | complete | 100%
1204-00-PV-TBA-214A | 00 | TECHNICAL BID ANALYSIS FOR TANK ACCESSORIES | DE | IFE | MD | PS-OT-T-0156 | 2013-12-21 |  | No | 2326 | 1204-Owner-v | 2015-12-22 15:44 | TBA | 2015-12-23 | 0 | 0 | 0 | 2015-12-23 | 2016-01-04 | MT-PS-9301-CS-071 | complete | 100%
1204-00-PI-APL-1400 | 00 | PIPING PLAN AREA-14 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:10 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-06 |  |  | InProgress | 80%
1204-00-PR-PID-011 | 01 | PIPING & INSTRUMENTATION DIAGRAM INDEX | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:27 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-00-ST-DWG-083 | 01 | PIPE RACK ZONE 8 / STEEL PARTS | DE | IFC | ST | PS-OT-T-0541 | 2018-01-10 |  | No | 845 | 1204-Owner-v | 2018-01-21 12:08 | CDW | 2018-01-10 | 0 | 0 | 0 | 2018-01-10 | 2018-01-21 | MT-PS-9609-CS-011 | complete | 100%
1204-00-EL-SDG-622 | 01 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - EARTHING | DE | IFR | EL | PS-OT-T-0118 | 2015-10-12 | 2015-11-28 09:19 | Yes | 33 | 1204-Owner-v | 2015-10-13 17:16 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | * | 2015-11-19 | MT-PS-9301-CS-044 | InProgress | 80%
1204-00-EL-SLD-022 | 01 | TYPICAL SINGLE LINE DIAGRAM FOR BATTERY CHARGER | DE | IFR | EL | PS-OT-T-0491 | 2017-09-18 | 2017-10-18 11:40 | Yes | 16 | 1204-Owner-v | 2017-09-21 08:10 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2017-10-09 | MT-PS-9301-CS-254 | InProgress | 80%
1204-05-EL-DWG-020 | 01 | EARTHING LAYOUT - AREA 05 | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 10:47 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:04 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | * | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-90-EL-DWG-621 | 01 | FIRE STATION LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:22 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-REQ-152 | 00 | REQUISITION FOR FIRE EXTINGUISHERS | DE | IFI | HSE | PS-OT-T-0082 | 2015-08-01 |  | No | 1738 | 1204-Owner-v | 2015-08-03 09:23 | REQ | 2020-07-31 | 0 | 0 | 2020-08-13 | 2015-08-02 | 2015-08-24 | MT-PS-9301-CS-008 | InProgress | 90%
1204-00-HS-REQ-154 | 01 | REQUISITION FOR FIRE AND GAS ALARM DEVICES | DE | IFI | HSE | PS-OT-T-0899 | 2020-02-18 |  | No | 76 | 1204-Owner-v | 2020-02-18 16:59 | REQ | 2020-07-07 | 0 | 0 | 2020-07-20 | * | 2020-03-01 | MT-PS-9609-CS-0289 | InProgress | 90%
1204-83-HS-LST-003 | 00 | ALARM AND TRIP SET POINTS FOR FLARE SYSTEM | DE | IFR | HSE | PS-OT-T-0027 | 2015-04-20 |  | No | 1841 | 1204-Owner-v | 2015-04-22 10:24 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | 2015-04-20 |  |  | InProgress | 90%
1204-00-IN-DSH-626 | 00 | DATA SHEET FOR MOTOR OPERATED VALVES | DE | IFR | IN | PS-OT-T-0174 | 2016-01-05 |  | No | 1581 | 1204-Owner-v | 2016-01-06 11:06 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2016-01-06 | 2016-01-18 | MT-PS-9301-CS-089 | InProgress | 80%
1204-00-PI-REQ-407A | 00 | REQUISITION FOR STRAINER(MTO I) | DE | IFI | PI | PS-OT-T-0934 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 15:54 | REQ | 2020-04-16 | 0 | 0 | 2020-04-29 | * | 2020-04-07 | MT-PS-9609-CS-0327 | InProgress | 90%
1204-63-PR-DSH-103 | 02 | DATASHEET FOR COOLING WATER SUPPLY PUMPS (P-6301 A~F) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-64-PR-DSH-106 | 01 | DATA SHEET FOR CONDENSATE TRANSFER PUMPS (P-6401 A/B) | BE | IFE | PR | TM-OT-9001-T-0299 | 2013-07-04 |  | No | 2496 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-00-EL-SLD-002 | 02 | SINGLE LINE DIAGRAM FOR 6KV SWITCHGEAR , MS-SWB2A,B-01 | DE | IFR | EL | PS-OT-T-0555 | 2018-02-13 | 2018-02-25 17:18 | Yes | -2 | 1204-Owner-v | 2018-02-17 10:58 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-034-R | InProgress | 80%
1204-00-IN-TBA-603 | 00 | TECHNICAL BID ANALYSIS FOR PROCESS STREAM ANALYZERS | DE | IFE | IN | PS-OT-T-0716 | 2018-11-11 |  | No | 540 | 1204-Owner-v | 2018-11-16 09:56 | TBA | 2018-11-17 | 0 | 0 | 0 | 2018-11-17 |  |  | complete | 100%
1204-00-HM-TBA-257A | 00 | TECHNICAL BID ANALYSIS FOR SHELL & TUBE HEAT EXCHANGERS (GROUP I) | DE | IFE | MD | TM-OT-9001-T-0419 | 2014-12-10 |  | No | 1972 | 1204-TKT-COLANGELI | 2014-12-09 13:23 | TBA | 2014-12-10 | 0 | 0 | 0 | 2014-12-10 | 2014-12-16 | MT-TM-9301-CS-025 | complete | 100%
1204-00-PI-APL-1100 | 00 | PIPING PLAN AREA-11 | DE | IFR | PI | PS-OT-T-0073 | 2015-07-07 |  | No | 1763 | 1204-Owner-v | 2015-07-11 11:55 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2015-07-07 |  |  | InProgress | 80%
1204-00-PR-PID-003 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR PIPING SYMBOLS II | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-12-10 11:41 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-63-PR-TBA-108 | 01 | TECHNICAL BID ANALYSIS FOR COOLING TOWER | DE | IFE | PR | PS-OT-T-0015 | 2015-04-07 |  | No | 1854 | 1204-Owner-v | 2015-07-22 11:34 | TBA | 2014-11-25 | 0 | 0 | 0 | 2014-11-25 | 2014-11-30 | MT-TM-9301-CS-016 | complete | 100%
1204-90-ST-DWG-1005 | 01 | CONTROL ROOM & LABORATORY / LABORATORY SHELTER & DETS. | DE | IFC | ST | TM-OT-9001-T-0432 | 2015-01-21 |  | No | 1930 | 1204-TKT-COLANGELI | 2015-01-20 13:02 | CDW | 2015-01-21 | 0 | 0 | 0 | 2015-01-21 |  |  | complete | 100%
1204-00-IN-DSH-641 | 00 | DATA SHEET FOR TEMPERATURE GAUGES AND TESTWELLS | DE | IFR | IN | TM-OT-9001-T-0275 | 2013-05-15 |  | No | 2546 | 1204-TKT-COLANGELI | 2013-05-15 11:27 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 |  |  |  | InProgress | 80%
1204-00-IN-REQ-617 | 00 | REQUISITION FOR VENTURI TUBES & FLOW NOZZLES | DE | IFI | IN | PS-OT-T-0251 | 2016-04-23 |  | No | 1472 | 1204-Owner-v | 2016-04-24 09:17 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | * | 2018-05-22 | MT-PS-9609-CS-068-R | InProgress | 90%
1204-00-RE-TBA-302 | 01 | TECHNICAL BID ANALYSIS FOR N2 CIRCULATOR COMPRESSOR | DE | IFE | MC | PS-OT-T-0963 | 2020-05-05 |  | No | -1 | 1204-Owner-v | 2020-05-07 13:20 | TBA | 2020-05-05 | 0 | 0 | 0 |  |  |  | complete | 100%
1204-00-HM-TBA-257C | 00 | TECHNICAL BID ANALYSIS FOR SHELL & TUBE HEAT EXCHANGERS (GROUP III) | DE | IFE | MD | PS-OT-T-0225 | 2016-03-16 |  | No | 1510 | 1204-Owner-v | 2016-04-02 10:42 | TBA | 2016-04-05 | 0 | 0 | 0 | 2016-04-05 |  |  | complete | 100%
1204-00-PV-REQ-201 | 02 | REQUISITION FOR REACTOR | DE | IFP | MD | PS-OT-T-0166 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:50 | REQ | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-17 | MT-PS-9301-CS-088 | complete | 100%
1204-00-PV-TBA-214B | 00 | TECHNICAL BID ANALYSIS FOR TANK SEALING SYSTEM | DE | IFE | MD | PS-OT-T-0288 | 2016-06-15 |  | No | 1419 | 1204-Owner-v | 2016-06-18 11:32 | TBA | 2020-07-01 | 0 | 0 | 2020-07-21 | 2016-06-20 |  |  | complete | 100%
1204-00-PI-ISO-1100 | 00 | A/G ISOMETRIC DRAWING OF AREA-11 | DE | IFR | PI | PS-OT-T-0073 | 2015-07-07 |  | No | 1763 | 1204-Owner-v | 2015-07-11 16:12 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2015-07-07 |  |  | InProgress | 80%
1204-00-PI-MTO-410A | 00 | MATERIAL TAKE OFF FOR C.S ELECTRODE & WELDING ROD (MTO I) | DE | IFE | PI | PS-OT-T-0303 | 2016-07-10 |  | No | 1394 | 1204-Owner-v | 2016-07-12 16:17 | LIST | 2016-07-16 | 0 | 0 | 0 | 2016-07-16 |  |  | complete | 100%
1204-30-PR-PID-306 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-SECOND REFINING OVERHEAD | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 10:14 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-40-PR-PID-409 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- PACKAGE BOILER | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:03 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-20-ST-DWG-205 | 02 | D-2002 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0312 | 2016-07-23 |  | No | 1381 | 1204-Owner-v | 2016-07-23 15:10 | CDW | 2016-07-26 | 0 | 0 | 0 | 2016-07-26 |  |  | complete | 100%
1204-00-IN-TBA-624 | 00 | TECHNICAL BID ANALYSIS FOR ELECTRONIC TRANSMITTERS | DE | IFE | IN | PS-OT-T-0592 | 2018-04-19 |  | No | 746 | 1204-Owner-v | 2018-04-23 09:55 | TBA | 2018-04-29 | 0 | 0 | 0 | 2018-04-29 | 2018-05-05 | MT-PS-9609-CS-062 | complete | 100%
1204-00-PI-APL-1200 | 00 | PIPING PLAN AREA-12 | DE | IFR | PI | PS-OT-T-0175 | 2016-01-06 |  | No | 1580 | 1204-Owner-v | 2016-01-07 12:46 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2016-01-16 | 2016-05-07 | MT-PS-9301-CS-144 | InProgress | 80%
1204-22-PR-DSH-139 | 00 | Process Instrument Data Sheet for Pressure Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-24 |  |  | InProgress | 80%
1204-62-PR-LST-002 | 00 | LINE LIST FOR INSTRUMENT AIR / PLANT AIR SYSTEM | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:34 | LIST | 2020-04-02 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-00-ST-DWG-025 | 02 | PIPE RACK ZONE 3 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0032 | 2015-05-04 |  | No | 1827 | 1204-Owner-v | 2015-05-05 11:37 | CDW | 2015-05-04 | 0 | 0 | 0 | 2015-05-04 |  |  | complete | 100%
1204-00-ST-DWG-074 | 03 | PIPE RACK ZONE 11 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0411 | 2017-01-21 |  | No | 1199 | 1204-Owner-v | 2017-01-22 13:16 | CDW | 2017-01-23 | 0 | 0 | 0 | 2017-01-23 |  | Closed | complete | 100%
1204-00-IN-REQ-634 | 00 | REQUISITION FOR RADAR TYPE LEVEL TRANSMITTERS | DE | IFI | IN | PS-OT-T-0396 | 2017-01-07 |  | No | 1213 | 1204-Owner-v | 2017-01-11 13:50 | REQ | 2020-02-18 | 0 | 0 | 2020-03-02 | 2017-01-31 | 2017-02-15 | MT-PS-9301-CS-207-1 | InProgress | 90%
1204-00-PI-PPL-002 | 00 | PLOT PLAN UNIT 100 | DE | IFR | PI | PS-OT-T-0426 | 2017-03-05 |  | No | 1156 | 1204-Owner-v | 2017-03-07 09:04 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-03-14 | 2017-03-12 | MT-PS-9301-CS-219-R | InProgress | 80%
1204-22-PR-PID-221 | 00 | Piping & Instrumentation Flow Diagram for Machinery Cooling Water System | BE | IFR | PR | TM-OT-9001-T-0049 | 2012-03-28 |  | No | 2959 | 1204-Owner-v | 2015-09-16 17:42 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2012-03-28 |  |  | InProgress | 80%
1204-40-PR-PID-404 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- MP / LP DITRIBUTION | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:04 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-62-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR INSTRUMENT AIR / PLANT AIR SYSTEM | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:14 | LIST | 2020-03-31 | 0 | 0 | 2020-05-06 | 2013-08-06 |  |  | InProgress | 90%
1204-64-PR-PID-641 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR WATER POLISHING SYSTEM (1 OF 3) | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:28 | EDW | 2017-02-23 | 0 | 0 | 0 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | complete | 100%
1204-00-ST-DWG-010 | 01 | PIPE RACK ZONE 1 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0402 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-29 16:02 | CDW | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 | 2014-11-11 | MT-TM-9301-CS-006 | complete | 100%
1204-10-ST-DWG-112 | 01 | STRUCTURE "K" FOR E-1001 / FDN. & STRUCTURE (PLAN & SECTIONS & DETS.) | DE | IFC | ST | PS-OT-T-0354 | 2016-10-26 |  | No | 1286 | 1204-Owner-v | 2016-10-29 10:17 | CDW | 2016-10-26 | 0 | 0 | 0 | 2016-10-26 |  |  | complete | 100%
1204-22-ST-DWG-659 | 01 | D-2201 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0238 | 2016-04-13 |  | No | 1482 | 1204-Owner-v | 2016-04-16 14:27 | CDW | 2016-04-13 | 0 | 0 | 0 | 2016-04-13 | 2016-04-19 | MT-PS-9301-CS-135 | complete | 100%
1204-02-EL-DWG-001 | 01 | POWER LAYOUT - AREA 02 | DE | IFR | EL | PS-OT-T-0114 | 2015-10-10 | 2016-01-14 12:03 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:07 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2015-11-19 | MT-PS-9301-CS-042 | InProgress | 80%
1204-90-EL-DWG-310 | 01 | RESTAURANT BUILDING LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:10 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-00-HS-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR PROCESS AND UTILITY OFFSITE UNITS | DE | IFR | HSE | PS-OT-T-0711 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-06 16:28 | LIST | 2019-10-22 | 0 | 0 | 2020-08-01 | * |  |  | InProgress | 90%
1204-00-HV-CSS-782 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR DUCTS AND ACCESSORIES | DE | IFE | HV | TM-OT-9001-T-0422 | 2014-12-11 |  | No | 1971 | 1204-TKT-COLANGELI | 2014-12-10 15:01 | SPEC | 2014-12-11 | 0 | 0 | 0 | 2014-12-11 |  |  | complete | 100%
1204-00-HV-TBA-791 | 00 | TECHNICAL BID ANALYSIS FOR EXPLOSION PROTECTION VALVES | DE | IFE | HV | TM-OT-9001-T-0378 | 2014-06-11 |  | No | 2154 | 1204-TKT-COLANGELI | 2014-06-11 13:16 | TBA | 2014-06-11 | 0 | 0 | 0 | 2014-06-11 |  |  | complete | 100%
1204-00-IN-REQ-627 | 00 | REQUISITION FOR INSTRUMENT JUNCTION BOXES & CABLE GLANDS | DE | IFI | IN | PS-OT-T-0881 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:09 | REQ | 2020-06-09 | 0 | 0 | 2020-06-15 | * | 2020-02-27 | MT-PS-9609-CS-0272 | InProgress | 90%
1204-00-PV-REQ-214B | 00 | REQUISITION FOR TANK SEALING SYSTEM | DE | IFI | MD | TM-OT-9001-T-0420 | 2014-12-10 |  | No | 1972 | 1204-TKT-COLANGELI | 2014-12-10 14:42 | REQ | 2020-04-15 | 0 | 0 | 2020-04-28 | 2014-12-10 |  |  | InProgress | 90%
1204-00-PI-ISO-7000 | 01 | U/G ISOMETRIC DRAWING OF AREA-70 | DE | IFC-WH | PI | PS-OT-T-0621 | 2018-05-30 |  | No | 705 | 1204-Owner-v | 2018-06-02 10:44 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-06-02 | 2018-06-02 | MT-PS-9609-CS-079 | InProgress | 90%
1204-00-PI-MTO-401A | 03 | MATERIAL TAKE OFF FOR PIPES & FITTINGS ABOVE GROUND (MTO I) | DE | IFE | PI | PS-OT-T-0469 | 2017-08-26 |  | No | 982 | 1204-Owner-v | 2017-08-27 11:42 | LIST | 2017-08-30 | 0 | 0 | 0 | 2017-08-30 | 2017-10-23 | MT-PS-9301-CS-259 | complete | 100%
1204-00-EL-SCH-502 | 02 | 6KV SWITCHGEAR SCHEDULE (MS-SWB2A,B-01) | DE | IFR | EL | PS-OT-T-0555 | 2018-02-13 | 2018-02-25 17:18 | Yes | -2 | 1204-Owner-v | 2018-02-17 11:01 | LIST | 2020-05-11 | 0 | 0 | 2020-05-11 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-034-R | InProgress | 90%
1204-01-EL-DWG-001 | 01 | POWER LAYOUT - AREA 01 | DE | IFR | EL | PS-OT-T-0737 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:00 | CDW | 2020-06-10 | 0 | 0 | 2020-06-10 | * |  |  | InProgress | 80%
1204-90-EL-DWG-821 | 01 | GUARD HOUSE LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:30 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-036 | 01 | CONTROL ROOM NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:29 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:41 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-83-HS-PID-830 | 03 | PIPING AND INSTRUMENTATION DIAGRAM FOR FLARE UNIT | DE | IFC-WH | HSE | PS-OT-T-0643 | 2018-07-08 |  | No | 666 | 1204-Owner-v | 2018-07-10 14:56 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | 2018-08-06 | 2018-07-10 | MT-PS-9609-CS-097 | InProgress | 90%
1204-00-HV-REQ-792 | 00 | REQUISITION FOR DUCT ACCESSORIES | DE | IFI | HV | PS-OT-T-0109 | 2015-10-06 |  | No | 1672 | 1204-Owner-v | 2015-10-07 08:29 | REQ | 2015-10-10 | 0 | 0 | 0 | 2015-10-10 |  |  | InProgress | 90%
1204-00-IN-DSH-604 | 03 | DATA SHEET FOR ON / OFF VALVES | DE | IFR | IN | PS-OT-T-0921 | 2020-02-27 |  | No | 67 | 1204-Owner-v | 2020-02-29 16:30 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-03-14 | MT-PS-9609-CS-0312 | InProgress | 80%
1204-00-IN-DSH-648 | 01 | DATA SHEET FOR ULTRASONIC LEVEL INSTRUMENTS | DE | IFR | IN | PS-OT-T-0546 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 08:48 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 |  |  |  | InProgress | 80%
1204-00-IN-SKT-005 | 01 | INSTRUMENT/ ELECTRICAL CONNECTION DETAILS | DE | IFC | IN | PS-OT-T-0244 | 2016-04-17 |  | No | 1478 | 1204-Owner-v | 2016-04-18 17:24 | CDW | 2016-04-17 | 0 | 0 | 0 | 2016-04-17 |  |  | complete | 100%
1204-00-PR-PID-010 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR NUMBERING PROCEDURE II | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:28 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-22-PR-DSH-134 | 00 | Process Instrument Data Sheet for Analyzers | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-00-EL-SCH-001 | 01 | ELECTRICAL LOAD SCHEDULE | DE | IFR | EL | TM-OT-9001-T-0403 | 2014-10-30 | 2015-08-12 15:56 | Yes | 272 | 1204-TKT-COLANGELI | 2014-10-30 12:54 | LIST | 2020-05-08 | 0 | 0 | 2020-05-08 | * |  |  | InProgress | 90%
1204-00-EL-SCH-018 | 00 | MOTOR & HEATER CONTROL PHILOSOPHY | DE | IFR | EL | TM-OT-9001-T-0344 | 2014-01-07 |  | No | 2309 | 1204-TKT-COLANGELI | 2014-01-07 11:16 | LIST | 2020-05-13 | 0 | 0 | 2020-05-13 | 2014-01-07 |  |  | InProgress | 90%
1204-00-EL-SLD-005 | 01 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR - MS-SWB3A,B-03 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:56 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:36 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2018-01-20 | 2018-05-31 | MT-PS-9609-CS-008-R | InProgress | 80%
1204-04-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 04 | DE | IFR | EL | PS-OT-T-537 | 2018-01-20 |  | No | 835 | 1204-Owner-v | 2018-01-24 09:12 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | 2018-01-21 | 2018-02-03 | MT-PS-9609-CS-022 | InProgress | 80%
1204-90-EL-DWG-830 | 01 | GUARD HOUSE COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:01 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:46 | CDW | 2014-01-29 | 0 | 0 | 0 | 2014-01-29 |  |  | complete | 100%
1204-00-HS-DWG-004 | 03 | FIRE AND GAS ALARM LAYOUT FOR PROCESS, UTILITY AND OFFSITE UNITS | DE | IFC-WH | HSE | PS-OT-T-0712 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-06 16:31 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | complete | 100%
1204-84-HS-DSH-003 | 01 | DATA SHEET FOR POC WATER PUMP P-8401 A/B | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:04 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-00-IN-SKT-003 | 00 | INSTRUMENT PROCESS HOOK UP’S | DE | IFR | IN | PS-OT-T-0018 | 2015-04-08 |  | No | 1853 | 1204-Owner-v | 2015-04-11 10:53 | CDW | 2015-04-04 | 0 | 0 | 0 | 2015-04-04 | 2015-05-04 | MT-TM-9301-CS-048 | InProgress | 80%
1204-00-PI-REQ-410A | 00 | REQUISITION FOR C.S ELECTRODE & WELDING ROD(MTO I) | DE | IFI | PI | PS-OT-T-0303 | 2016-07-10 |  | No | 1394 | 1204-Owner-v | 2016-07-12 16:27 | REQ | 2020-02-12 | 0 | 0 | 2020-02-18 | 2016-07-16 |  |  | InProgress | 90%
1204-00-IN-REQ-636 | 00 | REQUISITION FOR N2 BLANKETING SYSTEM | DE | IFI | IN | PS-OT-T-0539 | 2018-01-20 |  | No | 835 | 1204-Owner-v | 2018-01-21 09:55 | REQ | 2020-06-23 | 0 | 0 | 2020-07-06 | 2018-01-21 | 2018-01-28 | MT-PS-9609-CS-017 | InProgress | 90%
1204-00-IN-TBA-606 | 01 | TECHNICAL BID ANALYSIS FOR PRESSURE SAFETY/RELIEF VALVES | DE | IFE | IN | PS-OT-T-0968 | 2020-05-13 |  | No | -9 | 1204-Owner-v | 2020-05-16 08:45 | TBA | 2019-10-21 | 0 | 0 | 2019-11-08 | 2017-12-19 | 2017-12-20 | MT-PS-9301-CS-268-1 | complete | 100%
1204-00-PV-REQ-203 | 01 | REQUISITION FOR DEARATOR | DE | IFP | MD | PS-OT-T-0168 | 2016-01-03 |  | No | 1583 | 1204-Owner-v | 2016-01-06 11:20 | REQ | 2016-01-03 | 0 | 0 | 0 | 2016-01-03 | 2016-02-17 | MT-PS-9301-CS-108 | complete | 100%
1204-00-PV-TBA-203 | 01 | TECHNICAL BID ANALYSIS FOR DEARATOR | DE | IFE | MD | PS-OT-T-0135 | 2015-11-18 |  | No | 1629 | 1204-Owner-v | 2015-11-21 15:08 | TBA | 2015-11-19 | 0 | 0 | 0 | 2015-11-19 | 2016-01-12 | MT-PS-9301-CS-085 | complete | 100%
1204-00-PI-ISO-1500 | 00 | A/G ISOMETRIC DRAWING OF AREA-15 | DE | IFR | PI | PS-OT-T-0172 | 2016-01-04 |  | No | 1582 | 1204-Owner-v | 2016-01-06 12:08 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-09 | 2016-05-07 | MT-PS-9301-CS-143 | InProgress | 80%
1204-20-PR-TBA-105 | 02 | TECHNICAL BID ANALYSIS FOR HYDROGEN RECOVERY UNIT (HRU) | DE | IFE | PR | PS-OT-T-0036 | 2015-05-11 |  | No | 1820 | 1204-Owner-v | 2015-05-11 12:32 | TBA | 2015-05-11 | 0 | 0 | 0 | 2015-05-11 | 2015-05-27 | MT-TM-9301-CS-053 | complete | 100%
1204-40-PR-PID-405 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- PROCESS CONDENSATE STRIPPING | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:04 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-61-PR-PID-611 | 01 | PIPING & INSTRUMENTATION FLOW DIAGRAM FOR AIR SEPARATION UNIT (ASU) (PU-6101) | BE/DE | IFR | PR | PS-OT-T-0088 | 2015-08-08 |  | No | 1731 | 1204-Owner-v | 2015-08-15 17:24 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | * |  |  | InProgress | 80%
1204-72-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR CRUDE METHANOL STORAGE TANK | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:50 | LIST | 2020-04-02 | 0 | 0 | 2020-05-06 | 2013-08-06 |  |  | InProgress | 90%
1204-00-PI-TBA-405A | 00 | TECHNICAL BID ANALYSIS FOR BOLTS & NUTS(MTO I) | DE | IFE | PI | PS-OT-T-0935 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 15:52 | TBA | 2019-10-31 | 0 | 0 | 2019-11-01 | * |  |  | complete | 100%
1204-00-ST-DWG-018 | 04 | PIPE RACK ZONE 2 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0119 | 2015-10-17 |  | No | 1661 | 1204-Owner-v | 2015-10-18 11:10 | CDW | 2015-10-28 | 0 | 0 | 0 | 2015-10-28 | 2015-10-25 | MT-PS-9301-CS-026 | complete | 100%
1204-00-ST-DWG-048 | 04 | PIPE RACK ZONE 7 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0183 | 2016-01-12 |  | No | 1574 | 1204-Owner-v | 2016-01-16 10:01 | CDW | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 |  | Final Checked | complete | 100%
1204-10-ST-DWG-105 | 01 | D-1002 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0302 | 2016-07-04 |  | No | 1400 | 1204-Owner-v | 2016-07-05 10:46 | CDW | 2016-07-04 | 0 | 0 | 0 | 2016-07-04 | 2016-07-04 | MT-PS-9301-CS-174 | complete | 100%
1204-22-ST-DWG-666 | 01 | TK-2201 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0388 | 2014-08-04 |  | No | 2100 | 1204-TKT-COLANGELI | 2014-08-04 11:42 | CDW | 2014-08-04 | 0 | 0 | 0 | 2014-08-04 | 2014-08-03 | MT-OT-9301-CS-016 | complete | 100%
1204-00-HS-DSH-020 | 00 | DATA SHEET FOR GAS DETECTORS | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:17 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HV-MTO-793 | 01 | MATERIAL TAKE OFF FOR HVAC BULK ITEMS | DE | IFE | HV | PS-OT-T-0259 | 2016-05-10 |  | No | 1455 | 1204-Owner-v | 2016-05-14 17:22 | LIST | 2016-05-10 | 0 | 0 | 0 | 2016-05-10 |  |  | complete | 100%
1204-00-IN-DWG-005 | 01 | OVERALL CABLE ROUTING LAYOUT | DE | IFR | IN | PS-OT-T-0052 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:09 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-00-IN-REQ-625 | 00 | REQUISITION FOR TEMP. ELEMENTS / TRANSMITTERS & THERMOWELLS | DE | IFI | IN | PS-OT-T-0521 | 2017-12-19 |  | No | 867 | 1204-Owner-v | 2017-12-19 14:04 | REQ | 2020-02-18 | 0 | 0 | 2020-03-02 | * | 2018-01-03 | MT-PS-9301-CS-275-R | InProgress | 90%
1204-00-ST-CSS-750 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR FINISHING OF BUILDINGS | DE | IFC | ST | TM-OT-9001-T-0442 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:13 | SPEC | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-63-PR-DSH-105 | 03 | DATA SHEET FOR CORROSION INHIBITOR INJECTION PACKAGE (PU-6302) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-00-EL-DWG-008 | 01 | OVERALL COMMUNICATION LAYOUT | DE | IFR | EL | TM-OT-9001-T-0331 | 2013-10-29 |  | No | 2379 | 1204-TKT-COLANGELI | 2013-10-28 11:32 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | * |  |  | InProgress | 80%
1204-00-EL-SLD-006 | 01 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR - MS-SWB3A,B-04 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:56 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:28 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2018-01-20 | 2018-05-31 | MT-PS-9609-CS-008-R | InProgress | 80%
1204-03-EL-DWG-001 | 01 | POWER LAYOUT - AREA 03 | DE | IFR | EL | PS-OT-T-0115 | 2015-10-10 | 2016-01-14 11:56 | Yes | 82 | 1204-Owner-v | 2015-10-10 13:08 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2015-11-19 | MT-PS-9301-CS-043 | InProgress | 80%
1204-06-EL-DWG-020 | 01 | EARTHING LAYOUT - AREA 06 | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:54 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:49 | CDW | 2020-08-20 | 0 | 0 | 2020-08-20 | * | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-07-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 07 | DE | IFR | EL | PS-OT-T-0185 | 2016-01-18 | 2016-07-24 11:45 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:34 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2016-01-24 | 2016-01-25 | MT-PS-9301-CS-095 | InProgress | 80%
1204-90-EL-SLD-031 | 00 | MAIN EMERGENCY DISTRIBUTION PANEL SINGLE LINE DIAGRAM, MS-EDP-01 | DE | IFR | EL | PS-OT-T-0231 | 2013-04-06 | 2016-07-21 14:46 | Yes | 1188 | 1204-Owner-v | 2016-04-07 10:38 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-131 | InProgress | 80%
1204-00-HS-DSH-021 | 00 | DATA SHEET FOR MANUAL CALL POINTS | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:18 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HV-ESS-780 | 01 | ENGINEERING STANDARD SPECIFICATION FOR HVAC DESIGN CRITERIA | DE | IFE | HV | PS-OT-T-0559 | 2018-02-19 |  | No | 805 | 1204-Owner-v | 2018-02-21 10:48 | SPEC | 2018-03-15 | 0 | 0 | 0 | 2018-03-15 | 2018-05-01 | MT-PS-9609-CS-039-1-R | complete | 100%
1204-90-EL-SLD-038 | 01 | LABORATORY NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:37 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:43 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-001 | 00 | DATA SHEET FOR HYDRANT | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:11 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-00-HS-DSH-003 | 00 | DATA SHEET FOR FOAM/WATER MONITOR | DE | IFR | HSE | PS-OT-T-0738 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:00 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-00-IN-REQ-624 | 01 | REQUISITION FOR ELECTRONIC TRANSMITTERS | DE | IFP | IN | PS-OT-T-0940 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 16:55 | REQ | 2020-03-14 | 0 | 0 | 0 | 2020-03-14 | 2020-03-25 | MT-PS-9609-CS-0321 | complete | 100%
1204-00-PV-REQ-213A | 01 | REQUISITION FOR CARBON STEEL STORAGE TANKS | DE | IFP | MD | TM-OT-9001-T-0445 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2015-03-04 13:53 | REQ | 2015-03-04 | 0 | 0 | 0 | 2015-03-04 |  |  | complete | 100%
1204-00-PV-TBA-210 | 01 | TECHNICAL BID ANALYSIS FOR FLARE STACK | DE | IFE | MD | PS-OT-T-0923 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-03-03 12:18 | TBA | 2020-03-02 | 0 | 0 | 0 | 2020-03-02 | 2020-03-11 | MT-PS-9609-CS-0310 | complete | 100%
1204-00-PI-TBA-402A | 01 | TECHNICAL BID ANALYSIS FOR A/G FLANGES(MTO I) | DE | IFE | PI | PS-OT-T-0445 | 2017-04-29 |  | No | 1101 | 1204-Owner-v | 2017-05-06 12:31 | TBA | 2017-04-29 | 0 | 0 | 0 | 2017-04-29 | 2017-07-02 | MT-PS-9301-CS-228 | complete | 100%
1204-00-PR-PID-008 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR ABBREVIATIONS | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:29 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-63-PR-DSH-136 | 00 | Process Instrument Data Sheet for Level Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-90-EL-DWG-630 | 01 | FIRE STATION COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:00 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:44 | CDW | 2014-01-29 | 0 | 0 | 0 | 2014-01-29 |  |  | complete | 100%
1204-90-EL-SLD-043 | 01 | CLINIC EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:46 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-011 | 00 | DATA SHEET FOR PORTABLE DRY POWDER EXTINGUISHER | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:15 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-83-HS-LST-002 | 00 | LINE LIST FOR FLARE UNIT | DE | IFR | HSE | TM-OT-9001-T-0326 | 2013-09-30 |  | No | 2408 | 1204-TKT-COLANGELI | 2013-09-30 14:08 | LIST | 2019-10-01 | 2019-11-22 | 0 | 2020-07-15 | 2013-09-30 |  |  | InProgress | 90%
1204-84-HS-PFD-840 | 01 | PROCESS FLOW DIAGRAM FOR OILY WATER TREATMENT SYSTEM | DE | IFR | HSE | PS-OT-T-0696 | 2018-10-06 |  | No | 576 | 1204-Owner-v | 2018-10-13 13:55 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * |  |  | InProgress | 80%
1204-84-HS-PFD-841 | 02 | PROCESS FLOW DIAGRAM FOR SANITARY / LABORATORY WATER COLLECTION SYSTEM | DE | IFR | HSE | PS-OT-T-0851 | 2019-12-24 |  | No | 132 | 1204-Owner-v | 2019-12-30 08:37 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | 0 |  | MT-PS-9301-CS-0248 | InProgress | 80%
1204-10-PR-PID-112 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- FUEL GAS DISTRRIBUTION TO POST-BURNERS | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:20 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-10-PR-PID-113 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- ATR OXYGEN FEED & PROCESS STEAM | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:20 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-71-PR-PID-712 | 03 | PIPING & INSTRUMENTATION DIAGRAM FOR DAILY METHANOL STORAGE TANK B | BE/DE | IFC-WH | PR | PS-OT-T-0652 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-29 11:14 | EDW | 2020-05-01 | 0 | 0 | 2020-06-30 | 2018-08-02 | 2018-08-13 | MT-PS-9609-CS-109 | complete | 100%
1204-00-ST-REQ-740A | 01 | REQUISITION FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART A) | DE | IFI | ST | PS-OT-T-0269 | 2016-05-25 |  | No | 1440 | 1204-Owner-v | 2016-05-25 15:26 | REQ | 2016-05-25 | 0 | 0 | 0 |  |  |  | complete | 100%
1204-00-PV-REQ-206B | 01 | REQUISITION FOR SPECIAL COLUMNS (GROUP II) | DE | IFP | MD | PS-OT-T-0105 | 2015-09-23 |  | No | 1685 | 1204-Owner-v | 2015-09-28 09:30 | REQ | 2015-09-23 | 0 | 0 | 0 | 2015-09-23 | 2015-11-19 |  | complete | 100%
1204-00-PI-TBA-403A | 01 | TECHNICAL BID ANALYSIS FOR A/G GASKETS(MTO I) | DE | IFE | PI | PS-OT-T-0403 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-02-06 10:10 | TBA | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 | 2017-02-06 | MT-PS-9301-CS-211 | complete | 100%
1204-22-PR-DSH-140 | 00 | Process Instrument Data Sheet for Temperature Gauges | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-00-ST-DWG-032 | 01 | PIPE RACK ZONE 4 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0029 | 2015-04-29 |  | No | 1832 | 1204-Owner-v | 2015-08-09 11:21 | CDW | 2015-04-29 | 0 | 0 | 0 | 2015-04-29 |  |  | complete | 100%
1204-90-ST-DWG-923 | 03 | CONTROL ROOM & LABORATORY / BLOCK & JOIST | DE | IFC | ST | TM-OT-9001-T-0377 | 2014-06-11 |  | No | 2154 | 1204-TKT-COLANGELI | 2014-06-11 13:03 | CDW | 2014-06-11 | 0 | 0 | 0 | 2014-06-11 | 2014-07-12 | MT-OT-9301-CS-012 | complete | 100%
1204-90-ST-MTO-1026 | 01 | MATERIAL TAKE OFF FOR WORK SHOP / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0408 | 2014-11-06 |  | No | 2006 | 1204-TKT-COLANGELI | 2014-11-06 13:49 | LIST | 2014-11-06 | 0 | 0 | 0 | 2014-11-06 | 2014-12-30 | MT-TM-9301-CS-027 | complete | 100%
1204-72-PV-DSH-203 | 02 | MECHANICAL DATA SHEET FOR CRUDE METHANOL STORAGE TANK (TK-7201) | DE | IFE | MD | TM-OT-9001-T-0445 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2015-03-04 14:00 | DSH | 2015-03-04 | 0 | 0 | 0 | 2015-03-04 |  |  | complete | 100%
1204-90-IN-DWG-002 | 01 | CONTROL ROOM EQUIPMENT LAYOUT | DE | IFR | IN | PS-OT-T-479 | 2017-09-03 |  | No | 974 | 1204-Owner-v | 2017-09-04 09:23 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2017-10-02 | 2017-10-02 | MT-PS-9301-CS-237-R | InProgress | 80%
1204-00-PV-TBA-206B | 02 | TECHNICAL BID ANALYSIS FOR SPECIAL COLUMNS (GROUP II) | DE | IFE | MD | TM-OT-9001-T-0448 | 2015-03-05 |  | No | 1887 | 1204-TKT-COLANGELI | 2015-03-04 13:47 | TBA | 2015-03-05 | 0 | 0 | 0 | 2015-03-05 |  |  | complete | 100%
1204-00-PI-REQ-416A | 00 | REQUISITION FOR A.S & S.S ELECTRODE & WELDING ROD(MTO I) | DE | IFI | PI | PS-OT-T-0303 | 2016-07-10 |  | No | 1394 | 1204-Owner-v | 2016-07-12 16:27 | REQ | 2020-02-12 | 0 | 0 | 2020-02-25 | 2016-07-16 |  |  | InProgress | 90%
1204-00-PI-UPL-8000 | 03 | PAVING PLAN FOR PROCESS UNIT | DE | IFC-WH | PI | PS-OT-T-0776 | 2019-04-13 |  | No | 387 | 1204-Owner-v | 2019-04-18 11:07 | CDW | 2019-04-21 | 0 | 0 | 0 | 2019-04-21 |  |  | complete | 100%
1204-00-PR-PID-012 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR BATTERY LIMITS II | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:27 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-22-PR-LST-002 | 00 | LINE LIST FOR MACHINERY COOLING WATER SYSTEM | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:29 | LIST | 2020-03-27 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-30-PR-PID-301 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-TOPPING COLUMN | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:43 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-04-EL-DWG-001 | 01 | POWER LAYOUT - AREA 04 | DE | IFR | EL | PS-OT-T-0296 | 2016-06-25 | 2016-07-21 14:40 | Yes | 12 | 1204-Owner-v | 2016-06-26 08:27 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | * | 2016-06-29 | MT-PS-9301-CS-168 | InProgress | 80%
1204-90-EL-DWG-430 | 01 | CLINIC & TECHNICAL BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 07:58 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:40 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-90-EL-SLD-052 | 01 | WAREHOUSE NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:52 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-017 | 00 | DATA SHEET FOR SMOKE DETECTOR | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:13 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-IN-REQ-605 | 02 | REQUISITION FOR CONTROL VALVES | DE | IFP | IN | PS-OT-T-0912 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 17:09 | REQ | 2020-02-24 | 0 | 0 | 0 | 2020-02-24 | 2020-03-04 | MT-PS-9609-CS-0299 | complete | 100%
1204-00-PI-APL-1500 | 00 | PIPING PLAN AREA-15 | DE | IFR | PI | PS-OT-T-0172 | 2016-01-04 |  | No | 1582 | 1204-Owner-v | 2016-01-06 10:53 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-09 | 2016-05-07 | MT-PS-9301-CS-143 | InProgress | 80%
1204-00-PI-MTO-409A | 00 | MATERIAL TAKE OFF FOR PAINT (MTO I) | DE | IFE | PI | PS-OT-T-0771 | 2019-03-18 |  | No | 413 | 1204-Owner-v | 2019-03-19 11:22 | LIST | 2019-04-04 | 0 | 0 | 0 | 2019-04-04 |  |  | complete | 100%
1204-00-PI-REQ-411A | 00 | REQUISITION FOR HOSE & HOSE COUPLING(MTO I) | DE | IFI | PI | PS-OT-T-0965 | 2020-05-09 |  | No | -5 | 1204-Owner-v | 2020-05-11 14:16 | REQ | 2020-02-12 | 0 | 0 | 2020-02-25 |  |  |  | InProgress | 90%
1204-00-PR-PID-007 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR TYPICAL FOR SAMPLING | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:30 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-63-PR-DSH-135 | 00 | Process Instrument Data Sheet for Level Gauges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-62-PR-PID-622 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR INSTRUMENT AIR / PLANT AIR SYSTEM (2 OF 2) | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:28 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-63-PR-DSH-131 | 00 | Process Instrument Data Sheet for Control Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-63-PR-DSH-133 | 00 | Process Instrument Data Sheet for Safety Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-22-PV-DSH-210 | 01 | MECHANICAL DATA SHEET FOR CORROSION INHIBITOR VESSEL (D-2201) | DE | IFE | MD | TM-OT-9001-T-0149 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2014-09-30 10:58 | DSH | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-90-ST-DWG-1021 | 01 | WORK SHOP / FRAMES III | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 12:58 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-931 | 03 | SUBSTATION / FDN. (R.C. DETAILS I ) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-21 15:08 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-00-QC-SOI-203 | 00 | SCOPE OF INSPECTION FOR DEAERATOR | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-00-RE-REQ-326 | 00 | REQUISITION FOR CRANES | DE | IFI | MC | PS-OT-T-0649 | 2018-07-22 |  | No | 652 | 1204-Owner-v | 2018-07-24 15:22 | REQ | 2020-07-07 | 0 | 0 | 2020-07-20 | * | 2018-08-05 | MT-PS-9301-CS-100-R | InProgress | 90%
1204-90-ST-DWG-1055 | 00 | FIRE STATION / LINTEL , FINISHING & FALSE CEILING | DE | IFR | ST | TM-OT-9001-T-0200 | 2012-11-05 |  | No | 2737 | 1204-Owner-v | 2015-09-16 18:26 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2012-11-05 |  |  | InProgress | 80%
1204-90-ST-DWG-1088 | 00 | GUARD HOUSE / PLUMBING LAYOUT & DETAILS | DE | IFR | ST | TM-OT-9001-T-0421 | 2014-12-10 |  | No | 1972 | 1204-TKT-COLANGELI | 2014-12-10 14:31 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 2014-12-10 | 2014-12-30 | MT-TM-9301-CS-030 | InProgress | 80%
1204-40-RE-DSH-032 | 00 | Data Sheet for Steam Turbine for MP Boiler Feed Water Pumps PT-4002 A | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:54 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-00-PR-UDD-018 | 02 | UTILITY DISTRIBUTION DIAGRAM FOR CHEMICAL DRAIN RECOVERY SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:23 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2017-02-23 |  |  | InProgress | 80%
1204-90-EL-DWG-111 | 02 | CONTROL ROOM & LABORATORY BUILDING SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0439 | 2015-02-11 | 2015-03-02 17:53 | Yes | 5 | 1204-TKT-COLANGELI | 2015-02-10 18:55 | CDW | 2015-02-11 | 0 | 0 | 0 | 2015-02-11 |  |  | complete | 100%
1204-90-ST-DWG-987 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / BEAMS (R.C. II) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:46 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-947 | 02 | SUBSTATION / SLABS (R.C. III) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 13:37 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-00-QC-SOI-520 | 00 | SCOPE OF INSPECTION FOR LIGHTING FIXTURES | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-20-RE-DSH-029 | 00 | Data Sheet for Steam Turbine for Converter BW Circulation Pumps PT-2002 A | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:40 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-00-EL-REQ-504 | 02 | REQUISITION FOR POWER & DISTRIBUTION TRANSFORMER | DE | IFP | EL | PS-OT-T-0883 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:38 | REQ | 2016-04-19 | 0 | 0 | 0 | 2016-04-19 | 2020-03-09 | MT-PS-9609-CS-0305 | complete | 100%
1204-00-EL-REQ-510 | 01 | REQUISITION FOR CATHODIC PROTECTION | DE | IFP | EL | PS-OT-T-0951 | 2020-04-15 |  | No | 19 | 1204-Owner-v | 2020-04-18 08:52 | REQ | 2020-04-15 | 0 | 0 | 0 | 2020-04-15 |  |  | complete | 100%
1204-00-EL-REQ-526 | 01 | REQUISITION FOR JUNCTION BOXES | DE | IFI | EL | PS-OT-T-0906 | 2020-02-23 |  | No | 71 | 1204-Owner-v | 2020-02-23 13:06 | REQ | 2020-05-14 | 0 | 0 | 2020-05-20 | * | 2020-02-26 | MT-PS-9609-CS-280 | InProgress | 90%
1204-00-PV-REQ-205A | 02 | REQUISITION FOR PACKING & TRAYS & INTERNALS & DEMISTERS | DE | IFP | MD | TM-OT-9001-T-0389 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-11 11:42 | REQ | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-09-01 | MT-OT-9301-CS-022 | complete | 100%
1204-30-HM-DSH-237 | 00 | MECHANICAL DATA SHEET FOR CRUDE PREHEATER (E-3001) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:07 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-20-PR-PID-203 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS GAS CIRCULATOR | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:24 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-30-PR-PID-303 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-BFW PREHEATING SECTION | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:43 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-00-ST-DWG-031 | 02 | PIPE RACK ZONE 4 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0029 | 2015-04-29 |  | No | 1832 | 1204-Owner-v | 2015-08-09 11:21 | CDW | 2015-04-29 | 0 | 0 | 0 | 2015-04-29 |  |  | complete | 100%
1204-10-ST-DWG-148 | 02 | REFORMER (H-1001) / FDN. (R.C. & DETAILS I ) | DE | IFC | ST | PS-OT-T-0672 | 2018-08-28 |  | No | 615 | 1204-Owner-v | 2018-09-01 09:42 | CDW | 2018-09-03 | 0 | 0 | 0 | 2018-09-03 |  |  | complete | 100%
1204-90-ST-DWG-974 | 03 | ADMINISTRATION , RESTAURANT & CLINIC & GUARD HOUSE BUILDING / SECTIONS | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-03 10:02 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | * | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-22-PV-DSH-201 | 02 | MECHANICAL DATA SHEET FOR MACHINERY COOLING WATER STORAGE TANK (TK-2201) | DE | IFE | MD | TM-OT-9001-T-0445 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2014-10-06 10:37 | DSH | 2015-03-04 | 0 | 0 | 0 | 2015-03-04 |  |  | complete | 100%
1204-00-HV-SDG-786 | 01 | STANDARD DRAWING FOR HVAC | DE | IFC | HV | TM-OT-9001-T-0422 | 2014-12-11 |  | No | 1971 | 1204-TKT-COLANGELI | 2014-12-10 15:28 | SPEC | 2014-12-11 | 0 | 0 | 0 | 2014-12-11 |  |  | complete | 100%
1204-20-ST-DWG-209 | 01 | STRUCTURE "A" & STRUCTURE "M" / COMBINED FDN.(R.C. & DETAILS I) | DE | IFC | ST | PS-OT-T-0691 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-09-29 15:07 | CDW | 2018-09-29 | 0 | 0 | 0 | 2018-09-29 |  |  | complete | 100%
1204-90-ST-DWG-910 | 02 | CONTROL ROOM & LABORATORY / LINTEL , FINISHING & FALSE CEILING | DE | IFC-WH | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:39 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-90-ST-DWG-933 | 01 | SUBSTATION / FDN. (R.C. DETAILS III ) | DE | IFC | ST | TM-OT-9001-T-0345 | 2014-01-07 |  | No | 2309 | 1204-TKT-COLANGELI | 2014-01-07 13:02 | CDW | 2014-01-07 | 0 | 0 | 0 | 2014-01-07 |  |  | complete | 100%
1204-62-PV-DSH-206 | 01 | MECHANICAL DATA SHEET FOR PLANT/INSTRUMENT AIR RECEIVER (D-6201) | DE | IFE | MD | TM-OT-9001-T-0149 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2015-09-16 17:57 | DSH | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-00-QC-SOI-625 | 00 | SCOPE OF INSPECTION FOR TEMP. ELEMENTS / TEMP. TRANSMITTER &TW | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1052 | 02 | FIRE STATION. / G.A & FURNITURE PLAN | DE | IFC | ST | TM-OT-9001-T-0196 | 2012-10-30 |  | No | 2743 | 1204-Owner-v | 2015-08-26 21:04 | CDW | 2012-10-30 | 0 | 0 | 0 | 2012-10-30 |  |  | complete | 100%
1204-90-ST-DWG-1083 | 02 | GUARD HOUSE / ELEVATIONS | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 13:13 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-90-ST-DWG-938 | 01 | SUBSTATION / FINISHING, LINTEL PLAN & DETAILS | DE | IFC-WH | ST | TM-OT-9001-T-0368 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 15:40 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-90-ST-DWG-939 | 01 | SUBSTATION / ROOF SLOPING PLAN & DETAILS | DE | IFC | ST | TM-OT-9001-T-0368 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 14:54 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-90-ST-DWG-945 | 02 | SUBSTATION / SLABS (R.C. I) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 13:31 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-90-ST-DWG-1081 | 02 | GUARD HOUSE /G.A. PLAN & FURNITURE | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 12:50 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-00-EL-TBA-531 | 00 | TECHNICAL BID ANALYSIS FOR CABLE TRAYS AND LADDERS | DE | IFE | EL | PS-OT-T-0908 | 2020-02-23 |  | No | 71 | 1204-Owner-v | 2020-02-23 13:00 | TBA | 2020-01-31 | 0 | 0 | 2020-02-06 | * | 2020-02-26 | MT-PS-9609-CS-0281 | complete | 100%
1204-00-IN-DWG-011 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 11) | DE | IFR | IN | PS-OT-T-0167 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:54 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-01-06 | 2016-01-10 | MT-PS-9301-CS-082 | InProgress | 80%
1204-90-ST-DWG-992 | 01 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / INSERT PLATES | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:55 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-00-EL-DSH-5022 | 00 | DATA SHEET FOR AUTO/MANUAL TRANSFER, 6KV SWITCHGEAR MS-SWB2A,B-01 | DE | IFR | EL | TM-OT-9001-T-0247 | 2013-03-25 |  | No | 2597 | 1204-Owner-v | 2015-09-14 16:52 | DSH | 2020-05-12 | 0 | 0 | 2020-05-12 | 2013-03-25 |  |  | InProgress | 80%
1204-00-PI-REQ-401A | 02 | REQUISITION FOR A/G PIPES & FITTINGS(MTO I) | DE | IFP | PI | PS-OT-T-0513 | 2017-12-11 |  | No | 875 | 1204-Owner-v | 2017-12-16 11:08 | REQ | 2017-12-16 | 0 | 0 | 0 | 2017-12-16 | 2018-01-08 | MT-PS-9609-CS-004 | complete | 100%
1204-22-PR-DSH-138 | 00 | Process Instrument Data Sheet for Pressure Gauges | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-71-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR DAILY METHANOL STORAGE TANKS | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:30 | LIST | 2020-03-27 | 0 | 0 | 2020-05-06 | 2013-08-06 |  |  | InProgress | 90%
1204-00-ST-DWG-019 | 02 | PIPE RACK ZONE 2 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0013 | 2015-03-18 |  | No | 1874 | 1204-Owner-v | 2015-03-25 13:30 | CDW | 2015-03-18 | 0 | 0 | 0 | 2015-03-18 |  |  | complete | 100%
1204-00-ST-DWG-054 | 04 | PIPE RACK ZONE 8 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0183 | 2016-01-12 |  | No | 1574 | 1204-Owner-v | 2016-01-16 10:01 | CDW | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 |  | Final Checked | complete | 100%
1204-00-ST-DWG-067 | 02 | PIPE RACK ZONE 10 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0234 | 2016-04-10 |  | No | 1485 | 1204-Owner-v | 2016-04-11 13:27 | CDW | 2016-04-19 | 0 | 0 | 0 | 2016-04-19 |  | Final Checked | complete | 100%
1204-30-ST-DWG-319 | 02 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0757 | 2019-03-02 |  | No | 429 | 1204-Owner-v | 2019-03-04 09:42 | CDW | 2019-03-11 | 0 | 0 | 0 | 2019-03-11 |  |  | complete | 100%
1204-10-PR-PID-111 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- FUEL GAS DISTRRIBUTION TO ARCH-BURNERS | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:22 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-40-PR-PID-401 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- DEAREATION + BFW PUMPS | DE | IFC-WH | PR | PS-OT-T-0664 | 2018-08-11 |  | No | 632 | 1204-Owner-v | 2018-08-16 09:09 | EDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2018-08-15 |  |  | InProgress | 90%
1204-63-PR-LST-002 | 00 | LINE LIST FOR COOLING WATER SYSTEM | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:39 | LIST | 2020-03-30 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-00-ST-DWG-011 | 03 | PIPE RACK ZONE 1 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0110 | 2015-10-07 |  | No | 1671 | 1204-Owner-v | 2015-10-08 11:43 | CDW | 2015-10-20 | 0 | 0 | 0 | 2015-10-20 | 2015-10-20 | MT-PS-9301-CS-027 | complete | 100%
1204-00-ST-DWG-024 | 03 | PIPE RACK ZONE 3 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0119 | 2015-10-17 |  | No | 1661 | 1204-Owner-v | 2015-10-18 12:05 | CDW | 2015-10-28 | 0 | 0 | 0 | 2015-10-28 | 2015-10-25 | MT-PS-9301-CS-026 | complete | 100%
1204-20-ST-DWG-201 | 02 | D-2001 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0593 | 2018-04-24 |  | No | 741 | 1204-Owner-v | 2018-04-28 14:38 | CDW | 2018-05-03 | 0 | 0 | 0 | 2018-05-03 | 2018-04-29 | MT-PS-9609-CS-060 | complete | 100%
1204-90-ST-DWG-1011 | 02 | WORK SHOP / FDN.. (G.A.& DETAILS) | DE | IFC | ST | PS-TM-T-0252 | 2017-09-13 |  | No | 964 | 1204-TKT-COLANGELI | 2013-09-26 13:44 | CDW | 2017-09-13 | 0 | 0 | 0 | 2017-09-13 |  |  | complete | 100%
1204-10-ST-DWG-109 | 01 | D-1003 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0302 | 2016-07-04 |  | No | 1400 | 1204-Owner-v | 2016-07-05 10:47 | CDW | 2016-07-04 | 0 | 0 | 0 | 2016-07-04 | 2016-07-04 | MT-PS-9301-CS-174 | complete | 100%
1204-10-ST-DWG-155 | 01 | REFORMER (HORIZONTAL CONVECTION SECTION) / FDN. (R.C.) | DE | IFC | ST | PS-OT-T-0672 | 2018-08-28 |  | No | 615 | 1204-Owner-v | 2018-09-01 09:43 | CDW | 2018-08-28 | 0 | 0 | 0 | 2018-08-28 |  |  | complete | 100%
1204-90-ST-DWG-1013 | 02 | WORK SHOP / G.A. , FURNITURE & SECTIONS | DE | IFC | ST | TM-OT-9001-T-0261 | 2013-04-24 |  | No | 2567 | 1204-TKT-COLANGELI | 2013-04-24 11:29 | CDW | 2013-04-24 | 0 | 0 | 0 | 2013-04-24 |  |  | complete | 100%
1204-90-ST-DWG-904 | 03 | CONTROL ROOM & LABORATORY / FURNITURE PLAN | DE | IFC-WH | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:24 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-00-QC-SOI-256B | 00 | SCOPE OF INSPECTION FOR FILTERS | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-90-ST-DWG-934 | 03 | SUBSTATION / G.A PLAN OF GROUND FLOOR & FIRST FLOOR | DE | IFC-WH | ST | TM-OT-9001-T-0368 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 13:44 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-30-ST-DWG-337 | 00 | STRUCTURE "E" FOR E-3004,E-3012 / STAIRS | DE | IFR | ST | PS-OT-T-0428 | 2017-03-08 |  | No | 1153 | 1204-Owner-v | 2017-03-09 09:53 | CDW | 2017-04-09 | 0 | 0 | 0 | 2017-04-09 | 2017-03-11 | MT-PS-9301-CS-218 | InProgress | 80%
1204-90-ST-DWG-1004 | 01 | CONTROL ROOM & LABORATORY / CONTROL ROOM SHELTER & DETS. | DE | IFC | ST | TM-OT-9001-T-0432 | 2015-01-21 |  | No | 1930 | 1204-TKT-COLANGELI | 2015-01-20 12:58 | CDW | 2015-01-21 | 0 | 0 | 0 | 2015-01-21 |  |  | complete | 100%
1204-90-ST-DWG-966 | 05 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0956 | 2020-04-27 |  | No | 7 | 1204-Owner-v | 2020-04-29 09:03 | CDW | 2020-04-27 | 0 | 0 | 0 | 2020-04-27 |  |  | complete | 100%
1204-90-ST-DWG-988 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / COLUMNS & WALLS (R.C.DETAILS) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:49 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-1016 | 01 | WORK SHOP / LINTEL , FINISHING & FALSE CEILING PLAN | DE | IFC | ST | TM-OT-9001-T-0372 | 2014-05-27 |  | No | 2169 | 1204-TKT-COLANGELI | 2014-05-27 11:40 | CDW | 2014-05-27 | 0 | 0 | 0 | 2014-05-27 |  |  | complete | 100%
1204-90-ST-DWG-1040 | 01 | WAREHOUSE / FRAMES & PLAN FOR OFFICE PART | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:10 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-985 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / FRAMES | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:34 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-30-PV-DSH-232 | 01 | MECHANICAL DATA SHEET FOR TOPPING COLUMN (T-3001) | DE | IFE | MD | TM-OT-9001-T-0343 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:20 | DSH | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-20-PV-DSH-215 | 01 | MECHANICAL DATA SHEET FOR CRUDE METHANOL LET-DOWN SEPARATOR (D-2002) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:32 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | complete | 100%
1204-00-EL-CSS-502 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR ELECTRICAL INSTALLATION IN BUILDING | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:40 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-621 | 00 | Material Standard Specification for Displacer Type Level Transmitters | DE | IFR | IN | TM-OT-9001-T-0076 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 16:59 | SPEC | 2020-03-30 | 0 | 0 | 2020-03-30 | 2012-05-29 |  |  | InProgress | 80%
1204-71-PR-DSH-102 | 01 | DATA SHEET FOR DAILY METHANOL TRANSFER PUMPS (P-7101 A/B) | BE | IFE | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-Owner-v | 2015-09-16 18:06 | DSH | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-00-EL-DIG-005 | 02 | CCTV SYSTEM RISER DIAGRAM | DE | IFR | EL | PS-OT-T-0878 | 2020-02-04 |  | No | 90 | 1204-Owner-v | 2020-02-08 09:42 | CDW | 2020-04-20 | 0 | 0 | 2020-04-20 | * | 2020-03-07 | MT-PS-9609-CS-0302 | InProgress | 80%
1204-00-EL-DWG-001 | 00 | Electrical Symbols and Legends | DE | IFR | EL | TM-OT-9001-T-0097 | 2012-06-01 |  | No | 2894 | 1204-Owner-v | 2015-09-14 16:53 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2012-06-01 |  |  | InProgress | 80%
1204-00-EL-MSS-504 | 01 | MATERIAL STANDARD SPECIFICATION FOR POWER & DISTRIBUTION TRANSFORMERS | DE | IFE | EL | TM-OT-9001-T-0403 | 2014-10-30 | 2015-08-12 15:03 | Yes | 272 | 1204-TKT-COLANGELI | 2014-10-30 12:56 | SPEC | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 |  |  | complete | 100%
1204-00-IN-MSS-626 | 01 | MATERIAL STANDARD SPECIFICATION FOR MOTOR OPERATED VALVES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:08 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-627 | 01 | MATERIAL STANDARD SPECIFICATION FOR INSTRUMENT JUNCTION BOXES & CABLE GLANDS | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:04 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-71-ST-DWG-755 | 01 | DYKE WALL FOR TK-7101 A/B & TK-7201 / STAIRS | DE | IFC | ST | PS-OT-T-0577 | 2018-03-10 |  | No | 786 | 1204-Owner-v | 2018-03-12 12:07 | CDW | 2018-03-10 | 0 | 0 | 0 | 2018-03-10 | 2018-03-13 | MT-PS-9609-CS-046 | complete | 100%
1204-00-PI-TBA-401A | 02 | TECHNICAL BID ANALYSIS FOR A/G PIPES & FITTINGS(MTO I) | DE | IFE | PI | PS-OT-T-0425 | 2017-03-05 |  | No | 1156 | 1204-Owner-v | 2017-03-07 09:01 | TBA | 2017-03-14 | 0 | 0 | 0 | 2017-03-14 | 2017-03-08 | MT-PS-9301-CS-216 | complete | 100%
1204-10-PR-PID-102 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- NTURAL GAS FEED SUPPLY | DE | IFC-WH | PR | PS-OT-T-0749 | 2019-01-23 |  | No | 467 | 1204-Owner-v | 2019-01-27 13:52 | EDW | 2021-04-01 | 0 | 0 | 2021-04-01 | 2019-01-30 | 2020-04-20 | MT-PS-9609-CS-0331 | InProgress | 90%
1204-63-PR-PID-631 | 02 | PIPING AND INSTRUMENTATION DIAGRAM FOR COOLING WATER SYSTEM | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:30 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-10-ST-DWG-127 | 01 | E-1009 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0299 | 2016-06-28 |  | No | 1406 | 1204-Owner-v | 2016-06-28 17:33 | CDW | 2016-06-28 | 0 | 0 | 0 | 2016-06-28 |  |  | complete | 100%
1204-90-ST-MTO-961 | 00 | MATERIAL TAKE OFF FOR SUBSTATION / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:19 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-008 | complete | 100%
1204-00-QC-SOI-154 | 00 | SCOPE OF INSPECTION FOR FIRE AND GAS ALARM SYSTEM | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PV-REQ-220A | 02 | REQUISITION FOR SILENCERS | DE | IFP | MD | PS-OT-T-0962 | 2020-05-05 |  | No | -1 | 1204-Owner-v | 2020-05-07 13:18 | REQ | 2019-11-27 | 0 | 0 | 2020-01-03 | * | 2020-01-03 | MT-PS-9609-CS-0259 | complete | 100%
1204-90-ST-DWG-1018 | 01 | WORK SHOP / FRAMING PLANS | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 12:35 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-1038 | 01 | WAREHOUSE / FRAMES I | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:04 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-1062 | 00 | FIRE STATION / BLOCK & JOIST | DE | IFR | ST | TM-OT-9001-T-0421 | 2014-12-10 |  | No | 1972 | 1204-TKT-COLANGELI | 2014-12-10 14:34 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2014-12-10 | 2014-12-30 | MT-TM-9301-CS-030 | InProgress | 80%
1204-00-IN-CSS-601 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR INSTRUMENTATION | DE | IFE | IN | PS-OT-T-0058 | 2015-06-08 |  | No | 1792 | 1204-Owner-v | 2015-06-09 08:42 | SPEC | 2015-06-08 | 0 | 0 | 0 | 2015-06-08 |  |  | complete | 100%
1204-00-PV-SDG-240 | 00 | Standard Drawing for Pressure Vessel | DE | IFR | MD | TM-OT-9001-T-0130 | 2012-07-11 |  | No | 2854 | 1204-Owner-v | 2015-04-11 15:25 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * |  |  | InProgress | 80%
1204-64-PR-DSH-105 | 02 | PROCESS DATA SHEET FOR MIXED BED POLISHER PACKAGE (PU-6401) | BE | IFE | PR | PS-OT-T-0053 | 2015-05-30 |  | No | 1801 | 1204-Owner-v | 2015-05-30 15:36 | DSH | 2015-05-30 | 0 | 0 | 0 | 2015-05-30 |  |  | complete | 100%
1204-05-EL-DWG-030 | 00 | COMMUNICATION AND CCTV LAYOUT AREA 05 | DE | IFR | EL | PS-OT-T-0185 | 2016-01-18 | 2016-07-24 11:45 | Yes | 174 | 1204-Owner-v | 2016-01-19 15:34 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | 2016-01-24 | 2016-01-25 | MT-PS-9301-CS-095 | InProgress | 80%
1204-00-HS-DSH-009 | 00 | DATA SHEET FOR LINEAR CABLE HEAT DETECTOR | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:10 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HS-DSH-026 | 00 | DATA SHEET FOR AUTO/MANUAL/INHIBIT SWITCHES | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:24 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-IN-DSH-625 | 01 | DATA SHEET FOR TEMPERATURE ELEMENTS / TRANSMITTERS & THERMOWELLS | DE | IFR | IN | PS-OT-T-0520 | 2017-12-19 |  | No | 867 | 1204-Owner-v | 2017-12-19 14:04 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2017-12-25 | 2018-01-03 | MT-PS-9301-CS-274-R | InProgress | 80%
1204-00-EL-CSS-502 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR ELECTRICAL INSTALLATION IN BUILDING | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:40 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-MSS-623 | 01 | MATERIAL STANDARD SPECIFICATION FOR PRESSURE SWITCHES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:07 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-IN-MSS-631 | 01 | MATERIAL STANDARD SPECIFICATION FOR INSTRUMENT TUBE AND TUBE FITTINGS | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:04 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-00-ST-CSS-752 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR FABRICATION & ERECTION OF STEEL STRUCTURES | DE | IFC | ST | PS-OT-T-0031 | 2015-05-04 |  | No | 1827 | 1204-Owner-v | 2015-05-05 08:37 | SPEC | 2015-05-04 | 0 | 0 | 0 | 2015-05-04 |  |  | complete | 100%
1204-63-PR-DSH-102 | 01 | PROCESS DATA SHEET FOR COOLING TOWER BASIN (A-6301) | BE | IFE | PR | PS-OT-T-0004 | 2015-03-03 |  | No | 1889 | 1204-Owner-v | 2015-08-30 11:38 | DSH | 2015-03-03 | 0 | 0 | 0 | 2015-03-03 |  |  | complete | 100%
1204-63-PR-DSH-104 | 02 | DATA SHEET FOR COOLING WATER SUPPLY PUMPS STEAM TURBINE (PT-6301 A/B) | BE | IFE | PR | PS-OT-T-0292 | 2016-06-19 |  | No | 1415 | 1204-Owner-v | 2016-06-20 14:23 | DSH | 2016-06-26 | 0 | 0 | 0 | 2016-06-26 | 2016-07-02 | MT-PS-9301-CS-171 | complete | 100%
1204-00-EL-CSH-004 | 01 | CABLE SIZING CALCULATIONS | DE | IFR | EL | PS-OT-T-474 | 2017-08-29 |  | No | 979 | 1204-Owner-v | 2017-08-30 09:04 | LIST | 2020-08-30 | 0 | 0 | 2020-08-30 | * | 2017-09-04 | MT-PS-9301-CS-236 | InProgress | 90%
1204-00-PI-LST-415 | 00 | PIPING ALLOWABLE NOZZLE LOADS FOR STATIC EQUIPMENT | DE | IFR | PI | TM-OT-9001-T-0217 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 17:27 | LIST | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 90%
1204-00-ST-CSS-751 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR CONCRETE MATERIAL AND CONSTRUCTION | DE | IFC | ST | TM-OT-9001-T-0442 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:14 | SPEC | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-00-IN-MSS-634 | 01 | MATERIAL STANDARD SPECIFICATION FOR RADAR TYPE LEVEL TRANSMITTERS | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:08 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-64-PR-LST-001 | 01 | EQUIPMENT LIST FOR WATER POLISHING SYSTEM SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 11:59 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-72-PR-LST-001 | 01 | EQUIPMENT LIST FOR CRUDE METHANOL STORAGE TANK | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 11:59 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-00-EL-CSH-001 | 00 | SHORT CIRCUIT CALCULATION | DE | IFR | EL | PS-OT-T-0625 | 2018-06-03 |  | No | 701 | 1204-Owner-v | 2018-06-13 11:58 | LIST | 2020-08-15 | 0 | 0 | 2020-08-15 | * |  |  | InProgress | 90%
1204-00-EL-DSH-501 | 01 | DATA SHEET FOR NEUTRAL GROUNDING RESISTORS (MS-NGR-01A/B) | DE | IFR | EL | PS-OT-T-0925 | 2020-03-07 | 2020-04-04 11:07 | Yes | 14 | 1204-Owner-v | 2020-03-09 09:05 | DSH | 2020-05-08 | 0 | 0 | 2020-05-08 | * | 2020-03-25 | MT-PS-9609-CS-0319 | InProgress | 80%
1204-00-EL-SDG-626 | 00 | Electrical Installation Standard Drawings - Heat Tracing | DE | IFR | EL | TM-OT-9001-T-0096 | 2012-05-31 | 2015-08-12 12:10 | Yes | 1154 | 1204-Owner-v | 2015-09-14 17:23 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | 2012-05-31 | 2014-12-01 | MT-TM-9301-CS-021 | InProgress | 80%
1204-00-EL-SLD-020 | 01 | SINGLE LINE DIAGRAM FOR 110V AC UPS (CR-UPS-01, CR01-UPS-01) | DE | IFR | EL | PS-OT-T-483 | 2017-09-11 | 2017-10-18 16:49 | Yes | 23 | 1204-Owner-v | 2017-09-13 09:59 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2017-10-09 | MT-PS-9301-CS-252 | InProgress | 80%
1204-00-IN-MSS-608 | 01 | MATERIAL STANDARD SPECIFICATION FOR ANNUBAR FLOW ELEMENT | DE | IFE | IN | PS-OT-T-0048 | 2015-05-23 |  | No | 1808 | 1204-Owner-v | 2015-05-24 09:03 | SPEC | 2015-05-23 | 0 | 0 | 0 | 2015-05-23 |  |  | complete | 100%
1204-00-HS-ESS-154 | 02 | ENGINEERING STANDARD SPECIFICATION FOR SAFETY SIGNS | DE | IFE | HSE | PS-OT-T-0024 | 2015-04-20 |  | No | 1841 | 1204-Owner-v | 2015-04-21 09:50 | SPEC | 2015-04-20 | 0 | 0 | 0 | 2015-04-20 |  |  | complete | 100%
1204-00-EL-DSH-5032 | 01 | DATA SHEET FOR LV SWITCHGEAR (MS-SWB3A,B-02) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:23 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:08 | DSH | 2020-05-12 | 0 | 0 | 2020-05-12 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-CSS-501 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR ELECTRICAL INSTALLATION IN AREA | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:36 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-EL-CSS-501 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR ELECTRICAL INSTALLATION IN AREA | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:36 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-PI-SDG-403 | 01 | STANDARD DRAWING FOR UNDER GROUND PIPING | DE | IFE | PI | PS-OT-T-0408 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-02-26 11:23 | SPEC | 2017-01-17 | 0 | 0 | 0 | 2017-01-17 |  |  | complete | 100%
1204-00-IN-MSS-619 | 01 | MATERIAL STANDARD SPECIFICATION FOR LEVEL SWITCHES | DE | IFE | IN | PS-OT-T-0051 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:07 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-PV-ESS-248 | 01 | ENGINEERING STANDARD SPECIFICATION FOR CLADDING AND LINING | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-04-10 11:07 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-00-MC-MSS-006 | 00 | MATREIAL STANDARD SPECIFICATION FOR POSITIVE DISPLACEMENT PUMPS- CONTROLLED VOLUME | DE | IFR | MC | TM-OT-9001-T-0145 | 2012-08-30 |  | No | 2804 | 1204-Owner-v | 2015-04-15 14:19 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-71-PV-DSH-202 | 03 | MECHANICAL DATA SHEET FOR SHIFT METHANOL STORAGE TANK (TK-7101A/B) | DE | IFE | MD | TM-OT-9001-T-0445 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2015-03-04 14:01 | DSH | 2015-03-04 | 0 | 0 | 0 | 2015-03-04 |  |  | complete | 100%
1204-64-PV-DSH-208 | 01 | MECHANICAL DATA SHEET FOR SULFURIC ACID DRUM (D-6401) | DE | IFE | MD | TM-OT-9001-T-0149 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2014-09-30 11:00 | DSH | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-00-QC-SOI-152 | 00 | SCOPE OF INSPECTION FOR FIRE EXTINGUISHERS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PR-UDD-012 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR STEAM CONDENSATE & BLOWDOWN DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:25 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-IN-ESS-603 | 01 | ENGINEERING STANDARD SPECIFICATION FOR PACKAGE INSTRUMENTATION | DE | IFE | IN | PS-OT-T-0062 | 2015-06-16 |  | No | 1784 | 1204-Owner-v | 2015-06-17 15:25 | SPEC | 2015-06-16 | 0 | 0 | 0 | 2015-06-16 |  |  | complete | 100%
1204-00-ST-ESS-742 | 01 | ENGINEERING STANDARD SPECIFICATION FOR CONCRETE DESIGN AND MATERIAL | DE | IFC | ST | TM-OT-9001-T-0408 | 2014-11-06 |  | No | 2006 | 1204-TKT-COLANGELI | 2014-11-06 13:38 | SPEC | 2014-11-06 | 0 | 0 | 0 | 2014-11-06 | 2014-12-30 | MT-TM-9301-CS-027 | complete | 100%
1204-00-HS-ESS-152 | 01 | ENGINEERING STANDARD SPECIFICATION FOR FIRE AND GAS SYSTEM | DE | IFE | HSE | TM-OT-9001-T-0396 | 2014-10-02 |  | No | 2041 | 1204-TKT-COLANGELI | 2014-10-01 10:42 | SPEC | 2014-10-02 | 0 | 0 | 0 | 2014-10-02 | 2014-11-08 | MT-TM-9301-CS-001 | complete | 100%
1204-63-PR-LST-001 | 01 | EQUIPMENT LIST FOR COOLING WATER SYSTEM | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 12:00 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-00-MC-MSS-002 | 00 | Matreial Standard Specification for Special Purpose Steam Turbines | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-01-17 13:52 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-DIG-006 | 02 | RADIO SYSTEM BLOCK DIAGRAM | DE | IFC | EL | PS-OT-T-0960 | 2020-05-05 |  | No | -1 | 1204-Owner-v | 2020-05-07 13:14 | CDW | 2020-05-30 | 0 | 0 | 2020-05-30 | * | 2016-04-18 | MT-PS-9301-CS-129 | complete | 100%
1204-00-EL-SLD-008 | 00 | SINGLE LINE DIAGRAM FOR 6KV SWITCHGEAR (SS01-SWB2A,B-01) | DE | IFR | EL | PS-OT-T-0511 | 2017-12-09 | 2018-02-12 15:49 | Yes | 51 | 1204-Owner-v | 2017-12-11 09:33 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2017-12-12 | 2017-12-19 | MT-PS-9301-CS-272 | InProgress | 80%
1204-30-PV-DSH-217 | 01 | MECHANICAL DATA SHEET FOR LIGHT ENDS KO DRUM (D-3002) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 14:33 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-64-ST-MTO-713 | 00 | MATERIAL TAKE OFF FOR TK-6401 | DE | IFE | ST | TM-OT-9001-T-0404 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-30 15:40 | LIST | 2020-08-18 | 0 | 0 | 2020-08-18 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-007 | complete | 100%
1204-90-HV-DSH-102 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR EXHAUST FAN IN HVAC ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:48 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-30-PR-PID-309 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-METHANOL CLOSE DRAIN SYSTEM & SODA DOSING UNIT | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:44 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-10-PI-ISO-6800 | 01 | U/G ISOMETRIC DRAWING OF AREA-68 | DE | IFC-WH | PI | PS-OT-T-0647 | 2018-07-15 |  | No | 659 | 1204-Owner-v | 2018-07-16 10:12 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-07-21 | 2018-08-04 | MT-PS-9609-CS-098-R | InProgress | 90%
1204-10-QC-SOI-202S | 00 | SCOPE OF INSPECTION FOR STEAM SUPER HEATERS AND TRANSFER LINES OF WASTE HEAT BOILER | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PI-MTO-422 | 00 | MATERIAL TAKE OFF FOR PAINT FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0944 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:43 | MTO | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PI-REQ-417 | 00 | REQUISITION FOR PIPE FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:19 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-20-ST-DWG-212 | 02 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/STEEL STR. (FRAMES II) | DE | IFC-WH | ST | PS-OT-T-0812 | 2019-06-26 |  | No | 313 | 1204-Owner-v | 2019-07-01 10:59 | CDW | 2019-06-26 | 0 | 0 | 0 | 2019-06-26 |  |  | complete | 100%
1204-30-ST-DWG-341 | 02 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / FDN. (G.A. & R.C.) | DE | IFC-WH | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 07:47 | CDW | 2014-01-04 | 0 | 0 | 0 | 2014-01-04 |  |  | complete | 100%
1204-90-ST-DWG-907 | 01 | CONTROL ROOM & LABORATORY / FDN.. OF BLAST PART (G.A.& DETAILS) | DE | IFC | ST | PS-TM-T-0255 | 2021-09-13 |  | No | -497 | 1204-TKT-COLANGELI | 2013-09-27 11:08 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-90-ST-DWG-940 | 02 | SUBSTATION / BEAMS , WALLS & COLUMNS (G.A. PLAN & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 12:12 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-00-IN-MSS-611 | 01 | MATERIAL STANDARD SPECIFICATION FOR MASS FLOW METER | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:06 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-MC-MSS-010 | 00 | Matreial Standard Specification for Diesel Engine and Generators | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-04-15 14:19 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-SLD-007 | 01 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR - MS-SWB3A,B-05 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:57 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:26 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2018-01-20 | MT-PS-9609-CS-008 | InProgress | 80%
1204-90-EL-SLD-039 | 01 | LABORATORY EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:40 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:43 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-REQ-158 | 00 | REQUISITION FOR SAFETY SHOWER AND EYE WASH | DE | IFI | HSE | PS-OT-T-0085 | 2015-08-02 |  | No | 1737 | 1204-Owner-v | 2015-08-03 09:27 | REQ | 2020-12-22 | 0 | 0 | 2020-12-31 | 2015-08-02 | 2015-08-24 | MT-PS-9301-CS-010 | InProgress | 90%
1204-84-HS-LST-001 | 01 | EQUIPMENT LIST FOR EFFLUENT WATER TREATMENT UNIT | DE | IFR | HSE | PS-OT-T-0853 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:50 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2020-02-12 | MT-PS-9301-CS-0268 | InProgress | 90%
1204-90-HS-DWG-003 | 03 | FIRE & GAS ALARM LAYOUT FOR CONTROL ROOM | DE | IFE | HSE | PS-OT-T-0714 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-12 08:54 | EDW | 2018-11-14 | 0 | 0 | 0 | 2018-11-14 |  |  | complete | 100%
1204-00-IN-LST-002 | 01 | FCS I/O COUNT | DE | IFR | IN | PS-OT-T-0902 | 2020-02-19 |  | No | 75 | 1204-Owner-v | 2020-02-25 17:00 | LIST | 2020-04-14 | 0 | 0 | 2020-04-14 | * |  |  | InProgress | 90%
1204-00-IN-REQ-607 | 00 | REQUISITION FOR RUPTURE DISCS | DE | IFI | IN | PS-OT-T-0927 | 2020-03-07 |  | No | 58 | 1204-Owner-v | 2020-03-09 09:04 | REQ | 2020-07-07 | 0 | 0 | 2020-07-20 | * | 2020-03-26 | MT-PS-9609-CS-0323 | InProgress | 90%
1204-64-PR-PID-643 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR WATER POLISHING SYSTEM (3 OF 3) | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:29 | EDW | 2017-02-23 | 0 | 0 | 0 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | complete | 100%
1204-00-ST-DWG-062 | 03 | PIPE RACK ZONE 9 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0143 | 2015-12-06 |  | No | 1611 | 1204-Owner-v | 2015-12-08 16:21 | CDW | 2015-12-13 | 0 | 0 | 0 | 2015-12-13 | 2015-12-14 | MT-PS-9301-CS-054 | complete | 100%
1204-10-ST-DWG-152 | 03 | REFORMER (A.P.H.) / FDN. (G.A.) | DE | IFC | ST | PS-OT-T-0817 | 2019-07-22 |  | No | 287 | 1204-Owner-v | 2019-07-24 09:35 | CDW | 2019-07-24 | 0 | 0 | 0 | 2019-07-24 |  |  | complete | 100%
1204-20-ST-DWG-210 | 01 | STRUCTURE "A" & STRUCTURE "M" / COMBINED FDN.(R.C. & DETAILS II) | DE | IFC | ST | PS-OT-T-0691 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-09-29 15:07 | CDW | 2018-09-29 | 0 | 0 | 0 | 2018-09-29 |  |  | complete | 100%
1204-90-ST-DWG-957 | 01 | SUBSTATION / INSERT PLATES I | DE | IFC | ST | TM-OT-9001-T-0407 | 2014-11-04 |  | No | 2008 | 1204-TKT-COLANGELI | 2014-11-03 12:02 | CDW | 2014-11-04 | 0 | 0 | 0 | 2014-11-04 | 2014-11-10 | MT-TM-9301-CS-003 | complete | 100%
1204-90-EL-DWG-030 | 01 | SUBSTATION COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:02 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:38 | CDW | 2014-01-29 | 0 | 0 | 0 | 2014-01-29 |  |  | complete | 100%
1204-90-EL-DWG-110 | 02 | CONTROL ROOM & LABORATORY BUILDING LIGHTING LAYOUT | DE | IFC | EL | TM-OT-9001-T-0439 | 2015-02-11 | 2015-03-02 17:53 | Yes | 5 | 1204-TKT-COLANGELI | 2015-02-10 18:54 | CDW | 2015-02-11 | 0 | 0 | 0 | 2015-02-11 |  |  | complete | 100%
1204-90-ST-DWG-1030 | 03 | WAREHOUSE / FDN.. (G.A.& DETAILS) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:56 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-00-QC-SOI-204A | 00 | SCOPE OF INSPECTION FOR PRESSURE VESSELS (GROUP I) | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-30-RE-DSH-039 | 01 | DATA SHEET FOR TOPPING COLUMN REFLUX PUMPS (P-3001 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:25 | DSH | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 |  |  | InProgress | 80%
1204-64-RE-DSH-053 | 00 | DATA SHEET FOR SULFURIC ACID UNLOADING PUMP (P-6405) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-08 11:41 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-90-HV-DSH-020 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:36 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-90-HV-DSH-022 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:38 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-90-ST-DWG-908 | 01 | CONTROL ROOM & LABORATORY / FDN.. OF BLAST PART (R.C. DETAILS I) | DE | IFC | ST | PS-TM-T-0255 | 2021-09-13 |  | No | -497 | 1204-TKT-COLANGELI | 2013-09-27 11:21 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-90-ST-DWG-1050 | 01 | FIRE STATION. / FDN. (G.A. & R.C.) | DE | IFR | ST | PS-OT-T-0959 | 2020-04-30 |  | No | 4 | 1204-Owner-v | 2020-05-03 15:36 | CDW | 2012-10-09 | 0 | 0 | 0 | 2012-10-09 |  |  | InProgress | 80%
1204-90-ST-MTO-1093 | 00 | MATERIAL TAKE OFF FOR GUARD HOUSE / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:28 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-008 | complete | 100%
1204-40-RE-DSH-028 | 00 | Data Sheet for MP Boiler Feed Water Pumps P-4002 A/B/C | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:54 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-40-PV-DSH-225 | 01 | MECHANICAL DATA SHEET FOR MP CONDENSATE DRUM (D-4004) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 17:15 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-00-QC-SOI-205A | 01 | SCOPE OF INSPECTION FOR PACKING & TRAYS & INTERNALS & DEMISTERS | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 | 1204-Owner-v | 2020-05-07 09:59 | SCOPE | 2020-05-07 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-20-HM-DSH-233 | 00 | MECHANICAL DATA SHEET FOR SYNTHESIS TRIM CONDENSER (E-2003A/B) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 11:44 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | InProgress | 80%
1204-90-HV-DSH-011 | 00 | DATA SHEET FOR AIR CONDENSER FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:01 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-ST-DWG-919 | 01 | CONTROL ROOM & LABORATORY / PLUMBING LAYOUT ( GROUND FLOOR PLAN ) | DE | IFC | ST | TM-OT-9001-T-0394 | 2014-09-15 |  | No | 2058 | 1204-TKT-COLANGELI | 2014-09-12 12:19 | CDW | 2014-09-15 | 0 | 0 | 0 | 2014-09-15 | 2014-09-24 | MT-OT-9301-CS-025 | complete | 100%
1204-90-ST-DWG-990 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / BLOCK & JOIST | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:52 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-996 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / PLUMBING LAYOUT ( FIRST FLOOR PLAN ) | DE | IFR | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 15:05 | CDW | 2020-04-30 | 0 | 0 | 2020-04-30 | 2013-01-10 |  |  | InProgress | 80%
1204-90-ST-DWG-995 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / PLUMBING LAYOUT ( GROUND FLOOR PLAN ) | DE | IFR | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 14:32 | CDW | 2020-04-30 | 0 | 0 | 2020-04-30 | 2013-01-10 |  |  | InProgress | 80%
1204-62-PV-DSH-207 | 01 | MECHANICAL DATA SHEET FOR EMERGENCY INSTRUMENT AIR STORAGE (D-6202) | DE | IFE | MD | TM-OT-9001-T-0149 | 2012-09-05 |  | No | 2798 | 1204-Owner-v | 2015-09-16 17:57 | DSH | 2012-09-05 | 0 | 0 | 0 | 2012-09-05 |  |  | complete | 100%
1204-40-RE-DSH-027 | 00 | Data Sheet for HP Boiler Feed Water Pumps P-4001 A/B/C | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:54 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-00-EL-REQ-516 | 00 | REQUISITION FOR RADIO SYSTEM | DE | IFI | EL | PS-OT-T-0961 | 2020-05-05 |  | No | -1 | 1204-Owner-v | 2020-05-07 13:16 | REQ | 2020-06-23 | 0 | 0 | 2020-07-06 |  |  |  | InProgress | 90%
1204-63-PR-DSH-143 | 00 | Process Instrument Data Sheet for Level Switches | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-64-PR-DSH-139 | 00 | Process Instrument Data Sheet for Restriction Orifice | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-00-HS-REQ-157 | 01 | REQUISITION FOR DELUGE VALVES | DE | IFI | HSE | PS-OT-T-0850 | 2019-12-24 |  | No | 132 | 1204-Owner-v | 2019-12-29 09:12 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | * |  | MT-PS-9301-CS-0254 | InProgress | 90%
1204-00-IN-DSH-627 | 01 | DATA SHEET FOR JUNCTION BOXES AND CABLE GLANDS | DE | IFE | IN | PS-OT-T-0133 | 2015-11-17 |  | No | 1630 | 1204-Owner-v | 2015-11-18 09:26 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2015-11-28 | MT-PS-9301-CS-046 | complete | 100%
1204-00-IN-REQ-626 | 00 | REQUISITION FOR MOTOR OPERATED VALVES | DE | IFI | IN | PS-OT-T-0187 | 2016-01-19 |  | No | 1567 | 1204-Owner-v | 2016-01-21 12:04 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | 2016-01-24 | 2016-02-07 | MT-PS-9301-CS-101 | InProgress | 90%
1204-00-PI-MTO-407A | 01 | MATERIAL TAKE OFF FOR STRAINER (MTO I) | DE | IFE | PI | PS-OT-T-0954 | 2020-04-25 |  | No | 9 | 1204-Owner-v | 2020-04-28 09:31 | LIST | 2020-03-01 | 0 | 0 | 2020-03-30 | * | 2020-04-07 | MT-PS-9609-CS-0327 | complete | 100%
1204-00-PI-MTO-461A | 04 | MATERIAL TAKE OFF FOR U/G PIPES & FITTINGS (MTO I) | DE | IFE | PI | PS-OT-T-0470 | 2017-08-26 |  | No | 982 | 1204-Owner-v | 2017-08-30 09:58 | LIST | 2017-08-30 | 0 | 0 | 0 | 2017-08-30 | 2017-10-23 | MT-PS-9301-CS-260 | complete | 100%
1204-20-PR-PID-207 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-PURGE GAS WASHING / CRUDE MeOH | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:21 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-22-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR MACHINERY COOLING WATER SYSTEM | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:11 | LIST | 2020-03-26 | 0 | 0 | 2020-05-06 | * |  |  | InProgress | 90%
1204-00-QC-SOI-213A | 01 | SCOPE OF INSPECTION FOR CARBON STEEL STORAGE TANKS | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PR-UDD-014 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR MACHINERY COOLING WATER DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:23 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-90-ST-DWG-991 | 01 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / STEEL PARTS | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:53 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-HV-DWG-005 | 01 | CONTROL ROOM - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFC | HV | TM-OT-9001-T-0278 | 2013-05-17 |  | No | 2544 | 1204-TKT-COLANGELI | 2013-05-17 11:42 | CDW | 2013-05-17 | 0 | 0 | 0 | 2013-05-17 |  |  | complete | 100%
1204-90-HV-DWG-012 | 02 | LABORATORY - SECTION OF DUCTING | DE | IFC | HV | PS-OT-T-0007 | 2015-03-11 |  | No | 1881 | 1204-Owner-v | 2015-03-17 11:19 | CDW | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DID-024 | 03 | SUBSTATION - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | TM-OT-9001-T-0441 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:16 | CDW | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-00-ST-DWG-072 | 04 | PIPE RACK ZONE 11 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0411 | 2017-01-21 |  | No | 1199 | 1204-Owner-v | 2017-01-22 11:40 | CDW | 2017-01-23 | 0 | 0 | 0 | 2017-01-23 |  |  | complete | 100%
1204-90-HV-DSH-068 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR TRAINING | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:44 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-00-QC-CSS-802 | 00 | CONSTRUCTION STANDARD SPECIFICATION FOR NON DESTRUCTIVE TESTING OF PIPING | DE | IFC | QC | PS-OT-T-0600 | 2018-04-28 |  | No | 737 | 1204-Owner-v | 2018-04-28 15:57 | SPEC | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-20-PI-APL-2600 | 01 | PIPING PLAN AREA-26 | DE | IFC-WH | PI | PS-OT-T-0671 | 2018-08-25 |  | No | 618 | 1204-Owner-v | 2018-08-28 18:17 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-30-PI-ISO-2800 | 01 | A/G ISOMETRIC DRAWING OF AREA-28 | DE | IFC-WH | PI | PS-OT-T-0666 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-17 09:41 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-63-PI-ISO-1800 | 00 | A/G ISOMETRIC DRAWING OF AREA-18 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-64-PI-ISO-3100 | 00 | A/G ISOMETRIC DRAWING OF AREA-31 | DE | IFR | PI | PS-OT-T-0324 | 2016-08-23 |  | No | 1350 | 1204-Owner-v | 2016-08-24 15:16 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-08-29 |  |  | InProgress | 80%
1204-61-PR-REQ-104 | 02 | REQUISITION FOR AIR SEPARATION UNIT (ASU) (PU-6101) | DE | IFP | PR | PS-OT-T-0839 | 2019-11-28 |  | No | 158 | 1204-Owner-v | 2019-12-03 11:24 | REQ | 2019-11-28 | 0 | 0 | 0 | 2019-11-28 | 2020-01-20 | MT-PS-9301-CS-0243 | complete | 100%
1204-10-HM-REQ-251C | 01 | REQUSITION FOR CONVECTION COILS FABRICATION , MODULARIZATION& FINING AND CAST PARTS SUPPLY OF CONVECTION SECTION TUBE SHEETS | DE | IFP | MD | PS-OT-T-0867 | 2020-01-08 |  | No | 117 | 1204-Owner-v | 2020-01-09 13:43 | REQ | 2019-10-01 | 0 | 0 | 2019-10-14 | * | 2020-01-03 | MT-PS-9609-CS-0261 | complete | 100%
1204-64-PR-DSH-131 | 00 | Process Instrument Data Sheet for Orifice Plate and Flanges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-90-HV-DSH-043 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR PRAYER ROOM IN ADMINISTRATION | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:41 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-71-PR-LST-002 | 00 | LINE LIST FOR DAILY METHANOL STORAGE TANKS | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:14 | LIST | 2020-03-26 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-00-ST-DWG-026 | 01 | PIPE RACK ZONE 3 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0032 | 2015-05-04 |  | No | 1827 | 1204-Owner-v | 2015-05-05 11:38 | CDW | 2015-05-04 | 0 | 0 | 0 | 2015-05-04 |  |  | complete | 100%
1204-00-ST-DWG-061 | 02 | PIPE RACK ZONE 9 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0122 | 2015-10-26 |  | No | 1652 | 1204-Owner-v | 2015-10-27 08:59 | CDW | 2015-10-28 | 0 | 0 | 0 | 2015-10-28 | 2015-10-31 | MT-PS-9301-CS-029 | complete | 100%
1204-90-ST-DWG-1032 | 02 | WAREHOUSE / G.A. , FURNITURE PLAN & SECTIONS | DE | IFC | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 17:52 | CDW | 2013-01-10 | 0 | 0 | 0 | 2013-01-10 |  |  | complete | 100%
1204-90-ST-DWG-911 | 03 | CONTROL ROOM & LABORATORY / OPENING & SLEEVE PLAN | DE | IFC-WH | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:45 | CDW | 2014-08-13 | 0 | 0 | 0 | 2014-08-13 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-00-HM-REQ-261A | 00 | REQUISITION FOR PLATE TYPE HEAT EXCHANGER | DE | IFI | MD | TM-OT-9001-T-0215 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 17:21 | REQ | 2020-02-18 | 0 | 0 | 2020-03-02 | 2012-12-11 |  |  | InProgress | 90%
1204-90-ST-DWG-1060 | 01 | FIRE STATION / BEAMS (R.C. DETAILS II ) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 15:03 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-972 | 04 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING/ FURNITURE PLAN FOR FIRST FLOOR PLAN | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-03 10:02 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 0 | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-90-ST-DWG-1019 | 01 | WORK SHOP / FRAMES I | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 12:50 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-905 | 03 | CONTROL ROOM & LABORATORY / SECTIONS & DETAILS | DE | IFC | ST | TM-OT-9001-T-0377 | 2014-06-11 |  | No | 2154 | 1204-TKT-COLANGELI | 2014-06-11 11:59 | CDW | 2014-06-11 | 0 | 0 | 0 | 2014-06-11 | 2014-07-12 | MT-OT-9301-CS-012 | complete | 100%
1204-90-ST-DWG-964 | 00 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (R.C. PLAN & DETAILS IV ) | DE | IFC | ST | PS-OT-T-0952 | 2020-04-21 |  | No | 13 | 1204-Owner-v | 2020-04-22 11:24 | DWG | 2020-04-21 | #N/A | #N/A | #N/A | 2020-04-21 |  |  | complete | 100%
1204-63-PR-DSH-132 | 00 | Process Instrument Data Sheet for On / Off Valves | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-63-PR-REQ-108 | 01 | REQUISITION FOR COOLING TOWER | DE | IFP | PR | TM-OT-9001-T-0447 | 2015-03-05 |  | No | 1887 | 1204-TKT-COLANGELI | 2015-03-04 13:47 | REQ | 2015-03-05 | 0 | 0 | 0 | 2015-03-05 |  |  | complete | 100%
1204-64-PR-DSH-136 | 00 | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE GAUGES | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-20-PR-PID-201 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS GAS COMPRESSION | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-06 13:50 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-22-PR-DSH-136 | 00 | Process Instrument Data Sheet for Level Gauges | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-30-PR-PID-305 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-SECOND REFINING COLUMN | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:44 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-62-PR-DSH-138 | 00 | PROCESS INSTRUMENT DATASHEET FOR TEMPERATURE GAUGES | BE | IFR | PR | TM-OT-9001-T-0142 | 2012-08-28 |  | No | 2806 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-08-28 |  |  | InProgress | 80%
1204-63-PR-DSH-138 | 00 | Process Instrument Data Sheet for Pressure Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-90-ST-DWG-950 | 01 | SUBSTATION / STEEL STRUCTURE (PLAN) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-21 13:59 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 80%
1204-00-QC-SOI-261A | 00 | Scope of Inspection for PLATE TYPE HEAT EXCHANGER | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-00-QC-SOI-502 | 01 | SCOPE OF INSPECTION FOR MEDIUM VOLTAGE SWITCHGEARS | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-932 | 02 | SUBSTATION / FDN. (R.C. DETAILS II ) | DE | IFC | ST | TM-OT-9001-T-0345 | 2014-01-07 |  | No | 2309 | 1204-TKT-COLANGELI | 2014-01-07 13:00 | CDW | 2014-01-07 | 0 | 0 | 0 | 2014-01-07 |  |  | complete | 100%
1204-90-ST-DWG-958 | 01 | SUBSTATION / PLUMBING LAYOUT & DETAILS | DE | IFC | ST | TM-OT-9001-T-0395 | 2014-09-24 |  | No | 2049 | 1204-Owner-v | 2014-09-22 13:57 | CDW | 2014-09-24 | 0 | 0 | 0 | 2014-09-24 | 2014-09-24 | MT-OT-9301-CS-026 | complete | 100%
1204-90-ST-DWG-967 | 04 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (R.C. PLAN & DETAILS I ) | DE | IFC | ST | PS-OT-T-0952 | 2020-04-21 |  | No | 13 | 1204-Owner-v | 2020-04-22 11:22 | CDW | 2020-04-21 | 0 | 0 | 0 | 2020-04-21 |  |  | complete | 100%
1204-20-RE-DSH-026 | 01 | DATA SHEET FOR FIRST SATURATOR PUMPS (P-2003 A/B) | DE | IFR | MC | PS-OT-T-0314 | 2016-07-31 |  | No | 1373 | 1204-Owner-v | 2016-08-03 16:40 | DSH | 2016-07-31 | 0 | 0 | 0 | 2016-07-31 |  |  | InProgress | 80%
1204-00-PR-UDD-013 | 02 | UTILITY DISTRIBUTION DIAGRAM FOR COOLING WATER DISTRIBUTION SYSTEM | DE | IFC-WH | PR | PS-OT-T-0575 | 2018-03-06 |  | No | 790 | 1204-Owner-v | 2018-04-07 09:13 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2018-04-12 | 2018-03-07 | MT-PS-9609-CS-043 | InProgress | 90%
1204-63-PR-DSH-141 | 00 | Process Instrument Data Sheet for Pressure Switches | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-00-IN-DWG-012 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 12) | DE | IFR | IN | PS-OT-T-0189 | 2016-01-23 |  | No | 1563 | 1204-Owner-v | 2016-01-24 08:45 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-01-27 | 2016-01-30 | MT-PS-9301-CS-099 | InProgress | 80%
1204-90-ST-DWG-1034 | 02 | WAREHOUSE / FDN.. (R.C. DETAILS II) | DE | IFC | ST | PS-TM-T-0252 | 2017-09-13 |  | No | 964 | 1204-TKT-COLANGELI | 2013-09-26 14:04 | CDW | 2017-09-13 | 0 | 0 | 0 | 2017-09-13 |  |  | complete | 100%
1204-90-ST-DWG-1037 | 01 | WAREHOUSE/ FRAMINGS PLAN | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:02 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-ST-DWG-1063 | 00 | FIRE STATION / STEEL PARTS | DE | IFR | ST | TM-OT-9001-T-0421 | 2014-12-10 |  | No | 1972 | 1204-TKT-COLANGELI | 2014-12-10 14:36 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2014-12-10 | 2014-12-30 | MT-TM-9301-CS-030 | InProgress | 80%
1204-90-ST-DWG-1080 | 02 | GUARD HOUSE / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0377 | 2014-06-11 |  | No | 2154 | 1204-TKT-COLANGELI | 2014-06-11 11:41 | CDW | 2014-06-11 | 0 | 0 | 0 | 2014-06-11 | 2014-07-12 | MT-OT-9301-CS-012 | complete | 100%
1204-40-PV-DSH-235 | 01 | MECHANICAL DATA SHEET FOR PROCESS CONDENSATE STRIPPER COLUMN (T-4001) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:24 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | complete | 100%
1204-20-PV-DSH-214 | 02 | MECHANICAL DATA SHEET FOR CRUDE METHANOL SEPARATOR (D-2001) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 14:24 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-30-PV-DSH-216 | 02 | MECHANICAL DATA SHEET FOR TOPPING COLUMN REFLUX DRUM (D-3001) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:29 | DSH | 2019-11-13 | 0 | 0 | 0 | 0 |  |  | complete | 100%
1204-90-HV-DSH-015 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR LOCKER & SHOWER IN LABORATORY | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:16 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-ST-DWG-059 | 01 | PIPE RACK ZONE 9 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0034 | 2015-05-06 |  | No | 1825 | 1204-Owner-v | 2015-05-07 09:17 | CDW | 2015-05-06 | 0 | 0 | 0 | 2015-05-06 |  |  | complete | 100%
1204-00-ST-TBA-740A | 00 | TECHNICAL BID ANALYSIS FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART A) | DE | IFE | ST | PS-OT-T-0370 | 2016-11-19 |  | No | 1262 | 1204-Owner-v | 2016-11-22 13:49 | TBA | 2016-11-25 | 0 | 0 | 0 | 2016-11-25 |  |  | complete | 100%
1204-20-ST-DWG-244 | 02 | C-2001 / FDN. (G.A. & R.C.) | DE | IFC-WH | ST | PS-OT-T-0642 | 2018-07-08 |  | No | 666 | 1204-Owner-v | 2018-07-10 09:51 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-08-06 | 2018-07-10 | MT-PS-9609-CS-094 | complete | 100%
1204-90-ST-DWG-918 | 05 | CONTROL ROOM & LABORATORY / WALLS (G.A. , R.C. & DETAILS I ) | DE | IFC | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:17 | CDW | 2014-08-20 | 0 | 0 | 0 | 2014-08-20 |  | MT-OT-9301-CS-018 | complete | 100%
1204-90-ST-MTO-1046 | 01 | MATERIAL TAKE OFF FOR WAREHOUSE / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0408 | 2014-11-06 |  | No | 2006 | 1204-TKT-COLANGELI | 2014-11-06 13:50 | LIST | 2014-11-06 | 0 | 0 | 0 | 2014-11-06 | 2014-12-30 | MT-TM-9301-CS-027 | complete | 100%
1204-30-PV-DSH-219 | 02 | MECHANICAL DATA SHEET FOR SECOND REFINING COLUMN REFLUX DRUM (D-3004) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:28 | DSH | 2019-11-13 | 0 | 0 | 0 | 0 |  |  | complete | 100%
1204-64-ST-DWG-714 | 02 | TK-6402 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0364 | 2014-05-06 |  | No | 2190 | 1204-TKT-COLANGELI | 2014-05-06 12:34 | CDW | 2014-05-06 | 0 | 0 | 0 | 2014-05-06 |  |  | complete | 100%
1204-00-HM-TBA-260 | 00 | TECHNICAL BID ANALYSIS FOR DOUBLE PIPE HEAT EXCHANGERS | DE | IFE | MD | PS-OT-T-0468 | 2017-08-19 |  | No | 989 | 1204-Owner-v | 2017-08-27 11:56 | TBA | 2017-08-22 | 0 | 0 | 0 | 2017-08-22 | 2017-09-25 | MT-PS-9301-CS-245 | complete | 100%
1204-30-HM-DSH-247 | 00 | MECHANICAL DATA SHEET FOR TOPPING COLUMN ADDITIONAL REBOILER (E-3013) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:29 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DSH-021 | 01 | DATA SHEET FOR AIR CONDENSER FOR SUBSTATION | DE | IFE | HV | PS-OT-T-0566 | 2018-02-25 |  | No | 799 | 1204-Owner-v | 2018-02-26 08:29 | DSH | 2018-02-26 | 0 | 0 | 0 | 2018-02-26 | 2018-03-04 | MT-PS-9609-CS-037 | complete | 100%
1204-90-HV-DSH-104 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR PRD IN AUXILIARY ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:50 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-90-HV-DSH-210 | 01 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR LABORATORY | DE | IFE | HV | PS-OT-T-0259 | 2016-05-10 |  | No | 1455 | 1204-Owner-v | 2016-05-14 16:06 | DSH | 2016-05-10 | 0 | 0 | 0 | 2016-05-10 |  |  | complete | 100%
1204-90-HV-DSH-107 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR LOUVER IN BATTERY ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:54 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-90-HS-LST-006 | 01 | SAFETY EQUIPMENT LIST FOR FIRE STATION | DE | IFC-WH | HSE | PS-OT-T-0101 | 2015-09-13 |  | No | 1695 | 1204-Owner-v | 2015-09-14 09:46 | LIST | 2015-09-13 | 0 | 0 | 0 | 2015-09-13 | 2015-10-31 | MT-PS-9301-CS-035 | complete | 100%
1204-90-HS-LST-007 | 01 | SAFETY EQUIPMENT LIST FOR GUARD HOUSE | DE | IFC-WH | HSE | PS-OT-T-0101 | 2015-09-13 |  | No | 1695 | 1204-Owner-v | 2015-09-14 09:47 | LIST | 2015-09-13 | 0 | 0 | 0 | 2015-09-13 | 2015-10-31 | MT-PS-9301-CS-035 | complete | 100%
1204-90-HS-LST-009 | 02 | SAFETY EQUIPMENT LIST FOR WAREHOUSE | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:56 | LIST | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-10-QC-SOI-251B | 00 | SCOPE OF INSPECTION FOR STEEL WORK SUPPLY AND SHOP PREFABRICATION (FURNACE) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 | 1204-Owner-v | 2020-05-07 09:58 | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-64-PI-LST-3000 | 00 | A/G ISOMETRIC LIST OF AREA-30 | DE | IFR | PI | PS-OT-T-0071 | 2015-07-05 |  | No | 1765 | 1204-Owner-v | 2015-07-05 16:02 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2015-07-05 | 2015-08-29 | MT-PS-9301-CS-011 | InProgress | 80%
1204-90-HV-DSH-003 | 03 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:16 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-90-HV-DSH-203 | 02 | DATA SHEET FOR NON RETURN DAMPER FOR CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:56 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DSH-026 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR PDCS CO2 REMOVAL IN SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:52 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-ST-DWG-077 | 01 | PIPE RACK ZONE 12 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0929 | 2020-03-07 |  | No | 58 | 1204-Owner-v | 2020-03-09 09:02 | CDW | 2020-03-31 | 0 | 0 | 2020-05-18 | * | 2020-03-25 | MT-PS-9609-CS-0317 | complete | 100%
1204-00-HS-LST-006 | 00 | EQUIPMENT LIST WITH HAZARDOUS CLASSIFICATION FOR UTILITY & OFFSITE | DE | IFR | HSE | TM-OT-9001-T-0268 | 2013-05-02 |  | No | 2559 | 1204-Owner-v | 2015-04-19 13:06 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | 2013-05-02 |  |  | InProgress | 90%
1204-90-HV-DSH-024 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR MV SGR. CO2 REMOVAL IN SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:48 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-ST-DWG-1009 | 01 | SUBSTATION / MISCELLANEOUS DETAILS | DE | IFC | ST | TM-OT-9001-T-0368 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 14:48 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-30-PI-ISO-2300 | 01 | A/G ISOMETRIC DRAWING OF AREA-23 | DE | IFC-WH | PI | PS-OT-T-0651 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-28 13:29 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * | 2018-08-04 | MT-PS-9609-CS-105 | InProgress | 90%
1204-30-PI-UPL-6700 | 02 | UNDER GROUND PIPING PLAN AREA-67 | DE | IFC-WH | PI | PS-OT-T-0650 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-29 09:23 | CDW | 2018-07-31 | 0 | 0 | 0 | 2018-07-31 | 2018-07-29 | MT-PS-9609-CS-102 | InProgress | 90%
1204-00-PI-TBA-461A | 02 | TECHNICAL BID ANALYSIS FOR U/G PIPES & FITTINGS(MTO I) | DE | IFE | PI | PS-OT-T-0350 | 2016-10-10 |  | No | 1302 | 1204-Owner-v | 2016-10-15 13:44 | TBA | 2016-10-19 | 0 | 0 | 0 | 2016-10-19 | 2016-10-23 | MT-PS-9301-CS-192 | complete | 100%
1204-71-PI-LST-7400 | 03 | U/G ISOMETRIC LIST OF AREA-74 | DE | IFC-WH | PI | PS-OT-T-0598 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:31 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-03 |  |  | InProgress | 90%
1204-72-PI-LST-7300 | 03 | U/G ISOMETRIC LIST OF AREA-73 | DE | IFC-WH | PI | PS-OT-T-0599 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:38 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-03 |  |  | complete | 100%
1204-00-QC-SOI-461A | 00 | SCOPE OF INSPECTION FOR PIPE & FITTINGS A (UG) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-IN-MSS-602 | 00 | MATERIAL STANDARD SPECIFICATION FOR EMERGENCY SHUTDOWN SYSTEM(ESD) | DE | IFR | IN | PS-OT-T-371 | 2016-11-23 |  | No | 1258 | 1204-Owner-v | 2016-11-26 11:15 | SPEC | 2020-03-30 | 0 | 0 | 2020-03-30 | 2017-04-18 | 2017-05-16 | MT-PS-9301-CS-214-1 | InProgress | 80%
1204-04-EL-SLD-064 | 00 | SINGLE LINE DIAGRAM FOR 04-LP-01 | DE | IFR | EL | PS-OT-T-0297 | 2016-06-25 | 2016-07-21 14:35 | Yes | 12 | 1204-Owner-v | 2016-06-28 17:31 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-07-02 | 2016-06-25 | MT-PS-9301-CS-169 | InProgress | 80%
1204-30-ST-DWG-316 | 01 | STRUCTURE "G" FOR E-3013 / FDN. & STRUCTURE (PLAN & SECTIONS & DETS.) | DE | IFC | ST | PS-OT-T-0295 | 2016-06-22 |  | No | 1412 | 1204-Owner-v | 2016-06-25 10:31 | CDW | 2016-06-22 | 0 | 0 | 0 | 2016-06-22 | 2016-06-25 | MT-PS-9301-CS-166 | complete | 100%
1204-00-ST-DWG-1145 | 02 | VB-6303 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0571 | 2018-03-05 |  | No | 791 | 1204-Owner-v | 2018-03-12 14:57 | CDW | 2018-03-13 | 0 | 0 | 0 | 2018-03-13 | 2018-03-07 | MT-PS-9609-CS-041-R | complete | 100%
1204-61-ST-DWG-552 | 00 | ASU (AE-6187) / CONCRETE STRUCTURE (R.C. DETAILS) | DE | IFR | ST | PS-OT-T-0653 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-30 17:04 | CDW | 2018-07-23 | 0 | 0 | 0 | 2018-07-23 | 2018-08-04 | MT-PS-9609-CS-104 | InProgress | 80%
1204-10-ST-DWG-156 | 01 | REFORMER (VERTICAL CONVECTION SECTION) FDN. (G.A.) | DE | IFC | ST | PS-OT-T-0675 | 2018-09-05 |  | No | 607 | 1204-Owner-v | 2018-09-11 13:55 | CDW | 2018-09-05 | 0 | 0 | 0 | 2018-09-05 |  |  | complete | 100%
1204-10-HM-REQ-251R | 00 | REQUSITION FOR SUPPLY OF REFRACTORIES FOR PRIMARY REFORMER PACKAGE (INCLUDING ANCHORS AND DESIGN/LAYOUT DRAWINGS) | DE | IFI | MD | PS-OT-T-0801 | 2019-06-09 |  | No | 330 | 1204-Owner-v | 2019-06-12 10:20 | REQ | 2020-06-09 | 0 | 0 | 2020-06-22 | * |  |  | InProgress | 90%
1204-90-ST-DWG-963 | 02 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (R.C. PLAN & DETAILS III ) | DE | IFC | ST | PS-OT-T-0956 | 2020-04-27 |  | No | 7 | 1204-Owner-v | 2020-04-29 09:04 | DWG | 2020-04-27 | #N/A | #N/A | #N/A | 2020-04-27 |  |  | complete | 100%
1204-00-EL-REQ-527 | 00 | REQUISITION FOR LIGHTING POLES | DE | IFI | EL | PS-OT-T-0732 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:57 | REQ | 2020-09-17 | 0 | 0 | 2020-09-23 | * |  |  | InProgress | 90%
1204-72-RE-DSH-056 | 03 | DATA SHEET FOR CRUDE METHANOL TRANSFER PUMPS (P-7201 A/B/C) | DE | IFR | MC | PS-OT-T-0877 | 2020-02-03 |  | No | 91 | 1204-Owner-v | 2020-02-05 09:03 | DSH | 2020-02-03 | 0 | 0 | 0 | 2020-02-03 | 2020-02-27 | MT-PS-9301-CS-0263-1 | InProgress | 80%
1204-90-HV-DSH-101 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR EXHAUST FAN IN BATTERY ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:46 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-90-HV-DWG-025 | 03 | SUBSTATION - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFC | HV | TM-OT-9001-T-0441 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:18 | CDW | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-90-HV-DWG-091 | 01 | WAREHOUSE - HVAC SYSTEM LAYOUT | DE | IFC | HV | TM-OT-9001-T-0290 | 2013-06-07 |  | No | 2523 | 1204-TKT-COLANGELI | 2013-06-04 17:25 | CDW | 2013-06-07 | 0 | 0 | 0 | 2013-06-07 |  |  | complete | 100%
1204-90-HV-DID-064 | 02 | CLINIC AND TRAINING - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:33 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 | 2014-10-19 |  | complete | 100%
1204-90-HV-DSH-240 | 01 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR ADMINISTRATION | DE | IFE | HV | PS-OT-T-0259 | 2016-05-10 |  | No | 1455 | 1204-Owner-v | 2016-05-14 16:06 | DSH | 2016-05-10 | 0 | 0 | 0 | 2016-05-10 |  |  | complete | 100%
1204-00-ST-DWG-037 | 00 | PIPE RACK ZONE 5 / R.C. DETAILS | DE | IFR | ST | TM-OT-9001-T-0286 | 2013-06-05 |  | No | 2525 | 1204-TKT-COLANGELI | 2013-06-04 16:15 | CDW | 2020-06-03 | 0 | 0 | 2020-08-12 | 2013-06-05 |  |  | InProgress | 80%
1204-00-ST-DWG-043 | 02 | PIPE RACK ZONE 6 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0126 | 2015-11-04 |  | No | 1643 | 1204-Owner-v | 2015-11-05 10:14 | CDW | 2015-11-16 | 0 | 0 | 0 | 2015-11-16 | 2015-11-08 | MT-PS-9301-CS-040 | complete | 100%
1204-10-PV-TBA-202F | 02 | TECHNICAL BID ANALYSIS FOR STEAM DRUM, STEAM GENERATOR AND STEAM SUPER HEATER PACKAGE | DE | IFE | MD | PS-OT-T-0166 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:51 | TBA | 2019-12-17 | 0 | 0 | 2020-01-06 | 2016-01-06 | 2016-01-17 | MT-PS-9301-CS-088 | complete | 100%
1204-10-QC-SOI-202F | 00 | SCOPE OF INSPECTION FOR STEAM DRUM, STEAM GENERATOR AND STEAM SUPER HEATER PACKAGE | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-HS-DWG-006 | 00 | BLOCK DIAGRAM FOR FIRE/GAS ALARM & FIRE FIGHTING SYSTEM | DE | IFR | HSE | PS-OT-T-0713 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-06 16:32 | EDW | 2020-07-01 | 0 | 0 | 2020-07-01 | * |  |  | InProgress | 80%
1204-10-ST-DWG-163 | 01 | STRUCTURE FOR WHB, ATR, E-1003A/B & D-4001A/B / COMBINED FDN. (R.C. & DETAILS II) | DE | IFC | ST | PS-OT-T-0704 | 2018-10-21 |  | No | 561 | 1204-Owner-v | 2018-10-24 16:57 | CDW | 2018-10-21 | 0 | 0 | 0 | 2018-10-21 |  |  | complete | 100%
1204-30-PV-DSH-222 | 00 | Mechanical data sheet for second Condensate Separator (D-3007) | DE | IFR | MD | TM-OT-9001-T-0114 | 2012-06-13 |  | No | 2882 | 1204-Owner-v | 2015-09-16 17:47 | DSH | 2012-06-13 | 0 | 0 | 0 | 2012-06-13 |  |  | complete | 100%
1204-20-HM-DSH-234 | 00 | MECHANICAL DATA SHEET FOR BFW COOLER (E-2004) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 11:48 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DSH-004 | 03 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR BATTERY ROOM IN CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:16 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-90-HV-DSH-053 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR KITCHEN IN RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-10 13:19 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-ST-DWG-029 | 02 | PIPE RACK ZONE 4 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0402 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-29 16:00 | CDW | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 | 2014-11-11 | MT-TM-9301-CS-006 | complete | 100%
1204-00-QC-CSS-801 | 01 | CONSTRUCTION STANDARD SPECIFICATION FOR WELDING & HEAT TREATMENT OF PIPING | DE | IFC | QC | PS-OT-T-0600 | 2018-04-28 |  | No | 737 | 1204-Owner-v | 2018-04-28 15:55 | SPEC | 2018-04-28 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-IN-CAL-002 | 00 | CALCULATION SHEET FOR FLOW ELEMENTS | DE | IFR | IN | TM-OT-9001-T-0294 | 2013-07-01 |  | No | 2499 | 1204-Owner-v | 2015-09-16 16:56 | CAL | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-90-HV-DSH-083 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR TOILET IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:45 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-71-PI-APL-3300 | 00 | PIPING PLAN AREA-33 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-12 11:52 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-00-ST-DWG-1115 | 01 | PIPE CULVERT / R.C. DETAILS (II) | DE | IFC | ST | PS-OT-T-0022 | 2015-04-18 |  | No | 1843 | 1204-Owner-v | 2015-04-19 10:24 | CDW | 2015-04-18 | 0 | 0 | 0 | 2015-04-18 |  |  | complete | 100%
1204-00-PI-APL-4000 | 00 | PIPING PLAN AREA-40 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:02 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-61-PR-TBA-104 | 02 | TECHNICAL BID ANALYSIS FOR AIR SEPARATION UNIT (ASU) (PU-6101) | DE | IFE | PR | PS-OT-T-0783 | 2019-04-17 |  | No | 383 | 1204-Owner-v | 2019-04-18 10:09 | TBA | 2019-04-22 | 0 | 0 | 0 | 2019-04-22 |  |  | complete | 100%
1204-00-IN-DWG-040 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 40) | DE | IFR | IN | PS-OT-T-359 | 2016-11-12 |  | No | 1269 | 1204-Owner-v | 2016-11-16 11:14 | CDW | 2020-06-25 | 0 | 0 | 2020-06-25 | 2016-11-18 | 2016-11-26 | MT-PS-9301-CS-197-R | InProgress | 80%
1204-65-ST-DWG-725 | 01 | D-6501 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0389 | 2016-12-21 |  | No | 1230 | 1204-Owner-v | 2016-12-24 09:27 | CDW | 2016-12-21 | 0 | 0 | 0 | 2016-12-21 |  |  | complete | 100%
1204-90-HV-DSH-051 | 00 | DATA SHEET FOR AIR CONDENSER FOR RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-10 13:15 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DSH-072 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR BATH ROOM IN GUARD HOUSE | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:37 | DSH | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DWG-051 | 02 | RESTAURANT - DUCTING LAYOUT | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:44 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 |  |  | complete | 100%
1204-90-HV-DSH-084 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR STORE IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:45 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-00-ST-DWG-035 | 00 | PIPE RACK ZONE 5 / FDN. (G.A. & R.C.) | DE | IFR | ST | TM-OT-9001-T-0286 | 2013-06-05 |  | No | 2525 | 1204-TKT-COLANGELI | 2013-06-04 14:59 | CDW | 2020-06-03 | 0 | 0 | 2020-08-12 | * |  |  | InProgress | 80%
1204-00-ST-DWG-050 | 00 | PIPE RACK ZONE 7 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0087 | 2015-08-05 |  | No | 1734 | 1204-Owner-v | 2015-08-06 08:30 | CDW | 2015-08-05 | 0 | 0 | 0 | 2015-08-05 |  |  | complete | 100%
1204-20-PR-PID-208 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-HYDROGEN RECOVERY UNIT | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:21 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-90-HV-DSH-310 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 12:01 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-ST-DWG-1007 | 01 | CONTROL ROOM & LABORATORY / STAIRS | DE | IFC | ST | TM-OT-9001-T-0347 | 2014-01-22 |  | No | 2294 | 1204-Owner-v | 2015-09-16 18:22 | CDW | 2014-01-22 | 0 | 0 | 0 | 2014-01-22 |  |  | complete | 100%
1204-30-PI-ISO-2200 | 01 | A/G ISOMETRIC DRAWING OF AREA-22 | DE | IFC-WH | PI | PS-OT-T-0661 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-14 11:37 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-90-HV-DWG-053 | 01 | RESTAURANT - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | TM-OT-9001-T-0380 | 2014-07-01 |  | No | 2134 | 1204-TKT-COLANGELI | 2014-07-01 12:12 | CDW | 2014-07-01 | 0 | 0 | 0 | 2014-07-01 |  |  | complete | 100%
1204-90-HV-DWG-055 | 00 | RESTAURANT - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFE | HV | TM-OT-9001-T-0381 | 2014-07-03 |  | No | 2132 | 1204-TKT-COLANGELI | 2014-07-03 11:35 | CDW | 2014-07-03 | 0 | 0 | 0 | 2014-07-03 |  |  | complete | 100%
1204-90-HV-DSH-093 | 01 | DATA SHEET FOR SOUTH WALL TYPE EXHAUST FAN FOR GF TOILET IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:48 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DSH-055 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR KITCHEN IN RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-10 13:22 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-22-PI-LST-1900 | 00 | A/G ISOMETRIC LIST OF AREA-19 | DE | IFR | PI | PS-OT-T-0195 | 2016-02-13 |  | No | 1542 | 1204-Owner-v | 2016-02-15 11:27 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-02-20 |  |  | InProgress | 80%
1204-00-PI-REQ-462A | 01 | REQUISITION FOR U/G FLANGES(MTO I) | DE | IFP | PI | PS-OT-T-0404 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-06-10 11:08 | REQ | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-00-IN-DIG-005 | 01 | OVERAL CONTROL SYSTEM BLOCK DIAGRAM | DE | IFR | IN | PS-OT-T-480 | 2017-09-03 |  | No | 974 | 1204-Owner-v | 2017-09-04 09:27 | EDW | 2021-02-20 | 0 | 0 | 2021-02-20 | 2017-10-02 | 2017-10-02 | MT-PS-9301-CS-238-R | InProgress | 80%
1204-00-IN-MSS-601 | 00 | MATERIAL STANDARD SPECIFICATION FOR FIELDBUS CONTROL SYSTEM(FCS) | DE | IFR | IN | PS-OT-T-371 | 2016-11-23 |  | No | 1258 | 1204-Owner-v | 2016-11-26 11:11 | SPEC | 2020-03-30 | 0 | 0 | 2020-03-30 | 2017-04-18 | 2017-05-16 | MT-PS-9301-CS-214-1 | InProgress | 80%
1204-00-PV-TBA-201A | 00 | TECHNICAL BID ANALYSIS FOR REACTORS | DE | IFE | MD | PS-OT-T-0224 | 2016-03-16 |  | No | 1510 | 1204-Owner-v | 2016-03-16 15:32 | TBA | 2016-03-17 | 0 | 0 | 0 | 2016-03-17 | 2016-04-18 | MT-PS-9301-CS-127 | complete | 100%
1204-00-IN-DWG-036 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 36) | DE | IFR | IN | PS-OT-T-357 | 2016-11-02 |  | No | 1279 | 1204-Owner-v | 2016-11-09 09:51 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | 2016-11-11 | 2016-11-21 | MT-PS-9301-CS-195 | InProgress | 80%
1204-00-EL-MSS-508 | 01 | MATERIAL STANDARD SPECIFICATION FOR ELECTRICAL PANEL BOARDS | DE | IFE | EL | TM-OT-9001-T-0417 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:03 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 | 2014-12-31 | MT-TM-9301-CS-032 | complete | 100%
1204-00-EL-MSS-516 | 01 | MATERIAL STANDARD SPECIFICATION FOR RADIO SYSTEM | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:29 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-ESS-601 | 01 | ENGINEERING STANDARD SPECIFICATION FOR INSTRUMENTATION | DE | IFE | IN | PS-OT-T-0062 | 2015-06-16 |  | No | 1784 | 1204-Owner-v | 2015-06-17 15:24 | SPEC | 2015-06-16 | 0 | 0 | 0 | 2015-06-16 |  |  | complete | 100%
1204-71-PR-DBS-101 | 01 | BASIC ENGINEERING DESIGN BASIS FOR DAILY METHANOL STORAGE TANKS | BE/DE | IFE | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:12 | EDW | 2013-07-03 | 0 | 0 | 0 | 2013-07-03 |  |  | complete | 100%
1204-00-MC-MSS-004 | 00 | Matreial Standard Specification for Centrifugal Pumps | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-04-15 14:18 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-MSS-515 | 01 | MATERIAL STANDARD SPECIFICATION FOR ELECTRICAL HEAT TRACING | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:23 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 | 2014-12-31 | MT-TM-9301-CS-031 | complete | 100%
1204-00-EL-MSS-517 | 01 | MATERIAL STANDARD SPECIFICATION FOR VARIABLE SPEED DRIVES | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 12:32 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-00-IN-ESS-602 | 01 | ENGINEERING STANDARD SPECIFICATION FOR INSTRUMENT ACCESSIBILITY GUIDELINES | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:04 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-00-ST-SDG-764 | 00 | Standard Drawing for Road Cross Section Details | DE | IFR | ST | TM-OT-9001-T-0112 | 2012-06-13 |  | No | 2882 | 1204-Owner-v | 2015-08-27 11:59 | SPEC | 2020-03-30 | 0 | 0 | 2020-03-30 | * |  |  | InProgress | 80%
1204-00-ST-ESS-739 | 01 | ENGINEERING STANDARD SPECIFICATION FOR ROAD AND PAVEMENT | DE | IFC | ST | TM-OT-9001-T-0424 | 2014-12-19 |  | No | 1963 | 1204-TKT-COLANGELI | 2014-12-17 13:01 | SPEC | 2014-12-19 | 0 | 0 | 0 | 2014-12-19 |  |  | complete | 100%
1204-63-PR-DSH-101 | 02 | PROCESS DATA SHEET FOR COOLING TOWER (PU-6301) | BE | IFE | PR | PS-OT-T-0004 | 2015-03-03 |  | No | 1889 | 1204-Owner-v | 2015-06-15 10:07 | DSH | 2015-03-03 | 0 | 0 | 0 | 2015-03-03 |  |  | complete | 100%
1204-00-EL-DSH-5033 | 01 | DATA SHEET FOR LV SWITCHGEAR (MS-SWB3A,B-03) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:24 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:05 | DSH | 2020-05-12 | 0 | 0 | 2020-05-12 | 2018-01-27 | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-DWG-006 | 02 | OVERALL ROAD LIGHTING LAYOUT | DE | IFR | EL | PS-OT-T-0765 | 2019-03-13 |  | No | 418 | 1204-Owner-v | 2019-03-13 17:07 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | * |  |  | InProgress | 80%
1204-00-PI-ESS-405 | 01 | ENGINEERING STANDARD SPECIFICATION FOR PIPING DESIGN REQUIREMENT | DE | IFE | PI | TM-OT-9001-T-0370 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 13:55 | SPEC | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-64-PR-DSH-111 | 00 | Data Sheet For Caustic Transfer Pumps (P-6404 A/b) | BE | IFR | PR | TM-OT-9001-T-0011 | 2011-06-01 |  | No | 3260 | 1204-TKT-proietti | 2011-05-30 14:50 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2011-06-01 |  |  | InProgress | 80%
1204-00-HS-ESS-151 | 02 | ENGINEERING STANDARD SPECIFICATION FOR FIRE PROTECTION SYSTEM | DE | IFE | HSE | PS-OT-T-0024 | 2015-04-20 |  | No | 1841 | 1204-Owner-v | 2015-04-21 09:49 | SPEC | 2015-04-20 | 0 | 0 | 0 | 2015-04-20 |  |  | complete | 100%
1204-00-MC-MSS-008 | 00 | Matreial Standard Specification for Lubrication, Shaft Sealing and Control Oil Systems | DE | IFR | MC | TM-OT-9001-T-0133 | 2012-07-12 |  | No | 2853 | 1204-Owner-v | 2015-04-15 14:19 | SPEC | 2020-04-20 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 80%
1204-00-EL-CSH-003 | 03 | ELECTRICAL LOAD BALANCE SUMMARY | DE | IFR | EL | PS-OT-T-0585 | 2018-03-19 |  | No | 777 | 1204-Owner-v | 2018-03-26 09:52 | LIST | 2020-08-30 | 0 | 0 | 2020-08-30 | * | 2018-04-08 | MT-PS-9609-CS-054 | InProgress | 90%
1204-00-EL-DIG-004 | 02 | PAGING AND INTERCOM SYSTEM SPEECH CONNECTION DIAGRAM | DE | IFR | EL | PS-OT-T-0907 | 2020-02-23 |  | No | 71 | 1204-Owner-v | 2020-02-25 16:44 | CDW | 2020-04-20 | 0 | 0 | 2020-04-20 | * | 2020-02-29 | MT-PS-9609-CS-0285 | InProgress | 80%
1204-00-EL-DWG-002 | 00 | OVERALL HAZARDOUS AREA CLASSIFICATION DRAWING | DE | IFR | EL | PS-TM-T-0245 | 2013-08-03 | 2015-08-12 17:07 | Yes | 725 | 1204-TKT-COLANGELI | 2013-08-08 11:39 | DWG | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-07-EL-DWG-001 | 00 | POWER LAYOUT - AREA 07 | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 11:02 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:04 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2015-11-12 | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-90-EL-DWG-010 | 01 | SUBSTATION LIGHTING LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:43 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:58 | CDW | 2012-10-19 | 0 | 0 | 0 | 2012-10-19 |  |  | complete | 100%
1204-90-EL-DWG-330 | 01 | RESTAURANT BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 08:02 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:39 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-00-PI-LST-416 | 01 | PIPING ALLOWABLE NOZZLE LOADS FOR ROTARY EQUIPMENT | DE | IFE | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:00 | LIST | 2016-09-03 | 0 | 0 | 0 | 2016-09-03 |  |  | complete | 100%
1204-00-IN-MSS-612 | 01 | MATERIAL STANDARD SPECIFICATION FOR ORIFICE PLATES & FLANGES | DE | IFE | IN | PS-OT-T-0050 | 2015-05-26 |  | No | 1805 | 1204-Owner-v | 2015-05-27 10:06 | SPEC | 2015-05-26 | 0 | 0 | 0 | 2015-05-26 |  |  | complete | 100%
1204-63-PR-UFD-631 | 02 | UTILITY FLOW DIAGRAM FOR COOLING WATER SYSTEM | BE/DE | IFE | PR | PS-OT-T-0180 | 2016-01-11 |  | No | 1575 | 1204-Owner-v | 2016-01-12 09:41 | EDW | 2016-01-19 | 0 | 0 | 0 | 2016-01-19 | 2016-01-26 | MT-PS-9301-CS-092-1 | complete | 100%
1204-00-ST-SDG-701 | 01 | STANDARD DRAWING FOR GENERAL NOTE AND ABBREVIATIONS | DE | IFC | ST | TM-OT-9001-T-0449 | 2015-03-05 |  | No | 1887 | 1204-TKT-COLANGELI | 2015-03-04 13:48 | SPEC | 2015-03-05 | 0 | 0 | 0 | 2015-03-05 |  |  | complete | 100%
1204-00-ST-ESS-740 | 01 | ENGINEERING STANDARD SPECIFICATION FOR SITE GRADING(EARTH WORK) | DE | IFC | ST | TM-OT-9001-T-0411 | 2014-11-18 |  | No | 1994 | 1204-TKT-COLANGELI | 2014-11-17 12:46 | SPEC | 2014-11-18 | 0 | 0 | 0 | 2014-11-18 |  |  | complete | 100%
1204-71-PR-LST-001 | 01 | EQUIPMENT LIST FOR DAILY METHANOL STORAGE TANKS | BE/DE | IFE | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 11:59 | LIST | 2015-11-28 | 0 | 0 | 0 | 2015-11-28 | 2015-12-05 | MT-PS-9301-CS-051 | complete | 100%
1204-00-EL-DSH-5041 | 01 | DATA SHEET FOR POWER TRANSFORMERS - MS-TR1A/B-01 | DE | IFR | EL | PS-OT-T-0246 | 2016-04-18 | 2016-07-23 10:15 | Yes | 82 | 1204-Owner-v | 2016-04-18 17:28 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | * | 2016-04-23 | MT-PS-9301-CS-137 | InProgress | 80%
1204-00-EL-DSH-5043 | 00 | DATA SHEET FOR DISTRIBUTION TRANSFORMERS -2000 KVA | DE | IFR | EL | TM-OT-9001-T-0235 | 2013-02-06 |  | No | 2644 | 1204-TKT-COLANGELI | 2013-02-05 13:28 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | 2013-02-06 |  |  | InProgress | 80%
1204-00-EL-SCH-5033 | 00 | LV SWITCHGEAR SCHEDULE (MS-SWB3A,B-03) | DE | IFR | EL | TM-OT-9001-T-0319 | 2013-09-25 |  | No | 2413 | 1204-TKT-COLANGELI | 2013-09-23 11:29 | LIST | 2020-05-12 | 0 | 0 | 2020-05-12 | 2013-09-24 |  |  | InProgress | 90%
1204-90-HS-DWG-004 | 03 | FIRE & GAS ALARM LAYOUT FOR SUBSTATION | DE | IFE | HSE | PS-OT-T-379 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2018-12-22 12:30 | EDW | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-00-HV-TBA-790 | 00 | TECHNICAL BID ANALYSIS FOR HVAC EQUIPMENT | DE | IFI | HV | PS-OT-T-0741 | 2018-12-26 |  | No | 495 | 1204-Owner-v | 2018-12-29 10:37 | TBA | 2018-12-26 | 0 | 0 | 0 | 2018-12-26 |  |  | complete | 100%
1204-00-EL-MSS-507 | 01 | MATERIAL STANDARD SPECIFICATION FOR DC BATTERY CHARGER | DE | IFE | EL | PS-OT-T-0884 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:40 | SPEC | 2020-02-06 | 0 | 0 | 0 | 2020-02-06 | 2020-03-07 | MT-PS-9609-CS-0301 | complete | 100%
1204-00-QC-SOI-527 | 00 | SCOPE OF INSPECTION FOR LIGHTING POLES | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-10-PV-DSH-230 | 02 | MECHANICAL DATA SHEET FOR SATURATOR COLUMN (T-1001) | DE | IFE | MD | PS-OT-T-0504 | 2017-11-21 |  | No | 895 | 1204-Owner-v | 2017-11-28 15:43 | DSH | 2017-11-21 | 0 | 0 | 0 | 2017-11-21 | 2017-11-21 | MT-PS-9301-CS-263 | complete | 100%
1204-30-PV-DSH-220 | 02 | MECHANICAL DATA SHEET FOR FUSEL OIL DRUM (D-3005) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:28 | DSH | 2019-11-13 | 0 | 0 | 0 | 0 |  |  | complete | 100%
1204-00-EL-TBA-517 | 00 | TECHNICAL BID ANALYSIS FOR LV VSD PANELS | DE | IFE | EL | PS-OT-T-0966 | 2020-05-09 |  | No | -5 | 1204-Owner-v | 2020-05-11 14:13 | TBA | 2020-07-03 | 0 | 0 | 2020-07-23 |  |  |  | complete | 100%
1204-30-IN-DWG-029 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 29) | DE | IFR | IN | PS-OT-T-0140 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 09:02 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | 2015-12-15 | 2016-01-12 | MT-PS-9301-CS-086 | InProgress | 80%
1204-30-RE-DSH-040 | 00 | DATA SHEET FOR TOPPING COLUMN BOTTOM PUMPS (P-3002 A/B) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-07 13:50 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-30-RE-DSH-041 | 01 | DATA SHEET FOR 1ST REFINING COLUMN REFLUX PUMPS (P-3003 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:24 | DSH | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 |  |  | InProgress | 80%
1204-20-RE-DSH-330 | 00 | DATA SHEET FOR METHANOL START UP PUMP (P-2001) | DE | IFR | MC | PS-OT-T-0836 | 2019-11-16 |  | No | 170 | 1204-Owner-v | 2020-01-05 07:59 | DSH | 2019-11-16 | 0 | 0 | 0 |  |  |  | InProgress | 80%
1204-90-HV-DWG-003 | 04 | CONTROL ROOM - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | PS-OT-T-0706 | 2018-10-22 |  | No | 560 | 1204-Owner-v | 2018-10-24 16:28 | CDW | 2018-10-22 | 0 | 0 | 0 | 2018-10-22 |  |  | complete | 100%
1204-00-QC-SOI-155 | 00 | SCOPE OF INSPECTION FOR FIRE FIGHTING EQUIPMENT | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-QC-SOI-509A | 00 | SCOPE OF INSPECTION FOR POWER, CONTROL AND EARTHING CABLES | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-EL-REQ-509A | 01 | REQUISITION FOR POWER, CONTROL AND EARTHING CABLES | DE | IFP | EL | PS-OT-T-0950 | 2020-04-15 |  | No | 19 | 1204-Owner-v | 2020-04-18 09:51 | REQ | 2020-01-08 | 0 | 0 | 2020-01-14 | * |  |  | complete | 100%
1204-00-EL-TBA-501 | 00 | TECHNICAL BID ANALYSIS FOR NEUTRAL GROUNDING RESISTOR | DE | IFE | EL | PS-OT-T-0916 | 2020-02-26 |  | No | 68 | 1204-Owner-v | 2020-02-27 12:38 | TBA | 2019-11-12 | 0 | 0 | 2019-11-18 | * | 2020-02-29 | MT-PS-9609-CS-0286 | complete | 100%
1204-90-ST-DWG-1012 | 02 | WORK SHOP / FDN.. (R.C. DETAILS I) | DE | IFC | ST | PS-TM-T-0252 | 2017-09-13 |  | No | 964 | 1204-TKT-COLANGELI | 2013-09-26 13:46 | CDW | 2017-09-13 | 0 | 0 | 0 | 2017-09-13 |  |  | complete | 100%
1204-90-ST-DWG-906 | 04 | CONTROL ROOM & LABORATORY / ELEVATIONS & DETAILS | DE | IFC | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 11:31 | CDW | 2014-08-20 | 0 | 0 | 0 | 2014-08-20 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-90-ST-DWG-942 | 02 | SUBSTATION / BEAMS & WALLS (R.C. II) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-21 15:33 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-00-QC-SOI-201 | 01 | SCOPE OF INSPECTION FOR REACTORS | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-HM-ESS-273 | 01 | ENGINEERING STANDARD SPECIFICATION FOR WATER TUBE BOILER | DE | IFE | MD | PS-OT-T-0924 | 2020-03-02 |  | No | 63 | 1204-Owner-v | 2020-03-03 11:23 | SPEC | 2020-04-30 | 0 | 0 | 2020-04-30 | * | 2020-03-03 | MT-PS-9609-CS-0292 | complete | 100%
1204-90-ST-DWG-1043 | 02 | WAREHOUSE/ PLUMBING LAYOUT & DETAILS | DE | IFC | ST | PS-OT-T-0162 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2015-12-30 17:52 | CDW | 2016-01-06 | 0 | 0 | 0 | 2016-01-06 | 2016-01-16 | Final Checked | complete | 100%
1204-90-ST-DWG-1056 | 00 | FIRE STATION / ROOF SLOPING PLAN & DETAILS | DE | IFR | ST | TM-OT-9001-T-0200 | 2012-11-05 |  | No | 2737 | 1204-Owner-v | 2015-09-16 18:26 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2012-11-05 |  |  | InProgress | 80%
1204-90-ST-DWG-1085 | 01 | GUARD HOUSE / BLOCK & JOIST | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 13:37 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-00-QC-SOI-507 | 00 | SCOPE OF INSPECTION FOR DC BATTERY CHARGER | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-20-PI-ISO-2600 | 01 | A/G ISOMETRIC DRAWING OF AREA-26 | DE | IFC-WH | PI | PS-OT-T-0671 | 2018-08-25 |  | No | 618 | 1204-Owner-v | 2018-08-28 18:19 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-30-PI-ISO-2900 | 01 | A/G ISOMETRIC DRAWING OF AREA-29 | DE | IFC-WH | PI | PS-OT-T-0673 | 2018-08-29 |  | No | 614 | 1204-Owner-v | 2018-09-01 16:23 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-64-PI-APL-2000 | 00 | PIPING PLAN AREA-20 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:09 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-40-PI-LST-4200 | 00 | A/G ISOMETRIC LIST OF AREA-42 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:03 | CDW | 2020-01-13 | 0 | 0 | 2020-06-25 | 2016-09-03 |  |  | InProgress | 80%
1204-40-PI-LST-4400 | 01 | A/G ISOMETRIC LIST OF AREA-44 | DE | IFC-WH | PI | PS-OT-T-0681 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:35 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | * |  |  | InProgress | 90%
1204-30-IN-DWG-024 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 24) | DE | IFR | IN | PS-OT-T-442 | 2017-04-22 |  | No | 1108 | 1204-Owner-v | 2017-05-01 09:10 | CDW | 2020-06-22 | 0 | 0 | 2020-06-22 | 2017-05-03 |  |  | InProgress | 80%
1204-20-PI-ISO-2700 | 01 | A/G ISOMETRIC DRAWING OF AREA-27 | DE | IFC-WH | PI | PS-OT-T-0692 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-10-13 14:05 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-30-PI-ISO-6700 | 01 | U/G ISOMETRIC DRAWING OF AREA-67 | DE | IFC-WH | PI | PS-OT-T-0650 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-29 09:24 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-07-29 | MT-PS-9609-CS-102 | InProgress | 90%
1204-00-PI-LST-3600 | 00 | A/G ISOMETRIC LIST OF AREA-36 | DE | IFR | PI | PS-OT-T-0340 | 2016-09-28 |  | No | 1314 | 1204-Owner-v | 2016-10-01 11:11 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-00-IN-REQ-655 | 00 | REQUISITION FOR DESUPERHEATER VALVES | DE | IFI | IN | PS-OT-T-0148 | 2015-12-19 |  | No | 1598 | 1204-Owner-v | 2015-12-20 18:11 | REQ | 2019-12-10 | 0 | 0 | 2019-12-23 | * | 2016-08-06 | MT-PS-9301-CS-107-1 | InProgress | 90%
1204-02-EL-DWG-011 | 00 | LIGHTING LAYOUT AREA-02 (D-2003, E-2001A/B, 2002, 2003A/B, 2005A/B, 2006 & R-2001) | DE | IFR | EL | PS-OT-T-0130 | 2015-11-09 | 2016-07-24 11:01 | Yes | 244 | 1204-Owner-v | 2015-11-10 09:03 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-11-12 | 2015-12-08 | MT-PS-9301-CS-053 | InProgress | 80%
1204-00-QC-SOI-460A | 01 | SCOPE OF INSPECTION FOR COATING & WRAPPING (MTO I) | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-30-PI-LST-2400 | 00 | A/G ISOMETRIC LIST OF AREA-24 | DE | IFR | PI | PS-OT-T-0437 | 2017-04-09 |  | No | 1121 | 1204-Owner-v | 2017-04-16 14:51 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2017-04-25 |  |  | InProgress | 80%
1204-00-ST-DWG-1125 | 02 | DV-6202 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0725 | 2018-12-10 |  | No | 511 | 1204-Owner-v | 2018-12-12 08:11 | CDW | 2018-12-10 | 0 | 0 | 0 | 2018-12-10 |  |  | complete | 100%
1204-90-ST-DWG-1211 | 00 | CONTROL ROOM FOR ASU / CONCEPTUAL PLAN | DE | IFR | ST | PS-OT-T-0584 | 2018-03-19 |  | No | 777 | 1204-Owner-v | 2018-03-25 11:37 | CDW | 2020-05-30 | 0 | 0 | 2020-05-30 | * | 2018-07-03 | MT-PS-9609-CS-055-N | InProgress | 80%
1204-00-PI-REQ-419 | 00 | REQUISITION FOR FLANGE FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:21 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-00-ST-DWG-777 | 01 | GUARD RAIL DETAILS II | DE | IFC | ST | PS-OT-T-0317 | 2016-08-03 |  | No | 1370 | 1204-Owner-v | 2016-08-06 15:53 | CDW | 2016-08-03 | 0 | 0 | 0 | 2016-08-03 |  |  | complete | 100%
1204-30-ST-DWG-136 | 01 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 /STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0788 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:20 | CDW | 2019-05-13 | 0 | 0 | 0 | 2019-05-13 |  |  | complete | 100%
1204-00-PI-MTO-420 | 00 | MATERIAL TAKE OFF FOR GASKET FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0944 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:43 | MTO | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-IN-LST-003 | 01 | ESD I/O COUNT | DE | IFR | IN | PS-OT-T-0902 | 2020-02-19 |  | No | 75 | 1204-Owner-v | 2020-02-25 17:00 | LIST | 2020-04-14 | 0 | 0 | 2020-04-14 | * |  |  | InProgress | 90%
1204-00-IN-SKT-008 | 00 | ANALYZER SAMPLE CONNECTION DRAWING | DE | IFR | IN | PS-OT-T-0677 | 2018-08-08 |  | No | 635 | 1204-Owner-v | 2018-09-13 17:05 | CDW | 2018-08-08 | 0 | 0 | 0 | 2018-08-08 |  |  | InProgress | 80%
1204-00-PI-REQ-404A | 01 | REQUISITION FOR A/G VALVES(MTO I) | DE | IFP | PI | PS-OT-T-0561 | 2018-02-19 |  | No | 805 | 1204-Owner-v | 2018-03-08 09:34 | REQ | 2018-02-19 | 0 | 0 | 0 | 2018-02-19 | 2018-03-19 | MT-PS-9609-CS-50 | complete | 100%
1204-00-PR-PID-004 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR INSTRUMENT SYMBOLS I | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:31 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-71-ST-MTO-753 | 00 | MATERIAL TAKE OFF FOR TK-7101 A&B | DE | IFE | ST | TM-OT-9001-T-0404 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-30 15:44 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-007 | complete | 100%
1204-90-HV-DSH-221 | 02 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR SUBSTATION | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:38 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DWG-042 | 01 | ADMINISTRATION - SECTION OF DUCTING | DE | IFC | HV | TM-OT-9001-T-0382 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 13:22 | CDW | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-10-19 |  | complete | 100%
1204-64-RE-DSH-050 | 01 | DATA SHEET FOR DEMIN WATER TRANSFER PUMPS (P-6402 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:23 | DSH | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 | 2017-05-03 | MT-PS-9301-CS-225-R | InProgress | 80%
1204-20-HM-DSH-235 | 00 | MECHANICAL DATA SHEET FOR CONVERTER STEAM CONDENSER (E-2005A/B) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 11:50 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | InProgress | 80%
1204-90-HV-DWG-011 | 03 | LABORATORY - DUCTING LAYOUT | DE | IFC | HV | PS-OT-T-0007 | 2015-03-11 |  | No | 1881 | 1204-Owner-v | 2015-03-17 11:20 | CDW | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DSH-106 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR PRD IN UPS ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:53 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-00-PI-LST-6400 | 01 | U/G ISOMETRIC LIST OF AREA-64 | DE | IFC-WH | PI | PS-OT-T-0629 | 2018-06-13 |  | No | 691 | 1204-Owner-v | 2018-06-19 08:57 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-06-24 | MT-PS-9609-CS-088 | InProgress | 90%
1204-10-PI-UPL-7200 | 02 | UNDER GROUND PIPING PLAN AREA-72 | DE | IFC-WH | PI | PS-OT-T-0614 | 2018-05-19 |  | No | 716 | 1204-Owner-v | 2018-05-20 12:56 | CDW | 2018-06-02 | 0 | 0 | 0 | 2018-06-02 |  |  | InProgress | 90%
1204-63-PI-APL-1800 | 00 | PIPING PLAN AREA-18 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:12 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-64-PI-LST-6900 | 01 | U/G ISOMETRIC LIST OF AREA-69 | DE | IFC-WH | PI | PS-OT-T-0606 | 2018-05-12 |  | No | 723 | 1204-Owner-v | 2018-05-13 15:25 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-26 |  |  | InProgress | 90%
1204-10-PI-APL-4700 | 00 | PIPING PLAN AREA-47 | DE | IFR | PI | PS-OT-T-0343 | 2016-10-01 |  | No | 1311 | 1204-Owner-v | 2016-10-04 07:29 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-10 |  |  | InProgress | 80%
1204-10-PI-LST-4700 | 00 | A/G ISOMETRIC LIST OF AREA-47 | DE | IFR | PI | PS-OT-T-0343 | 2016-10-01 |  | No | 1311 | 1204-Owner-v | 2016-10-04 08:18 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-10 |  |  | InProgress | 80%
1204-00-IN-REQ-622 | 00 | REQUISITION FOR PRESSURE GAUGES | DE | IFI | IN | PS-OT-T-0550 | 2018-02-06 |  | No | 818 | 1204-Owner-v | 2018-02-07 12:06 | REQ | 2020-05-05 | 0 | 0 | 2020-05-18 | 2018-02-10 | 2018-02-17 | MT-PS-9609-CS-031 | InProgress | 90%
1204-00-PI-REQ-402B | 00 | REQUISITION FOR A/G FLANGES(MTO II) | DE | IFI | PI | PS-OT-T-0946 | 2020-04-11 |  | No | 23 | 1204-Owner-v | 2020-04-15 11:16 | REQ | 2020-04-16 | 0 | 0 | 2020-04-29 | * |  |  | InProgress | 90%
1204-30-ST-DWG-302 | 03 | STRUCTURE "B" FOR D-3003 & E-3003A/B / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0452 | 2017-05-31 |  | No | 1069 | 1204-Owner-v | 2017-06-17 09:08 | CDW | 2017-06-10 | 0 | 0 | 0 | 2017-06-10 |  |  | complete | 100%
1204-30-ST-DWG-308 | 01 | STRUCTURE "B" FOR D-3003 & E-3003A/B / CONCRETE STRUCTURE (R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0347 | 2016-10-04 |  | No | 1308 | 1204-Owner-v | 2016-10-05 13:54 | CDW | 2016-10-04 | 0 | 0 | 0 | 2016-10-04 |  |  | complete | 100%
1204-90-ST-DWG-976 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BLDG / EAST & WEST ELEVATION & DETAILS | DE | IFR | ST | TM-OT-9001-T-0116 | 2012-06-19 |  | No | 2876 | 1204-Owner-v | 2015-09-16 18:35 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 2012-06-19 |  |  | InProgress | 80%
1204-00-QC-SOI-213B | 01 | SCOPE OF INSPECTION FOR STAINLESS STEEL STORAGE TANKS | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-QC-SOI-641 | 00 | SCOPE OF INSPECTION FOR TEMPERATURE GAUGES AND THERMOWELL | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1059 | 01 | FIRE STATION / BEAMS (R.C. DETAILS I ) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:59 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-915 | 02 | CONTROL ROOM & LABORATORY / BEAMS (R.C. DETAILS ) | DE | IFC | ST | TM-OT-9001-T-0330 | 2013-10-29 |  | No | 2379 | 1204-TKT-COLANGELI | 2013-10-28 11:13 | CDW | 2013-10-29 | 0 | 0 | 0 | 2013-10-29 |  |  | complete | 100%
1204-90-ST-DWG-916 | 01 | CONTROL ROOM & LABORATORY / COLUMNS (R.C. DETAILS) | DE | IFC | ST | PS-TM-T-0255 | 2021-09-13 |  | No | -497 | 1204-TKT-COLANGELI | 2013-09-27 12:31 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-90-ST-DWG-971 | 04 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FURNITURE PLAN FOR GROUND FLOOR PLAN | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-03 10:02 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 0 | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-63-RE-DSH-033 | 01 | DATA SHEET FOR COOLING WATER SUPPLY PUMPS (P-6301 A~F) | DE | IFR | MC | PS-OT-T-0314 | 2016-07-31 |  | No | 1373 | 1204-Owner-v | 2016-08-03 16:42 | DSH | 2016-07-31 | 0 | 0 | 0 | 2016-07-31 |  |  | InProgress | 80%
1204-00-PR-UDD-015 | 03 | UTILITY DISTRIBUTION DIAGRAM FOR SERVICE WATER DISTRIBUTION SYSTEM | DE | IFC-WH | PR | PS-OT-T-0575 | 2018-03-06 |  | No | 790 | 1204-Owner-v | 2018-04-07 09:13 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2018-04-12 | 2018-03-07 | MT-PS-9609-CS-043 | InProgress | 90%
1204-00-ST-ESS-743 | 01 | ENGINEERING STANDARD SPECIFICATION FOR DESIGN OF STEEL STRUCTURE | DE | IFC | ST | TM-OT-9001-T-0408 | 2014-11-06 |  | No | 2006 | 1204-TKT-COLANGELI | 2014-11-06 13:40 | SPEC | 2014-11-06 | 0 | 0 | 0 | 2014-11-06 | 2014-12-30 | MT-TM-9301-CS-027 | complete | 100%
1204-00-ST-ESS-744 | 01 | ENGINEERING STANDARD SPECIFICATION FOR FIRE PROOFING (STRUCTURAL PART) | DE | IFC | ST | TM-OT-9001-T-0411 | 2014-11-18 |  | No | 1994 | 1204-TKT-COLANGELI | 2014-11-17 12:48 | SPEC | 2014-11-18 | 0 | 0 | 0 | 2014-11-18 |  |  | complete | 100%
1204-64-PR-DSH-103 | 01 | DATA SHEET FOR CONDENSATE STORAGE TANK (TK-6401) | BE | IFE | PR | TM-OT-9001-T-0299 | 2013-07-04 |  | No | 2496 | 1204-Owner-v | 2015-04-13 16:18 | DSH | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-22-PR-DBS-101 | 00 | Basic Engineering Design Basis For Machinery Cooling Water System | BE | IFR | PR | TM-OT-9001-T-0007 | 2011-05-10 |  | No | 3282 | 1204-TKT-proietti | 2011-05-09 17:18 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | * |  |  | InProgress | 80%
1204-00-EL-MTO-002 | 00 | MATERIAL TAKE OFF FOR POWER SYSTEM | DE | IFE | EL | PS-OT-T-0232 | 2013-04-06 | 2016-07-21 15:05 | Yes | 1188 | 1204-Owner-v | 2016-04-07 10:38 | LIST | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 | 2016-04-18 | MT-PS-9301-CS-132 | complete | 100%
1204-00-EL-SDG-620 | 01 | ELECTRICAL INSTALLATION STANDARD DRAWINGS - POWER | DE | IFR | EL | PS-OT-T-0118 | 2015-10-12 | 2015-11-28 09:17 | Yes | 33 | 1204-Owner-v | 2015-10-13 17:14 | CDW | 2020-09-10 | 0 | 0 | 2020-09-10 | * | 2015-11-19 | MT-PS-9301-CS-044 | InProgress | 80%
1204-00-EL-SLD-001 | 04 | OVERALL ELECTRICAL ONE LINE DIAGRAM | DE | IFR | EL | PS-OT-T-0590 | 2018-04-19 | 2018-04-24 16:29 | Yes | -9 | 1204-Owner-v | 2018-04-22 09:01 | CDW | 2020-09-20 | 0 | 0 | 2020-09-20 | * | 2018-04-24 | MT-PS-9609-CS-058 | InProgress | 80%
1204-90-EL-SLD-045 | 01 | ADMIN. EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:48 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-EL-MSS-513 | 01 | MATERIAL STANDARD SPECIFICATION FOR PUBLIC ADDRESS AND INTERCOM SYSTEM | DE | IFE | EL | TM-OT-9001-T-0414 | 2014-12-03 |  | No | 1979 | 1204-TKT-COLANGELI | 2014-12-03 11:46 | SPEC | 2014-12-03 | 0 | 0 | 0 | 2014-12-03 |  |  | complete | 100%
1204-71-PR-UFD-711 | 01 | UTILITY FLOW DIAGRAM FOR DAILY METHANOL STORAGE TANKS | BE/DE | IFE | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-TKT-COLANGELI | 2013-03-12 12:23 | EDW | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-00-ST-SDG-766 | 01 | STANDARD DRAWING FOR FENCING & GATE | DE | IFC | ST | PS-OT-T-0245 | 2016-04-17 |  | No | 1478 | 1204-Owner-v | 2016-04-18 17:28 | SPEC | 2016-04-19 | 0 | 0 | 0 | 2016-04-19 |  |  | complete | 100%
1204-72-PR-DSH-101 | 01 | DATA SHEET FOR CRUDE METHANOL STORAGE TANK (TK-7201) | BE | IFE | PR | TM-OT-9001-T-0242 | 2013-03-14 |  | No | 2608 | 1204-Owner-v | 2015-09-16 18:08 | DSH | 2013-03-14 | 0 | 0 | 0 | 2013-03-14 |  |  | complete | 100%
1204-40-PI-APL-4400 | 01 | PIPING PLAN AREA-44 | DE | IFC-WH | PI | PS-OT-T-0681 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:37 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | * |  |  | InProgress | 90%
1204-84-HS-DSH-008 | 00 | DATA SHEET FOR COC WATER PUMP P-8403 A/B | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:06 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-02-EL-SLD-058 | 00 | SINGLE LINE DIAGRAM FOR 02-DP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:02 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:41 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-90-EL-DIG-002 | 00 | FIRE ALARM RISER DIAGRAM FOR WORKSHOP BUILDING | DE | IFR | EL | PS-OT-T-0123 | 2015-10-31 | 2016-07-24 11:25 | Yes | 253 | 1204-Owner-v | 2015-11-01 10:24 | CDW | 2020-04-21 | 0 | 0 | 2020-04-21 | 2015-11-16 | 2015-12-26 | MT-PS-9301-CS-067 | InProgress | 80%
1204-00-PI-ESS-418 | 00 | ENGINEERING STANDARD SPECIFICATION FOR PLANT LAY OUT | DE | IFR | PI | TM-OT-9001-T-0370 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 14:03 | SPEC | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-EL-REQ-501 | 01 | REQUISITION FOR NEUTRAL GROUNDING RESISTOR | DE | IFP | EL | PS-OT-T-0931 | 2020-03-09 |  | No | 56 | 1204-Owner-v | 2020-03-15 16:28 | REQ | 2020-03-09 | 0 | 0 | 0 | 2020-03-09 | 2020-04-05 | MT-PS-9609-CS-0320-1 | complete | 100%
1204-30-IN-DWG-028 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 28) | DE | IFR | IN | PS-OT-T-0147 | 2015-12-09 |  | No | 1608 | 1204-Owner-v | 2015-12-09 12:01 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | 2015-12-15 | 2016-02-09 | MT-PS-9301-CS-104 | InProgress | 80%
1204-90-EL-SLD-081 | 01 | SUBSTATION SAFETY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:55 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-64-ST-MTO-716 | 00 | MATERIAL TAKE OFF FOR TK-6402 | DE | IFE | ST | TM-OT-9001-T-0404 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-30 15:40 | LIST | 2020-08-25 | 0 | 0 | 2020-08-25 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-007 | complete | 100%
1204-00-HM-REQ-260 | 02 | REQUISITION FOR DOUBLE PIPE HEAT EXCHANGERS | DE | IFP | MD | PS-OT-T-0893 | 2020-02-16 |  | No | 78 | 1204-Owner-v | 2020-03-01 11:13 | REQ | 2020-02-16 | 0 | 0 | 0 | 2020-02-16 | 2020-02-27 | MT-PS-9301-CS- 0275 | complete | 100%
1204-90-HV-DSH-040 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR ADMINISTRATION | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:40 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-080 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR PANTRY IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:44 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-091 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR PANTRY AND MS.R. IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:46 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DSH-222 | 01 | DATA SHEET FOR PRESSURE RELIEF DAMPER FOR SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:49 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-00-IN-TBA-601 | 01 | TECHNICAL BID ANALYSIS FOR FCS/ ESD SYSTEMS | DE | IFE | IN | PS-OT-T-0655 | 2018-07-25 |  | No | 649 | 1204-Owner-v | 2018-07-28 16:34 | TBA | 2018-07-31 | 0 | 0 | 0 | 2018-07-31 | 2018-07-29 | MT-PS-9609-CS-101 | complete | 100%
1204-61-QC-SOI-104 | 00 | SCOPE OF INSPECTION FOR AIR SEPARATION UNIT (ASU) (PU-6101) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-84-HS-DSH-009 | 01 | DATA SHEET FOR CHEMICAL/LABORATORY EFFLUENT SUMP SU-8404 | DE | IFR | HSE | PS-OT-T-0854 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:52 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * | 2020-02-12 | MT-PS-9301-CS-0269-1 | InProgress | 80%
1204-62-ST-DWG-650 | 01 | D-6202 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0291 | 2016-06-18 |  | No | 1416 | 1204-Owner-v | 2016-06-19 13:14 | CDW | 2016-06-18 | 0 | 0 | 0 | 2016-06-18 |  |  | complete | 100%
1204-00-ST-DWG-088 | 03 | PIPE RACK ZONE 11 / STEEL STRUCTURE | DE | IFC | ST | PS-OT-T-0411 | 2017-01-21 |  | No | 1199 | 1204-Owner-v | 2017-01-24 10:38 | CDW | 2017-01-23 | 0 | 0 | 0 | 2017-01-23 |  |  | complete | 100%
1204-04-EL-DWG-021 | 00 | EARTHING LAYOUT FOR AREA-04 - AE-3001 AND DA-4001 | DE | IFR | EL | PS-OT-T-330 | 2016-08-28 | 2016-10-10 17:00 | Yes | 29 | 1204-Owner-v | 2016-08-28 16:07 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | * | 2016-09-03 | MT-PS-9301-CS-182-R | InProgress | 80%
1204-30-RE-DSH-042 | 01 | DATA SHEET FOR 2nd REFINING COLUMN REFLUX PUMPS (P-3004 A/B) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:23 | DSH | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 |  |  | InProgress | 80%
1204-90-HV-DSH-220 | 01 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0429 | 2015-01-14 |  | No | 1937 | 1204-TKT-COLANGELI | 2015-01-14 13:41 | DSH | 2015-01-14 | 0 | 0 | 0 | 2015-01-14 | 2015-01-27 | MT-TM-9301-CS-033 | complete | 100%
1204-30-ST-DWG-311 | 02 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 / FDN. (G.A. & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0757 | 2019-03-02 |  | No | 429 | 1204-Owner-v | 2019-03-04 09:42 | CDW | 2019-03-02 | 0 | 0 | 0 | 2019-03-02 |  |  | complete | 100%
1204-10-PV-REQ-202F | 01 | REQUISITION FOR STEAM DRUM, STEAM GENERATOR AND STEAM SUPER HEATER PACKAGE | DE | IFP | MD | PS-OT-T-0166 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:59 | REQ | 2019-10-01 | 0 | 0 | 2019-10-14 | * | 2016-01-17 | MT-PS-9301-CS-088 | complete | 100%
1204-00-PI-LST-1400 | 00 | A/G ISOMETRIC LIST OF AREA-14 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:11 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-01-06 |  |  | InProgress | 80%
1204-10-PI-ISO-7100 | 01 | U/G ISOMETRIC DRAWING OF AREA-71 | DE | IFC-WH | PI | PS-OT-T-0618 | 2018-05-23 |  | No | 712 | 1204-Owner-v | 2018-06-03 10:51 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-05-23 | MT-PS-9609-CS-076 | InProgress | 90%
1204-00-QC-SOI-506 | 00 | SCOPE OF INSPECTION FOR AC UPS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-RE-REQ-307B | 01 | REQUISITION FOR CENTRIFUGAL PUMPS (GROUP B) | DE | IFI | MC | PS-OT-T-0385 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2018-05-01 10:51 | REQ | 2016-12-20 | 0 | 0 | 0 | 2016-12-20 |  |  | InProgress | 90%
1204-10-ST-DWG-164 | 02 | REFORMER (TRANSFERLINE SUPPORTS 4 TO 7) / FDN.(G.A. & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0705 | 2018-10-21 |  | No | 561 | 1204-Owner-v | 2018-10-23 12:04 | CDW | 2018-10-24 | 0 | 0 | 0 | 2018-10-24 |  |  | complete | 100%
1204-00-IN-DWG-037 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 37) | DE | IFR | IN | PS-OT-T-0280 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-13 09:05 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | * | 2016-08-15 | MT-PS-9301-CS-164-R | InProgress | 80%
1204-64-ST-DWG-717 | 01 | D-6401 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0384 | 2016-12-18 |  | No | 1233 | 1204-Owner-v | 2016-12-21 10:47 | CDW | 2016-12-18 | 0 | 0 | 0 | 2016-12-18 |  |  | complete | 100%
1204-00-ST-DWG-1133 | 01 | VB-6102 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0580 | 2018-03-13 |  | No | 783 | 1204-Owner-v | 2018-04-14 11:39 | CDW | 2018-03-13 | 0 | 0 | 0 | 2018-03-13 |  |  | complete | 100%
1204-10-PV-REQ-202S | 00 | REQUISITION FOR STEAM SUPER HEATERS AND TRANSFER LINES OF WASTE HEAT BOILER | DE | IFI | MD | PS-OT-T-0848 | 2019-12-23 |  | No | 133 | 1204-Owner-v | 2019-12-26 14:39 | REQ | 2019-10-14 | 0 | 0 | 2019-10-14 | * | 2020-01-03 | MT-PS-9609-CS-0259 | InProgress | 90%
1204-40-ST-DWG-455 | 01 | BOILER (PU-4006 A ) / FDN. (G.A. & R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0191 | 2016-01-30 |  | No | 1556 | 1204-Owner-v | 2016-01-31 09:33 | CDW | 2016-01-30 | 0 | 0 | 0 | 2016-01-30 | 2016-02-01 | MT-PS-9301-CS-097 | complete | 100%
1204-03-EL-DWG-012 | 00 | LIGHTING LAYOUT AREA-03 (D-3001, 3002, E-3002, 3007, 3011, T-3001) | DE | IFR | EL | PS-OT-T-0159 | 2015-12-28 | 2016-07-21 15:12 | Yes | 192 | 1204-Owner-v | 2015-12-30 13:56 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2016-01-16 | 2016-01-19 | MT-PS-9301-CS-078-1 | InProgress | 80%
1204-40-IN-DWG-042 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 42) | DE | IFR | IN | PS-OT-T-333 | 2016-09-03 |  | No | 1339 | 1204-Owner-v | 2016-09-03 18:21 | CDW | 2020-06-25 | 0 | 0 | 2020-06-25 | * | 2016-09-17 | MT-PS-9301-CS-187-R | InProgress | 80%
1204-40-ST-DWG-462 | 01 | BOILER (PU-4006 B ) / FDN. ( R.C. DETAILS III ) | DE | IFC | ST | PS-OT-T-0243 | 2016-04-16 |  | No | 1479 | 1204-Owner-v | 2016-04-17 14:44 | CDW | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 |  |  | complete | 100%
1204-10-RE-DSH-060 | 01 | DATA SHEET FOR E.O.T CRANE FOR N2 COMPRESSOR, CN-1001 | DE | IFR | MC | PS-OT-T-0660 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-15 15:54 | DSH | 2018-08-05 | 0 | 0 | 0 | 2018-08-05 |  |  | InProgress | 80%
1204-61-ST-DWG-551 | 00 | ASU (AE-6187) / CONCRETE STRUCTURE (G.A. PLANS & DETAILS) | DE | IFR | ST | PS-OT-T-0653 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-30 17:04 | CDW | 2018-07-23 | 0 | 0 | 0 | 2018-07-23 | 2018-08-04 | MT-PS-9609-CS-104 | InProgress | 80%
1204-20-RE-DSH-064 | 01 | DATA SHEET FOR MANUAL CHAIN HOIST FOR E-2003 A/B, CN-2002 | DE | IFR | MC | PS-OT-T-0660 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-15 15:51 | DSH | 2018-08-05 | 0 | 0 | 0 | 2018-08-05 |  |  | InProgress | 80%
1204-10-ST-DWG-161 | 01 | STRUCTURE FOR WHB, ATR, E-1003A/B & D-4001A/B/COMBINED FDN. (G.A. & DETAILS ) | DE | IFC | ST | PS-OT-T-0704 | 2018-10-21 |  | No | 561 | 1204-Owner-v | 2018-10-24 16:57 | CDW | 2018-10-21 | 0 | 0 | 0 | 2018-10-21 |  |  | complete | 100%
1204-30-ST-DWG-136 | 01 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 /STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0788 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:20 | CDW | 2019-05-13 | 0 | 0 | 0 | 2019-05-13 |  |  | complete | 100%
1204-00-QC-SOI-514 | 00 | SCOPE OF INSPECTION FOR CCTV SYSTEM | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 | 1204-Owner-v | 2020-02-25 13:18 | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-40-PV-DSH-224 | 01 | MECHANICAL DATA SHEET FOR LP CONDENSATE DRUM (D-4003) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 16:20 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-90-EL-SLD-079 | 01 | TECHNICAL BUILDING NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:53 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-HV-DSH-025 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR LV SGR. CO2 REMOVAL IN SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:50 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DSH-096 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR CAT. AND CHEM. ST. IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:55 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DSH-105 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR PRD IN ENGINEERING ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:51 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-72-HS-PID-001 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR SPRAY NOZZLE SYSTEM FOR TK-7201 | DE | IFR | HSE | PS-OT-T-0012 | 2015-03-17 |  | No | 1875 | 1204-Owner-v | 2015-03-25 13:27 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * |  |  | InProgress | 80%
1204-10-PI-UPL-6100 | 02 | UNDER GROUND PIPING PLAN AREA-61 | DE | IFC-WH | PI | PS-OT-T-0627 | 2018-06-03 |  | No | 701 | 1204-Owner-v | 2018-06-09 08:19 | CDW | 2018-06-17 | 0 | 0 | 0 | 2018-06-17 |  |  | InProgress | 90%
1204-30-PI-APL-2200 | 01 | PIPING PLAN AREA-22 | DE | IFC-WH | PI | PS-OT-T-0661 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:52 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-40-PI-UPL-6600 | 02 | UNDER GROUND PIPING PLAN AREA-66 | DE | IFC-WH | PI | PS-OT-T-0682 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:38 | CDW | 2018-10-02 | 0 | 0 | 0 | 2018-10-02 |  |  | InProgress | 90%
1204-60-PI-ISO-6200 | 01 | U/G ISOMETRIC DRAWING OF AREA-62 | DE | IFC-WH | PI | PS-OT-T-0597 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:22 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 90%
1204-63-PI-APL-1700 | 00 | PIPING PLAN AREA-17 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-00-PI-ISO-3800 | 00 | A/G ISOMETRIC DRAWING OF AREA-38 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:03 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-09-03 |  |  | InProgress | 80%
1204-10-PI-APL-4600 | 00 | PIPING PLAN AREA-46 | DE | IFR | PI | PS-OT-T-0349 | 2016-10-10 |  | No | 1302 | 1204-Owner-v | 2016-10-23 09:13 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-19 |  |  | InProgress | 80%
1204-10-RE-DSH-016 | 01 | DATA SHEETS FOR N2 CIRCULATOR COMPRESSOR (C-1001) | DE | IFR | MC | PS-OT-T-0434 | 2017-04-05 |  | No | 1125 | 1204-Owner-v | 2017-04-08 08:26 | DSH | 2017-04-05 | 0 | 0 | 0 | 2017-04-05 |  |  | InProgress | 80%
1204-03-EL-SLD-062 | 00 | SINGLE LINE DIAGRAM FOR 03-DP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 15:02 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:41 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-03-09 | 2016-03-05 | MT-PS-9301-CS-112 | InProgress | 80%
1204-00-IN-DWG-035 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 35) | DE | IFR | IN | PS-OT-T-332 | 2016-08-31 |  | No | 1342 | 1204-Owner-v | 2016-09-01 13:48 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | * | 2016-09-17 | MT-PS-9301-CS-186-R | InProgress | 80%
1204-64-IN-DWG-031 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 31) | DE | IFR | IN | PS-OT-T-0326 | 2016-08-27 |  | No | 1346 | 1204-Owner-v | 2016-08-28 09:30 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | * | 2016-09-17 | MT-PS-9301-CS-185-R | InProgress | 80%
1204-04-EL-SLD-065 | 00 | SINGLE LINE DIAGRAM FOR 04-ELP-01 | DE | IFR | EL | PS-OT-T-0297 | 2016-06-25 | 2016-07-21 14:36 | Yes | 12 | 1204-Owner-v | 2016-06-28 17:31 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-07-02 | 2016-06-25 | MT-PS-9301-CS-169 | InProgress | 80%
1204-30-ST-DWG-323 | 01 | STRUCTURE "D" FOR E-3006,E-3010A/B / STEEL STRUCTURE (ELEVATION & DETS.) | DE | IFC | ST | PS-OT-T-0789 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:25 | CDW | 2019-05-08 | 0 | 0 | 0 | 2019-05-08 |  |  | complete | 100%
1204-63-PI-APL-1600 | 00 | PIPING PLAN AREA-16 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-61-PR-DSH-101 | 00 | DATASHEET FOR AIR SEPARATION UNIT (ASU) (PU-6101) | BE | IFR | PR | PS-OT-T-0086 | 2015-08-03 |  | No | 1736 | 1204-Owner-v | 2015-08-04 17:22 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2015-08-04 |  |  | InProgress | 80%
1204-62-ST-DWG-620 | 01 | D-6201 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0293 | 2016-06-21 |  | No | 1413 | 1204-Owner-v | 2016-06-22 10:16 | CDW | 2016-06-21 | 0 | 0 | 0 | 2016-06-21 |  |  | complete | 100%
1204-00-PI-MTO-416A | 00 | MATERIAL TAKE OFF FOR A.S & S.S ELECTRODE & WELDING ROD (MTO I) | DE | IFE | PI | PS-OT-T-0303 | 2016-07-10 |  | No | 1394 | 1204-Owner-v | 2016-07-12 16:17 | LIST | 2016-07-16 | 0 | 0 | 0 | 2016-07-16 |  |  | complete | 100%
1204-00-EL-SLD-089 | 01 | PDCS GRAPHIC DISPLAY DIAGRAM | DE | IFR | EL | PS-OT-T-0736 | 2018-12-22 | 2019-01-22 16:02 | Yes | 17 | 1204-Owner-v | 2018-12-23 11:59 | CDW | 2018-12-22 | 0 | 0 | 0 | 2018-12-22 |  |  | InProgress | 80%
1204-00-ST-DWG-1137 | 02 | VB-6203 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0725 | 2018-12-10 |  | No | 511 | 1204-Owner-v | 2018-12-12 08:12 | CDW | 2018-12-10 | 0 | 0 | 0 | 2018-12-10 |  |  | complete | 100%
1204-10-PV-REQ-202D | 00 | REQUISITION FOR STEAM DRUMS OF WASTE HEAT BOILER | DE | IFI | MD | PS-OT-T-0848 | 2019-12-23 |  | No | 133 | 1204-Owner-v | 2019-12-29 14:59 | REQ | 2019-10-14 | 0 | 0 | 2019-10-14 | 0 | 0 | 0 | InProgress | 90%
1204-00-ST-REQ-740D | 00 | REQUISITION FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART D) | DE | IFI | ST | PS-OT-T-0915 | 2020-02-25 |  | No | 69 | 1204-Owner-v | 2020-02-27 12:45 | REQ | 2020-06-23 | 0 | 0 | 2020-06-30 | * |  |  | complete | 100%
1204-90-HS-LST-008 | 02 | SAFETY EQUIPMENT LIST FOR WORK SHOP | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-19 15:41 | LIST | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-10-HM-TBA-251B | 00 | TECHNICAL BID ANALYSIS FOR STEEL WORK SUPPLY AND SHOP PREFABRICATION (FURNACE) | DE | IFE | MD | PS-OT-T-0709 | 2018-10-27 |  | No | 555 | 1204-Owner-v | 2018-10-28 11:42 | TBA | 2018-10-27 | 0 | 0 | 0 | 2018-10-27 |  |  | complete | 100%
1204-00-ST-DWG-1111 | 01 | PIPE CULVERT / G.A. PLANS & SECTIONS | DE | IFC | ST | PS-OT-T-0022 | 2015-04-18 |  | No | 1843 | 1204-Owner-v | 2015-04-19 10:24 | CDW | 2015-04-18 | 0 | 0 | 0 | 2015-04-18 |  |  | complete | 100%
1204-83-HS-UDD-001 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR FLARE NETWORK | DE | IFC-WH | HSE | PS-OT-T-0658 | 2018-08-01 |  | No | 642 | 1204-Owner-v | 2018-08-07 15:55 | LIST | 2020-08-01 | 0 | 0 | 2020-08-01 | * |  |  | complete | 100%
1204-00-PI-ISO-3600 | 00 | A/G ISOMETRIC DRAWING OF AREA-36 | DE | IFR | PI | PS-OT-T-0340 | 2016-09-28 |  | No | 1314 | 1204-Owner-v | 2016-10-01 11:34 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-90-EL-DIG-003 | 00 | FIRE ALARM RISER DIAGRAM FOR WAREHOUSE BUILDING | DE | IFR | EL | PS-OT-T-0123 | 2015-10-31 | 2016-07-24 11:26 | Yes | 253 | 1204-Owner-v | 2015-11-01 10:24 | CDW | 2020-04-21 | 0 | 0 | 2020-04-21 | 2015-11-16 | 2015-12-26 | MT-PS-9301-CS-067 | InProgress | 80%
1204-00-PI-REQ-460A | 02 | REQUISITION FOR COATING & WRAPPING(MTO I) | DE | IFP | PI | PS-OT-T-0513 | 2017-12-11 |  | No | 875 | 1204-Owner-v | 2017-12-16 11:06 | REQ | 2017-12-16 | 0 | 0 | 0 | 2017-12-16 | 2018-01-08 | MT-PS-9609-CS-004 | complete | 100%
1204-00-ST-DWG-087 | 01 | PIPE RACK STAIRS (ZONE 6 TO 9) / STRUCTURE (G.A. & SECTIONS II ) | DE | IFC | ST | PS-OT-T-0254 | 2016-05-02 |  | No | 1463 | 1204-Owner-v | 2016-05-03 13:11 | CDW | 2016-05-02 | 0 | 0 | 0 | 2016-05-02 |  |  | complete | 100%
1204-64-ST-DWG-720 | 01 | D-6402 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0391 | 2016-12-25 |  | No | 1226 | 1204-Owner-v | 2016-12-26 12:21 | CDW | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 |  |  | complete | 100%
1204-20-ST-DWG-261 | 02 | PU-2001 (HRU) / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0690 | 2018-09-26 |  | No | 586 | 1204-Owner-v | 2018-09-29 15:11 | CDW | 2018-10-02 | 0 | 0 | 0 | 2018-10-02 |  |  | complete | 100%
1204-83-ST-DWG-771 | 01 | D-8301 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0291 | 2016-06-18 |  | No | 1416 | 1204-Owner-v | 2016-06-19 13:14 | CDW | 2016-06-18 | 0 | 0 | 0 | 2016-06-18 |  |  | complete | 100%
1204-00-ST-DWG-778 | 02 | CONCRETE CABLE TRENCH / SECTIONS & DETAILS | DE | IFC | ST | PS-OT-T-0662 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-11 09:09 | CDW | 2018-08-05 | 0 | 0 | 0 | 0 | 0 | 0 | complete | 100%
1204-00-ST-DWG-1112 | 01 | EAST RETAINING WALL (FIRST PART) / G.A. PLAN & R.C. DETAILS (II) | DE | IFC | ST | PS-OT-T-0700 | 2018-10-10 |  | No | 572 | 1204-Owner-v | 2018-10-11 11:02 | CDW | 2018-10-10 | 0 | 0 | 0 | 2018-10-10 |  |  | complete | 100%
1204-90-HS-DWG-015 | 00 | FIRE AND GAS ALARM LAYOUT FOR ASU SUBSTATION | DE | IFR | HSE | PS-OT-T-0713 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-06 17:14 | EDW | 2020-07-10 | 0 | 0 | 2020-07-10 | * |  |  | InProgress | 80%
1204-00-PI-PPL-009 | 01 | ABOVE GROUND AND UNDERGROUND TIE IN LOCATION | DE | IFR | PI | PS-OT-T-0710 | 2018-11-03 |  | No | 548 | 1204-Owner-v | 2018-11-16 10:00 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-20-ST-DWG-215 | 01 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/CONC. STR. (R.C. DETS. II) | DE | IFC | ST | PS-OT-T-0785 | 2019-04-27 |  | No | 373 | 1204-Owner-v | 2019-04-28 11:15 | CDW | 2019-05-22 | 0 | 0 | 0 | 2019-05-22 |  |  | complete | 100%
1204-00-ST-DWG-186 | 00 | PIPE RACK ZONE 14 / FDN. (G.A. & R.C.) | DE | IFR | ST | PS-OT-T-0958 | 2020-04-28 |  | No | 6 | 1204-Owner-v | 2020-04-29 15:21 | CDW | 2020-03-23 | 0 | 0 | 2020-03-23 | 0 | 0 | 0 | InProgress | 90%
1204-90-HV-DWG-002 | 04 | CONTROL ROOM - SECTION OF DUCTING | DE | IFC | HV | PS-OT-T-0706 | 2018-10-22 |  | No | 560 | 1204-Owner-v | 2018-10-24 16:28 | CDW | 2018-10-22 | 0 | 0 | 0 | 2018-10-22 |  |  | complete | 100%
1204-90-HV-DWG-022 | 03 | SUBSTATION - SECTION OF DUCTING | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:43 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 |  |  | complete | 100%
1204-90-HV-DWG-037 | 01 | FIRE STATION - HVAC SYSTEM LAYOUT | DE | IFC | HV | TM-OT-9001-T-0317 | 2013-09-16 |  | No | 2422 | 1204-TKT-COLANGELI | 2013-09-11 15:41 | CDW | 2013-09-16 | 0 | 0 | 0 | 2013-09-16 |  |  | InProgress | 80%
1204-90-HV-DSH-065 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET IN ADMINISTRATION AND TRAINING | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:43 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DWG-092 | 01 | WAREHOUSE - HVAC OPENING LOCATION AND SUPPORTS | DE | IFC | HV | TM-OT-9001-T-0290 | 2013-06-07 |  | No | 2523 | 1204-TKT-COLANGELI | 2013-06-04 17:34 | CDW | 2013-06-07 | 0 | 0 | 0 | 2013-06-07 |  |  | complete | 100%
1204-90-HV-DSH-044 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TEA ROOM IN ADMINSTRATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 15:16 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DSH-066 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR TRAINING | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:43 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-30-ST-DWG-344 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / BEAMS (G.A. PLAN & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0393 | 2016-12-28 |  | No | 1223 | 1204-Owner-v | 2016-12-28 16:37 | CDW | 2016-12-28 | 0 | 0 | 0 | 2016-12-28 |  |  | complete | 100%
1204-00-EL-DWG-022 | 02 | OVERALL HAZARDOUS AREA CLASSIFICATION DRAWING | DE | IFR | EL | PS-OT-T-0304 | 2016-07-11 | 2016-07-24 10:42 | Yes | -1 | 1204-Owner-v | 2016-07-12 13:44 | CDW | 2020-08-30 | 0 | 0 | 2020-08-30 | 2016-07-21 |  |  | InProgress | 80%
1204-10-PI-ISO-6100 | 01 | U/G ISOMETRIC DRAWING OF AREA-61 | DE | IFC-WH | PI | PS-OT-T-0627 | 2018-06-03 |  | No | 701 | 1204-Owner-v | 2018-06-09 08:21 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * |  |  | InProgress | 90%
1204-30-PI-LST-2300 | 01 | A/G ISOMETRIC LIST OF AREA-23 | DE | IFC-WH | PI | PS-OT-T-0651 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-28 13:27 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * | 2018-08-04 | MT-PS-9609-CS-105 | InProgress | 90%
1204-00-ST-DWG-055 | 01 | PIPE RACK ZONE 8 / CONCRETE STRUCTURE ( R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0069 | 2015-07-01 |  | No | 1769 | 1204-Owner-v | 2015-07-01 15:58 | CDW | 2015-07-01 | 0 | 0 | 0 | 2015-07-01 |  |  | complete | 100%
1204-10-ST-DWG-131 | 03 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 / FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0967 | 2020-05-09 |  | No | -5 | 1204-Owner-v | 2020-05-11 14:14 | CDW | 2019-04-16 | 0 | 0 | 0 | 2019-04-16 |  |  | complete | 100%
1204-10-ST-DWG-149 | 02 | REFORMER (H-1001) / FDN. (R.C. & DETAILS II ) | DE | IFC | ST | PS-OT-T-0672 | 2018-08-28 |  | No | 615 | 1204-Owner-v | 2018-09-01 09:42 | CDW | 2018-09-03 | 0 | 0 | 0 | 2018-09-03 |  |  | complete | 100%
1204-30-ST-DWG-309 | 01 | STRUCTURE "B" FOR D-3003 & E-3003A/B / CONCRETE STRUCTURE (R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0347 | 2016-10-04 |  | No | 1308 | 1204-Owner-v | 2016-10-05 13:55 | CDW | 2016-10-04 | 0 | 0 | 0 | 2016-10-04 |  |  | complete | 100%
1204-90-ST-DWG-901 | 01 | CONTROL ROOM & LABORATORY / FDN.. OF NON BLAST PART(G.A.& DETAILS) | DE | IFC | ST | PS-TM-T-0255 | 2021-09-13 |  | No | -497 | 1204-TKT-COLANGELI | 2013-09-27 10:55 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-00-QC-SOI-206A | 01 | SCOPE OF INSPECTION FOR COLUMNS (GROUP I) | DE | IFP | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1058 | 01 | FIRE STATION / BEAMS & COLUMNS (G.A. PLAN) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:57 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-913 | 01 | CONTROL ROOM & LABORATORY / MISCELLANEOUS DETAILS | DE | IFC | ST | TM-OT-9001-T-0334 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 13:02 | CDW | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-20-ST-DWG-214 | 01 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/CONC. STR. (R.C. DETS. I) | DE | IFC | ST | PS-OT-T-0785 | 2019-04-27 |  | No | 373 | 1204-Owner-v | 2019-04-28 11:15 | CDW | 2019-05-22 | 0 | 0 | 0 | 2019-05-22 |  |  | complete | 100%
1204-00-ST-DWG-184 | 01 | PIPE RACK ZONE 13 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0955 | 2020-04-27 |  | No | 7 | 1204-Owner-v | 2020-04-29 09:01 | CDW | 2020-03-31 | 0 | 0 | 2020-05-31 | * | 2020-04-06 | MT-PS-9609-CS-0324 | complete | 100%
1204-00-ST-REQ-740C | 01 | REQUISITION FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART C) | DE | IFP | ST | PS-OT-T-0886 | 2020-02-09 |  | No | 85 | 1204-Owner-v | 2020-02-10 10:30 | REQ | 2019-12-24 | 0 | 0 | 2019-12-30 | * |  |  | complete | 100%
1204-90-HV-DID-014 | 03 | LABORATORY - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | PS-OT-T-0007 | 2015-03-11 |  | No | 1881 | 1204-Owner-v | 2015-03-17 11:18 | CDW | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DSH-039 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TEA ROOM IN FIRE STATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 15:10 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DSH-054 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET IN ADM./TR./RE. | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:42 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-63-PI-LST-2100 | 01 | A/G ISOMETRIC LIST OF AREA-21 | DE | IFC-WH | PI | PS-OT-T-0933 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 15:58 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-71-PI-ISO-3300 | 00 | A/G ISOMETRIC DRAWING OF AREA-33 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-09 15:15 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-00-DC-PCJ-001 | 04 | VENDOR DOCUMENT MANAGEMENT PROCEDURE | DE | IFE | QA | PS-OT-T-10000 | 2020-12-20 |  | No | -230 | 1204-Owner-v | 2020-01-28 10:37 | VDR | 2020-01-28 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PI-LST-3900 | 00 | A/G ISOMETRIC LIST OF AREA-39 | DE | IFR | PI | PS-OT-T-0344 | 2016-10-02 |  | No | 1310 | 1204-Owner-v | 2016-10-04 10:01 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-10-10 |  |  | InProgress | 80%
1204-10-IN-DWG-046 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 46) | DE | IFR | IN | PS-OT-T-0353 | 2016-10-19 |  | No | 1293 | 1204-Owner-v | 2016-10-23 11:02 | CDW | 2020-06-26 | 0 | 0 | 2020-06-26 | * | 2017-05-07 | MT-PS-9301-CS-224-R | InProgress | 80%
1204-00-EL-DSH-5038 | 00 | DATA SHEET FOR LV SWITCHGEAR (SS01-SWB3A,B,C-02) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:27 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:07 | DSH | 2020-05-08 | 0 | 0 | 2020-05-08 | * | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-40-ST-DWG-452 | 02 | BOILER (PU-4006 B ) / FDN. (G.A. & R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0237 | 2016-04-13 |  | No | 1482 | 1204-Owner-v | 2016-04-16 14:16 | CDW | 2016-04-19 | 0 | 0 | 0 | 2016-04-19 |  |  | complete | 100%
1204-02-EL-SLD-056 | 00 | SINGLE LINE DIAGRAM FOR 02-LP-01 | DE | IFR | EL | PS-OT-T-0203 | 2016-02-28 | 2016-07-21 14:58 | Yes | 130 | 1204-Owner-v | 2016-02-29 10:40 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 |  |  |  | InProgress | 80%
1204-03-EL-DWG-002 | 00 | POWER LAYOUT AREA-03 AE-3002 | DE | IFR | EL | PS-OT-T-0204 | 2016-02-28 | 2016-07-23 10:07 | Yes | 132 | 1204-Owner-v | 2016-03-02 15:18 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | * | 2016-04-05 | MT-PS-9301-CS-119-1 | InProgress | 80%
1204-00-PR-LST-016 | 00 | EFFLUENT SUMMARY | DE | IFR | PR | PS-OT-T-447 | 2017-05-06 |  | No | 1094 | 1204-Owner-v | 2017-05-07 13:29 | LIST | 2020-08-20 | 0 | 0 | 2020-08-20 | 2017-05-07 |  |  | InProgress | 90%
1204-00-EL-SLD-023 | 01 | SINGLE LINE DIAGRAM FOR LV VSD PANEL MS-VSD-01 | DE | IFR | EL | PS-OT-T-0735 | 2018-12-22 | 2019-01-22 16:25 | Yes | 17 | 1204-Owner-v | 2018-12-23 11:59 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * |  |  | InProgress | 80%
1204-30-PI-ISO-2400 | 00 | A/G ISOMETRIC DRAWING OF AREA-24 | DE | IFR | PI | PS-OT-T-0437 | 2017-04-09 |  | No | 1121 | 1204-Owner-v | 2017-04-16 14:53 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2017-04-25 |  |  | InProgress | 80%
1204-61-ST-DWG-554 | 00 | ASU (E-6124) / FDN. (G.A. & R.C.) | DE | IFR | ST | PS-OT-T-0653 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-30 17:04 | CDW | 2018-07-23 | 0 | 0 | 0 | 2018-07-23 | 2018-08-04 | MT-PS-9609-CS-104 | InProgress | 80%
1204-00-ST-REQ-742 | 02 | REQUISITION FOR ANCHOR BOLTS | DE | IFI | ST | PS-OT-T-0248 | 2016-04-19 |  | No | 1476 | 1204-Owner-v | 2016-04-20 08:34 | REQ | 2016-04-25 | 0 | 0 | 0 | 2016-04-25 |  |  | complete | 100%
1204-00-IN-DSH-615 | 00 | DATA SHEET FOR SIGHT GLASSES | DE | IFR | IN | PS-OT-T-446 | 2017-04-29 |  | No | 1101 | 1204-Owner-v | 2017-05-07 11:36 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2017-01-24 | MT-PS-9301-CS-206 | InProgress | 80%
1204-30-ST-DWG-340 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / FDN. ( R.C. DET. II ) | DE | IFC | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 07:51 | CDW | 2017-01-01 | 0 | 0 | 0 | 2017-01-01 |  |  | complete | 100%
1204-00-EL-DSH-511 | 00 | DATA SHEET FOR 230V AC UPS (MS-UPS-01) | DE | IFR | EL | PS-OT-T-481 | 2017-09-11 |  | No | 966 | 1204-Owner-v | 2017-09-13 11:37 | DSH | 2020-04-21 | 0 | 0 | 2020-04-21 | * | 2018-06-10 | MT-PS-9301-CS-250-R | InProgress | 80%
1204-00-ST-DWG-1128 | 01 | DV-6301 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0562 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-27 09:30 | CDW | 2018-02-21 | 0 | 0 | 0 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-038 | complete | 100%
1204-10-ST-DWG-157 | 01 | REFORMER (VERTICAL CONVECTION SECTION) FDN. (R.C.) | DE | IFC | ST | PS-OT-T-0675 | 2018-09-05 |  | No | 607 | 1204-Owner-v | 2018-09-11 13:55 | CDW | 2018-09-05 | 0 | 0 | 0 | 2018-09-05 | 2018-08-03 | MT-PS-9609-CS-103 | complete | 100%
1204-84-HS-DSH-012 | 01 | DATA SHEET FOR SANITARY WATER COLLECTION BASIN (SU-8405) | DE | IFR | HSE | PS-OT-T-0854 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:52 | DSH | 2020-10-10 | 0 | 0 | 2020-10-10 | * | 2020-02-12 | MT-PS-9301-CS-0269-1 | InProgress | 80%
1204-10-ST-DWG-133 | 01 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 /STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0788 | 2019-05-08 |  | No | 362 | 1204-Owner-v | 2019-05-12 11:19 | CDW | 2019-05-13 | 0 | 0 | 0 | 2019-05-13 |  |  | complete | 100%
1204-64-PI-APL-3000 | 00 | PIPING PLAN AREA-30 | DE | IFR | PI | PS-OT-T-0071 | 2015-07-05 |  | No | 1765 | 1204-Owner-v | 2015-07-05 16:02 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2015-07-05 | 2015-08-29 | MT-PS-9301-CS-011 | InProgress | 80%
1204-00-PI-APL-3700 | 00 | PIPING PLAN AREA-37 | DE | IFR | PI | PS-OT-T-0282 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:45 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 | 2016-06-20 | MT-PS-9301-CS-162 | InProgress | 80%
1204-00-PI-LST-3800 | 00 | A/G ISOMETRIC LIST OF AREA-38 | DE | IFR | PI | PS-OT-T-0331 | 2016-08-30 |  | No | 1343 | 1204-Owner-v | 2016-08-31 13:33 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-09-03 |  |  | InProgress | 80%
1204-10-IN-DWG-045 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 45) | DE | IFR | IN | PS-OT-T-335 | 2016-09-05 |  | No | 1337 | 1204-Owner-v | 2016-09-06 14:19 | CDW | 2020-06-25 | 0 | 0 | 2020-06-25 | * | 2016-09-17 | MT-PS-9301-CS-188-R | InProgress | 80%
1204-10-PI-ISO-4600 | 00 | A/G ISOMETRIC DRAWING OF AREA-46 | DE | IFR | PI | PS-OT-T-0349 | 2016-10-10 |  | No | 1302 | 1204-Owner-v | 2016-10-23 09:12 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-19 |  |  | InProgress | 80%
1204-00-EL-DSH-5037 | 00 | DATA SHEET FOR LV SWITCHGEAR (SS01-SWB3A,B-01) | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:27 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:03 | DSH | 2020-05-11 | 0 | 0 | 2020-05-11 | * | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-EL-SLD-010 | 00 | SINGLE LINE DIAGRAM FOR 400V SWITCHGEAR -SS01-SWB3A,B,C-02 | DE | IFR | EL | PS-OT-T-0523 | 2017-12-25 | 2018-06-30 10:58 | Yes | 173 | 1204-Owner-v | 2017-12-30 13:40 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * | 2018-05-31 | MT-PS-9609-CS-008-R | InProgress | 80%
1204-22-IN-DWG-019 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 19) | DE | IFR | IN | PS-OT-T-0275 | 2016-06-05 |  | No | 1429 | 1204-Owner-v | 2016-06-05 16:02 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | * | 2016-08-15 | MT-PS-9301-CS-163-R | InProgress | 80%
1204-40-ST-DWG-460 | 01 | BOILER (PU-4006 A ) / FDN. ( R.C. DETAILS III ) | DE | IFC | ST | PS-OT-T-0243 | 2016-04-16 |  | No | 1479 | 1204-Owner-v | 2016-04-17 14:21 | CDW | 2016-04-16 | 0 | 0 | 0 | 2016-04-16 |  |  | complete | 100%
1204-05-EL-DWG-021 | 00 | EARTHING LAYOUT AREA-05 AE-3002 | DE | IFR | EL | PS-OT-T-0204 | 2016-02-28 | 2016-07-23 10:10 | Yes | 132 | 1204-Owner-v | 2016-03-02 15:18 | CDW | 2020-07-30 | 0 | 0 | 2020-07-30 | * | 2016-04-05 | MT-PS-9301-CS-119-1 | InProgress | 80%
1204-00-ST-DWG-1129 | 02 | DV-6301 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0571 | 2018-03-05 |  | No | 791 | 1204-Owner-v | 2018-03-12 15:06 | CDW | 2018-03-13 | 0 | 0 | 0 | 2018-03-13 | 2018-03-07 | MT-PS-9609-CS-041-R | complete | 100%
1204-20-ST-DWG-1171 | 02 | STRUCTURE "M" FOR R-2001 / STEEL STRUCTURE (PLAN &DETS.) | DE | IFC | ST | PS-OT-T-0743 | 2019-01-05 |  | No | 485 | 1204-Owner-v | 2019-01-12 11:22 | CDW | 2019-01-08 | 0 | 0 | 0 | 2019-01-08 |  |  | complete | 100%
1204-00-QC-SOI-522 | 00 | SCOPE OF INSPECTION FOR MV ELECTRICAL MOTORS FOR PRIMERY REFORMER | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-944 | 03 | SUBSTATION / SLABS (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0014 | 2015-04-04 |  | No | 1857 | 1204-Owner-v | 2015-04-05 16:10 | CDW | 2015-04-04 | 0 | 0 | 0 | 2015-04-04 |  |  | complete | 100%
1204-90-ST-DWG-970 | 01 | ADMINISTRATION , RESTAURANT & CLINIC BLDG. / G.A FOR SECOND FLOOR PLAN | DE | IFC | ST | TM-OT-9001-T-0116 | 2012-06-19 |  | No | 2876 | 1204-Owner-v | 2015-09-16 18:35 | CDW | 2012-06-19 | 0 | 0 | 0 | 2012-06-19 |  |  | complete | 100%
1204-00-QC-SOI-525 | 00 | SCOPE OF INSPECTION FOR SOCKET OUTLET AND PLUGS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-994 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / PLUMBING (RISER DIAGRAM) | DE | IFR | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 14:28 | CDW | 2020-04-30 | 0 | 0 | 2020-04-30 | 2013-01-10 |  |  | InProgress | 80%
1204-10-ST-DWG-1231 | 01 | STRUCTURE "H" FOR E-1011 / FDN. & STRUCTURE (PLAN , SECTIONS & DETS.) | DE | IFC | ST | PS-OT-T-0820 | 2019-07-29 |  | No | 280 | 1204-Owner-v | 2019-07-30 10:51 | CDW | 2019-08-01 | 0 | 0 | 0 | 2019-08-01 |  |  | complete | 100%
1204-10-ST-DWG-1234 | 02 | STRUCTURE "L" FOR E-1008 / FDN. & STRUCTURE (PLAN , SECTIONS & DETS.) | DE | IFC | ST | PS-OT-T-0819 | 2019-07-22 |  | No | 287 | 1204-Owner-v | 2019-07-24 11:58 | CDW | 2019-07-30 | 0 | 0 | 0 | 2019-07-30 |  |  | complete | 100%
1204-01-EL-DWG-020 | 00 | EARTHING LAYOUT - AREA 01 | DE | IFR | EL | TM-OT-9001-T-0328 | 2013-10-11 |  | No | 2397 | 1204-TKT-COLANGELI | 2013-10-11 10:47 | CDW | 2020-06-10 | 0 | 0 | 2020-06-10 | 2013-10-11 |  |  | InProgress | 80%
1204-04-EL-DWG-020 | 01 | EARTHING LAYOUT - AREA 04 | DE | IFR | EL | PS-OT-T-0296 | 2016-06-25 | 2016-07-21 14:41 | Yes | 12 | 1204-Owner-v | 2016-06-26 08:30 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | * | 2016-06-29 | MT-PS-9301-CS-168 | InProgress | 80%
1204-90-EL-SLD-035 | 01 | SUBSTATION EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:44 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:41 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-037 | 01 | CONTROL ROOM EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:40 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:42 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-IN-DSH-612 | 01 | DATA SHEET FOR ORIFICE PLATE & FLANGES | DE | IFR | IN | PS-OT-T-0174 | 2016-01-05 |  | No | 1581 | 1204-Owner-v | 2016-01-06 11:04 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2016-01-18 | MT-PS-9301-CS-089 | InProgress | 80%
1204-00-PI-LST-1200 | 00 | A/G ISOMETRIC LIST OF AREA-12 | DE | IFR | PI | PS-OT-T-0175 | 2016-01-06 |  | No | 1580 | 1204-Owner-v | 2016-01-07 12:47 | CDW | 2020-05-25 | 0 | 0 | 2020-05-25 | 2016-01-16 |  |  | InProgress | 80%
1204-20-PI-LST-2600 | 01 | A/G ISOMETRIC LIST OF AREA-26 | DE | IFC-WH | PI | PS-OT-T-0671 | 2018-08-25 |  | No | 618 | 1204-Owner-v | 2018-08-28 18:15 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-00-PR-EQL-001 | 00 | EQUIPMENT LIST FOR PROCESS UNIT | DE | IFR | PR | PS-OT-T-0138 | 2015-11-28 |  | No | 1619 | 1204-Owner-v | 2015-11-29 11:59 | LIST | 2020-03-31 | 0 | 0 | 2020-05-06 | 2015-12-01 | 2015-12-05 | MT-PS-9301-CS-051 | InProgress | 90%
1204-30-IN-DWG-023 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 23) | DE | IFR | IN | PS-OT-T-0140 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 09:06 | CDW | 2020-06-22 | 0 | 0 | 2020-06-22 | 2015-12-15 | 2016-01-12 | MT-PS-9301-CS-086 | InProgress | 80%
1204-10-HM-REQ-251A | 00 | REQUSITION FOR PRIMARY REFORMER PACKAGE | DE | IFI | MD | PS-OT-T-0199 | 2016-02-15 |  | No | 1540 | 1204-Owner-v | 2016-02-20 11:05 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-EL-SLD-024 | 01 | SINGLE LINE DIAGRAM FOR LV VSD PANEL MS-VSD-02 | DE | IFR | EL | PS-OT-T-0735 | 2018-12-22 | 2019-01-22 16:26 | Yes | 17 | 1204-Owner-v | 2018-12-23 11:59 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | * |  |  | InProgress | 80%
1204-00-ST-DWG-1120 | 01 | DV-6101 /FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0562 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-27 09:25 | CDW | 2018-02-21 | 0 | 0 | 0 | 2018-02-21 | 2018-02-27 | MT-PS-9609-CS-038 | complete | 100%
1204-00-ST-MTO-1122 | 00 | MATERIAL TAKE OFF FOR DV-6101 | DE | IFE | ST | PS-OT-T-0594 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-28 08:38 | LIST | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 | 2018-05-09 | MT-PS-9609-CS-064 | complete | 100%
1204-10-QC-SOI-202G | 00 | SCOPE OF INSPECTION FOR STEEL STRUCTURE OF WASTE HEAT BOILER | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-ST-DWG-1117 | 02 | RETAINING WALL (WEST) / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0764 | 2019-03-12 |  | No | 419 | 1204-Owner-v | 2019-03-13 10:15 | CDW | 2019-03-16 | 0 | 0 | 0 | 2019-03-16 |  |  | complete | 100%
1204-00-HM-REQ-256A | 01 | REQUISITION FOR COOLING WATER SIDE STREAM FILTERS | DE | IFI | MD | PS-OT-T-0315 | 2016-08-03 |  | No | 1370 | 1204-Owner-v | 2016-08-03 18:06 | REQ | 2016-08-03 | 0 | 0 | 0 | 2016-08-03 |  |  | InProgress | 90%
1204-20-PV-DSH-226 | 00 | MECHANICAL DATA SHEET FOR CONVERTER STEAM DRUM (D-2003) | DE | IFR | MD | TM-OT-9001-T-0197 | 2012-10-30 |  | No | 2743 | 1204-Owner-v | 2015-09-16 17:39 | DSH | 2012-10-30 | 0 | 0 | 0 | 2012-10-30 |  |  | complete | 100%
1204-64-RE-DSH-052 | 00 | DATA SHEET FOR CAUSTIC TRANSFER PUMPS (P-6404 A/B) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-07 16:48 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-90-HV-DSH-201 | 02 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:17 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-63-PR-DSH-140 | 00 | Process Instrument Data Sheet for Temperature Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-64-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR WATER POLISHING SYSTEM SYSTEM | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:20 | LIST | 2020-04-01 | 0 | 0 | 2020-05-06 | 2013-08-06 |  |  | InProgress | 90%
1204-72-PR-LST-002 | 00 | LINE LIST FOR CRUDE METHANOL STORAGE TANK | BE | IFR | PR | TM-OT-9001-T-0297 | 2013-07-03 |  | No | 2497 | 1204-TKT-COLANGELI | 2013-07-02 19:23 | LIST | 2020-04-01 | 0 | 0 | 2020-05-06 | 2013-07-03 |  |  | InProgress | 90%
1204-72-PR-PID-721 | 02 | PIPING & INSTRUMENTATION DIAGRAM FOR CRUDE METHANOL STORAGE TANK SYSTEM | BE/DE | IFE | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:59 | EDW | 2013-08-06 | 0 | 0 | 0 | 2013-08-06 |  |  | complete | 100%
1204-30-ST-DWG-301 | 01 | STRUCTURE "B" FOR D-3003 & E-3003A/B / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0279 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-13 09:03 | CDW | 2016-06-12 | 0 | 0 | 0 | 2016-06-12 |  |  | complete | 100%
1204-90-ST-DWG-989 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / CONCRETE STAIR (G.A. , R.C. & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:20 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-936 | 02 | SUBSTATION / ELEVATIONS | DE | IFC-WH | ST | TM-OT-9001-T-0368 | 2014-05-20 |  | No | 2176 | 1204-TKT-COLANGELI | 2014-05-20 14:02 | CDW | 2014-05-20 | 0 | 0 | 0 | 2014-05-20 |  |  | complete | 100%
1204-00-PR-UDD-017 | 02 | UTILITY DISTRIBUTION DIAGRAM FOR METHANOL DRAIN RECOVERY SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:24 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2017-02-23 |  |  | InProgress | 80%
1204-30-PV-DSH-221 | 00 | Mechanical data sheet for first Condensate Separator (D-3006) | DE | IFR | MD | TM-OT-9001-T-0114 | 2012-06-13 |  | No | 2882 | 1204-Owner-v | 2015-09-16 17:47 | DSH | 2012-06-13 | 0 | 0 | 0 | 2012-06-13 |  |  | complete | 100%
1204-00-EL-REQ-520 | 01 | REQUISITION FOR EXPLOSION PROOF LIGHTING FIXTURES | DE | IFI | EL | PS-OT-T-0892 | 2020-02-16 |  | No | 78 | 1204-Owner-v | 2020-02-26 17:06 | REQ | 2020-01-07 | 0 | 0 | 2020-01-20 | * |  |  | InProgress | 90%
1204-20-IN-DWG-027 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 27) | DE | IFR | IN | PS-OT-T-0140 | 2015-12-05 |  | No | 1612 | 1204-Owner-v | 2015-12-06 09:09 | CDW | 2020-06-22 | 0 | 0 | 2020-06-22 | 2015-12-15 | 2016-01-12 | MT-PS-9301-CS-086 | InProgress | 80%
1204-40-PV-DSH-223 | 01 | MECHANICAL DATA SHEET FOR BLOWDOWN DRUM (D-4002) | DE | IFE | MD | TM-OT-9001-T-0214 | 2012-12-11 |  | No | 2701 | 1204-TKT-COLANGELI | 2012-12-11 14:41 | DSH | 2012-12-11 | 0 | 0 | 0 | 2012-12-11 |  |  | complete | 100%
1204-00-EL-REQ-514 | 01 | REQUISITION FOR CCTV SYSTEM | DE | IFI | EL | PS-OT-T-0889 | 2020-02-12 |  | No | 82 | 1204-Owner-v | 2020-02-16 14:20 | REQ | 2020-06-09 | 0 | 0 | 2020-06-22 | * | 2020-03-07 | MT-PS-9609-CS-0304 | InProgress | 90%
1204-00-IN-DWG-010 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 10) | DE | IFR | IN | PS-OT-T-0167 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:53 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-01-06 | 2016-01-10 | MT-PS-9301-CS-082 | InProgress | 80%
1204-64-RE-DSH-049 | 00 | DATA SHEET FOR CONDENSATE TRANSFER PUMPS (P-6401 A/B) | DE | IFR | MC | PS-OT-T-0386 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:17 | DSH | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 | 2017-03-03 | MT-PS-9301-CS-221 | InProgress | 80%
1204-90-HV-DSH-005 | 03 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR HVAC ROOM IN CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:16 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-90-HV-DSH-010 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR LABORATORY | DE | IFE | HV | PS-OT-T-0009 | 2015-03-14 |  | No | 1878 | 1204-TKT-COLANGELI | 2015-03-04 13:39 | DSH | 2015-03-14 | 0 | 0 | 0 | 2015-03-14 |  |  | complete | 100%
1204-90-HV-DSH-060 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR CLINIC | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:42 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-095 | 01 | DATA SHEET FOR ROOF TYPE EXHAUST FAN FOR FF TOILET IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:50 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-71-HS-PID-001 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR SPRAY NOZZLE SYSTEM FOR TK-7101 A/B | DE | IFR | HSE | PS-OT-T-0012 | 2015-03-17 |  | No | 1875 | 1204-Owner-v | 2015-03-25 13:27 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * |  |  | InProgress | 80%
1204-00-ST-DWG-071 | 01 | PIPE RACK ZONE 11 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0316 | 2016-08-03 |  | No | 1370 | 1204-Owner-v | 2016-08-03 18:04 | CDW | 2016-08-03 | 0 | 0 | 0 | 2016-08-03 |  |  | complete | 100%
1204-30-ST-DWG-342 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 07:54 | CDW | 2017-01-01 | 0 | 0 | 0 | 2017-01-01 |  |  | complete | 100%
1204-00-PR-PID-009 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR NUMBERING PROCEDURE I | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:29 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-20-PR-PID-202 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNGAS COMPRESSOR TURBINE & HP STEAM STATION LET DOWN | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:09 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-22-PR-DSH-135 | 00 | Process Instrument Data Sheet for Orifice Plate and Flanges | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-22-PR-DSH-137 | 00 | Process Instrument Data Sheet for Level Transmitters | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-62-PR-DSH-137 | 00 | Process Instrument Data Sheet for Pressure Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-07-24 |  |  | InProgress | 80%
1204-63-PR-DSH-137 | 00 | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE GAUGES | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-64-PR-DSH-133 | 00 | Process Instrument Data Sheet for Level Transmitters | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-00-ST-DWG-086 | 01 | PIPE RACK STAIRS (ZONE 6 TO 9) / STRUCTURE (G.A. & SECTIONS I ) | DE | IFC | ST | PS-OT-T-0254 | 2016-05-02 |  | No | 1463 | 1204-Owner-v | 2016-05-03 13:11 | CDW | 2016-05-02 | 0 | 0 | 0 | 2016-05-02 |  |  | complete | 100%
1204-90-ST-DWG-973 | 03 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FURNITURE PLAN FOR SECOND FLOOR PLAN | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-14 09:52 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 0 | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-90-ST-DWG-975 | 00 | ADMINISTRATION , RESTAURANT & CLINIC BLDG / NORTH & SOUTH ELEVATION & DETAILS | DE | IFR | ST | TM-OT-9001-T-0116 | 2012-06-19 |  | No | 2876 | 1204-Owner-v | 2015-09-16 18:35 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 2012-06-19 |  |  | InProgress | 80%
1204-00-HV-SDG-785 | 01 | HVAC GENERAL NOTES AND SYMBOLS | DE | IFC | HV | TM-OT-9001-T-0422 | 2014-12-11 |  | No | 1971 | 1204-TKT-COLANGELI | 2014-12-10 15:16 | SPEC | 2014-12-11 | 0 | 0 | 0 | 2014-12-11 |  |  | complete | 100%
1204-00-QC-SOI-204C | 00 | SCOPE OF INSPECTION FOR High Pressure Vessels C (Stailess Steel) | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-90-ST-DWG-1035 | 01 | WAREHOUSE / LINTEL , FINISHING & FALSE CEILING PLAN | DE | IFC | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 19:13 | CDW | 2013-01-10 | 0 | 0 | 0 | 2013-01-10 |  |  | complete | 100%
1204-00-PI-REQ-418 | 00 | REQUISITION for FITTING FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:20 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-00-IN-REQ-608 | 00 | REQUISITION FOR ANNUBAR FLOW ELEMENT | DE | IFI | IN | PS-OT-T-0392 | 2016-12-27 |  | No | 1224 | 1204-Owner-v | 2017-01-11 12:16 | REQ | 2020-06-09 | 0 | 0 | 2020-06-22 | * | 2017-01-31 | MT-PS-9301-CS-206-R | InProgress | 90%
1204-00-PI-MTO-464A | 03 | MATERIAL TAKE OFF FOR U/G VALVES (MTO I) | DE | IFE | PI | PS-OT-T-0348 | 2016-10-08 |  | No | 1304 | 1204-Owner-v | 2016-10-09 11:01 | LIST | 2016-10-19 | 0 | 0 | 0 | 2016-10-19 |  |  | complete | 100%
1204-00-PI-REQ-415A | 00 | REQUISITION FOR SAMPLE COOLER(MTO I) | DE | IFI | PI | PS-OT-T-0936 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 16:04 | REQ | 2020-05-28 | 0 | 0 | 2020-06-03 | * | 2020-03-17 | MT-PS-9609-CS-0315 | InProgress | 90%
1204-63-PR-DIG-001 | 00 | CAUSE AND EFFECT DIAGRAM FOR COOLING WATER SYSTEM | BE | IFR | PR | TM-OT-9001-T-0310 | 2013-08-06 |  | No | 2463 | 1204-TKT-COLANGELI | 2013-08-06 12:17 | LIST | 2020-03-30 | 0 | 0 | 2020-05-06 | 2013-08-06 |  |  | InProgress | 90%
1204-63-PR-PID-632 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR COOLING WATER SYSTEM INJECTION PACKAGES 1 OF 2 | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:29 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | * | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-63-PR-PID-633 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR COOLING WATER SYSTEM INJECTION PACKAGES 2 OF 2 | DE | IFR | PR | PS-OT-T-0417 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:29 | EDW | 2020-05-01 | 0 | 2020-05-30 | 2020-06-30 | 2017-02-23 | 2017-02-25 | MT-PS-9301-CS-215 | InProgress | 80%
1204-30-RE-DSH-044 | 01 | DATA SHEET FOR WASTE METHANOL PUMP (P-3007) | DE | IFR | MC | PS-OT-T-0387 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:21 | DSH | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 | 2017-05-03 | MT-PS-9301-CS-225-R | InProgress | 80%
1204-90-HV-DSH-063 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TEA ROOM IN CLINIC AND TRAINING | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:43 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-103 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR PRD IN CONTROL ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:49 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-90-HV-DSH-251 | 01 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 12:00 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DWG-013 | 02 | LABORATORY - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | PS-OT-T-0007 | 2015-03-11 |  | No | 1881 | 1204-Owner-v | 2015-03-17 11:19 | CDW | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-90-HV-DSH-108 | 02 | DATA SHEET FOR BLAST PROTECTION VALVE FOR LOUVER IN HVAC ROOM IN CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0383 | 2014-07-07 |  | No | 2128 | 1204-TKT-COLANGELI | 2014-07-07 12:56 | DSH | 2014-07-07 | 0 | 0 | 0 | 2014-07-07 | 2014-11-22 | MT-TM-9301-CS-014 | complete | 100%
1204-71-RE-DSH-057 | 02 | DATA SHEET FOR DAILY METHANOL TRANSFER PUMPS (P-7101 A/B) | DE | IFR | MC | PS-OT-T-0870 | 2020-01-13 |  | No | 112 | 1204-Owner-v | 2020-01-19 09:50 | DSH | 2020-01-13 | 0 | 0 | 0 | 0 | 0 |  | InProgress | 80%
1204-00-EL-SLD-021 | 00 | SINGLE LINE DIAGRAM FOR 230V AC UPS | DE | IFR | EL | TM-OT-9001-T-0269 | 2013-05-06 | 2015-03-03 08:17 | Yes | 652 | 1204-Owner-v | 2015-09-16 16:33 | CDW | 2020-09-30 | 0 | 0 | 2020-09-30 | 2013-05-06 |  |  | InProgress | 80%
1204-90-HS-DWG-005 | 02 | FIRE AND GAS ALARM LAYOUT FOR ADMINISTRATION, RESTAURANT, CLINIC AND GUARDHOUSE BUILDING | DE | IFE | HSE | PS-OT-T-0714 | 2018-11-04 |  | No | 547 | 1204-Owner-v | 2018-11-11 11:02 | EDW | 2018-11-14 | 0 | 0 | 0 | 2018-11-14 |  |  | complete | 100%
1204-90-HS-DWG-012 | 01 | SAFETY EQUIPMENT LAYOUT FOR GUARD HOUSE | DE | IFC | HSE | PS-OT-T-0102 | 2015-09-13 |  | No | 1695 | 1204-Owner-v | 2015-09-14 09:52 | EDW | 2015-09-13 | 0 | 0 | 0 | 2015-09-13 | 2015-10-31 | MT-PS-9301-CS-036 | complete | 100%
1204-63-PI-ISO-1700 | 00 | A/G ISOMETRIC DRAWING OF AREA-17 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:14 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-71-PI-ISO-7400 | 03 | U/G ISOMETRIC DRAWING OF AREA-74 | DE | IFC-WH | PI | PS-OT-T-0598 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:32 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-03 |  |  | InProgress | 90%
1204-10-PI-UPL-7100 | 02 | UNDER GROUND PIPING PLAN AREA-71 | DE | IFC-WH | PI | PS-OT-T-0618 | 2018-05-23 |  | No | 712 | 1204-Owner-v | 2018-06-03 10:53 | CDW | 2018-06-02 | 0 | 0 | 0 | 2018-06-02 | 2018-05-23 | MT-PS-9609-CS-076 | InProgress | 90%
1204-30-PR-PID-310 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-TMA REMOVAL SYSTEM | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:45 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-10-PV-DSH-203 | 00 | MECHANICAL DATA SHEET FOR PRE-REFORMER REACTOR (R-1003) | DE | IFR | MD | PS-OT-T-0124 | 2015-11-02 |  | No | 1645 | 1204-Owner-v | 2015-11-02 16:29 | DSH | 2015-11-04 | 0 | 0 | 0 | 2015-11-04 | 2015-11-14 | MT-PS-9301-CS-041 | InProgress | 80%
1204-10-RE-DSH-058 | 00 | DATA SHEET FOR PROCESS CONDENSATE PUMPS P-1001 A/B | DE | IFR | MC | PS-OT-T-0386 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:17 | DSH | 2016-12-25 | 0 | 0 | 0 | 2016-12-25 | 2017-03-03 | MT-PS-9301-CS-221 | InProgress | 80%
1204-00-IN-DWG-034 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 34) | DE | IFR | IN | PS-OT-T-357 | 2016-11-02 |  | No | 1279 | 1204-Owner-v | 2016-11-09 09:51 | CDW | 2020-06-24 | 0 | 0 | 2020-06-24 | * | 2017-01-11 | MT-PS-9301-CS-195-R | InProgress | 80%
1204-63-IN-DWG-021 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 21) | DE | IFR | IN | PS-OT-T-0275 | 2016-06-05 |  | No | 1429 | 1204-Owner-v | 2016-06-05 16:03 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | * | 2016-08-15 | MT-PS-9301-CS-163-R | InProgress | 80%
1204-00-QC-SOI-516 | 00 | SCOPE OF INSPECTION FOR RADIO SYSTEM | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-RE-REQ-307A | 02 | REQUISITION FOR CENTRIFUGAL PUMPS (GROUP A) | DE | IFP | MC | PS-OT-T-0495 | 2017-10-04 |  | No | 943 | 1204-Owner-v | 2017-10-04 16:10 | REQ | 2017-10-09 | 0 | 0 | 0 | 2017-10-09 |  |  | complete | 100%
1204-00-EL-REQ-531 | 00 | REQUISITION FOR CABLE TRAYS AND LADDERS | DE | IFI | EL | PS-OT-T-0732 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 11:57 | REQ | 2019-12-20 | 0 | 0 | 2019-12-26 | * |  |  | InProgress | 90%
1204-30-HM-DSH-239 | 00 | MECHANICAL DATA SHEET FOR CONDENSER/REBOILER (E-3003A/B/C/D) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:10 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DSH-050 | 01 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:41 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-052 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR RESTAURANT | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:41 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-200 | 02 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:17 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-64-IN-DWG-020 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 20) | DE | IFR | IN | PS-OT-T-0147 | 2015-12-09 |  | No | 1608 | 1204-Owner-v | 2015-12-09 11:59 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | 2015-12-15 | 2016-02-09 | MT-PS-9301-CS-104 | InProgress | 80%
1204-00-ST-MTO-1146 | 00 | MATERIAL TAKE OFF FOR VB-6303 | DE | IFE | ST | PS-OT-T-0594 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-28 08:39 | LIST | 2018-05-17 | 0 | 0 | 0 | 2018-05-17 | 2018-05-09 | MT-PS-9609-CS-064 | complete | 100%
1204-00-QC-SOI-466A | 00 | SCOPE OF INSPECTION FOR U/G POLYPROPYLENE ITEMS(MTO I) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-10-QC-SOI-251R | 00 | SUPPLY OF REFRACTORIES FOR PRIMARY REFORMER PACKAGE (INCLUDING ANCHORS AND DESIGN/LAYOUT DRAWINGS) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-PI-MTO-417 | 01 | MATERIAL TAKE OFF FOR PIPE FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0953 | 2020-04-21 |  | No | 13 | 1204-Owner-v | 2020-04-22 18:40 | MTO | 2020-04-21 | #N/A | #N/A | #N/A | 0 | 0 | 0 | complete | 100%
1204-00-PI-MTO-419 | 00 | MATERIAL TAKE OFF FOR FLANGE FOR FLARE AND UTILITY LINE(OSBL) | DE | IFE | PI | PS-OT-T-0944 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:42 | MTO | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-RE-TBA-307A | 01 | TECHNICAL BID ANALYSIS FOR CENTRIFUGAL PUMPS (GROUP A) | DE | IFE | MC | PS-OT-T-0787 | 2019-05-07 |  | No | 363 | 1204-Owner-v | 2019-05-07 13:04 | TBA | 2019-05-07 | 0 | 0 | 0 | 2019-05-07 |  |  | complete | 100%
1204-71-ST-DWG-750 | 02 | TK-7101 A&B / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0364 | 2014-05-06 |  | No | 2190 | 1204-TKT-COLANGELI | 2014-05-06 12:40 | CDW | 2014-05-06 | 0 | 0 | 0 | 2014-05-06 |  |  | complete | 100%
1204-30-HM-DSH-242 | 00 | MECHANICAL DATA SHEET FOR REFINING GAS HEATED REBOILER (E-3006) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:19 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | InProgress | 80%
1204-90-HV-DSH-092 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR LCR. AND JTR. IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:47 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DWG-081 | 01 | WORKSHOP - HVAC SYSTEM LAYOUT | DE | IFC | HV | TM-OT-9001-T-0290 | 2013-06-07 |  | No | 2523 | 1204-TKT-COLANGELI | 2013-06-04 16:59 | CDW | 2013-06-07 | 0 | 0 | 0 | 2013-06-07 |  |  | complete | 100%
1204-90-HV-DSH-241 | 01 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR ADMINISTRATION | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:58 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-00-ST-DWG-030 | 03 | PIPE RACK ZONE 4 / CONCRETE STRUCTURE ( G.A. PLANS & DETAILS ) | DE | IFC | ST | PS-OT-T-0110 | 2015-10-07 |  | No | 1671 | 1204-Owner-v | 2015-10-08 11:44 | CDW | 2015-10-20 | 0 | 0 | 0 | 2015-10-20 | 2015-10-20 | MT-PS-9301-CS-027 | complete | 100%
1204-00-HS-LST-005 | 01 | EQUIPMENT LIST WITH HAZARDOUS CLASSIFICATION FOR PROCESS UNIT | DE | IFR | HSE | PS-OT-T-0100 | 2015-09-13 |  | No | 1695 | 1204-Owner-v | 2015-09-14 09:40 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | * |  |  | InProgress | 90%
1204-40-PI-LST-6600 | 01 | U/G ISOMETRIC LIST OF AREA-66 | DE | IFC-WH | PI | PS-OT-T-0682 | 2018-09-16 |  | No | 596 | 1204-Owner-v | 2018-09-18 17:37 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-10-02 |  |  | InProgress | 90%
1204-64-PI-ISO-6900 | 01 | U/G ISOMETRIC DRAWING OF AREA-69 | DE | IFC-WH | PI | PS-OT-T-0606 | 2018-05-12 |  | No | 723 | 1204-Owner-v | 2018-05-13 15:33 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-26 |  |  | InProgress | 90%
1204-64-PI-LST-3100 | 00 | A/G ISOMETRIC LIST OF AREA-31 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:04 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2016-09-03 |  |  | InProgress | 80%
1204-00-PI-ISO-3500 | 00 | A/G ISOMETRIC DRAWING OF AREA-35 | DE | IFR | PI | PS-OT-T-0324 | 2016-08-23 |  | No | 1350 | 1204-Owner-v | 2016-08-24 15:19 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-08-29 |  |  | InProgress | 80%
1204-00-PV-REQ-201A | 01 | REQUISITION FOR REACTORS | DE | IFP | MD | PS-OT-T-0255 | 2016-05-07 |  | No | 1458 | 1204-Owner-v | 2016-05-09 12:09 | REQ | 2016-05-07 | 0 | 0 | 0 | 2016-05-07 |  |  | complete | 100%
1204-00-QC-SOI-467A | 00 | SCOPE OF INSPECTION FOR U/G HDPE ITEMS(MTO I) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-10-ST-DWG-162 | 01 | STRUCTURE FOR WHB, ATR, E-1003A/B & D-4001A/B /COMBINED FDN. (R.C. & DETAILS I) | DE | IFC | ST | PS-OT-T-0704 | 2018-10-21 |  | No | 561 | 1204-Owner-v | 2018-10-24 16:57 | CDW | 2018-10-21 | 0 | 0 | 0 | 2018-10-21 |  |  | complete | 100%
1204-00-ST-DWG-1157 | 01 | ADDITIONAL CONCRETE WALLS / G.A. & R.C. DETAILS | DE | IFC | ST | PS-OT-T-0816 | 2019-07-15 |  | No | 294 | 1204-Owner-v | 2019-07-20 16:34 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-00-HS-DSH-010 | 01 | DATA SHEET FOR DELUGE VALVES | DE | IFR | HSE | PS-OT-T-0847 | 2019-12-22 |  | No | 134 | 1204-Owner-v | 2019-12-29 09:12 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * | 2020-03-10 | MT-PS-9301-CS-0309 | InProgress | 80%
1204-82-HS-LST-001 | 02 | LINE LIST FOR FIRE WATER NETWORK | DE | IFC-WH | HSE | PS-OT-T-377 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 09:01 | LIST | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 | 2017-01-30 | MT-PS-9301-CS-209 | complete | 100%
1204-83-HS-DSH-003 | 00 | DATA SHEET FOR K.O. DRUM PUMPS (P-8301 A/B) | DE | IFR | HSE | TM-OT-9001-T-0229 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-09 11:55 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-01-10 |  |  | InProgress | 80%
1204-83-HS-LST-001 | 00 | EQUIPMENT LIST FOR FLARE UNIT | DE | IFR | HSE | PS-OT-T-0016 | 2015-04-08 |  | No | 1853 | 1204-Owner-v | 2015-04-11 10:34 | LIST | 2020-07-15 | 0 | 0 | 2020-07-15 | 2015-04-08 |  |  | InProgress | 90%
1204-00-HV-ESS-783 | 01 | ENGINEERING STANDARD SPECIFICATION FOR HVAC CONTROL SYSTEM | DE | IFE | HV | PS-OT-T-0559 | 2018-02-19 |  | No | 805 | 1204-Owner-v | 2018-02-21 10:49 | SPEC | 2018-03-15 | 0 | 0 | 0 | 2018-03-15 | 2018-05-01 | MT-PS-9609-CS-039-1-R | complete | 100%
1204-00-IN-DSH-628 | 02 | DATA SHEET FOR INSTRUMENT CABLES | DE | IFE | IN | PS-OT-T-0896 | 2020-02-18 |  | No | 76 | 1204-Owner-v | 2020-02-18 16:57 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-04-14 | MT-PS-9609-CS-0277-R | complete | 100%
1204-00-IN-REQ-614 | 00 | REQUISITION FOR ROTAMETERS | DE | IFI | IN | PS-OT-T-0900 | 2020-02-19 |  | No | 75 | 1204-Owner-v | 2020-02-19 16:07 | REQ | 2020-03-03 | 0 | 0 | 2020-03-16 | * | 2020-03-03 | MT-PS-9609-CS-0294 | InProgress | 90%
1204-00-PI-ISO-3400 | 00 | A/G ISOMETRIC DRAWING OF AREA-34 | DE | IFR | PI | PS-OT-T-0287 | 2016-06-13 |  | No | 1421 | 1204-Owner-v | 2016-06-14 09:56 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 |  |  | InProgress | 80%
1204-10-ST-DWG-116 | 01 | E-1004 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0811 | 2019-06-25 |  | No | 314 | 1204-Owner-v | 2019-07-01 10:51 | CDW | 2019-06-25 | 0 | 0 | 0 | 2019-06-25 |  |  | complete | 100%
1204-00-QC-SOI-204D | 00 | SCOPE OF INSPECTION FOR PRESSURE VESSELS (GROUP IV) | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1036 | 01 | WAREHOUSE / MISCELLANEOUS DETAILS | DE | IFC | ST | TM-OT-9001-T-0227 | 2013-01-10 |  | No | 2671 | 1204-TKT-COLANGELI | 2013-01-08 19:25 | CDW | 2013-01-10 | 0 | 0 | 0 | 2013-01-10 |  |  | complete | 100%
1204-90-ST-DWG-948 | 01 | SUBSTATION / CONCRETE STAIR (G.A. , R.C. & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0300 | 2013-07-04 |  | No | 2496 | 1204-TKT-COLANGELI | 2013-07-03 12:10 | CDW | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-90-ST-DWG-969 | 01 | ADMINISTRATION , RESTAURANT & CLINIC BLDG. / G.A FOR FIRST FLOOR PLAN | DE | IFC | ST | TM-OT-9001-T-0116 | 2012-06-19 |  | No | 2876 | 1204-Owner-v | 2015-09-16 18:35 | CDW | 2012-06-19 | 0 | 0 | 0 | 2012-06-19 |  |  | complete | 100%
1204-63-RE-DSH-034 | 02 | DATA SHEET FOR STEAM TURBINE FOR COOLING WATER SUPPLY PUMPS (PT-6301 A/B) | DE | IFE | MC | PS-OT-T-0314 | 2016-07-31 |  | No | 1373 | 1204-Owner-v | 2016-08-03 16:42 | DSH | 2016-08-08 | 0 | 0 | 0 | 2016-08-08 |  |  | complete | 100%
1204-00-EL-REQ-529 | 00 | REQUISITION FOR EARTHING AND LIGHTNING MATERIAL | DE | IFI | EL | PS-OT-T-0669 | 2018-08-20 |  | No | 623 | 1204-Owner-v | 2018-08-21 14:00 | REQ | 2019-12-24 | 0 | 0 | 2019-12-30 | 2018-08-25 | 2018-08-26 | MT-PS-9609-CS-111 | InProgress | 90%
1204-72-ST-MTO-737 | 00 | MATERIAL TAKE OFF FOR TK-7201 | DE | IFE | ST | TM-OT-9001-T-0404 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-30 15:37 | LIST | 2020-09-29 | 0 | 0 | 2020-11-02 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-007 | complete | 100%
1204-30-HM-DSH-241 | 00 | MECHANICAL DATA SHEET FOR FUSEL OIL COOLER (E-3005) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:16 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-EL-DWG-810 | 01 | GUARD HOUSE LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-08-12 15:35 | Yes | 552 | 1204-TKT-COLANGELI | 2014-01-23 12:29 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-019 | 00 | DATA SHEET FOR FLAME DETECTOR | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:15 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HV-REQ-791 | 02 | REQUISITION FOR EXPLOSION PROTECTION VALVES | DE | IFP | HV | TM-OT-9001-T-0386 | 2014-07-15 |  | No | 2120 | 1204-TKT-COLANGELI | 2014-07-15 18:18 | REQ | 2014-07-15 | 0 | 0 | 0 | 2014-07-15 |  |  | complete | 100%
1204-00-IN-DSH-614 | 00 | DATA SHEET FOR ROTAMETERS | DE | IFR | IN | PS-OT-T-0901 | 2020-02-19 |  | No | 75 | 1204-Owner-v | 2020-02-19 16:12 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2020-03-03 | MT-PS-9609-CS-0293 | InProgress | 80%
1204-00-PI-REQ-401B | 00 | REQUISITION FOR A/G PIPES & FITTINGS(MTO II) | DE | IFI | PI | PS-OT-T-0946 | 2020-04-11 |  | No | 23 | 1204-Owner-v | 2020-04-15 11:12 | REQ | 2020-03-18 | 0 | 0 | 2020-03-24 | * |  |  | InProgress | 90%
1204-00-PI-REQ-402A | 01 | REQUISITION FOR A/G FLANGES(MTO I) | DE | IFP | PI | PS-OT-T-0513 | 2017-12-11 |  | No | 875 | 1204-Owner-v | 2017-12-16 11:10 | REQ | 2017-12-11 | 0 | 0 | 0 | 2017-12-11 | 2018-01-08 | MT-PS-9609-CS-004 | complete | 100%
1204-20-PR-PID-204 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS GAS CIRCULATOR TURBINE | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:24 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-30-PR-PID-302 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 300-TOPPING OVERHEAD | DE | IFC-WH | PR | PS-OT-T-0641 | 2018-07-07 |  | No | 667 | 1204-Owner-v | 2018-07-10 09:43 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | * | 2018-07-10 | MT-PS-9609-CS-096 | InProgress | 90%
1204-62-PR-DSH-139 | 00 | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE TRANSMITTERS | BE | IFR | PR | TM-OT-9001-T-0142 | 2012-08-28 |  | No | 2806 | 1204-Owner-v | 2015-09-16 17:57 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-08-28 |  |  | InProgress | 80%
1204-90-ST-DWG-1084 | 01 | GUARD HOUSE / ROOF SLOPING, LINTEL & FINISHING PLAN | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 13:18 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-00-EL-REQ-525 | 01 | REQUISITION FOR SOCKET OUTLET AND PLUGS | DE | IFI | EL | PS-OT-T-0892 | 2020-02-16 |  | No | 78 | 1204-Owner-v | 2020-02-26 17:07 | REQ | 2020-07-08 | 0 | 0 | 2020-07-21 | * |  |  | InProgress | 90%
1204-64-RE-DSH-054 | 00 | DATA SHEET FOR CAUSTIC UNLOADING PUMP (P-6406) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-08 11:44 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-00-ST-DWG-065 | 01 | PIPE RACK ZONE 10 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0170 | 2016-01-03 |  | No | 1583 | 1204-Owner-v | 2016-01-04 10:13 | CDW | 2016-01-03 | 0 | 0 | 0 | 2016-01-03 | 2016-01-04 | MT-PS-9301-CS-072 | complete | 100%
1204-90-HS-DWG-011 | 01 | SAFETY EQUIPMENT LAYOUT FOR FIRE STATION | DE | IFC | HSE | PS-OT-T-0102 | 2015-09-13 |  | No | 1695 | 1204-Owner-v | 2015-09-14 09:51 | EDW | 2015-09-13 | 0 | 0 | 0 | 2015-09-13 | 2015-10-31 | MT-PS-9301-CS-036 | complete | 100%
1204-00-ST-DWG-044 | 02 | PIPE RACK ZONE 6 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0126 | 2015-11-04 |  | No | 1643 | 1204-Owner-v | 2015-11-05 10:14 | CDW | 2015-11-16 | 0 | 0 | 0 | 2015-11-16 | 2015-11-08 | MT-PS-9301-CS-040 | complete | 100%
1204-90-HV-DSH-018 | 00 | DATA SHEET FOR GAS CH. ROOM HOOD CENTRIFUGAL EXHAUST FAN FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:23 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-82-HS-BOD-001 | 00 | BASIS OF DESIGN FOR FIRE WATER SYSTEM | DE | IFR | HSE | TM-OT-9001-T-0446 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2015-03-04 13:34 | EDW | 2019-10-01 | 0 | 0 | 2020-06-01 | 2015-04-03 |  |  | InProgress | 80%
1204-63-PI-LST-1800 | 00 | A/G ISOMETRIC LIST OF AREA-18 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:12 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-71-PI-LST-3200 | 00 | A/G ISOMETRIC LIST OF AREA-32 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-09 14:57 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-00-PR-UDD-020 | 02 | UTILITY DISTRIBUTION DIAGRAM FOR POTABLE WATER SYSTEM | DE | IFC-WH | PR | PS-OT-T-0575 | 2018-03-06 |  | No | 790 | 1204-Owner-v | 2018-04-07 09:12 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2018-04-12 | 2018-03-07 | MT-PS-9609-CS-043 | InProgress | 90%
1204-00-PI-LST-3700 | 00 | A/G ISOMETRIC LIST OF AREA-37 | DE | IFR | PI | PS-OT-T-0282 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:43 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 | 2016-06-20 | MT-PS-9301-CS-162 | InProgress | 80%
1204-10-PI-ISO-4700 | 00 | A/G ISOMETRIC DRAWING OF AREA-47 | DE | IFR | PI | PS-OT-T-0343 | 2016-10-01 |  | No | 1311 | 1204-Owner-v | 2016-10-04 07:39 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-10-10 |  |  | InProgress | 80%
1204-00-RE-REQ-304 | 00 | REQUISITION FOR EMERGENCY AIR COMPRESSOR | DE | IFI | MC | PS-OT-T-0443 | 2017-04-22 |  | No | 1108 | 1204-Owner-v | 2017-05-01 09:10 | REQ | 2017-05-03 | 0 | 0 | 0 | 2017-05-03 |  |  | InProgress | 90%
1204-00-QC-SOI-510 | 00 | SCOPE OF INSPECTION FOR CATHODIC PROTECTION | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-EL-REQ-513 | 00 | REQUISITION FOR PUBLIC ADDRESS AND INTERCOM SYSTEM | DE | IFI | EL | PS-OT-T-0917 | 2020-02-26 |  | No | 68 | 1204-Owner-v | 2020-02-27 11:50 | REQ | 2020-06-23 | 0 | 0 | 2020-07-06 | * | 2020-03-09 | MT-PS-9609-CS-0307 | InProgress | 90%
1204-00-EL-TBA-509A | 00 | TECHNICAL BID ANALYSIS FOR POWER, CONTROL AND EARTHING CABLES | DE | IFE | EL | PS-OT-T-0922 | 2020-03-01 |  | No | 64 | 1204-Owner-v | 2020-03-03 11:41 | TBA | 2020-02-19 | 0 | 0 | 2020-02-25 | 0 | 0 | 0 | complete | 100%
1204-00-EL-TBA-510 | 01 | TECHNICAL BID ANALYSIS FOR CATHODIC PROTECTION | DE | IFE | EL | PS-OT-T-0875 | 2020-01-27 |  | No | 98 | 1204-Owner-v | 2020-02-01 08:52 | TBA | 2020-01-27 | 0 | 0 | 0 | 2020-01-27 |  |  | complete | 100%
1204-71-ST-DWG-754 | 03 | DYKE WALL FOR TK-7101 A/B & TK-7201 / G.A. PLAN & DETAILS | DE | IFC | ST | PS-OT-T-0395 | 2017-01-03 |  | No | 1217 | 1204-Owner-v | 2017-01-04 09:54 | CDW | 2017-01-14 | 0 | 0 | 0 | 2017-01-14 |  |  | complete | 100%
1204-90-HV-DSH-013 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR CHEMICAL STORE IN LABORATORY | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:40 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-062 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR CLINIC | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:42 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-202 | 02 | DATA SHEET FOR PRESSURE RELIEF DAMPER FOR CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0006 | 2015-03-09 |  | No | 1883 | 1204-Owner-v | 2015-03-17 11:17 | DSH | 2015-03-09 | 0 | 0 | 0 | 2015-03-09 |  |  | complete | 100%
1204-90-HV-DWG-061 | 02 | CLINIC AND TRAINING - DUCTING LAYOUT | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:45 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 |  |  | complete | 100%
1204-83-RE-DSH-055 | 00 | DATA SHEET FOR FLARE KNOCK-OUT DRUM PUMPS (P-8301 A/B) | DE | IFR | MC | PS-OT-T-0836 | 2019-11-16 |  | No | 170 | 1204-Owner-v | 2020-01-05 07:59 | DSH | 2019-11-16 | 0 | 0 | 0 |  |  |  | InProgress | 80%
1204-90-HV-DSH-094 | 01 | DATA SHEET FOR NORTH WALL TYPE EXHAUST FAN FOR GF TOILET IN WAREHOUSE | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:49 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DWG-063 | 01 | CLINIC AND TRAINING - DUCT SUPPORTING AND OPENING LOCATION | DE | IFC | HV | TM-OT-9001-T-0380 | 2014-07-01 |  | No | 2134 | 1204-TKT-COLANGELI | 2014-07-01 14:55 | CDW | 2014-07-01 | 0 | 0 | 0 | 2014-07-01 |  |  | complete | 100%
1204-90-HS-DWG-010 | 01 | SAFETY EQUIPMENT LAYOUT FOR ADMINISTRATION, RESTAURANT AND CLINIC BUILDING | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:57 | EDW | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-20-RE-DSH-002 | 00 | DATA SHEET FOR STEAM TURBINE FOR SYNTHESIS GAS COMPRESSOR STC-2001 | DE | IFR | MC | PS-OT-T-0157 | 2015-12-21 |  | No | 1596 | 1204-Owner-v | 2015-12-22 15:46 | DSH | 2015-12-23 | 0 | 0 | 0 | 2015-12-23 | 2016-01-06 | MT-PS-9301-CS-076 | InProgress | 80%
1204-10-PI-LST-6100 | 01 | U/G ISOMETRIC LIST OF AREA-61 | DE | IFC-WH | PI | PS-OT-T-0633 | 2018-06-18 |  | No | 686 | 1204-Owner-v | 2018-06-24 08:26 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-06-24 | MT-PS-9609-CS-089 | InProgress | 90%
1204-20-PI-UPL-6500 | 02 | UNDER GROUND PIPING PLAN AREA-65 | DE | IFC-WH | PI | PS-OT-T-0665 | 2018-08-13 |  | No | 630 | 1204-Owner-v | 2018-08-15 17:15 | CDW | 2018-08-27 | 0 | 0 | 0 | 2018-08-27 |  |  | InProgress | 90%
1204-30-PI-LST-2900 | 01 | A/G ISOMETRIC LIST OF AREA-29 | DE | IFC-WH | PI | PS-OT-T-0673 | 2018-08-29 |  | No | 614 | 1204-Owner-v | 2018-09-01 16:18 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-63-PI-LST-1700 | 00 | A/G ISOMETRIC LIST OF AREA-17 | DE | IFR | PI | PS-OT-T-0165 | 2015-12-30 |  | No | 1587 | 1204-Owner-v | 2016-01-02 10:13 | CDW | 2019-12-20 | 0 | 0 | 2020-06-04 | 2016-01-06 | 2016-05-07 | MT-PS-9301-CS-142 | InProgress | 80%
1204-00-PR-UDD-021 | 02 | UTILITY DISTRIBUTION DIAGRAM FOR SANITARY GATHERING SYSTEM | DE | IFC-WH | PR | PS-OT-T-0575 | 2018-03-06 |  | No | 790 | 1204-Owner-v | 2018-04-07 09:13 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | 2018-04-12 | 2018-03-07 | MT-PS-9609-CS-043 | InProgress | 90%
1204-10-PI-LST-4500 | 00 | A/G ISOMETRIC LIST OF AREA-45 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:02 | CDW | 2020-06-16 | 0 | 0 | 2020-06-16 | 2016-09-03 |  |  | InProgress | 80%
1204-30-HM-DSH-238 | 00 | MECHANICAL DATA SHEET FOR TOPPING COLUMN SECONDARY CONDENSER (E-3002) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:09 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | complete | 100%
1204-90-HV-DSH-001 | 03 | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR CONTROL BUILDING | DE | IFE | HV | PS-OT-T-0707 | 2018-10-24 |  | No | 558 | 1204-Owner-v | 2018-10-29 09:27 | DSH | 2018-10-24 | 0 | 0 | 0 | 2018-10-24 |  |  | complete | 100%
1204-90-HV-DSH-250 | 01 | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR RESTAURANT | DE | IFE | HV | PS-OT-T-0259 | 2016-05-10 |  | No | 1455 | 1204-Owner-v | 2016-05-14 16:07 | DSH | 2016-05-10 | 0 | 0 | 0 | 2016-05-10 |  |  | complete | 100%
1204-30-ST-DWG-331 | 02 | STRUCTURE "E" FOR E-3004,E-3012 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0307 | 2016-07-13 |  | No | 1391 | 1204-Owner-v | 2016-07-14 11:33 | CDW | 2016-07-21 | 0 | 0 | 0 | 2016-07-21 |  |  | complete | 100%
1204-90-EL-SLD-048 | 01 | WORK SHOP NORMAL LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:50 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-DSH-013 | 00 | DATA SHEET FOR PORTABLE CO2 EXTINGUISHER | DE | IFR | HSE | TM-OT-9001-T-0342 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-18 11:16 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2013-12-18 |  |  | InProgress | 80%
1204-83-HS-PFD-830 | 02 | PROCESS FLOW DIAGRAM FOR FLARE UNIT | DE | IFE | HSE | PS-OT-T-0506 | 2017-12-02 |  | No | 884 | 1204-Owner-v | 2017-12-03 15:27 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * | 2017-12-17 | MT-PS-9301-CS-267 | complete | 100%
1204-00-HM-REQ-254 | 01 | REQUISITION FOR AUXILIARY WATER TUBE BOILER | DE | IFP | MD | TM-OT-9001-T-0434 | 2015-02-05 |  | No | 1915 | 1204-TKT-COLANGELI | 2015-02-05 13:14 | REQ | 2015-02-05 | 0 | 0 | 0 | 2015-02-05 |  |  | complete | 100%
1204-00-PI-PPL-004 | 01 | PLOT PLAN UNIT 300 | DE | IFR | PI | PS-OT-T-0430 | 2017-03-12 |  | No | 1149 | 1204-Owner-v | 2017-03-14 08:59 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | * |  |  | InProgress | 80%
1204-00-PI-REQ-403B | 00 | REQUISITION FOR A/G GASKETS(MTO II) | DE | IFI | PI | PS-OT-T-0946 | 2020-04-11 |  | No | 23 | 1204-Owner-v | 2020-04-15 11:21 | REQ | 2020-04-16 | 0 | 0 | 2020-04-20 | * |  |  | InProgress | 90%
1204-00-PR-PID-005 | 01 | PIPING & INSTRUMENTATION DIAGRAM FOR INSTRUMENT SYMBOLS II | DE | IFR | PR | PS-OT-T-365 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:31 | EDW | 2020-08-01 | 0 | 0 | 2020-10-20 | 2017-04-16 | 2017-05-20 | MT-PS-9301-CS-201-R | InProgress | 80%
1204-10-PR-PID-108 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- PRIMARY REFORMER RAD & CONV. SECTION FLUE GAS SIDE | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:07 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-10-PR-PID-117 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- SYNTHESIS GAS COOLING | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:09 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-30-HM-DSH-243 | 00 | MECHANICAL DATA SHEET FOR TOPPING COLUMN REBOILER (E-3007) | DE | IFR | MD | TM-OT-9001-T-0333 | 2013-11-06 |  | No | 2371 | 1204-TKT-COLANGELI | 2013-11-06 12:25 | DSH | 2013-11-06 | 0 | 0 | 0 | 2013-11-06 |  |  | InProgress | 80%
1204-90-HV-DSH-002 | 02 | DATA SHEET FOR AIR CONDENSER FOR CONTROL BUILDING | DE | IFE | HV | TM-OT-9001-T-0391 | 2014-09-09 |  | No | 2064 | 1204-TKT-COLANGELI | 2014-09-09 11:54 | DSH | 2014-09-09 | 0 | 0 | 0 | 2014-09-09 | 2014-10-01 | MT-OT-9301-CS-019 | complete | 100%
1204-90-HV-DSH-041 | 00 | DATA SHEET FOR AIR CONDENSER FOR ADMINISTRATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 15:12 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DSH-042 | 01 | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR ADMINISTRATION | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:40 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DWG-041 | 02 | ADMINISTRATION - DUCTING LAYOUT | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:44 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 | 2014-10-19 |  | complete | 100%
1204-90-HV-DID-044 | 02 | ADMINISTRATION - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | PS-TM-T-0386 | 2028-01-15 |  | No | -2812 | 1204-Owner-v | 2015-04-18 15:31 | CDW | 2028-01-15 | 0 | 0 | 0 | 2028-01-15 | 2014-10-19 |  | complete | 100%
1204-90-HV-DSH-082 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR SHOWER IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:45 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-045 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR TOILET IN ADMINISTRATION AND CLINIC | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:41 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-067 | 00 | DATA SHEET FOR AIR CONDENSER FOR TRAINING | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-10 14:06 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-00-PI-LST-7000 | 01 | U/G ISOMETRIC LIST OF AREA-70 | DE | IFC-WH | PI | PS-OT-T-0627 | 2018-06-03 |  | No | 701 | 1204-Owner-v | 2018-06-19 17:24 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-06-17 |  |  | InProgress | 90%
1204-71-PI-ISO-3200 | 00 | A/G ISOMETRIC DRAWING OF AREA-32 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-09 15:07 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-20-ST-DWG-249 | 01 | C-2002 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0638 | 2018-07-01 |  | No | 673 | 1204-Owner-v | 2018-07-03 12:48 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-07-07 | 2018-07-04 | MT-PS-9609-CS-092 | complete | 100%
1204-64-PV-DSH-205 | 04 | MECHANICAL DATA SHEET FOR DEMIN WATER STORAGE TANK (TK-6402) | DE | IFE | MD | TM-OT-9001-T-0445 | 2015-03-04 |  | No | 1888 | 1204-TKT-COLANGELI | 2015-03-04 14:02 | DSH | 2015-03-04 | 0 | 0 | 0 | 2015-03-04 |  |  | complete | 100%
1204-90-ST-DWG-984 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / BEAMS , WALLS & COLUMNS (G.A. PLAN & DETAILS) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 11:06 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-90-ST-DWG-986 | 02 | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / BEAMS (R.C. I) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 14:36 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-00-QC-SOI-529 | 00 | SCOPE OF INSPECTION FOR EARTHING AND LIGHTNING MATERIALS | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1041 | 01 | WAREHOUSE / FRAMES & PLAN FOR CHEMICAL STORAGE | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:12 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-00-PI-TBA-462A | 01 | TECHNICAL BID ANALYSIS FOR U/G FLANGES(MTO I) | DE | IFE | PI | PS-OT-T-0266 | 2016-05-18 |  | No | 1447 | 1204-Owner-v | 2016-05-18 16:10 | TBA | 2016-05-18 | 0 | 0 | 0 | 2016-05-18 |  |  | complete | 100%
1204-00-PI-APL-3500 | 00 | PIPING PLAN AREA-35 | DE | IFR | PI | PS-OT-T-0324 | 2016-08-23 |  | No | 1350 | 1204-Owner-v | 2016-08-24 16:16 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-08-29 |  |  | InProgress | 80%
1204-00-EL-DSH-508 | 00 | DATA SHEET FOR 110V AC UPS (CR01-UPS-01) | DE | IFR | EL | PS-OT-T-481 | 2017-09-11 |  | No | 966 | 1204-Owner-v | 2017-09-13 11:36 | DSH | 2020-04-21 | 0 | 0 | 2020-04-21 | * | 2018-06-10 | MT-PS-9301-CS-250-R | InProgress | 80%
1204-20-ST-DWG-271 | 02 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/STEEL STR.(PLAN & DET. I) | DE | IFC-WH | ST | PS-OT-T-0816 | 2019-07-15 |  | No | 294 | 1204-Owner-v | 2019-07-20 16:36 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-00-EL-DSH-5072 | 00 | DATA SHEET FOR BATTERY CHARGER (SS01-CH-01) | DE | IFR | EL | PS-OT-T-0489 | 2017-09-18 | 2017-10-18 16:08 | Yes | 16 | 1204-Owner-v | 2017-09-21 08:08 | DSH | 2020-05-13 | 0 | 0 | 2020-05-13 | 2017-09-19 | 2017-10-09 | MT-PS-9301-CS-253 | InProgress | 80%
1204-00-ST-DWG-1110 | 05 | EAST RETAINING WALL (FIRST PART) / G.A. PLAN & R.C. DETAILS (I) | DE | IFC | ST | PS-OT-T-0816 | 2019-07-15 |  | No | 294 | 1204-Owner-v | 2019-07-20 16:35 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-00-ST-DWG-1153 | 01 | VB-6905 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0580 | 2018-03-13 |  | No | 783 | 1204-Owner-v | 2018-04-14 11:38 | CDW | 2018-03-13 | 0 | 0 | 0 | 2018-03-13 |  |  | complete | 100%
1204-20-ST-DWG-1173 | 02 | STRUCTURE "M" FOR R-2001 / CONCRETE STRUCTURE (R.C. DETAILS I ) | DE | IFC | ST | PS-OT-T-0717 | 2018-11-11 |  | No | 540 | 1204-Owner-v | 2018-11-12 09:17 | CDW | 2018-11-21 | 0 | 0 | 0 | 2018-11-21 |  |  | complete | 100%
1204-61-ST-DWG-553 | 00 | ASU (DR-6101A & DR-6101B) / FDN. (G.A. & R.C.) | DE | IFR | ST | PS-OT-T-0653 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-08-03 10:29 | CDW | 2018-07-23 | 0 | 0 | 0 | 2018-07-23 | 2018-08-04 | MT-PS-9609-CS-104 | InProgress | 80%
1204-00-EL-REQ-519 | 00 | REQUISITION FOR STREET LIGHTING FIXTURES | DE | IFI | EL | PS-OT-T-0903 | 2020-02-19 |  | No | 75 | 1204-Owner-v | 2020-02-22 15:06 | REQ | 2020-02-19 | #N/A | #N/A | #N/A | 2020-02-19 | 2020-02-26 | MT-PS-9609-CS-0279 | InProgress | 90%
1204-40-IN-DWG-044 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 44) | DE | IFR | IN | PS-OT-T-0345 | 2016-10-03 |  | No | 1309 | 1204-Owner-v | 2016-10-08 16:00 | CDW | 2020-06-25 | 0 | 0 | 2020-06-25 | * | 2016-10-18 | MT-PS-9301-CS-191-R | InProgress | 80%
1204-00-ST-DWG-776 | 03 | GUARD RAIL DETAILS | DE | IFC | ST | PS-OT-T-0857 | 2019-12-29 |  | No | 127 | 1204-Owner-v | 2020-01-02 07:27 | CDW | 2019-12-29 | 0 | 0 | 0 | 2019-12-29 |  | MT-PS-9609-CS-0252 | complete | 100%
1204-00-PI-REQ-461AP | 01 | REQUISITION FOR U/G PIPES(MTO I) | DE | IFP | PI | PS-OT-T-0404 | 2017-01-15 |  | No | 1205 | 1204-Owner-v | 2017-06-10 11:07 | REQ | 2017-01-15 | 0 | 0 | 0 | 2017-01-15 |  |  | complete | 100%
1204-90-RE-DSH-062 | 01 | DATA SHEET FOR E.O.T CRANE FOR MAIN WAREHOUSE, CN-9001 | DE | IFR | MC | PS-OT-T-0660 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-15 15:53 | DSH | 2018-08-05 | 0 | 0 | 0 | 2018-08-05 |  |  | InProgress | 80%
1204-20-ST-DWG-273 | 01 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/STEEL STR.(STAIR) | DE | IFC | ST | PS-OT-T-0802 | 2019-06-10 |  | No | 329 | 1204-Owner-v | 2019-06-12 17:33 | CDW | 2019-06-10 | 0 | 0 | 0 | 2019-06-10 |  |  | complete | 100%
1204-90-EL-DWG-421 | 01 | ADMIN, REST & CLINIC BUILDING LIGHTNING PROTECTION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:16 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-00-HS-DSH-002 | 01 | DATA SHEET FOR WATER MONITOR | DE | IFR | HSE | PS-OT-T-0738 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:00 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-00-HS-DSH-018 | 00 | DATA SHEET FOR HEAT DETECTOR | DE | IFR | HSE | TM-OT-9001-T-0412 | 2014-11-24 |  | No | 1988 | 1204-TKT-COLANGELI | 2014-11-24 12:14 | DSH | 2019-10-12 | 0 | 0 | 2020-10-10 | 2014-11-24 |  |  | InProgress | 80%
1204-00-HS-LST-001 | 01 | SAFETY EQUIPMENT LIST FOR PROCESS UNITS | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:57 | LIST | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-84-HS-DIG-001 | 01 | CAUSE AND EFFECT DIAGRAMS FOR EFFLUENT WATER TREATMENT UNIT | DE | IFR | HSE | PS-OT-T-0855 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:54 | LIST | 2019-10-10 | 0 | 0 | 2020-08-01 | * | 2020-04-20 | MT-PS-9301-CS-0332 | InProgress | 90%
1204-00-IN-DSH-617 | 02 | DATA SHEET FOR VENTURI & FLOW NOZZLES | DE | IFR | IN | PS-OT-T-0602 | 2018-04-30 |  | No | 735 | 1204-Owner-v | 2018-05-03 16:30 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | * | 2018-05-22 | MT-PS-9609-CS-068-R | InProgress | 80%
1204-00-IN-REQ-604 | 02 | REQUISITION FOR ON / OFF VALVES | DE | IFP | IN | PS-OT-T-0911 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 17:08 | REQ | 2020-02-24 | 0 | 0 | 0 | 2020-02-24 | 2020-03-02 | MT-PS-9609-CS-0290 | complete | 100%
1204-00-IN-SKT-004 | 00 | INSTRUMENT AIR HOOK UP’S | DE | IFR | IN | TM-OT-9001-T-0280 | 2013-05-24 |  | No | 2537 | 1204-TKT-COLANGELI | 2013-05-21 17:23 | CDW | 2013-05-24 | 0 | 0 | 0 | 2013-05-24 |  |  | InProgress | 80%
1204-00-PV-REQ-214A | 01 | REQUISITION FOR TANK ACCESSORIES | DE | IFP | MD | PS-OT-T-0255 | 2016-05-07 |  | No | 1458 | 1204-Owner-v | 2016-05-09 12:05 | REQ | 2016-05-07 | 0 | 0 | 0 | 2016-05-07 |  |  | complete | 100%
1204-00-PI-UPL-7800 | 00 | UNDER GROUND PIPING PLAN AREA-78 | DE | IFR | PI | TM-OT-9001-T-0173 | 2012-10-04 |  | No | 2769 | 1204-Owner-v | 2015-04-18 09:02 | CDW | 2019-12-13 | 2020-06-08 | 0 | 0 | 2012-10-04 |  |  | InProgress | 80%
1204-90-HV-DSH-211 | 01 | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR LABORATORY | DE | IFE | HV | TM-OT-9001-T-0443 | 2015-02-24 |  | No | 1896 | 1204-TKT-COLANGELI | 2015-02-24 11:57 | DSH | 2015-02-24 | 0 | 0 | 0 | 2015-02-24 |  |  | complete | 100%
1204-90-HV-DWG-021 | 04 | SUBSTATION - DUCTING LAYOUT | DE | IFC | HV | TM-OT-9001-T-0441 | 2015-02-20 |  | No | 1900 | 1204-TKT-COLANGELI | 2015-02-20 11:17 | CDW | 2015-02-20 | 0 | 0 | 0 | 2015-02-20 |  |  | complete | 100%
1204-90-HV-DSH-085 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR WORKSHOP AREA IN WORKSHOP | DE | IFE | HV | TM-OT-9001-T-0452 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:46 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HS-LST-003 | 02 | SAFETY EQUIPMENT LIST FOR CONTROL ROOM | DE | IFE | HSE | PS-OT-T-0027 | 2015-04-20 |  | No | 1841 | 1204-Owner-v | 2015-04-22 10:22 | LIST | 2015-04-20 | 0 | 0 | 0 | 2015-04-20 |  |  | complete | 100%
1204-20-PI-LST-2700 | 01 | A/G ISOMETRIC LIST OF AREA-27 | DE | IFC-WH | PI | PS-OT-T-0692 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-10-13 13:58 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-30-PI-APL-2900 | 01 | PIPING PLAN AREA-29 | DE | IFC-WH | PI | PS-OT-T-0673 | 2018-08-29 |  | No | 614 | 1204-Owner-v | 2018-09-01 16:22 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-60-PI-UPL-6300 | 02 | UNDER GROUND PIPING PLAN AREA-63 | DE | IFC-WH | PI | PS-OT-T-0554 | 2018-02-12 |  | No | 812 | 1204-Owner-v | 2018-02-14 08:46 | CDW | 2018-02-22 | 0 | 0 | 0 | 2018-02-22 |  |  | InProgress | 90%
1204-64-PI-ISO-3000 | 00 | A/G ISOMETRIC DRAWING OF AREA-30 | DE | IFR | PI | PS-OT-T-0071 | 2015-07-05 |  | No | 1765 | 1204-Owner-v | 2015-07-05 16:04 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2015-07-05 |  |  | InProgress | 80%
1204-00-PI-APL-3800 | 00 | PIPING PLAN AREA-38 | DE | IFR | PI | PS-OT-T-0327 | 2016-08-28 |  | No | 1345 | 1204-Owner-v | 2016-08-28 16:01 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-09-03 |  |  | InProgress | 80%
1204-03-EL-DWG-013 | 00 | LIGHTING LAYOUT AREA-03 (D-3003, 3004, E-3003A/B/C/D, T-3003) | DE | IFR | EL | PS-OT-T-0139 | 2015-11-29 | 2016-07-24 10:51 | Yes | 224 | 1204-Owner-v | 2015-12-05 14:43 | CDW | 2020-07-15 | 0 | 0 | 2020-07-15 | 2015-12-17 | 2015-12-26 | MT-PS-9301-CS-066 | InProgress | 80%
1204-00-IN-DWG-015 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 15) | DE | IFR | IN | PS-OT-T-0190 | 2016-01-25 |  | No | 1561 | 1204-Owner-v | 2016-01-25 14:53 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-01-28 | 2016-01-30 | MT-PS-9301-CS-100 | InProgress | 80%
1204-20-ST-DWG-211 | 02 | STRUCTURE "A" FOR D-2003,E-2001A/B,E-2003A/B,E-2002,E-2005A/B,E-2006/STEEL STR. (FRAMES I) | DE | IFC-WH | ST | PS-OT-T-0812 | 2019-06-26 |  | No | 313 | 1204-Owner-v | 2019-07-01 10:59 | CDW | 2019-06-26 | 0 | 0 | 0 | 2019-06-26 |  |  | complete | 100%
1204-30-ST-DWG-333 | 02 | STRUCTURE "E" FOR E-3004,E-3012 / STEEL STRUCTURE (ELEVATION & DETS.) | DE | IFC | ST | PS-OT-T-0413 | 2017-02-07 |  | No | 1182 | 1204-Owner-v | 2017-02-08 14:32 | CDW | 2017-02-14 | 0 | 0 | 0 | 2017-02-14 |  |  | complete | 100%
1204-90-ST-DWG-909 | 01 | CONTROL ROOM & LABORATORY / FDN.. OF BLAST PART (R.C. DETAILS II) | DE | IFC | ST | TM-OT-9001-T-0325 | 2013-09-27 |  | No | 2411 | 1204-TKT-COLANGELI | 2013-09-27 11:30 | CDW | 2020-06-20 | 0 | 0 | 2020-06-20 | * |  |  | InProgress | 80%
1204-90-ST-DWG-1070 | 00 | FIRE STATION. / PLUMBING LAYOUT & DETAILS | DE | IFR | ST | TM-OT-9001-T-0425 | 2015-01-09 |  | No | 1942 | 1204-TKT-COLANGELI | 2015-01-07 13:33 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2015-01-09 | 2015-01-28 | MT-TM-9301-CS-034 | InProgress | 80%
1204-90-ST-DWG-1082 | 02 | GUARD HOUSE / SECTIONS | DE | IFC | ST | TM-OT-9001-T-0273 | 2013-05-14 |  | No | 2547 | 1204-TKT-COLANGELI | 2013-05-14 13:10 | CDW | 2013-05-14 | 0 | 0 | 0 | 2013-05-14 |  |  | complete | 100%
1204-90-ST-DWG-937 | 00 | SUBSTATION / 3D VIEWS | DE | IFR | ST | TM-OT-9001-T-0140 | 2012-08-09 |  | No | 2825 | 1204-Owner-v | 2015-09-16 18:33 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2012-08-09 |  |  | InProgress | 80%
1204-20-RE-DSH-025 | 00 | Data Sheet for Converter BW Circulation Pumps P-2002 A/B | DE | IFR | MC | TM-OT-9001-T-0075 | 2012-05-29 |  | No | 2897 | 1204-Owner-v | 2015-09-16 17:39 | DSH | 2012-05-29 | 0 | 0 | 0 | 2012-05-29 |  |  | InProgress | 80%
1204-00-PR-UDD-010 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR HP & MP STEAM DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:26 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-PR-UDD-011 | 01 | UTILITY DISTRIBUTION DIAGRAM FOR DMW & BFW DISTRIBUTION SYSTEM | DE | IFR | PR | PS-OT-T-0416 | 2017-02-11 |  | No | 1178 | 1204-Owner-v | 2017-02-19 10:25 | EDW | 2020-05-01 | 0 | 0 | 2020-05-01 | * |  |  | InProgress | 80%
1204-00-IN-DWG-013 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 13) | DE | IFR | IN | PS-OT-T-0290 | 2016-06-18 |  | No | 1416 | 1204-Owner-v | 2016-06-18 11:36 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-06-20 |  |  | InProgress | 80%
1204-00-EL-SCH-5021 | 00 | 6KV SWITCHGEAR SCHEDULE (SS01-SWB2A,B-01) | DE | IFR | EL | PS-OT-T-0525 | 2018-01-01 | 2018-02-12 15:32 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:01 | LIST | 2020-05-11 | 0 | 0 | 2020-05-11 | 2018-01-21 | 2018-05-31 | MT-PS-9609-CS-002-1-R | InProgress | 90%
1204-71-IN-DWG-032 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 32) | DE | IFR | IN | PS-OT-T-0158 | 2015-12-23 |  | No | 1594 | 1204-Owner-v | 2015-12-23 15:38 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | 2015-12-28 | 2016-01-10 | MT-PS-9301-CS-080 | InProgress | 80%
1204-00-ST-DWG-171 | 01 | PIPE BRIDGE “ I “ / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0558 | 2018-02-14 |  | No | 810 | 1204-Owner-v | 2018-02-17 09:08 | CDW | 2018-02-14 | 0 | 0 | 0 | 2018-02-14 | 2018-02-17 | MT-PS-9609-CS-032 | complete | 100%
1204-00-EL-DSH-5024 | 00 | DATA SHEET FOR AUTO/MANUAL TRANSFER, 6KV SWITCHGEAR SS01-SWB2A,B-01 | DE | IFR | EL | PS-OT-T-0527 | 2018-01-01 | 2018-02-12 16:06 | Yes | 28 | 1204-Owner-v | 2018-01-02 11:06 | DSH | 2020-05-25 | 0 | 0 | 2020-05-25 | * | 2018-05-31 | MT-PS-9609-CS-013-R | InProgress | 80%
1204-00-ST-DWG-1141 | 01 | VB-6301 / R.C. DETAILS | DE | IFC | ST | PS-OT-T-0725 | 2018-12-10 |  | No | 511 | 1204-Owner-v | 2018-12-12 08:11 | CDW | 2018-12-10 | 0 | 0 | 0 | 2018-12-10 |  |  | complete | 100%
1204-00-ST-DWG-1242 | 02 | SUN CANOPY FOR ELECTRO MOTORS / STEEL PARTS (G.A.& DETAILS) | DE | IFC | ST | PS-OT-T-0805 | 2019-06-12 |  | No | 327 | 1204-Owner-v | 2019-06-23 09:31 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-20-ST-DWG-208 | 01 | STRUCTURE "A" & STRUCTURE "M" / COMBINED FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0691 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-09-29 15:07 | CDW | 2018-09-29 | 0 | 0 | 0 | 2018-09-29 |  |  | complete | 100%
1204-84-HS-DSH-010 | 00 | DATA SHEET FOR SANITARY DISCHARGE PUMP (P-8405) | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:07 | DSH | 2020-10-10 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-10-PV-REQ-202G | 02 | REQUISITION FOR STEEL STRUCTURE OF WASTE HEAT BOILER | DE | IFP | MD | PS-OT-T-0913 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 18:21 | REQ | 2020-02-25 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-ST-DWG-188 | 00 | PIPE RACK ZONE 14 / STEEL STRUCTURE (ELEVATION & DETS.) | DE | IFR | ST | PS-OT-T-0973 | 2020-05-13 |  | No | -9 | 1204-Owner-v | 2020-05-16 08:36 | CDW | 2020-03-23 | 0 | 0 | 2020-03-23 | 0 | 0 | 0 | InProgress | 50%
1204-00-PV-REQ-201B | 01 | REQUISITION FOR AUTO THERMAL REACTOR | DE | IFP | MD | PS-OT-T-0568 | 2018-02-27 |  | No | 797 | 1204-Owner-v | 2018-04-15 15:32 | REQ | 2018-02-27 | 0 | 0 | 0 | 2018-02-27 |  |  | complete | 100%
1204-90-EL-DIG-001 | 00 | FIRE ALARM RISER DIAGRAM FOR MAIN SUBSTATION | DE | IFR | EL | PS-OT-T-0123 | 2015-10-31 | 2016-07-24 11:25 | Yes | 253 | 1204-Owner-v | 2015-11-01 10:23 | CDW | 2020-04-21 | 0 | 0 | 2020-04-21 | 2015-11-16 | 2015-12-26 | MT-PS-9301-CS-067 | InProgress | 80%
1204-00-IN-DWG-014 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 14) | DE | IFR | IN | PS-OT-T-0190 | 2016-01-25 |  | No | 1561 | 1204-Owner-v | 2016-01-25 14:53 | CDW | 2020-06-18 | 0 | 0 | 2020-06-18 | 2016-01-28 | 2016-01-30 | MT-PS-9301-CS-100 | InProgress | 80%
1204-02-EL-DWG-022 | 00 | EARTHING LAYOUT AREA-02 (AE-2001) | DE | IFR | EL | PS-OT-T-0193 | 2016-02-02 | 2016-07-21 15:09 | Yes | 156 | 1204-Owner-v | 2016-02-02 17:01 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2016-02-17 | 2016-02-13 | MT-PS-9301-CS-106 | InProgress | 80%
1204-30-ST-DWG-347 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / COLUMNS (G.A. PLAN & R.C. DETAILS II) | DE | IFC | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 08:08 | CDW | 2017-01-01 | 0 | 0 | 0 | 2017-01-01 |  |  | complete | 100%
1204-30-ST-DWG-353 | 01 | STRUCTURE "F" FOR D-3004,D-3005,E-3003C/D,E-3005,E-3009 / STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0394 | 2017-01-01 |  | No | 1219 | 1204-Owner-v | 2017-01-02 08:10 | CDW | 2017-01-01 | 0 | 0 | 0 | 2017-01-01 |  |  | complete | 100%
1204-00-ST-DWG-1113 | 04 | EAST RETAINING WALL (SECOND PART) / G.A. PLAN & R.C. DETAILS | DE | IFC | ST | PS-OT-T-0816 | 2019-07-15 |  | No | 294 | 1204-Owner-v | 2019-07-20 16:35 | CDW | 2019-07-20 | 0 | 0 | 0 | 2019-07-20 |  |  | complete | 100%
1204-00-ST-DWG-1136 | 02 | VB-6203/FDN. (G.A. & DETAILS) | DE | IFC | ST | PS-OT-T-0616 | 2018-05-21 |  | No | 714 | 1204-Owner-v | 2018-05-22 11:56 | CDW | 2018-05-26 | 0 | 0 | 0 | 2018-05-26 | 2018-05-22 | MT-PS-9609-CS-075 | complete | 100%
1204-90-ST-DWG-1181 | 00 | SUBSTATION FOR ASU / CONCEPTUAL PLAN | DE | IFR | ST | PS-OT-T-0586 | 2018-03-19 |  | No | 777 | 1204-Owner-v | 2018-04-03 13:23 | CDW | 2020-05-30 | 0 | 0 | 2020-05-30 | * | 2018-07-03 | MT-PS-9609-CS-057-N | InProgress | 80%
1204-10-ST-DWG-132 | 03 | STRUCTURE "Q" FOR R-1001,R-1002A/B & R-1003 / FDN. (R.C. & DETAILS) | DE | IFC | ST | PS-OT-T-0967 | 2020-05-09 |  | No | -5 | 1204-Owner-v | 2020-05-11 14:15 | CDW | 2019-04-16 | 0 | 0 | 0 | 2019-04-16 |  |  | complete | 100%
1204-00-PI-REQ-420 | 00 | REQUISITION FOR GASKET FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:21 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-20-PR-PID-206 | 02 | PIPING & INSTRUMENTATION DIAGRAM UNIT 200-SYNTHESIS LOOP COOLING / SEPARATION | DE | IFC-WH | PR | PS-OT-T-0659 | 2018-08-05 |  | No | 638 | 1204-Owner-v | 2018-08-08 09:23 | EDW | 2020-06-15 | 0 | 0 | 2020-06-15 | 2018-08-09 |  |  | InProgress | 90%
1204-20-PR-REQ-105 | 02 | REQUISITION FOR HYDROGEN RECOVERY UNIT (HRU) (PU-2001) | DE | IFP | PR | PS-OT-T-0107 | 2015-09-27 |  | No | 1681 | 1204-Owner-v | 2015-09-28 09:37 | REQ | 2015-10-10 | 0 | 0 | 0 | 2015-10-10 | 2015-10-11 | MT-PS-9301-CS-017-1 | complete | 100%
1204-22-PR-DSH-133 | 00 | Process Instrument Data Sheet for Safety Valves | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:41 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-00-ST-TBA-743 | 00 | TECHNICAL BID ANALYSIS FOR STEEL GRATING | DE | IFE | ST | PS-OT-T-0564 | 2018-02-21 |  | No | 803 | 1204-Owner-v | 2018-02-24 09:20 | TBA | 2018-03-01 | 0 | 0 | 0 | 2018-03-01 | 2018-02-24 | MT-PS-9609-CS-036 | complete | 100%
1204-90-ST-DWG-1020 | 01 | WORK SHOP / FRAMES II | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 12:55 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-00-QC-SOI-256A | 00 | SCOPE OF INSPECTION FOR FILTERS | DE | IFR | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 50%
1204-00-PV-TBA-204D | 00 | TECHNICAL BID ANALYSIS FOR PRESSURE VESSELS (GROUP IV) | DE | IFE | MD | PS-OT-T-0464 | 2017-08-05 |  | No | 1003 | 1204-Owner-v | 2017-08-06 10:39 | TBA | 2017-08-08 | 0 | 0 | 0 | 2017-08-08 |  |  | complete | 100%
1204-90-ST-DWG-1039 | 01 | WAREHOUSE / FRAMES II | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:08 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-90-EL-SLD-080 | 01 | TECHNICAL BUILDING EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 11:55 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-64-RE-DSH-051 | 00 | DATA SHEET FOR SULFURIC ACID TRANSFER PUMPS (P-6403 A/B) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-07 16:46 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-90-HV-DSH-012 | 01 | DATA SHEET FOR WALL TYPE EXHAUST FAN FOR HVAC ROOM IN LABORATORY | DE | IFE | HV | TM-OT-9001-T-0450 | 2015-03-06 |  | No | 1886 | 1204-TKT-COLANGELI | 2015-03-04 13:39 | DSH | 2015-03-06 | 0 | 0 | 0 | 2015-03-06 |  |  | complete | 100%
1204-90-HV-DSH-061 | 00 | DATA SHEET FOR AIR CONDENSER FOR CLINIC | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-10 13:25 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-90-HV-DWG-015 | 00 | LABORATORY - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN | DE | IFR | HV | TM-OT-9001-T-0388 | 2014-08-04 |  | No | 2100 | 1204-TKT-COLANGELI | 2014-08-04 11:33 | CDW | 2014-08-04 | 0 | 0 | 0 | 2014-08-04 |  |  | InProgress | 80%
1204-90-HV-DWG-052 | 01 | RESTAURANT - SECTION OF DUCTING | DE | IFC | HV | TM-OT-9001-T-0380 | 2014-07-01 |  | No | 2134 | 1204-TKT-COLANGELI | 2014-07-01 12:08 | CDW | 2014-07-01 | 0 | 0 | 0 | 2014-07-01 |  |  | complete | 100%
1204-90-HV-DID-004 | 04 | CONTROL ROOM - MECHANICAL ROOM GENERAL DIAGRAM | DE | IFC | HV | PS-OT-T-0708 | 2018-10-24 |  | No | 558 | 1204-Owner-v | 2018-10-29 13:59 | CDW | 2018-10-24 | 0 | 0 | 0 | 2018-10-24 |  |  | complete | 100%
1204-90-HV-DSH-028 | 01 | DATA SHEET ROOF TYPE EXHAUST FAN FOR DIESEL GEN. ROOM IN SUBSTATION | DE | IFE | HV | PS-OT-T-0010 | 2015-03-11 |  | No | 1881 | 1204-TKT-COLANGELI | 2015-03-04 13:38 | DSH | 2015-03-11 | 0 | 0 | 0 | 2015-03-11 |  |  | complete | 100%
1204-00-ST-DWG-023 | 02 | PIPE RACK ZONE 3 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0402 | 2014-10-30 |  | No | 2013 | 1204-TKT-COLANGELI | 2014-10-29 15:58 | CDW | 2014-10-30 | 0 | 0 | 0 | 2014-10-30 | 2014-11-11 | MT-TM-9301-CS-006 | complete | 100%
1204-00-ST-DWG-056 | 00 | PIPE RACK ZONE 8 / CONCRETE STRUCTURE ( R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0069 | 2015-07-01 |  | No | 1769 | 1204-Owner-v | 2015-07-01 15:58 | CDW | 2015-07-01 | 0 | 0 | 0 | 2015-07-01 |  |  | complete | 100%
1204-30-ST-DWG-354 | 01 | D-3006 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-338 | 2016-09-19 |  | No | 1323 | 1204-Owner-v | 2016-09-21 08:50 | CDW | 2016-09-19 | 0 | 0 | 0 | 2016-09-19 | 2016-09-21 | MT-PS-9301-CS-189 | complete | 100%
1204-90-HV-DSH-016 | 01 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR MESS ROOM & TEA ROOM IN LABORATORY | DE | IFE | HV | PS-OT-T-0009 | 2015-03-14 |  | No | 1878 | 1204-Owner-v | 2015-03-17 11:12 | DSH | 2015-03-14 | 0 | 0 | 0 | 2015-03-14 |  |  | complete | 100%
1204-20-PI-APL-2700 | 01 | PIPING PLAN AREA-27 | DE | IFC-WH | PI | PS-OT-T-0692 | 2018-09-29 |  | No | 583 | 1204-Owner-v | 2018-10-13 14:04 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-60-PI-ISO-6300 | 01 | U/G ISOMETRIC DRAWING OF AREA-63 | DE | IFC-WH | PI | PS-OT-T-0554 | 2018-02-12 |  | No | 812 | 1204-Owner-v | 2018-02-14 08:31 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | * | 2018-02-14 | MT-PS-9609-CS-029 | InProgress | 90%
1204-60-PI-LST-6300 | 01 | U/G ISOMETRIC LIST OF AREA-63 | DE | IFC-WH | PI | PS-OT-T-0554 | 2018-02-12 |  | No | 812 | 1204-Owner-v | 2018-02-14 08:40 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2017-02-18 |  |  | InProgress | 90%
1204-71-PI-LST-3300 | 00 | A/G ISOMETRIC LIST OF AREA-33 | DE | IFR | PI | TM-OT-9001-T-0427 | 2015-01-12 |  | No | 1939 | 1204-TKT-COLANGELI | 2015-01-09 14:59 | CDW | 2019-12-13 | 0 | 0 | 2020-05-28 | 2015-01-12 |  |  | InProgress | 80%
1204-90-EL-DWG-530 | 01 | ADMINISTRATION BUILDING COMMUNICATION LAYOUT | DE | IFC | EL | TM-OT-9001-T-0351 | 2014-01-29 | 2015-03-03 07:57 | Yes | 384 | 1204-TKT-COLANGELI | 2014-01-29 13:41 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-90-EL-SLD-047 | 01 | FIRE STATION EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:35 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:49 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-EL-SLD-051 | 01 | GUARD HOUSE EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:36 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:51 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-00-HS-REQ-155 | 00 | REQUISITION FOR FIRE FIGHTING EQUIPMENT | DE | IFI | HSE | PS-OT-T-0740 | 2018-12-22 |  | No | 499 | 1204-Owner-v | 2018-12-23 12:01 | REQ | 2020-09-15 | 0 | 0 | 2020-09-28 | * |  |  | InProgress | 90%
1204-20-HS-PID-001 | 01 | PIPING AND INSTRUMENTATION DIAGRAM FOR SPRAY NOZZLE SYSTEM FOR C-2001 & 2002 | DE | IFR | HSE | PS-OT-T-0545 | 2018-02-03 |  | No | 821 | 1204-Owner-v | 2018-02-04 08:23 | EDW | 2019-10-01 | 0 | 0 | 2020-07-30 | * | 2018-02-07 | MT-PS-9609-CS-024 | InProgress | 80%
1204-00-PV-TBA-201 | 03 | TECHNICAL BID ANALYSIS FOR SYNTHESIS CONVERTER (R-2001) | DE | IFE | MD | PS-OT-T-0108 | 2015-10-03 |  | No | 1675 | 1204-Owner-v | 2015-10-04 08:33 | TBA | 2015-10-10 | 0 | 0 | 0 | 2015-10-10 | 2015-10-20 |  | complete | 100%
1204-00-PI-MTO-404A | 05 | MATERIAL TAKE OFF FOR VALVES ABOVE GROUND (MTO I) | DE | IFE | PI | PS-OT-T-0552 | 2018-02-07 |  | No | 817 | 1204-Owner-v | 2018-02-12 07:56 | LIST | 2018-02-15 | 0 | 0 | 0 | 2018-02-15 | 2018-04-04 | MT-PS-9609-CS-049-R | complete | 100%
1204-00-PI-UPL-7600 | 00 | UNDER GROUND PIPING PLAN AREA-76 | DE | IFR | PI | TM-OT-9001-T-0173 | 2012-10-04 |  | No | 2769 | 1204-Owner-v | 2015-04-18 09:02 | CDW | 2019-12-17 | 0 | 0 | 2020-06-08 | 2012-10-04 |  |  | InProgress | 80%
1204-10-PR-PID-109 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- INDUCED DRAFT FAN & COMBUSTION AIR FAN | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:24 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-01 | 2017-05-20 | MT-PS-9301-CS-200-R | InProgress | 80%
1204-22-PR-DSH-141 | 00 | Process Instrument Data Sheet for Temperature Transmitters | BE | IFR | PR | TM-OT-9001-T-0134 | 2012-07-13 |  | No | 2852 | 1204-Owner-v | 2015-09-16 17:42 | DSH | 2019-10-01 | 0 | 0 | 2020-11-20 | 2012-07-13 |  |  | InProgress | 80%
1204-00-EL-CSH-006 | 00 | LOAD FLOW ANALYSIS | DE | IFR | EL | PS-OT-T-0634 | 2018-06-19 |  | No | 685 | 1204-Owner-v | 2018-06-24 08:27 | LIST | 2020-10-10 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 90%
1204-40-ST-DWG-456 | 01 | BOILER (PU-4006 B ) / FDN. (G.A. & R.C. DETAILS II ) | DE | IFC | ST | PS-OT-T-0191 | 2016-01-30 |  | No | 1556 | 1204-Owner-v | 2016-01-31 09:33 | CDW | 2016-01-30 | 0 | 0 | 0 | 2016-01-30 | 2016-02-01 | MT-PS-9301-CS-097 | complete | 100%
1204-04-EL-SLD-066 | 00 | SINGLE LINE DIAGRAM FOR 04-DP-01 | DE | IFR | EL | PS-OT-T-0297 | 2016-06-25 | 2016-07-21 14:36 | Yes | 12 | 1204-Owner-v | 2016-06-28 17:31 | CDW | 2020-10-10 | 0 | 0 | 2020-10-10 | 2016-07-02 | 2016-06-25 | MT-PS-9301-CS-169 | InProgress | 80%
1204-40-ST-DWG-467 | 01 | D-4003 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0295 | 2016-06-22 |  | No | 1412 | 1204-Owner-v | 2016-06-25 10:31 | CDW | 2016-06-22 | 0 | 0 | 0 | 2016-06-22 | 2016-06-25 | MT-PS-9301-CS-166 | complete | 100%
1204-00-PI-MTO-415A | 00 | MATERIAL TAKE OFF FOR SAMPLE COOLER (MTO I) | DE | IFE | PI | PS-OT-T-0936 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 16:03 | LIST | 2020-11-15 | 0 | 0 | 2020-09-01 | * | 2020-03-17 | MT-PS-9609-CS-0315 | complete | 100%
1204-84-HS-DSH-013 | 01 | DATA SHEET FOR SANITARY WATER COLLECTION BASIN (SU-8406) | DE | IFR | HSE | PS-OT-T-0854 | 2019-12-28 |  | No | 128 | 1204-Owner-v | 2020-01-03 09:53 | DSH | 2020-10-10 | 0 | 0 | 2020-10-10 | * | 2020-02-12 | MT-PS-9301-CS-0269-1 | InProgress | 80%
1204-10-QC-SOI-202D | 00 | SCOPE OF INSPECTION FOR STEAM DRUMS OF WASTE HEAT BOILER | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-22-PI-ISO-1900 | 00 | A/G ISOMETRIC DRAWING OF AREA-19 | DE | IFR | PI | PS-OT-T-0195 | 2016-02-13 |  | No | 1542 | 1204-Owner-v | 2016-02-15 11:45 | CDW | 2020-06-04 | 0 | 0 | 2020-06-04 | 2016-02-20 |  |  | InProgress | 80%
1204-30-PI-APL-2300 | 01 | PIPING PLAN AREA-23 | DE | IFC-WH | PI | PS-OT-T-0651 | 2018-07-23 |  | No | 651 | 1204-Owner-v | 2018-07-28 13:24 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * | 2018-08-04 | MT-PS-9609-CS-105 | InProgress | 90%
1204-00-PI-REQ-461A | 00 | REQUISITION FOR U/G PIPES & FITTINGS(MTO I) | DE | IFI | PI | TM-OT-9001-T-0430 | 2015-01-15 |  | No | 1936 | 1204-TKT-COLANGELI | 2015-01-15 14:38 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-00-IN-DSH-636 | 00 | DATA SHEET FOR N2 BLANKETING SYSTEM | DE | IFR | IN | PS-OT-T-0538 | 2018-01-20 |  | No | 835 | 1204-Owner-v | 2018-01-21 10:32 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2018-01-21 | 2018-01-28 | MT-PS-9609-CS-016 | InProgress | 80%
1204-00-IN-REQ-601 | 01 | REQUISITION FOR FIELDBUS CONTROL SYSTEM | DE | IFP | IN | PS-OT-T-0909 | 2020-02-24 |  | No | 70 | 1204-Owner-v | 2020-02-25 17:01 | REQ | 2020-02-24 | 0 | 0 | 0 | 2020-02-24 | 2020-03-01 | MT-PS-9609-CS-0291 | complete | 100%
1204-00-ST-DWG-084 | 01 | PIPE RACK ZONE 3 / STEEL PARTS | DE | IFC | ST | PS-OT-T-0541 | 2018-01-10 |  | No | 845 | 1204-Owner-v | 2018-01-21 12:27 | CDW | 2018-01-10 | 0 | 0 | 0 | 2018-01-10 | 2018-01-21 | MT-PS-9609-CS-011 | complete | 100%
1204-63-IN-DWG-017 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 17) | DE | IFR | IN | PS-OT-T-0220 | 2016-03-14 |  | No | 1512 | 1204-Owner-v | 2016-03-14 11:10 | CDW | 2020-06-19 | 0 | 0 | 2020-06-19 | * | 2016-03-16 | MT-PS-9301-CS-117-1 | InProgress | 80%
1204-64-IN-DWG-030 | 00 | INSTRUMENT FIELD & CABLE LAYOUT (AREA 30) | DE | IFR | IN | PS-OT-T-0152 | 2015-12-20 |  | No | 1597 | 1204-Owner-v | 2015-12-22 13:28 | CDW | 2020-06-23 | 0 | 0 | 2020-06-23 | 2015-12-28 | 2016-01-10 | MT-PS-9301-CS-079 | InProgress | 80%
1204-04-EL-DWG-002 | 00 | POWER LAYOUT FOR AREA-04 - AE-3001 AND DA-4001 | DE | IFR | EL | PS-OT-T-330 | 2016-08-28 | 2016-10-10 16:59 | Yes | 29 | 1204-Owner-v | 2016-08-28 16:07 | CDW | 2020-07-20 | 0 | 0 | 2020-07-20 | * | 2016-09-03 | MT-PS-9301-CS-182-R | InProgress | 80%
1204-20-ST-DWG-1172 | 03 | STRUCTURE "M" FOR R-2001 / CONCRETE STRUCTURE (G.A. PLAN & DETAILS) | DE | IFC | ST | PS-OT-T-0781 | 2019-04-17 |  | No | 383 | 1204-Owner-v | 2019-04-18 11:29 | CDW | 2019-04-20 | 0 | 0 | 0 | 2019-04-20 |  |  | complete | 100%
1204-64-PV-DSH-204 | 03 | MECHANICAL DATA SHEET FOR CONDENSATE STORAGE TANK (TK-6401) | DE | IFE | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:27 | DSH | 2019-11-13 | 0 | 0 | 0 | 0 |  |  | complete | 100%
1204-00-QC-SOI-214B | 00 | SCOPE OF INSPECTION FOR TANK SEALING SYSTEM | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-90-ST-DWG-1014 | 01 | WORK SHOP / ELEVATIONS | DE | IFC | ST | TM-OT-9001-T-0261 | 2013-04-24 |  | No | 2567 | 1204-TKT-COLANGELI | 2013-04-24 11:31 | CDW | 2013-04-24 | 0 | 0 | 0 | 2013-04-24 |  |  | complete | 100%
1204-63-PR-DSH-142 | 00 | Process Instrument Data Sheet for Orifice Plate and Flanges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:59 | DSH | 2019-10-01 | 0 | 0 | 2020-12-30 | 2012-07-24 |  |  | InProgress | 80%
1204-90-HV-DSH-027 | 00 | DATA SHEET FOR CENTRIFUGAL EXHAUST FAN FOR CABLE CELLAR CO2 REMOVAL IN SUBSTATION | DE | IFE | HV | TM-OT-9001-T-0316 | 2013-09-11 |  | No | 2427 | 1204-TKT-COLANGELI | 2013-09-09 14:54 | DSH | 2013-09-11 | 0 | 0 | 0 | 2013-09-11 |  |  | InProgress | 80%
1204-62-PR-DSH-136 | 00 | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE GAUGES | BE | IFR | PR | TM-OT-9001-T-0142 | 2012-08-28 |  | No | 2806 | 1204-Owner-v | 2015-09-16 17:56 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-08-28 |  |  | InProgress | 80%
1204-64-PR-DSH-132 | 00 | PROCESS INSTRUMENT DATA SHEET FOR LEVEL GAUGES | BE | IFR | PR | TM-OT-9001-T-0142 | 2012-08-28 |  | No | 2806 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-08-28 |  |  | InProgress | 80%
1204-64-PR-DSH-134 | 00 | Process Instrument Data Sheet for Pressure Gauges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 18:02 | DSH | 2019-10-01 | 0 | 0 | 2020-10-20 | 2012-07-24 |  |  | InProgress | 80%
1204-30-ST-DWG-313 | 01 | STRUCTURE "C" FOR D-3001,D-3002,E-3001,E-3002,E-3007,E-3011 / STEEL STRUCTURE (STAIR) | DE | IFC | ST | PS-OT-T-0751 | 2019-02-05 |  | No | 454 | 1204-Owner-v | 2019-02-06 09:22 | CDW | 2019-02-05 | 0 | 0 | 0 | 2019-02-05 |  |  | complete | 100%
1204-90-ST-DWG-924 | 01 | CONTROL ROOM & LABORATORY / PLUMBING LAYOUT ( FIRST FLOOR PLAN ) | DE | IFC | ST | TM-OT-9001-T-0394 | 2014-09-15 |  | No | 2058 | 1204-TKT-COLANGELI | 2014-09-12 12:27 | CDW | 2014-09-15 | 0 | 0 | 0 | 2014-09-15 | 2014-09-24 | MT-OT-9301-CS-025 | complete | 100%
1204-90-ST-DWG-1061 | 01 | FIRE STATION / COLUMN (R.C. DETAILS) | DE | IFC | ST | TM-OT-9001-T-0341 | 2013-12-18 |  | No | 2329 | 1204-TKT-COLANGELI | 2013-12-16 15:04 | CDW | 2013-12-18 | 0 | 0 | 0 | 2013-12-18 |  |  | complete | 100%
1204-00-QC-SOI-526 | 00 | SCOPE OF INSPECTION FOR JUNCTION BOXES | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-30-RE-DSH-331 | 00 | DATA SHEET FOR FUSEL OIL PUMPS (P-3005 A/B) | DE | IFR | MC | PS-OT-T-0836 | 2019-11-16 |  | No | 170 | 1204-Owner-v | 2020-01-05 07:59 | DSH | 2019-11-16 | 0 | 0 | 0 |  |  |  | InProgress | 80%
1204-90-EL-SLD-082 | 01 | CONTROL ROOM SAFETY LIGHTING PANEL ONE LINE DIAGRAM | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 | 2015-03-03 08:41 | Yes | 390 | 1204-TKT-COLANGELI | 2014-01-23 11:56 | CDW | 2014-01-23 | 0 | 0 | 0 | 2014-01-23 |  |  | complete | 100%
1204-90-ST-DWG-1095 | 03 | ADMINISTRATION , RESTAURANT ,CLINIC & GUARD HOUSE BUILDING / FURNITURE PLAN FOR THIRD FLOOR PLAN | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-03 10:03 | CDW | 2020-03-30 | 0 | 0 | 2020-03-30 | 0 | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-00-EL-TBA-522 | 01 | TECHNICAL BID ANALYSIS FOR MV ELECTRICAL MOTORS FOR PRIMERY REFORMER | DE | IFE | EL | PS-OT-T-0837 | 2019-11-19 |  | No | 167 | 1204-Owner-v | 2019-11-26 15:16 | TBA | 2020-02-25 | 0 | 0 | 2020-03-02 | 0 | 2020-01-12 | MT-PS-9609-CS-0242-1 | complete | 100%
1204-00-ST-DWG-193 | 02 | PIPE RACK ZONE 16 / STEEL STRUCTURE (PLAN & DETS.) | DE | IFC | ST | PS-OT-T-0862 | 2020-01-01 |  | No | 124 | 1204-Owner-v | 2020-01-02 08:28 | CDW | 2020-01-01 | 0 | 0 | 0 | 2020-01-01 |  |  | complete | 100%
1204-90-EL-DWG-510 | 01 | ADMINISTRATION BUILDING LIGHTING AND SMALL POWER LAYOUT | DE | IFC | EL | TM-OT-9001-T-0349 | 2014-01-23 |  | No | 2293 | 1204-TKT-COLANGELI | 2014-01-23 12:17 | CDW | 2021-04-15 | 0 | 0 | 2021-04-15 | * |  |  | complete | 100%
1204-00-IN-DSH-634 | 01 | DATA SHEET FOR RADAR TYPE LEVEL TRANSMITTERS | DE | IFR | IN | PS-OT-T-0396 | 2017-01-07 |  | No | 1213 | 1204-Owner-v | 2017-01-11 13:49 | DSH | 2020-08-10 | 0 | 0 | 2020-08-10 | 2017-01-31 | 2017-02-15 | MT-PS-9301-CS-207-1 | InProgress | 80%
1204-00-IN-MTO-003 | 00 | MATERIAL TAKE OFF FOR INSTRUMENT CABLE GLAND | DE | IFE | IN | PS-OT-T-0880 | 2020-02-06 |  | No | 88 | 1204-Owner-v | 2020-02-08 10:12 | LIST | 2019-12-25 | 0 | 0 | 2020-04-28 | * | 2020-04-16 | MT-PS-9609-CS-0271-R | complete | 100%
1204-00-IN-REQ-628 | 00 | REQUISITION FOR INSTRUMENT CABLES | DE | IFI | IN | PS-OT-T-0897 | 2020-02-18 |  | No | 76 | 1204-Owner-v | 2020-02-18 16:58 | REQ | 2020-06-09 | 0 | 0 | 2020-06-15 | * | 2020-02-27 | MT-PS-9609-CS-0278 | InProgress | 90%
1204-00-PI-MTO-462A | 04 | MATERIAL TAKE OFF FOR U/G FLANGES (MTO I) | DE | IFE | PI | PS-OT-T-0470 | 2017-08-26 |  | No | 982 | 1204-Owner-v | 2017-08-30 15:03 | LIST | 2017-08-30 | 0 | 0 | 0 | 2017-08-30 | 2017-10-23 | MT-PS-9301-CS-260 | complete | 100%
1204-00-PI-PPL-003 | 01 | PLOT PLAN UNIT 200 | DE | IFR | PI | PS-OT-T-0427 | 2017-03-06 |  | No | 1155 | 1204-Owner-v | 2017-05-01 09:58 | CDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-04-09 | 2017-05-08 | MT-PS-9301-CS-226-R | InProgress | 80%
1204-00-PI-UPL-7000 | 03 | UNDER GROUND PIPING PLAN AREA-70 | DE | IFC-WH | PI | PS-OT-T-0621 | 2018-05-30 |  | No | 705 | 1204-Owner-v | 2018-06-02 10:43 | CDW | 2018-06-02 | 0 | 0 | 0 | 2018-06-02 | 2018-06-02 | MT-PS-9609-CS-079 | InProgress | 90%
1204-10-PR-PID-107 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- PRIMARY REFORMER RAD & CONV. SECTION PROCESS COILS | DE | IFR | PR | PS-OT-T-363 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-12-10 11:37 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2016-11-18 | 2017-01-04 | MT-PS-9301-CS-200 | InProgress | 80%
1204-65-PR-DSH-101 | 00 | DATA SHEET FOR FUEL GAS CONDENSATE POT | BE | IFR | PR | TM-OT-9001-T-0276 | 2013-05-16 |  | No | 2545 | 1204-TKT-COLANGELI | 2013-05-16 11:57 | DSH | 2020-05-01 | 0 | 0 | 2020-06-30 | 2013-05-16 |  |  | InProgress | 80%
1204-30-ST-DWG-335 | 02 | STRUCTURE "E" FOR E-3004,E-3012 / BEAMS (G.A. PLAN & R.C. DETAILS) | DE | IFC | ST | PS-OT-T-0413 | 2017-02-07 |  | No | 1182 | 1204-Owner-v | 2017-02-08 14:33 | CDW | 2017-02-14 | 0 | 0 | 0 | 2017-02-14 |  |  | complete | 100%
1204-90-HS-DWG-009 | 02 | FIRE ALARM LAYOUT FOR WAREHOUSE | DE | IFE | HSE | PS-OT-T-0128 | 2015-11-04 |  | No | 1643 | 1204-Owner-v | 2015-11-05 10:31 | EDW | 2015-11-17 | 0 | 0 | 0 | 2015-11-17 | 2015-11-29 | MT-PS-9301-CS-048 | complete | 100%
1204-90-HS-LST-005 | 01 | SAFETY EQUIPMENT LIST FOR ADMINISTRATION, RESTAURANT AND CLINIC BUILDING | DE | IFE | HSE | PS-OT-T-376 | 2016-12-12 |  | No | 1239 | 1204-Owner-v | 2016-12-24 08:56 | LIST | 2016-12-12 | 0 | 0 | 0 | 2016-12-12 |  |  | complete | 100%
1204-00-ST-MTO-1107 | 01 | MATERIAL TAKE OFF FOR RETAINING WALL | DE | IFE | ST | TM-OT-9001-T-0401 | 2014-10-20 |  | No | 2023 | 1204-TKT-COLANGELI | 2014-10-20 10:59 | LIST | 2014-10-20 | 0 | 0 | 0 | 2014-10-20 | 2014-11-11 | MT-TM-9301-CS-005 | complete | 100%
1204-10-PI-LST-7100 | 01 | U/G ISOMETRIC LIST OF AREA-71 | DE | IFC-WH | PI | PS-OT-T-0618 | 2018-05-23 |  | No | 712 | 1204-Owner-v | 2018-06-03 11:19 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-06-02 | 2018-05-23 | MT-PS-9609-CS-076 | InProgress | 90%
1204-63-PI-APL-2100 | 01 | PIPING PLAN AREA-21 | DE | IFC-WH | PI | PS-OT-T-0933 | 2020-03-14 |  | No | 51 | 1204-Owner-v | 2020-03-15 15:56 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | * |  |  | InProgress | 90%
1204-64-PI-UPL-6900 | 02 | UNDER GROUND PIPING PLAN AREA-69 | DE | IFC-WH | PI | PS-OT-T-0606 | 2018-05-12 |  | No | 723 | 1204-Owner-v | 2018-05-13 15:30 | CDW | 2018-05-26 | 0 | 0 | 0 | 2018-05-26 |  |  | InProgress | 90%
1204-72-PI-ISO-7300 | 03 | U/G ISOMETRIC DRAWING OF AREA-73 | DE | IFC-WH | PI | PS-OT-T-0598 | 2018-04-25 |  | No | 740 | 1204-Owner-v | 2018-04-30 09:29 | CDW | 2020-06-30 | 0 | 0 | 2020-06-30 | 2018-05-03 |  |  | complete | 100%
1204-10-PR-PID-118 | 01 | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- ATR BURNER COOLING SYSTEM | DE | IFR | PR | PS-OT-T-364 | 2016-11-13 |  | No | 1268 | 1204-Owner-v | 2016-11-16 12:25 | EDW | 2020-06-01 | 0 | 0 | 2020-06-01 | 2017-05-20 | 2017-05-21 | MT-PS-9301-CS-202-1-R | InProgress | 80%
1204-00-PI-ISO-3700 | 00 | A/G ISOMETRIC DRAWING OF AREA-37 | DE | IFR | PI | PS-OT-T-0282 | 2016-06-12 |  | No | 1422 | 1204-Owner-v | 2016-06-14 09:44 | CDW | 2020-06-11 | 0 | 0 | 2020-06-11 | 2016-06-18 | 2016-06-20 | MT-PS-9301-CS-162 | InProgress | 80%
1204-10-PV-DSH-210 | 00 | MECHANICAL DATA SHEET FOR NATURAL GAS SEPARATOR (D-1001) | DE | IFR | MD | PS-OT-T-0833 | 2019-11-13 |  | No | 173 | 1204-Owner-v | 2019-11-27 10:40 | DSH | 2019-11-13 | 0 | 0 | 0 | 2019-11-13 |  |  | InProgress | 80%
1204-10-RE-DSH-059 | 00 | DATA SHEET FOR SECOND SATURATION PUMPS P-1002 A/B | DE | IFR | MC | PS-OT-T-0385 | 2016-12-20 |  | No | 1231 | 1204-Owner-v | 2016-12-24 09:14 | DSH | 2016-12-27 | 0 | 0 | 0 | 2016-12-27 | 2017-04-15 | MT-PS-9301-CS-210-1 | InProgress | 80%
1204-90-ST-DWG-946 | 02 | SUBSTATION / SLABS (R.C. II) | DE | IFC | ST | TM-OT-9001-T-0369 | 2014-05-23 |  | No | 2173 | 1204-TKT-COLANGELI | 2014-05-22 13:35 | CDW | 2014-05-23 | 0 | 0 | 0 | 2014-05-23 |  |  | complete | 100%
1204-90-ST-MTO-927 | 00 | MATERIAL TAKE OFF FOR CONTROL ROOM & LABORATORY / ARCHITECTURAL | DE | IFE | ST | TM-OT-9001-T-0405 | 2014-10-31 |  | No | 2012 | 1204-TKT-COLANGELI | 2014-10-31 13:21 | LIST | 2014-10-31 | 0 | 0 | 0 | 2014-10-31 | 2014-11-11 | MT-TM-9301-CS-008 | complete | 100%
1204-00-QC-SOI-517 | 00 | SCOPE OF INSPECTION FOR LV VARIABLE SPEED DRIVES | DE | IFI | QC | PS-OT-T-9999 | 1930-12-30 |  | No | 32633 |  |  | SCOPE | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | complete | 100%
1204-62-PR-DSH-141 | 00 | Process Instrument Data Sheet for Orifice Plate and Flanges | BE | IFR | PR | TM-OT-9001-T-0136 | 2012-07-24 |  | No | 2841 | 1204-Owner-v | 2015-09-16 17:57 | DSH | 2019-10-01 | 0 | 0 | 2020-12-20 | 2012-07-24 |  |  | InProgress | 80%
1204-90-ST-DWG-1087 | 01 | GUARD HOUSE / STEEL STRUCTURE | DE | IFC | ST | TM-OT-9001-T-0234 | 2013-02-05 |  | No | 2645 | 1204-TKT-COLANGELI | 2013-02-05 13:18 | CDW | 2013-02-05 | 0 | 0 | 0 | 2013-02-05 |  |  | complete | 100%
1204-72-ST-DWG-735 | 02 | TK-7201 / FDN. (G.A. & R.C.) | DE | IFC | ST | TM-OT-9001-T-0364 | 2014-05-06 |  | No | 2190 | 1204-TKT-COLANGELI | 2014-05-06 13:14 | CDW | 2014-05-06 | 0 | 0 | 0 | 2014-05-06 |  |  | complete | 100%
1204-22-RE-DSH-038 | 00 | DATA SHEET FOR MACHINERY COOLING WATER PUMPS (P-2201 A/B) | DE | IFR | MC | TM-OT-9001-T-0226 | 2013-01-09 |  | No | 2672 | 1204-TKT-COLANGELI | 2013-01-07 13:41 | DSH | 2013-01-09 | 0 | 0 | 0 | 2013-01-09 |  |  | InProgress | 80%
1204-10-ST-DWG-153 | 02 | REFORMER (A.P.H.) / FDN. (R.C.) | DE | IFC | ST | PS-OT-T-0817 | 2019-07-22 |  | No | 287 | 1204-Owner-v | 2019-07-24 09:35 | CDW | 2019-07-24 | 0 | 0 | 0 | 2019-07-24 |  |  | complete | 100%
1204-90-ST-DWG-921 | 04 | CONTROL ROOM & LABORATORY / WALLS (R.C.DETAILS II ) | DE | IFC | ST | TM-OT-9001-T-0390 | 2014-08-13 |  | No | 2091 | 1204-TKT-COLANGELI | 2014-08-12 12:16 | CDW | 2014-08-20 | 0 | 0 | 0 | 2014-08-20 | 2014-08-20 | MT-OT-9301-CS-018 | complete | 100%
1204-84-HS-DSH-011 | 00 | DATA SHEET FOR SANITARY DISCHARGE PUMP (P-8406) | DE | IFR | HSE | PS-OT-T-0685 | 2018-09-24 |  | No | 588 | 1204-Owner-v | 2018-10-06 11:08 | DSH | 2020-10-10 | 0 | 0 | 2020-10-10 | * |  |  | InProgress | 80%
1204-10-PV-TBA-202G | 01 | TECHNICAL BID ANALYSIS FOR STEEL STRUCTURE OF WASTE HEAT BOILER | DE | IFE | MD | PS-OT-T-0891 | 2020-02-15 |  | No | 79 | 1204-Owner-v | 2020-02-16 09:25 | TBA | 2020-01-09 | 0 | 0 | 2020-01-21 | * | 2020-03-10 | MT-PS-9609-CS-0308 | complete | 100%
1204-10-HM-TBA-251C | 00 | TECHNICAL BID ANALYSIS FOR CONVECTION COILS FABRICATION , MODULARIZATION& FINING AND CAST PARTS SUPPLY OF CONVECTION SECTION TUBE SHEETS | DE | IFE | MD | PS-OT-T-0779 | 2019-04-14 |  | No | 386 | 1204-Owner-v | 2019-04-15 16:53 | TBA | 2019-11-26 | 0 | 0 | 2019-12-16 | 2019-04-18 |  |  | complete | 100%
1204-00-PI-MTO-409M | 00 | MATERIAL TAKE OFF FOR PAINT MTO (PIPES) | DE | IFE | PI | PS-OT-T-0771 | 2019-03-18 |  | No | 413 | 1204-Owner-v | 2019-03-19 11:21 | LIST | 2019-04-04 | 0 | 0 | 0 | 2019-04-04 |  |  | complete | 100%
1204-90-ST-DWG-993 | 00 | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FURNITURE PLAN FOR BASEMENT | DE | IFR | ST | PS-OT-T-0863 | 2020-01-02 |  | No | 123 | 1204-Owner-v | 2020-01-03 10:03 | CDW | 2020-01-02 | 0 | 0 | 0 | 2020-01-02 | 2020-02-08 | MT-PS-9609-CS-0266 | InProgress | 80%
1204-00-PI-REQ-422 | 00 | REQUISITION FOR PAINT FOR FLARE AND UTILITY LINE(OSBL) | DE | IFI | PI | PS-OT-T-0943 | 2020-04-05 |  | No | 29 | 1204-Owner-v | 2020-04-07 08:22 | REQ | 2020-05-15 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | InProgress | 90%
1204-40-ST-DWG-417 | 01 | T-4001 / FDN. (G.A. & R.C.) | DE | IFC | ST | PS-OT-T-0177 | 2016-01-09 |  | No | 1577 | 1204-Owner-v | 2016-01-10 09:13 | CDW | 2016-01-09 | 0 | 0 | 0 | 2016-01-09 |  | Final Checked | complete | 100%
1204-90-ST-DWG-1010 | 00 | SUBSTATION / SLABS (R.C. IV) | DE | IFC | ST | TM-OT-9001-T-0300 | 2013-07-04 |  | No | 2496 | 1204-TKT-COLANGELI | 2013-07-03 12:14 | CDW | 2013-07-04 | 0 | 0 | 0 | 2013-07-04 |  |  | complete | 100%
1204-00-PR-BFD-101 |  | BLOCK FLOW DIAGRAM FOR COMPLEX |  |  | PR | [7 empty] | EDW | 2019-10-01 |  |  | 2021-02-03 |  |  |  | notIssue | 0%
1204-00-PR-LST-001 |  | TIE IN POINT LIST |  |  | PR | [7 empty] | LIST | 2020-04-01 |  |  | 2020-04-30 |  |  |  | InProgress | 90%
1204-00-PR-ESS-101 |  | ENGINEERING STANDARD SPECIFICATION FOR AMBIENT AND SITE CONDITION DATA |  |  | PR | [7 empty] | SPEC | 2019-10-01 |  |  | 2020-05-11 |  |  |  | notIssue | 0%
1204-00-PR-ESS-102 |  | ENGINEERING STANDARD SPECIFICATION FOR UTILITY DATA |  |  | PR | [7 empty] | SPEC | 2019-10-01 |  |  | 2020-05-11 |  |  |  | notIssue | 0%
1204-00-PR-ESS-103 |  | ENGINEERING STANDARD SPECIFICATION FOR UNITS OF MEASUREMENTS |  |  | PR | [7 empty] | SPEC | 2019-10-01 |  |  | 2020-05-11 |  |  |  | notIssue | 0%
1204-66-PR-UFD-661 |  | UTILITY FLOW DIAGRAM FOR DIESEL FUEL SYSTEM |  |  | PR | [7 empty] | EDW | 2020-06-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-66-PR-PID-661 |  | PIPING & INSTRUMENTATION FLOW DIAGRAM FOR DIESEL FUEL SYSTEM |  |  | PR | [7 empty] | EDW | 2020-05-01 |  |  | 2020-06-30 |  |  |  | InProgress | 80%
1204-66-PR-DBS-101 |  | BASIC ENGINEERING DESIGN FOR DIESEL FUEL SYSTEM |  |  | PR | [7 empty] | EDW | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-66-PR-LST-001 |  | EQUIPMENT LIST FOR DIESEL SYSTEM |  |  | PR | [7 empty] | LIST | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PR-LST-005 |  | PROCESS STEAM TRAP LIST |  |  | PR | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PR-LST-006 |  | CATALYST SUMMARY PROCESS DESCRIPTION |  |  | PR | [7 empty] | LIST | 2020-03-26 |  |  | 2020-05-06 |  |  |  | notIssue | 0%
1204-00-PR-LST-007 |  | CHEMICALS SUMMARY LIST FOR LABORATORY |  |  | PR | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PR-LST-017 |  | LABORATORY ANALYSIS SHEDULE |  |  | PR | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-61-PR-LST-002 |  | LINE LIST FOR NITROGEN (ASU) SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-08 |  |  | 2020-05-06 |  |  |  | InProgress | 5%
1204-65-PR-LST-002 |  | LINE LIST FOR FUEL GAS SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-08 |  |  | 2020-05-06 |  |  |  | InProgress | 5%
1204-66-PR-LST-002 |  | LINE LIST FOR DIESEL SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-08 |  |  | 2020-05-06 |  |  |  | notIssue | 0%
1204-06-PR-LST-004 |  | OVERALL UTILITY SUMMARY FOR UTILITY UNIT |  |  | PR | [7 empty] | LIST | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-22-PR-LST-004 |  | ALARM SET POINT LIST FOR MACHINERY COOLING WATER SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-61-PR-LST-004 |  | ALARM SET POINT LIST FOR NITROGEN (ASU) SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-62-PR-LST-004 |  | ALARM SET POINT LIST FOR INSTRUMENT AIR / PLANT AIR SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-15 |  |  |  | notIssue | 0%
1204-63-PR-LST-004 |  | ALARM SET POINT LIST FOR COOLING WATER SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-15 |  |  |  | notIssue | 0%
1204-64-PR-LST-004 |  | ALARM SET POINT LIST FOR WATER POLISHING SYSTEM SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-65-PR-LST-004 |  | ALARM SET POINT LIST FOR FUEL GAS SYSTEM |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-71-PR-LST-004 |  | ALARM SET POINT LIST FOR DAILY METHANOL STORAGE TANKS |  |  | PR | [7 empty] | LIST | 2020-01-22 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-72-PR-LST-004 |  | UTILITY SUMMARY LIST FOR CRUDE METHANOL STORAGE TANK |  |  | PR | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-61-PR-DIG-001 |  | CAUSE AND EFFECT DIAGRAM FOR NITROGEN (ASU) SYSTEM |  |  | PR | [7 empty] | LIST | 2020-02-05 |  |  | 2020-05-06 |  |  |  | notIssue | 0%
1204-65-PR-DIG-001 |  | CAUSE AND EFFECT DIAGRAM FOR FUEL GAS SYSTEM |  |  | PR | [7 empty] | LIST | 2020-02-05 |  |  | 2020-05-07 |  |  |  | notIssue | 0%
1204-00-PR-DSH-101 |  | DATA SHEET FOR LABORATORY EQUIPMENT |  |  | PR | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-63-PR-DSH-110 |  | DATA SHEET FOR COOLING TOWER BLOW DOWN PUMPS (P-6303 A/B) |  |  | PR | [7 empty] | DSH | 2020-06-23 | [6 empty] | complete | 100%
1204-64-PR-DSH-112 |  | DATA SHEET FOR CONDENSATE / DEMIN WATER EXCHNAGER (E-6401) |  |  | PR | [7 empty] | DSH | 2020-05-01 |  |  | 2020-06-30 |  |  |  | InProgress | 80%
1204-64-PR-DSH-113 |  | DATA SHEET FOR CONDENSATE COOLER (E-6402) |  |  | PR | [7 empty] | DSH | 2020-05-01 |  |  | 2020-06-30 |  |  |  | InProgress | 80%
1204-66 PR-DSH-101 |  | DATA SHEET FOR DIESEL STORAGE TANK (TK-6601) |  |  | PR | [7 empty] | DSH | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-66-PR-DSH-102 |  | DATA SHEET FOR DIESEL TRANSFER PUMPS (P-6601 A/B) |  |  | PR | [7 empty] | DSH | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-66-PR-DSH-103 |  | DATA SHEET FOR DIESEL UNLOADING PUMP (P-6601) |  |  | PR | [7 empty] | DSH | 2020-05-01 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-62-PR-DSH-135 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL TRANSMITTERS (UNIT 62) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-12-20 |  |  |  | InProgress | 5%
1204-64-PR-DSH-135 |  | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE TRANSMITTERS (UNIT 64) |  |  | PR | [7 empty] | DSH | 2019-12-09 |  |  | 2020-10-20 |  |  |  | InProgress | 5%
1204-64-PR-DSH-137 |  | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE TRANSMITTERS (UNIT 64) |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-10-20 |  |  |  | InProgress | 5%
1204-65-PR-DSH-131 |  | PROCESS INSTRUEMNT DATA SHEET FOR CONTROL VALVES |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-65-PR-DSH-133 |  | PROCESS INSTRUEMNT DATA SHEET FOR SAFETY VALVES |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-65-PR-DSH-136 |  | PROCESS INSTRUEMNT DATA SHEET FOR LEVEL GAUGE |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-65-PR-DSH-138 |  | PROCESS INSTRUEMNT DATA SHEET FOR PRESSURE GAUGE |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-65-PR-DSH-139 |  | PROCESS INSTRUEMNT DATA SHEET FOR PRESSURE TRANSMITTER |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-65-PR-DSH-140 |  | PROCESS INSTRUEMNT DATA SHEET FOR SELF CONTAINED REGULATOR |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-71-PR-DSH-131 |  | PROCESS INSTRUMENT DATA SHEET FOR CONTROL VALVES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-04-13 |  |  |  | InProgress | 5%
1204-71-PR-DSH-132 |  | PROCESS INSTRUMENT DATA SHEET FOR ON / OFF VALVES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-03 |  |  | 2020-04-09 |  |  |  | InProgress | 35%
1204-71-PR-DSH-133 |  | PROCESS INSTRUMENT DATA SHEET FOR SAFETY VALVES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-14 |  |  |  | InProgress | 35%
1204-71-PR-DSH-134 |  | PROCESS INSTRUMENT DATA SHEET FOR BREATHER VALVES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-10 |  |  |  | InProgress | 5%
1204-71-PR-DSH-135 |  | PROCESS INSTRUMENT DATA SHEET FOR ORIFICE PLATE AND FLANGES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-13 |  |  |  | InProgress | 5%
1204-71-PR-DSH-136 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL GAUGES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-14 |  |  |  | InProgress | 5%
1204-71-PR-DSH-137 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL TRANSMITTERS (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-10 |  |  |  | InProgress | 35%
1204-71-PR-DSH-138 |  | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE GAUGES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-01-20 |  |  |  | InProgress | 35%
1204-71-PR-DSH-139 |  | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE TRANSMITTERS (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-13 |  |  |  | InProgress | 35%
1204-71-PR-DSH-140 |  | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE GAUGES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-10 |  |  |  | InProgress | 35%
1204-71-PR-DSH-141 |  | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE TRANSMITTERS (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-10 |  |  |  | InProgress | 5%
1204-71-PR-DSH-142 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL SWITCHES (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-04 |  |  | 2020-04-14 |  |  |  | InProgress | 35%
1204-71-PR-DSH-143 |  | PROCESS INSTRUMENT DATA SHEET FOR ANALYZERS (UNIT 71) |  |  | PR | [7 empty] | DSH | 2019-10-07 |  |  | 2020-04-09 |  |  |  | InProgress | 35%
1204-72-PR-DSH-131 |  | PROCESS INSTRUMENT DATA SHEET FOR CONTROL VALVES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-07 |  |  | 2020-04-08 |  |  |  | InProgress | 5%
1204-72-PR-DSH-132 |  | PROCESS INSTRUMENT DATA SHEET FOR ON / OFF VALVES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-07 |  |  | 2020-04-08 |  |  |  | InProgress | 5%
1204-72-PR-DSH-133 |  | PROCESS INSTRUMENT DATA SHEET FOR SAFETY VALVES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-07 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-134 |  | PROCESS INSTRUMENT DATA SHEET FOR BREATHER VALVES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 5%
1204-72-PR-DSH-135 |  | PROCESS INSTRUMENT DATA SHEET FOR ORIFICE PLATE AND FLANGES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 5%
1204-72-PR-DSH-136 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL GAUGES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-137 |  | PROCESS INSTRUMENT DATA SHEET FOR LEVEL TRANSMITTERS (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-138 |  | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE GAUGES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-139 |  | PROCESS INSTRUMENT DATA SHEET FOR PRESSURE TRANSMITTERS (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-140 |  | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE GAUGES (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 35%
1204-72-PR-DSH-141 |  | PROCESS INSTRUMENT DATA SHEET FOR TEMPERATURE TRANSMITTERS (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | InProgress | 5%
1204-72-PR-DSH-142 |  | PROCESS INSTRUMENT DATA SHEET FOR ANALYZERS (UNIT 72) |  |  | PR | [7 empty] | DSH | 2019-10-01 |  |  | 2020-04-08 |  |  |  | notIssue | 0%
1204-06-PR-LST-005 |  | CATALYST AND CHEMICAL LIST FOR UTILITY UNIT |  |  | PR | [7 empty] | LIST | 2021-05-01 |  |  | 2021-07-30 |  |  |  | InProgress | 90%
1204-22-PR-MNL-001 |  | OPERATING MANUAL FOR MACHINERY COOLING WATER SYSTEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-61-PR-MNL-001 |  | OPERATING MANUAL FOR NITROGEN (ASU) SYETEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-62-PR-MNL-001 |  | OPERATING MANUAL FOR INSTRUMENT AIR / PLANT AIR SYSTEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-63-PR-MNL-001 |  | OPERATING MANUAL FOR COOLING WATER SYSTEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-64-PR-MNL-001 |  | OPERATING MANUAL FOR WATER POLISHING SYSTEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-65-PR-MNL-001 |  | OPERATING MANUAL FOR FUEL GAS SYSTEM |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-71-PR-MNL-001 |  | OPERATING MANUAL FOR DAILY METHANOL STORAGE TANKS |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-72-PR-MNL-001 |  | OPERATING MANUAL FOR CRUDE METHANOL STORAGE TANK |  |  | PR | [7 empty] | SPEC | 2020-06-01 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-10-PR-PID-114 |  | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- AUTOTHERMAL REFORMER |  |  | PR | [7 empty] | EDW | 2020-06-01 |  |  | 2020-06-01 |  |  |  | InProgress | 80%
1204-10-PR-PID-115 |  | PIPING & INSTRUMENTATION DIAGRAM UNIT 100- 2nd BOILER & STEAM DRUM |  |  | PR | [7 empty] | EDW | 2020-06-01 |  |  | 2020-06-01 |  |  |  | InProgress | 80%
1204-66-PR-PID-601 |  | PIPING & INSTRUMENTATION DIAGRAM FOR DIESEL SYSTEM |  |  | PR | [7 empty] | EDW | 2020-06-15 |  |  | 2020-06-15 |  |  |  | notIssue | 0%
1204-40-PR-PID-407 |  | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- SYNGAS COMPRESSOR TURBINE SURFACE CONDENSER |  |  | PR | [7 empty] | EDW | 2020-07-15 |  |  | 2020-07-15 |  |  |  | InProgress | 80%
1204-40-PR-PID-408 |  | PIPING & INSTRUMENTATION DIAGRAM UNIT 400- BFW PUMPS TURBINE SURFACE CONDENSER |  |  | PR | [7 empty] | EDW | 2020-07-15 |  |  | 2020-07-15 |  |  |  | InProgress | 80%
1204-10-PR-DSH-125 |  | DATA SHEET FOR SATURATOR PURGE COOLER (E-1012) |  |  | PR | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-66-PR-UFD-601 |  | UTILITY FLOW DIAGRAM FOR DIESEL SYSTEM |  |  | PR | [7 empty] | EDW | 2020-05-01 |  |  | 2020-05-01 |  |  |  | notIssue | 0%
1204-00-PR-LST-013 |  | OVERALL UTILITY SUMMARY |  |  | PR | [7 empty] | LIST | 2020-03-31 |  |  | 2020-05-06 |  |  |  | notIssue | 0%
1204-00-PR-LST-014 |  | ALARM SET POINT LIST FOR PROCESS UNIT |  |  | PR | [7 empty] | LIST | 2020-04-09 |  |  | 2020-05-20 |  |  |  | InProgress | 90%
1204-00-PR-LST-015 |  | CATALYST AND CHEMICAL LIST FOR PROCESS UNIT |  |  | PR | [7 empty] | LIST | 2020-03-26 |  |  | 2020-05-06 |  |  |  | InProgress | 90%
1204-00-PR-DIG-010 |  | CAUSE AND EFFECT DIAGRAM FOR PROCESS UNIT |  |  | PR | [7 empty] | LIST | 2020-03-23 |  |  | 2020-04-29 |  |  |  | InProgress | 90%
1204-00-PR-MNL-001 |  | OPERATING & SAFETY MANUAL |  |  | PR | [7 empty] | SPEC | 2020-05-21 |  |  | 2020-10-07 |  |  |  | notIssue | 0%
1204-00-PR-MNL-002 |  | LABORATORY MANUAL |  |  | PR | [7 empty] | SPEC | 2020-04-21 |  |  | 2021-09-01 |  |  |  | notIssue | 0%
1204-64-PR-TBA-101 |  | TECHNICAL BID ANALYSIS FOR MIXED BED POLISHER UNIT (PU-6401) |  |  | PR | [7 empty] | TBA | 2020-06-16 |  |  | 2020-07-16 |  |  |  | notIssue | 0%
/1204-64-PR-ACT-101VD |  | VENDOR DOCUMENT CHECKING FOR MIXED BED POLISHER UNIT (PU-6401) |  |  | PR | [7 empty] | VDR | 2020-09-14 |  |  | 2021-06-10 |  |  |  | notIssue | 0%
1204-00-PR-REQ-102 |  | REQUISITION FOR CATALYST |  |  | PR | [7 empty] | REQ | 2021-02-02 |  |  | 2021-02-15 |  |  |  | notIssue | 0%
1204-00-PR-TBA-102 |  | TECHNICAL BID ANALYSIS FOR CATALYST |  |  | PR | [7 empty] | TBA | 2021-03-23 |  |  | 2021-03-29 |  |  |  | notIssue | 0%
/1204-00-PR-ACT-102VD |  | VENDOR DOCUMENT CHECKING FOR CATALYST |  |  | PR | [7 empty] | VDR | 2021-05-27 |  |  | 2021-11-03 |  |  |  | notIssue | 0%
1204-00-PR-REQ-103 |  | REQUISITION FOR LABORATORY EQUIPMENTS |  |  | PR | [7 empty] | REQ | 2021-02-02 |  |  | 2021-02-15 |  |  |  | notIssue | 0%
1204-00-PR-TBA-103 |  | TECHNICAL BID ANALYSIS FOR LABORATORY EQUIPMENTS |  |  | PR | [7 empty] | TBA | 2021-03-23 |  |  | 2021-04-05 |  |  |  | notIssue | 0%
/1204-00-PR-ACT-103VD |  | VENDOR DOCUMENT CHECKING FOR LABORATORY EQUIPMENTS |  |  | PR | [7 empty] | VDR | 2021-05-21 |  |  | 2021-09-17 |  |  |  | notIssue | 0%
/1204-61-PR-ACT-104VD |  | VENDOR DOCUMENT CHECKING FOR AIR SEPARATION UNIT (ASU) (PU-6101) |  |  | PR | [7 empty] | VDR | 2019-12-05 |  |  | 2022-01-31 |  |  |  | InProgress | 74%
/1204-20-PR-ACT-105VD |  | VENDOR DOCUMENT CHECKING FOR HYDROGEN RECOVERY UNIT (HRU) (PU-2001) |  |  | PR | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PR-REQ-106 |  | REQUISITION FOR CHEMICALS |  |  | PR | [7 empty] | REQ | 2021-06-09 |  |  | 2021-06-15 |  |  |  | notIssue | 0%
1204-00-PR-TBA-106 |  | TECHNICAL BID ANALYSIS FOR CHEMICALS |  |  | PR | [7 empty] | TBA | 2021-07-21 |  |  | 2021-07-22 |  |  |  | notIssue | 0%
/1204-00-PR-ACT-106VD |  | VENDOR DOCUMENT CHECKING FOR CHEMICALS |  |  | PR | [7 empty] | VDR | 2021-08-10 |  |  | 2021-10-27 |  |  |  | notIssue | 0%
1204-00-PR-REQ-107 |  | REQUISITION FOR CERAMIC BALLS |  |  | PR | [7 empty] | REQ | 2020-11-11 |  |  | 2020-11-24 |  |  |  | notIssue | 0%
1204-00-PR-TBA-107 |  | TECHNICAL BID ANALYSIS FOR CERAMIC BALLS |  |  | PR | [7 empty] | TBA | 2021-01-27 |  |  | 2021-02-16 |  |  |  | notIssue | 0%
/1204-00-PR-ACT-107VD |  | VENDOR DOCUMENT CHECKING FOR CERAMIC BALLS |  |  | PR | [7 empty] | VDR | 2021-05-19 |  |  | 2021-09-29 |  |  |  | notIssue | 0%
/1204-63-PR-ACT-108VD |  | VENDOR DOCUMENT CHECKING FOR COOLING TOWER |  |  | PR | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-83-HS-LST-004 |  | UTILITY CONSUMPTION LIST FOR FLARE SYSTEM |  |  | HSE | [7 empty] | LIST | 2020-07-15 |  |  | 2020-07-15 |  |  |  | notIssue | 0%
1204-84-HS-DSH-001 |  | DATA SHEET FOR OILY WATER DIVERTER |  |  | HSE | [7 empty] | DSH | 2019-10-12 |  |  | 2020-10-10 |  |  |  | notIssue | 0%
1204-84-HS-DSH-004 |  | DATA SHEET FOR CHEMICAL/LABORATORY EFFLUENT PUMP P-8404 |  |  | HSE | [7 empty] | DSH | 2019-10-12 |  |  | 2020-10-10 |  |  |  | notIssue | 0%
1204-00-HS-DSH-007 |  | DATA SHEET FOR COMPRESSORS FOAM SYSTEM |  |  | HSE | [7 empty] | DSH | 2019-10-12 |  |  | 2020-10-10 |  |  |  | notIssue | 0%
1204-00-HS-DSH-015 |  | DATA SHEET FOR PORTABLE WATER EXTINGUISHER |  |  | HSE | [7 empty] | DSH | 2019-10-12 |  |  | 2020-10-10 |  |  |  | notIssue | 0%
1204-00-HS-SCH-002 |  | FIRE PROOFING SCHEDULE FOR UTILITY OFFSITE UNITS |  |  | HSE | [7 empty] | LIST | 2020-07-30 |  |  | 2020-07-30 |  |  |  | notIssue | 0%
1204-00-HS-DIG-002 |  | CAUSE AND EFFECT DIAGRAMS FOR UTILITY OFFSITE UNITS |  |  | HSE | [7 empty] | LIST | 2019-10-01 |  |  | 2020-08-01 |  |  |  | notIssue | 0%
1204-90-HS-DIG-001 |  | CAUSE AND EFFECT DIAGRAMS FOR BUILDINGS |  |  | HSE | [7 empty] | LIST | 2019-10-01 |  |  | 2020-08-01 |  |  |  | notIssue | 0%
1204-83-HS-DIG-001 |  | CAUSE AND EFFECT DIAGRAMS FOR FLARE UNIT |  |  | HSE | [7 empty] | LIST | 2019-10-01 |  |  | 2020-08-01 |  |  |  | notIssue | 0%
1204-82-HS-MNL-001 |  | OPERATING MANUAL FOR FIRE WATER SYSTEM |  |  | HSE | [7 empty] | SPEC | 2020-01-27 |  |  | 2021-05-27 |  |  |  | notIssue | 0%
1204-83-HS-MNL-001 |  | OPERATING MANUAL FOR FLARE SYSTEM |  |  | HSE | [7 empty] | SPEC | 2020-01-27 |  |  | 2021-05-27 |  |  |  | notIssue | 0%
1204-00-HS-MNL-001 |  | GENERAL SAFETY MANUAL |  |  | HSE | [7 empty] | SPEC | 2021-05-27 |  |  | 2021-05-27 |  |  |  | notIssue | 0%
1204-00-HS-MNL-002 |  | SAFETY MATERIAL HANDLING MANUAL |  |  | HSE | [7 empty] | SPEC | 2021-05-27 |  |  | 2021-05-27 |  |  |  | notIssue | 0%
1204-83-HS-BOD-001 |  | BASIS OF DESIGN FOR FLARE SYSTEM |  |  | HSE | [7 empty] | EDW | 2019-10-01 |  |  | 2020-06-01 |  |  |  | notIssue | 0%
1204-00-HS-TBA-151 |  | TECHNICAL BID ANALYSIS FOR SPRAY NOZZLE |  |  | HSE | [7 empty] | TBA | 2021-02-16 |  |  | 2021-02-22 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-151VD |  | VENDOR DOCUMENT CHECKING (Spray Nozzle) |  |  | HSE | [7 empty] | VDR | 2021-03-31 |  |  | 2021-06-04 |  |  |  | notIssue | 0%
1204-00-HS-TBA-152 |  | TECHNICAL BID ANALYSIS FOR FIRE EXTINGUISHERS |  |  | HSE | [7 empty] | TBA | 2020-10-16 |  |  | 2020-11-05 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-152VD |  | VENDOR DOCUMENT CHECKING (Fire Extinguishers) |  |  | HSE | [7 empty] | VDR | 2021-01-29 |  |  | 2021-07-21 |  |  |  | notIssue | 0%
1204-00-HS-TBA-153 |  | TECHNICAL BID ANALYSIS FOR AUTOMATIC CO2/CLEAN AGENT SYSTEM |  |  | HSE | [7 empty] | TBA | 2020-10-26 |  |  | 2020-11-13 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-153VD |  | VENDOR DOCUMENT CHECKING (Automatic CO2/Clean agent syst) |  |  | HSE | [7 empty] | VDR | 2021-01-11 |  |  | 2021-06-03 |  |  |  | notIssue | 0%
1204-00-HS-TBA-154 |  | TECHNICAL BID ANALYSIS FOR FOR FIRE AND GAS ALARM DEVICES |  |  | HSE | [7 empty] | TBA | 2020-09-22 |  |  | 2020-10-12 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-154VD |  | VENDOR DOCUMENT CHECKING FOR FIRE AND GAS ALARM DEVICES |  |  | HSE | [7 empty] | VDR | 2021-01-05 |  |  | 2021-06-15 |  |  |  | notIssue | 0%
1204-00-HS-TBA-155 |  | TECHNICAL BID ANALYSIS FOR FIRE FIGHTING EQUIPMENT |  |  | HSE | [7 empty] | TBA | 2020-11-17 |  |  | 2020-12-07 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-155VD |  | VENDOR DOCUMENT CHECKING (FIRE FIGHTING EQUIPMENT) |  |  | HSE | [7 empty] | VDR | 2021-01-12 |  |  | 2021-06-08 |  |  |  | notIssue | 0%
1204-00-HS-REQ-156 |  | REQUISITION FOR FOAM SYSTEM |  |  | HSE | [7 empty] | REQ | 2020-07-28 |  |  | 2020-08-10 |  |  |  | notIssue | 0%
1204-00-HS-TBA-156 |  | TECHNICAL BID ANALYSIS FOR FOAM SYSTEM |  |  | HSE | [7 empty] | TBA | 2020-10-13 |  |  | 2020-11-02 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-156VD |  | VENDOR DOCUMENT CHECKING (Foam System) |  |  | HSE | [7 empty] | VDR | 2021-01-26 |  |  | 2021-05-28 |  |  |  | notIssue | 0%
1204-00-HS-TBA-157 |  | TECHNICAL BID ANALYSIS FOR DELUGE VALVES |  |  | HSE | [7 empty] | TBA | 2020-02-11 |  |  | 2020-03-02 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-157VD |  | VENDOR DOCUMENT CHECKING (Deluge Valves) |  |  | HSE | [7 empty] | VDR | 2020-05-26 |  |  | 2020-10-29 |  |  |  | notIssue | 0%
1204-00-HS-TBA-158 |  | TECHNICAL BID ANALYSIS FOR SAFETY SHOWER AND EYE WASH |  |  | HSE | [7 empty] | TBA | 2021-02-05 |  |  | 2021-02-11 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-158VD |  | VENDOR DOCUMENT CHECKING (Safety Shower and Eye Wash) |  |  | HSE | [7 empty] | VDR | 2021-03-12 |  |  | 2021-05-21 |  |  |  | notIssue | 0%
1204-00-HS-REQ-159 |  | REQUISITION FOR SAFETY SIGNS |  |  | HSE | [7 empty] | REQ | 2020-07-21 |  |  | 2020-08-03 |  |  |  | notIssue | 0%
1204-00-HS-TBA-159 |  | TECHNICAL BID ANALYSIS FOR SAFETY SIGNS |  |  | HSE | [7 empty] | TBA | 2020-10-06 |  |  | 2020-10-26 |  |  |  | notIssue | 0%
/1204-00-HS-ACT-159VD |  | VENDOR DOCUMENT CHECKING (Safety Signs) |  |  | HSE | [7 empty] | VDR | 2021-01-19 |  |  | 2021-06-08 |  |  |  | notIssue | 0%
1204-00-PI-SDG-404A |  | STANDARD DRAWING FOR SPECIAL PIPING SUPPORT |  |  | PI | [7 empty] | SPEC | 2020-05-01 |  |  | 2020-05-01 |  |  |  | notIssue | 0%
1204-00-PI-ISO-1000 |  | A/G ISOMETRIC DRAWING OF AREA-10 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-20-PI-ISO-2500 |  | A/G ISOMETRIC DRAWING OF AREA-25 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-00-PI-ISO-4100 |  | A/G ISOMETRIC DRAWING OF AREA-41 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-10-PI-ISO-4300 |  | A/G ISOMETRIC DRAWING OF AREA-43 |  |  | PI | [7 empty] | CDW | 2019-11-27 |  |  | 2020-06-16 |  |  |  | notIssue | 0%
1204-10-PI-ISO-4800 |  | A/G ISOMETRIC DRAWING OF AREA-48 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-ISO-4900 |  | A/G ISOMETRIC DRAWING OF AREA-49 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-ISO-5000 |  | A/G ISOMETRIC DRAWING OF AREA-50 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-00-PI-LST-1000 |  | A/G ISOMETRIC LIST OF AREA-10 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-20-PI-LST-2500 |  | A/G ISOMETRIC LIST OF AREA-25 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-00-PI-LST-4100 |  | A/G ISOMETRIC LIST OF AREA-41 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-10-PI-LST-4300 |  | A/G ISOMETRIC LIST OF AREA-43 |  |  | PI | [7 empty] | CDW | 2019-11-27 |  |  | 2020-06-16 |  |  |  | notIssue | 0%
1204-10-PI-LST-4800 |  | A/G ISOMETRIC LIST OF AREA-48 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-LST-4900 |  | A/G ISOMETRIC LIST OF AREA-49 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-LST-5000 |  | A/G ISOMETRIC LIST OF AREA-50 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-00-PI-APL-1000 |  | PIPING PLAN AREA-10 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-06-11 |  |  |  | InProgress | 5%
1204-20-PI-APL-2500 |  | PIPING PLAN AREA-25 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | InProgress | 5%
1204-00-PI-APL-4100 |  | PIPING PLAN AREA-41 |  |  | PI | [7 empty] | CDW | 2019-11-13 |  |  | 2020-06-11 |  |  |  | notIssue | 0%
1204-10-PI-APL-4300 |  | PIPING PLAN AREA-43 |  |  | PI | [7 empty] | CDW | 2019-11-27 |  |  | 2020-06-16 |  |  |  | notIssue | 0%
1204-10-PI-APL-4800 |  | PIPING PLAN AREA-48 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-APL-4900 |  | PIPING PLAN AREA-49 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-10-PI-APL-5000 |  | PIPING PLAN AREA-50 |  |  | PI | [7 empty] | CDW | 2019-10-02 |  |  | 2020-07-03 |  |  |  | notIssue | 0%
1204-00-PI-MTO-406A |  | MATERIAL TAKE OFF FOR STEAM TRAP (MTO I) |  |  | PI | [7 empty] | LIST | 2020-03-01 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-00-PI-MTO-408A |  | MATERIAL TAKE OFF FOR INSULATION MATERIAL (MAY BREAK INTO SEVERAL MATERIAL TAKE OFF SUCH AS CELLULAR GLASS, MINERAL WOOL, ETC.) (MTO I) |  |  | PI | [7 empty] | LIST | 2020-03-01 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-00-PI-MTO-412A |  | MATERIAL TAKE OFF FOR SPRING (MTO I) |  |  | PI | [7 empty] | LIST | 2020-05-01 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
1204-00-PI-MTO-413A |  | MATERIAL TAKE OFF FOR EXPANSION JOINT(METAL AND RUBBER) (MTO I) |  |  | PI | [7 empty] | LIST | 2020-06-15 |  |  | 2020-07-01 |  |  |  | notIssue | 0%
1204-00-PI-MTO-414A |  | MATERIAL TAKE OFF FOR METAL JACKET (INSULATION COVER) (MTO I) |  |  | PI | [7 empty] | LIST | 2020-05-01 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
1204-00-PI-MTO-401B |  | MATERIAL TAKE OFF FOR A/G PIPES & FITTINGS (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-402B |  | MATERIAL TAKE OFF FOR A/G FLANGES (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-403B |  | MATERIAL TAKE OFF FOR A/G GASKETS (MTO II) |  |  | PI | [7 empty] | LIST | 2020-07-04 |  |  | 2020-08-10 |  |  |  | notIssue | 0%
1204-00-PI-MTO-404B |  | MATERIAL TAKE OFF FOR A/G VALVES (MTO II) |  |  | PI | [7 empty] | LIST | 2020-05-01 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
1204-00-PI-MTO-405B |  | MATERIAL TAKE OFF FOR BOLTS & NUTS (MTO II) |  |  | PI | [7 empty] | LIST | 2020-04-01 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-406B |  | MATERIAL TAKE OFF FOR STEAM TRAP (MTO II) |  |  | PI | [7 empty] | LIST | 2020-06-15 |  |  | 2020-07-05 |  |  |  | notIssue | 0%
1204-00-PI-MTO-407B |  | MATERIAL TAKE OFF FOR STRAINER (MTO II) |  |  | PI | [7 empty] | LIST | 2020-08-01 |  |  | 2020-08-10 |  |  |  | notIssue | 0%
1204-00-PI-MTO-408B |  | MATERIAL TAKE OFF FOR INSULATION MATERIAL (MTO II) |  |  | PI | [7 empty] | LIST | 2020-10-01 |  |  | 2020-10-26 |  |  |  | notIssue | 0%
1204-00-PI-MTO-409B |  | MATERIAL TAKE OFF FOR PAINT (MTO II) |  |  | PI | [7 empty] | LIST | 2020-04-01 |  |  | 2020-04-16 |  |  |  | notIssue | 0%
1204-00-PI-MTO-410B |  | MATERIAL TAKE OFF FOR C.S ELECTRODE & WELDING ROD (MTO II) |  |  | PI | [7 empty] | LIST | 2020-05-01 |  |  | 2020-05-29 |  |  |  | notIssue | 0%
1204-00-PI-MTO-411B |  | MATERIAL TAKE OFF FOR HOSE & HOSE COUPLING (MTO II) |  |  | PI | [7 empty] | LIST | 2020-11-15 |  |  | 2020-12-01 |  |  |  | notIssue | 0%
1204-00-PI-MTO-412B |  | MATERIAL TAKE OFF FOR SPRING (MTO II) |  |  | PI | [7 empty] | LIST | 2020-09-01 |  |  | 2020-09-14 |  |  |  | notIssue | 0%
1204-00-PI-MTO-413B |  | MATERIAL TAKE OFF FOR EXPANSION JOINT( MAY BREAK INTO METAL AND RUBBER) (MTO II) |  |  | PI | [7 empty] | LIST | 2020-10-01 |  |  | 2020-10-26 |  |  |  | notIssue | 0%
1204-00-PI-MTO-414B |  | MATERIAL TAKE OFF FOR METAL JACKET (INSULATION COVER) (MTO II) |  |  | PI | [7 empty] | LIST | 2020-10-01 |  |  | 2020-10-26 |  |  |  | notIssue | 0%
1204-00-PI-MTO-415B |  | MATERIAL TAKE OFF FOR SAMPLE COOLER (MTO II) |  |  | PI | [7 empty] | LIST | 2020-11-15 |  |  | 2020-12-01 |  |  |  | notIssue | 0%
1204-00-PI-MTO-416B |  | MATERIAL TAKE OFF FOR A.S & S.S ELECTRODE & WELDING ROD (MTO II) |  |  | PI | [7 empty] | LIST | 2020-05-01 |  |  | 2020-05-29 |  |  |  | notIssue | 0%
1204-00-PI-MTO-460B |  | MATERIAL TAKE OFF FOR COATING AND WRAPPING (MTO II) |  |  | PI | [7 empty] | LIST | 2020-02-15 |  |  | 2020-03-06 |  |  |  | notIssue | 0%
1204-00-PI-MTO-461B |  | MATERIAL TAKE OFF FOR U/G PIPES & FITTINGS (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-462B |  | MATERIAL TAKE OFF FOR U/G FLANGES (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-463B |  | MATERIAL TAKE OFF FOR U/G GASKETS (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-464B |  | MATERIAL TAKE OFF FOR U/G VALVES (MTO II) |  |  | PI | [7 empty] | LIST | 2020-03-06 |  |  | 2020-04-15 |  |  |  | notIssue | 0%
1204-00-PI-MTO-401C |  | MATERIAL TAKE OFF FOR PIPES & FITTINGS (MTO III) |  |  | PI | [7 empty] | LIST | 2021-04-01 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-00-PI-MTO-402C |  | MATERIAL TAKE OFF FOR FLANGES (MTO III) |  |  | PI | [7 empty] | LIST | 2021-04-01 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-00-PI-MTO-403C |  | MATERIAL TAKE OFF FOR GASKETS (MTO III) |  |  | PI | [7 empty] | LIST | 2021-04-01 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-00-PI-MTO-404C |  | MATERIAL TAKE OFF FOR VALVES (MTO III) |  |  | PI | [7 empty] | LIST | 2021-04-01 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-62-PI-UPL-7500 |  | UNDER GROUND PIPING PLAN AREA-75 |  |  | PI | [7 empty] | CDW | 2019-10-01 |  |  | 2020-06-08 |  |  |  | InProgress | 5%
1204-62-PI-UPL-7700 |  | UNDER GROUND PIPING PLAN AREA-77 |  |  | PI | [7 empty] | CDW | 2019-10-01 |  |  | 2020-06-08 |  |  |  | InProgress | 5%
1204-00-PI-UPL-7900 |  | UNDER GROUND PIPING PLAN AREA-79 |  |  | PI | [7 empty] | CDW | 2019-10-01 |  |  | 2020-06-08 |  |  |  | notIssue | 0%
1204-00-PI-UPL-8100 |  | PAVING PLAN FOR ASU UNIT |  |  | PI | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-62-PI-ISO-7500 |  | U/G ISOMETRIC DRAWING OF AREA-75 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-ISO-7600 |  | U/G ISOMETRIC DRAWING OF AREA-76 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-62-PI-ISO-7700 |  | U/G ISOMETRIC DRAWING OF AREA-77 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-ISO-7800 |  | U/G ISOMETRIC DRAWING OF AREA-78 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-ISO-7900 |  | U/G ISOMETRIC DRAWING OF AREA-79 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-62-PI-LST-7500 |  | U/G ISOMETRIC LIST OF AREA-75 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-LST-7600 |  | U/G ISOMETRIC LIST OF AREA-76 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-62-PI-LST-7700 |  | U/G ISOMETRIC LIST OF AREA-77 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-LST-7800 |  | U/G ISOMETRIC LIST OF AREA-78 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-00-PI-LST-7900 |  | U/G ISOMETRIC LIST OF AREA-79 |  |  | PI | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-401AVD |  | VENDOR DOCUMENT CHECKING FOR A/G PIPES & FITTINGS(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-TBA-401B |  | TECHNICAL BID ANALYSIS FOR A/G PIPES & FITTINGS(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-13 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-401BVD |  | VENDOR DOCUMENT CHECKING FOR A/G PIPES & FITTINGS(MTO II) |  |  | PI | [7 empty] | VDR | 2020-07-08 |  |  | 2020-01-26 |  |  |  | notIssue | 0%
1204-00-PI-REQ-401C |  | REQUISITION FOR PIPES & FITTINGS(MTO III) |  |  | PI | [7 empty] | REQ | 2020-08-10 |  |  | 2020-08-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-401C |  | TECHNICAL BID ANALYSIS FOR PIPES & FITTINGS(MTO III) |  |  | PI | [7 empty] | TBA | 2020-10-05 |  |  | 2020-10-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-401CVD |  | VENDOR DOCUMENT CHECKING FOR PIPES & FITTINGS(MTO III) |  |  | PI | [7 empty] | VDR | 2020-11-23 |  |  | 2021-04-29 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-402AVD |  | VENDOR DOCUMENT CHECKING FOR A/G FLANGES(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-TBA-402B |  | TECHNICAL BID ANALYSIS FOR A/G FLANGES(MTO II) |  |  | PI | [7 empty] | TBA | 2020-06-04 |  |  | 2020-06-10 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-402BVD |  | VENDOR DOCUMENT CHECKING FOR A/G FLANGES(MTO II) |  |  | PI | [7 empty] | VDR | 2020-08-06 |  |  | 2020-01-15 |  |  |  | notIssue | 0%
1204-00-PI-REQ-402C |  | REQUISITION FOR FLANGES(MTO III) |  |  | PI | [7 empty] | REQ | 2020-08-10 |  |  | 2020-08-17 |  |  |  | notIssue | 0%
1204-00-PI-TBA-402C |  | TECHNICAL BID ANALYSIS FOR FOR FLANGES(MTO III) |  |  | PI | [7 empty] | TBA | 2020-09-21 |  |  | 2020-09-28 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-402CVD |  | VENDOR DOCUMENT CHECKING FOR FLANGES(MTO III) |  |  | PI | [7 empty] | VDR | 2020-11-03 |  |  | 2021-03-11 |  |  |  | notIssue | 0%
1204-00-PI-REQ-403A |  | REQUISITION FOR A/G GASKETS(MTO I) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | InProgress | 90%
/1204-00-PI-ACT-403AVD |  | VENDOR DOCUMENT CHECKING FOR A/G GASKETS(MTO I) |  |  | PI | [7 empty] | VDR | 2019-10-16 |  |  | 2020-01-16 |  |  |  | notIssue | 0%
1204-00-PI-TBA-403B |  | TECHNICAL BID ANALYSIS FOR A/G GASKETS(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-19 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-403BVD |  | VENDOR DOCUMENT CHECKING FOR A/G GASKETS(MTO II) |  |  | PI | [7 empty] | VDR | 2020-06-17 |  |  | 2020-09-25 |  |  |  | notIssue | 0%
1204-00-PI-REQ-403C |  | REQUISITION FOR GASKETS(MTO III) |  |  | PI | [7 empty] | REQ | 2020-08-10 |  |  | 2020-08-13 |  |  |  | notIssue | 0%
1204-00-PI-TBA-403C |  | TECHNICAL BID ANALYSIS FOR GASKETS(MTO III) |  |  | PI | [7 empty] | TBA | 2020-09-08 |  |  | 2020-09-15 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-403CVD |  | VENDOR DOCUMENT CHECKING FOR GASKETS(MTO III) |  |  | PI | [7 empty] | VDR | 2020-10-28 |  |  | 2020-12-17 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-404AVD |  | VENDOR DOCUMENT CHECKING FOR A/G VALVES(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-404AJ |  | REQUISITION FOR A/G VALVES FOR OXYGEN SERVICE(MTO I) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-TBA-404AJ |  | TECHNICAL BID ANALYSIS FOR A/G VALVES FOR OXYGEN SERVICE(MTO I) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PI-ACT-404AJVD |  | VENDOR DOCUMENT CHECKING FOR A/G VALVES FOR OXYGEN SERVICE(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-TBA-404B |  | TECHNICAL BID ANALYSIS FOR A/G VALVES(MTO II) |  |  | PI | [7 empty] | TBA | 2020-07-16 |  |  | 2020-07-29 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-404BVD |  | VENDOR DOCUMENT CHECKING FOR A/G VALVES(MTO I) |  |  | PI | [7 empty] | VDR | 2020-08-31 |  |  | 2020-04-17 |  |  |  | notIssue | 0%
1204-00-PI-REQ-404C |  | REQUISITION FOR VALVES(MTO III) |  |  | PI | [7 empty] | REQ | 2020-08-10 |  |  | 2020-08-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-404C |  | TECHNICAL BID ANALYSIS FOR VALVES(MTO III) |  |  | PI | [7 empty] | TBA | 2020-09-28 |  |  | 2020-10-12 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-404CVD |  | VENDOR DOCUMENT CHECKING FOR VALVES(MTO III) |  |  | PI | [7 empty] | VDR | 2020-11-23 |  |  | 2021-04-09 |  |  |  | notIssue | 0%
1204-00-PI-REQ-405A |  | REQUISITION FOR BOLTS & NUTS(MTO I) |  |  | PI | [7 empty] | REQ | 2019-10-01 |  |  | 2019-10-02 |  |  |  | complete | 100%
/1204-00-PI-ACT-405AVD |  | VENDOR DOCUMENT CHECKING (BOLTS & NUTS) |  |  | PI | [7 empty] | VDR | 2019-12-02 |  |  | 2020-03-09 |  |  |  | notIssue | 0%
1204-00-PI-REQ-405B |  | REQUISITION FOR BOLTS & NUTS(MTO II) |  |  | PI | [7 empty] | REQ | 2020-04-16 |  |  | 2020-04-17 |  |  |  | notIssue | 0%
1204-00-PI-TBA-405B |  | TECHNICAL BID ANALYSIS FOR BOLTS & NUTS(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-18 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-405BVD |  | VENDOR DOCUMENT CHECKING (BOLTS & NUTS) |  |  | PI | [7 empty] | VDR | 2020-06-17 |  |  | 2020-10-02 |  |  |  | notIssue | 0%
1204-00-PI-REQ-406A |  | REQUISITION FOR STEAM TRAP(MTO I) |  |  | PI | [7 empty] | REQ | 2020-04-16 |  |  | 2020-04-29 |  |  |  | notIssue | 0%
1204-00-PI-TBA-406A |  | TECHNICAL BID ANALYSIS FOR STEAM TRAP(MTO I) |  |  | PI | [7 empty] | TBA | 2020-07-02 |  |  | 2020-07-22 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-406AVD |  | VENDOR DOCUMENT CHECKING FOR STEAM TRAP(MTO I) |  |  | PI | [7 empty] | VDR | 2020-10-01 |  |  | 2021-04-09 |  |  |  | notIssue | 0%
1204-00-PI-REQ-406B |  | REQUISITION FOR STEAM TRAP(MTO II) |  |  | PI | [7 empty] | REQ | 2020-07-06 |  |  | 2020-07-17 |  |  |  | notIssue | 0%
1204-00-PI-TBA-406B |  | TECHNICAL BID ANALYSIS FOR STEAM TRAP(MTO II) |  |  | PI | [7 empty] | TBA | 2020-09-18 |  |  | 2020-10-09 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-406BVD |  | VENDOR DOCUMENT CHECKING FOR STEAM TRAP(MTO II) |  |  | PI | [7 empty] | VDR | 2020-11-20 |  |  | 2021-05-28 |  |  |  | notIssue | 0%
1204-00-PI-TBA-407A |  | TECHNICAL BID ANALYSIS FOR STRAINER(MTO I) |  |  | PI | [7 empty] | TBA | 2020-07-02 |  |  | 2020-07-22 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-407AVD |  | VENDOR DOCUMENT CHECKING FOR STRAINER(MTO I) |  |  | PI | [7 empty] | VDR | 2020-09-21 |  |  | 2020-05-17 |  |  |  | notIssue | 0%
1204-00-PI-REQ-407B |  | REQUISITION FOR STRAINER(MTO II) |  |  | PI | [7 empty] | REQ | 2020-08-10 |  |  | 2020-08-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-407B |  | TECHNICAL BID ANALYSIS FOR STRAINER(MTO II) |  |  | PI | [7 empty] | TBA | 2020-10-26 |  |  | 2020-11-16 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-407BVD |  | VENDOR DOCUMENT CHECKING FOR STRAINER(MTO II) |  |  | PI | [7 empty] | VDR | 2021-01-25 |  |  | 2021-05-21 |  |  |  | notIssue | 0%
1204-00-PI-REQ-408A |  | REQUISITION FOR INSULATION MATERIAL(MTO I) |  |  | PI | [7 empty] | REQ | 2020-04-16 |  |  | 2020-04-17 |  |  |  | notIssue | 0%
1204-00-PI-TBA-408A |  | TECHNICAL BID ANALYSIS FOR INSULATION MATERIAL(MTO I) |  |  | PI | [7 empty] | TBA | 2020-05-20 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-408AVD |  | VENDOR DOCUMENT CHECKING INSULATION MATERIAL(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-19 |  |  | 2020-09-15 |  |  |  | notIssue | 0%
1204-00-PI-REQ-408B |  | REQUISITION FOR INSULATION MATERIAL(MTO II) |  |  | PI | [7 empty] | REQ | 2020-10-26 |  |  | 2020-10-27 |  |  |  | notIssue | 0%
1204-00-PI-TBA-408B |  | TECHNICAL BID ANALYSIS FOR INSULATION MATERIAL(MTO II) |  |  | PI | [7 empty] | TBA | 2020-11-27 |  |  | 2020-12-02 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-408BVD |  | VENDOR DOCUMENT CHECKING FOR INSULATION MATERIAL(MTO II) |  |  | PI | [7 empty] | VDR | 2020-12-29 |  |  | 2021-04-05 |  |  |  | notIssue | 0%
1204-00-PI-REQ-409A |  | REQUISITION FOR PAINT(MTO I) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-409A |  | TECHNICAL BID ANALYSIS FOR PAINT(MTO I) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-409AVD |  | VENDOR DOCUMENT CHECKING FOR PAINT(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-REQ-409B |  | REQUISITION FOR PAINT(MTO II) |  |  | PI | [7 empty] | REQ | 2020-04-16 |  |  | 2020-04-22 |  |  |  | notIssue | 0%
1204-00-PI-TBA-409B |  | TECHNICAL BID ANALYSIS FOR PAINT(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-21 |  |  | 2020-05-27 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-409BVD |  | VENDOR DOCUMENT CHECKING FOR PAINT(MTO II) |  |  | PI | [7 empty] | VDR | 2020-06-15 |  |  | 2020-08-28 |  |  |  | notIssue | 0%
1204-00-PI-REQ-409M |  | REQUISITION FOR PAINT MTO (PIPES) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-409M |  | TECHNICAL BID ANALYSIS FOR PAINT MTO (PIPES) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-409MVD |  | VENDOR DOCUMENT CHECKING PAINT MTO (PIPES) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-410A |  | TECHNICAL BID ANALYSIS FOR C.S ELECTROD & WELDING ROD(MTO I) |  |  | PI | [7 empty] | TBA | 2020-03-18 |  |  | 2020-03-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-410AVD |  | VENDOR DOCUMENT CHECKING ( C.S Electrod & Welding Rod ) |  |  | PI | [7 empty] | VDR | 2020-04-10 |  |  | 2020-06-01 |  |  |  | notIssue | 0%
1204-00-PI-REQ-410B |  | REQUISITION FOR C.S ELECTRODE & WELDING ROD(MTO II) |  |  | PI | [7 empty] | REQ | 2020-05-29 |  |  | 2020-06-04 |  |  |  | notIssue | 0%
1204-00-PI-TBA-410B |  | TECHNICAL BID ANALYSIS FOR C.S ELECTROD & WELDING ROD(MTO II) |  |  | PI | [7 empty] | TBA | 2020-07-02 |  |  | 2020-07-06 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-410BVD |  | VENDOR DOCUMENT CHECKING ( C.S Electrod &Welding Rod ) |  |  | PI | [7 empty] | VDR | 2020-08-10 |  |  | 2020-10-01 |  |  |  | notIssue | 0%
1204-00-PI-TBA-411A |  | TECHNICAL BID ANALYSIS FOR HOSE & HOSE COUPLING(MTO I) |  |  | PI | [7 empty] | TBA | 2020-04-01 |  |  | 2020-04-07 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-411AVD |  | VENDOR DOCUMENT CHECKING FOR HOSE & HOSE COUPLING(MTO I) |  |  | PI | [7 empty] | VDR | 2020-05-06 |  |  | 2020-08-31 |  |  |  | notIssue | 0%
1204-00-PI-REQ-411B |  | REQUISITION FOR HOSE & HOSE COUPLING(MTO II) |  |  | PI | [7 empty] | REQ | 2020-07-09 |  |  | 2020-07-22 |  |  |  | notIssue | 0%
1204-00-PI-TBA-411B |  | TECHNICAL BID ANALYSIS FOR HOSE & HOSE COUPLING(MTO II) |  |  | PI | [7 empty] | TBA | 2020-08-27 |  |  | 2020-09-09 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-411BVD |  | VENDOR DOCUMENT CHECKING FOR HOSE & HOSE COUPLING(MTO II) |  |  | PI | [7 empty] | VDR | 2020-10-08 |  |  | 2021-02-04 |  |  |  | notIssue | 0%
1204-00-PI-REQ-412A |  | REQUISITION FOR SPRING SUPPORT(MTO I) |  |  | PI | [7 empty] | REQ | 2020-07-09 |  |  | 2020-07-22 |  |  |  | notIssue | 0%
1204-00-PI-TBA-412A |  | TECHNICAL BID ANALYSIS FOR SPRING SUPPORT(MTO I) |  |  | PI | [7 empty] | TBA | 2020-08-14 |  |  | 2020-08-21 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-412AVD |  | VENDOR DOCUMENT CHECKING FOR SPRING SUPPORT(MTO I) |  |  | PI | [7 empty] | VDR | 2020-09-07 |  |  | 2020-11-06 |  |  |  | notIssue | 0%
1204-00-PI-REQ-412B |  | REQUISITION FOR SPRING SUPPORT(MTO II) |  |  | PI | [7 empty] | REQ | 2020-12-01 |  |  | 2020-12-15 |  |  |  | notIssue | 0%
1204-00-PI-TBA-412B |  | TECHNICAL BID ANALYSIS FOR SPRING SUPPORT(MTO II) |  |  | PI | [7 empty] | TBA | 2021-01-07 |  |  | 2021-01-14 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-412BVD |  | VENDOR DOCUMENT CHECKING FOR SPRING SUPPORT(MTO I) |  |  | PI | [7 empty] | VDR | 2021-01-29 |  |  | 2021-04-06 |  |  |  | notIssue | 0%
1204-00-PI-REQ-413A |  | REQUISITION FOR EXPANSION JOINT(MTO I) |  |  | PI | [7 empty] | REQ | 2020-05-28 |  |  | 2020-05-29 |  |  |  | notIssue | 0%
1204-00-PI-TBA-413A |  | TECHNICAL BID ANALYSIS FOR EXPANSION JOINT(MTO I) |  |  | PI | [7 empty] | TBA | 2020-07-13 |  |  | 2020-07-24 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-413AVD |  | VENDOR DOCUMENT CHECKINGFOR EXPANSION JOINT(MTO I) |  |  | PI | [7 empty] | VDR | 2020-09-09 |  |  | 2021-01-15 |  |  |  | notIssue | 0%
1204-00-PI-REQ-413B |  | REQUISITION FOR EXPANSION JOINT(MTO II) |  |  | PI | [7 empty] | REQ | 2020-09-14 |  |  | 2020-09-16 |  |  |  | notIssue | 0%
1204-00-PI-TBA-413B |  | TECHNICAL BID ANALYSIS FOR EXPANSION JOINT(MTO II) |  |  | PI | [7 empty] | TBA | 2020-10-21 |  |  | 2020-10-28 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-413BVD |  | VENDOR DOCUMENT CHECKING FOR EXPANSION JOINT(MTO II) |  |  | PI | [7 empty] | VDR | 2020-11-13 |  |  | 2021-04-23 |  |  |  | notIssue | 0%
1204-00-PI-REQ-414A |  | REQUISITION FOR METAL JACKET FOR INSULATION(MTO I) |  |  | PI | [7 empty] | REQ | 2020-07-09 |  |  | 2020-07-13 |  |  |  | notIssue | 0%
1204-00-PI-TBA-414A |  | TECHNICAL BID ANALYSIS FOR METAL JACKET FOR INSULATION(MTO I) |  |  | PI | [7 empty] | TBA | 2020-08-18 |  |  | 2020-08-24 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-414AVD |  | VENDOR DOCUMENT CHECKING FOR METAL JACKET FOR INSULATION(MTO I) |  |  | PI | [7 empty] | VDR | 2020-09-10 |  |  | 2020-12-17 |  |  |  | notIssue | 0%
1204-00-PI-REQ-414B |  | REQUISITION FOR METAL JACKET FOR INSULATION(MTO II) |  |  | PI | [7 empty] | REQ | 2020-10-26 |  |  | 2020-10-28 |  |  |  | notIssue | 0%
1204-00-PI-TBA-414B |  | TECHNICAL BID ANALYSIS FOR METAL JACKET FOR INSULATION(MTO II) |  |  | PI | [7 empty] | TBA | 2020-12-03 |  |  | 2020-12-09 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-414BVD |  | VENDOR DOCUMENT CHECKING FOR METAL JACKET FOR INSULATION(MTO I) |  |  | PI | [7 empty] | VDR | 2020-12-28 |  |  | 2021-04-08 |  |  |  | notIssue | 0%
1204-00-PI-TBA-415A |  | TECHNICAL BID ANALYSIS FOR SAMPLE COOLER(MTO I) |  |  | PI | [7 empty] | TBA | 2020-06-30 |  |  | 2020-07-02 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-415AVD |  | VENDOR DOCUMENT CHECKING FOR METAL JACKET FOR INSULATION(MTO I) |  |  | PI | [7 empty] | VDR | 2020-07-13 |  |  | 2020-08-31 |  |  |  | notIssue | 0%
1204-00-PI-REQ-415B |  | REQUISITION FOR SAMPLE COOLER(MTO II) |  |  | PI | [7 empty] | REQ | 2020-10-26 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-00-PI-TBA-415B |  | TECHNICAL BID ANALYSIS FOR SAMPLE COOLER(MTO II) |  |  | PI | [7 empty] | TBA | 2020-11-25 |  |  | 2020-11-30 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-415BVD |  | VENDOR DOCUMENT CHECKING FOR SAMPLE COOLER(MTO II) |  |  | PI | [7 empty] | VDR | 2020-12-09 |  |  | 2021-01-22 |  |  |  | notIssue | 0%
1204-00-PI-TBA-416A |  | TECHNICAL BID ANALYSIS FOR A.S & S.S ELECTROD & WELDING ROD(MTO I) |  |  | PI | [7 empty] | TBA | 2020-04-01 |  |  | 2020-04-07 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-416AVD |  | VENDOR DOCUMENT CHECKING ( A.S & S.S Electrod & Welding Rod ) |  |  | PI | [7 empty] | VDR | 2020-05-06 |  |  | 2020-08-31 |  |  |  | notIssue | 0%
1204-00-PI-REQ-416B |  | REQUISITION FOR A.S & S.S ELECTRODE & WELDING ROD(MTO II) |  |  | PI | [7 empty] | REQ | 2020-07-09 |  |  | 2020-07-22 |  |  |  | notIssue | 0%
1204-00-PI-TBA-416B |  | TECHNICAL BID ANALYSIS FOR A.S & S.S ELECTROD & WELDING ROD(MTO II) |  |  | PI | [7 empty] | TBA | 2020-08-17 |  |  | 2020-09-09 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-416BVD |  | VENDOR DOCUMENT CHECKING ( A.S & S.S Electrod & Welding Rod ) |  |  | PI | [7 empty] | VDR | 2020-10-08 |  |  | 2020-02-04 |  |  |  | notIssue | 0%
1204-00-PI-TBA-417A |  | TECHNICAL BID ANALYSIS FOR PIPE FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-417AVD |  | VENDOR DOCUMENT CHECKING FOR PIPE FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-418A |  | TECHNICAL BID ANALYSIS for FITTING FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-418AVD |  | VENDOR DOCUMENT CHECKING for FITTING FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-419A |  | TECHNICAL BID ANALYSIS FOR FLANGE FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-419AVD |  | VENDOR DOCUMENT CHECKING FOR FLANG FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-420A |  | TECHNICAL BID ANALYSIS FOR GASKET FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-420AVD |  | VENDOR DOCUMENT CHECKING FOR GASKET FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-421A |  | TECHNICAL BID ANALYSIS FOR BOLT&NUT FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-421AVD |  | VENDOR DOCUMENT CHECKING FOR BOLT&NUT FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-TBA-422A |  | TECHNICAL BID ANALYSIS FOR PAINT FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-422AVD |  | VENDOR DOCUMENT CHECKING FOR PAINT FOR FLARE AND UTILITY LINE(OSBL) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PI-ACT-460AVD |  | VENDOR DOCUMENT CHECKING FOR COATING & WRAPPING(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-460B |  | REQUISITION FOR COATING & WRAPPING(MTO II) |  |  | PI | [7 empty] | REQ | 2020-03-06 |  |  | 2020-03-12 |  |  |  | notIssue | 0%
1204-00-PI-TBA-460B |  | TECHNICAL BID ANALYSIS FOR COATING & WRAPPING(MTO II) |  |  | PI | [7 empty] | TBA | 2020-04-10 |  |  | 2020-04-16 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-460BVD |  | VENDOR DOCUMENT CHECKING FOR COATING & WRAPPING(MTO II) |  |  | PI | [7 empty] | VDR | 2020-05-04 |  |  | 2020-06-18 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-461AVD |  | VENDOR DOCUMENT CHECKING FOR U/G PIPES & FITTINGS(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-461B |  | REQUISITION FOR U/G PIPES & FITTINGS(MTO II) |  |  | PI | [7 empty] | REQ | 2020-03-18 |  |  | 2020-03-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-461B |  | TECHNICAL BID ANALYSIS FOR U/G PIPES & FITTINGS(MTOII) |  |  | PI | [7 empty] | TBA | 2020-05-13 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-461BVD |  | VENDOR DOCUMENT CHECKING FOR U/G PIPES & FITTINGS(MTO II) |  |  | PI | [7 empty] | VDR | 2020-07-08 |  |  | 2020-01-26 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-462AVD |  | VENDOR DOCUMENT CHECKING FOR U/G FLANGES(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-462B |  | REQUISITION FOR U/G FLANGES(MTOII) |  |  | PI | [7 empty] | REQ | 2020-03-18 |  |  | 2020-03-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-462B |  | TECHNICAL BID ANALYSIS FOR U/G FLANGES(MTOII) |  |  | PI | [7 empty] | TBA | 2020-05-13 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-462BVD |  | VENDOR DOCUMENT CHECKING FOR U/G FLANGES(MTOII) |  |  | PI | [7 empty] | VDR | 2020-07-08 |  |  | 2020-01-26 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-463AVD |  | VENDOR DOCUMENT CHECKING FOR U/G GASKETS(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-463B |  | REQUISITION FOR U/G GASKETS(MTO II) |  |  | PI | [7 empty] | REQ | 2020-03-18 |  |  | 2020-03-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-463B |  | TECHNICAL BID ANALYSIS FOR U/G GASKETS(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-13 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-463BVD |  | VENDOR DOCUMENT CHECKING FOR U/G GASKETS(MTO II) |  |  | PI | [7 empty] | VDR | 2020-07-08 |  |  | 2020-01-26 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-464AVD |  | VENDOR DOCUMENT CHECKING FOR U/G VALVES(MTO I) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-464B |  | REQUISITION FOR U/G VALVES(MTO II) |  |  | PI | [7 empty] | REQ | 2020-03-18 |  |  | 2020-03-24 |  |  |  | notIssue | 0%
1204-00-PI-TBA-464B |  | TECHNICAL BID ANALYSIS FOR FOR U/G VALVES(MTO II) |  |  | PI | [7 empty] | TBA | 2020-05-13 |  |  | 2020-05-19 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-464BVD |  | VENDOR DOCUMENT CHECKING FOR U/G VALVES(MTO II) |  |  | PI | [7 empty] | VDR | 2020-07-08 |  |  | 2020-01-26 |  |  |  | notIssue | 0%
/1204-00-PI-ACT-465AVD |  | VENDOR DOCUMENT CHECKING ( Bolts & nuts )(U/G) |  |  | PI | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PI-REQ-466A |  | REQUISITION FOR U/G POLYPROPYLENE ITEMS(MTO I) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PI-REQ-467A |  | REQUISITION FOR U/G HDPE ITEMS(MTO I) |  |  | PI | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-HM-ESS-288 |  | ENGINEERING STANDARD SPECIFICATION FOR AIR COOLED HEAT EXCHANGERS |  |  | MD | [7 empty] | SPEC | 2020-04-30 |  |  | 2020-04-30 |  |  |  | InProgress | 80%
1204-10-PV-DSH-211 |  | MECHANICAL DATA SHEET FOR 3RD CONDENSATE SEPARATOR (D-1002) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-PV-DSH-212 |  | MECHANICAL DATA SHEET FOR SYNGAS COMPRESSOR SUCTION SEPARATOR (D-1003) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-248 |  | MECHANICAL DATA SHEET FOR BOTTOM WATER / FUSEL OIL HEATER (E-1001) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-249 |  | MECHANICAL DATA SHEET FOR WASTE GAS 2ND HEATER (E-1009) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-250 |  | MECHANICAL DATA SHEET FOR 1ST OEM I WATER HEATER (E-1005) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-251 |  | MECHANICAL DATA SHEET FOR REFORMED GAS COOLER (E-1006) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-252 |  | MECHANICAL DATA SHEET FOR SATURATOR BOTTOM HEATER (E-1011) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-253 |  | MECHANICAL DATA SHEET FOR NATURAL GAS FEED EFFLUENT HEATER (E-1004) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-HM-DSH-254 |  | MECHANICAL DATA SHEET FOR OXYGEN 2ND HEATER (E-1008) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PV-ACT-201VD |  | VENDOR DOCUMENT CHECKING (Reactor) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
/1204-00-PV-ACT-201AVD |  | VENDOR DOCUMENT CHECKINGFOR REACTORS |  |  | MD | [7 empty] | VDR | 2019-10-01 |  |  | 2020-09-15 |  |  |  | InProgress | 70.23%
/1204-00-PV-ACT-201BVD |  | VENDOR DOCUMENT CHECKING FOR AUTO THERMAL REACTOR |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
/1204-10-PV-ACT-202FVD |  | VENDOR DOCUMENT CHECKING (STEAM DRUM, STEAM GENERATOR AND STEAM SUPER HEATER PACKAGE) |  |  | MD | [7 empty] | VDR | 2020-04-14 |  |  | 2021-07-01 |  |  |  | InProgress | 88%
1204-10-PV-TBA-202D |  | TECHNICAL BID ANALYSIS FOR STEAM DRUMS OF WASTE HEAT BOILER |  |  | MD | [7 empty] | TBA | 2019-12-17 |  |  | 2020-01-06 |  |  |  | complete | 100%
/1204-10-PV-ACT-202DVD |  | VENDOR DOCUMENT CHECKING (STEAM DRUMS OF WASTE HEAT BOILER) |  |  | MD | [7 empty] | VDR | 2020-04-14 |  |  | 2021-07-01 |  |  |  | notIssue | 0%
1204-10-PV-TBA-202S |  | TECHNICAL BID ANALYSIS FOR STEAM SUPER HEATERS AND TRANSFER LINES OF WASTE HEAT BOILER |  |  | MD | [7 empty] | TBA | 2019-12-17 |  |  | 2020-01-06 |  |  |  | complete | 100%
/1204-10-PV-ACT-202SVD |  | VENDOR DOCUMENT CHECKING (STEAM SUPER HEATERS AND TRANSFER LINES OF WASTE HEAT BOILER) |  |  | MD | [7 empty] | VDR | 2020-04-14 |  |  | 2021-07-01 |  |  |  | notIssue | 0%
/1204-10-PV-ACT-202GVD |  | VENDOR DOCUMENT CHECKING FOR STEEL STRUCTURE OF WASTE HEAT BOILER |  |  | MD | [7 empty] | VDR | 2020-04-01 |  |  | 2020-12-03 |  |  |  | notIssue | 0%
/1204-00-PV-ACT-203VD |  | VENDOR DOCUMENT CHECKING FOR DEAERATOR |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-204AVD |  | VENDOR DOCUMENT CHECKING ( Pressure Vessels Group I) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-204BVD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE VESSELS (GROUP II) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PV-REQ-204C |  | REQUISITION FOR PRESSURE VESSEL (GROUP III) |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-204CVD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE VESSEL (GROUP III) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
1204-00-PV-REQ-204D |  | REQUISITION FOR PRESSURE VESSELS (GROUP IV) |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | InProgress | 90%
/1204-00-PV-ACT-204DVD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE VESSELS (GROUP IV) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
1204-00-PV-TBA-205A |  | TECHNICAL BID ANALYSIS FOR PACKING & TRAYS & INTERNALS & DEMISTERS |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-205AVD |  | VENDOR DOCUMENT CHECKING FOR PACKING & TRAYS & INTERNALS & DEMISTERS |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-205BVD |  | VENDOR DOCUMENT CHECKING FOR INTERNALS (GROUP II) |  |  | MD | [7 empty] | VDR | 2020-03-11 |  |  | 2021-10-21 |  |  |  | notIssue | 0%
1204-00-PV-REQ-206A |  | REQUISITION FOR COLUMNS (GROUP I) |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-206AVD |  | VENDOR DOCUMENT CHECKING FOR COLUMNS (GROUP I) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-206BVD |  | VENDOR DOCUMENT CHECKING FOR SPECIAL COLUMNS (GROUP II) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PV-DSH-210 |  | DATA SHEET FOR FLARE STACK |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PV-ACT-210VD |  | VENDOR DOCUMENT CHECKING FOR FLARE STACK |  |  | MD | [7 empty] | VDR | 2020-04-20 |  |  | 2021-02-23 |  |  |  | notIssue | 0%
1204-00-PV-TBA-213A |  | TECHNICAL BID ANALYSIS FOR CARBON STEEL STORAGE TANKS |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-213AVD |  | VENDOR DOCUMENT CHECKING FOR CARBON STEEL STORAGE TANKS |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
1204-00-PV-REQ-213B |  | REQUISITION FOR STAINLESS STEEL STORAGE TANKS |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
1204-00-PV-TBA-213B |  | TECHNICAL BID ANALYSIS FOR STAINLESS STEEL STORAGE TANKS |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-213BVD |  | VENDOR DOCUMENT CHECKINGFOR STAINLESS STEEL STORAGE TANKS |  |  | MD | [7 empty] | VDR | 2020-04-13 |  |  | 2021-02-18 |  |  |  | InProgress | 40%
/1204-00-PV-ACT-214AVD |  | VENDOR DOCUMENT CHECKING FOR TANK ACCESSORIES |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-214BVD |  | VENDOR DOCUMENT CHECKING FOR TANK SEALING SYSTEM |  |  | MD | [7 empty] | VDR | 2020-10-28 |  |  | 2021-03-05 |  |  |  | notIssue | 0%
/1204-00-PV-ACT-220AVD |  | VENDOR DOCUMENT CHECKING FOR SILENCERS |  |  | MD | [7 empty] | VDR | 2020-06-11 |  |  | 2020-10-21 |  |  |  | notIssue | 0%
1204-00-PV-TBA-231B |  | TECHNICAL BID ANALYSIS FOR LADDER AND PLATFORMS |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-PV-ACT-231BVD |  | VENDOR DOCUMENT CHECKING FOR LADDER AND PLATFORMS |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
1204-00-PV-REQ-231C |  | REQUISITION FOR LADDER AND PLATFORMS |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-PV-TBA-231C |  | TECHNICAL BID ANALYSIS FOR LADDER AND PLATFORMS |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-PV-ACT-231CVD |  | VENDOR DOCUMENT CHECKING FOR LADDER AND PLATFORMS |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 50%
1204-00-HM-REQ-251 |  | REQUSITION FOR PRIMARY REFORMER PACKAGE |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
1204-00-HM-TBA-251 |  | TECHNICAL BID ANALYSIS FOR PRIMARY REFORMER PACKAGE |  |  | MD | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HM-ACT-251VD |  | VENDOR DOCUMENT CHECKING FOR PRIMARY REFORMER PACKAGE |  |  | MD | [7 empty] | VDR | 2020-05-30 |  |  | 2020-05-30 |  |  |  | InProgress | 78%
/1204-10-HM-ACT-251BVD |  | VENDOR DOCUMENT CHECKING FOR STEEL WORK SUPPLY AND SHOP PREFABRICATION (FURNACE) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 85%
/1204-10-HM-ACT-251CVD |  | VENDOR DOCUMENT CHECKING FOR CONVECTION COILS FABRICATION , MODULARIZATION& FINING AND CAST PARTS SUPPLY OF CONVECTION SECTION TUBE SHEETS |  |  | MD | [7 empty] | VDR | 2020-03-05 |  |  | 2021-04-30 |  |  |  | InProgress | 18.55%
/1204-10-HM-ACT-251DVD |  | VENDOR DOCUMENT CHECKING FOR REFORMER INLET AND OUTLET LINES, COLD COLLECTOR & TRANSFER LINE INCLUDING REFRACTORYMATERIAL SUPPLY AND INSTALLATION |  |  | MD | [7 empty] | VDR | 2020-04-24 |  |  | 2020-12-30 |  |  |  | InProgress | 6%
1204-10-HM-REQ-251E |  | REQUSITION FOR EXPANSION JOINTS OF PRIMARY REFORMER PACKAGE |  |  | MD | [7 empty] | REQ | 2020-04-14 |  |  | 2020-04-28 |  |  |  | InProgress | 90%
/1204-10-HM-ACT-251EVD |  | VENDOR DOCUMENT CHECKING FOR EXPANSION JOINTS OF PRIMARY REFORMER PACKAGE INSTALLATION |  |  | MD | [7 empty] | VDR | 2020-10-27 |  |  | 2021-04-28 |  |  |  | InProgress | 10%
1204-10-HM-TBA-251R |  | TECHNICAL BID ANALYSIS FOR SUPPLY OF REFRACTORIES FOR PRIMARY REFORMER PACKAGE (INCLUDING ANCHORS AND DESIGN/LAYOUT DRAWINGS) |  |  | MD | [7 empty] | TBA | 2020-08-25 |  |  | 2020-09-14 |  |  |  | notIssue | 0%
/1204-10-HM-ACT-251RVD |  | VENDOR DOCUMENT CHECKING FOR SUPPLY OF REFRACTORIES FOR PRIMARY REFORMER PACKAGE (INCLUDING ANCHORS AND DESIGN/LAYOUT DRAWINGS) |  |  | MD | [7 empty] | VDR | 2020-12-08 |  |  | 2020-04-26 |  |  |  | notIssue | 0%
1204-00-HM-REQ-253A |  | REQUISITION FOR AIR COOLED HEAT EXCHANGER |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HM-ACT-253AVD |  | VENDOR DOCUMENT CHECKING FOR AIR COOLED HEAT EXCHANGERS |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HM-ACT-254VD |  | VENDOR DOCUMENT CHECKING FOR AUXILIARY WATER TUBE BOILER |  |  | MD | [7 empty] | VDR | 2020-05-01 |  |  | 2020-05-01 |  |  |  | InProgress | 88%
/1204-00-HM-ACT-256AVD |  | VENDOR DOCUMENT CHECKING FOR COOLING WATER SIDE STREAM FILTERS |  |  | MD | [7 empty] | VDR | 2020-04-30 |  |  | 2020-11-20 |  |  |  | notIssue | 0%
1204-00-HM-TBA-256B |  | TECHNICAL BID ANALYSIS FOR FILTERS |  |  | MD | [7 empty] | TBA | 2020-07-14 |  |  | 2020-08-03 |  |  |  | notIssue | 0%
/1204-00-HM-ACT-256BVD |  | VENDOR DOCUMENT CHECKING FOR FILTERS |  |  | MD | [7 empty] | VDR | 2020-11-10 |  |  | 2021-05-07 |  |  |  | notIssue | 0%
1204-00-HM-REQ-257A |  | REQUISITION FOR SHELL & TUBE HEAT EXCHANGERS (GROUP I) |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HM-ACT-257AVD |  | VENDOR DOCUMENT CHECKING FOR SHELL & TUBE HEAT EXCHANGERS (GROUP I) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HM-ACT-257BVD |  | VENDOR DOCUMENT CHECKING FOR SHELL & TUBE HEAT EXCHANGERS (GROUP II) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 98.6%
1204-20-HM-DSH-231 |  | MECHANICAL DATA SHEET FOR CONVERTER FEED / EFFLUENT EXCHANGER (E-2001A/B) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 5%
1204-20-HM-DSH-232 |  | MECHANICAL DATA SHEET FOR CONVERTER EFFLUENT / NG EXCHANGER (E-2002) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 5%
1204-20-HM-DSH-236 |  | MECHANICAL DATA SHEET FOR SECOND DEMIWATER HEATER (E-2006) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 5%
1204-30-HM-DSH-244 |  | MECHANICAL DATA SHEET FOR SECOND BFW PREHEATER (E-3010A/B) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 35%
1204-30-HM-DSH-245 |  | MECHANICAL DATA SHEET FOR FIRST BFW PREHEATER (E-3011) |  |  | MD | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 35%
1204-00-HM-REQ-257C |  | REQUISITION FOR SHELL & TUBE HEAT EXCHANGERS (GROUP III) |  |  | MD | [7 empty] | REQ | 2020-06-23 | [6 empty] | InProgress | 90%
/1204-00-HM-ACT-257CVD |  | VENDOR DOCUMENT CHECKING FOR SHELL & TUBE HEAT EXCHANGERS (GROUP III) |  |  | MD | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
/1204-00-HM-ACT-260VD |  | VENDOR DOCUMENT CHECKING FOR DOUBLE PIPE HEAT EXCHANGERS |  |  | MD | [7 empty] | VDR | 2020-04-22 |  |  | 2021-02-10 |  |  |  | notIssue | 0%
1204-00-HM-TBA-261A |  | TECHNICAL BID ANALYSIS FOR PLATE TYPE HEAT EXCHANGER |  |  | MD | [7 empty] | TBA | 2020-05-05 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
/1204-00-HM-ACT-261AVD |  | VENDOR DOCUMENT CHECKING FOR PLATE TYPE HEAT EXCHANGER |  |  | MD | [7 empty] | VDR | 2020-08-17 |  |  | 2021-05-21 |  |  |  | notIssue | 0%
1204-00-MC-MSS-001 |  | MATERIAL STANDARD SPECIFICATION FOR CENTRIFUGAL COMPRESSORS |  |  | MC | [7 empty] | SPEC | 2020-04-20 |  |  | 2020-04-20 |  |  |  | InProgress | 80%
1204-00-MC-MSS-011 |  | MATERIAL STANDARD SPECIFICATION FOR EJECTOR SYSTEMS |  |  | MC | [7 empty] | SPEC | 2019-10-07 |  |  | 2020-04-20 |  |  |  | notIssue | 0%
/1204-00-RE-ACT-301VD |  | VENDOR DOCUMENT CHECKING Centrifugal Compressor |  |  | MC | [7 empty] | VDR | 2020-03-31 |  |  | 2022-01-05 |  |  |  | InProgress | 51%
1204-00-RE-REQ-302 |  | REQUISITION FOR N2 CIRCULATOR COMPRESSOR |  |  | MC | [7 empty] | REQ | 2020-06-23 | [6 empty] | InProgress | 90%
/1204-00-RE-ACT-302VD |  | VENDOR DOCUMENT CHECKING FOR N2 CIRCULATOR COMPRESSOR |  |  | MC | [7 empty] | VDR | 2020-06-01 |  |  | 2021-03-19 |  |  |  | notIssue | 0%
1204-00-RE-TBA-304 |  | TECHNICAL BID ANALYSIS FOR EMERGENCY AIR COMPRESSOR |  |  | MC | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-RE-ACT-304VD |  | VENDOR DOCUMENT CHECKING FOR Emergency Air Compressor |  |  | MC | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-RE-DSH-031 |  | DATA SHEET FOR STEAM TURBINE FOR HP BOILER FEED WATER PUMPS (PT-4001 A/B) |  |  | MC | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 80%
/1204-00-RE-ACT-307AVD |  | VENDOR DOCUMENT CHECKING FOR Process Centrifugal Pumps |  |  | MC | [7 empty] | VDR | 2019-12-24 |  |  | 2021-02-18 |  |  |  | InProgress | 95%
1204-40-RE-DSH-048 |  | DATA SHEET FOR CONDENSATE PUMPS FOR AE-6301 (P-6302 A/B) |  |  | MC | [7 empty] | DSH | 2020-06-23 | [6 empty] | InProgress | 35%
/1204-00-RE-ACT-307BVD |  | VENDOR DOCUMENT CHECKING FOR Process Centrifugal Pumps |  |  | MC | [7 empty] | VDR | 2020-04-09 |  |  | 2020-06-19 |  |  |  | InProgress | 5%
1204-00-RE-REQ-327 |  | REQUISITION FOR CHEMICAL INJECTION PACKAGES |  |  | MC | [7 empty] | REQ | 2020-07-07 |  |  | 2020-07-13 |  |  |  | InProgress | 5%
1204-00-RE-TBA-327 |  | TECHNICAL BID ANALYSIS FOR CHEMICAL INJECTION PACKAGES |  |  | MC | [7 empty] | TBA | 2020-09-01 |  |  | 2020-09-21 |  |  |  | notIssue | 0%
/1204-00-RE-ACT-327VD |  | VENDOR DOCUMENT CHECKING FOR Chemical Injection Packages |  |  | MC | [7 empty] | VDR | 2020-12-08 |  |  | 2021-06-18 |  |  |  | notIssue | 0%
1204-00-RE-DSH-322 |  | DATA SHEETS FOR EMERGENCY DIESEL GENERATOR |  |  | MC | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-RE-REQ-322 |  | REQUISITION FOR EMERGENCY DIESEL GENERATOR |  |  | MC | [7 empty] | REQ | 2020-05-27 |  |  | 2020-06-09 |  |  |  | notIssue | 0%
1204-00-RE-TBA-322 |  | TECHNICAL BID ANALYSIS FOR EMERGENCY DIESEL GENERATOR |  |  | MC | [7 empty] | TBA | 2020-07-28 |  |  | 2020-08-18 |  |  |  | notIssue | 0%
/1204-00-RE-ACT-322VD |  | VENDOR DOCUMENT CHECKING FOR Emergency Diesel Generator |  |  | MC | [7 empty] | VDR | 2020-11-24 |  |  | 2021-07-07 |  |  |  | notIssue | 0%
1204-00-RE-DSH-326 |  | DATA SHEETS FOR CRANES |  |  | MC | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-RE-TBA-326 |  | TECHNICAL BID ANALYSIS FOR CRANES |  |  | MC | [7 empty] | TBA | 2020-09-22 |  |  | 2020-10-12 |  |  |  | notIssue | 0%
/1204-00-RE-ACT-326VD |  | VENDOR DOCUMENT CHECKING FOR Cranes |  |  | MC | [7 empty] | VDR | 2021-01-05 |  |  | 2021-06-15 |  |  |  | notIssue | 0%
1204-00-RE-REQ-332 |  | REQUISITION FOR LUBRICANTS |  |  | MC | [7 empty] | REQ | 2020-06-08 |  |  | 2020-06-14 |  |  |  | notIssue | 0%
1204-00-RE-TBA-332 |  | TECHNICAL BID ANALYSIS FOR LUBRICANTS |  |  | MC | [7 empty] | TBA | 2021-07-13 |  |  | 2021-07-19 |  |  |  | notIssue | 0%
/1204-00-RE-ACT-332VD |  | VENDOR DOCUMENT CHECKING FOR Lubricants |  |  | MC | [7 empty] | VDR | 2021-08-12 |  |  | 2021-10-15 |  |  |  | notIssue | 0%
1204-00-ST-MTO-782 |  | MATERIAL TAKE OFF FOR INTERCONNECTION CONCRETE CABLE TRENCH |  |  | ST | [7 empty] | LIST | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-ST-MTO-1114 |  | MATERIAL TAKE OFF FOR RETAINING WALL (EAST) |  |  | ST | [7 empty] | LIST | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-ST-DWG-173 |  | PIPE BRIDGE “ I “ / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-DWG-180 |  | PIPE BRIDGE “ II “ / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-02-17 |  |  | 2020-02-17 |  |  |  | notIssue | 0%
1204-00-ST-DWG-181 |  | PIPE BRIDGE " II " / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2020-02-17 |  |  | 2020-02-17 |  |  |  | notIssue | 0%
1204-00-ST-DWG-182 |  | PIPE BRIDGE “ II “ / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-02-17 |  |  | 2020-02-17 |  |  |  | notIssue | 0%
1204-00-ST-DWG-774 |  | OVERALL LAYOUT / SITE FINISHING |  |  | ST | [7 empty] | CDW | 2020-12-30 |  |  | 2020-12-30 |  |  |  | notIssue | 0%
1204-00-ST-DWG-775 |  | SITE PREPARATION |  |  | ST | [7 empty] | CDW | 2020-12-30 |  |  | 2020-12-30 |  |  |  | notIssue | 0%
1204-10-ST-DWG-104 |  | ACCESS PLATFORM FOR D-1001 /STEEL STRUCTURE |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-10-ST-DWG-119 |  | E-1007 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1237 |  | STRUCTURE "N" FOR ACCESS TO P-2002 A&B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1238 |  | STRUCTURE "N" FOR ACCESS TO P-2002 A&B / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1239 |  | STRUCTURE "N" FOR ACCESS TO P-2002 A&B / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1252 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1253 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / CONCRETE STRUCTURE (G.A. PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1254 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / CONCRETE STRUCTURE (R.C. DETAILS I ) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1255 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / CONCRETE STRUCTURE (R.C. DETAILS II ) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1256 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1257 |  | STRUCTURE S" FOR E-1005 & 6 , SIL-4003 & 4 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-10-ST-DWG-1258 |  | STRUCTURE "S" FOR E-1005 & 6 , SIL-4003 & 4 / STEEL STRUCTURE (STAIR) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-00-ST-DWG-217 |  | T-SUPPORTS (TP-1901 TO TP-1905 & TP-2001)/ FDN.(G.A. & R.C. DETAILS) |  |  | ST | [7 empty] | DWG | 2020-04-30 |  |  | 2020-04-30 |  |  |  | InProgress | 60%
1204-00-ST-DWG-218 |  | T-SUPPORTS (TP-1901 TO TP-1905 & TP-2001)/ STEEL PARTS |  |  | ST | [7 empty] | DWG | 2020-04-30 |  |  | 2020-04-30 |  |  |  | InProgress | 60%
1204-20-ST-DWG-228 |  | FT-2001A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-05-20 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-20-ST-MTO-230 |  | MATERIAL TAKE OFF FOR FT-2001 A/B |  |  | ST | [7 empty] | LIST | 2020-05-20 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-20-ST-DWG-232 |  | P-2001 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-05-05 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-20-ST-MTO-234 |  | MATERIAL TAKE OFF FOR P-2001 |  |  | ST | [7 empty] | LIST | 2020-05-05 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-20-ST-DWG-236 |  | P-2002 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-20-ST-MTO-238 |  | MATERIAL TAKE OFF FOR P-2002 A/B |  |  | ST | [7 empty] | LIST | 2020-03-01 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-20-ST-DWG-240 |  | P-2003 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-20-ST-MTO-242 |  | MATERIAL TAKE OFF FOR P-2003 A/B |  |  | ST | [7 empty] | LIST | 2020-03-31 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-20-ST-DWG-245 |  | C-2001 / CONCRETE STRUCTURE |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-20-ST-MTO-247 |  | MATERIAL TAKE OFF FOR C-2001 |  |  | ST | [7 empty] | LIST | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-20-ST-DWG-250 |  | C-2002 / CONCRETE STRUCTURE |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-20-ST-MTO-267 |  | MATERIAL TAKE OFF FOR E-2004 |  |  | ST | [7 empty] | LIST | 2020-09-09 |  |  | 2020-10-19 |  |  |  | notIssue | 0%
1204-20-ST-MTO-252 |  | MATERIAL TAKE OFF FOR C-2002 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-20-ST-DWG-254 |  | COMPRESSOR SHELTER (UNIT 20) / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-07-10 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
1204-20-ST-DWG-255 |  | COMPRESSOR SHELTER (UNIT 20) / STEEL STRUCTURE (PLAN) |  |  | ST | [7 empty] | CDW | 2020-07-10 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
1204-20-ST-DWG-256 |  | COMPRESSOR SHELTER (UNIT 20) / STEEL STRUCTURE (ELEVATION) |  |  | ST | [7 empty] | CDW | 2020-07-10 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
1204-20-ST-DWG-257 |  | COMPRESSOR SHELTER (UNIT 20) / STEEL STRUCTURE (DETAILS) |  |  | ST | [7 empty] | CDW | 2020-07-10 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
1204-20-ST-MTO-259 |  | MATERIAL TAKE OFF FOR COMPRESSOR SHELTER (UNIT 20) |  |  | ST | [7 empty] | LIST | 2020-07-10 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
1204-20-ST-MTO-263 |  | MATERIAL TAKE OFF FOR PU-2001(HRU) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-20-ST-DWG-1247 |  | STRUCTURE "P" FOR ACCESS TO P-2003 A&B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-20-ST-DWG-1248 |  | STRUCTURE "P" FOR ACCESS TO P-2003 A&B / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-20-ST-DWG-1249 |  | STRUCTURE "P" FOR ACCESS TO P-2003 A&B / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-30-ST-MTO-386 |  | MATERIAL TAKE OFF FOR E-3010 (MTO I) |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-30-ST-DWG-388 |  | E-3011 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-20 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-30-ST-DWG-504 |  | FT-3001 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-30-ST-DWG-508 |  | P-3001 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-10 |  |  | 2020-08-12 |  |  |  | notIssue | 0%
1204-30-ST-MTO-510 |  | MATERIAL TAKE OFF FOR P-3001 A/B |  |  | ST | [7 empty] | LIST | 2020-10-22 |  |  | 2020-12-30 |  |  |  | notIssue | 0%
1204-30-ST-DWG-512 |  | P-3002 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-10 |  |  | 2020-08-12 |  |  |  | notIssue | 0%
1204-30-ST-MTO-514 |  | MATERIAL TAKE OFF FOR P-3002 A/B |  |  | ST | [7 empty] | LIST | 2020-10-22 |  |  | 2020-12-14 |  |  |  | notIssue | 0%
1204-30-ST-DWG-516 |  | P-3003 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-17 |  |  | 2020-08-19 |  |  |  | notIssue | 0%
1204-30-ST-MTO-518 |  | MATERIAL TAKE OFF FOR P-3003 A/B |  |  | ST | [7 empty] | LIST | 2020-10-29 |  |  | 2021-01-12 |  |  |  | notIssue | 0%
1204-30-ST-DWG-520 |  | P-3004 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-17 |  |  | 2020-08-19 |  |  |  | notIssue | 0%
1204-30-ST-MTO-522 |  | MATERIAL TAKE OFF FOR P-3004 A/B |  |  | ST | [7 empty] | LIST | 2020-10-29 |  |  | 2021-01-12 |  |  |  | notIssue | 0%
1204-30-ST-DWG-524 |  | P-3005 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-08-20 |  |  | 2020-08-20 |  |  |  | notIssue | 0%
1204-30-ST-MTO-526 |  | MATERIAL TAKE OFF FOR P-3005 A/B |  |  | ST | [7 empty] | LIST | 2020-08-20 |  |  | 2020-08-20 |  |  |  | notIssue | 0%
1204-30-ST-DWG-528 |  | P-3006 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-18 |  |  | 2020-08-19 |  |  |  | notIssue | 0%
1204-30-ST-MTO-530 |  | MATERIAL TAKE OFF FOR P-3006 A/B |  |  | ST | [7 empty] | LIST | 2020-10-30 |  |  | 2021-01-12 |  |  |  | notIssue | 0%
1204-30-ST-DWG-532 |  | PU-3001 /FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-30-ST-MTO-534 |  | MATERIAL TAKE OFF FOR PU-3001 |  |  | ST | [7 empty] | LIST | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-30-ST-DWG-536 |  | SU-3001 /CONCRETE SUMP (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-30-ST-MTO-538 |  | MATERIAL TAKE OFF FOR SU-3001 |  |  | ST | [7 empty] | LIST | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-40-ST-DWG-401 |  | E-4001 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-05-01 |  |  | 2020-05-01 |  |  |  | notIssue | 0%
1204-40-ST-DWG-409 |  | E-4007 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-411 |  | MATERIAL TAKE OFF FOR E-4007 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-DWG-413 |  | E-4008 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-415 |  | MATERIAL TAKE OFF FOR E-4008 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-DWG-433 |  | P-4001 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-40-ST-MTO-435 |  | MATERIAL TAKE OFF FOR P-4001 AB |  |  | ST | [7 empty] | LIST | 2020-03-31 |  |  | 2020-05-26 |  |  |  | notIssue | 0%
1204-40-ST-DWG-437 |  | P-4002 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-06-02 |  |  |  | notIssue | 0%
1204-40-ST-MTO-439 |  | MATERIAL TAKE OFF FOR P-4002 AB |  |  | ST | [7 empty] | LIST | 2020-03-31 |  |  | 2020-06-02 |  |  |  | notIssue | 0%
1204-40-ST-DWG-441 |  | P-4001 C/ FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-443 |  | MATERIAL TAKE OFF FOR P-4001 C |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-DWG-445 |  | P-4005 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-08-20 |  |  | 2020-08-20 |  |  |  | notIssue | 0%
1204-40-ST-MTO-447 |  | MATERIAL TAKE OFF FOR P-4005 A/B |  |  | ST | [7 empty] | LIST | 2020-08-20 |  |  | 2020-08-20 |  |  |  | notIssue | 0%
1204-40-ST-MTO-453 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 A ) / PART I |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-454 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 B ) / PART I |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-457 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 A ) / PART II |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-MTO-458 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 B ) / PART II |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-40-ST-DWG-476 |  | BOILER (PU-4006 A/B ) / STEEL STRUCTURE (PLAN) |  |  | ST | [7 empty] | CDW | 2019-10-01 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-40-ST-DWG-477 |  | BOILER (PU-4006 A/B ) / STEEL STRUCTURE (ELEVATION) |  |  | ST | [7 empty] | CDW | 2019-10-01 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-40-ST-DWG-478 |  | BOILER (PU-4006 A/B ) / STEEL STRUCTURE (DETAILS) |  |  | ST | [7 empty] | CDW | 2019-10-01 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-40-ST-MTO-479 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 A ) / PART III |  |  | ST | [7 empty] | CDW | 2019-10-01 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-40-ST-MTO-480 |  | MATERIAL TAKE OFF FOR BOILER (PU-4006 B ) / PART III |  |  | ST | [7 empty] | CDW | 2019-10-01 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-40-ST-DWG-1242 |  | STRUCTURE "O" FOR ACCESS TO P-4001 A&B&C / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-40-ST-DWG-1243 |  | STRUCTURE "O" FOR ACCESS TO P-4001 A&B&C / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-40-ST-DWG-1244 |  | STRUCTURE "O" FOR ACCESS TO P-4001 A&B&C / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2021-03-10 |  |  | 2021-03-10 |  |  |  | notIssue | 0%
1204-61-ST-DWG-550 |  | ASU (AE-6187) / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-61-ST-DWG-601 |  | ASU / FDN. (PART 1) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-602 |  | ASU / FDN. (PART 2) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-603 |  | ASU / FDN. (PART 3) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-604 |  | ASU / FDN. (PART 4) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-605 |  | ASU / FDN. (PART 5) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-606 |  | ASU / FDN. (PART 6) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-607 |  | ASU / FDN. (PART 7) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-608 |  | ASU / FDN. (PART 8) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-DWG-609 |  | ASU / FDN. (PART 9) |  |  | ST | [7 empty] | CDW | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-61-ST-MTO-611 |  | MATERIAL TAKE OFF FOR ASU |  |  | ST | [7 empty] | LIST | 2020-02-15 |  |  | 2020-06-20 |  |  |  | notIssue | 0%
1204-62-ST-DWG-626 |  | V-7401 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-20 |  |  | 2020-09-20 |  |  |  | notIssue | 0%
1204-62-ST-DWG-627 |  | V-7401 A/B / CONCRETE STRUCTURE |  |  | ST | [7 empty] | CDW | 2020-09-20 |  |  | 2020-09-20 |  |  |  | notIssue | 0%
1204-62-ST-MTO-629 |  | MATERIAL TAKE OFF FOR V-7401 AB |  |  | ST | [7 empty] | LIST | 2020-09-20 |  |  | 2020-09-20 |  |  |  | notIssue | 0%
1204-62-ST-DWG-631 |  | COMPRESSOR SHELTER / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 |  |  | 2020-10-28 |  |  |  | notIssue | 0%
1204-62-ST-DWG-632 |  | COMPRESSOR SHELTER / STEEL STRUCTURE (PLAN) |  |  | ST | [7 empty] | CDW | 2020-06-23 |  |  | 2020-08-26 |  |  |  | notIssue | 0%
1204-62-ST-DWG-633 |  | COMPRESSOR SHELTER / STEEL STRUCTURE (ELEVATION) |  |  | ST | [7 empty] | CDW | 2020-06-23 |  |  | 2020-08-26 |  |  |  | notIssue | 0%
1204-62-ST-DWG-634 |  | COMPRESSOR SHELTER / STEEL STRUCTURE (DETAILS) |  |  | ST | [7 empty] | CDW | 2020-06-23 |  |  | 2020-08-26 |  |  |  | notIssue | 0%
1204-62-ST-MTO-636 |  | MATERIAL TAKE OFF FOR COMPRESSOR SHELTER |  |  | ST | [7 empty] | LIST | 2020-06-23 |  |  | 2020-08-26 |  |  |  | notIssue | 0%
1204-63-ST-DWG-651 |  | P-6301 A/B/C/D/E/F / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-06-02 |  |  |  | notIssue | 0%
1204-63-ST-MTO-654 |  | MATERIAL TAKE OFF FOR P-6301 A/B/C/D/E/F |  |  | ST | [7 empty] | LIST | 2020-03-31 |  |  | 2020-06-02 |  |  |  | notIssue | 0%
1204-22-ST-DWG-662 |  | E-2201 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-10 |  |  | 2020-09-10 |  |  |  | notIssue | 0%
1204-22-ST-MTO-668 |  | MATERIAL TAKE OFF FOR TK-2201 |  |  | ST | [7 empty] | LIST | 2020-09-09 |  |  | 2020-10-19 |  |  |  | notIssue | 0%
1204-64-ST-DWG-670 |  | P-7502 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-64-ST-MTO-719 |  | MATERIAL TAKE OFF FOR D-6401 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-72-ST-DWG-731 |  | P-7001 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-10 |  |  | 2020-09-10 |  |  |  | notIssue | 0%
1204-72-ST-MTO-733 |  | MATERIAL TAKE OFF FOR P-7001 A/B |  |  | ST | [7 empty] | LIST | 2020-09-10 |  |  | 2020-09-10 |  |  |  | notIssue | 0%
1204-72-ST-DWG-739 |  | P-7101 A/B / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-11-03 | [6 empty] | notIssue | 0%
1204-72-ST-MTO-741 |  | MATERIAL TAKE OFF FOR P-7101 A/B |  |  | ST | [7 empty] | LIST | 2020-07-22 |  |  | 2021-02-16 |  |  |  | notIssue | 0%
1204-71-ST-DWG-747 |  | P-4501 A/B/C / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-09-10 |  |  | 2020-09-10 |  |  |  | notIssue | 0%
1204-71-ST-MTO-749 |  | MATERIAL TAKE OFF FOR P-4501 A/B/C |  |  | ST | [7 empty] | LIST | 2020-09-10 |  |  | 2020-09-10 |  |  |  | notIssue | 0%
1204-71-ST-DWG-756 |  | DYKE WALL FOR TK-7101 A/B & TK-7201 / CALCULATION SHEET |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-84-ST-DWG-801 |  | V-8401 /CONCRETE SUMP (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-MTO-803 |  | MATERIAL TAKE OFF FOR V-8401 |  |  | ST | [7 empty] | LIST | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-DWG-805 |  | A-8401 /CONCRETE SUMP (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-MTO-807 |  | MATERIAL TAKE OFF FOR A-8401 |  |  | ST | [7 empty] | LIST | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-DWG-809 |  | A-8402 /CONCRETE SUMP (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-MTO-811 |  | MATERIAL TAKE OFF FOR A-8402 |  |  | ST | [7 empty] | LIST | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-DWG-812 |  | P-8402 A/B /CONCRETE SUMP (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-84-ST-MTO-814 |  | MATERIAL TAKE OFF FOR P-8402 AB |  |  | ST | [7 empty] | LIST | 2020-10-30 |  |  | 2020-10-30 |  |  |  | notIssue | 0%
1204-90-ST-DWG-955 |  | SUBSTATION / TRANSFORMER FDN. & PLAN DETAILS |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-960 |  | MATERIAL TAKE OFF FOR SUBSTATION / PLUMBING |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-DWG-965 |  | ADMINISTRATION , RESTAURANT, CLINIC & GUARD HOUSE BUILDING / FDN. (R.C. PLAN & DETAILS V ) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-DWG-977 |  | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / ROOF SLOPING PLAN & DETAILS |  |  | ST | [7 empty] | CDW | 2020-03-30 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-90-ST-DWG-978 |  | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / LINTEL , FINISHING & FALSE CEILING FOR GROUND FLOOR PLAN |  |  | ST | [7 empty] | CDW | 2020-03-30 |  |  | 2020-03-30 |  |  |  | InProgress | 30%
1204-90-ST-DWG-979 |  | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / LINTEL , FINISHING & FALSE CEILING FOR FIRST FLOOR PLAN |  |  | ST | [7 empty] | CDW | 2020-03-30 |  |  | 2020-03-30 |  |  |  | InProgress | 30%
1204-90-ST-DWG-980 |  | ADMINISTRATION , RESTAURANT & CLINIC BUILDING / LINTEL , FINISHING & FALSE CEILING FOR SECOND FLOOR PLAN |  |  | ST | [7 empty] | CDW | 2020-03-30 |  |  | 2020-03-30 |  |  |  | InProgress | 30%
1204-90-ST-DWG-1017 |  | WORK SHOP / MISCELLANEOUS DETAILS |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1025 |  | MATERIAL TAKE OFF FOR WORK SHOP / PLUMBING |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1027 |  | MATERIAL TAKE OFF FOR WORK SHOP STEEL STRUCTURE |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1028 |  | MATERIAL TAKE OFF FOR WORK SHOP / FDN. |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1045 |  | MATERIAL TAKE OFF FOR WAREHOUSE / PLUMBING |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1047 |  | MATERIAL TAKE OFF FOR WAREHOUSE STEEL STRUCTURE |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1048 |  | MATERIAL TAKE OFF FOR WAREHOUSE / FDN. |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-DWG-1051 |  | FIRE STATION. / FDN. (R.C.DETAILS) |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-DWG-1054 |  | FIRE STATION / 3D VIEWS |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-DWG-1057 |  | FIRE STATION / MISCELLANEOUS DETAILS |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-DWG-1064 |  | FIRE STATION / SLABS (R.C.DETAILS II ) |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-DWG-1065 |  | FIRE STATION / DOWELS FOR WALLS & COLUMNS |  |  | ST | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1072 |  | MATERIAL TAKE OFF FOR FIRE STATION. / PLUMBING |  |  | ST | [7 empty] | LIST | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1074 |  | MATERIAL TAKE OFF FOR FIRE STATION BEAMS & SLABS |  |  | ST | [7 empty] | LIST | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1075 |  | MATERIAL TAKE OFF FOR FIRE STATION WALLS & COLUMNS |  |  | ST | [7 empty] | LIST | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1076 |  | MATERIAL TAKE OFF FOR FIRE STATION FDN. |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-ST-MTO-1090 |  | MATERIAL TAKE OFF FOR GUARD HOUSE / FDN. |  |  | ST | [7 empty] | LIST | 2020-03-30 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1091 |  | MATERIAL TAKE OFF FOR GUARD HOUSE / STEEL STRUCTURE |  |  | ST | [7 empty] | LIST | 2020-03-30 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-90-ST-MTO-1092 |  | MATERIAL TAKE OFF FOR GUARD HOUSE / PLUMBING |  |  | ST | [7 empty] | LIST | 2020-03-30 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-00-ST-MTO-1113 |  | MATERIAL TAKE OFF FOR PIPE CULVERT |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | complete | 100%
1204-00-ST-MTO-1118 |  | MATERIAL TAKE OFF FOR RETAINING WALL (WEST) |  |  | ST | [7 empty] | LIST | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-00-ST-DWG-013 |  | PIPE RACK ZONE 1 / CONCRETE STRUCTURE ( R.C. DETAILS II ) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-015 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 1 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-022 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 2 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-028 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 3 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-034 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 4 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-DWG-038 |  | PIPE RACK ZONE 5 / CONCRETE STRUCTURE ( R.C. DETAILS II ) |  |  | ST | [7 empty] | CDW | 2020-06-03 |  |  | 2020-08-12 |  |  |  | notIssue | 0%
1204-00-ST-MTO-040 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 5 |  |  | ST | [7 empty] | LIST | 2020-06-23 |  |  | 2020-08-12 |  |  |  | notIssue | 0%
1204-00-ST-MTO-046 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 6 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-052 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 7 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-058 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 8 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-064 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 9 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-DWG-068 |  | PIPE RACK ZONE 10 / CONCRETE STRUCTURE ( R.C. DETAILS II ) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-070 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 10 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-076 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 11 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-DWG-078 |  | PIPE RACK ZONE 12 / STEEL STRUCTURE (PLAN, ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-06-07 |  |  |  | InProgress | 80%
1204-00-ST-DWG-079 |  | PIPE RACK ZONE 12 / STEEL STRUCTURE (VIEW & DETS.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-06-07 |  |  |  | notIssue | 0%
1204-00-ST-DWG-185 |  | PIPE RACK ZONE 13 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-05-31 |  |  |  | notIssue | 0%
1204-00-ST-DWG-189 |  | PIPE RACK ZONE 15 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-04-05 |  |  | 2020-04-05 |  |  |  | notIssue | 0%
1204-00-ST-DWG-190 |  | PIPE RACK ZONE 15 / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2020-04-05 |  |  | 2020-04-05 |  |  |  | notIssue | 0%
1204-00-ST-DWG-191 |  | PIPE RACK ZONE 15 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-04-05 |  |  | 2020-04-05 |  |  |  | notIssue | 0%
1204-00-ST-DWG-194 |  | PIPE RACK ZONE 16 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-DWG-195 |  | PIPE RACK ZONE 17 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-04-29 |  |  | 2020-04-29 |  |  |  | notIssue | 0%
1204-00-ST-DWG-196 |  | PIPE RACK ZONE 17 / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2020-04-29 |  |  | 2020-04-29 |  |  |  | notIssue | 0%
1204-00-ST-DWG-197 |  | PIPE RACK ZONE 17 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-04-29 |  |  | 2020-04-29 |  |  |  | notIssue | 0%
1204-00-ST-DWG-198 |  | PIPE RACK ZONE 18 / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-05-12 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-00-ST-DWG-199 |  | PIPE RACK ZONE 18 / STEEL STRUCTURE (PLAN & DETS.) |  |  | ST | [7 empty] | CDW | 2020-05-12 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-00-ST-DWG-200 |  | PIPE RACK ZONE 18 / STEEL STRUCTURE (ELEVATION & DETS.) |  |  | ST | [7 empty] | CDW | 2020-05-12 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-00-ST-MTO-082 |  | MATERIAL TAKE OFF FOR PIPE RACK ZONE 12 |  |  | ST | [7 empty] | LIST | 2020-03-31 |  |  | 2020-06-07 |  |  |  | notIssue | 0%
1204-00-ST-DWG-080 |  | PIPE RACK ZONE 12 / CONCRETE STRUCTURE ( R.C. DETAILS II ) |  |  | ST | [7 empty] | CDW | 2020-03-31 |  |  | 2020-06-07 |  |  |  | notIssue | 0%
1204-00-ST-DWG-089 |  | FLARE / FDN. (G.A. & R.C.) |  |  | ST | [7 empty] | CDW | 2020-12-29 |  |  | 2021-03-16 |  |  |  | notIssue | 0%
1204-00-ST-MTO-091 |  | MATERIAL TAKE OFF FOR FLARE |  |  | ST | [7 empty] | LIST | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-DWG-092 |  | PIPE SUPPORTS / FDN. |  |  | ST | [7 empty] | CDW | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-DWG-093 |  | PIPE SUPPORTS / STEEL STRUCTURE |  |  | ST | [7 empty] | CDW | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-MTO-095 |  | MATERIAL TAKE OFF FOR PIPE SUPPORTS |  |  | ST | [7 empty] | LIST | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-DWG-096 |  | SLEEPERS / GENERAL ARRANGEMENT & DETAILS |  |  | ST | [7 empty] | CDW | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-DWG-097 |  | SLEEPERS / DETAILS |  |  | ST | [7 empty] | CDW | 2021-03-16 |  |  | 2021-05-04 |  |  |  | notIssue | 0%
1204-00-ST-MTO-1126 |  | MATERIAL TAKE OFF FOR DV-6202 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-099 |  | MATERIAL TAKE OFF FOR SLEEPERS |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-1138 |  | MATERIAL TAKE OFF FOR VB-6203 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-1142 |  | MATERIAL TAKE OFF FOR VB-6301 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-BBS-1147 |  | BAR BENDING SCHEDULE FOR VB-6303 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-1150 |  | MATERIAL TAKE OFF FOR VB-6601 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-BBS-1155 |  | BAR BENDING SCHEDULE FOR VB-6905 |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-ST-MTO-1158 |  | MATERIAL TAKE OFF FOR ADDITIONAL CONCRETE WALLS |  |  | ST | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-ST-ACT-740AVD |  | VENDOR DOCUMENT CHECKING FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART A) |  |  | ST | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
1204-00-ST-REQ-740B |  | REQUISITION FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART B) |  |  | ST | [7 empty] | REQ | 2020-06-23 | [6 empty] | complete | 100%
1204-00-ST-TBA-740B |  | TECHNICAL BID ANALYSIS FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART B) |  |  | ST | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-ST-ACT-740BVD |  | VENDOR DOCUMENT CHECKING FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART B) |  |  | ST | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
/1204-00-ST-ACT-740CVD |  | VENDOR DOCUMENT CHECKING FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART C) |  |  | ST | [7 empty] | VDR | 2020-03-10 |  |  | 2020-10-20 |  |  |  | InProgress | 40%
1204-00-ST-TBA-740D |  | TECHNICAL BID ANALYSIS FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART D) |  |  | ST | [7 empty] | TBA | 2020-07-09 |  |  | 2020-07-13 |  |  |  | complete | 100%
/1204-00-ST-ACT-740DVD |  | VENDOR DOCUMENT CHECKING FOR FABRICATION & SUPPLY OF STEEL STRUCTURES (PART D) |  |  | ST | [7 empty] | VDR | 2020-09-08 |  |  | 2021-06-25 |  |  |  | InProgress | 10%
1204-00-ST-TBA-742 |  | TECHNICAL BID ANALYSIS FOR ANCHOR BOLTS |  |  | ST | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-ST-ACT-742VD |  | VENDOR DOCUMENT CHECKING FOR ANCHOR BOLTS |  |  | ST | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 99%
/1204-00-ST-ACT-743VD |  | VENDOR DOCUMENT CHECKING (STEEL GRATING) |  |  | ST | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 92%
1204-90-HV-DWG-031 |  | ANALYZER ROOM - DUCTING LAYOUT |  |  | HV | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DWG-032 |  | ANALYZER ROOM - SECTION OF DUCTING |  |  | HV | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DWG-033 |  | ANALYZER ROOM - DUCT SUPPORTING AND OPENING LOCATION |  |  | HV | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DID-034 |  | ANALYZER ROOM - MECHANICAL ROOM GENERAL DIAGRAM |  |  | HV | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DWG-035 |  | ANALYZER ROOM - HVAC EQUIPMENT ARRANGEMENT & REFRIGERANT PIPING PLAN |  |  | HV | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-030 |  | DATA SHEET FOR PACKAGE AIR HANDLING UNIT FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-031 |  | DATA SHEET FOR AIR CONDENSER FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-032 |  | DATA SHEET FOR FRESH AIR FAN & FILTER UNIT FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-212 |  | DATA SHEET FOR PRESSURE RELIEF DAMPER FOR LABORATORY |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-230 |  | DATA SHEET FOR MOTORIZED FIRE DAMPER FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-231 |  | DATA SHEET FOR MOTORIZED BLOCK DAMPER FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-HV-DSH-232 |  | DATA SHEET FOR PRESSURE RELIEF DAMPER FOR ANALYZER |  |  | HV | [7 empty] | DSH | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-HV-ACT-790VDR |  | VENDOR DOCUMENT CHECKING (HVAC EQUIPMENT) |  |  | HV | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-HV-ACT-791VDR |  | VENDOR DOCUMENT CHECKING (EXPLOSION PROTECTION VALVE) |  |  | HV | [7 empty] | VDR | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-HV-ACT-792VDR |  | VENDOR DOCUMENT CHECKING (DUCT ACCESSORIES) |  |  | HV | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-EL-CSH-002 |  | RELAY SETTING SCHEDULE & COORDINATION STUDIES |  |  | EL | [7 empty] | LIST | 2020-08-15 |  |  | 2020-08-15 |  |  |  | notIssue | 0%
1204-00-EL-CSH-005 |  | LIGHTING CALCULATIONS & ILLUMINATION LEVELS (SAMPLE CAL.) |  |  | EL | [7 empty] | LIST | 2020-10-10 |  |  | 2020-10-10 |  |  |  | notIssue | 0%
1204-00-EL-CSH-007 |  | LARGE DRIVE STARTING STUDIES |  |  | EL | [7 empty] | LIST | 2020-11-30 |  |  | 2020-11-30 |  |  |  | notIssue | 0%
1204-00-EL-CSH-008 |  | ELECTRICAL HEAT TRACING CALCULATION LIST |  |  | EL | [7 empty] | LIST | 2020-11-30 |  |  | 2020-11-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-032 |  | MAIN NORMAL DISTRIBUTION PANEL SINGLE LINE DIAGRAM NO.2 |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-09-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-033 |  | MAIN EMERGENCY DISTRIBUTION PANEL SINGLE LINE DIAGRAM NO.2 |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-09-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-054 |  | WAREHOUSE BACKYARD NORMAL LIGHTING PANEL SINGLE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-055 |  | WAREHOUSE BACKYARD EMERGENCY LIGHTING & RECEPTACLE PANEL SINGLE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-072 |  | AREA NORMAL LIGHTING PANEL SINGLE LINE DIAGRAM NO. 5 |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-073 |  | AREA EMERGENCY LIGHTING PANEL SINGLE LINE DIAGRAM NO.5 |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-074 |  | AREA RECEPTACLE PANEL SINGLE LINE DIAGRAM NO.5 |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-077 |  | ELECTRICAL HEAT TRACING DISTRIBUTION PANEL SINGLE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-090 |  | GUARD HOUSE NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-091 |  | GUARD HOUSE EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-092 |  | CLINIC NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-093 |  | CLINIC EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-094 |  | ADMINS. NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-095 |  | ADMINS. EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-096 |  | TRAINING NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-097 |  | TRAINING EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-04-30 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-098 |  | RESTAURANT NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-099 |  | RESTAURANT EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-100 |  | ADMINISTRATION BUILDING MAIN NORMAL DISTRIBUTION PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-101 |  | ADMINISTRATION BUILDING MAIN EMERGENCY DISTRIBUTION PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-05-30 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-083 |  | UTILITY SUBSTATION NORMAL LIGHTING PANEL ONE LINE DIAGRAM, |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-084 |  | UTILITY SUBSTATION EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-085 |  | UTILITY CONTROL ROOM NORMAL LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-EL-SLD-086 |  | UTILITY CONTROL ROOM EMERGENCY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-087 |  | UTILITY SUBSTATION SAFETY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-90-EL-SLD-088 |  | UTILITY CONTROL ROOM SAFETY LIGHTING PANEL ONE LINE DIAGRAM |  |  | EL | [7 empty] | CDW | 2019-10-01 |  |  | 2020-05-30 |  |  |  | notIssue | 0%
1204-00-EL-DIG-002 |  | TELEPHONE SYSTEM RISER DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-02-18 |  |  | 2020-04-20 |  |  |  | notIssue | 0%
1204-90-EL-DIG-004 |  | FIRE ALARM RISER DIAGRAM FOR CENTRAL CONTROL BUILDING |  |  | EL | [7 empty] | CDW | 2020-03-31 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-90-EL-DIG-005 |  | FIRE ALARM RISER DIAGRAM FOR FIRE STATION |  |  | EL | [7 empty] | CDW | 2020-04-01 |  |  | 2020-04-22 |  |  |  | notIssue | 0%
1204-90-EL-DIG-006 |  | FIRE ALARM RISER DIAGRAM FOR GUARD HOUSE |  |  | EL | [7 empty] | CDW | 2020-04-01 |  |  | 2020-04-22 |  |  |  | notIssue | 0%
1204-90-EL-DIG-007 |  | FIRE ALARM RISER DIAGRAM FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-EL-SDG-500 |  | ELECTRICAL/INSTRUMENT INTERCONNECTION DIAGRAM, MAIN SUBSTATION |  |  | EL | [7 empty] | CDW | 2020-02-21 |  |  | 2020-04-23 |  |  |  | notIssue | 0%
1204-00-EL-SDG-501 |  | ELECTRICAL/INSTRUMENT INTERCONNECTION DIAGRAM, UTILITY SUBSTATION |  |  | EL | [7 empty] | CDW | 2020-02-21 |  |  | 2020-04-23 |  |  |  | notIssue | 0%
1204-00-EL-SDG-502 |  | MV SWITCHGEAR WIRING INTERCONNECTION DIAGRAM |  |  | EL | [7 empty] | CDW | 2020-02-21 |  |  | 2020-04-23 |  |  |  | notIssue | 0%
1204-00-EL-SDG-503 |  | INTERCONNECTION DIAGRAM 6KV SWITCHGEAR (SS01-SWB2A,B-01) |  |  | EL | [7 empty] | CDW | 2020-02-24 |  |  | 2020-04-24 |  |  |  | notIssue | 0%
1204-00-EL-SDG-504 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (MS-SWB3A,B-01) |  |  | EL | [7 empty] | CDW | 2020-02-24 |  |  | 2020-04-24 |  |  |  | notIssue | 0%
1204-00-EL-SDG-505 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (MS-SWB3A,B-02) |  |  | EL | [7 empty] | CDW | 2020-02-24 |  |  | 2020-04-24 |  |  |  | notIssue | 0%
1204-00-EL-SDG-506 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (MS-SWB3A,B-03) |  |  | EL | [7 empty] | CDW | 2020-02-24 |  |  | 2020-04-27 |  |  |  | notIssue | 0%
1204-00-EL-SDG-507 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (MS-SWB3A,B-04) |  |  | EL | [7 empty] | CDW | 2020-02-18 |  |  | 2020-04-20 |  |  |  | notIssue | 0%
1204-00-EL-SDG-508 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (MS-SWB3A,B,C-05) |  |  | EL | [7 empty] | CDW | 2020-02-18 |  |  | 2020-04-20 |  |  |  | notIssue | 0%
1204-00-EL-SDG-509 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (SS01-SWB3A,B-01) |  |  | EL | [7 empty] | CDW | 2020-02-18 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-00-EL-SDG-510 |  | INTERCONNECTION DIAGRAM 0.4KV SWITCHGEAR (SS01-SWB3A,B-02) |  |  | EL | [7 empty] | CDW | 2020-02-18 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-00-EL-SCH-509 |  | ELECTRICAL CABLE SCHEDULE |  |  | EL | [7 empty] | LIST | 2020-01-07 |  |  | 2020-05-08 |  |  |  | notIssue | 0%
1204-00-EL-SCH-512 |  | COMMUNICATION CABLE SCHEDULE |  |  | EL | [7 empty] | LIST | 2020-01-08 |  |  | 2020-05-11 |  |  |  | notIssue | 0%
1204-00-EL-SCH-5036 |  | LV SWITCHGEAR SCHEDULE (SS01-SWB3A,B-01) |  |  | EL | [7 empty] | LIST | 2020-01-09 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-00-EL-SCH-5037 |  | LV SWITCHGEAR SCHEDULE (SS01-SWB3A,B,C-02) |  |  | EL | [7 empty] | LIST | 2020-01-09 |  |  | 2020-05-12 |  |  |  | notIssue | 0%
1204-00-EL-SCH-528 |  | LOCAL CONTROL STATION SCHEDULE |  |  | EL | [7 empty] | LIST | 2020-01-10 |  |  | 2020-05-13 |  |  |  | notIssue | 0%
1204-00-EL-SCH-5091 |  | ELECTRICAL CABLES DRUM INDEX/SCHEDULE |  |  | EL | [7 empty] | LIST | 2020-01-10 |  |  | 2020-05-13 |  |  |  | notIssue | 0%
1204-00-EL-SCH-5092 |  | COMMUNICATION CABLES DRUM INDEX/SCHEDULE |  |  | EL | [7 empty] | LIST | 2020-01-10 |  |  | 2020-05-13 |  |  |  | notIssue | 0%
1204-00-EL-SCH-5093 |  | SCHEDULE FOR ELECTRICAL CABLE CUTTING |  |  | EL | [7 empty] | LIST | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-EL-DSH-509 |  | TYPICAL DATA SHEET FOR ELECTRICAL CABLES |  |  | EL | [7 empty] | DSH | 2020-02-24 |  |  | 2020-04-21 |  |  |  | InProgress | 5%
1204-00-EL-DSH-510 |  | DATA SHEET FOR UTILITY SUBSTATION DC BATTERY CHARGER (SS01) |  |  | EL | [7 empty] | DSH | 2020-02-18 |  |  | 2020-04-21 |  |  |  | InProgress | 5%
1204-00-EL-DSH-521 |  | TYPICAL DATA SHEET FOR MV INDUCTION MOTOR |  |  | EL | [7 empty] | DSH | 2020-02-18 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-00-EL-DSH-522 |  | TYPICAL DATA SHEET FOR LV INDUCTION MOTOR |  |  | EL | [7 empty] | DSH | 2020-02-18 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-00-EL-MTO-001 |  | MATERIAL TAKE OFF FOR CABLE ACCESSORIES |  |  | EL | [7 empty] | LIST | 2020-01-10 |  |  | 2020-09-16 |  |  |  | notIssue | 0%
1204-00-EL-MTO-005 |  | MATERIAL TAKE OFF FOR COMMUNICATION SYSTEMS |  |  | EL | [7 empty] | LIST | 2020-01-10 |  |  | 2020-09-16 |  |  |  | notIssue | 0%
1204-01-EL-DWG-010 |  | LIGHTING FIXTURES AND SOCKET OUTLET LAYOUT - AREA 01 |  |  | EL | [7 empty] | CDW | 2020-06-10 |  |  | 2020-06-10 |  |  |  | notIssue | 0%
1204-01-EL-DWG-030 |  | COMMUNICATION AND CCTV LAYOUT AREA 01 |  |  | EL | [7 empty] | CDW | 2020-06-10 |  |  | 2020-06-10 |  |  |  | notIssue | 0%
1204-04-EL-DWG-014 |  | LIGHTING LAYOUT FOR AREA-04 – PRIMARY REFORMER |  |  | EL | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-08-EL-DWG-001 |  | POWER LAYOUT - AREA 08 |  |  | EL | [7 empty] | CDW | 2020-10-01 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-08-EL-DWG-010 |  | LIGHTING FIXTURES AND SOCKET OUTLET LAYOUT - AREA 08 |  |  | EL | [7 empty] | CDW | 2020-10-01 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-08-EL-DWG-020 |  | EARTHING LAYOUT - AREA 08 |  |  | EL | [7 empty] | CDW | 2020-10-01 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-08-EL-DWG-030 |  | COMMUNICATION AND CCTV LAYOUT AREA 08 |  |  | EL | [7 empty] | CDW | 2020-10-01 |  |  | 2020-04-21 |  |  |  | notIssue | 0%
1204-90-EL-DWG-001 |  | MAIN SUBSTATION EQUIPMENT ARRANGEMENT LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-002 |  | MAIN SUBSTATION CABLE ROUTING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-003 |  | MAIN SUBSTATION CABLE ROUTING ARRANGEMENT OF VIEWS / SECTIONS |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-020 |  | MAIN SUBSTATION EARTHING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-050 |  | SUBSTATION SS01 EQUIPMENT ARRANGEMENT LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-051 |  | SUBSTATION SS01 CABLE ROUTING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-052 |  | SUBSTATION SS01 CABLE ROUTING ARRANGEMENT OF VIEWS / SECTIONS |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-053 |  | SUBSTATION SS01 LIGHTING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-054 |  | SUBSTATION SS01 SMALL POWER LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-055 |  | SUBSTATION SS01 EARTHING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-056 |  | SUBSTATION SS01 LIGHTNING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-057 |  | SUBSTATION SS01 COMMUNICATION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-30 |  |  | 2020-06-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-101 |  | CENTRAL CONTROL BUILDING ELECTRICAL CABLE ROUTING / CROSS SECTION DRAWINGS |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-120 |  | CENTRAL CONTROL BUILDING EARTHING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-150 |  | UTILITY CONTROL BUILDING SS01 ELECTRICAL CABLE ROUTING / CROSS SECTION DRAWINGS |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-151 |  | UTILITY CONTROL BUILDING LIGHTING LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-152 |  | UTILITY CONTROL BUILDING SMALL POWER LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-153 |  | UTILITY CONTROL BUILDING EARTHING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-154 |  | UTILITY CONTROL BUILDING LIGHTNING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-155 |  | UTILITY CONTROL BUILDING COMMUNICATION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-210 |  | LABORATORY BUILDING LIGHTING AND SOCKET OUTLET LAYOUT |  |  | EL | [7 empty] | CDW | 2021-04-30 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-220 |  | LABORATORY BUILDING EARTHING LAYOUT |  |  | EL | [7 empty] | CDW | 2021-04-30 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-221 |  | LABORATORY BUILDING LIGHTNING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2021-04-30 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-230 |  | LABORATORY BUILDING PAGING/INTERCOM/TELEPHONE LAYOUT |  |  | EL | [7 empty] | CDW | 2021-04-30 |  |  | 2021-04-30 |  |  |  | notIssue | 0%
1204-90-EL-DWG-311 |  | LIGHTING LAYOUT FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2021-04-15 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-90-EL-DWG-312 |  | SMALL POWER LAYOUT FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2021-04-15 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-90-EL-DWG-313 |  | LIGHTNING PROTECTION LAYOUT FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2021-04-15 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-90-EL-DWG-314 |  | POWER LAYOUT FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2021-04-15 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-90-EL-DWG-315 |  | COMMIUNICATION LAYOUT FOR ADMINSTRATION,RESTAURANT,CLINIC & GUARD HOUSE BUILDING |  |  | EL | [7 empty] | CDW | 2021-04-15 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-90-EL-DWG-950 |  | WAREHOUSE BACKYARD BUILDING LIGHTING AND SOCKET OUTLET LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-EL-DWG-961 |  | WAREHOUSE BACKYARD BUILDING LIGHTNING PROTECTION LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
1204-90-EL-DWG-970 |  | WAREHOUSE BACKYARD BUILDING PAGING/INTERCOM/TELEPHONE LAYOUT |  |  | EL | [7 empty] | CDW | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-EL-ACT-501VD |  | VENDOR DOCUMENT CHECKING FOR NEUTRAL GROUNDING RESISTOR |  |  | EL | [7 empty] | VDR | 2020-01-10 |  |  | 2020-04-17 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-502VD |  | VENDOR DOCUMENT CHECKING FOR MEDIUM VOLTAGE SWITCHGEARS |  |  | EL | [7 empty] | VDR | 2020-04-27 |  |  | 2021-02-04 |  |  |  | InProgress | 5%
1204-00-EL-REQ-503 |  | REQUISITION FOR LOW VOLTAGE SWITCHGEARS/MCC |  |  | EL | [7 empty] | REQ | 2020-04-23 |  |  | 2020-05-06 |  |  |  | notIssue | 0%
1204-00-EL-TBA-503 |  | TECHNICAL BID ANALYSIS FOR LOW VOLTAGE SWITCHGEARS/MCC |  |  | EL | [7 empty] | TBA | 2020-07-09 |  |  | 2020-07-29 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-503VD |  | VENDOR DOCUMENT CHECKING FOR MEDIUM VOLTAGE SWITCHGEARS |  |  | EL | [7 empty] | VDR | 2020-10-08 |  |  | 2021-06-11 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-504VD |  | VENDOR DOCUMENT CHECKING FOR POWER & DISTRIBUTION TRANSFORMER |  |  | EL | [7 empty] | VDR | 2020-04-28 |  |  | 2020-01-27 |  |  |  | InProgress | 1%
/1204-00-EL-ACT-505VD |  | VENDOR DOCUMENT CHECKING FOR POWER DISTRIBUTION CONTROL SYSTEM (PDCS) |  |  | EL | [7 empty] | VDR | 2021-04-07 |  |  | 2021-07-21 |  |  |  | notIssue | 0%
1204-00-EL-TBA-506 |  | TECHNICAL BID ANALYSIS FOR AC UPS |  |  | EL | [7 empty] | TBA | 2020-04-30 |  |  | 2020-05-21 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-506VD |  | VENDOR DOCUMENT CHECKING FOR AC UPS |  |  | EL | [7 empty] | VDR | 2020-08-27 |  |  | 114-JUL-21 |  |  |  | notIssue | 0%
1204-00-EL-TBA-507 |  | TECHNICAL BID ANALYSIS FOR BATTERY CHARGER |  |  | EL | [7 empty] | TBA | 2020-04-13 |  |  | 2020-05-04 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-507VD |  | VENDOR DOCUMENT CHECKING FOR BATTERY CHARGER |  |  | EL | [7 empty] | VDR | 2020-08-10 |  |  | 2021-06-30 |  |  |  | notIssue | 0%
1204-00-EL-REQ-508 |  | REQUISITION FOR LIGHTING & DISTRIBUTION PANEL |  |  | EL | [7 empty] | REQ | 2020-05-26 |  |  | 2020-06-08 |  |  |  | notIssue | 0%
1204-00-EL-TBA-508 |  | TECHNICAL BID ANALYSIS FOR LIGHTING & DISTRIBUTION PANEL |  |  | EL | [7 empty] | TBA | 2020-08-11 |  |  | 2020-08-31 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-508VD |  | VENDOR DOCUMENT CHECKING FOR LIGHTING & DISTRIBUTION PANEL |  |  | EL | [7 empty] | VDR | 2020-11-10 |  |  | 2021-03-19 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-509AVD |  | VENDOR DOCUMENT CHECKING FOR POWER, CONTROL AND EARTHING CABLES |  |  | EL | [7 empty] | VDR | 2020-03-27 |  |  | 2020-08-19 |  |  |  | notIssue | 0%
1204-00-EL-REQ-509B |  | REQUISITION FOR COMMUNICATION CABLES |  |  | EL | [7 empty] | REQ | 2020-04-28 |  |  | 2020-05-04 |  |  |  | notIssue | 0%
1204-00-EL-TBA-509B |  | TECHNICAL BID ANALYSIS FOR COMMUNICATION CABLES |  |  | EL | [7 empty] | TBA | 2020-06-09 |  |  | 2020-06-22 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-509BVD |  | VENDOR DOCUMENT CHECKING FOR POWER, CONTROL AND EARTHING CABLES |  |  | EL | [7 empty] | VDR | 2020-08-04 |  |  | 2020-12-17 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-510VD |  | VENDOR DOCUMENT CHECKING FOR CATHODIC PROTECTION |  |  | EL | [7 empty] | VDR | 2020-03-02 |  |  | 2020-08-13 |  |  |  | notIssue | 0%
1204-00-EL-REQ-512 |  | REQUISITION FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | REQ | 2020-06-05 |  |  | 2020-06-18 |  |  |  | notIssue | 0%
1204-00-EL-TBA-512 |  | TECHNICAL BID ANALYSIS FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | TBA | 2020-08-06 |  |  | 2020-08-27 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-512VD |  | VENDOR DOCUMENT CHECKING FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | VDR | 2020-10-23 |  |  | 2021-05-28 |  |  |  | notIssue | 0%
1204-00-EL-TBA-513 |  | TECHNICAL BID ANALYSIS FOR PUBLIC ADDRESS AND INTERCOM SYSTEM |  |  | EL | [7 empty] | TBA | 2020-08-24 |  |  | 2020-09-14 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-513VD |  | VENDOR DOCUMENT CHECKING FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | VDR | 2020-12-09 |  |  | 2021-05-24 |  |  |  | notIssue | 0%
1204-00-EL-TBA-514 |  | TECHNICAL BID ANALYSIS FOR CCTV SYSTEM |  |  | EL | [7 empty] | TBA | 2020-08-25 |  |  | 2020-09-14 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-514VD |  | VENDOR DOCUMENT CHECKING FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | VDR | 2020-11-12 |  |  | 2021-06-01 |  |  |  | notIssue | 0%
1204-00-EL-REQ-515 |  | REQUISITION FOR ELECTRICAL HEAT TRACING |  |  | EL | [7 empty] | REQ | 2020-04-17 |  |  | 2020-04-30 |  |  |  | notIssue | 0%
1204-00-EL-TBA-515 |  | TECHNICAL BID ANALYSIS FOR ELECTRICAL HEAT TRACING |  |  | EL | [7 empty] | TBA | 2020-06-22 |  |  | 2020-07-10 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-515VD |  | VENDOR DOCUMENT CHECKING FOR TELEPHONE SYSTEM |  |  | EL | [7 empty] | VDR | 2020-10-06 |  |  | 2021-05-11 |  |  |  | notIssue | 0%
1204-00-EL-TBA-516 |  | TECHNICAL BID ANALYSIS FOR RADIO SYSTEM |  |  | EL | [7 empty] | TBA | 2020-08-27 |  |  | 2020-09-16 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-516VD |  | VENDOR DOCUMENT CHECKING FOR RADIO SYSTEM |  |  | EL | [7 empty] | VDR | 2020-11-11 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-517VD |  | VENDOR DOCUMENT CHECKING FOR LV VSD PANELS |  |  | EL | [7 empty] | VDR | 2020-10-02 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-00-EL-TBA-519 |  | TECHNICAL BID ANALYSIS FOR STREET LIGHTING FIXTURES |  |  | EL | [7 empty] | TBA | 2020-07-03 |  |  | 2020-07-23 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-519VD |  | VENDOR DOCUMENT CHECKING FOR STREET LIGHTING FIXTURES |  |  | EL | [7 empty] | VDR | 2020-10-02 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-00-EL-TBA-520 |  | TECHNICAL BID ANALYSIS FOR EXPLOSION PROOF LIGHTING FIXTURES |  |  | EL | [7 empty] | TBA | 2020-03-10 |  |  | 2020-03-16 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-520VD |  | VENDOR DOCUMENT CHECKING FOR EXPLOSION PROOF LIGHTING FIXTURES |  |  | EL | [7 empty] | VDR | 2020-04-28 |  |  | 2020-09-17 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-522VD |  | VENDOR DOCUMENT CHECKING FOR MV ELECTRICAL MOTORS FOR PRIMERY REFORMER |  |  | EL | [7 empty] | VDR | 2020-04-14 |  |  | 2020-01-05 |  |  |  | notIssue | 0%
1204-00-EL-TBA-525 |  | TECHNICAL BID ANALYSIS FOR SOCKET OUTLET AND PLUGS |  |  | EL | [7 empty] | TBA | 2020-09-23 |  |  | 2020-10-13 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-525VD |  | VENDOR DOCUMENT CHECKING FOR SOCKET OUTLET AND PLUGS |  |  | EL | [7 empty] | VDR | 2020-12-21 |  |  | 2021-04-15 |  |  |  | notIssue | 0%
1204-00-EL-TBA-526 |  | TECHNICAL BID ANALYSIS FOR JUNCTION BOXES |  |  | EL | [7 empty] | TBA | 2020-06-25 |  |  | 2020-07-01 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-526VD |  | VENDOR DOCUMENT CHECKING FOR JUNCTION BOXES |  |  | EL | [7 empty] | VDR | 2020-07-21 |  |  | 2020-11-02 |  |  |  | notIssue | 0%
1204-00-EL-TBA-527 |  | TECHNICAL BID ANALYSIS FOR LIGHTING POLES |  |  | EL | [7 empty] | TBA | 2020-10-22 |  |  | 2020-10-28 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-527VD |  | VENDOR DOCUMENT CHECKING FOR LIGHTING POLES |  |  | EL | [7 empty] | VDR | 2020-11-26 |  |  | 2021-02-25 |  |  |  | notIssue | 0%
1204-00-EL-REQ-528 |  | REQUISITION FOR LOCAL CONTROL STATION |  |  | EL | [7 empty] | REQ | 2020-09-17 |  |  | 2020-09-30 |  |  |  | notIssue | 0%
1204-00-EL-TBA-528 |  | TECHNICAL BID ANALYSIS FOR LOCAL CONTROL STATION |  |  | EL | [7 empty] | TBA | 2020-11-05 |  |  | 2020-11-11 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-528VD |  | VENDOR DOCUMENT CHECKING FOR LOCAL CONTROL STATION |  |  | EL | [7 empty] | VDR | 2020-12-24 |  |  | 2020-04-06 |  |  |  | notIssue | 0%
1204-00-EL-TBA-529 |  | TECHNICAL BID ANALYSIS FOR EARTHING AND LIGHTNING MATERIAL |  |  | EL | [7 empty] | TBA | 2020-01-28 |  |  | 2020-02-03 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-529VD |  | VENDOR DOCUMENT CHECKING FOR EARTHING AND LIGHTNING MATERIAL |  |  | EL | [7 empty] | VDR | 2020-02-13 |  |  | 2020-03-27 |  |  |  | notIssue | 0%
1204-00-EL-REQ-530 |  | REQUISITION FOR CABLE GLANDS |  |  | EL | [7 empty] | REQ | 2020-05-14 |  |  | 2020-05-20 |  |  |  | notIssue | 0%
1204-00-EL-TBA-530 |  | TECHNICAL BID ANALYSIS FOR CABLE GLANDS |  |  | EL | [7 empty] | TBA | 2020-06-25 |  |  | 2020-07-01 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-530VD |  | VENDOR DOCUMENT CHECKING FOR CABLE GLANDS |  |  | EL | [7 empty] | VDR | 2020-07-23 |  |  | 2020-10-15 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-531VD |  | VENDOR DOCUMENT CHECKING FOR CABLE TRAYS AND LADDERS |  |  | EL | [7 empty] | VDR | 2020-02-25 |  |  | 2020-06-08 |  |  |  | notIssue | 0%
1204-00-EL-REQ-533 |  | REQUISITION FOR CABLE TERMINATION & ACCESSORIES |  |  | EL | [7 empty] | REQ | 2020-05-14 |  |  | 2020-05-18 |  |  |  | notIssue | 0%
1204-00-EL-TBA-533 |  | TECHNICAL BID ANALYSIS FOR CABLE TERMINATION & ACCESSORIES |  |  | EL | [7 empty] | TBA | 2020-06-23 |  |  | 2020-06-29 |  |  |  | notIssue | 0%
/1204-00-EL-ACT-533VD |  | VENDOR DOCUMENT CHECKING FOR CABLE TRAYS AND LADDERS |  |  | EL | [7 empty] | VDR | 2020-08-05 |  |  | 2020-09-29 |  |  |  | notIssue | 0%
1204-90-IN-DWG-003 |  | CONTROL ROOM CABLE ROUTING LAYOUT |  |  | IN | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-90-IN-DWG-004 |  | CONTROL ROOM EQUIPMENT LAYOUT for ASU/BOILER UNITS |  |  | IN | [7 empty] | CDW | 2020-08-30 |  |  | 2020-08-30 |  |  |  | notIssue | 0%
1204-00-IN-DWG-006 |  | ANALYZER ROOM LAYOUT |  |  | IN | [7 empty] | CDW | 2020-06-10 |  |  | 2020-06-10 |  |  |  | notIssue | 0%
1204-20-IN-DWG-025 |  | INSTRUMENT FIELD & CABLE LAYOUT (AREA 25) |  |  | IN | [7 empty] | CDW | 2020-06-22 |  |  | 2020-06-22 |  |  |  | notIssue | 0%
1204-00-IN-DWG-041 |  | INSTRUMENT FIELD & CABLE LAYOUT (AREA 41) |  |  | IN | [7 empty] | CDW | 2020-01-01 |  |  | 2020-06-25 |  |  |  | notIssue | 0%
1204-40-IN-DWG-043 |  | INSTRUMENT FIELD & CABLE LAYOUT (AREA 43) |  |  | IN | [7 empty] | CDW | 2020-01-01 |  |  | 2020-06-25 |  |  |  | notIssue | 0%
1204-10-IN-DWG-048 |  | INSTRUMENT FIELD & CABLE LAYOUT (AREA 48) |  |  | IN | [7 empty] | CDW | 2020-01-02 |  |  | 2020-06-26 |  |  |  | notIssue | 0%
1204-00-IN-LST-004 |  | INSTRUMENT CABLE LIST |  |  | IN | [7 empty] | LIST | 2019-10-02 |  |  | 2020-04-14 |  |  |  | notIssue | 0%
1204-00-IN-LST-005 |  | INSTRUMENT JUNCTION BOX NAMEPLATE LIST |  |  | IN | [7 empty] | LIST | 2019-10-02 |  |  | 2020-04-14 |  |  |  | notIssue | 0%
1204-00-IN-LST-006 |  | INSTRUMENT CABLE DRUM ALLOCATION LIST |  |  | IN | [7 empty] | LIST | 2019-10-02 |  |  | 2020-04-14 |  |  |  | notIssue | 0%
1204-00-IN-LST-007 |  | INSTRUMENT POWER CONSUMER LIST |  |  | IN | [7 empty] | LIST | 2019-10-02 |  |  | 2020-04-14 |  |  |  | notIssue | 0%
1204-00-IN-SKT-002 |  | INSTRUMENT COMPLEX LOOP SKETCH |  |  | IN | [7 empty] | CDW | 2021-02-20 |  |  | 2021-02-20 |  |  |  | notIssue | 0%
1204-00-IN-SKT-007 |  | ANALYZER PROCESS HOOK-UP'S |  |  | IN | [7 empty] | CDW | 2020-08-20 |  |  | 2020-08-20 |  |  |  | notIssue | 0%
1204-00-IN-MTO-005 |  | MATERIAL TAKE OFF FOR INSTRUMENT TUBES AND TUBE FITTING |  |  | IN | [7 empty] | LIST | 2019-12-25 |  |  | 2020-04-28 |  |  |  | notIssue | 0%
1204-00-IN-MTO-006 |  | MATERIAL TAKE OFF FOR PIPE AND PIPE FITTINGS |  |  | IN | [7 empty] | LIST | 2019-12-25 |  |  | 2020-04-28 |  |  |  | notIssue | 0%
1204-00-IN-MTO-007 |  | MATERIAL TAKE OFF FOR INSTRUMENT INSTALLATION MATERIALS |  |  | IN | [7 empty] | LIST | 2019-12-25 |  |  | 2020-04-28 |  |  |  | notIssue | 0%
1204-00-IN-MTO-008 |  | MATERIAL TAKE OFF FOR INSTRUMENT CABLE ACCESSORIES |  |  | IN | [7 empty] | LIST | 2019-12-25 |  |  | 2020-04-28 |  |  |  | notIssue | 0%
1204-00-IN-DIG-002 |  | ESD LOGIC DIAGRAM |  |  | IN | [7 empty] | EDW | 2020-02-05 |  |  | 2020-06-23 |  |  |  | notIssue | 0%
1204-00-IN-DIG-004 |  | INTERCONNECTION DIAGRAM |  |  | IN | [7 empty] | EDW | 2020-11-10 |  |  | 2020-11-10 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-601VD |  | VENDOR DOCUMENT CHECKING FOR FIELDBUS CONTROL SYSTEM |  |  | IN | [7 empty] | VDR | 2020-05-06 |  |  | 2021-03-23 |  |  |  | InProgress | 5%
1204-00-IN-TBA-602 |  | TECHNICAL BID ANALYSIS FOR EMERGENCY SHUTDOWN SYSTEM |  |  | IN | [7 empty] | TBA | 2020-06-23 | [6 empty] | complete | 100%
/1204-00-IN-ACT-602VD |  | VENDOR DOCUMENT FOR CHECKING EMERGENCY SHUTDOWN SYSTEM |  |  | IN | [7 empty] | VDR | 2020-06-23 | [6 empty] | InProgress | 5%
/1204-00-IN-ACT-603VD |  | VENDOR DOCUMENT CHECKING FOR PROCESS STREAM ANALYZERS |  |  | IN | [7 empty] | VDR | 2020-05-12 |  |  | 2020-12-07 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-604VD |  | VENDOR DOCUMENT CHECKING FOR ON / OFF VALVES |  |  | IN | [7 empty] | VDR | 2020-04-28 |  |  | 2020-03-16 |  |  |  | InProgress | 5%
/1204-00-IN-ACT-605VD |  | VENDOR DOCUMENT CHECKING FOR CONTROL VALVES |  |  | IN | [7 empty] | VDR | 2020-04-28 |  |  | 2021-05-07 |  |  |  | InProgress | 5%
/1204-00-IN-ACT-606VD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE SAFETY/RELIEF VALVES |  |  | IN | [7 empty] | VDR | 2020-02-17 |  |  | 2020-10-08 |  |  |  | notIssue | 0%
1204-00-IN-TBA-607 |  | TECHNICAL BID ANALYSIS FOR RUPTURE DISCS |  |  | IN | [7 empty] | TBA | 2020-08-11 |  |  | 2020-09-21 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-607VD |  | VENDOR DOCUMENT CHECKING FOR RUPTURE DISCS |  |  | IN | [7 empty] | VDR | 2021-01-19 |  |  | 2021-05-10 |  |  |  | notIssue | 0%
1204-00-IN-TBA-608 |  | TECHNICAL BID ANALYSIS FOR ANNUBAR FLOW ELEMENT |  |  | IN | [7 empty] | TBA | 2020-08-25 |  |  | 2020-09-14 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-608VD |  | VENDOR DOCUMENT CHECKING FOR RRUPTURE DISCS |  |  | IN | [7 empty] | VDR | 2020-12-22 |  |  | 2020-05-17 |  |  |  | notIssue | 0%
1204-00-IN-TBA-611 |  | TECHNICAL BID ANALYSIS FOR MASS FLOW METER |  |  | IN | [7 empty] | TBA | 2020-02-25 |  |  | 16-MER |  |  |  | notIssue | 0%
/1204-00-IN-ACT-611VD |  | VENDOR DOCUMENT CHECKING FOR MASS FLOW METER |  |  | IN | [7 empty] | VDR | 2020-05-26 |  |  | 2021-01-21 |  |  |  | notIssue | 0%
1204-00-IN-TBA-612 |  | TECHNICAL BID ANALYSIS FOR ORIFICE PLATES & FLANGES |  |  | IN | [7 empty] | TBA | 2020-02-25 |  |  | 2020-03-16 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-612VD |  | VENDOR DOCUMENT CHECKING FOR ORIFICE PLATES & FLANGES |  |  | IN | [7 empty] | VDR | 2020-06-23 |  |  | 2020-11-09 |  |  |  | notIssue | 0%
1204-00-IN-TBA-614 |  | TECHNICAL BID ANALYSIS FOR ROTAMETERS |  |  | IN | [7 empty] | TBA | 2020-05-19 |  |  | 2020-06-08 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-614VD |  | VENDOR DOCUMENT CHECKING FOR ROTAMETERS |  |  | IN | [7 empty] | VDR | 2020-09-15 |  |  | 2020-05-28 |  |  |  | notIssue | 0%
1204-00-IN-REQ-615 |  | REQUISITION FOR SIGHT GLASS |  |  | IN | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-IN-TBA-615 |  | TECHNICAL BID ANALYSIS FOR SIGHT GLASS |  |  | IN | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-IN-ACT-615VD |  | VENDOR DOCUMENT CHECKING FOR SIGHT GLASS |  |  | IN | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-IN-TBA-617 |  | TECHNICAL BID ANALYSIS FOR VENTURI TUBES & FLOW NOZZLES |  |  | IN | [7 empty] | TBA | 2020-02-25 |  |  | 2020-03-16 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-617VD |  | VENDOR DOCUMENT CHECKING FOR VENTURI TUBES & FLOW NOZZLES |  |  | IN | [7 empty] | VDR | 2020-05-26 |  |  | 2020-12-23 |  |  |  | notIssue | 0%
1204-00-IN-TBA-619 |  | TECHNICAL BID ANALYSIS FOR LEVEL SWITCHES |  |  | IN | [7 empty] | TBA | 2020-07-14 |  |  | 2020-08-03 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-619VD |  | VENDOR DOCUMENT CHECKING FOR LEVEL SWITCHES |  |  | IN | [7 empty] | VDR | 2020-11-10 |  |  | 2021-07-09 |  |  |  | notIssue | 0%
1204-00-IN-REQ-620 |  | REQUISITION FOR LEVEL GAUGES |  |  | IN | [7 empty] | REQ | 2020-04-28 |  |  | 2020-05-11 |  |  |  | notIssue | 0%
1204-00-IN-TBA-620 |  | TECHNICAL BID ANALYSIS FOR LEVEL GAUGES |  |  | IN | [7 empty] | TBA | 2020-07-14 |  |  | 2020-08-03 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-620VD |  | VENDOR DOCUMENT CHECKING FOR LEVEL GAUGES |  |  | IN | [7 empty] | VDR | 2020-11-10 |  |  | 2021-05-10 |  |  |  | notIssue | 0%
1204-00-IN-TBA-622 |  | TECHNICAL BID ANALYSIS FOR PRESSURE GAUGES |  |  | IN | [7 empty] | TBA | 2020-07-21 |  |  | 2020-08-10 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-622VD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE GAUGES |  |  | IN | [7 empty] | VDR | 2020-11-17 |  |  | 2020-03-30 |  |  |  | notIssue | 0%
1204-00-IN-TBA-623 |  | TECHNICAL BID ANALYSIS FOR PRESSURE SWITCHES |  |  | IN | [7 empty] | TBA | 2020-07-10 |  |  | 2020-07-30 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-623VD |  | VENDOR DOCUMENT CHECKING FOR PRESSURE SWITCHES |  |  | IN | [7 empty] | VDR | 2020-11-06 |  |  | 2020-03-25 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-624VD |  | VENDOR DOCUMENT CHECKING FOR ELECTRONIC TRANSMITTERS |  |  | IN | [7 empty] | VDR | 2020-05-12 |  |  | 2020-06-25 |  |  |  | notIssue | 0%
1204-00-IN-TBA-625 |  | TECHNICAL BID ANALYSIS FOR TEMP. ELEMENTS / TRANSMITTERS & THERMOWELLS |  |  | IN | [7 empty] | TBA | 2020-05-05 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-625VD |  | VENDOR DOCUMENT CHECKING FOR TEMP. ELEMENTS / TRANSMITTERS & THERMOWELLS |  |  | IN | [7 empty] | VDR | 2020-09-01 |  |  | 2020-07-27 |  |  |  | notIssue | 0%
1204-00-IN-TBA-626 |  | TECHNICAL BID ANALYSIS FOR MOTOR OPERATED VALVES |  |  | IN | [7 empty] | TBA | 2020-02-25 |  |  | 2020-03-16 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-626VD |  | VENDOR DOCUMENT CHECKING FOR MOTOR OPERATED VALVES |  |  | IN | [7 empty] | VDR | 2020-06-23 |  |  | 2021-05-24 |  |  |  | notIssue | 0%
1204-00-IN-TBA-627 |  | TECHNICAL BID ANALYSIS FOR INSTRUMENT JUNCTION BOXES & CABLE GLANDS |  |  | IN | [7 empty] | TBA | 2020-07-14 |  |  | 2020-07-20 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-627VD |  | VENDOR DOCUMENT CHECKING FOR INSTRUMENT JUNCTION BOXES & CABLE GLANDS |  |  | IN | [7 empty] | VDR | 2020-09-03 |  |  | 2020-12-04 |  |  |  | notIssue | 0%
1204-00-IN-TBA-628 |  | TECHNICAL BID ANALYSIS FOR INSTRUMENT CABLES |  |  | IN | [7 empty] | TBA | 2020-07-28 |  |  | 2020-08-03 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-628VD |  | VENDOR DOCUMENT CHECKING FOR INSTRUMENT CABLES |  |  | IN | [7 empty] | VDR | 2020-09-15 |  |  | 2021-01-18 |  |  |  | notIssue | 0%
1204-00-IN-REQ-630 |  | REQUISITION FOR INSTRUMENT CABLE LADDERS / TRAYS & ACCESSORIES |  |  | IN | [7 empty] | REQ | 2020-06-09 |  |  | 2020-06-15 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-630VD |  | VENDOR DOCUMENT CHECKING FOR INSTRUMENT CABLE LADDERS / TRAYS & ACCESSORIES |  |  | IN | [7 empty] | VDR | 2020-09-04 |  |  | 2020-12-25 |  |  |  | notIssue | 0%
1204-00-IN-REQ-631 |  | REQUISITION FOR TUBE AND TUBE FITTINGS |  |  | IN | [7 empty] | REQ | 2020-06-09 |  |  | 2020-06-19 |  |  |  | notIssue | 0%
1204-00-IN-TBA-631 |  | TECHNICAL BID ANALYSIS FOR TUBE AND TUBE FITTINGS |  |  | IN | [7 empty] | TBA | 2020-07-14 |  |  | 2020-07-20 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-631VD |  | VENDOR DOCUMENT CHECKING FOR TUBE AND TUBE FITTINGS |  |  | IN | [7 empty] | VDR | 2020-08-21 |  |  | 2020-11-10 |  |  |  | notIssue | 0%
1204-00-IN-REQ-632 |  | REQUISITION FOR PIPE AND PIPE FITTINGS |  |  | IN | [7 empty] | REQ | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-IN-TBA-632 |  | TECHNICAL BID ANALYSIS FOR PIPE AND PIPE FITTINGS |  |  | IN | [7 empty] | TBA | 2020-06-23 | [6 empty] | notIssue | 0%
/1204-00-IN-ACT-632VD |  | VENDOR DOCUMENT CHECKING FOR PIPE AND PIPE FITTINGS |  |  | IN | [7 empty] | VDR | 2020-06-23 | [6 empty] | notIssue | 0%
1204-00-IN-TBA-634 |  | TECHNICAL BID ANALYSIS FOR RADAR TYPE LEVEL TRANSMITTERS |  |  | IN | [7 empty] | TBA | 2020-05-05 |  |  | 2020-05-25 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-634VD |  | VENDOR DOCUMENT CHECKING FOR RADAR TYPE LEVEL TRANSMITTERS |  |  | IN | [7 empty] | VDR | 2020-09-01 |  |  | 2021-06-04 |  |  |  | notIssue | 0%
1204-00-IN-TBA-636 |  | TECHNICAL BID ANALYSIS FOR N2 BLANKETING SYSTEM |  |  | IN | [7 empty] | TBA | 2020-09-08 |  |  | 2020-09-28 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-636VD |  | VENDOR DOCUMENT CHECKING FOR N2 BLANKETING SYSTEM |  |  | IN | [7 empty] | VDR | 2021-01-05 |  |  | 2021-05-26 |  |  |  | notIssue | 0%
1204-00-IN-REQ-641 |  | REQUISITION FOR TEMPERATURE GAUGES & TESTWELLS |  |  | IN | [7 empty] | REQ | 2020-06-23 |  |  | 2020-07-06 |  |  |  | notIssue | 0%
1204-00-IN-TBA-641 |  | TECHNICAL BID ANALYSIS FOR TEMPERATURE GAUGES & TESTWELLS |  |  | IN | [7 empty] | TBA | 2020-09-08 |  |  | 2020-09-28 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-641VD |  | VENDOR DOCUMENT CHECKING FOR TEMPERATURE GAUGES & TESTWELLS |  |  | IN | [7 empty] | VDR | 2021-01-05 |  |  | 2021-05-31 |  |  |  | notIssue | 0%
1204-00-IN-TBA-648 |  | TECHNICAL BID ANALYSIS FOR ULTRASONIC LEVEL TRANSMITTERS |  |  | IN | [7 empty] | TBA | 2020-06-30 |  |  | 2020-07-20 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-648VD |  | VENDOR DOCUMENT CHECKING FOR ULTRASONIC LEVEL TRANSMITTERS |  |  | IN | [7 empty] | VDR | 2020-10-27 |  |  | 2021-06-11 |  |  |  | notIssue | 0%
1204-00-IN-REQ-654 |  | REQUISITION FOR POWER DISTRIBUTION PANEL |  |  | IN | [7 empty] | REQ | 2020-07-07 |  |  | 2020-07-20 |  |  |  | notIssue | 0%
1204-00-IN-TBA-654 |  | TECHNICAL BID ANALYSIS FOR POWER DISTRIBUTION PANEL |  |  | IN | [7 empty] | TBA | 2020-09-22 |  |  | 2020-10-12 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-654VD |  | VENDOR DOCUMENT CHECKING FOR POWER DISTRIBUTION PANEL |  |  | IN | [7 empty] | VDR | 2020-01-19 |  |  | 2021-05-20 |  |  |  | notIssue | 0%
1204-00-IN-TBA-655 |  | TECHNICAL BID ANALYSIS FOR DESUPERHEATER VALVES |  |  | IN | [7 empty] | TBA | 2020-02-25 |  |  | 2020-03-16 |  |  |  | notIssue | 0%
/1204-00-IN-ACT-655VD |  | VENDOR DOCUMENT CHECKING FOR DESUPERHEATER VALVES |  |  | IN | [7 empty] | VDR | 2020-06-23 |  |  | 16-FRB |  |  |  | notIssue | 0%